## NestedView
Aspect | Man-days | Man-hours | Actual Hours | Actual Days | Planned Start Date | Planned End Date
CRM | 48.44 | 387.5 | 183 | 22.88 | 2026-01-01 | 2026-12-31
CRM-186 - CRM Configuration Maintenance 2026 | 48.44 | 387.5 | 151 | 18.88 | 2026-01-01 | 2026-12-31
CRM-187 - CRM Configuration | 12 | 96 | 75.5 | 9.44 | 2026-02-02 | 2026-05-31
CRM-188 - CRM Handover February 2026 | 1 | 8 | 8 | 1 | 2026-02-11 | 2026-02-11
CRM-189 - CRM Handover February 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-25 | 2026-02-25
CRM-190 - CRM Handover March 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-11 | 2026-03-11
CRM-191 - CRM Handover March 2026 | 1 | 8 | 8 | 1 | 2026-03-26 | 2026-03-26
CRM-192 - CRM Handover February 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-20 | 2026-02-20
CRM-193 - CRM AMS Configuration and Testing April 2026 | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-01
CRM-194 - CRM AMS Configuration and Testing April 2026 | 1 | 8 | 8 | 1 | 2026-04-10 | 2026-04-10
CRM-195 - CRM AMS Configuration and Testing May 2026 | 1 | 8 | 8 | 1 | 2026-05-06 | 2026-05-06
CRM-196 - CRM AMS Configuration and Testing April 2026 | 1 | 8 | 8 | 1 | 2026-04-24 | 2026-04-24
CRM-197 - CRM AMS Configuration and Testing May 2026 | 1 | 8 | 8 | 1 | 2026-05-08 | 2026-05-08
CRM-198 - CRM AMS Configuration and Testing May 2026 | 1 | 8 | 0 | 0 | 2026-05-13 | 2026-05-13
CRM-199 - CRM AMS Configuration and Testing May 2026 | 2 | 16 | 0 | 0 | 2026-05-25 | 2026-05-26
DIGITALLOG | 1582.92 | 12663.37 | 7357.41 | 919.68 | 2025-09-22 | 2026-06-18
DIGITALLOG-1 - Holidays Feature / Mobile App SSO Integration | 39 | 312 | 677 | 84.62
DIGITALLOG-2 - Holiday Feature Integration | 15 | 120 | 156.5 | 19.56 | 2025-09-22 | 2025-09-26
DIGITALLOG-10 - Able to change status of holiday toggle in checklist builder while respective checklist is active. | 0 | 0 | 0.25 | 0.03
DIGITALLOG-11 - No character limit is applied on name field of custom weekend in holidays. | 0 | 0 | 0.25 | 0.03
DIGITALLOG-12 - Unable to save changes in organization holidays. | 0 | 0 | 1.5 | 0.19
DIGITALLOG-13 - Unable to select only Sundays after selecting weekends in organization holidays. | 0 | 0 | 0.5 | 0.06
DIGITALLOG-14 - Able to enter and set holidays in previous months by manually entering start date in custom weekend selection. | 0 | 0 | 1 | 0.12
DIGITALLOG-15 - Able to select previous date by manually entering after click on any specific date slot. | 0 | 0 | 0.17 | 0.02
DIGITALLOG-16 - The application does not prompt for confirmation when removing weekends, whereas it does show a confirmation and the ‘Save Changes’ button enabled as well while adding weekends. | 0 | 0 | 0.5 | 0.06
DIGITALLOG-17 - Upon trying to save changes in organization management, application is just loading to implement changes for multiple minutes. | 0 | 0 | 1.5 | 0.19
DIGITALLOG-18 - Able to submit a checklist on holiday. | 0 | 0 | 0.5 | 0.06
DIGITALLOG-19 - Schedule is creating against checklist 5 hours previous from current time when only frequency changes and it does not create in previous 5 hours when start time is changed. | 0 | 0 | 1 | 0.12
DIGITALLOG-20 - Manual Checklist is not activating | 0 | 0 | 0.33 | 0.04
DIGITALLOG-21 - Performed analysis of all time entries submitted in DL across different time zones. | 0 | 0 | 14.5 | 1.81
DIGITALLOG-9 - No option is selected by default when organizational management is selected in creating or editing a role. | 0 | 0 | 0.5 | 0.06
DIGITALLOG-3 - Mobile App SSO Integration | 10 | 80 | 88 | 11 | 2025-09-29 | 2025-10-03
DIGITALLOG-4 - SQA | 4 | 32 | 22 | 2.75 | 2025-10-06 | 2025-10-09
DIGITALLOG-5 - Production Release | 3 | 24 | 16 | 2 | 2025-10-10 | 2025-10-10
DIGITALLOG-6 - User Manual | 4 | 32 | 56 | 7 | 2025-10-06 | 2025-10-09
DIGITALLOG-7 - Confluence Migration - Web App | 3 | 24 | 44 | 5.5 | 2025-10-01 | 2025-10-03
DIGITALLOG-8 - Confluence - Mobile App | 0 | 0 | 12 | 1.5
DIGITALLOG-146 - Digital Log Read API | 69.34 | 554.75 | 364 | 45.5 | 2026-01-07 | 2026-02-20
DIGITALLOG-147 - SQA | 0 | 0 | 0 | 0
DIGITALLOG-148 - User Manual | 0 | 0 | 0 | 0
DIGITALLOG-149 - Production Release | 3 | 24 | 14 | 1.75 | 2026-02-20 | 2026-02-20
DIGITALLOG-230 - Production Deployment & Post-Deployment Verification. - AZ | 0.34 | 2.75 | 2.75 | 0.34 | 2026-02-20 | 2026-02-20
DIGITALLOG-231 - Production Deployment & Post-Deployment Verification. - NA | 1 | 8 | 8 | 1 | 2026-02-20 | 2026-02-20
DIGITALLOG-232 - Production Deployment & Post-Deployment Verification. - MA | 1 | 8 | 3.25 | 0.41 | 2026-02-20 | 2026-02-20
DIGITALLOG-68 - Development | 21 | 168 | 168 | 21 | 2026-01-14 | 2026-01-22
DIGITALLOG-100 - Get hierarchy nodes with their associated tags. - AZ | 1 | 8 | 8 | 1 | 2026-01-21 | 2026-01-21
DIGITALLOG-102 - Get tag data for multiple tags within a date range - AZ | 1 | 8 | 8 | 1 | 2026-01-22 | 2026-01-22
DIGITALLOG-103 - UI Wrapper - Get tag data for multiple tags within a date range - MA | 1 | 8 | 8 | 1 | 2026-01-22 | 2026-01-22
DIGITALLOG-105 - Get tag data for multiple tags within a date range - NA | 1 | 8 | 0 | 0
DIGITALLOG-157 - Get All Checklists API - Retrieves a complete list of checklists accessible to the authenticated user. - NA | 1 | 8 | 8 | 1 | 2026-01-14 | 2026-01-14
DIGITALLOG-158 - Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - NA | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
DIGITALLOG-160 - Get Tag Data by Date Range with Tags Filter API - Retrieves tag data for a defined date range filtered by selected tag(s). - NA | 1 | 8 | 8 | 1 | 2026-01-19 | 2026-01-19
DIGITALLOG-161 - User Authorization for Read API (Backend) - Implements backend-level authorization to control and validate user access to Read APIs. - NA | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
DIGITALLOG-162 - Get hierarchy nodes with their associated tags. - NA | 1 | 8 | 8 | 1 | 2026-01-21 | 2026-01-21
DIGITALLOG-165 - Get tag data for multiple tags within a date range - NA | 1 | 8 | 8 | 1 | 2026-01-22 | 2026-01-22
DIGITALLOG-174 - Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - NA | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
DIGITALLOG-82 - Get All Checklists API - Retrieves a complete list of checklists accessible to the authenticated user. - AZ | 1 | 8 | 8 | 1 | 2026-01-14 | 2026-01-14
DIGITALLOG-83 - Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - AZ | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
DIGITALLOG-84 - Get Tag Data by Date Range API - Returns historical tag data within a specified start and end date range. - AZ | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
DIGITALLOG-85 - Get Tag Data by Date Range with Tags Filter API - Retrieves tag data for a defined date range filtered by selected tag(s). - AZ | 1 | 8 | 8 | 1 | 2026-01-19 | 2026-01-19
DIGITALLOG-86 - User Authorization for Read API (Backend) - Implements backend-level authorization to control and validate user access to Read APIs. - AZ | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
DIGITALLOG-87 - User Authorization for Read API (Frontend) - Enforces frontend access control to expose Read API features based on user roles and permissions. - MA | 1 | 8 | 8 | 1 | 2026-01-14 | 2026-01-14
DIGITALLOG-88 - UI Wrapper - Get All Checklists – Implement frontend wrapper/service to securely call and display data from the Get All Checklists API via public domain. - MA | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
DIGITALLOG-89 - UI Wrapper - Get Tags for Multiple Checklists – Develop frontend wrapper to invoke the API and present tags for selected multiple checklists. - MA | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
DIGITALLOG-90 - UI Wrapper - Get Tag Data by Date Range – Create UI wrapper to fetch and visualize tag data based on user-selected date range. - MA | 1 | 8 | 8 | 1 | 2026-01-19 | 2026-01-19
DIGITALLOG-91 - UI Wrapper - Get Tag Data by Date Range with Tags Filter – Implement frontend wrapper to call the API with date range and tag filters and render filtered results. - MA | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
DIGITALLOG-98 - UI Wrapper - Get All Tags Hierarchy – Implement frontend wrapper/service to securely call and display data from the Get Hierarchy Tags API via public domain. - MA | 1 | 8 | 8 | 1 | 2026-01-21 | 2026-01-21
DIGITALLOG-150 - Digital Log Journal Operator | 93.34 | 746.75 | 428 | 53.5 | 2026-01-07 | 2026-02-20
DIGITALLOG-151 - SQA | 0 | 0 | 0 | 0
DIGITALLOG-152 - User Manual | 0 | 0 | 0 | 0
DIGITALLOG-153 - Production Release | 3 | 24 | 6 | 0.75 | 2026-02-20 | 2026-02-20
DIGITALLOG-227 - Production Deployment & Post-Deployment Verification. - AZ | 0.34 | 2.75 | 2.75 | 0.34 | 2026-02-20 | 2026-02-20
DIGITALLOG-229 - Production Deployment & Post-Deployment Verification. MA | 1 | 8 | 3.25 | 0.41 | 2026-02-20 | 2026-02-20
DIGITALLOG-69 - Development | 30 | 240 | 208 | 26 | 2026-01-23 | 2026-02-06
DIGITALLOG-108 - Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - AZ | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
DIGITALLOG-121 - Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - AZ | 1 | 8 | 8 | 1 | 2026-01-27 | 2026-01-27
DIGITALLOG-122 - Implement JPA entities for all journal-related tables following existing standards. - AZ | 1 | 8 | 8 | 1 | 2026-01-28 | 2026-01-28
DIGITALLOG-124 - Requirements analysis, UX flow finalization, and R&D for Journal module - MA | 1 | 8 | 8 | 1 | 2026-01-23 | 2026-01-23
DIGITALLOG-125 - Design Journal Template UI - MA | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
DIGITALLOG-126 - Integrate Journal Template backend APIs and implement dynamic template persistence - MA | 1 | 8 | 8 | 1 | 2026-01-27 | 2026-01-27
DIGITALLOG-127 - Develop Journal Builder CRUD UI using templates - MA | 1 | 8 | 8 | 1 | 2026-01-28 | 2026-01-28
DIGITALLOG-128 - Integrate Journal Builder APIs and implement user/group assignment workflows - MA | 1 | 8 | 8 | 1 | 2026-01-29 | 2026-01-29
DIGITALLOG-129 - Build Journal Collector – Assigned Journals listing and data-fetch APIs - MA | 1 | 8 | 8 | 1 | 2026-02-02 | 2026-02-02
DIGITALLOG-130 - Implement journal submission UI with validation and submit APIs (Web) - MA | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-03
DIGITALLOG-131 - Develop Review Journals UI and integrate journal detail & comment APIs - MA | 2 | 16 | 16 | 2 | 2026-02-04 | 2026-02-04
DIGITALLOG-134 - Create repository interfaces and required queries for journals, entries, and filtering. - AZ | 1 | 8 | 8 | 1 | 2026-01-29 | 2026-01-29
DIGITALLOG-139 - Implement backend logic and APIs to manage template fields. - AZ | 1 | 8 | 8 | 1 | 2026-01-30 | 2026-01-30
DIGITALLOG-140 - Implement journal creation and enforce group-based access and visibility rules. - AZ | 1 | 8 | 8 | 1 | 2026-02-02 | 2026-02-02
DIGITALLOG-141 - Develop services and APIs for submitting journal entries with dynamic field data. - AZ | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-03
DIGITALLOG-144 - Implement multi-user remarks and commenting support for journal entries. | 1 | 8 | 8 | 1 | 2026-02-04 | 2026-02-04
DIGITALLOG-156 - Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - NA | 0 | 0 | 0 | 0
DIGITALLOG-159 - Implement filtering by department, section, and fields, and perform functional validation. - AZ | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-06
DIGITALLOG-166 - Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - NA | 1 | 8 | 8 | 1 | 2026-01-23 | 2026-01-23
DIGITALLOG-167 - Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - NA | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
DIGITALLOG-169 - Implement JPA entities for all journal-related tables following existing standards. - NA | 1 | 8 | 0 | 0 | 2026-01-28 | 2026-01-28
DIGITALLOG-171 - Create repository interfaces and required queries for journals, entries, and filtering. - NA | 1 | 8 | 0 | 0 | 2026-01-29 | 2026-01-29
DIGITALLOG-172 - Implement backend logic and APIs to manage template fields. - NA | 1 | 8 | 0 | 0 | 2026-01-30 | 2026-01-30
DIGITALLOG-173 - Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - NA | 1 | 8 | 8 | 1 | 2026-01-27 | 2026-01-27
DIGITALLOG-176 - Implement journal creation and enforce group-based access and visibility rules. - NA | 1 | 8 | 8 | 1 | 2026-02-02 | 2026-02-02
DIGITALLOG-177 - Develop services and APIs for submitting journal entries with dynamic field data. - NA | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-03
DIGITALLOG-178 - Implement multi-user remarks and commenting support for journal entries. - NA | 1 | 8 | 8 | 1 | 2026-02-04 | 2026-02-04
DIGITALLOG-179 - Implement filtering by department, section, and fields, and perform functional validation. - NA | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-06
DIGITALLOG-233 - Make improvements as well as fix reported issues by team member During testing of Journals Module after completion | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
DIGITALLOG-154 - Domain Migration to Branded Domain of ODL | 39 | 312 | 236 | 29.5 | 2026-01-07 | 2026-02-20
DIGITALLOG-155 - SQA | 0 | 0 | 0 | 0
DIGITALLOG-70 - Development | 12 | 96 | 118 | 14.75 | 2026-02-09 | 2026-02-12
DIGITALLOG-163 - Tenant & Domain Mapping Preparation. - AZ | 1 | 8 | 8 | 1 | 2026-02-09 | 2026-02-09
DIGITALLOG-164 - Microservices Configuration & Routing Update. - AZ | 1 | 8 | 8 | 1 | 2026-02-10 | 2026-02-10
DIGITALLOG-170 - Tenant & Domain Mapping Preparation. - MA | 1 | 8 | 8 | 1 | 2026-02-09 | 2026-02-09
DIGITALLOG-184 - Authentication, CORS & Inter-Service Validation. - AZ | 1 | 8 | 6 | 0.75 | 2026-02-13 | 2026-02-13
DIGITALLOG-197 - Tenant & Domain Mapping Preparation. - NA | 1 | 8 | 8 | 1 | 2026-02-09 | 2026-02-09
DIGITALLOG-198 - SSL Post-Implementation Verification for octopusdtl Domain. -AZ | 2 | 16 | 16 | 2 | 2026-02-16 | 2026-02-17
DIGITALLOG-203 - Microservices Configuration & Routing Update. - NA | 1 | 8 | 8 | 1 | 2026-02-10 | 2026-02-10
DIGITALLOG-204 - Authentication, CORS & Inter-Service Validation. - NA | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
DIGITALLOG-205 - Microservices Configuration & Routing Update. - MA | 1 | 8 | 8 | 1 | 2026-02-10 | 2026-02-10
DIGITALLOG-207 - SSL Post-Implementation Verification for octopusdtl Domain. - NA | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
DIGITALLOG-210 - Authentication, CORS & Inter-Service Validation. - MA | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
DIGITALLOG-217 - SSL Post-Implementation Verification for octopusdtl Domain. - MA | 2 | 16 | 16 | 2 | 2026-02-16 | 2026-02-17
DIGITALLOG-322 - SSL Post-Implementation Verification for octopusdtl Domain - NA | 1 | 8 | 8 | 1 | 2026-02-17 | 2026-02-17
DIGITALLOG-192 - Log Chat Integration | 35 | 280 | 240 | 30 | 2026-01-07 | 2026-02-20
DIGITALLOG-193 - SQA | 0 | 0 | 0 | 0
DIGITALLOG-66 - Development | 10 | 80 | 120 | 15 | 2026-01-07 | 2026-01-13
DIGITALLOG-104 - Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 1 - AZ | 0.75 | 6 | 6 | 0.75 | 2026-01-08 | 2026-01-08
DIGITALLOG-106 - Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 2 - AZ | 1 | 8 | 8 | 1 | 2026-01-09 | 2026-01-09
DIGITALLOG-107 - Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 3 - AZ | 1 | 8 | 8 | 1 | 2026-01-12 | 2026-01-12
DIGITALLOG-175 - Requirement Understanding & Analysis - NA | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
DIGITALLOG-194 - Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application, and create and verify analytical questions to ensure accurate and reliable results. 1 | 1 | 8 | 8 | 1 | 2026-02-11 | 2026-02-11
DIGITALLOG-195 - Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application, and create and verify analytical questions to ensure accurate and reliable results. 2 | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
DIGITALLOG-209 - Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application - NA | 1 | 8 | 8 | 1 | 2026-02-11 | 2026-02-11
DIGITALLOG-211 - LogChat UI/UX Improvements & Usability Enhancement - MA | 1 | 8 | 8 | 1 | 2026-02-11 | 2026-02-11
DIGITALLOG-212 - Fix Performance & Loading Issues in Highcharts Integration | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
DIGITALLOG-92 - Requirement Understanding & Analysis - AZ | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
DIGITALLOG-93 - UI/UX Design & Architecture - MA | 1 | 8 | 8 | 1 | 2026-01-08 | 2026-01-08
DIGITALLOG-94 - Core UI Development - MA | 1 | 8 | 8 | 1 | 2026-01-09 | 2026-01-09
DIGITALLOG-95 - Integration of Log Chat Apis - MA | 1 | 8 | 8 | 1 | 2026-01-12 | 2026-01-12
DIGITALLOG-96 - Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application - MA | 1 | 8 | 8 | 1 | 2026-01-13 | 2026-01-13
DIGITALLOG-97 - Creation of read-only users to securely access client databases without modification privileges. - AZ | 0.25 | 2 | 2 | 0.25 | 2026-01-08 | 2026-01-08
DIGITALLOG-99 - Requirement Understanding & Analysis - MA | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
DIGITALLOG-196 - Technical Support (May 2026) | 22.25 | 178 | 298.4 | 37.3 | 2026-05-01 | 2026-05-31
DIGITALLOG-237 - Technical Support by Nadeem May 2026 | 17 | 136 | 66 | 8.25 | 2026-05-01 | 2026-05-31
DIGITALLOG-238 - Checklists are not triggered (day was specified as holiday) | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
DIGITALLOG-340 - Email Notifications should be sending actual domain url | 0.31 | 2.5 | 2.5 | 0.31 | 2026-03-26 | 2026-03-26
DIGITALLOG-345 - Allow Same Section Name With Different Department | 0.31 | 2.5 | 2.5 | 0.31 | 2026-03-26 | 2026-03-26
DIGITALLOG-357 - Email Notifications should be sending actual domain url & Allow Same Section Name With Different Department - NA | 0.88 | 7 | 7 | 0.88 | 2026-03-26 | 2026-03-26
DIGITALLOG-380 - Allow Same Section Name With Different Department - Hot Fix Production Release and Post Production Verification. - AZ | 0.25 | 2 | 2 | 0.25 | 2026-03-31 | 2026-03-31
DIGITALLOG-382 - Allow Same Section Name With Different Department - Hot Fix Production Release and Post Production Verification. - MA | 0.5 | 4 | 4 | 0.5 | 2026-03-31 | 2026-03-31
DIGITALLOG-427 - Investigate and resolve SSL compatibility issues affecting backward compatibility on older Android mobile app versions. - AZ | 1 | 8 | 8 | 1 | 2026-04-20 | 2026-04-20
DIGITALLOG-428 - Investigate and resolve SSL compatibility issues affecting backward compatibility on older Android mobile app versions. - MA | 1 | 8 | 8 | 1 | 2026-04-20 | 2026-04-20
DIGITALLOG-478 - Bug fixing, communication with clients/customers and meeting within team | 0 | 0 | 0 | 0
DIGITALLOG-218 - PowerPoint/Demo | 2.75 | 22 | 40 | 5
DIGITALLOG-225 - LogChat Demo | 0 | 0 | 8.5 | 1.06
DIGITALLOG-226 - LogChat Demo Internal And Bug RCAs. - AZ | 0.31 | 2.5 | 2.5 | 0.31 | 2026-02-19 | 2026-02-19
DIGITALLOG-324 - LogChat testing and evaluation - NA | 1 | 8 | 6 | 0.75 | 2026-02-19 | 2026-02-19
DIGITALLOG-317 - DL Demo | 0 | 0 | 3.5 | 0.44
DIGITALLOG-318 - Digital Log - Product/Platform Orientation Training | 0.12 | 1 | 1 | 0.12 | 2026-03-04 | 2026-03-04
DIGITALLOG-329 - Digital Log - Product/Platform Orientation Training March 11 | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-11 | 2026-03-11
DIGITALLOG-349 - Digital Log: Inhouse Training Session - 2 - AZ | 0.12 | 1 | 1 | 0.12 | 2026-03-26 | 2026-03-26
DIGITALLOG-350 - Digital Log: Inhouse Training Session - 2 - NA | 0.12 | 1 | 1 | 0.12 | 2026-03-26 | 2026-03-26
DIGITALLOG-378 - General Training/Demo | 0 | 0 | 8 | 1
DIGITALLOG-379 - Training Session ¦ Power of Mindset - AZ | 0.5 | 4 | 4 | 0.5 | 2026-03-31 | 2026-03-31
DIGITALLOG-381 - Training Session ¦ Power of Mindset - MA | 0.5 | 4 | 4 | 0.5 | 2026-03-31 | 2026-03-31
DIGITALLOG-219 - Journal for Mobile App | 159.5 | 1276 | 620 | 77.5 | 2026-02-23 | 2026-03-30
DIGITALLOG-239 - Development | 28 | 224 | 124.5 | 15.56 | 2026-02-23 | 2026-03-12
DIGITALLOG-275 - Implement Journal module bottom tabs (My Journal(s) & Review Journal(s)) with icons, navigation routing, and base screen layouts. - MA | 1 | 8 | 6.5 | 0.81 | 2026-02-24 | 2026-02-24
DIGITALLOG-276 - Integrate backend API to fetch My Journal(s) list, implement FlatList with pagination/loading states and Redux/offline state handling. - MA | 1 | 8 | 6.5 | 0.81 | 2026-02-25 | 2026-02-25
DIGITALLOG-277 - Implement Journal Detail screen, integrate API to load journal template version fields dynamically, render dynamic form components. - MA | 1 | 8 | 6.5 | 0.81 | 2026-02-26 | 2026-02-26
DIGITALLOG-278 - Implement form state management, validation logic, input handling (text, dropdowns, date, etc.), and attachment picker integration. - MA | 1 | 8 | 6.5 | 0.81 | 2026-02-27 | 2026-02-27
DIGITALLOG-279 - Implement journal submission API integration, attachment upload handling (online), success flow navigation back to My Journal(s), error handling. - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-02 | 2026-03-02
DIGITALLOG-280 - Implement offline support for My Journal(s) (SQLite schema, save draft entries, attachment queue, sync queue structure). - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-03 | 2026-03-03
DIGITALLOG-281 - Implement Review Journal(s) base UI with advanced filters (Department, Section, Users, Date Range, All Journals dropdown). - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-04 | 2026-03-04
DIGITALLOG-282 - Integrate APIs for Journals dropdown, load selected Journal versions dynamically, and render dynamic filterable template fields. - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-05 | 2026-03-05
DIGITALLOG-283 - Implement advancedFilter API integration to fetch review entries, implement default loading of all entries with filter badges (Open, Closed, Attachments). - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-06 | 2026-03-06
DIGITALLOG-284 - Implement Review Detail screen to load filled entries, integrate remarks APIs (view, add, update, delete own remarks). - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-09 | 2026-03-09
DIGITALLOG-286 - Implement Close/Reopen journal entry functionality with remarks, integrate APIs, update list state and badge counts dynamically. - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-11 | 2026-03-11
DIGITALLOG-287 - Implement full offline support for Review module (cache entries, remarks, attachments, close/reopen queue), sync mechanism, testing, performance optimization, and bug fixing. - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-12 | 2026-03-12
DIGITALLOG-288 - Design lightweight mobile-specific REST endpoints and DTOs to minimize payload size and improve performance. - AZ | 1 | 8 | 6.5 | 0.81 | 2026-02-25 | 2026-02-25
DIGITALLOG-289 - Implement APIs to fetch lightweight journals and journal entries for mobile listing screens. - AZ | 1 | 8 | 6.5 | 0.81 | 2026-02-26 | 2026-02-26
DIGITALLOG-290 - Extend the JournalEntry entity to include metadata timestamps for attachments and remarks and update business logic to auto-maintain them. -AZ | 1 | 8 | 6.5 | 0.81 | 2026-02-27 | 2026-02-27
DIGITALLOG-291 - Develop a bulk API to retrieve attachments and remarks metadata for multiple journal entries in a single request. - AZ | 1 | 8 | 6.5 | 0.81 | 2026-03-02 | 2026-03-02
DIGITALLOG-292 - Implement a delta API to return journal entries modified after a given last sync timestamp. -AZ | 1 | 8 | 6.5 | 0.81 | 2026-03-03 | 2026-03-03
DIGITALLOG-306 - Develop a bulk API to retrieve attachments and remarks metadata for multiple journal entries in a single request. - NA | 1 | 8 | 6 | 0.75 | 2026-03-02 | 2026-03-02
DIGITALLOG-321 - Implement a delta API to return journal entries modified after a given last sync timestamp. -NA | 1 | 8 | 8 | 1 | 2026-03-03 | 2026-03-03
DIGITALLOG-240 - SQA | 3 | 24 | 10 | 1.25 | 2026-03-25 | 2026-03-27
DIGITALLOG-315 - Testing By Zeeshan | 5 | 40 | 10 | 1.25 | 2026-03-20 | 2026-03-26
DIGITALLOG-241 - User Manual - Textual Guide (no screenshots) | 0.5 | 4 | 3 | 0.38 | 2026-03-25 | 2026-03-27
DIGITALLOG-242 - Production Release | 2 | 16 | 19 | 2.38 | 2026-03-30 | 2026-03-30
DIGITALLOG-361 - Production Deployment & Post-Deployment Verification. - AZ | 0.5 | 4 | 4 | 0.5 | 2026-03-30 | 2026-03-30
DIGITALLOG-363 - Production Deployment & Post-Deployment Verification. - MA | 0.5 | 4 | 4 | 0.5 | 2026-03-30 | 2026-03-30
DIGITALLOG-365 - Production Deployment & Post-Deployment Verification. - NA | 1 | 8 | 8 | 1 | 2026-03-30 | 2026-03-30
DIGITALLOG-393 - Announcement Email Compilation | 0.12 | 1 | 1 | 0.12 | 2026-03-30 | 2026-03-30
DIGITALLOG-270 - ReadApi | 12 | 96 | 79 | 9.88 | 2026-03-13 | 2026-03-24
DIGITALLOG-330 - Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - AZ | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-13 | 2026-03-13
DIGITALLOG-331 - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - AZ | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-17 | 2026-03-17
DIGITALLOG-332 - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - AZ | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-18 | 2026-03-18
DIGITALLOG-333 - Develop and test APIs for retrieving journal entry field data and remarks data by entry IDs. - AZ | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-25
DIGITALLOG-334 - UI Wrapper - Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-13 | 2026-03-13
DIGITALLOG-335 - UI Wrapper - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-16 | 2026-03-16
DIGITALLOG-336 - UI-Wrapper - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. Develop and test APIs for retrieving journal entry field data and remarks data by entry IDs. - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-18 | 2026-03-18
DIGITALLOG-353 - Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - NA | 1 | 8 | 8 | 1 | 2026-03-13 | 2026-03-13
DIGITALLOG-355 - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - NA | 2 | 16 | 16 | 2 | 2026-03-16 | 2026-03-17
DIGITALLOG-356 - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - NA | 1 | 8 | 8 | 1 | 2026-03-18 | 2026-03-18
DIGITALLOG-271 - DDS | 2.88 | 23 | 24 | 3 | 2026-02-26 | 2026-03-02
DIGITALLOG-303 - Writing DDS (Document Design Specification) for Journal Mobile App - 1 | 1 | 8 | 8 | 1 | 2026-02-25 | 2026-02-25
DIGITALLOG-304 - Writing DDS (Document Design Specification) for Journal Mobile App - 2 | 1 | 8 | 8 | 1 | 2026-02-26 | 2026-02-26
DIGITALLOG-305 - Writing and review of DDS (Document Design Specification) for Journal Mobile App - 3 | 1 | 8 | 8 | 1 | 2026-02-27 | 2026-02-27
DIGITALLOG-295 - QA Handover | 0.12 | 1 | 0.5 | 0.06 | 2026-03-24 | 2026-03-24
DIGITALLOG-297 - Bug Fixing | 7 | 56 | 50 | 6.25 | 2026-03-20 | 2026-03-27
DIGITALLOG-343 - Read API is only displaying active journals where as it should also display pending journals. | 0.25 | 2 | 2 | 0.25
DIGITALLOG-344 - Mobile App Octopusdtl Domain Switching Issue RCA - AZ | 1.88 | 15 | 15 | 1.88 | 2026-03-25 | 2026-03-27
DIGITALLOG-346 - Input field in remarks option is not displaying properly to enter text in it. | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-26 | 2026-03-26
DIGITALLOG-347 - Count on review tab of journal is not displaying when opening application. | 0.12 | 1 | 1 | 0.12 | 2026-03-27 | 2026-03-27
DIGITALLOG-348 - Open and closed journal status entries are not displaying with its previous and current values on web application. | 0.12 | 1 | 1 | 0.12 | 2026-03-27 | 2026-03-27
DIGITALLOG-358 - Mobile App Octopusdtl Domain Switching Issue | 1 | 8 | 8 | 1 | 2026-03-27 | 2026-03-27
DIGITALLOG-359 - Mobile App Octopusdtl Domain Switching Issue RCA - MA | 3 | 24 | 22.5 | 2.81 | 2026-03-24 | 2026-03-26
DIGITALLOG-220 - Holidays Management – manage the start and end time for the holiday | 62.38 | 499 | 232 | 29 | 2026-02-23 | 2026-03-30
DIGITALLOG-243 - Development | 13 | 104 | 92.5 | 11.56 | 2026-03-04 | 2026-03-12
DIGITALLOG-308 - Update database schema to add holiday start_datetime and end_datetime fields with proper indexing and non-overlapping range constraints per organization. - AZ | 1 | 8 | 5.5 | 0.69 | 2026-03-04 | 2026-03-04
DIGITALLOG-309 - Modify Holiday JPA entity, DTOs, and repository layer to support CRUD operations for holiday date-time ranges. - AZ | 1 | 8 | 6.5 | 0.81 | 2026-03-05 | 2026-03-05
DIGITALLOG-310 - Implement REST APIs to create and update holiday ranges with validation (start < end, no overlapping holidays, timezone normalization to UTC). - AZ | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-06 | 2026-03-06
DIGITALLOG-311 - Develop API to retrieve holidays with filtering by date range and organization, including pagination support. - AZ | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-09 | 2026-03-09
DIGITALLOG-312 - Enhance checklist scheduler service logic to check current execution time against configured holiday ranges and skip triggering if within range. - AZ | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-10 | 2026-03-10
DIGITALLOG-313 - Perform developer testing to validate holiday CRUD operations, overlapping range validations, and scheduler suppression behaviour during defined holiday periods. - AZ | 0.75 | 6 | 6 | 0.75 | 2026-03-11 | 2026-03-11
DIGITALLOG-314 - Update scheduler logging and monitoring to record skipped executions due to holidays, finalize Swagger documentation, and deploy changes to development for QA testing. - AZ | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-12 | 2026-03-12
DIGITALLOG-320 - Modify Holiday JPA entity, DTOs, and repository layer to support CRUD operations for holiday date-time ranges. - NA | 1 | 8 | 8 | 1 | 2026-03-05 | 2026-03-05
DIGITALLOG-325 - Implement REST APIs to create and update holiday ranges with validation (start < end, no overlapping holidays, timezone normalization to UTC). - NA | 1 | 8 | 8 | 1 | 2026-03-06 | 2026-03-06
DIGITALLOG-326 - Develop API to retrieve holidays with filtering by date range and organization - NA | 1 | 8 | 8 | 1 | 2026-03-09 | 2026-03-09
DIGITALLOG-328 - Add start and end time selection, select and unselect Saturdays as well as other improvements done for holiday module - MA | 1 | 8 | 6.5 | 0.81 | 2026-03-10 | 2026-03-10
DIGITALLOG-351 - Perform developer testing to validate holiday CRUD operations, overlapping range validations, and scheduler suppression behaviour during defined holiday periods. - NA | 1 | 8 | 8 | 1 | 2026-03-11 | 2026-03-11
DIGITALLOG-352 - Update scheduler logging and monitoring to record skipped executions due to holidays, finalize Swagger documentation, and deploy changes to development for QA testing. - NA | 1 | 8 | 8 | 1 | 2026-03-12 | 2026-03-12
DIGITALLOG-354 - Enhance checklist scheduler service logic to check current execution time against configured holiday ranges and skip triggering if within range. - NA | 0.25 | 2 | 2 | 0.25 | 2026-03-10 | 2026-03-10
DIGITALLOG-244 - SQA | 4 | 32 | 6 | 0.75 | 2026-03-25 | 2026-03-27
DIGITALLOG-341 - Testing by Zeeshan | 3 | 24 | 0 | 0 | 2026-03-25 | 2026-03-27
DIGITALLOG-245 - User Manual | 0.5 | 4 | 1 | 0.12 | 2026-03-25 | 2026-03-27
DIGITALLOG-404 - User Manual | 0.5 | 4 | 1 | 0.12 | 2026-03-25 | 2026-03-27
DIGITALLOG-246 - Production Release | 2 | 16 | 10 | 1.25 | 2026-03-30 | 2026-03-30
DIGITALLOG-362 - Production Deployment & Post-Deployment Verification. - AZ | 0.5 | 4 | 4 | 0.5 | 2026-03-30 | 2026-03-30
DIGITALLOG-364 - Production Deployment & Post-Deployment Verification. - MA | 0.5 | 4 | 4 | 0.5 | 2026-03-30 | 2026-03-30
DIGITALLOG-273 - DDS | 1 | 8 | 8 | 1 | 2026-03-04 | 2026-03-04
DIGITALLOG-360 - Creation of DDS for Holidays Management Module | 1 | 8 | 8 | 1 | 2026-03-04 | 2026-03-04
DIGITALLOG-296 - QA Handover | 0.12 | 1 | 0.5 | 0.06 | 2026-03-24 | 2026-03-24
DIGITALLOG-298 - Bug Fixing | 0.88 | 7 | 1 | 0.12 | 2026-03-17 | 2026-03-27
DIGITALLOG-342 - Able to select previous time in current day, where as it should be restricted to create a holiday in past dates or past time in current date. | 0.12 | 1 | 1 | 0.12 | 2026-03-25 | 2026-03-25
DIGITALLOG-221 - Return & Re-Approval param values and comments traceability | 70.56 | 564.51 | 359.01 | 44.88 | 2026-04-01 | 2026-04-27
DIGITALLOG-247 - Development | 18 | 144 | 94 | 11.75 | 2026-04-01 | 2026-04-08
DIGITALLOG-387 - Design database schema changes to store return and re-approval parameter values along with comments history and traceability metadata. - AZ | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-01
DIGITALLOG-388 - Implement backend entities, DTOs, and repository layer to support storing and retrieving return and re-approval data. - AZ | 1 | 8 | 8 | 1 | 2026-04-02 | 2026-04-02
DIGITALLOG-389 - Develop APIs to capture return actions with parameter values and user comments, including audit fields (user, timestamp). - AZ | 1 | 8 | 8 | 1 | 2026-04-03 | 2026-04-03
DIGITALLOG-390 - Implement APIs for re-approval workflow capturing updated parameter values and associated comments with version tracking. - AZ | 1 | 8 | 8 | 1 | 2026-04-06 | 2026-04-06
DIGITALLOG-391 - Build service-layer logic to maintain full traceability history (who, when, what changes) for return and re-approval actions. - AZ | 1 | 8 | 8 | 1 | 2026-04-07 | 2026-04-07
DIGITALLOG-392 - Perform developer testing to validate end-to-end traceability, data consistency, and audit history retrieval across return and re-approval scenarios. - AZ | 1 | 8 | 6 | 0.75 | 2026-04-08 | 2026-04-08
DIGITALLOG-395 - Analyze UI requirements for Return/Re-Approval old vs new param value traceability across web and mobile applications. - MA | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-01
DIGITALLOG-396 - Identify Return/Re-Approval fields required for change comparison in web and mobile UI. - MA | 1 | 8 | 8 | 1 | 2026-04-02 | 2026-04-02
DIGITALLOG-397 - Implement changed-field comparison logic for Return/Re-Approval params in web and mobile applications. - MA | 1 | 8 | 8 | 1 | 2026-04-03 | 2026-04-03
DIGITALLOG-398 - Build traceability UI section to display old vs new parameter values in web and mobile applications. - MA | 1 | 8 | 8 | 1 | 2026-04-06 | 2026-04-06
DIGITALLOG-399 - Render comments with corresponding Return/Re-Approval param changes in web and mobile UI. - MA | 1 | 8 | 8 | 1 | 2026-04-07 | 2026-04-07
DIGITALLOG-400 - Validate web and mobile UI rendering for Return/Re-Approval value comparison and comments traceability. - MA | 1 | 8 | 8 | 1 | 2026-04-08 | 2026-04-08
DIGITALLOG-248 - SQA | 2.5 | 20 | 54 | 6.75 | 2026-04-10 | 2026-04-20
DIGITALLOG-410 - Testing By Kamran | 5 | 40 | 46 | 5.75 | 2026-04-13 | 2026-04-29
DIGITALLOG-249 - User Manual | 1 | 8 | 0 | 0
DIGITALLOG-250 - Production Release | 1 | 8 | 8 | 1 | 2026-05-27 | 2026-04-27
DIGITALLOG-468 - Production Deployment & Post-Deployment Verification. - AZ | 0.33 | 2.67 | 2.67 | 0.33 | 2026-04-28 | 2026-04-28
DIGITALLOG-473 - Production Deployment & Post-Deployment Verification. - MA | 0.67 | 5.33 | 5.34 | 0.67 | 2026-04-28 | 2026-04-28
DIGITALLOG-366 - DDS | 1 | 8 | 0 | 0 | 2026-04-02 | 2026-04-02
DIGITALLOG-367 - QA Handover | 0.12 | 1 | 1.5 | 0.19 | 2026-04-09 | 2026-04-09
DIGITALLOG-409 - Handover to QA - AZ | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-09 | 2026-04-09
DIGITALLOG-414 - Handover session Digital Log | 0.12 | 1 | 0.5 | 0.06
DIGITALLOG-424 - Handover to QA - MA | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-09 | 2026-04-09
DIGITALLOG-375 - URS | 1 | 8 | 0 | 0 | 2026-04-01 | 2026-04-01
DIGITALLOG-376 - Bug Fixing | 0.38 | 3 | 22 | 2.75
DIGITALLOG-432 - Checklist Name is appearing instead of Approver Name | 0 | 0 | 2 | 0.25
DIGITALLOG-433 - HEADER NOT RESPONSIVE | 0.19 | 1.5 | 1.5 | 0.19 | 2026-04-23 | 2026-04-23
DIGITALLOG-434 - Refresh button is not loading latest data into the list | 0.25 | 2 | 2 | 0.25 | 2026-04-24 | 2026-04-24
DIGITALLOG-435 - Permission issue for my user as i installed the new version of the mobile app | 0.33 | 2.67 | 2.67 | 0.33 | 2026-04-27 | 2026-04-27
DIGITALLOG-438 - Newly created checklists do not appear at the top, and there is no filter available to sort by creation time. | 0.25 | 2 | 2 | 0.25 | 2026-04-24 | 2026-04-24
DIGITALLOG-439 - Time-based scheduled checklist activation fails on the first attempt. However, after changing the checklist type from "Time Based" to "Scheduled", the activation succeeds, including validation through developer testing | 0.5 | 4 | 4 | 0.5 | 2026-04-24 | 2026-04-24
DIGITALLOG-440 - Time-based checklist is not triggering according to the 24-hour format, even after multiple screen refresh attempts. | 0 | 0 | 0.5 | 0.06
DIGITALLOG-441 - E-Signature field should be Mandatory on web and mobile | 0.33 | 2.67 | 2.67 | 0.33
DIGITALLOG-442 - Checklist gets activated when Start Time and End Time are identical (zero-duration window not validated) | 0.33 | 2.67 | 2.67 | 0.33 | 2026-04-27 | 2026-04-27
DIGITALLOG-413 - Change Texts on the Timestamp Labels and correct the Signature label Alignment | 0.12 | 1 | 1 | 0.12 | 2026-04-15 | 2026-04-15
DIGITALLOG-222 - User Specified Time based Checklist Scheduling | 43.3 | 346.4 | 210 | 26.25 | 2026-04-01 | 2026-04-27
DIGITALLOG-251 - Development | 8.62 | 69 | 72.5 | 9.06 | 2026-04-15 | 2026-04-20
DIGITALLOG-416 - Design database schema and backend models to support user-defined checklist scheduling with configurable execution times and frequency - AZ | 1 | 8 | 8 | 1 | 2026-04-15 | 2026-04-15
DIGITALLOG-417 - Implement APIs to create and update checklist schedules with user-specified time, timezone handling, and validation rules - AZ | 1 | 8 | 8 | 1 | 2026-04-16 | 2026-04-16
DIGITALLOG-418 - Develop API to retrieve checklist schedules with filtering and organization-level configuration support - AZ | 1 | 8 | 8 | 1 | 2026-04-17 | 2026-04-17
DIGITALLOG-419 - Enhance scheduler service to trigger checklists based on user-defined times and integrate with existing scheduling framework - AZ | 1 | 8 | 8 | 1 | 2026-04-21 | 2026-04-21
DIGITALLOG-420 - Perform developer testing to validate scheduling accuracy, timezone consistency, and edge cases (missed triggers, overlaps, holiday conflicts) - AZ | 1 | 8 | 13.5 | 1.69 | 2026-04-22 | 2026-04-22
DIGITALLOG-429 - Refactor checklist builder UI by replacing Scheduled/Non-Scheduled checkboxes with a dropdown (Scheduled, Non-Scheduled, Time-based) and default to Non-Scheduled. - MA | 1 | 8 | 7 | 0.88 | 2026-04-15 | 2026-04-15
DIGITALLOG-430 - Implement dynamic UI behavior to show/hide scheduling controls based on selected dropdown option, including new time-based inputs. - MA | 1 | 8 | 8 | 1 | 2026-04-16 | 2026-04-16
DIGITALLOG-431 - Update scheduling API payload to support the new Time-based option and ensure proper data handling for all scheduling types. - MA | 1 | 8 | 8 | 1 | 2026-04-17 | 2026-04-17
DIGITALLOG-252 - SQA | 2.5 | 20 | 0 | 0 | 2026-04-21 | 2026-04-23
DIGITALLOG-253 - User manual | 1 | 8 | 0 | 0
DIGITALLOG-254 - Production release | 1 | 8 | 8 | 1 | 2026-04-27 | 2026-04-27
DIGITALLOG-469 - Production Deployment & Post-Deployment Verification. - AZ | 0.33 | 2.67 | 2.67 | 0.33 | 2026-04-28 | 2026-04-28
DIGITALLOG-472 - Production Deployment & Post-Deployment Verification. - MA | 0.67 | 5.33 | 5.34 | 0.67 | 2026-04-28 | 2026-04-28
DIGITALLOG-368 - QA Handover | 0.12 | 1 | 1 | 0.12 | 2026-04-23 | 2026-04-23
DIGITALLOG-437 - Handover to QA - AZ | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-23 | 2026-04-23
DIGITALLOG-474 - Handover to QA - MA | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-23 | 2026-04-23
DIGITALLOG-369 - DDS | 1.5 | 12 | 12 | 1.5 | 2026-04-15 | 2026-04-16
DIGITALLOG-370 - Bug Fixing | 0.38 | 3 | 13.5 | 1.69 | 2026-04-24 | 2026-04-27
DIGITALLOG-466 - Update checklist scheduling logic to ensure triggers occur only after the configured checklist start time, including validation and developer testing for edge cases - AZ | 1 | 8 | 7.5 | 0.94 | 2026-04-27 | 2026-04-27
DIGITALLOG-467 - Fix checklist scheduling logic to preserve original start time and prevent schedule shifts during checklist deactivation and reactivation, including validation through developer testing - AZ | 0.75 | 6 | 6 | 0.75 | 2026-04-24 | 2026-04-24
DIGITALLOG-383 - URS | 1 | 8 | 0 | 0 | 2026-04-13 | 2026-04-13
DIGITALLOG-223 - Digital Signatures (Like DocuSign idea) | 28.06 | 224.5 | 146 | 18.25 | 2026-04-01 | 2026-04-27
DIGITALLOG-255 - Development | 5.25 | 42 | 52.5 | 6.56 | 2026-04-09 | 2026-04-13
DIGITALLOG-405 - Design and implement backend data model and APIs to support digital signature requests, signer details, and document status tracking. | 1 | 8 | 8 | 1 | 2026-04-09 | 2026-04-10
DIGITALLOG-406 - Update existing submit and approver endpoints to incorporate digital signature validation, capture signer details, and persist signature metadata with audit trail. | 1 | 8 | 8 | 1 | 2026-04-10 | 2026-04-13
DIGITALLOG-407 - Perform developer testing and integrate digital signature workflow with checklist modules ensuring security, validation, and end-to-end traceability. | 1 | 8 | 8 | 1 | 2026-04-13 | 2026-04-13
DIGITALLOG-421 - Implement e-signature enablement on Web including checklist builder toggle, list filters/badges, submission & review modals with signature capture, and signature display via API. - MA | 1 | 8 | 9.5 | 1.19 | 2026-04-09 | 2026-04-09
DIGITALLOG-422 - Implement e-signature functionality on Mobile (React Native) including checklist filters/badges, submission & review modals with signature capture, and signature display via API. - MA | 1 | 8 | 11 | 1.38 | 2026-04-10 | 2026-04-10
DIGITALLOG-423 - Integrate e-signature APIs across Web and Mobile, ensuring payload handling, signature retrieval, and visualization in checklist and data modules. - MA | 1 | 8 | 8 | 1 | 2026-04-13 | 2026-04-13
DIGITALLOG-256 - SQA | 1.5 | 12 | 0 | 0 | 2026-04-14 | 2026-04-16
DIGITALLOG-257 - User Manual | 0.5 | 4 | 0 | 0
DIGITALLOG-258 - Production Release | 1 | 8 | 8 | 1 | 2026-04-27 | 2026-04-27
DIGITALLOG-470 - Production Deployment & Post-Deployment Verification. - AZ | 0.33 | 2.67 | 2.67 | 0.33 | 2026-04-28 | 2026-04-28
DIGITALLOG-471 - Production Deployment & Post-Deployment Verification. - MA | 0.67 | 5.33 | 5.34 | 0.67 | 2026-04-28 | 2026-04-28
DIGITALLOG-371 - DDS | 1 | 8 | 8 | 1 | 2026-04-09 | 2026-04-10
DIGITALLOG-372 - Bug Fixing | 0.62 | 5 | 0 | 0
DIGITALLOG-373 - QA Handover | 0.12 | 1 | 0.5 | 0.06 | 2026-04-14 | 2026-04-14
DIGITALLOG-408 - Handover to QA - AZ | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-14 | 2026-04-14
DIGITALLOG-377 - URS | 0.5 | 4 | 4 | 0.5 | 2026-04-09 | 2026-04-09
DIGITALLOG-234 - Default Reports Generation Via LogChat | 46.88 | 375 | 336 | 42 | 2026-02-23 | 2026-03-30
DIGITALLOG-235 - RND | 1 | 8 | 35.5 | 4.44 | 2026-02-23 | 2026-03-30
DIGITALLOG-236 - Research & Validation: Confirm Default Reports generation capability through LogChat 1/3 - NA | 1 | 8 | 8 | 1 | 2026-02-23 | 2026-02-23
DIGITALLOG-301 - Research & Validation: Confirm Default Reports generation capability through LogChat 2/3 - NA | 1 | 8 | 8 | 1 | 2026-02-24 | 2026-02-24
DIGITALLOG-339 - Research: Testing Omnichat with Postgress SQL | 3 | 24 | 19.5 | 2.44 | 2026-03-10 | 2026-03-12
DIGITALLOG-272 - Development | 10 | 80 | 132.5 | 16.56 | 2026-02-25 | 2026-03-31
DIGITALLOG-299 - Integrating Inactive logs and Latest log Report | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-25 | 2026-02-25
DIGITALLOG-300 - Integrating capability to fetch tags based on Units and field type | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-26 | 2026-02-26
DIGITALLOG-307 - Integrating capability to fetch the logs and tags/items with remarks | 1.62 | 13 | 13 | 1.62 | 2026-02-27 | 2026-03-02
DIGITALLOG-316 - Working XY Plot and multi-line graph in chat | 1.62 | 13 | 13 | 1.62 | 2026-03-03 | 2026-03-04
DIGITALLOG-327 - Upcoming checklist Activities report | 3 | 24 | 19.5 | 2.44 | 2026-03-05 | 2026-03-09
DIGITALLOG-337 - Testing and Retraining of LLM | 3 | 24 | 19.5 | 2.44 | 2026-03-16 | 2026-03-18
DIGITALLOG-338 - Integrating comparison of tags reports | 1 | 8 | 6.5 | 0.81 | 2026-03-13 | 2026-03-13
DIGITALLOG-401 - Update the pie chart logic in logchat | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-24
DIGITALLOG-402 - Adding statistical analysis in logchat | 3 | 24 | 24 | 3 | 2026-03-25 | 2026-03-27
DIGITALLOG-403 - Creating dataset (checklists) and testing on production | 2 | 16 | 16 | 2 | 2026-03-30 | 2026-03-31
DIGITALLOG-259 - LogChat - User Help, Journals | 30.3 | 242.4 | 80 | 10 | 2026-04-01 | 2026-04-27
DIGITALLOG-260 - Development | 5.6 | 44.8 | 40 | 5 | 2026-04-01 | 2026-04-16
DIGITALLOG-425 - Code to fetch the Confluence File and store in vector store | 3 | 24 | 24 | 3 | 2026-04-01 | 2026-04-03
DIGITALLOG-426 - Integrate User manual/confluence file vector store in the Log chat | 2 | 16 | 16 | 2 | 2026-04-06 | 2026-04-07
DIGITALLOG-261 - SQA | 3 | 24 | 0 | 0 | 2026-04-17 | 2026-04-21
DIGITALLOG-262 - User Manual | 1 | 8 | 0 | 0
DIGITALLOG-263 - Production Release | 1 | 8 | 0 | 0 | 2026-04-27 | 2026-04-27
DIGITALLOG-374 - QA Handover | 0.12 | 1 | 0 | 0 | 2026-04-17 | 2026-04-17
DIGITALLOG-384 - Bug Fixing | 1.88 | 15 | 0 | 0
DIGITALLOG-385 - URS | 0.6 | 4.8 | 0 | 0 | 2026-04-09 | 2026-04-09
DIGITALLOG-386 - DDS | 1.1 | 8.8 | 0 | 0 | 2026-04-10 | 2026-04-13
DIGITALLOG-27 - Dashboard, Data & Mobile Improvements | 90 | 720 | 992 | 124
DIGITALLOG-25 - Ensure consistent UTC time usage across the application & checklist scheduling creation according org time zone | 15 | 120 | 84 | 10.5 | 2025-10-13 | 2025-10-17
DIGITALLOG-26 - Consolidated View implementation in Mobile App + Checklist Search View + Filters +Sorting | 15 | 120 | 68 | 8.5 | 2025-10-13 | 2025-10-17
DIGITALLOG-46 - Correct list of checklist are not displaying when they are returned in bulk through mobile app. | 0 | 0 | 0 | 0
DIGITALLOG-28 - Improved Legends in Data Visualization | 9 | 72 | 88 | 11 | 2025-10-20 | 2025-10-22
DIGITALLOG-29 - Alert not deleting | 6 | 48 | 48 | 6 | 2025-10-23 | 2025-10-24
DIGITALLOG-30 - Tables on Dashboard | 6 | 48 | 32 | 4 | 2025-10-27 | 2025-10-28
DIGITALLOG-31 - Template Duplication (clone) Feature & Checklist Duplicate (clone) Feature | 15 | 120 | 136 | 17 | 2025-10-27 | 2025-10-31
DIGITALLOG-32 - SQA | 20 | 160 | 24 | 3 | 2025-11-03 | 2025-11-07
DIGITALLOG-47 - Date format parameter value is displaying in data visualizer with some random long integer value. | 0 | 0 | 0 | 0
DIGITALLOG-34 - Production Release | 4 | 32 | 16 | 2 | 2025-11-10 | 2025-11-10
DIGITALLOG-35 - Checklist Stats Enhancements + Dashboard User Activity Logs | 125.8 | 1006.4 | 1354 | 169.25
DIGITALLOG-36 - Checklist Stats Optimization and enhancement | 21 | 168 | 136 | 17 | 2025-11-11 | 2025-11-19
DIGITALLOG-37 - Custom Date Range in Checklist Stats | 6 | 48 | 40 | 5 | 2025-11-20 | 2025-11-21
DIGITALLOG-38 - SQA | 15 | 120 | 112 | 14 | 2025-12-22 | 2026-01-02
DIGITALLOG-49 - Irrelevant information is displaying in tabs of count present on starting of activity stats page. | 0 | 0 | 0.5 | 0.06
DIGITALLOG-50 - Backend programming language is displaying against update activity of template structure. | 0 | 0 | 2 | 0.25
DIGITALLOG-51 - Format of date and time in any activity update is not correct. | 0 | 0 | 1 | 0.12
DIGITALLOG-52 - Module name that is created, updated or deleted should display first and then its entity should display in brackets while viewing its details. | 0 | 0 | 0.5 | 0.06
DIGITALLOG-53 - Department name is not displaying correct after creating a section. | 0 | 0 | 0 | 0
DIGITALLOG-54 - Checklist update activity is automatically triggered where as only group is updated. | 0 | 0 | 0 | 0
DIGITALLOG-55 - Dept and section for data visualization checkbox is not selected when clicking on select all option while creating or updating role. | 0 | 0 | 1 | 0.12
DIGITALLOG-56 - Role ID and other details are displaying while viewing user create activity. | 0 | 0 | 0 | 0
DIGITALLOG-57 - Holiday declared in organizational management is not displaying with its date in activity stats screen. | 0 | 0 | 0 | 0
DIGITALLOG-58 - Activity detail done in hierarchy builder is not displaying where as its count is displaying. | 0 | 0 | 1 | 0.12
DIGITALLOG-59 - Activity of parameter creation in asset builder is displaying as creating it in template. | 0 | 0 | 0 | 0
DIGITALLOG-60 - Required toggle activate/deactivate activity is with only type change description where as input type is not changed. | 0 | 0 | 1 | 0.12
DIGITALLOG-61 - Location or asset is not displaying for selection again while configuring checklist after it is removed one time. | 0 | 0 | 0 | 0
DIGITALLOG-62 - Start and end date as well as frequency changings are not displaying in checklist details on activity stats screen. | 0 | 0 | 1 | 0.12
DIGITALLOG-39 - Production Release | 6 | 48 | 48 | 6 | 2026-01-05 | 2026-01-06
DIGITALLOG-41 - User Activity Logs + Dashboards | 60 | 480 | 341 | 42.62 | 2025-11-24 | 2025-12-19
DIGITALLOG-48 - User Manual | 2 | 16 | 0 | 0 | 2025-12-22 | 2026-01-02
DIGITALLOG-443 - Enhance User Access Rights at granular level of Create, Read, Update, Delete like OmniConnect | 34 | 272 | 0 | 0
DIGITALLOG-444 - Email text formatting | 7.2 | 57.6 | 0 | 0
DIGITALLOG-445 - Notifications (desktop) at due, overdue checklist(s) | 27.8 | 222.4 | 0 | 0
DIGITALLOG-446 - Mobile App iOS | 5.8 | 46.4 | 0 | 0
DIGITALLOG-447 - DL Default Reports | 43.45 | 347.6 | 0 | 0 | 2026-05-04 | 2026-06-18
DIGITALLOG-500 - URS | 1 | 8 | 0 | 0
DIGITALLOG-501 - DDS | 1.9 | 15.2 | 0 | 0
DIGITALLOG-502 - Development | 8 | 64 | 0 | 0 | 2026-05-18 | 2026-05-21
DIGITALLOG-650 - Backend | 4 | 32 | 0 | 0 | 2026-05-18 | 2026-05-21
DIGITALLOG-503 - SQA | 3 | 24 | 0 | 0
DIGITALLOG-504 - Bug Fixing | 2.9 | 23.2 | 0 | 0 | 2026-05-25 | 2026-05-26
DIGITALLOG-654 - Backend | 1.45 | 11.6 | 0 | 0 | 2026-05-25 | 2026-05-29
DIGITALLOG-505 - QA Handover | 0.5 | 4 | 0 | 0 | 2026-05-22 | 2026-05-22
DIGITALLOG-506 - Production Release | 1 | 8 | 0 | 0 | 2026-06-18 | 2026-06-18
DIGITALLOG-507 - User Manual | 1 | 8 | 0 | 0
DIGITALLOG-448 - Journals for Mobile iOS | 12.5 | 100 | 0 | 0
DIGITALLOG-449 - Reports list is not available/viewable in tablet portrait mode | 2.9 | 23.2 | 0 | 0
DIGITALLOG-450 - User Remarks Traceability | 6.14 | 49.16 | 0 | 0 | 2026-05-04 | 2026-06-18
DIGITALLOG-658 - Development | 4.1 | 32.78 | 0 | 0 | 2026-06-01 | 2026-06-02
DIGITALLOG-668 - Backend | 2.05 | 16.38 | 0 | 0 | 2026-06-01 | 2026-06-02
DIGITALLOG-451 - DL Analytics (Dependent upon client need & Data) | 17.3 | 138.4 | 0 | 0
DIGITALLOG-452 - Calculated tags | 24 | 192 | 0 | 0
DIGITALLOG-453 - LogChat - Data Analysis | 32 | 256 | 0 | 0 | 2026-05-04 | 2026-06-18
DIGITALLOG-516 - URS | 0.8 | 6.4 | 0 | 0
DIGITALLOG-517 - DDS | 1.6 | 12.8 | 0 | 0
DIGITALLOG-518 - Development | 6.6 | 52.8 | 0 | 0 | 2026-06-01 | 2026-06-09
DIGITALLOG-519 - SQA | 2.5 | 20 | 0 | 0
DIGITALLOG-520 - QA Handover | 0.5 | 4 | 0 | 0 | 2026-06-10 | 2026-06-10
DIGITALLOG-521 - Production Release | 1 | 8 | 0 | 0 | 2026-06-18 | 2026-06-18
DIGITALLOG-522 - Bug Fixing | 2.4 | 19.2 | 0 | 0 | 2026-06-11 | 2026-06-12
DIGITALLOG-523 - User Manual | 0.8 | 6.4 | 0 | 0
DIGITALLOG-454 - Attachments at remarks from approver1, approver2 | 9.6 | 76.8 | 0 | 0
DIGITALLOG-455 - DL Trial on WebSite | 30.2 | 241.6 | 0 | 0
DIGITALLOG-456 - Delete option to admin (to delete unclaimed checklists) Data Collector -> Inbox | 6.2 | 49.6 | 0 | 0
DIGITALLOG-457 - Triggering of checklist instance on some event (we have scheduled checklist feature & it is triggered on given frequency) | 15.8 | 126.4 | 0 | 0
DIGITALLOG-458 - Attachment pic with each Checklist (, audio, video, pdf, etc) | 8.1 | 64.8 | 0 | 0
DIGITALLOG-459 - Validation of Values to be within defined threshold | 7.2 | 57.6 | 0 | 0
DIGITALLOG-460 - Automated Triggered O&M Actions | 13.9 | 111.2 | 0 | 0
DIGITALLOG-461 - Import & export of assets hierarchy | 18.2 | 145.6 | 0 | 0
DIGITALLOG-462 - Bulk creation of parameters through importing CSV file(s) (User can develop a template of parameters and then can use for multiple areas/assets) | 15.8 | 126.4 | 0 | 0
DIGITALLOG-463 - Import & export of checklists | 18.2 | 145.6 | 0 | 0
DIGITALLOG-464 - Request for Digital Log Usage Dashboard Report | 24.4 | 195.2 | 0 | 0
DIGITALLOG-475 - Enhanced search functionality with dropdown-based filtering across the application | 16.2 | 129.6 | 0 | 0 | 2026-05-04 | 2026-06-18
DIGITALLOG-491 - Development | 2.8 | 22.4 | 0 | 0 | 2026-05-11 | 2026-05-13
DIGITALLOG-492 - URS | 0.4 | 3.2 | 0 | 0
DIGITALLOG-493 - DDS | 0.8 | 6.4 | 0 | 0
DIGITALLOG-494 - SQA | 1 | 8 | 0 | 0
DIGITALLOG-495 - QA Handover | 0.5 | 4 | 0 | 0 | 2026-05-14 | 2026-05-14
DIGITALLOG-496 - Production Release | 1 | 8 | 0 | 0 | 2026-06-18 | 2026-06-18
DIGITALLOG-497 - Bug Fixing | 1.2 | 9.6 | 0 | 0 | 2026-05-15 | 2026-05-15
DIGITALLOG-498 - User Manual | 0.4 | 3.2 | 0 | 0
DIGITALLOG-476 - Image integration in checklist PDF export for Review and Data Visualization screens. | 18 | 144 | 64 | 8 | 2026-05-04 | 2026-06-18
DIGITALLOG-484 - Development | 2.8 | 22.4 | 22.4 | 2.8 | 2026-05-04 | 2026-05-06
DIGITALLOG-524 - Image integration into PDF Export in Data Visualization Module - MA | 1 | 8 | 8 | 1 | 2026-05-04 | 2026-05-04
DIGITALLOG-525 - Image integration into email sent export pdf in Data Visualization Module - MA | 1 | 8 | 8 | 1 | 2026-05-05 | 2026-05-05
DIGITALLOG-526 - Image integration into email sent export pdf in Review Checklist Module - MA | 0.8 | 6.4 | 6.4 | 0.8 | 2026-05-06 | 2026-05-06
DIGITALLOG-485 - URS | 0.4 | 3.2 | 3.2 | 0.4 | 2026-05-04 | 2026-05-04
DIGITALLOG-486 - DDS | 0.8 | 6.4 | 6.4 | 0.8 | 2026-05-05 | 2026-05-05
DIGITALLOG-487 - SQA | 0 | 0 | 0 | 0
DIGITALLOG-488 - QA Handover | 0.5 | 4 | 0 | 0 | 2026-05-07 | 2026-05-07
DIGITALLOG-489 - Production Release | 1 | 8 | 0 | 0 | 2026-06-18 | 2026-06-18
DIGITALLOG-490 - Bug Fixing | 1.2 | 9.6 | 0 | 0 | 2026-05-08 | 2026-05-08
DIGITALLOG-499 - User Manual | 0.4 | 3.2 | 0 | 0
DIGITALLOG-477 - Configurable email notifications for checklist statuses (assigned, approved, returned, rejected, etc.). | 40.5 | 324 | 0 | 0 | 2026-05-04 | 2026-06-18
DIGITALLOG-508 - URS | 0.9 | 7.2 | 0 | 0
DIGITALLOG-509 - DDS | 1.8 | 14.4 | 0 | 0
DIGITALLOG-510 - Development | 7.3 | 58.4 | 0 | 0 | 2026-06-05 | 2026-06-10
DIGITALLOG-672 - Backend | 3.65 | 29.2 | 0 | 0 | 2026-06-05 | 2026-06-10
DIGITALLOG-511 - SQA | 2.7 | 21.6 | 0 | 0
DIGITALLOG-512 - QA Handover | 0.5 | 4 | 0 | 0 | 2026-06-11 | 2026-06-11
DIGITALLOG-513 - User Manual | 0.9 | 7.2 | 0 | 0
DIGITALLOG-514 - Production Release | 1 | 8 | 0 | 0 | 2026-06-18 | 2026-06-18
DIGITALLOG-515 - Bug Fixing | 2.7 | 21.6 | 0 | 0 | 2026-06-12 | 2026-06-15
DIGITALLOG-674 - Backend | 1.35 | 10.8 | 0 | 0 | 2026-06-12 | 2026-06-15
DIGITALLOG-479 - LogChat - Knowledge Transfer Sessions (May 2026) | 22 | 176 | 24 | 3 | 2026-05-04 | 2026-05-08
DIGITALLOG-480 - KT Session - Ibrahim | 0 | 0 | 0 | 0
DIGITALLOG-481 - KT Session - Yousaf | 0 | 0 | 0 | 0
DIGITALLOG-482 - KT Session - Hassan Wattoo | 2 | 16 | 12 | 1.5 | 2026-05-04 | 2026-05-08
DIGITALLOG-483 - KT Session - Hamza | 0 | 0 | 0 | 0
DIGITALLOG-65 - Digital Log Enhancements & Integration | 136.06 | 1088.5 | 657 | 82.12 | 2026-01-07 | 2026-02-20
DIGITALLOG-109 - URS | 0 | 0 | 0 | 0
DIGITALLOG-110 - DDS | 0 | 0 | 0 | 0
DIGITALLOG-113 - DEV: Log Chat Development | 32 | 256 | 201 | 25.12 | 2026-01-07 | 2026-02-20
DIGITALLOG-114 - SQL Database Development for Log Chat | 3 | 24 | 40 | 5 | 2026-01-07 | 2026-01-09
DIGITALLOG-115 - Creating API for fetching all chats for each thread | 2 | 16 | 16 | 2 | 2026-01-12 | 2026-01-14
DIGITALLOG-116 - Creating API for fetching all threads of the specific user | 2 | 16 | 12 | 1.5 | 2026-01-13 | 2026-01-15
DIGITALLOG-117 - Creating API for Deleting chat thread | 0.5 | 4 | 4 | 0.5 | 2026-03-13 | 2026-03-13
DIGITALLOG-118 - adjusting timestamps in LLM tools to UTC time according to organization timezone dynamically from DB | 4 | 32 | 32 | 4 | 2026-01-14 | 2026-01-16
DIGITALLOG-136 - Integerating confluence documentation in log chat | 4 | 32 | 32 | 4 | 2026-01-28 | 2026-02-03
DIGITALLOG-137 - updating SQL and code for multi tenant database configuration | 1 | 8 | 8 | 1 | 2026-01-29 | 2026-01-29
DIGITALLOG-168 - Development for new tool call to add template details in chatbot | 3 | 24 | 24 | 3 | 2026-02-04 | 2026-02-09
DIGITALLOG-214 - Separating the data analysis and user manual part from the chatbot | 1 | 8 | 4 | 0.5 | 2026-02-17 | 2026-02-17
DIGITALLOG-215 - Preparing Demo questions and testing log chat | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
DIGITALLOG-269 - Retraining of LLM to resolve issues related to logchat | 3 | 24 | 21 | 2.62 | 2026-02-18 | 2026-02-20
DIGITALLOG-67 - DEV: Default Reports (Research & Definition) | 3 | 24 | 16 | 2 | 2026-01-09 | 2026-01-13
DIGITALLOG-71 - SQA | 20 | 160 | 103.5 | 12.94 | 2026-02-13 | 2026-02-19
DIGITALLOG-119 - SQA-Log Chat | 3 | 24 | 24 | 3 | 2026-01-22 | 2026-02-19
DIGITALLOG-120 - SQA-Read API | 2 | 16 | 16 | 2 | 2026-01-22 | 2026-01-30
DIGITALLOG-123 - Wrong organization is displaying against my user ID and due to this issue all data is wrong. | 0 | 0 | 0 | 0
DIGITALLOG-135 - Read API is displaying other organization checklist data which is not present in my organization. | 0 | 0 | 8 | 1
DIGITALLOG-138 - Displaying data is not user friendly. It is displaying with programming language. | 0 | 0 | 0 | 0
DIGITALLOG-142 - Need to remove Template column when asking about all assets and locations in an organization. | 0.5 | 4 | 4 | 0.5 | 2026-02-10 | 2026-02-10
DIGITALLOG-143 - Wrong list of templates are displaying in log chat. | 0.5 | 4 | 4 | 0.5 | 2026-02-10 | 2026-02-10
DIGITALLOG-182 - Wrong data is displaying against active checklists in log chat. | 1 | 8 | 8 | 1 | 2026-02-11 | 2026-02-11
DIGITALLOG-183 - No excel file is downloaded in log chat after waiting. | 0 | 0 | 0 | 0
DIGITALLOG-185 - Wrong data is displaying against those checklists in which attachments are added. | 0 | 0 | 0 | 0
DIGITALLOG-186 - No data is displaying against returned checklists assigned to specific user. | 0 | 0 | 0 | 0
DIGITALLOG-187 - No data is displaying against specific checklist with a due date as well. | 0 | 0 | 0 | 0
DIGITALLOG-188 - No values in exported file is displaying against time frames. | 0 | 0 | 0 | 0
DIGITALLOG-189 - Unable to give answer on predictive question. | 0 | 0 | 0 | 0
DIGITALLOG-190 - Chat returns procedure instead of performing calculation. | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
DIGITALLOG-191 - No response is given against highest and lowest average against specific parameter data. | 0 | 0 | 0 | 0
DIGITALLOG-199 - SQA-Journal | 2 | 16 | 16 | 2 | 2026-02-13 | 2026-02-19
DIGITALLOG-200 - Assigned module access is not correct. | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-19 | 2026-02-19
DIGITALLOG-201 - No department or section is displaying in drop down while creating journal. | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-19 | 2026-02-19
DIGITALLOG-213 - Unable to activate my initial version of journal template again after creating and activating its second version. | 0 | 0 | 2 | 0.25
DIGITALLOG-216 - Journal template is not deleting where as success message is displayed. | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-19 | 2026-02-19
DIGITALLOG-224 - Error display when activating a previous version of journal template. It only displays when performing this activity first time. | 0 | 0 | 1 | 0.12 | 2026-02-20 | 2026-02-20
DIGITALLOG-323 - Read API is displaying other organization checklist data which is not present in my organization. - NA | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
DIGITALLOG-72 - User Manual/Documentation | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-19
DIGITALLOG-111 - URS and DDS Formatting for Digital Log Read API | 0 | 0 | 8 | 1
DIGITALLOG-73 - Production Release | 4 | 32 | 0 | 0 | 2026-02-20 | 2026-02-20
FF | 1497.03 | 11976.21 | 8584.92 | 1073.12 | 2025-08-19 | 2026-12-31
FF-1 - Fintech Fuel: Version 1 | 22 | 176 | 374 | 46.75
FF-2 - Improved UI | 6 | 48 | 48 | 6 | 2025-08-19 | 2025-08-27
FF-3 - Dashboard | 3 | 24 | 17 | 2.12 | 2025-09-11 | 2025-09-15
FF-4 - Transaction | 2 | 16 | 9 | 1.12 | 2025-09-11 | 2025-09-13
FF-5 - SQA | 5 | 40 | 101 | 12.62 | 2025-09-14 | 2025-09-17
FF-29 - After 10:43 AM utc time The Data for (PARCO GUNOVER) Gardenia Filling Station and (Adnan Chaudary) Palace View FS the Files are getting landed From the Un Processed Folder to the "Exceptional Folder". | 0 | 0 | 4 | 0.5 | 2025-10-02 | 2025-10-02
FF-30 - Again 2 files has been missed in the Processed folder for "Gardenia Filling Station" found in "Exception Folder". | 0 | 0 | 1 | 0.12
FF-31 - The Forgot password screen is the old screen and is not responsive and does not align with the new layout. | 0 | 0 | 1.33 | 0.17
FF-32 - Kindly update the email validation check upon forgot password screen as we have currently encounter client emails such as "Nida.wasif@parcogunvor.com.pk" as currently its not accepting. | 0 | 0 | 0.67 | 0.08
FF-33 - The links in the email for Forgot Password not working. | 0 | 0 | 1.33 | 0.17
FF-34 - Login with Microsoft button not clickable | 0 | 0 | 0.5 | 0.06
FF-35 - Data does not align with the Fuel Transaction trend as selected in the filter applied | 0 | 0 | 1 | 0.12
FF-36 - width of the selected option (selected Site) as the UI is disturbed in the filter modal | 0 | 0 | 0.67 | 0.08
FF-37 - Multiple Customers are showing in the customer dropdown in the filter modal | 0 | 0 | 8.33 | 1.04 | 2025-09-30
FF-38 - The Recon report which was working earlier just data not matched is now not working | 0 | 0 | 0.5 | 0.06
FF-39 - For specific time filter Day End sales filter is showing data but on the same time duration Day End Sales Summary is not working. | 0 | 0 | 1 | 0.12
FF-40 - kindly remove the user profile image selecting option as its no longer required | 0 | 0 | 0.83 | 0.1
FF-41 - Kindly update the Update button name to generate report | 0 | 0 | 0.67 | 0.08
FF-42 - When user apply the filter for 6 days and calculate the recon the data is not fetched. | 0 | 0 | 0.5 | 0.06
FF-43 - API Failure error when user tries to visit to Nozzle usage link while the Main Filter Modal is open. | 0 | 0 | 0.67 | 0.08
FF-44 - The SMTP email issue, Emails not sending to users through both the “Forgot Password” and new user activation emails depend on it. | 0 | 0 | 0.5 | 0.06
FF-45 - The issue is arising for Newly created users as the activation links redirects to 404 Error page | 0 | 0 | 0.5 | 0.06
FF-6 - Production Release | 1 | 8 | 8 | 1 | 2025-09-18 | 2025-09-18
FF-95 - User Manual / Guide | 5 | 40 | 4 | 0.5 | 2025-09-14 | 2025-09-17
FF-96 - Features and Functionalities - Word/PDF Doc | 0 | 0 | 4 | 0.5
FF-119 - Mobile App | 173.13 | 1385.02 | 1093.66 | 136.71 | 2025-11-17 | 2026-02-12
FF-120 - Development | 40 | 320 | 298 | 37.25 | 2025-11-24 | 2025-12-31
FF-159 - Login Page | 1 | 8 | 4 | 0.5 | 2025-12-01 | 2025-12-01
FF-160 - Forgot Password Screen | 1 | 8 | 8 | 1 | 2026-01-02 | 2026-01-02
FF-161 - Dashboard Home Page | 0 | 0 | 24 | 3 | 2025-12-03 | 2025-12-04
FF-162 - Alarms Page | 0 | 0 | 16 | 2 | 2025-12-08 | 2025-12-09
FF-163 - Deliveries Page | 0 | 0 | 16 | 2 | 2025-12-10 | 2025-12-11
FF-164 - Transactions Page | 0 | 0 | 16 | 2 | 2025-12-12 | 2025-12-15
FF-165 - Reconciliation Report Page | 0 | 0 | 16 | 2 | 2025-12-18 | 2025-12-19
FF-166 - Loss & Gain Charts Page | 0 | 0 | 16 | 2 | 2025-12-22 | 2025-12-23
FF-167 - Sales Target Page | 0 | 0 | 16 | 2 | 2025-12-26 | 2025-12-29
FF-168 - Stock Management Page | 0 | 0 | 8 | 1 | 2025-12-05 | 2025-12-05
FF-169 - Nozzle Usage Page | 0 | 0 | 8 | 1 | 2025-12-16 | 2025-12-16
FF-170 - FuelChat | 0 | 0 | 8 | 1 | 2025-12-24 | 2025-12-24
FF-171 - Crash Fixes | 2 | 16 | 8 | 1 | 2025-12-30 | 2026-01-06
FF-172 - Optimization for Responsiveness | 2 | 16 | 4 | 0.5 | 2025-12-31 | 2026-01-01
FF-199 - Play Store Deployment for Testers | 2 | 16 | 16 | 2 | 2026-01-13 | 2026-01-13
FF-218 - Low Stock Page | 1 | 8 | 8 | 1 | 2026-01-19 | 2026-01-19
FF-245 - Site Level Alerts Page | 0.25 | 2 | 2 | 0.25 | 2026-01-28 | 2026-01-28
FF-121 - SQA-Fintech Mobile App | 25 | 200 | 232.83 | 29.1 | 2026-01-08 | 2026-02-12
FF-177 - Tagline is Not same on Web And Mobile Application, Moreover it should be "Welcome To" Instead of "welcome Back" | 0.12 | 1 | 1 | 0.12 | 2026-01-08 | 2026-01-08
FF-178 - In Footer rights should be reserved for 2026 instead of 2025,The link to OctopusDigital should be included on the dashboard and throughout all other screens of the application. and the link should take users back to its original page | 0.12 | 1 | 1 | 0.12 | 2026-01-08 | 2026-01-08
FF-179 - Symmetry in icons and colors: Mentioned in the description | 0.12 | 1 | 1 | 0.12 | 2026-01-08 | 2026-01-09
FF-180 - "Username" is missing from Placeholder, Need to add it. | 0.12 | 1 | 1 | 0.12 | 2026-01-08 | 2026-01-08
FF-181 - "Sign in With Microsoft" is missing from Fintech Fuel Mobile Application. | 0 | 0.02 | 0 | 0 | 2026-01-08 | 2026-01-08
FF-182 - Unable to Reset the Password. | 0.25 | 2 | 2 | 0.25 | 2026-01-08 | 2026-01-08
FF-183 - “The eye icon should be updated to its inverse version.” on dashboard and Portal. | 0.12 | 1 | 1 | 0.12 | 2026-01-09 | 2026-01-12
FF-185 - “An expired OTP is being validated, allowing the user to log in and access the dashboard.” | 0.12 | 1 | 1 | 0.12 | 2026-01-12 | 2026-01-12
FF-186 - need to implement an error message on character limit | 0.12 | 1 | 1 | 0.12 | 2026-01-12 | 2026-01-12
FF-187 - Days and dates should be displayed as on dashboard, if both aren't manageable because of UI, Date must be displayed in Sales vs Target(Dashboard). | 0.12 | 1 | 1 | 0.12 | 2026-01-12 | 2026-01-12
FF-188 - Invalid OTP is being validated, allowing the user to log in and access the dashboard. | 0.31 | 2.5 | 2.5 | 0.31 | 2026-01-12 | 2026-01-12
FF-189 - Need to Remove upper extra section, Moreover all the highlighted values need to be displayed same as its on web | 0.06 | 0.5 | 0.5 | 0.06 | 2026-01-12 | 2026-01-12
FF-190 - 1.Profile menu is not getting vanished while clicking anywhere on the dashboard screen, 2. Dashboard: Tagline need to be same | 0.12 | 1 | 1 | 0.12 | 2026-01-12 | 2026-01-12
FF-191 - Forgot Password: Check the description | 0.12 | 1 | 1 | 0.12 | 2026-01-14 | 2026-01-14
FF-192 - Week Fuel Trend is not Interactive Left Side Values are not same with web dashboard, Secondly Product colors are not same. | 0.12 | 1 | 1 | 0.12 | 2026-01-27 | 2026-01-27
FF-194 - Selected Customer's logo is not getting displayed in the top menu. | 0.12 | 1 | 1 | 0.12 | 2026-01-14 | 2026-01-14
FF-195 - Dashboard Left menu amendments in text and missing pages, including Sequence of left Menu. | 0.25 | 2 | 2 | 0.25 | 2026-01-14 | 2026-01-14
FF-197 - Application doesn't blocks multiple failed login attempts | 0.12 | 1 | 1 | 0.12 | 2026-01-27 | 2026-01-27
FF-198 - Same web's error messages need to be displayed on mobile app, need to be fixed on all error messages. | 0.25 | 2 | 2 | 0.25 | 2026-01-14 | 2026-01-14
FF-200 - Alarms Issues: | 0.5 | 4 | 4 | 0.5 | 2026-01-14 | 2026-01-14
FF-201 - Alarms and their Icons and colors need to be matched with web dashboard. | 0.12 | 1 | 1 | 0.12 | 2026-01-15 | 2026-01-15
FF-203 - Search Placeholder is not visible completely, nor Icons and descriptions are same, alarm types Are missing also. | 0.12 | 1 | 1 | 0.12 | 2026-01-15 | 2026-01-15
FF-204 - User should Search/ Filter alarms on the basis of their: Title, Description, Severity | 0.06 | 0.5 | 0.5 | 0.06 | 2026-01-15 | 2026-01-15
FF-205 - While filtering multiple sites, or single site "Other" Alarm type is missing and its showing invalid count for that | 0.06 | 0.5 | 0.5 | 0.06 | 2026-01-15 | 2026-01-15
FF-206 - Severity Filter dropdown not implemented and functional. | 0.12 | 1 | 1 | 0.12 | 2026-01-15 | 2026-01-15
FF-207 - Selected Site/Customer name should be displayed. (on all screens) | 0.5 | 4 | 4 | 0.5 | 2026-01-15 | 2026-01-15
FF-208 - Date Range is limited to 2 weeks, Any 2 months for selection should be allowed to view data. It should be flexible that user can select data of 2 weeks or 1 month of any year, or 2 months or 1 day. | 0.25 | 2 | 2 | 0.25 | 2026-01-16 | 2026-01-16
FF-209 - The Application does not load data after login, Until we click the Refresh button. | 0.25 | 2 | 2 | 0.25 | 2026-01-16 | 2026-01-16
FF-211 - "Reconciliation Report" issues | 0.12 | 1 | 1 | 0.12 | 2026-01-16 | 2026-01-16
FF-212 - Missing Columns from Recon table: | 0.25 | 2 | 2 | 0.25 | 2026-01-16 | 2026-01-16
FF-213 - The Excel button for downloading the file is not implemented. | 0 | 0 | 0 | 0
FF-214 - Pagination needs to be implemented. on all the required pages as on web dashboard | 0 | 0 | 0 | 0
FF-215 - The Excel button for downloading the file is not implemented on Nozzle Usage, and description is not mentioned. | 0 | 0 | 0 | 0
FF-216 - All necessary columns must include IDs as well as inactive hours. | 0.12 | 1 | 1 | 0.12 | 2026-01-16 | 2026-01-16
FF-219 - Select All functionality is missing, It should be implemented on all the filters as on web dashboard. | 0.25 | 2 | 2 | 0.25 | 2026-01-21 | 2026-01-21
FF-220 - Inactive hours should not be less than 0 | 0.25 | 2 | 2 | 0.25 | 2026-01-21 | 2026-01-21
FF-221 - Overall Active Hours of Last 7 days are not available on the nozzle usage screen. | 0.25 | 2 | 2 | 0.25 | 2026-01-27 | 2026-01-27
FF-222 - The values on the column should match against the Column names in the table | 0.25 | 2 | 1 | 0.12 | 2026-01-27 | 2026-01-27
FF-223 - Failed to load Nozzle Usage Data for 2 days | 0.25 | 2 | 1 | 0.12 | 2026-01-27 | 2026-01-27
FF-224 - Stock Levels Issues | 0.25 | 2 | 2 | 0.25 | 2026-01-22 | 2026-01-22
FF-225 - All the Values must be same On Stock Levels. | 0.25 | 2 | 2 | 0.25 | 2026-01-22 | 2026-01-22
FF-226 - "Confirmed Quantity" and "Bill of Lading Reference" is missing from Deliveries Table, Moreover there must be some space in between Tank and Timestamp column. | 0.12 | 1 | 1 | 0.12 | 2026-02-04 | 2026-02-04
FF-227 - The Excel button for downloading the file is not implemented on Deliveries | 0 | 0 | 0 | 0
FF-239 - Low Stocks Issues which need to be fixed: | 0.12 | 1 | 1 | 0.12 | 2026-01-28 | 2026-01-28
FF-240 - Low Stocks: When choosing multiple sites, some values do not match, and Total Alerts should also be shown (for multiple sites/single sites). | 0.25 | 2 | 2 | 0.25 | 2026-01-29 | 2026-01-29
FF-241 - Low Stocks (Tank View ) : Alerts and Status column and Stock levels are missing | 0.25 | 2 | 2 | 0.25 | 2026-01-29 | 2026-01-29
FF-242 - Current Levels and Days Left should be same as implemented on Web Dashboard | 0.12 | 1 | 1 | 0.12 | 2026-01-29 | 2026-01-29
FF-243 - Grade View : | 0.25 | 2 | 2 | 0.25 | 2026-01-29 | 2026-01-29
FF-246 - All values of Deliveries page and all other screen need to be same, and .00 should be removed as we don't have much space in the mobile app nor it is implemented on web dashboard. | 0.12 | 1 | 1 | 0.12 | 2026-01-29 | 2026-01-29
FF-247 - Contact Support button need to be implemented on Mobile application | 0 | 0 | 0 | 0
FF-248 - Sales Target is not same as on web, values sales trend analysis: line charts and bar charts Daily sales summary fields and values Performance Summary (need to remove Extra) | 0.25 | 2 | 2 | 0.25 | 2026-02-02 | 2026-02-02
FF-249 - Missing Alerts and invalid total alerts for single and multiple sites On both Tank view and Grade view of low stocks | 0.25 | 2 | 2 | 0.25 | 2026-02-02 | 2026-02-02
FF-250 - Grade view values are not same while selecting single or multiple sites | 0 | 0 | 0 | 0
FF-251 - Card view should be same as table view of transactions , (Day end Sales), ⁠Pump and Hose Filter dropdowns are missing from transaction page. | 0.38 | 3 | 3 | 0.38 | 2026-02-02 | 2026-02-02
FF-252 - Excel button should be available and functional to be downloaded for transaction screen (Day end Sales) | 0 | 0 | 0 | 0
FF-253 - (Day end sales Summary) title need to be correct and extra columns should be removed, | 0.25 | 2 | 2 | 0.25 | 2026-02-02 | 2026-02-04
FF-254 - Card view should be same as table view of transactions , ("Day End Sales Summary"). | 0.12 | 1 | 1 | 0.12 | 2026-02-04 | 2026-02-04
FF-255 - Excel button should be available and Functional for the types of reports of transaction | 0 | 0 | 0 | 0
FF-256 - Need to remove unstable pagination from Transactions level sales and wherever else it is implemented as we are using (Load more button previously) So Load more button should be implemented now on every screen | 0.25 | 2 | 2 | 0.25 | 2026-02-03 | 2026-02-03
FF-257 - Transaction level sales : Title should complete. Padding must be added in between "Row Number" and "Site Name" | 0.12 | 1 | 1 | 0.12 | 2026-02-04 | 2026-02-04
FF-259 - Loss & Gain Chart : dates are mismatched. and need discussion on other graph values | 0.25 | 2 | 2 | 0.25 | 2026-02-03 | 2026-02-03
FF-260 - Invalid values for Daily Deliveries chart (Loss Gain Charts) | 0 | 0 | 0 | 0
FF-261 - Critical : Application is Crashing while changing the customer and transaction type, on Loss & Gain screen | 0 | 0 | 0 | 0
FF-262 - headings should be same while selecting any chart type on Loss Gain | 0 | 0 | 0 | 0
FF-263 - Selected date for filtration is from 26 but data is filtered from 25 (Sales target). | 0.25 | 2 | 2 | 0.25 | 2026-02-03 | 2026-02-03
FF-264 - Daily sales summary is getting displayed in weekly sales Summary | 0.38 | 3 | 3 | 0.38 | 2026-02-04 | 2026-02-04
FF-268 - While filtering the results for "92" which should be only 2 records its displaying 6 records, for card view of transactions | 0 | 0 | 0 | 0
FF-269 - those nozzles which are associated to the Pump2 should be filtered out, when user has specified the pump (Day end sales -Transactions ) instead of all the nozzles to be selected | 0 | 0 | 0 | 0
FF-272 - Transaction , Recon Report Booked: minus sign with zero is being displayed in mobile app | 0.12 | 1 | 1 | 0.12 | 2026-02-06 | 2026-02-06
FF-273 - Displaying Invalid Count while selecting multiple or all the sites of a customer (Low Stocks) | 0 | 0 | 0 | 0
FF-283 - Unable to Delete any chat from FuelCHat | 0 | 0 | 0 | 0
FF-284 - Unable to Edit any chat from FuelCHat | 0 | 0 | 0 | 0
FF-320 - Need to modify finchat to "FuelChat" | 0 | 0 | 0 | 0
FF-321 - FuelChat is showing invalid results while we ask for sites of a tenant | 0 | 0 | 0 | 0
FF-322 - Site name, Cite and Province is missing from the table | 0 | 0 | 0 | 0
FF-323 - While we login with portal user, Customer is not changeable on mobile application | 0 | 0 | 0 | 0
FF-324 - When dashboard user is assigned only one customer, and asking question related to another customer which is not assigned to it, the system shows information related to the assigned customer without displaying any restriction message. | 0 | 0 | 0 | 0
FF-326 - User can not Export chat in PDF by clicking on the "Export Chat" button. | 0 | 0 | 0 | 0
FF-327 - Bar Charts, Line Charts, Pie Chart are not available in Fuel chat | 0 | 0 | 0 | 0
FF-342 - Fintech Mobile App (Fuel Chat) | 4 | 32 | 12.83 | 1.6 | 2026-02-13 | 2026-02-18
FF-428 - Testing by Namra | 6 | 48 | 48 | 6 | 2026-01-08 | 2026-02-12
FF-122 - User Manual | 4 | 32 | 16 | 2 | 2026-01-01 | 2026-01-15
FF-123 - Production Release | 4 | 32 | 0 | 0 | 2026-01-16 | 2026-01-16
FF-16 - Fintech Fuel : Version 3 | 73.25 | 586 | 1782 | 222.75
FF-118 - User Manual | 0 | 0 | 52 | 6.5 | 2025-10-29 | 2025-10-30
FF-151 - Configuration Portal Updates | 0 | 0 | 12 | 1.5
FF-17 - Manual Entry Portal | 5 | 40 | 56 | 7 | 2025-10-21 | 2025-10-27
FF-109 - Manual Tank Delivery Recon | 0 | 0 | 40 | 5
FF-18 - Submit Data | 10 | 80 | 68 | 8.5 | 2025-10-20 | 2025-10-24
FF-19 - Support Portal | 2 | 16 | 16 | 2 | 2025-10-17 | 2025-10-20
FF-20 - SQA | 2 | 16 | 151 | 18.88 | 2025-10-29 | 2025-10-30
FF-217 - Fuel Chat Testing | 5 | 40 | 40 | 5 | 2026-01-19 | 2026-01-23
FF-258 - Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-02-04 | 2026-02-04
FF-265 - Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
FF-266 - Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
FF-267 - Fuel Chat Testing | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-26 | 2026-02-26
FF-285 - Fuel Chat Testing | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-04 | 2026-03-04
FF-286 - Fuel Chat Testing | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-12 | 2026-03-12
FF-287 - Fuel Chat Testing | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-18 | 2026-03-18
FF-288 - Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-03-25 | 2026-03-25
FF-21 - Production Release | 1 | 8 | 8 | 1 | 2025-11-03 | 2025-11-03
FF-487 - SQA Fuel Chat | 4 | 32 | 32 | 4 | 2026-04-01 | 2026-04-30
FF-488 - Fintech Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-04-17 | 2026-04-17
FF-489 - Fintech Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-04-08 | 2026-04-08
FF-490 - Fintech Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-04-22 | 2026-04-22
FF-491 - Fintech Fuel Chat Testing | 1 | 8 | 8 | 1 | 2026-04-29 | 2026-04-29
FF-97 - Fuel Chat | 28 | 224 | 508 | 63.5 | 2025-10-23 | 2025-10-27
FF-108 - FuelChat - DE API | 0 | 0 | 296 | 37
FF-202 - Fuel Chat Testing | 5 | 40 | 16 | 2
FF-98 - FuelChat - Development( Frontend + Backend) | 0 | 0 | 43 | 5.38
FF-99 - FuelChat - Visualization | 0 | 0 | 137 | 17.12
FF-271 - Fintech Fuel Read API | 76.88 | 615 | 342 | 42.75 | 2026-07-06 | 2026-07-24
FF-275 - Development | 10 | 80 | 113.5 | 14.19 | 2026-02-02 | 2026-02-13
FF-281 - R&D | 3 | 24 | 16 | 2 | 2026-01-21 | 2026-01-23
FF-282 - Swagger API Development | 4 | 32 | 32 | 4 | 2026-02-02 | 2026-02-06
FF-453 - SP for Product-wise and Tank-wise Reconciliation | 1 | 8 | 6.5 | 0.81 | 2026-03-09 | 2026-03-09
FF-458 - API Development Architecture Rework | 5 | 40 | 35 | 4.38 | 2026-03-06 | 2026-03-13
FF-546 - Add Rate Limiting for ReadAPI | 5 | 40 | 12 | 1.5 | 2026-04-20 | 2026-04-23
FF-547 - Add API Logs for ReadAPI | 5 | 40 | 12 | 1.5 | 2026-04-20 | 2026-04-23
FF-548 - Add a new API User type | 0 | 0 | 0 | 0
FF-276 - Staging Handover | 1 | 8 | 2 | 0.25 | 2026-02-23 | 2026-02-23
FF-460 - QA Handover | 0 | 0 | 2 | 0.25 | 2026-02-23 | 2026-02-23
FF-289 - SQA | 10 | 80 | 49 | 6.12 | 2026-06-17 | 2026-07-24
FF-459 - Testing By Kamran | 5 | 40 | 49 | 6.12 | 2026-03-11
FF-291 - Bug Fixing | 0 | 0 | 6 | 0.75
FF-471 - Product Availability Percentage showing 0 despite Available Volume having value in API response | 0.12 | 1 | 1 | 0.12 | 2026-03-16 | 2026-03-16
FF-472 - Read API not returning all deliveries within the specified 'FromDate' and 'ToDate' range | 0.25 | 2 | 1 | 0.12 | 2026-03-16 | 2026-03-16
FF-473 - Read API (Get Tank Levels) returning data for Customer and Site not assigned to the authenticated user | 0.38 | 3 | 3 | 0.38 | 2026-03-16 | 2026-03-16
FF-474 - The API accepts multiple parameters with the same name in the request but processes only the first parameter value while ignoring the remaining values without validation or error response. | 0.12 | 1 | 1 | 0.12 | 2026-03-16 | 2026-03-16
FF-475 - Enhance Read API to support multiple site inputs for a single customer | 0 | 0 | 0 | 0
FF-478 - Kindly provide Formula to calculate Variance and Variance Percentage only in Tank Levels | 0 | 0 | 0 | 0
FF-480 - The Get Transaction Summarized By Product API does not return aggregated (summarized) results for the provided date range. Instead of combining the data, the API response includes separate entries for each day within the range. | 0 | 0 | 0 | 0 | 2026-03-25 | 2026-03-25
FF-414 - User Manual | 1 | 8 | 0.5 | 0.06 | 2026-03-11 | 2026-03-16
FF-415 - Production Release | 0 | 0 | 0 | 0
FF-274 - Site Diagnostics Dashboard (System Health Monitoring) | 105.56 | 844.5 | 488 | 61 | 2026-04-08 | 2026-05-06
FF-277 - Development | 7 | 56 | 127.5 | 15.94 | 2026-02-06 | 2026-02-17
FF-279 - Frontend Development | 0 | 0 | 0 | 0
FF-280 - Backend API Development | 5 | 40 | 40 | 5 | 2026-02-19 | 2026-02-25
FF-346 - Alarm triggering logic + Development | 3 | 24 | 24 | 3 | 2026-01-28 | 2026-01-30
FF-372 - Integration of backend and frontend | 1 | 8 | 6.5 | 0.81 | 2026-02-20 | 2026-02-20
FF-391 - Unit testing | 0.81 | 6.5 | 4.5 | 0.56 | 2026-02-23 | 2026-02-23
FF-400 - Improvements after unit testing | 2 | 16 | 16.5 | 2.06 | 2026-02-24 | 2026-02-25
FF-406 - Diagnostics Dashboard is loading data for sites other than the customer selected and this user has not access to Aramco sites | 2 | 16 | 3 | 0.38 | 2026-02-26 | 2026-02-27
FF-419 - Diagnostic Dashboard displaying timestamps in UTC instead of Local Time Zone | 0.25 | 2 | 2 | 0.25 | 2026-03-05 | 2026-03-09
FF-420 - Active and Inactive Site Status Count should not Dependent on Grid Pagination | 1 | 8 | 2 | 0.25 | 2026-03-05 | 2026-03-09
FF-421 - “Per Site” Tab on Diagnostic Dashboard Displays Only Inactive Sites | 0.25 | 2 | 0 | 0 | 2026-03-05 | 2026-03-09
FF-422 - Notification Groups Can Be Created Using Only Numbers or Special Characters | 1 | 8 | 2 | 0.25 | 2026-03-05 | 2026-03-09
FF-423 - The Diagnostic Icon on the Top right bar shows notification number as "3" but in actual the customer has only one site and two activities in total | 1 | 8 | 3 | 0.38 | 2026-03-04 | 2026-03-06
FF-424 - The SITE LEVEL ALARM (Connectivity / Disconnectivity) email should not contain Tank ID and Tank Capacity and Current Value | 0 | 0 | 0 | 0
FF-425 - Integrate Additional Modules into Fuel Chat | 0 | 0 | 0 | 0
FF-429 - Connectivity Alarms Not Visible on Dashboard Despite Email Notifications | 0.25 | 2 | 0 | 0 | 2026-03-05 | 2026-03-09
FF-574 - UI Design Rework from AI | 2 | 16 | 16 | 2 | 2026-05-11 | 2026-05-12
FF-575 - UI Revamp and Graph Constructions | 3 | 24 | 8 | 1 | 2026-05-13 | 2026-05-15
FF-278 - SQA | 7 | 56 | 39.5 | 4.94 | 2026-02-18 | 2026-02-26
FF-426 - Testing by Kamran | 5 | 40 | 39.5 | 4.94
FF-290 - User Manual | 5 | 40 | 0 | 0
FF-311 - Research | 6 | 48 | 48 | 6 | 2026-02-03 | 2026-02-10
FF-462 - Initial requirements gathering and finalizing | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-03
FF-463 - Screen Designing and UI/UX creation | 2 | 16 | 16 | 2 | 2026-02-04 | 2026-02-05
FF-464 - Database schema designing | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-06
FF-465 - Finalizing development and unit testing with team | 1 | 8 | 8 | 1 | 2026-02-09 | 2026-02-09
FF-466 - Preparing for staging release and handover | 1 | 8 | 8 | 1 | 2026-02-10 | 2026-02-10
FF-416 - Production | 0 | 0 | 0 | 0
FF-527 - Development (Enhancement) | 0 | 0 | 29 | 3.62
FF-543 - Email and db structure modification | 5 | 40 | 29 | 3.62 | 2026-04-10 | 2026-04-15
FF-292 - ALSONs device data collection (read only) | 82.56 | 660.5 | 944 | 118 | 2026-02-09 | 2026-03-31
FF-293 - Development | 15 | 120 | 472 | 59 | 2026-02-01 | 2026-03-31
FF-439 - Alson Device Integration R&D | 2 | 16 | 3 | 0.38 | 2026-03-04 | 2026-03-06
FF-441 - R&D: ALSONS device data format & ingestion approach | 3 | 24 | 24 | 3 | 2026-02-01
FF-442 - R&D on Tank Level Data and Delivery Detection Logic | 3 | 24 | 19.5 | 2.44 | 2026-03-03 | 2026-03-06
FF-443 - Design & Develop: Ingestion MQTT Broker service | 7 | 56 | 56 | 7 | 2026-02-05 | 2026-02-12
FF-444 - Implement: Buffering & backpressure (MQTT-ETL) | 5 | 40 | 41 | 5.12 | 2026-02-16 | 2026-02-20
FF-445 - Build: ETL flow to land raw data on SFTP | 7 | 56 | 40 | 5 | 2026-02-21 | 2026-02-28
FF-451 - Develop VM ETL to transform incoming files/data - PART B | 4.06 | 32.5 | 40 | 5 | 2026-03-02 | 2026-03-06
FF-452 - Implement and Test Logic on Dummy Delivery Table | 3 | 24 | 19.5 | 2.44 | 2026-03-10 | 2026-03-12
FF-454 - Integrate Logic with Logic App and Validate | 2 | 16 | 13 | 1.62 | 2026-03-13 | 2026-03-16
FF-461 - Create a Demo Web Application for PGL | 3 | 24 | 20 | 2.5 | 2026-03-12 | 2026-03-16
FF-467 - Develop VM ETL to transform incoming files/data - PART A | 2.44 | 19.5 | 24 | 3 | 2026-02-25 | 2026-02-27
FF-468 - Develop VM ETL to transform incoming files/data - PART C | 4.06 | 32.5 | 40 | 5 | 2026-03-09 | 2026-03-13
FF-469 - SQL Insertion Pipeline for PGL Demo | 5 | 40 | 8 | 1 | 2026-03-16 | 2026-03-20
FF-479 - Alson data understanding to modify the SP accordingly | 2 | 16 | 20 | 2.5 | 2026-03-17 | 2026-03-18
FF-294 - SQA | 0 | 0 | 0 | 0
FF-295 - User Manual | 0 | 0 | 0 | 0
FF-296 - Production Release | 0 | 0 | 0 | 0
FF-297 - Alsons Integration with FintechFuel | 69 | 552 | 444 | 55.5 | 2026-03-26 | 2026-05-06
FF-298 - Development | 15 | 120 | 128 | 16 | 2026-03-30 | 2026-04-16
FF-497 - Updated Site Configuration for Alson Devices | 5 | 40 | 48 | 6 | 2026-04-02 | 2026-04-09
FF-511 - ETL Modification for Alson | 5 | 40 | 24 | 3 | 2026-04-10 | 2026-04-16
FF-529 - Current SP Modification + New SP for Tank Deliveries Calculation | 4 | 32 | 16 | 2 | 2026-04-08 | 2026-04-13
FF-544 - Testing the SP and integrating the logic into the current tank delivery table. | 3 | 24 | 24 | 3 | 2026-04-16 | 2026-04-20
FF-545 - Pointer table changes and Integration with web team | 2 | 16 | 16 | 2 | 2026-04-21 | 2026-04-22
FF-299 - SQA | 15 | 120 | 0 | 0 | 2026-04-17 | 2026-05-06
FF-300 - User Manual | 0 | 0 | 0 | 0
FF-301 - Production Release | 0 | 0 | 0 | 0
FF-483 - Research | 10 | 80 | 94 | 11.75 | 2026-03-26 | 2026-04-09
FF-484 - Requirements understanding and analyzing | 1 | 8 | 8 | 1 | 2026-03-26 | 2026-03-26
FF-485 - Requirements gathering | 1 | 8 | 24 | 3 | 2026-03-26 | 2026-03-30
FF-486 - Database schema design planning | 1 | 8 | 8 | 1 | 2026-03-27 | 2026-03-27
FF-492 - Alson requirements gathering | 4 | 32 | 38 | 4.75 | 2026-03-27 | 2026-04-10
FF-493 - Schema design validation and rectification | 2 | 16 | 16 | 2 | 2026-03-27 | 2026-03-30
FF-528 - Sp modification to insert Alson data into current TankDelivery | 0 | 0 | 0 | 0
FF-539 - Bug Fixing | 0 | 0 | 0 | 0
FF-540 - SQA Handover | 1 | 8 | 0 | 0 | 2026-04-17 | 2026-04-17
FF-302 - Fuel price write back | 10 | 80 | 0 | 0 | 2026-04-20 | 2026-05-11
FF-303 - Development | 0 | 0 | 0 | 0
FF-304 - SQA | 10 | 80 | 0 | 0 | 2026-05-01 | 2026-05-11
FF-305 - User Manual | 0 | 0 | 0 | 0
FF-306 - Production Release | 0 | 0 | 0 | 0
FF-312 - FuelChat - Summarized Version | 34 | 272 | 40 | 5 | 2026-05-04 | 2026-02-18
FF-505 - SQA | 10 | 80 | 0 | 0 | 2026-05-12 | 2026-05-18
FF-565 - Development | 6 | 48 | 20 | 2.5 | 2026-05-04 | 2026-05-11
FF-566 - Summarizer code addition | 3 | 24 | 4 | 0.5 | 2026-05-04 | 2026-05-06
FF-567 - Integration of summarizer with the current code | 1 | 8 | 4 | 0.5 | 2026-05-14 | 2026-05-14
FF-568 - Instruction revamp | 2 | 16 | 12 | 1.5 | 2026-05-08 | 2026-05-11
FF-314 - Configurable Alarms and Sites, Notifications | 95.09 | 760.69 | 595.04 | 74.38 | 2026-02-06 | 2026-03-16
FF-315 - Development | 7 | 56 | 217.77 | 27.22 | 2026-02-06 | 2026-02-16
FF-318 - Designing Database Schema | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-06
FF-319 - Backend API Development | 3 | 24 | 16 | 2 | 2026-02-06 | 2026-02-12
FF-328 - Creating Notification Group Page | 0.5 | 4 | 4 | 0.5 | 2026-02-06 | 2026-02-06
FF-329 - Creating Alarms Configurations Page | 0.5 | 4 | 4 | 0.5 | 2026-02-06 | 2026-02-06
FF-330 - Integrating APIs (Notifications Group Page) | 1 | 8 | 7 | 0.88 | 2026-02-09 | 2026-02-09
FF-331 - Integrating APIs (Alarm Configurations Page) | 1 | 8 | 7 | 0.88 | 2026-02-10 | 2026-02-10
FF-332 - Sanity and Bug Fixes | 3 | 24 | 23 | 2.88 | 2026-02-11 | 2026-02-16
FF-338 - Integrating new APIs for Alarms page with Acknowledge functionality | 0.5 | 4 | 4 | 0.5 | 2026-02-12 | 2026-02-12
FF-339 - Alarm Triggering Logic | 2 | 16 | 16 | 2 | 2026-02-09 | 2026-02-10
FF-340 - SQL Triggers for Alarm Triggering | 2 | 16 | 16 | 2 | 2026-02-11 | 2026-02-12
FF-341 - Logic App Development for Email Notifications | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-16
FF-344 - Requirement finalizing, unit testing, task management and staging release preparation | 6 | 48 | 48 | 6 | 2026-02-11 | 2026-02-18
FF-345 - Improvements in SQL Alarm Triggering Logic | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
FF-352 - Unit Testing with web team | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
FF-370 - Making fuelchat compatible | 3 | 24 | 19 | 2.38 | 2026-02-17 | 2026-02-20
FF-376 - Current Value For Delivery Arrival Alarm triggered is showing value in Percentages% | 2 | 16 | 0.5 | 0.06 | 2026-02-24 | 2026-02-27
FF-377 - Acknowledge Alarm should show the user name by which it is Acknowledge and the acknowledge time also | 0.12 | 1 | 1 | 0.12 | 2026-02-24 | 2026-02-25
FF-378 - Variance Alarms Not Triggering Despite Condition Match | 0.25 | 2 | 2 | 0.25 | 2026-02-23 | 2026-02-23
FF-380 - Site Dropdown Inactive and doesn't show site name in Alarm Configuration When Single Site Selected in Main Filter | 2 | 16 | 0.25 | 0.03 | 2026-02-24 | 2026-02-27
FF-385 - Unable to delete alarms | 2 | 16 | 0.25 | 0.03 | 2026-02-24 | 2026-02-27
FF-386 - Inactive (Unacknowledged) Alarms Not Visible in Historical Tab as its showing inthe Data base | 2 | 16 | 0 | 0 | 2026-02-24 | 2026-02-25
FF-387 - Pagination is not applied on alarms screen on configured alarms table | 0.06 | 0.5 | 0.5 | 0.06 | 2026-02-24 | 2026-02-27
FF-388 - Application Not Redirecting to Login Page (MAIN URL) After Session Timeout on Refresh | 2 | 16 | 0.75 | 0.09 | 2026-02-25 | 2026-02-27
FF-389 - System Allows Creation of Duplicate Notification Groups | 2 | 16 | 0.25 | 0.03 | 2026-02-24 | 2026-02-27
FF-397 - Updated Time Field Not Refreshing on Alarm Activation/Deactivation | 2 | 16 | 1 | 0.12 | 2026-02-25 | 2026-02-27
FF-402 - While Editing an existing alarm, the fields Customer, Sites, Alarm Type, and Sub Alarm Type should not be editable. | 0.25 | 2 | 1 | 0.12 | 2026-02-25 | 2026-02-27
FF-409 - ADD Scroll functionality for Notification Group Section | 0 | 0.02 | 0.02 | 0 | 2026-02-26 | 2026-02-27
FF-410 - ADD pagination in the following screens 1. Recipients Groups 2. Diagnostic Configuration tabs in the Notifications group | 0.06 | 0.5 | 0.25 | 0.03 | 2026-02-26 | 2026-02-27
FF-417 - Testing for fuelchat | 1 | 8 | 6.5 | 0.81 | 2026-02-27 | 2026-02-27
FF-430 - Mismatch in Configured Alarms for ROSE MOUNT Between Dashboard and Fuel Chat | 0.12 | 1 | 1 | 0.12 | 2026-03-04 | 2026-03-04
FF-431 - Created Date and Updated Date format is not correct in the CSV downloaded from FUEL chat for Configured Alarms | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-04 | 2026-03-04
FF-432 - Updated time is missing for some alarms on Fuel Chat | 0.25 | 2 | 0.5 | 0.06 | 2026-03-05 | 2026-03-09
FF-433 - Some of Inactive Alarms Missing in Fuel Chat Despite Being Present on Dashboard | 0.12 | 1 | 1 | 0.12 | 2026-03-04 | 2026-03-04
FF-434 - Fuel Chat Missed Disconnectivity Event Displayed on Dashboard | 0.12 | 1 | 1 | 0.12 | 2026-03-04 | 2026-03-04
FF-435 - Fuel Chat Not Displaying Tank-Wise Delivery Alarms as Shown on Dashboard | 0 | 0 | 1 | 0.12
FF-436 - Fuel Chat Not Retrieving Alarm Trigger Conditions | 0.25 | 2 | 1.5 | 0.19 | 2026-03-04 | 2026-03-04
FF-437 - Fuel Chat Not Displaying Only Active Notification Groups Used in Alarm Configuration | 0 | 0 | 0 | 0
FF-438 - Fuel Chat Session Does Not Expire After Inactivity | 1 | 8 | 0.5 | 0.06 | 2026-03-05 | 2026-03-09
FF-440 - Duplicates found in terms of Notification groups in Fuel Chat | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-04 | 2026-03-04
FF-316 - SQA | 4 | 32 | 58.5 | 7.31 | 2026-02-18 | 2026-02-24
FF-354 - Testing By Kamran | 4 | 32 | 39.5 | 4.94 | 2026-02-18 | 2026-02-23
FF-362 - User is able to create alarms with empty conditions | 2 | 16 | 3 | 0.38 | 2026-02-17 | 2026-02-17
FF-363 - Alarms permissions missing for Create, Edit and Delete | 2 | 16 | 3 | 0.38 | 2026-02-17 | 2026-02-17
FF-364 - Delivery Arrival time for alarms mismatch with the original deliveries landed in the prod env | 0.5 | 4 | 4 | 0.5 | 2026-02-18 | 2026-02-18
FF-365 - Add the Setpoints for Alarms triggered such as variance, Tanks Levels and others alarms too where suitable | 0.75 | 6 | 5 | 0.62 | 2026-02-18 | 2026-02-18
FF-366 - While Configuring Condition based alarms if user selects a condition, no option is available to revert it i.e reverting back to single state | 2 | 16 | 1 | 0.12 | 2026-02-19 | 2026-02-19
FF-367 - Remove ID's along with entities on all pages | 0.12 | 1 | 1 | 0.12 | 2026-02-19 | 2026-02-19
FF-368 - Inactive Customer still showing on staging | 2 | 16 | 0 | 0 | 2026-02-19 | 2026-02-19
FF-369 - LOGIN with Microsoft not working | 2 | 16 | 1 | 0.12 | 2026-02-19 | 2026-02-19
FF-371 - "<=" amd ">=" conditions missing for Tank Level Alarms & Recon Alarms | 0.12 | 1 | 1 | 0.12 | 2026-02-19 | 2026-02-19
FF-455 - Incorrect Side Navigation and Message Box Visibility Issue on Fuel Chat Screen | 0.25 | 2 | 0 | 0 | 2026-03-18 | 2026-03-18
FF-317 - User Manual | 0 | 0 | 0 | 0
FF-337 - Production Release | 2 | 16 | 0 | 0 | 2026-02-27 | 2026-02-27
FF-348 - Staging Release | 2 | 16 | 18.5 | 2.31 | 2026-02-16 | 2026-02-17
FF-349 - Deployment of Backend on Staging | 1 | 8 | 6 | 0.75 | 2026-02-16 | 2026-02-16
FF-350 - Deployment of Frontend on Staging | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
FF-351 - QA Handover | 1 | 8 | 4 | 0.5 | 2026-02-17 | 2026-02-17
FF-361 - QA Handover | 0.06 | 0.5 | 0.5 | 0.06 | 2026-02-17 | 2026-02-17
FF-355 - QA-Handover | 0.62 | 5 | 2.75 | 0.34 | 2026-02-17 | 2026-02-17
FF-356 - Namra | 0.08 | 0.67 | 0.67 | 0.08 | 2026-02-17 | 2026-02-17
FF-357 - M.Abbas | 0.12 | 1 | 0.58 | 0.07 | 2026-02-17 | 2026-02-17
FF-358 - Zeeshan | 0 | 0 | 0 | 0
FF-359 - Kamran | 0.12 | 1 | 1 | 0.12 | 2026-02-17 | 2026-02-17
FF-360 - Waqar | 0.06 | 0.5 | 0.5 | 0.06 | 2026-02-17 | 2026-02-17
FF-343 - Technical Support | 379.06 | 3032.5 | 186 | 23.25
FF-476 - PGL - Fintech Fuel Functional and Architectural Document | 0 | 0 | 34 | 4.25 | 2026-03-13 | 2026-03-17
FF-477 - Documentation | 1.31 | 10.5 | 10 | 1.25 | 2026-03-16 | 2026-03-17
FF-481 - Addressing client's queries, review and finalizing documentation | 1 | 8 | 8 | 1 | 2026-03-18 | 2026-03-18
FF-482 - Internal data source backup and restoring(on local machine) practice | 2 | 16 | 16 | 2 | 2026-03-24 | 2026-03-25
FF-495 - Addressing technical support tickets | 0 | 0 | 1 | 0.12 | 2026-04-02
FF-496 - Renaming site name, marking site inactive and verifying reactivation | 0.12 | 1 | 1 | 0.12 | 2026-04-02 | 2026-04-02
FF-531 - Support for Ticket FIN-112 COCO LHR-1 (Aramco) | 2 | 16 | 14 | 1.75 | 2026-04-13 | 2026-05-13
FF-532 - Support for Ticket FIN-116 COCO-GUJRANWALA 2 (ARAMCO) | 2 | 16 | 11 | 1.38 | 2026-05-13 | 2026-05-13
FF-533 - Support for Fin-116 COCO ISB 2 (ARAMCO) | 1 | 8 | 6 | 0.75 | 2026-04-13 | 2026-05-13
FF-534 - Support for Fin-116 COCO ISB 2 (ARAMCO) | 0.38 | 3 | 3 | 0.38 | 2026-04-13
FF-549 - Support for site validations fintech | 0.5 | 4 | 4 | 0.5 | 2026-04-23 | 2026-04-23
FF-550 - Support for Site Validations(COCO UET, COCO MULTAN and COCO Peshawar) | 0.75 | 6 | 6 | 0.75 | 2026-04-23 | 2026-04-23
FF-558 - Customer Products – Add Create & Modify Audit Fields | 0 | 0 | 0 | 0
FF-559 - Customer Sites – Executive Summary & Usage Overview | 0 | 0 | 0 | 0
FF-560 - Prevent Activated Sites from Appearing in Site Configuration Workflow | 0 | 0 | 0 | 0
FF-563 - Make site configuration page independent of sites. Access by clicking on customer. | 0 | 0 | 0 | 0
FF-564 - Change workflow by introducing inactive button and inactive workflow via modal | 0 | 0 | 0 | 0
FF-561 - Allow Asset Deletion During Pre-Configuration Stage | 0 | 0 | 0 | 0
FF-562 - Send Automated Diagnostic Email After Site Activation with Data Quality & Rectification Details | 0 | 0 | 0 | 0
FF-573 - Support for WAFI ENERGIES pilot sites on Boarding | 3 | 24 | 14 | 1.75 | 2026-05-11 | 2026-05-13
FF-373 - Fintech Fuel - Regression | 89.38 | 715 | 267.06 | 33.38 | 2026-01-01 | 2026-12-31
FF-374 - Fintech-Regression (2/23/26 - 2/27/26) | 8 | 64 | 23.25 | 2.91 | 2026-02-23 | 2026-02-27
FF-379 - User type is not getting changed to AAD User, and showing the error while user tries to login with Microsoft. | 2 | 16 | 0 | 0 | 2026-02-23 | 2026-02-26
FF-382 - Forgot Password Functionality if Failed with this error | 2 | 16 | 1 | 0.12 | 2026-02-24 | 2026-02-25
FF-383 - After turning on the OTP, Instead of letting the user to be logged in, its showing the Error | 2 | 16 | 1 | 0.12 | 2026-02-24 | 2026-02-25
FF-384 - login with Microsoft functionality should be implemented for dashboard user also. TASK | 0 | 0 | 0 | 0
FF-392 - “Account Does Not Exist” Error on Staging and Forgot Password Failure | 2 | 16 | 0.25 | 0.03 | 2026-02-24 | 2026-02-25
FF-393 - Selected Sites Not Displayed in Site Field (Deliveries Screen) — Implement Fix Across Application | 0 | 0 | 2 | 0.25
FF-394 - Search Functionality Limited to Site Name and Article Columns on Deliveries Screen | 0 | 0 | 0.5 | 0.06
FF-395 - Date Filter on Deliveries Screen Returns Data Outside Selected Date Range | 2 | 16 | 0.25 | 0.03 | 2026-02-25 | 2026-02-27
FF-396 - Validation Error Placement and Value Reset Issue When Entering Quantity Greater Than Capacity on Deliveries screen | 2 | 16 | 0.25 | 0.03 | 2026-02-25 | 2026-02-27
FF-398 - “Submit Values” Button Enabled by Default on Deliveries Screen even when the Confirmed Quantity field and Bill of Lading Reference field is empty | 2 | 16 | 0.75 | 0.09 | 2026-02-25 | 2026-02-27
FF-399 - Warning Status Displayed for 3 Days Remaining on Low Stock Screen | 2 | 16 | 0.25 | 0.03 | 2026-02-25 | 2026-02-27
FF-401 - Support Icon Overlapping with “Next” Pagination Text on Low Stock Screen | 2 | 16 | 1 | 0.12 | 2026-02-25 | 2026-02-27
FF-403 - Search and Filter Functionality Not Working Correctly on Deliveries Screen | 2 | 16 | 0.5 | 0.06 | 2026-02-26 | 2026-02-27
FF-404 - Summary Metrics Not Updating According to Applied Search on Deliveries Screen | 2 | 16 | 0.5 | 0.06 | 2026-02-26 | 2026-02-27
FF-405 - Inconsistent Timestamp Format on Deliveries Screen | 2 | 16 | 0.5 | 0.06 | 2026-02-26 | 2026-02-27
FF-407 - Tooltip Color Mismatch on Loss/Gain Chart Screen | 2 | 16 | 1.5 | 0.19 | 2026-02-26 | 2026-02-27
FF-408 - Stock Volume Mismatch Between Loss/Gain Chart and Recon Report (Hi Super & Excellium) | 0 | 0 | 4 | 0.5
FF-411 - Opening Level Field Not Editable for Non-Consecutive Days on Submit Data Screen | 2 | 16 | 5 | 0.62 | 2026-03-02 | 2026-03-09
FF-412 - Side Menu “Submit Data” Tab Not Highlighted on Day Submission Screen | 2 | 16 | 1 | 0.12 | 2026-03-02 | 2026-03-09
FF-413 - Actual Closing Field Should Auto-Populate and Be Non-Editable on Submit Data Screen. Also add respective unit with each column | 0.38 | 3 | 3 | 0.38 | 2026-03-02 | 2026-03-09
FF-418 - Pagination malfunction on Deliveries page | 0 | 0 | 0 | 0 | 2026-03-05
FF-427 - Fintech-Regression (2/23/26 - 2/27/26) | 8 | 64 | 62.28 | 7.79 | 2026-02-23 | 2026-02-27
FF-375 - Testing By Namra | 4 | 32 | 36.78 | 4.6 | 2026-02-23 | 2026-02-27
FF-390 - Testing By Waqar | 4 | 32 | 25.5 | 3.19 | 2026-02-23 | 2026-02-26
FF-456 - Fintech-Staging-Regression(3/10/2026 - 3/17/2026) | 10 | 80 | 40 | 5 | 2026-03-10 | 2026-03-17
FF-457 - Testing By Kamran | 3 | 24 | 8 | 1 | 2026-03-10 | 2026-03-13
FF-530 - Testing By waqar | 2 | 16 | 16 | 2 | 2026-04-13 | 2026-04-14
FF-569 - Testing By Kamran April | 2 | 16 | 16 | 2 | 2026-04-01 | 2026-04-02
FF-503 - Fintech-Regression-Bug-Fixing (2/23/26 - 2/27/26) | 2 | 16 | 8 | 1 | 2026-02-23 | 2026-02-27
FF-504 - QA Reported UI Bugs | 1 | 8 | 8 | 1 | 2026-04-07 | 2026-04-07
FF-570 - Regression Staging (12-05-2026 --20-05-2026) | 5 | 40 | 0 | 0 | 2026-05-13 | 2026-05-20
FF-571 - Testing By kamran | 5 | 40 | 0 | 0 | 2026-05-13 | 2026-05-20
FF-572 - Testing By Namra | 5 | 40 | 0 | 0 | 2026-05-13 | 2026-05-20
FF-581 - Forgot Password is failed | 0 | 0 | 0 | 0
FF-446 - Audit trails (phase 1) - User-management | 36 | 288 | 10 | 1.25 | 2026-05-13 | 2026-06-03
FF-447 - Development | 20 | 160 | 5 | 0.62 | 2026-05-15 | 2026-05-29
FF-448 - Database Schema Design | 1 | 8 | 2 | 0.25 | 2026-02-02 | 2026-02-03
FF-449 - Backend Development | 2 | 16 | 3 | 0.38 | 2026-02-09 | 2026-02-12
FF-450 - SQA Handover | 1 | 8 | 0 | 0 | 2026-03-06 | 2026-03-06
FF-523 - SQA | 5 | 40 | 0 | 0 | 2026-06-01 | 2026-06-03
FF-524 - Production Release | 2 | 16 | 0 | 0 | 2026-06-03 | 2026-06-04
FF-526 - Research | 5 | 40 | 0 | 0 | 2026-05-13 | 2026-05-14
FF-498 - Multi Language Support | 44.75 | 358 | 224 | 28 | 2026-04-08 | 2026-05-06
FF-499 - Research | 4 | 32 | 32 | 4 | 2026-04-08 | 2026-04-10
FF-501 - Research on Multi Language Support | 2 | 16 | 16 | 2 | 2026-04-08 | 2026-04-09
FF-502 - Research on Angular i18n for LS | 1 | 8 | 8 | 1 | 2026-04-10 | 2026-04-10
FF-535 - Dashboard POC Implementation | 1 | 8 | 8 | 1 | 2026-04-13 | 2026-04-13
FF-500 - Development | 8 | 64 | 80 | 10 | 2026-04-13 | 2026-04-22
FF-551 - Integrating i18n + 8 Languages Support | 1 | 8 | 8 | 1 | 2026-04-27 | 2026-04-27
FF-552 - Dashboard Language Change | 0.25 | 2 | 2 | 0.25 | 2026-05-28 | 2026-05-28
FF-553 - Alarms/Daily Deliveries/ Recon Page | 0.75 | 6 | 6 | 0.75 | 2026-04-28 | 2026-04-28
FF-554 - Nozzle/Stock/ Low Stock Page | 0.75 | 6 | 6 | 0.75 | 2026-04-29 | 2026-04-29
FF-555 - Transactions/ Sales Target/Target Setup Page | 2 | 16 | 10 | 1.25 | 2026-04-29 | 2026-04-30
FF-556 - Submit Data/ Daily Sales/ Loss Gain Charts Page | 3 | 24 | 24 | 3 | 2026-05-01 | 2026-05-05
FF-557 - My Profile/ Site Diag/ Notifications Group Page | 3 | 24 | 24 | 3 | 2026-05-06 | 2026-05-08
FF-510 - SQA | 3 | 24 | 0 | 0 | 2026-05-04 | 2026-05-06
FF-536 - Bug Fixing | 0 | 0 | 0 | 0
FF-537 - Production Release | 0 | 0 | 0 | 0
FF-538 - Handover | 0 | 0 | 0 | 0
FF-512 - Audit trails (phase 2) - Module Interaction | 27 | 216 | 0 | 0 | 2026-06-04 | 2026-06-22
FF-513 - Development | 15 | 120 | 0 | 0 | 2026-06-08 | 2026-06-17
FF-514 - SQA | 5 | 40 | 0 | 0 | 2026-07-01 | 2026-06-22
FF-515 - Research | 5 | 40 | 0 | 0 | 2026-06-04 | 2026-06-05
FF-516 - Production Release | 2 | 16 | 0 | 0 | 2026-06-22 | 2026-06-23
FF-517 - Audit trails (phase 3) - Activity Log | 54 | 432 | 0 | 0 | 2026-06-22 | 2026-07-03
FF-518 - Development | 15 | 120 | 0 | 0 | 2026-06-24 | 2026-06-30
FF-519 - SQA | 5 | 40 | 0 | 0 | 2026-07-01 | 2026-07-03
FF-520 - Research | 5 | 40 | 0 | 0 | 2026-06-22 | 2026-06-23
FF-521 - Production Release | 2 | 16 | 0 | 0 | 2026-07-03 | 2026-07-06
FF-541 - User & role management | 0 | 0 | 0 | 0
FF-542 - Calculate Tank delivery (Alsons device) | 0 | 0 | 0 | 0
FF-576 - Dashboard Enhancement | 5 | 40 | 0 | 0 | 2026-09-15 | 2026-09-21
FF-577 - Historical Comparison & Trend Analysis | 8 | 64 | 0 | 0 | 2026-09-22 | 2026-10-01
FF-578 - Reporting, Terminology & Units | 5 | 40 | 0 | 0 | 2026-10-02 | 2026-10-08
FF-579 - Date Range & Time Handling | 6 | 48 | 0 | 0 | 2026-10-09 | 2026-10-16
FF-580 - Configurable Site Reconn. Time | 6 | 48 | 0 | 0 | 2026-10-19 | 2026-10-26
FF-7 - Fintech Fuel : Version 2 | 18 | 144 | 766.66 | 95.83
FF-10 - Sales Targets | 1 | 8 | 58 | 7.25 | 2025-09-26 | 2025-10-02
FF-15 - SP modification (Bug reported) | 0 | 0 | 10 | 1.25
FF-11 - Sudden Loss | 1 | 8 | 16 | 2 | 2025-09-26 | 2025-09-30
FF-12 - Alarms | 4 | 32 | 53 | 6.62 | 2025-10-05 | 2025-10-08
FF-13 - SQA | 5 | 40 | 166.33 | 20.79 | 2025-10-09 | 2025-10-16
FF-100 - The Filter on the Transaction page is not working correctly as i have applied filter the data for "PUMP_4" but its showing data of other pumps too | 0 | 0 | 0.5 | 0.06
FF-101 - ON the Nozzle usage page in the table the customer name is showing instead of site in the column "site name" | 0 | 0 | 0.75 | 0.09
FF-102 - The filter functionality is not consistent across pages. | 0 | 0 | 0 | 0
FF-103 - The purpose of the filter on the Loss Gain Chart page is unclear, as it’s currently not functioning. The filter appears inactive, while the Loss Gain Chart itself is working correctly and displaying data. | 0 | 0 | 0 | 0
FF-104 - 1. Remove datetime range control 2. Show respective tank name 3. Control to toggle view between tank / product wise display in Stock Level pages Pages | 0 | 0 | 1 | 0.12
FF-105 - Floating value display on column and show units as well like PKR, Ltr etc 1. Volume, 2. Money, and 3. PPU in Transaction page | 0 | 0 | 1.33 | 0.17
FF-106 - Icon needs to be replaced with appropriate icon in "per week target", "Daily average target" cards, | 0 | 0 | 0.42 | 0.05
FF-107 - Mock targets are being displayed | 0 | 0 | 0 | 0
FF-110 - On the Loss Gain Chart page the tank level filter is not working | 1 | 8 | 3.5 | 0.44 | 2025-10-16 | 2025-10-17
FF-111 - User Manual | 0 | 0 | 13 | 1.62
FF-48 - Update the unit From Dollars to PKR as highlighted in the screenshot | 0 | 0 | 1 | 0.12
FF-49 - Generate button is containing string (DEBUG :FALSE) and its not working for Daily Stock chart for the same time period as selected for Daily sales chart | 0 | 0 | 0.5 | 0.06
FF-50 - when i change the option from "Daily Sales Chart" to "Daily Stock Chart", then the system generates error Timeout expired | 0 | 0 | 1.5 | 0.19
FF-51 - While reviewing the Daily Sales chart for the one-month period, the report shows a total loss of 17.9k liters. This value appears incorrect and suggests an issue with the calculation or data representation. | 0 | 0 | 6 | 0.75
FF-52 - kindly change the Arrow position downwards as its reflecting LOSS not Gain | 0 | 0 | 0.5 | 0.06
FF-53 - Upon Checking the Deliveries chart From Time Period 1 may to 30th may 2025 for Site COCO-Liberty as compared to the Data with the same Filter Applied on SM 360 Web Application. The Data Mismatch | 0 | 0 | 0 | 0
FF-54 - Daily Stock Level Mismatch as of 1st May 2025 as compared to SM 360 for site COCO Liberty | 0 | 0 | 2.5 | 0.31
FF-55 - Loader is missing on the Loss Gain Charts | 0 | 0 | 1.08 | 0.14
FF-56 - AS compared to SM 360 when user applies the Daily Sales filter the Fintech App showing values on the Loss Gain Chart in term of Money and on the other hand the SM 360 shows it in terms of Liters | 0 | 0 | 1 | 0.12
FF-57 - Kindly update the Date Time Filter as compared to SM 360 as currently it does not help the users | 0 | 0 | 0 | 0
FF-58 - The Tank filter should be dependent on Grade filter it should show only the tanks of the product selected. | 0 | 0 | 1 | 0.12
FF-59 - Dashboard data for Revenue does not match with the Production data for Same time period applied on both environments | 0 | 0 | 4 | 0.5
FF-60 - In Recon Report every column should not be displayed in floating please verify it from Production as retail team has specified some column to be round off | 0 | 0 | 1.33 | 0.17
FF-61 - There is no such thing as Low Stock Alert Management as we do not manage any alerts regarding low stocks and secondly the columns mismatch as Capacity is missing Date column is missing threshold missing. | 0 | 0 | 1.5 | 0.19
FF-62 - Sales data is not getting loaded against tank levels in Sales Target Module. | 0 | 0 | 3 | 0.38
FF-63 - I have Applied Filter for Weekly Sales but the error is showing for Daily Sales | 0 | 0 | 1 | 0.12
FF-64 - I have set the Target for 10 days up to "500000" liters but the total target showing "5,150,000" Liters as in SM 360 the target is the total volume for the selected period not for a single day | 0 | 0 | 0 | 0
FF-65 - I Have set Target for Aramco Site but when i changed the filter to Total site the same targeted data is shown for Total as i have not set any targets for Total | 0 | 0 | 1.5 | 0.19
FF-66 - Success messages are not properly handled, please look into it | 0 | 0 | 1.33 | 0.17
FF-67 - Filter is not available for Recon Page and Nozzle Page | 0 | 0 | 0.83 | 0.1
FF-68 - Username Field on login page accepts spaces which is in correct, please restrict it as its restricted while creating user. | 0 | 0 | 0.5 | 0.06
FF-69 - Reset Password Validations are missing on Password and Confirm Password Fields, kindly apply validations | 0 | 0 | 1 | 0.12
FF-70 - new Sites for Total Parco got configured but some of the file of the sites landed in the exceptional folder, please look into it | 0 | 0 | 0.5 | 0.06
FF-71 - Increase the font size of the filter heading and dropdown text to ensure consistency with the other elements on the dashboard.” | 0 | 0 | 0.67 | 0.08
FF-72 - Never saw this column in Recon Report named "Variances" containing "Nan" values, please remove this and look into it why this appear | 0 | 0 | 1 | 0.12
FF-73 - Variance % and Cumulative Variances % column does not match with the Columns data for recon report with Production | 0 | 0 | 1.67 | 0.21
FF-74 - Spelling Mistake, please update cancel button spellings on the date Time Filter. | 0 | 0 | 0.42 | 0.05
FF-75 - user is able to select the future Dates from the calendar in the filter, kindly restrict selecting future dates. | 0 | 0 | 0 | 0
FF-76 - Export to excel is downloading empty file for Nozzle usage | 0 | 0 | 0.83 | 0.1
FF-77 - There are duplicate tanks named with "Site ID" With all the products in the stock level page | 0 | 0 | 1.17 | 0.15
FF-78 - When user Clicks on the Deliveries page the page loads with a filter error "Please select both From and to date/time | 0 | 0 | 1.33 | 0.17
FF-79 - Kindly remove the Debug Info section from deliveries page. | 0 | 0 | 0.5 | 0.06
FF-80 - kindly remove the floating datatype conversion from tanks column in the deliveries page. | 0 | 0 | 0.67 | 0.08
FF-81 - Product names does not match with the Total Parco "gardenia filling station" Products in Low Stock Page. | 0 | 0 | 1 | 0.12
FF-82 - The Low Stock page is not displaying accurate predictions under the “Product Wise” filter. Please review this issue, and also update the label from “Grade View” to “Product View”, along with updating the product names accordingly. | 0 | 0 | 0 | 0
FF-83 - Bug: Alarms for the Aramco site “COCO-Liberty” are not being displayed. Muhammad Usman Javed has already processed the Aramco site data on the Staging ETL. | 0 | 0 | 2 | 0.25
FF-84 - Kindly finalize which filter will be applicable on the Sales Target page — the first or the second — as discussed. One of the filters was supposed to be removed, but currently both are still visible. | 0 | 0 | 0 | 0
FF-85 - The sales showing in the graph for "SALES and TARGET" GRAPH for the day "30 SEPT" is not matching with the sales data on the production | 0 | 0 | 8 | 1
FF-86 - Day End Sale Summary and Recon again not working as new filter is added previously it was working | 0 | 0 | 0 | 0
FF-87 - Tank Filter is not working for Loss Gain Charts as its showing total sum of deliveries of a single product | 1 | 8 | 2 | 0.25 | 2025-10-16 | 2025-10-16
FF-14 - Production Release | 1 | 8 | 3 | 0.38 | 2025-10-17 | 2025-10-17
FF-8 - Loss/Gain Charts | 3 | 24 | 45 | 5.62 | 2025-09-19 | 2025-09-24
FF-9 - Low Stock Report | 1 | 8 | 42 | 5.25 | 2025-09-28 | 2025-10-05
FF-88 - ZDT on Fintech | 0 | 0 | 0 | 0
FF-89 - Research/URS | 0 | 0 | 0 | 0
FF-90 - Research/DDS | 0 | 0 | 0 | 0
FF-91 - Development | 0 | 0 | 0 | 0
FF-92 - SQA | 0 | 0 | 0 | 0
FF-93 - User Manual | 0 | 0 | 0 | 0
FF-94 - Production Release | 0 | 0 | 0 | 0
MN | 924.95 | 7399.58 | 1196 | 149.5 | 2025-12-17 | 2026-12-31
MN-1 - Omni Chat Onboarding | 75 | 600 | 362 | 45.25 | 2025-12-17 | 2026-02-27
MN-110 - Understanding core OmniChat concepts | 3 | 24 | 24 | 3 | 2026-02-11 | 2026-02-13
MN-112 - MCP server architecture | 1 | 8 | 8 | 1 | 2026-02-11 | 2026-02-11
MN-113 - Import mechanisms. | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
MN-114 - Direct connection model | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
MN-2 - Knowledge Transfer | 0 | 0 | 136 | 17
MN-138 - Yousaf's Onboarding | 8 | 64 | 32 | 4 | 2026-02-16 | 2026-02-27
MN-72 - Ibhrahim's Onboarding | 0 | 0 | 0 | 0
MN-73 - Hamza's Onboarding | 0 | 0 | 0 | 0
MN-74 - Aiza's Onboarding | 0 | 0 | 0 | 0
MN-43 - URS Handover and Work Breakdown Structure | 3 | 24 | 21 | 2.62 | 2026-02-12 | 2026-02-17
MN-44 - Requirement Gathering from URS | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
MN-71 - Meetings and Requirements finalization | 2 | 16 | 13 | 1.62 | 2026-02-17 | 2026-02-18
MN-46 - SQA Knowledge Transfer Recorded Sessions | 10 | 80 | 0 | 0 | 2026-02-13 | 2026-02-20
MN-116 - User Access Setting | 0 | 0 | 0 | 0
MN-137 - Chat Deletion Support | 6 | 48 | 48 | 6
MN-3 - Add the Support to Delete Chats | 3 | 24 | 24 | 3 | 2026-02-16 | 2026-02-18
MN-128 - Delete chats | 2 | 16 | 16 | 2 | 2026-02-16 | 2026-02-17
MN-129 - User testing | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
MN-4 - Chat Deletion Front-End Development | 0 | 0 | 0 | 0
MN-139 - Missing Hierarchy Structure in UM | 2 | 16 | 16 | 2
MN-5 - Missing Hierarchy Structure in UM | 1 | 8 | 8 | 1 | 2026-02-20 | 2026-02-20
MN-130 - Missing Hierarchy Structure in UM | 1 | 8 | 8 | 1 | 2026-02-20 | 2026-02-20
MN-140 - Dataset Import Restrictions | 9 | 72 | 64 | 8 | 2026-03-30 | 2026-04-08
MN-141 - Development | 9 | 72 | 32 | 4 | 2026-03-30 | 2026-04-08
MN-142 - Data Transformations failure | 35 | 280 | 115 | 14.38 | 2026-03-10 | 2026-03-27
MN-144 - Dev | 14 | 112 | 53.5 | 6.69 | 2026-03-10 | 2026-03-27
MN-155 - Development | 14 | 112 | 53.5 | 6.69 | 2026-03-10 | 2026-03-27
MN-147 - Omni Chat Regression | 33 | 264 | 48 | 6 | 2026-01-01 | 2026-12-31
MN-148 - Omni Chat Regression(4/15/2026) | 30 | 240 | 24 | 3 | 2026-04-14 | 2026-05-25
MN-149 - Forgot Password Module Regression | 2 | 16 | 16 | 2 | 2026-04-14 | 2026-04-15
MN-150 - Login Module Regression | 1 | 8 | 8 | 1 | 2026-04-14 | 2026-04-14
MN-151 - System accepts unregistered email and does not display proper error message | 0 | 0 | 0 | 0 | 2026-04-15
MN-152 - Input field does not enforce min/max length constraints | 0 | 0 | 0 | 0 | 2026-04-15
MN-154 - Mismatch in reset link expiration time between application and email | 0 | 0 | 0 | 0 | 2026-04-15
MN-153 - Text Overlap in Graphs (x-axis) | 20.01 | 160.08 | 32 | 4 | 2026-04-16 | 2026-04-22
MN-158 - Development | 8 | 64 | 16 | 2 | 2026-04-16 | 2026-04-27
MN-160 - Graph resizing | 5 | 40 | 16 | 2 | 2026-04-16 | 2026-04-22
MN-159 - SQA | 0.01 | 0.08 | 0 | 0
MN-167 - SQA Handover | 1 | 8 | 0 | 0 | 2026-04-20 | 2026-04-20
MN-168 - Production Release | 1 | 8 | 0 | 0 | 2026-04-22 | 2026-04-22
MN-29 - Auto Dataset Selection | 36 | 288 | 0 | 0 | 2026-04-13 | 2026-05-01
MN-34 - Development | 13 | 104 | 0 | 0 | 2026-04-06 | 2026-04-24
MN-47 - Front-end Changes | 0 | 0 | 0 | 0
MN-48 - Function-App Changes | 0 | 0 | 0 | 0
MN-49 - Open AI Integration and Changes | 0 | 0 | 0 | 0
MN-50 - SQA | 5 | 40 | 0 | 0
MN-30 - Dashboard-level Filtering | 48 | 384 | 0 | 0 | 2026-04-10 | 2026-04-30
MN-145 - SQA Handover | 1 | 8 | 0 | 0 | 2026-04-23 | 2026-04-23
MN-146 - Regression SQA | 0 | 0 | 0 | 0
MN-35 - Development | 4 | 32 | 0 | 0 | 2026-04-10 | 2026-04-22
MN-51 - SQA | 1 | 8 | 0 | 0
MN-52 - User Manual | 3 | 24 | 0 | 0
MN-31 - Team Collaborative Chat (Group Chat) | 90 | 720 | 0 | 0 | 2026-07-01 | 2026-08-26
MN-165 - Production Release | 1 | 8 | 0 | 0 | 2026-08-26 | 2026-08-26
MN-166 - SQA Handover | 1 | 8 | 0 | 0 | 2026-08-17 | 2026-08-17
MN-36 - Development | 34 | 272 | 0 | 0 | 2026-07-01 | 2026-08-13
MN-62 - SQA | 5 | 40 | 0 | 0 | 2026-08-17 | 2026-08-26
MN-63 - User Manual | 5 | 40 | 0 | 0 | 2026-08-17 | 2026-08-26
MN-32 - Advanced Relationships for Multiple Datasets | 98 | 784 | 0 | 0 | 2026-05-19 | 2026-07-07
MN-157 - SQA Handover | 1 | 8 | 0 | 0 | 2026-06-30 | 2026-06-30
MN-37 - Development | 51 | 408 | 0 | 0 | 2026-05-19 | 2026-06-29
MN-60 - SQA | 5 | 40 | 0 | 0 | 2026-06-30 | 2026-07-06
MN-61 - User Manual | 5 | 40 | 0 | 0
MN-33 - Enterprise Communication Channels Support | 120 | 960 | 0 | 0
MN-38 - Development | 50 | 400 | 0 | 0
MN-58 - SQA | 10 | 80 | 0 | 0
MN-59 - Manual | 10 | 80 | 0 | 0
MN-42 - Technical Support | 0 | 0 | 0 | 0
MN-53 - Forgot Password Functionality | 19.25 | 154 | 31 | 3.88 | 2026-02-16 | 2026-03-04
MN-177 - SQA Handover | 0 | 0 | 0 | 0
MN-54 - Development | 5 | 40 | 14.5 | 1.81 | 2026-02-16 | 2026-03-03
MN-156 - Implementation of Forgot Password Module in Omni Chat Application | 0 | 0 | 8 | 1
MN-56 - Password Reset Functionality | 1 | 8 | 6.5 | 0.81 | 2026-03-03 | 2026-03-03
MN-57 - Unit Testing | 0 | 0 | 0 | 0
MN-55 - SQA | 0.12 | 1 | 1 | 0.12 | 2026-03-03 | 2026-03-04
MN-108 - Forgot Password Module is Failing | 0 | 0 | 0 | 0
MN-93 - Testing By M.Abbas | 0.12 | 1 | 1 | 0.12 | 2026-02-24 | 2026-03-04
MN-75 - Panel-level Filtering | 33 | 264 | 0 | 0 | 2026-04-21 | 2026-05-12
MN-161 - Development | 9 | 72 | 0 | 0 | 2026-04-21 | 2026-05-01
MN-162 - SQA Handover | 1 | 8 | 0 | 0 | 2026-05-04 | 2026-05-04
MN-163 - SQA | 0 | 0 | 0 | 0 | 2026-05-04 | 2026-05-12
MN-164 - Production Release | 1 | 8 | 0 | 0 | 2026-05-12 | 2026-05-12
MN-76 - Panel Resizing | 20 | 160 | 0 | 0 | 2026-04-29 | 2026-05-22
MN-173 - Development | 5 | 40 | 0 | 0 | 2026-04-29 | 2026-05-06
MN-174 - SQA Handover | 1 | 8 | 0 | 0 | 2026-05-07 | 2026-05-07
MN-175 - SQA | 0 | 0 | 0 | 0 | 2026-05-07
MN-176 - Production Release | 1 | 8 | 0 | 0 | 2026-05-22 | 2026-05-22
MN-77 - Auto Dashboard Sharing | 27 | 216 | 0 | 0 | 2026-05-04 | 2026-05-22
MN-169 - Development | 5 | 40 | 0 | 0 | 2026-05-04 | 2026-05-15
MN-170 - SQA Handover | 1 | 8 | 0 | 0 | 2026-05-18 | 2026-05-18
MN-171 - SQA | 5 | 40 | 0 | 0 | 2026-05-18 | 2026-05-22
MN-172 - Production Release | 1 | 8 | 0 | 0 | 2026-05-22 | 2026-05-22
MN-78 - OmniChat Bugs Fixing | 131.69 | 1053.5 | 448 | 56 | 2026-01-07 | 2026-03-13
MN-121 - Collaboration with Implementation Team | 1 | 8 | 5 | 0.62 | 2026-03-05 | 2026-03-05
MN-122 - Meeting - March 5, 2026 | 0.25 | 2 | 2 | 0.25
MN-123 - Meeting - March 5, 2026 | 0.25 | 2 | 2 | 0.25 | 2026-03-05 | 2026-03-05
MN-124 - Meeting - March 5, 2026 | 0 | 0 | 0 | 0
MN-125 - Meeting - March 5, 2026 | 0 | 0 | 0 | 0
MN-126 - Meeting - March 5, 2026 | 0.12 | 1 | 1 | 0.12 | 2026-03-05 | 2026-03-05
MN-6 - Frontend Changes | 37 | 296 | 185.5 | 23.19 | 2026-01-07 | 2026-02-24
MN-10 - Keeps loading if you click integrations and no option to stop | 1 | 8 | 8 | 1 | 2026-01-28 | 2026-01-28
MN-11 - Explanations button not working in chat page | 0.12 | 1 | 1 | 0.12 | 2026-01-30 | 2026-01-30
MN-118 - Text adjustment in chat input (Known Bug) | 1 | 8 | 6.5 | 0.81 | 2026-02-27 | 2026-02-27
MN-119 - Keeps loading if you click integrations and no option to stop (Known Bug) | 0.5 | 4 | 2.5 | 0.31 | 2026-03-02 | 2026-03-02
MN-12 - Cant connect tables with spaces in Direct Connection | 1 | 8 | 8 | 1 | 2026-01-27 | 2026-01-27
MN-120 - Cant connect tables with spaces in Direct Connection (Known Bug) | 0.5 | 4 | 4 | 0.5 | 2026-03-02 | 2026-03-02
MN-13 - Background Image changed | 1 | 8 | 7 | 0.88 | 2026-01-19 | 2026-01-19
MN-131 - Explanation button not working (Known bug) | 1 | 8 | 6.5 | 0.81 | 2026-03-04 | 2026-03-04
MN-14 - Chat and icons changed | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
MN-15 - KT session for code | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
MN-16 - Understading of how the code works | 1 | 8 | 8 | 1 | 2026-01-08 | 2026-01-08
MN-17 - Flask and Jinja training | 1 | 8 | 8 | 1 | 2026-01-23 | 2026-01-23
MN-18 - Refactor code structure for improved readability and maintainability | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-03
MN-19 - update SweetAlert2 color scheme to use a green palette | 1 | 8 | 8 | 1 | 2026-02-04 | 2026-02-04
MN-20 - Update and add image assets in static directory | 1 | 8 | 8 | 1 | 2026-02-09 | 2026-02-09
MN-21 - Handled navigation bar in Data and SOPs field for chat mode | 1 | 8 | 4 | 0.5 | 2026-01-29 | 2026-01-29
MN-22 - Edited Feedback Report and Response Report | 0.88 | 7 | 7 | 0.88 | 2026-01-30 | 2026-01-30
MN-23 - Positive Feedback also gets saved to be presented in Feedback Report page | 1 | 8 | 8 | 1 | 2026-02-02 | 2026-02-02
MN-24 - Dark mode and Light mode color changes | 1 | 8 | 8 | 1 | 2026-02-10 | 2026-02-10
MN-25 - Separated navigation items for SOPs and Data | 1 | 8 | 6.5 | 0.81 | 2026-02-19 | 2026-02-19
MN-26 - Enhance UI elements and add keyboard shortcuts for improved user interaction | 0.5 | 4 | 4 | 0.5 | 2026-02-11 | 2026-02-11
MN-27 - Enhance styling for FAQs and VM Manager | 1 | 8 | 6 | 0.75 | 2026-02-13 | 2026-02-13
MN-28 - Enhanced file for Data Warehouse steps | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
MN-7 - Main Logo changed | 1 | 8 | 8 | 1 | 2026-01-14 | 2026-01-14
MN-70 - Password Reset through ACS functionality | 1 | 8 | 8 | 1 | 2026-02-17 | 2026-02-17
MN-8 - LogIn page color scheme altered | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
MN-89 - OmniAgent logo addition | 1 | 8 | 6.5 | 0.81 | 2026-02-20 | 2026-02-20
MN-9 - Text adjustment in chat input | 1 | 8 | 4 | 0.5 | 2026-01-29 | 2026-01-29
MN-86 - OmniChat Front-End Testing | 1 | 8 | 8 | 1 | 2026-03-03 | 2026-03-03
MN-117 - Testing By M.Abbas | 1 | 8 | 8 | 1 | 2026-03-03 | 2026-03-03
MN-95 - Staging Release | 10 | 80 | 25.5 | 3.19 | 2026-02-24 | 2026-03-13
MN-127 - Staging Release | 0 | 0 | 0 | 0
MN-133 - Staging Release Unit Testing | 0.75 | 6 | 4.5 | 0.56 | 2026-03-05 | 2026-03-05
MN-96 - Staging Release | 1.5 | 12 | 12 | 1.5 | 2026-02-23 | 2026-02-24
MN-97 - Staging Release | 0.5 | 4 | 2.5 | 0.31 | 2026-02-24 | 2026-02-24
MN-98 - Staging Release | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-24 | 2026-02-24
MN-99 - SQA Testing | 0 | 0 | 0 | 0
MN-90 - 2FA Alignment | 0 | 0 | 0 | 0
MN-91 - Development | 0 | 0 | 0 | 0
MN-92 - SQA | 0 | 0 | 0 | 0
MN-94 - OmniChat Regression | 122 | 976 | 32 | 4 | 2026-03-02 | 2026-04-10
MN-100 - SQA | 60 | 480 | 16 | 2 | 2026-03-02 | 2026-04-10
MN-104 - LoginPage | 2 | 16 | 16 | 2 | 2026-02-25 | 2026-02-26
MN-106 - Login with Microsoft is Not Working | 0 | 0 | 0 | 0
MN-107 - User Management Module is Not Working | 0 | 0 | 0 | 0
MN-109 - 2FA is Not Implemented for All Users in Omni Chat | 0 | 0 | 0 | 0
MN-111 - Please change the Settings icon to a User Profile button and label it "User Profile. | 0 | 0 | 0 | 0
O2 | 5919.45 | 47355.61 | 42379.06 | 5297.38 | 2025-03-20 | 2026-12-31
O2-10 - Code Reusability in existing Batch/Bpm Jobs | 34.62 | 277 | 536 | 67 | 2026-02-27 | 2026-03-26
O2-19 - Research/DDS | 0 | 0 | 24 | 3
O2-2162 - Initial POC | 3 | 24 | 24 | 3 | 2026-02-27 | 2026-03-03
O2-20 - Development | 0 | 0 | 228 | 28.5
O2-2145 - Changes in BPM Engine | 3 | 24 | 19.5 | 2.44 | 2026-03-02 | 2026-03-05
O2-2146 - Changes in Batch Engine | 3 | 24 | 19.5 | 2.44 | 2026-03-06 | 2026-03-12
O2-2147 - End To End testing | 1.62 | 13 | 13 | 1.62 | 2026-03-13 | 2026-03-16
O2-2151 - UI Changes Batch Trigger | 1 | 8 | 8 | 1 | 2026-02-27 | 2026-02-27
O2-2152 - UI Changes BPM Trigger | 1 | 8 | 8 | 1 | 2026-03-02 | 2026-03-02
O2-2153 - Batch Variable Mapping | 2 | 16 | 16 | 2 | 2026-03-03 | 2026-03-04
O2-2154 - BPM Variable Mapping | 2 | 16 | 16 | 2 | 2026-03-10 | 2026-03-11
O2-2155 - Design and implement SQL tables for BPM/Batch variable mapping | 1 | 8 | 8 | 1 | 2026-03-12 | 2026-03-12
O2-2156 - Unit Testing Frontend | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-24
O2-2157 - Unit Testing Backend | 1 | 8 | 8 | 1 | 2026-03-26 | 2026-03-26
O2-2158 - UI Integrate With API | 4 | 32 | 32 | 4 | 2026-03-13 | 2026-03-18
O2-2163 - BATCH and BPM Trigger Design Changes | 5 | 40 | 40 | 5 | 2026-03-09 | 2026-03-13
O2-2164 - Instance api Development Changes | 2 | 16 | 16 | 2
O2-2165 - Unit Testing | 2 | 16 | 16 | 2 | 2026-03-25 | 2026-03-26
O2-21 - SQA | 0 | 0 | 0 | 0
O2-22 - Production Release | 0 | 0 | 0 | 0
O2-2416 - Bug Fixing | 0 | 0 | 16 | 2
O2-2417 - Republish Job With Updated variable value | 1 | 8 | 8 | 1 | 2026-03-31 | 2026-03-31
O2-2418 - Bug Fixing Batch/Bpm Schedule | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-01
O2-46 - User Manual | 0 | 0 | 0 | 0
O2-1005 - Centrifugal Compressor What-If (Fixed / Variable Speed) | 4 | 32 | 64 | 8
O2-1006 - Design What-If Model (P) | 0 | 0 | 0 | 0
O2-1007 - Development (if required) | 0 | 0 | 0 | 0
O2-1008 - Template, wizards and dashboard design (P) | 0 | 0 | 0 | 0
O2-1009 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-1010 - OC Process testing (P) | 0 | 0 | 32 | 4
O2-1418 - OC Process Testing (P) | 4 | 32 | 32 | 4 | 2026-01-30 | 2026-02-04
O2-1011 - SQA | 0 | 0 | 0 | 0
O2-1012 - User Manual | 0 | 0 | 0 | 0
O2-1013 - Production Release | 0 | 0 | 0 | 0
O2-1014 - Add Training Material (P) | 0 | 0 | 0 | 0
O2-1018 - Cooling Tower What-If | 20.75 | 166 | 92 | 11.5
O2-1019 - Design What-If Model (P) | 15 | 120 | 0 | 0 | 2025-11-03 | 2026-02-13
O2-1020 - Development (if required) | 0 | 0 | 0 | 0
O2-1021 - Template, wizards and dashboard design (P) | 0 | 0 | 8 | 1
O2-1672 - Template, wizards and dashboard design (P) | 1 | 8 | 8 | 1 | 2026-02-25 | 2026-02-27
O2-1022 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-1023 - OC Process testing (P) | 0 | 0 | 38 | 4.75
O2-1432 - OC Process testing (P) | 2.75 | 22 | 22 | 2.75 | 2026-02-02 | 2026-02-06
O2-1835 - OC Process testing (P) | 2 | 16 | 16 | 2 | 2026-01-29 | 2026-01-30
O2-1024 - SQA | 0 | 0 | 0 | 0
O2-1025 - User Manual | 0 | 0 | 0 | 0
O2-1026 - Production Release | 0 | 0 | 0 | 0
O2-1027 - Add Training Material (P) | 0 | 0 | 0 | 0
O2-1028 - Electric Motor - Health | 36.75 | 294 | 540 | 67.5
O2-1029 - Module Design (P) | 0 | 0 | 149 | 18.62
O2-1420 - Module Design Induction (P) | 12 | 96 | 94 | 11.75 | 2026-01-15 | 2026-02-28
O2-1965 - Module Design (P) Review | 0 | 0 | 13 | 1.62
O2-1986 - Module Design Synchronous (P) | 5 | 40 | 40 | 5
O2-1030 - Template (P) | 2 | 16 | 37.5 | 4.69 | 2026-02-09 | 2026-02-20
O2-1673 - Template (P) | 0.88 | 7 | 7 | 0.88 | 2026-02-25 | 2026-02-28
O2-1839 - Template (P) | 1.88 | 15 | 14.5 | 1.81 | 2026-03-09 | 2026-03-25
O2-2569 - Template issues and configuration | 2 | 16 | 16 | 2 | 2026-04-22 | 2026-04-30
O2-1031 - Asset type addition | 0 | 0 | 0 | 0
O2-1032 - OC Process testing (P) | 0 | 0 | 83.5 | 10.44
O2-1762 - Data Prep. & Offline testing | 5 | 40 | 40 | 5 | 2026-03-02 | 2026-03-31
O2-2071 - Data Prep. & Offline testing - Sync Motor | 5 | 40 | 35.5 | 4.44 | 2026-03-27 | 2026-04-30
O2-2617 - Data Prep. & Offline testing - Sync Motor | 3 | 24 | 8 | 1 | 2026-05-01 | 2026-05-22
O2-1033 - SQA | 0 | 0 | 0 | 0
O2-1034 - User Manual | 0 | 0 | 0 | 0
O2-1035 - Production Release | 0 | 0 | 0 | 0
O2-1036 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-1044 - Centrifugal Compressor - Health (Fixed / Variable Speed) | 28.75 | 230 | 308 | 38.5
O2-1045 - Module Design (P) | 10 | 80 | 109 | 13.62 | 2025-12-15 | 2026-02-10
O2-1057 - Finalise Taglist | 0 | 0 | 0 | 0
O2-1422 - Module Design (P) | 10 | 80 | 48 | 6 | 2025-12-15 | 2026-02-10
O2-1897 - Module Design - Fixed Speed (P) | 0 | 0 | 13 | 1.62
O2-1046 - Template (P) | 0 | 0 | 8 | 1
O2-2613 - Variable Speed Compressor Template (P) | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-30
O2-1047 - Asset type addition | 0 | 0 | 0 | 0
O2-1048 - OC Process testing (P) | 0 | 0 | 37 | 4.62
O2-1756 - Create Training data set | 0.5 | 4 | 4 | 0.5
O2-2616 - OC Process Testing RCA | 5 | 40 | 20 | 2.5 | 2026-05-04 | 2026-05-20
O2-2618 - OC process Testing RCA | 0.25 | 2 | 2 | 0.25 | 2026-04-30 | 2026-04-30
O2-2619 - OC Process Testing (P) | 2 | 16 | 11 | 1.38 | 2026-04-28 | 2026-04-30
O2-1049 - SQA | 0 | 0 | 0 | 0
O2-1050 - User Manual | 0 | 0 | 0 | 0
O2-1051 - Production Release | 0 | 0 | 0 | 0
O2-1052 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-1070 - Process Eng. tasks: working, review and management | 59 | 472 | 885 | 110.62
O2-1254 - Process Eng. tasks: working, review and management | 0 | 0 | 442.5 | 55.31
O2-1498 - Process Eng. tasks: working, review and management | 16.88 | 135 | 131 | 16.38 | 2026-01-01 | 2026-01-30
O2-1499 - Process Eng. tasks: working, review and management | 14.25 | 114 | 77 | 9.62 | 2026-02-02 | 2026-02-27
O2-1675 - Process Eng. tasks: working, review and management | 12.88 | 103 | 103 | 12.88 | 2026-03-02 | 2026-03-31
O2-2234 - Process Eng. tasks: working, review and management | 15 | 120 | 119.5 | 14.94 | 2026-04-01 | 2026-04-30
O2-2605 - Process Eng. tasks: working, review and management | 0 | 0 | 12 | 1.5 | 2026-05-01 | 2026-05-29
O2-108 - OC Faster | 173 | 1384 | 1221.06 | 152.63
O2-110 - Research/DDS | 5 | 40 | 8 | 1 | 2025-09-15 | 2025-09-19
O2-111 - Development | 120 | 960 | 216 | 27 | 2025-09-22 | 2025-10-13
O2-224 - Event-based Real-Time Tags | 0 | 0 | 0 | 0 | 2025-09-15 | 2025-10-07
O2-225 - Timer-based Processed Tags | 0 | 0 | 160 | 20 | 2025-09-15 | 2025-10-07
O2-304 - iothub data is stored from iothub as is | 0 | 0 | 0 | 0
O2-112 - SQA | 19 | 152 | 338.53 | 42.32 | 2025-10-14 | 2025-11-04
O2-357 - OCM-Regression | 25 | 200 | 194.5 | 24.31 | 2025-10-21 | 2025-11-11
O2-378 - Deleted Cal Tag Duplicating While we access the dependencies of any type of tag which is used in this cal tag | 0 | 0 | 2.5 | 0.31
O2-379 - Ingestion Format unusual behavior | 0 | 0 | 0 | 0
O2-380 - When user tries to set datapoints using floating values the validation is missing i.e (only numeric values ) | 0 | 0 | 2 | 0.25
O2-381 - User unable to create same name notification group in different SIs. | 0 | 0 | 2 | 0.25
O2-382 - Resource creation ticket for data center specificity is not getting created when the site is created in a data center other than Southeast Asia. | 0 | 0 | 1 | 0.12
O2-383 - Omni Agent Chat responds to queries from other sites even when the user has selected a different site. | 0 | 0 | 0 | 0
O2-384 - Agent returns data when user shares a Read API payload — which is not a valid implementation. | 0 | 0 | 0 | 0
O2-387 - User has created multiple tags from the IoT device using the same source tag. However, the live value is populating for only one tag, while the others are not updating.# | 0 | 0 | 1 | 0.12
O2-388 - While updating the Data Points of a specific site, all other sites are getting system alarms of it. | 0 | 0 | 1 | 0.12
O2-389 - Counter tag latest values are not updating. | 0 | 0 | 1 | 0.12
O2-390 - Timer Tag latest values are not showing | 0 | 0 | 1 | 0.12
O2-391 - Latest values for AHU and variable pump speed performance APX asset are not updating. | 0 | 0 | 1 | 0.12
O2-393 - The GPS tag is not displaying the Longitude and Latitude values — only the Altitude value is being shown. | 0 | 0 | 2.5 | 0.31
O2-429 - Cal tags values are not getting updated | 0 | 0 | 2 | 0.25 | 2025-10-24
O2-431 - Update option is not showing when user open saved trending graph and click on Save as button | 0 | 0 | 0 | 0 | 2025-10-27 | 2025-10-29
O2-432 - Invalid modeled tags count is getting displayed for user Trained anomaly group, Kindly look into it. | 0 | 0 | 1.5 | 0.19 | 2025-10-24
O2-541 - When import data toggle in role management is disabled in edge configuration then it should be restricted from IOT and MQTT establish connection option as well. | 0 | 0 | 0 | 0
O2-542 - GPS latest values for both IOT and MQTT devices are not displaying. | 0 | 0 | 0 | 0
O2-545 - Unable to search real time tag while creating totalizer tag. | 0 | 0 | 6 | 0.75
O2-550 - Latest values for write back and Bulk write are not getting displayed | 0 | 0 | 0 | 0
O2-555 - Repetition is displaying against selected single tag in results of user-trained anomaly. | 0 | 0 | 0 | 0
O2-556 - Real time tag names are not displaying in results of user trained anomaly. | 0 | 0 | 0 | 0
O2-557 - all types of tags values are not getting landed because there are no values for real time tags, kindly look into it. | 0 | 0 | 8.5 | 1.06
O2-558 - GPS listing screen is not loading. | 0 | 0 | 5 | 0.62
O2-559 - All tags are selected in waiting to transfer screen when page record is only set to 50 where as its working fine in import data point screen. | 0 | 0 | 0 | 0
O2-560 - Totalizer Tag creation popup is not closed after tag creation also created tag shows on listing screen after manual refresh | 0 | 0 | 8 | 1 | 2025-11-04 | 2025-11-05
O2-567 - User is able to create Batch/BPM workflow and Batch/BPM Trigger with only numeric characters. It should be Alpha-numeric | 0 | 0 | 4 | 0.5
O2-569 - Create/Edit modal of Real Time and Calculated tag of type Boolean is showing error on Set points field | 0 | 0 | 0 | 0 | 2025-11-04 | 2025-11-04
O2-572 - Selected tags from the fields disappeared when user Edit the Time and Counter Tags | 0 | 0 | 4 | 0.5 | 2025-11-06 | 2025-11-06
O2-576 - BPM Activity Deletion system alarm is not triggering | 0 | 0 | 0 | 0
O2-578 - When the user clicks Save and Publish after executing all and saving the output, an error appears saying "Table is required." However, when the user clicks on End Activity to add a table, the Save button does not appear. | 0 | 0 | 0 | 0
O2-579 - Again Live Values are not getting updated. | 0 | 0 | 0.5 | 0.06 | 2025-11-04
O2-582 - The user changed the subtype of one APX asset, and after importing the file, errors are appearing for all APX assets in the fault file. | 0 | 0 | 0 | 0
O2-583 - Scheduled Raw: Table is created but all log records are fail and no data is available in tables. | 0 | 0 | 1 | 0.12
O2-584 - Export To SQL : Displaying an Invalid error "User is not Authorized" with all failure log results No Data Availability in sql. | 0 | 0 | 1 | 0.12
O2-585 - Schedule Site Hierarchy is displaying success with 0 Effected Rows in Log details but no data or table is created in sql db. | 0 | 0 | 0.5 | 0.06 | 2025-11-04
O2-587 - Batch Monitoring is displaying error instead of results | 0 | 0 | 0 | 0
O2-593 - Statistical Alarms Are not getting triggered, these were configured 3 hours ago | 0 | 0 | 1 | 0.12
O2-596 - Schedule for Stats: Giving FAILURE in logs with 4 effected rows and the message "No data available for this execution". Hence Data is shown in the SQL DB's Table | 0 | 0 | 0 | 0
O2-608 - Add a column named "Tag Type" in the Data Not Landing Alert emails. | 0 | 0 | 8 | 1
O2-614 - Formula Validation API is getting failed , Unable to create Call tag | 0 | 0 | 1 | 0.12
O2-615 - IOT Values are not getting updated again. | 0 | 0 | 0.5 | 0.06
O2-617 - Duplication in Calculated tag | 0 | 0 | 0 | 0
O2-620 - In Enterprise Connectors, the trigger should automatically start upon first-time creation; when the user stops and restarts it, the system should prompt for a new start time in UTC. | 0 | 0 | 8 | 1
O2-621 - Duplicate calculated tags are creating through import site layout. | 0 | 0 | 2 | 0.25
O2-622 - Unknown error occurs during CAL tag creation via Import Site Layout when importing 400–500 tags; resources fail to load (not related to internet connection). | 0 | 0 | 3 | 0.38
O2-627 - Totalizer Calculated tag Live values are not landing where as Calculated tag used in Totalizer condition live values are populating | 0 | 0 | 0 | 0
O2-651 - Circular dependency in formula is present due to which selected formula calculation is not ending where it is applied. | 0 | 0 | 2 | 0.25
O2-652 - UI Disturbed for all dropdowns of Settings | 0 | 0 | 0 | 0
O2-113 - User Manual | 2 | 16 | 40 | 5 | 2025-10-14 | 2025-11-04
O2-242 - How To | 0 | 0 | 40 | 5
O2-114 - Production Release | 2 | 16 | 8 | 1 | 2025-11-04 | 2025-11-07
O2-185 - Production Release | 0 | 0 | 0 | 0
O2-11 - Batch/BPM V6 (SQL) | 0 | 0 | 0 | 0
O2-23 - Research/URS | 0 | 0 | 0 | 0
O2-24 - Research/DDS | 0 | 0 | 0 | 0
O2-25 - Dev | 0 | 0 | 0 | 0
O2-26 - SQA | 0 | 0 | 0 | 0
O2-27 - Production Release | 0 | 0 | 0 | 0
O2-45 - User Manual | 0 | 0 | 0 | 0
O2-1109 - Azure Cost, Reservation, & Subscription Management | 79.81 | 638.5 | 274 | 34.25 | 2026-01-01 | 2026-04-30
O2-1111 - APX: KPIE VM Reservation Exchange | 0.5 | 4 | 4 | 0.5 | 2026-01-27 | 2026-01-27
O2-1385 - Reservation Activity | 1 | 8 | 4 | 0.5 | 2026-01-27 | 2026-01-27
O2-1115 - Staging and Production Database Cleanup | 10 | 80 | 8 | 1 | 2026-01-01 | 2026-02-06
O2-1386 - Kick-off Meeting | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
O2-1116 - VPC: KSA - RFQ Timing and Draft Specifications | 2 | 16 | 4 | 0.5 | 2026-01-27 | 2026-01-29
O2-1387 - Documentation | 2 | 16 | 4 | 0.5 | 2026-01-27 | 2026-01-30
O2-1214 - Demo OmniPetrol Reservation Renewel and Monitoring | 2 | 16 | 20 | 2.5 | 2026-01-30 | 2026-02-06
O2-1579 - Reservation task | 2 | 16 | 16 | 2
O2-1580 - Rservation Renewel | 1 | 8 | 2 | 0.25 | 2026-01-30 | 2026-01-30
O2-1276 - Azure Cost and ASP Utilization Management | 5 | 40 | 8 | 1 | 2026-02-06 | 2026-02-13
O2-1388 - Utilization Management | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-13
O2-1684 - Tapal ETL Redesign by Implementation Team: Monitoring and Reporting | 7 | 56 | 37 | 4.62 | 2026-02-25 | 2026-03-31
O2-1688 - Monitoring and Reporting - February 2026 | 2.44 | 19.5 | 19.5 | 2.44 | 2026-02-25 | 2026-02-27
O2-1768 - Monitoring and Reporting - March 2026 | 2.44 | 19.5 | 17.5 | 2.19 | 2026-03-02 | 2026-03-30
O2-1784 - Read/Write API Bearer Token Client Secret Renewel | 4 | 32 | 29.5 | 3.69 | 2026-03-07 | 2026-03-09
O2-1785 - Read API Client Secrete Bearer Token Regeneration | 0.5 | 4 | 2 | 0.25 | 2026-03-07 | 2026-03-08
O2-1786 - Write API Client Secrete Bearer Token Regeneration | 0.5 | 4 | 2 | 0.25 | 2026-03-07 | 2026-03-08
O2-1787 - SQA Testing | 0 | 0 | 0 | 0
O2-1788 - Read API Validation and Monitoring | 0.75 | 6 | 4 | 0.5 | 2026-03-07 | 2026-03-08
O2-1789 - Write API Validation and Monitoring | 0.25 | 2 | 2 | 0.25
O2-1791 - Key Vault Integration and Updates | 2.44 | 19.5 | 19.5 | 2.44 | 2026-03-09 | 2026-03-11
O2-1990 - Costs review and optimizations | 5 | 40 | 14.5 | 1.81 | 2026-03-16 | 2026-03-27
O2-2505 - Cost Review and Optimizations | 5 | 40 | 14.5 | 1.81 | 2026-03-16 | 2026-03-31
O2-2507 - Azure Region Availability | 2 | 16 | 8 | 1 | 2026-03-30 | 2026-03-31
O2-2509 - Key Vault Integration - March | 1 | 8 | 4 | 0.5 | 2026-03-31 | 2026-03-31
O2-1199 - test | 0 | 0 | 0 | 0
O2-1201 - a | 0 | 0 | 0 | 0
O2-1200 - 1 | 0 | 0 | 0 | 0
O2-1204 - Omni OEE | 0 | 0 | 0 | 0
O2-1205 - URS | 0 | 0 | 0 | 0
O2-1206 - DDS | 0 | 0 | 0 | 0
O2-1207 - Development | 0 | 0 | 0 | 0
O2-1208 - SQA | 0 | 0 | 0 | 0
O2-1209 - User Manual | 0 | 0 | 0 | 0
O2-1210 - Production Release | 0 | 0 | 0 | 0
O2-130 - Read API Enhancement | 157 | 1256 | 1032 | 129 | 2025-11-03 | 2025-12-31
O2-1145 - Code Cleanup | 0 | 0 | 0 | 0
O2-131 - Smart Limit Optimizations | 6 | 48 | 16 | 2 | 2025-09-29 | 2025-10-01
O2-190 - Code Review and Feedback | 0 | 0 | 16 | 2
O2-132 - Custom Tables JSON Schema Retrieval | 10 | 80 | 28 | 3.5 | 2025-09-22 | 2025-09-26
O2-188 - Code Review and Feedback | 0 | 0 | 8 | 1
O2-158 - Edge Metrics Data Retrieval | 3 | 24 | 40 | 5 | 2025-09-29 | 2025-10-01
O2-191 - Discussion and Review | 0 | 0 | 16 | 2
O2-159 - Site Hierarchy Retrieval | 15 | 120 | 28 | 3.5 | 2025-09-22 | 2025-09-26
O2-189 - Code Review and Feedback | 0 | 0 | 8 | 1
O2-170 - SQA | 2 | 16 | 4 | 0.5 | 2025-10-02 | 2025-10-02
O2-171 - Production Release | 1 | 8 | 0 | 0 | 2025-10-03 | 2025-10-03
O2-316 - Enhancements for anomaly detection | 0 | 0 | 56 | 7
O2-577 - Asset Description Retrieval | 10 | 80 | 40 | 5 | 2025-11-03 | 2025-11-14
O2-1485 - Dev Work | 5 | 40 | 40 | 5
O2-727 - Asset Hierarchy Metadata | 0 | 0 | 128 | 16 | 2025-12-01 | 2025-12-08
O2-730 - User Manual - API Guide | 0 | 0 | 40 | 5 | 2025-12-04 | 2025-12-08
O2-804 - Read API Advancements for OC | 0 | 0 | 56 | 7
O2-805 - Alarms Configuration Retrieval | 0 | 0 | 72 | 9
O2-806 - Anomaly Data Configuration | 0 | 0 | 4 | 0.5
O2-856 - User Manual | 2 | 16 | 16 | 2 | 2026-01-07 | 2026-01-09
O2-886 - Read API Anomaly Data Configuration SQA | 3 | 24 | 16 | 2 | 2026-01-14 | 2026-01-16
O2-1302 - OmniOEE (P) | 30.5 | 244 | 301 | 37.62
O2-1375 - OmniOEE Pre-URS working (P) | 10 | 80 | 96.5 | 12.06 | 2026-02-11 | 2026-03-11
O2-1436 - OmniOEE Pre-URS working (P) | 4.88 | 39 | 38.5 | 4.81 | 2026-02-11 | 2026-02-23
O2-1832 - OmniOEE Pre-URS working (P) | 5.88 | 47 | 47 | 5.88 | 2026-03-02 | 2026-03-11
O2-1833 - OmniOEE Pre-URS working (P) | 1.38 | 11 | 11 | 1.38 | 2026-02-18 | 2026-02-27
O2-1855 - OmniOEE URS (P) | 0 | 0 | 54 | 6.75
O2-1871 - OmniOEE URS (P) | 3 | 24 | 18.5 | 2.31 | 2026-03-12 | 2026-03-19
O2-1913 - OmniOEE Method Selection & Formulae Setup (P) | 2 | 16 | 8.5 | 1.06 | 2026-03-17 | 2026-03-31
O2-2098 - OmniOEE Method Selection & Formulae Setup (P) | 3 | 24 | 24 | 3 | 2026-04-06 | 2026-04-30
O2-2621 - OmniOEE Handover Session | 0.38 | 3 | 3 | 0.38 | 2026-04-28 | 2026-04-28
O2-1303 - Heat Exchangers What-If | 9 | 72 | 110 | 13.75
O2-1304 - Design What-If Model (P) | 0 | 0 | 0 | 0
O2-1305 - Development (if required) | 0 | 0 | 0 | 0
O2-1306 - Template, wizards and dashboard design (P) | 2 | 16 | 16 | 2 | 2026-02-12 | 2026-02-12
O2-1425 - Template, wizards and dashboard design (P) | 2 | 16 | 16 | 2 | 2026-02-12 | 2026-02-13
O2-1307 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-1308 - OC Process Testing (P) | 0 | 0 | 39 | 4.88
O2-1414 - OC Process Testing (P) | 5 | 40 | 39 | 4.88
O2-1309 - SQA | 0 | 0 | 0 | 0
O2-1310 - User Manual | 0 | 0 | 0 | 0
O2-1311 - Add Training Material (P) | 0 | 0 | 0 | 0
O2-1318 - OmniOEE | 9 | 72 | 96 | 12
O2-1320 - Development | 0 | 0 | 0 | 0
O2-1321 - SQA | 0 | 0 | 0 | 0
O2-1378 - Research | 6 | 48 | 48 | 6 | 2026-01-28 | 2026-01-30
O2-1752 - Initial Research OEE NO CODE | 3 | 24 | 16 | 2 | 2026-01-28 | 2026-01-30
O2-1753 - Initial Research OEE NO CODE | 0 | 0 | 24 | 3 | 2026-01-28
O2-133 - OC Security - Enhancement and Documentations | 159.81 | 1278.5 | 349 | 43.62 | 2025-10-06 | 2026-04-03
O2-1203 - Baladna Utilities Digitalization Documentation and Diagrams | 2 | 16 | 16 | 2 | 2026-01-29 | 2026-01-30
O2-1390 - Documentation | 1 | 8 | 8 | 1 | 2026-01-29 | 2026-01-29
O2-1391 - Diagram | 1 | 8 | 8 | 1 | 2026-01-30 | 2026-01-30
O2-1219 - Security Architecture and Documentation for Gunvor | 7 | 56 | 42.5 | 5.31 | 2026-02-02 | 2026-03-31
O2-1354 - Security Documentation | 1 | 8 | 8 | 1 | 2026-02-02 | 2026-02-02
O2-1355 - Security Documentation Review and Feedback | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-03
O2-1356 - Security Architecture | 2 | 16 | 16 | 2 | 2026-02-04 | 2026-02-05
O2-1357 - Security Architecture Review and Feedback | 0.5 | 4 | 4 | 0.5 | 2026-02-10 | 2026-02-10
O2-1792 - Fintech Fuel For PGL Leadership - Documentation and Diagram | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-06 | 2026-03-06
O2-136 - Defender for IoT | 10 | 80 | 0 | 0 | 2026-02-23 | 2026-03-06
O2-161 - Azure Front Door | 10 | 80 | 0 | 0 | 2026-03-16 | 2026-03-27
O2-162 - Azure Web Application Firewall | 10 | 80 | 0 | 0 | 2026-03-02 | 2026-03-13
O2-163 - API Management for DDOS Protection | 10 | 80 | 0 | 0 | 2026-03-02 | 2026-03-13
O2-2513 - Audit Report | 0.5 | 4 | 4 | 0.5 | 2026-04-01 | 2026-04-01
O2-254 - Cost Estimation - Defender for Cloud/IOT | 2 | 16 | 8 | 1 |  | 2025-10-17
O2-1486 - Cost Estimation | 1 | 8 | 8 | 1
O2-356 - Documentation | 0 | 0 | 104 | 13 | 2025-09-01 | 2025-11-21
O2-358 - Umair Iftikhar - Quick Security Questions | 0 | 0 | 16 | 2
O2-618 - Product Related Security Documentation | 0 | 0 | 24 | 3
O2-619 - Organization Related Security Documentation | 0 | 0 | 0 | 0
O2-648 - ODL-PD-110 - Identity and Access Management Procedures | 0 | 0 | 64 | 8
O2-1340 - OmniAgent - Multi-agent system | 82.25 | 658 | 873 | 109.12 | 2026-02-02 | 2026-02-28
O2-1341 - Production Release | 1 | 8 | 0 | 0
O2-1342 - Development | 5 | 40 | 162 | 20.25
O2-1346 - Site Configuration Manager API: Tag Catalog | 1 | 8 | 8 | 1 | 2026-02-09 | 2026-02-09
O2-1349 - Site Configuration Manager API: Custom Table Catalog | 0.5 | 4 | 4 | 0.5 | 2026-02-09 | 2026-02-09
O2-1350 - Site Configuration Manager API: Anomaly Catalog | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
O2-1352 - Tag Data Agent | 3 | 24 | 8 | 1 | 2026-02-10 | 2026-02-12
O2-1353 - Custom Table Agent | 1 | 8 | 8 | 1 | 2026-02-10 | 2026-02-12
O2-1583 - Site Configuration Manager: Alarm Catalog | 0.5 | 4 | 4 | 0.5 | 2026-02-16 | 2026-02-16
O2-1584 - Anomaly Data Agent | 2 | 16 | 12 | 1.5 | 2026-02-16 | 2026-02-20
O2-1610 - Alarm Data Agent | 2 | 16 | 36 | 4.5 | 2026-02-20 | 2026-02-26
O2-1854 - Changed Data Analysis API Format | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-06 | 2026-03-06
O2-1869 - Testing the data analysis flow | 0.12 | 1 | 1 | 0.12 | 2026-03-09 | 2026-03-09
O2-1933 - Code Merge + Testing + Deployement to staging | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-17 | 2026-03-17
O2-1949 - Orchestrator Agent | 2 | 16 | 13 | 1.62 | 2026-03-04 | 2026-03-06
O2-2472 - Integration Testing | 0 | 0 | 40.5 | 5.06
O2-2473 - Agent Improvements | 0 | 0 | 6.5 | 0.81
O2-1343 - SQA | 10 | 80 | 150.5 | 18.81 | 2026-03-18 | 2026-03-30
O2-1942 - Testing By Namra march | 5 | 40 | 15.5 | 1.94 | 2026-03-18 | 2026-03-30
O2-1975 - QA Testing (P) | 5 | 40 | 40 | 5 | 2026-03-18 | 2026-03-31
O2-2045 - When querying “how many total areas/assets are in this site (with names)”, the OmniAgent Data Analysis module returns only one area/asset and does not display the complete list or count. | 0 | 0 | 4 | 0.5 | 2026-03-31
O2-2047 - Omni Agent fail to answer this question Which machine experienced the most downtime and how long did it last? | 0 | 0 | 4 | 0.5
O2-2048 - Bug: Instead of devices name omni agent is returning asset names | 0 | 0 | 4 | 0.5 | 2026-03-31
O2-2049 - Bug: Omni Agent showing zero tag incase deadband and persistence | 0 | 0 | 8 | 1
O2-2050 - Bug: Omni Agent is not fetching only acknowledge alarm | 0 | 0 | 3 | 0.38
O2-2051 - Bug: Omni Agent fail to fetch suppress alarms name, and Omni Agent fail to fetch suppress time duration of tag alarm | 0 | 0 | 5 | 0.62 | 2026-03-31
O2-2053 - Incorrect asset types displayed in OmniAgent query response | 0 | 0 | 4 | 0.5 | 2026-03-31
O2-2099 - QA Testing (P) | 5 | 40 | 39 | 4.88 | 2026-04-02 | 2026-04-17
O2-2682 - Testing by Namra April | 2 | 16 | 16 | 2 | 2026-04-01 | 2026-04-02
O2-2686 - Testing by Namra April (2 ) | 1 | 8 | 8 | 1 | 2026-04-13 | 2026-04-13
O2-1344 - Research | 5 | 40 | 32 | 4 | 2026-02-02 | 2026-02-06
O2-1347 - Researching against OpenAI practices | 3 | 24 | 24 | 3 | 2026-02-02 | 2026-02-04
O2-1348 - Researching Documentation | 1 | 8 | 8 | 1 | 2026-02-05 | 2026-02-06
O2-1345 - User Manual | 5 | 40 | 0 | 0
O2-1562 - Read API Support | 1 | 8 | 8 | 1 | 2026-01-09 | 2026-01-09
O2-1563 - Added host in ReadAPI and response format for all tags | 1 | 8 | 8 | 1 | 2026-01-09 | 2026-01-09
O2-1937 - Handover | 0.12 | 1 | 5 | 0.62 | 2026-03-18 | 2026-03-18
O2-1938 - Handover By Namra | 0.12 | 1 | 1 | 0.12 | 2026-03-18 | 2026-03-18
O2-1939 - Handover By Waqar | 0.12 | 1 | 1 | 0.12
O2-1940 - Handover By Zeeshan | 0.12 | 1 | 1 | 0.12
O2-1941 - Handover By Abbas | 0.12 | 1 | 0 | 0
O2-1944 - Handover - Hassan Saeed Wattoo | 0.12 | 1 | 1 | 0.12 | 2026-03-18 | 2026-03-18
O2-1950 - Handover - Hassan Malik | 0.12 | 1 | 1 | 0.12
O2-2022 - Bug Fixing | 0 | 0 | 35 | 4.38
O2-2063 - Deleted chats reappear after navigation or logout in OmniAgent | 0.25 | 2 | 2 | 0.25 | 2026-04-14 | 2026-04-14
O2-2064 - Timer tag value not retrieved; schema error shown instead of value and timestamp | 0 | 0 | 4 | 0.5 | 2026-04-01
O2-2065 - Duplicate information displayed in OmniAgent response (text + scrollable error) | 0 | 0 | 4 | 0.5 | 2026-04-01
O2-2066 - Not showing complete data for all tags and incorrect missing tags list on re-query | 0 | 0 | 8 | 1 | 2026-04-01
O2-2069 - Publish Changes version is not getting updated | 0.25 | 2 | 2 | 0.25 | 2026-04-02 | 2026-04-02
O2-2075 - Duplicate tags created on single tag creation and reflected in Latest Values screen | 0.12 | 1 | 1 | 0.12 | 2026-04-02 | 2026-04-02
O2-2081 - OmniAgent fails to detect configured and fired Statistical Alarms | 0 | 0 | 6 | 0.75 | 2026-04-02
O2-2082 - OmniAgent gets stuck on “Please wait for response” after network interruption and does not recover | 0 | 0 | 8 | 1 | 2026-04-02
O2-2466 - Demo & Presentation | 0 | 0 | 44 | 5.5
O2-1395 - OC Regression 2026 | 134.49 | 1075.92 | 1276.84 | 159.6 | 2026-01-01 | 2026-12-31
O2-1396 - Feb-2026 Release | 0 | 0 | 0 | 0
O2-2025 - SAP Testing (Ticket created by implementation team) | 1 | 8 | 24 | 3 | 2026-03-26 | 2026-03-27
O2-2026 - Testing By Kamran | 2 | 16 | 16 | 2 | 2026-03-26 | 2026-03-27
O2-2040 - End Date is not working on when specified on Trigger while creating a trigger as it does not stopped on the date specified | 0 | 0 | 0 | 0
O2-2041 - validation update in Validate button on entering Complex Query while creating sap HANA and ODBC Connector | 0 | 0 | 0 | 0
O2-2038 - OC_Training To Avanceon | 0.88 | 7 | 3 | 0.38 | 2026-03-30 | 2026-04-03
O2-2039 - Training By Abbas | 0.38 | 3 | 3 | 0.38 | 2026-03-30 | 2026-03-30
O2-2084 - Sanity_Testing_4/3/26(Staging) | 4 | 32 | 70 | 8.75 | 2026-04-03 | 2026-04-03
O2-2085 - Testing By Kamran | 1 | 8 | 18 | 2.25 | 2026-04-03 | 2026-04-03
O2-2086 - Testing By Waqar | 2 | 16 | 16 | 2 | 2026-04-03 | 2026-04-06
O2-2087 - Testing By Namra | 2 | 16 | 16 | 2 | 2026-04-03 | 2026-04-06
O2-2088 - Testing By Abbas | 2 | 16 | 16 | 2 | 2026-04-03 | 2026-04-06
O2-2090 - Latest Values are not populating for real tags on Staging. | 0 | 0 | 0 | 0 | 2026-04-03
O2-2094 - Version is not getting updated again. | 0 | 0 | 0 | 0
O2-2103 - Anomaly Group Model is not getting created. | 0 | 0 | 0 | 0 | 2026-04-06
O2-2117 - “Get Latest Values” Not Working for Single and Bulk Write Back | 0 | 0 | 0 | 0
O2-2118 - Unable to create SAP HANA and ODBC Connector | 0 | 0 | 0 | 0
O2-2119 - Diagnostics Email Alerts Are Not Being Received | 0 | 0 | 0 | 0
O2-2120 - Data center Specified module failed on staging | 0 | 0 | 0 | 0
O2-2121 - Asset and Real , Manual and Cal tags are getting duplicated, while we create Asset Built In, and double click on the save button | 0 | 0 | 0 | 0 | 2026-04-06
O2-2127 - Anomaly Group results are not getting displayed | 0 | 0 | 4 | 0.5 | 2026-04-06
O2-2132 - Unable to verify phone number using SMS OPT-IN feature | 0 | 0 | 0 | 0
O2-2133 - MQTT Default Simulator for Ingestion Transfection is getting closed with this error , right after running it. | 0 | 0 | 0 | 0
O2-2134 - EMAIL Alerts for alarms notifications are not triggering | 0 | 0 | 0 | 0
O2-2137 - Sanity_Testing_4/7/26(Prod Green) | 4 | 32 | 97.17 | 12.15 | 2026-04-07 | 2026-04-07
O2-2138 - Testing By Kamran | 1 | 8 | 16 | 2 | 2026-04-07 | 2026-04-07
O2-2139 - Testing By Waqar | 1.88 | 15 | 15 | 1.88 | 2026-04-07 | 2026-04-08
O2-2140 - Testing By Namra | 1 | 8 | 16 | 2 | 2026-04-07 | 2026-04-07
O2-2141 - Testing By M.Abbas | 1.75 | 14 | 14 | 1.75 | 2026-04-07 | 2026-04-07
O2-2150 - Latest Values are not getting populated (Green Production) | 0 | 0 | 0 | 0 | 2026-04-07
O2-2159 - Data center module fail on prod green env | 0 | 0 | 0 | 0
O2-2160 - Unable to create Enterprise Connectors on Production (Green). The issue was recently fixed on the staging environment but the fix has not yet been deployed to production. | 0 | 0 | 0 | 0
O2-2161 - Request A Format For Ingestion Transformation is not getting created, Showing this error. | 1 | 8 | 8 | 1 | 2026-04-07
O2-2169 - “Get Latest Values” Not Working for Single and Bulk Write Back | 0 | 0 | 0 | 0
O2-2170 - Site Changes Refresh button is not working. as its not showing newly created Real tag even after clicking on refresh button. Prod green | 0 | 0 | 4 | 0.5 | 2026-04-08
O2-2174 - Schedule Scanning not Woking for Digital LOG Device | 0.5 | 4 | 8 | 1 | 2026-04-08 | 2026-04-09
O2-2175 - Publish Changes version is not getting updated Again (Production Green) | 1 | 8 | 8 | 1 | 2026-04-09 | 2026-04-09
O2-2176 - Application is getting logout While we Create model for Anomaly group. | 0 | 0 | 0 | 0 | 2026-04-08
O2-2180 - Data Alarms and Stats Alarms are configured and getting fired, but OmniAgent is not Showing records. | 0 | 0 | 8 | 1
O2-2181 - Real Time tags are getting Duplicated while we create from Wizard | 0.02 | 0.17 | 0.17 | 0.02
O2-2212 - APX Asset Creation – Next Button Creates Tag but Does Not Navigate, Causes Duplication Error on Re-click | 0 | 0 | 0 | 0
O2-2217 - Sanity_Testing_4/9/26(Prod Blue) | 4 | 32 | 61 | 7.62 | 2026-04-09 | 2026-04-09
O2-2218 - Testing By Kamran | 1 | 8 | 17 | 2.12 | 2026-04-09 | 2026-04-09
O2-2220 - Testing By Namra | 1 | 8 | 16 | 2 | 2026-04-09 | 2026-04-09
O2-2221 - Testing By Abbas | 2 | 16 | 16 | 2 | 2026-04-09 | 2026-04-09
O2-2226 - Values are not populating for newly created sites, Second time In a day, and we will be creating all the site third time now | 0 | 0 | 0 | 0 | 2026-04-09
O2-2227 - Unable to Create connectors | 0 | 0 | 0 | 0
O2-2231 - “Get Latest Values” Not Working for Single and Bulk Write Back | 0 | 0 | 0 | 0
O2-2232 - Testing By Waqar | 1 | 8 | 8 | 1 | 2026-04-09 | 2026-04-09
O2-2233 - Anomaly Group Results are not getting displayed | 0 | 0 | 0 | 0 | 2026-04-09
O2-2236 - Failed to refresh with button and we cant proceed with OmniAgent Testing Prod Blue | 0 | 0 | 4 | 0.5
O2-2238 - State Duplication in Data Alarms for Totalizer Tags | 0 | 0 | 0 | 0
O2-2448 - Sanity_Testing_4/21/26(Staging) | 3 | 24 | 106.25 | 13.28 | 2026-04-21 | 2026-04-22
O2-2449 - Testing by kamran | 3 | 24 | 19 | 2.38 | 2026-04-21 | 2026-04-23
O2-2450 - Testing by Waqar | 3 | 24 | 24 | 3 | 2026-04-22 | 2026-04-24
O2-2451 - Diagnostics Alarm Not Triggered Despite No Latest Values Since 10:55 | 1 | 8 | 8 | 1 | 2026-04-22 | 2026-04-23
O2-2452 - Data center Specified module failed on staging | 0.12 | 1 | 1 | 0.12
O2-2455 - “Get Latest Values” Not Working for Single and Bulk Write Back | 0 | 0 | 0 | 0
O2-2457 - State duplication occurred in Totalizer tags Alarms | 0 | 0 | 0 | 0
O2-2458 - Unable to Verify Phone number for SMS alerts | 0.25 | 2 | 0 | 0
O2-2459 - Diagnostics Email Alerts Are Not Being Received | 0 | 0 | 0 | 0
O2-2460 - Scheduled scanning is unable to retrieve new parameters in the case of Digital Log. Additionally, on multiple scan triggers, it is duplicating the newly added parameters. | 0.5 | 4 | 4 | 0.5
O2-2488 - Testing By M.Abbas | 2 | 16 | 16 | 2 | 2026-04-23 | 2026-04-24
O2-2489 - Testing By Zeeshan | 1 | 8 | 32 | 4 | 2026-04-24 | 2026-04-24
O2-2548 - Real-time tag latest values are not populating for any device type on the newly created site. | 0 | 0 | 0 | 0
O2-2687 - Testing by Waqar 28 April | 0.28 | 2.25 | 2.25 | 0.28 | 2026-04-28 | 2026-04-28
O2-2574 - Sanity_Testing_4/30/26(Prod Green) | 5 | 40 | 133 | 16.62 | 2026-04-30 | 2026-05-04
O2-2575 - Testing By Namra ( April 30 ) | 1.5 | 12 | 8 | 1 | 2026-04-30 | 2026-04-30
O2-2576 - Testing By Kamran April | 1 | 8 | 8 | 1 | 2026-04-30 | 2026-04-30
O2-2577 - Testing By Zeeshan April | 1.5 | 12 | 8 | 1 | 2026-04-30 | 2026-05-04
O2-2578 - Testing By Waqar (April) | 1 | 8 | 8 | 1 | 2026-04-30 | 2026-04-30
O2-2579 - Testing By M.Abbas Apirl | 1.5 | 12 | 8 | 1 | 2026-04-30 | 2026-05-30
O2-2582 - Live values of real/ cal tags are not getting populated. | 1 | 8 | 8 | 1 | 2026-04-30 | 2026-05-01
O2-2583 - “Get Latest Values” Not Working for Single and Bulk Write Back | 0 | 0 | 0 | 0
O2-2584 - Model is not getting created for Anomaly Group | 0.25 | 2 | 2 | 0.25 | 2026-04-30
O2-2585 - Unable to verify number for SMS_OPT_IN | 0 | 0 | 0 | 0
O2-2586 - SQL pipelines are getting displayed with triggers in monitoring logs | 0 | 0 | 0 | 0
O2-2587 - Invalid Critical Errors are getting displayed of un-authorization and Read API Issue of Customer and site not found, In logs. | 0 | 0 | 0 | 0
O2-2596 - NO Values for these tags Calculated, Timer, Counter, Totalizer Real, Totalizer Cal. With New Site. Only Real and GPS values are here. | 0 | 0 | 0 | 0
O2-2600 - The System Alarms need to be updated in the green environment to align with the staging environment. | 0.19 | 1.5 | 1.5 | 0.19
O2-2601 - The SQL has failed again. No data is being displayed in the logs or in the SQL database tables. Please investigate and resolve the issue. | 0 | 0 | 0 | 0
O2-2602 - An issue has been observed where state duplication occurs along with multiple states being triggered at the same timestamp for a single tag. This results in conflicting state entries and inconsistent system behavior | 0 | 0 | 0 | 0
O2-2603 - The Watchdog module is missing in the Docker deployment on Green Production. Due to this, critical metrics including Upload Speed, Download Speed, and OPC Server metrics are not being populated in the system. | 0 | 0 | 0 | 0
O2-2606 - Email Notifications are not getting received as alarms are triggering | 0 | 0 | 0 | 0
O2-2610 - The Run On Demand popup for Batch and BPM jobs is behaving incorrectly across environments | 0 | 0 | 0 | 0
O2-2612 - Duplicated real tags Bug Reproduced again, Kindly Check | 0 | 0 | 0 | 0
O2-2614 - Omni Agent Invalid response: Show my Assets with asset type and asset names | 0 | 0 | 0 | 0
O2-2615 - Tooltip Spacing Issue on Green Prod Compared to Prod Blue | 0 | 0 | 0 | 0
O2-2680 - Testing By Namra- May ( 4, 5 ) | 2 | 16 | 16 | 2 | 2026-05-04 | 2026-05-05
O2-2681 - Testing By M.Abbas May | 2 | 16 | 16 | 2 | 2026-05-04 | 2026-05-05
O2-2683 - Testing By Zeeshan May | 0 | 0 | 17.5 | 2.19
O2-2684 - Testing By Kamran May | 2 | 16 | 16 | 2 | 2026-05-04 | 2026-05-05
O2-2685 - Testing By Waqar (May) | 2 | 16 | 16 | 2 | 2026-05-04 | 2026-05-05
O2-2627 - Sanity_Testing_5/5/26(Prod Blue) | 5 | 40 | 72 | 9 | 2026-05-06 | 2026-05-06
O2-2628 - Testing By Kamran | 1 | 8 | 8 | 1 | 2026-05-06 | 2026-05-06
O2-2629 - Testing By Waqar | 2 | 16 | 16 | 2 | 2026-05-06 | 2026-05-07
O2-2630 - Testing By Zeeshan | 1 | 8 | 16 | 2 | 2026-05-06 | 2026-05-06
O2-2631 - Testing By Namra | 1 | 8 | 24 | 3 | 2026-05-06 | 2026-05-06
O2-2632 - Testing By M.Abbas | 1 | 8 | 8 | 1 | 2026-05-06 | 2026-05-06
O2-2633 - CRITICAL: False alarms triggered for Boolean tag — TRUE-configured alarm firing on FALSE state and condition set by default & not editable | 0 | 0 | 0 | 0
O2-2634 - Read API fail to fetch False Alarm against Boolean tag | 0 | 0 | 0 | 0
O2-2635 - Different Alarm states are triggering for a single totalizer Tag on same timestamp | 0 | 0 | 0 | 0
O2-2636 - Anomaly Group Results screen is displaying Error | 0 | 0 | 0 | 0
O2-2637 - Omni Agent displays False results in response. | 0 | 0 | 0 | 0
O2-2638 - Invalid response for assets types again | 0 | 0 | 0 | 0
O2-2639 - OC_Known_Issues | 0 | 0 | 0 | 0
O2-2640 - Extra Space Displayed Between Tooltip Icon and Tooltip Popup | 0 | 0 | 0 | 0
O2-2641 - Different Alarm states are triggering for a single totalizer Tag on same timestamp | 0 | 0 | 0 | 0
O2-2642 - An issue has been observed where state duplication occurs along with multiple states being triggered at the same timestamp for a single tag. This results in conflicting state entries and inconsistent system behavior | 0 | 0 | 0 | 0
O2-2643 - Email Notifications are not getting received as alarms are triggering from "alerts@octopusdtl.com" account | 0 | 0 | 0 | 0
O2-2644 - The Watchdog module is missing in the Docker deployment on Green Production. Due to this, critical metrics including Upload Speed, Download Speed, and OPC Server metrics are not being populated in the system. | 0 | 0 | 0 | 0
O2-2645 - Table Conflict Detected popup appears when user tries to publish a BPM job in a new site. | 0 | 0 | 0 | 0
O2-2646 - when user selects an existing table while creating a BPM job an error occurs that "NO publish Columns Found in the request" | 0 | 0 | 0 | 0
O2-2648 - Totalizer_Landing_Pattern_Testing | 5 | 40 | 32 | 4 | 2026-05-07 | 2026-05-11
O2-2649 - Testing By M.Abbas | 5 | 40 | 32 | 4 | 2026-05-07 | 2026-05-11
O2-2678 - Latest values of All Calculated tags are not populating on newly created site after deployment | 0 | 0 | 0 | 0
O2-2706 - Regression_Testing_18/5/26 | 21 | 168 | 80 | 10 | 2026-05-18 | 2026-05-26
O2-2707 - Testing By M.Abbas | 7 | 56 | 0 | 0 | 2026-05-18 | 2026-05-26
O2-2708 - Testing By Zeeshan | 7 | 56 | 0 | 0 | 2026-05-18 | 2026-05-26
O2-2709 - Testing By Waqar | 7 | 56 | 0 | 0 | 2026-05-18 | 2026-05-26
O2-2844 - Digital Twin models are not creating against variable speed health asset from almost half an hour. | 0 | 0 | 0 | 0
O2-1453 - Read API - Handling Deleted Sites | 19 | 152 | 96 | 12 | 2026-02-17 | 2026-02-24
O2-1500 - Development | 3 | 24 | 29 | 3.62 | 2026-02-17 | 2026-02-23
O2-1544 - Handling API Calls for Deleted Sites | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
O2-1564 - Read API is Returning internal server error after latest deployment | 0.12 | 1 | 1 | 0.12 | 2026-02-23 | 2026-02-23
O2-1574 - Incase of Real-Stat Read API is returning R-Mapped name instead of user-friendly name even user-friendly parameter is set to true | 0 | 0 | 0 | 0
O2-1582 - Unauthorized Tag Data Accessible via Read API | 0.5 | 4 | 4 | 0.5 | 2026-02-24 | 2026-02-24
O2-1592 - Deleted Sites' Record | 2 | 16 | 16 | 2 | 2026-02-17 | 2026-02-18
O2-1501 - SQA | 2 | 16 | 16 | 2 | 2026-02-23 | 2026-02-25
O2-1554 - Testing By M.Abbas | 2 | 16 | 16 | 2 | 2026-02-23 | 2026-02-25
O2-1560 - Production Release | 1 | 8 | 3 | 0.38 | 2026-02-25 | 2026-02-25
O2-1561 - Testing By M.Abbas | 0.12 | 1 | 1 | 0.12 | 2026-02-25 | 2026-02-25
O2-1609 - Deployment to Production and Unit Testing | 0.25 | 2 | 2 | 0.25 | 2026-02-25 | 2026-02-25
O2-1459 - OC Security - Defender for Cloud | 14 | 112 | 64 | 8
O2-135 - Defender for Cloud | 5 | 40 | 32 | 4 | 2026-02-02 | 2026-02-27
O2-616 - Storage Accounts Deletion - 2025 | 4 | 32 | 32 | 4 | 2025-11-01 | 2025-11-25
O2-1460 - OC Security - Azure Key Vault Integration | 138.88 | 1111 | 632 | 79
O2-134 - Key Vault Integration | 110 | 880 | 308 | 38.5 | 2025-10-06 | 2025-11-14
O2-1389 - Key Vault Setup and Integration | 15 | 120 | 88 | 11 | 2025-10-01 | 2025-11-28
O2-206 - Moving Read API Configurations to Environment Variables | 0 | 0 | 40 | 5
O2-207 - Moving Configurations to Environment Variables | 0 | 0 | 8 | 1
O2-208 - Moving Configurations to Environment Variables | 0 | 0 | 8 | 1
O2-209 - Moving Configurations to Environment Variables | 0 | 0 | 16 | 2
O2-210 - Moving Configurations to Environment Variables | 0 | 0 | 8 | 1
O2-211 - Moving Configurations to Environment Variables | 0 | 0 | 8 | 1
O2-212 - Moving Configurations to Environment Variables | 0 | 0 | 8 | 1
O2-213 - Moving Configurations to Environment Variables | 0 | 0 | 48 | 6
O2-214 - Moving Configurations to Environment Variables | 0 | 0 | 8 | 1
O2-215 - usamaMoving Configurations to Environment Variables | 0 | 0 | 0 | 0
O2-216 - Trigger API | 0 | 0 | 16 | 2
O2-300 - Logic App Integration | 0 | 0 | 0 | 0
O2-301 - Data Factory Integration | 0 | 0 | 0 | 0
O2-302 - IoT Hub Integration | 0 | 0 | 0 | 0
O2-440 - Analyzing KeyVault integration in OC | 0 | 0 | 14 | 1.75 | 2025-10-27
O2-638 - Key Vault Integration in OC | 0 | 0 | 29 | 3.62
O2-689 - Moving all Web Appsettings and Function Apps secrets in Production Green to Key Vault | 0 | 0 | 9 | 1.12
O2-253 - Cost Estimation - Key Vault | 1 | 8 | 8 | 1 | 2025-10-13 | 2025-10-17
O2-1487 - Estimation | 1 | 8 | 8 | 1
O2-255 - Change Password for Production SQL | 11.88 | 95 | 0 | 0 | 2025-12-01 | 2025-12-05
O2-1461 - OmniChat Integration with OmniAgent | 166 | 1328 | 721 | 90.12 | 2026-02-23 | 2026-05-04
O2-1462 - DDS | 4 | 32 | 42 | 5.25 | 2026-02-23 | 2026-02-26
O2-1503 - OmniChat Integration with OmniAgent DDS - Hamza Ali | 2 | 16 | 32 | 4 | 2026-02-23 | 2026-02-26
O2-1504 - OmniChat Integration with OmniAgent DDS - Aiza Hamid | 2 | 16 | 10 | 1.25 | 2026-02-25 | 2026-02-26
O2-1469 - SQA | 5 | 40 | 16 | 2 | 2026-03-17 | 2026-03-24
O2-1510 - SQA | 5 | 40 | 16 | 2 | 2026-03-17 | 2026-03-23
O2-1470 - User Manual | 3 | 24 | 0 | 0 | 2026-03-17 | 2026-03-24
O2-1511 - Documentation Task | 0 | 0 | 0 | 0
O2-1472 - Development | 33 | 264 | 302.5 | 37.81 | 2026-02-26 | 2026-04-17
O2-1473 - RBAC for OmniChat (aligned with OmniConnect/ReadAPI) | 3 | 24 | 0 | 0 | 2026-03-12 | 2026-03-16
O2-1474 - OmniChat Database Changes to save OmniAgent Conversation | 4 | 32 | 0 | 0 | 2026-03-09 | 2026-03-12
O2-1475 - OmniAgent Payload Support for Clean Response - Part B | 2 | 16 | 0 | 0 | 2026-03-12 | 2026-03-13
O2-1476 - OmniAgent Payload Support for Clean Response - Part A | 3 | 24 | 0 | 0 | 2026-03-02 | 2026-03-04
O2-1478 - OmniAgent Database Changes to save OmniChat Conversations | 4 | 32 | 0 | 0 | 2026-03-05 | 2026-03-10
O2-1479 - Front-end Development - Chat window modifications | 2 | 16 | 0 | 0 | 2026-02-26 | 2026-02-27
O2-1480 - Front-end Development - OmniAgent Button | 8 | 64 | 0 | 0 | 2026-03-02 | 2026-03-10
O2-1481 - Back-end Integration - Part A | 2 | 16 | 8 | 1 | 2026-02-26 | 2026-02-27
O2-1482 - Back-end Integration - Part B | 9 | 72 | 59.5 | 7.44 | 2026-03-16 | 2026-03-31
O2-1834 - User Management for Omni Connect through Omni Agent | 2 | 16 | 13 | 1.62 | 2026-03-06 | 2026-03-09
O2-1932 - Meetings and Discussions | 1.62 | 13 | 13 | 1.62 | 2026-03-11 | 2026-03-13
O2-1962 - SQL/Databse Layers including SPs | 4.06 | 32.5 | 32.5 | 4.06 | 2026-03-02 | 2026-03-06
O2-1963 - Backend Endpoints OmniChat | 4.06 | 32.5 | 32.5 | 4.06 | 2026-03-09 | 2026-03-13
O2-1964 - Metadata Linkage for Integration | 0 | 0 | 0 | 0
O2-2564 - Support for Omniagent Charting (AMcharts) | 6 | 48 | 48 | 6 | 2026-04-20 | 2026-04-27
O2-2565 - Sync Site configuration Button and API integration | 5 | 40 | 40 | 5 | 2026-04-13 | 2026-04-17
O2-2566 - Back-end Integration- Part C | 10 | 80 | 56 | 7 | 2026-04-01 | 2026-04-10
O2-2567 - Code Merge (OmniAgent Feature and Prod) | 0 | 0 | 0 | 0
O2-1506 - Production Release | 4 | 32 | 0 | 0 | 2026-04-30 | 2026-05-01
O2-1507 - Production Release - Hamza Ali | 2 | 16 | 0 | 0 | 2026-03-25 | 2026-03-26
O2-1508 - Production Release - Aiza Hamid | 2 | 16 | 0 | 0 | 2026-03-25 | 2026-03-26
O2-1509 - Production Release - Ibrahim A. Qureshi | 2 | 16 | 0 | 0 | 2026-03-25 | 2026-03-26
O2-1512 - Production Release Testing - Abbas | 3 | 24 | 0 | 0 | 2026-03-24 | 2026-03-26
O2-1513 - Production Release - Taimur | 0 | 0 | 0 | 0
O2-1514 - Production Release Testing - Kamran | 0 | 0 | 0 | 0
O2-2224 - SQA Handover | 0.25 | 2 | 0 | 0 | 2026-04-20 | 2026-04-20
O2-2225 - Regression SQA | 3 | 24 | 0 | 0
O2-2660 - Bug Fixing | 0 | 0 | 0 | 0
O2-2661 - BLOCKER: OmniConnect–OmniChat Integration Failed: Newly Created Customers/Sites Not Synced to OmniChat | 0 | 0 | 0 | 0
O2-2672 - Blocker in Forgot Password Module – Registered User is Unable to Receive Password Reset Email | 0 | 0 | 0 | 0
O2-2677 - Critical Blocker : Authentication Failure – Users Unable to Login Due to Missing 2FA Verification Email | 0 | 0 | 0 | 0
O2-151 - OmniAgent Phase 2.0 | 72 | 576 | 192 | 24
O2-152 - Development | 20 | 160 | 0 | 0 | 2025-09-22 | 2025-10-03
O2-153 - SQA | 9 | 72 | 0 | 0 | 2025-10-06 | 2025-10-16
O2-154 - User Manual | 22 | 176 | 24 | 3 | 2025-10-06 | 2025-10-16
O2-176 - How to | 0 | 0 | 16 | 2
O2-177 - Fields | 0 | 0 | 0 | 0
O2-376 - Read AI Update for Device Diagnostics | 0 | 0 | 8 | 1
O2-155 - Production Release | 1 | 8 | 8 | 1 | 2025-10-17 | 2025-10-17
O2-56 - Development | 20 | 160 | 0 | 0 | 2025-10-06 | 2025-10-17
O2-1521 - Read API - Nanosecond Support | 2.25 | 18 | 18 | 2.25
O2-1133 - Development | 1 | 8 | 8 | 1 | 2026-01-01 | 2026-01-01
O2-1542 - Added support for nanoseconds and micro seconds in timestamps (start and end timestamps) | 1 | 8 | 8 | 1 | 2026-01-01 | 2026-01-01
O2-1522 - SQA | 0.12 | 1 | 1 | 0.12 | 2026-01-15 | 2026-01-15
O2-1557 - Testing By M.Abbas | 0.12 | 1 | 1 | 0.12 | 2026-01-15 | 2026-01-15
O2-1523 - Read API - Support for Long and Wide Response Layouts | 2.5 | 20 | 20 | 2.5
O2-1134 - Dev | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-06
O2-1541 - Added support for wide and long response layouts | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-06
O2-1524 - SQA | 0.25 | 2 | 2 | 0.25 | 2026-02-04 | 2026-02-04
O2-1559 - Testing By Abbas | 0.25 | 2 | 2 | 0.25 | 2026-02-04 | 2026-02-04
O2-1525 - Read API - Query Optimisation | 11.15 | 89.17 | 84 | 10.5 | 2026-01-02 | 2026-01-23
O2-1532 - Development | 4.75 | 38 | 40 | 5 | 2026-01-02 | 2026-01-16
O2-1533 - Optimized queries for Read API | 1 | 8 | 8 | 1 | 2026-01-02 | 2026-01-02
O2-1534 - Updated stored procedure for hierarchies | 1 | 8 | 8 | 1 | 2026-01-05 | 2026-01-05
O2-1536 - Updated custom table schemas query to add description | 1 | 8 | 8 | 1 | 2026-01-06 | 2026-01-06
O2-1539 - Read API ADX Query Optimization | 1 | 8 | 8 | 1 | 2026-01-13 | 2026-01-13
O2-1565 - Code Refactoring | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
O2-1540 - SQA | 0.12 | 1 | 1 | 0.12 | 2026-01-19 | 2026-01-19
O2-1558 - Testing By Abbas | 0.12 | 1 | 1 | 0.12 | 2026-01-19 | 2026-01-19
O2-1566 - Production Release | 1 | 8 | 1 | 0.12 | 2026-01-19 | 2026-01-19
O2-1567 - Dev | 0.12 | 1 | 1 | 0.12 | 2026-01-19 | 2026-01-19
O2-1568 - SQA | 0 | 0 | 0 | 0
O2-1545 - APX Health multiple asset configuration | 9.62 | 77 | 52 | 6.5 | 2026-02-23 | 2026-02-24
O2-1546 - APX Health multiple asset configuration | 2 | 16 | 26 | 3.25 | 2026-02-23 | 2026-02-24
O2-1547 - APX Health multiple asset configuration (ADE) | 1.62 | 13 | 13 | 1.62 | 2026-02-23 | 2026-02-24
O2-1548 - APX Health multiple asset configuration (APXE) | 2 | 16 | 13 | 1.62 | 2026-02-23 | 2026-02-24
O2-1551 - Process Testing (P) | 0 | 0 | 0 | 0
O2-1552 - Process Testing (P) | 2 | 16 | 0 | 0 | 2026-02-23 | 2026-02-25
O2-1595 - Process Team Sales / marketing Tasks | 14.75 | 118 | 148 | 18.5
O2-1596 - Process Team Sales / marketing Tasks | 2 | 16 | 16 | 2 | 2026-01-01 | 2026-01-30
O2-1597 - Ashghal demo support | 2 | 16 | 16 | 2 | 2026-01-19 | 2026-01-20
O2-1598 - Process Team Sales / marketing Tasks | 3.5 | 28 | 28 | 3.5 | 2026-02-02 | 2026-02-27
O2-1599 - Marketing team support for APX | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-04
O2-1600 - Health module marketing video update | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
O2-1601 - MPCL ADE demo support | 1.25 | 10 | 10 | 1.25 | 2026-02-05 | 2026-02-27
O2-1602 - MPCL data review for demo | 0.25 | 2 | 2 | 0.25 | 2026-02-04 | 2026-02-05
O2-2368 - Process Team Sales / marketing Tasks | 0 | 0 | 30 | 3.75
O2-2369 - PPX marketing presentation for gas processing plant | 3.75 | 30 | 30 | 3.75 | 2026-04-15 | 2026-04-23
O2-1621 - OmniEMS pre-URS working (P) | 0 | 0 | 49 | 6.12
O2-1622 - OmniEMS pre-URS working (P) | 0 | 0 | 24.5 | 3.06
O2-1623 - OmniEMS pre-URS working (P) | 0 | 0 | 24.5 | 3.06
O2-1625 - Ingestion Time-based Data Alarms | 25 | 200 | 0 | 0
O2-1626 - Dev | 0 | 0 | 0 | 0
O2-1627 - SQA | 0 | 0 | 0 | 0
O2-1628 - User Manual | 0 | 0 | 0 | 0
O2-1633 - Read API Support | 0 | 0 | 0 | 0
O2-164 - Trigger API | 50 | 400 | 152 | 19 | 2025-09-19 | 2025-10-17
O2-165 - Authentication and Authorization | 5 | 40 | 24 | 3 | 2025-09-22 | 2025-09-26
O2-1488 - Authentication and Authorization Tasks | 3 | 24 | 24 | 3
O2-166 - Pipeline Scheduling | 6 | 48 | 16 | 2 | 2025-09-29 | 2025-10-06
O2-197 - Code Review and Feedback | 0 | 0 | 4 | 0.5
O2-167 - Pipeline Status | 6 | 48 | 16 | 2 | 2025-09-29 | 2025-10-06
O2-198 - Code Review and Feedback | 0 | 0 | 4 | 0.5
O2-168 - SQA | 2 | 16 | 4 | 0.5 | 2025-10-07 | 2025-10-07
O2-169 - Production Release | 1 | 8 | 0 | 0 | 2025-10-08 | 2025-10-08
O2-178 - User Manual | 2 | 16 | 16 | 2 | 2025-10-07 | 2025-10-07
O2-179 - API Documentation | 0 | 0 | 16 | 2
O2-1654 - Steam Surface Condenser What-If | 3 | 24 | 48 | 6
O2-1656 - Design What-If Model (P) | 0 | 0 | 0 | 0
O2-1657 - Development (if required) | 0 | 0 | 0 | 0
O2-1658 - Template, wizards and dashboard design (P) | 0 | 0 | 0 | 0
O2-1659 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-1660 - OC Process testing (P) | 3 | 24 | 24 | 3
O2-1661 - SQA | 0 | 0 | 0 | 0
O2-1662 - User Manual | 0 | 0 | 0 | 0
O2-1663 - Production Release | 0 | 0 | 0 | 0
O2-1664 - Add Training Material (P) | 0 | 0 | 0 | 0
O2-1755 - SQA | 67.25 | 538 | 164 | 20.5 | 2026-01-01 | 2026-12-31
O2-1967 - SQA OmniConnect | 9 | 72 | 82 | 10.25 | 2026-02-02 | 2026-04-30
O2-1968 - Automation Learning Coding | 1 | 8 | 8 | 1 | 2026-02-06 | 2026-02-06
O2-1969 - Automation Learning Coding | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
O2-1970 - Automation Learning Coding | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-27 | 2026-02-27
O2-1971 - Automation Learning Coding | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-19 | 2026-02-19
O2-1972 - Automation Learning Coding | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-05 | 2026-03-05
O2-1973 - Automation Learning Coding | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-13 | 2026-03-13
O2-1974 - Automation Learning Coding | 1 | 8 | 8 | 1 | 2026-03-27 | 2026-03-27
O2-2042 - OmniConnect Testing Automation Learning Coding | 1 | 8 | 8 | 1 | 2026-04-09 | 2026-04-09
O2-2044 - OmniConnect Testing Automation Learning Coding | 1 | 8 | 8 | 1 | 2026-04-16 | 2026-04-16
O2-2046 - OmniConnect Testing Automation Learning Coding | 1 | 8 | 8 | 1 | 2026-04-23 | 2026-04-23
O2-2054 - OmniConnect Testing Automation Learning Coding | 1 | 8 | 8 | 1 | 2026-04-30 | 2026-04-30
O2-1783 - OmniConnect SaaS Cost Optimization: Azure Functions | 45 | 360 | 0 | 0 | 2026-03-09 | 2026-04-10
O2-2020 - Research | 0 | 0 | 0 | 0 | 2026-03-09 | 2026-03-10
O2-2021 - hello world of function apps and app service on azure app service plan | 0 | 0 | 0 | 0 | 2026-03-30
O2-1935 - Disaster Recovery | 0 | 0 | 0 | 0
O2-1953 - Trigger API Integration with Batch/BPM | 42.12 | 337 | 562 | 70.25 | 2026-03-17 | 2026-04-21
O2-1954 - User Manual | 0 | 0 | 0 | 0
O2-1955 - Development | 0 | 0 | 224 | 28
O2-1999 - Batch On Demand Integration | 3 | 24 | 24 | 3 | 2026-03-31 | 2026-04-02
O2-2334 - BPM On Demand Integration | 3 | 24 | 24 | 3 | 2026-04-03 | 2026-04-07
O2-2336 - BPM Job Tracking Integration | 2 | 16 | 16 | 2 | 2026-04-08 | 2026-04-09
O2-2337 - Batch Job Tracking Integration | 2 | 16 | 16 | 2 | 2026-04-10 | 2026-04-13
O2-2338 - Authorization Implementation for BPM/Batch | 3 | 24 | 24 | 3 | 2026-04-14 | 2026-04-16
O2-2391 - Batch Job On Demand API | 3 | 24 | 24 | 3 | 2026-04-02 | 2026-04-06
O2-2392 - BPM Job On Demand API | 3 | 24 | 24 | 3 | 2026-04-07 | 2026-04-09
O2-2393 - Variables Mapping | 3 | 24 | 24 | 3 | 2026-04-10 | 2026-04-14
O2-2394 - End to End Testing | 1 | 8 | 8 | 1 | 2026-04-15 | 2026-04-15
O2-2419 - Design Review and Discussion | 3 | 24 | 24 | 3 | 2026-04-06 | 2026-04-16
O2-2421 - Batch/BPM Code Improvements and testing | 2 | 16 | 16 | 2 | 2026-04-15 | 2026-04-16
O2-1957 - SQA | 0 | 0 | 0 | 0
O2-2326 - SQA | 5 | 40 | 40 | 5 | 2026-04-16 | 2026-04-22
O2-2379 - Trigger-API-Testing(16,17 April) | 2 | 16 | 16 | 2 | 2026-04-16 | 2026-04-17
O2-2701 - Trigger API-Testing (27,28,29 April) | 3 | 24 | 24 | 3 | 2026-04-27 | 2026-04-29
O2-2365 - Bug-Fixing | 0 | 0 | 0 | 0
O2-2367 - Trigger AP returns “Variable 'StartTime' not found” error despite variable being configured | 0 | 0 | 0 | 0
O2-2373 - SQA Handover | 0 | 0 | 1 | 0.12
O2-2374 - Handover By Abbas | 0.12 | 1 | 1 | 0.12 | 2026-04-15 | 2026-04-15
O2-2475 - KT | 2 | 16 | 16 | 2 | 2026-03-27 | 2026-03-30
O2-2479 - Code Review | 2 | 16 | 16 | 2 | 2026-03-27 | 2026-03-30
O2-2476 - Development | 0 | 0 | 0 | 0
O2-2477 - Production Release | 0 | 0 | 0 | 0
O2-1976 - OmniConnect Export to SQL Enhancement | 78.62 | 628.96 | 773.33 | 96.67 | 2026-03-17 | 2026-04-16
O2-1977 - Development | 2.5 | 20 | 152 | 19 | 2026-03-17 | 2026-04-03
O2-1980 - Code Setup + Understanding of the repo | 2 | 16 | 9 | 1.12 | 2026-03-17 | 2026-03-18
O2-1989 - Create Scheduled Trigger API -With AI | 0.5 | 4 | 3.5 | 0.44 | 2026-03-18 | 2026-03-26
O2-2013 - Re-Develop Create Trigger API | 1 | 8 | 7 | 0.88 | 2026-03-25 | 2026-03-26
O2-2014 - Modify Create Apis | 0.62 | 5 | 4 | 0.5 | 2026-03-25 | 2026-03-26
O2-2019 - Code Understanding | 0.75 | 6 | 6 | 0.75 | 2026-03-18 | 2026-03-25
O2-2028 - Get all triggers API | 0.75 | 6 | 6 | 0.75 | 2026-03-27 | 2026-03-27
O2-2029 - Fixes, while API integrations | 0.25 | 2 | 2 | 0.25 | 2026-03-27 | 2026-03-31
O2-2059 - Removing trigger fields from Export to SQL | 0.5 | 4 | 4 | 0.5 | 2026-03-25 | 2026-03-25
O2-2060 - Creating a new triggers page for Export to SQL | 2 | 16 | 12 | 1.5 | 2026-03-25 | 2026-03-26
O2-2061 - Integrating NEW APIs for Triggers page | 2 | 16 | 8 | 1 | 2026-03-27 | 2026-03-27
O2-2076 - Set up Start And End Pull time for each trigger | 0.75 | 6 | 6 | 0.75 | 2026-04-02 | 2026-04-03
O2-2092 - Update Create trigger api, Check for unique names only | 0.12 | 1 | 1 | 0.12 | 2026-04-03 | 2026-04-03
O2-2093 - modify get trigger api, bring trigger name and is enabled | 0.38 | 3 | 3 | 0.38 | 2026-04-03 | 2026-04-03
O2-2100 - API Changes for Triggers | 2 | 16 | 12 | 1.5 | 2026-04-01 | 2026-04-02
O2-2101 - Bug Fixes Dev Side | 3 | 24 | 20 | 2.5 | 2026-04-03 | 2026-04-06
O2-2345 - Delete Trigger API Creation | 0.19 | 1.5 | 1.5 | 0.19 | 2026-04-15 | 2026-04-16
O2-2346 - Post Handover feedback Incorporated | 0.12 | 1 | 1 | 0.12 | 2026-04-15 | 2026-04-15
O2-2348 - Resolve Update Pipeline API Issues | 0.62 | 5 | 5 | 0.62 | 2026-04-16 | 2026-04-17
O2-2364 - Add Quality Codes in Export pipeline table , update all crud operations | 0.25 | 2 | 2 | 0.25 | 2026-04-16 | 2026-04-16
O2-2486 - Requirements Change / Rework | 5 | 40 | 39 | 4.88 | 2026-04-15 | 2026-04-24
O2-2177 - URS | 0.4 | 3.2 | 0 | 0 | 2026-03-17
O2-2178 - DDS | 1.25 | 10 | 0 | 0
O2-2179 - SQA | 5 | 40 | 80 | 10 | 2026-04-16 | 2026-04-22
O2-2263 - Export To Sql (April16, 17) | 2 | 16 | 16 | 2 | 2026-04-16 | 2026-04-17
O2-2688 - Export To Sql (April 20, 21, 22 ) | 3 | 24 | 24 | 3 | 2026-04-20 | 2026-04-22
O2-2689 - Export To Sql (April 23, 24 ) | 2 | 16 | 16 | 2 | 2026-04-23 | 2026-04-24
O2-2691 - Export To Sql (April 27, 28, 29 ) | 3 | 24 | 24 | 3 | 2026-04-27 | 2026-04-29
O2-2265 - QA Handover | 0.75 | 6 | 4.5 | 0.56 | 2026-04-15 | 2026-04-16
O2-2266 - Handover By Abbas | 0.12 | 1 | 1 | 0.12 | 2026-04-15 | 2026-04-15
O2-2267 - Handover Taken By Kamran | 0.12 | 1 | 1 | 0.12 | 2026-04-15 | 2026-04-15
O2-2268 - Handover By Namra | 0.12 | 1 | 1 | 0.12 | 2026-04-15 | 2026-04-15
O2-2343 - Handover to QA | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-15 | 2026-04-15
O2-2485 - Handover to QA | 0.12 | 1 | 1 | 0.12 | 2026-04-15 | 2026-04-15
O2-2276 - Bug Fixing | 0 | 0 | 136.17 | 17.02
O2-2363 - Values are not getting displayed (Staging) | 0 | 0 | 0 | 0 | 2026-04-16
O2-2375 - SQL Manual pipeline is not getting started and Showing An ERROR | 0 | 0 | 0 | 0 | 2026-04-17
O2-2376 - Manual and Scheduled Export to SQL are not aligned in terms of data export. Please align both manual and scheduled export types for SQL export. | 0 | 0 | 0 | 0
O2-2377 - On all types of SQL(Scheduled, Manual) This Error is getting displayed while we Stop or Start the Pipelie | 0 | 0 | 0 | 0
O2-2378 - Trigger Name Minimum Length Validation Not Implemented | 0 | 0 | 0 | 0
O2-2382 - Bug fixing | 0 | 0 | 12 | 1.5 | 2026-04-17 | 2026-04-21
O2-2390 - Pagination, footer, and grid UI get disturbed after creating multiple triggers | 0.25 | 2 | 2 | 0.25 | 2026-04-20 | 2026-04-23
O2-2395 - Trigger is not getting deleted and an error is displayed | 0 | 0 | 1 | 0.12 | 2026-04-20
O2-2406 - Create Trigger API fails on decimal Recurrence input and shows multiple errors instead of a single validation message. | 0.12 | 1 | 1 | 0.12 | 2026-04-20 | 2026-04-21
O2-2413 - 🚫Blocker: Trigger creation fails in UTC and data export fails in Local time due to incorrect time validation handling | 0.17 | 1.33 | 1.33 | 0.17 | 2026-04-20 | 2026-04-24
O2-2414 - Implement info icon for time fields indicating all times should be in UTC | 0.25 | 2 | 2 | 0.25 | 2026-04-20 | 2026-04-21
O2-2420 - Trigger cannot be restarted after being stopped before first execution (of time. | 0 | 0 | 0 | 0 | 2026-04-20
O2-2422 - Bug: I created an IT data pipeline, but when I edit the same pipeline, the pipeline type is shown as OT instead of IT. | 0.25 | 2 | 2 | 0.25 | 2026-04-20 | 2026-04-22
O2-2423 - Bug: IT data is successfully exported to SQL, but the logs are not appearing on the Monitoring page. | 0 | 0 | 0 | 0
O2-2424 - Bug: Trigger delete System Alarm is not available | 0.17 | 1.33 | 1.33 | 0.17 | 2026-04-21 | 2026-04-23
O2-2425 - Critical Bug: When the pipeline is stopped and restarted, it does not export data. | 0.12 | 1 | 1 | 0.12 | 2026-04-21 | 2026-04-23
O2-2426 - Bug: While associating tags from the wizard, the asset list is not being displayed. | 0.12 | 1 | 1 | 0.12 | 2026-04-20 | 2026-04-22
O2-2427 - Bug: After stopping and restarting the trigger, system alarms are not being triggered. | 0.23 | 1.83 | 1.83 | 0.23 | 2026-04-20 | 2026-04-23
O2-2428 - Bug: Permissions for Trigger Start/Stop, Create, Update, Delete, and Read are not available in the Roles and Permissions module. | 0.5 | 4 | 4 | 0.5 | 2026-04-20 | 2026-04-23
O2-2429 - Task: Error message should be only Pipeline name is duplicated or A Pipeline with this name already exist | 0.12 | 1 | 1 | 0.12 | 2026-04-21 | 2026-04-21
O2-2430 - Read the title below | 0 | 0 | 0 | 0
O2-2431 - Bug: The pipeline can still be edited while its associated trigger is turned on. The system should restrict users from editing a pipeline if any associated trigger is in the running state. | 0.12 | 1 | 1 | 0.12 | 2026-04-20 | 2026-04-22
O2-2432 - Bug: Trigger names should not be allowed to consist of only numbers. | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-21 | 2026-04-21
O2-2433 - Bug: In the case of minute-based recurrence, the minimum allowed limit should be 5 minutes, as it was implemented in this module before this enhancement. | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-20 | 2026-04-23
O2-2434 - Bug: Trigger should not create with only underscore in the name | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-21 | 2026-04-22
O2-2435 - An undefined/empty space is displayed at the bottom of the Trigger list page. Scrollbar is not properly implemented on the Trigger list page, resulting in a large empty space at the bottom. | 0 | 0 | 0 | 0
O2-2436 - Bug (Security Concern): Password field can be exposed via DOM manipulation Issue: | 0 | 0 | 0 | 0
O2-2437 - Bug: Trigger name is not visible on the Monitoring page, which is necessary because multiple triggers can be associated with a single pipeline. | 0.5 | 4 | 4 | 0.5 | 2026-04-22 | 2026-04-24
O2-2438 - Task: This should be Site name | 0.02 | 0.17 | 0.17 | 0.02 | 2026-04-21 | 2026-04-22
O2-2439 - Bug: Unable to export Site Hierarchy | 0 | 0 | 0 | 0
O2-2440 - Bug: In the case of Data, Stat, and Quality Code alarms, the following options should not be displayed: Resolution Value Data Quality Filter Aggregate | 0 | 0 | 0 | 0
O2-2441 - Bug: Unable to export alarms | 0 | 0 | 0 | 0
O2-2442 - Site Hierarchy trigger created successfully but data is not exported to SQL | 0 | 0 | 0 | 0
O2-2443 - QA Reported Bugs | 0.38 | 3 | 3 | 0.38 | 2026-04-21 | 2026-04-21
O2-2446 - Changings are not getting saved and Showing Error after deleting few tags from SQL pipeline | 0.12 | 1 | 1 | 0.12 | 2026-04-22 | 2026-04-23
O2-2447 - Mapped name of tags are not getting displayed | 0.12 | 1 | 1 | 0.12 | 2026-04-21 | 2026-04-22
O2-2456 - IT table and Time stamp column name is getting removed , While editing IT pipelines. | 0.12 | 1 | 1 | 0.12 | 2026-04-22 | 2026-04-22
O2-2478 - No data is getting exported to SQL nor Monitoring logs are getting displayed | 0 | 0 | 0 | 0
O2-2487 - Need to remove the extra stats alarms related to Schedule SQL start and stop | 0.12 | 1 | 1 | 0.12 | 2026-04-23 | 2026-04-24
O2-2491 - Weekly Scheduled export to SQL FAILED, NO monitoring no export | 0 | 0 | 0 | 0
O2-2492 - Schedule Type as Monthly Export is also Failed with Data Alarm | 0 | 0 | 0 | 0
O2-2493 - Bugs Fixing and management | 8 | 64 | 64 | 8 | 2026-04-15 | 2026-04-29
O2-2494 - Task | 0 | 0 | 0 | 0
O2-2495 - Bug Fixing and Discussions | 1 | 8 | 8 | 1 | 2026-04-24 | 2026-04-24
O2-2558 - Invalid error message persists and blocks trigger creation | 0 | 0 | 0 | 0 | 2026-04-28
O2-2559 - Weekly and Monthly triggers are still FAILED for SQL Pipelines | 0 | 0 | 0 | 0
O2-2568 - Schedule SQL is Failed when Granularity =Day, Job Start Time = Day | 0 | 0 | 0 | 0
O2-2572 - Bug Fixing | 0.38 | 3 | 3 | 0.38 | 2026-04-27 | 2026-04-28
O2-2625 - Release bugs fixing, and release management | 2 | 16 | 16 | 2 | 2026-05-04 | 2026-05-05
O2-2573 - Production Release | 0 | 0 | 14 | 1.75
O2-2581 - Production Green Release Management / Deployment | 1 | 8 | 8 | 1 | 2026-04-30 | 2026-04-30
O2-2611 - Release Support | 0.75 | 6 | 6 | 0.75 | 2026-05-04 | 2026-05-04
O2-1981 - HVAC-APX (P) | 66.19 | 529.5 | 997 | 124.62
O2-1982 - Kick-off meetings | 0 | 0 | 35.5 | 4.44
O2-1983 - Kick-off meetings (DR) | 0 | 0 | 16 | 2
O2-1984 - Kick-off meetings (MAW) | 1.25 | 10 | 8.5 | 1.06 | 2026-03-24 | 2026-03-31
O2-1985 - Kick-off meetings (DA) | 0 | 0 | 2 | 0.25 | 2026-03-24
O2-2074 - Kick-off working | 1.25 | 10 | 9 | 1.12
O2-2097 - Kick-off meetings (FB) | 0 | 0 | 0 | 0
O2-2057 - Initial Research | 0 | 0 | 48 | 6
O2-2058 - Initial Research (DR) | 0 | 0 | 24 | 3
O2-2096 - Initial Research (FB) | 0 | 0 | 24 | 3
O2-2245 - APX Chiller Performance | 0 | 0 | 212 | 26.5
O2-2247 - Asset Design, HB and Expected models (P) | 10 | 80 | 48 | 6 | 2026-04-09 | 2026-04-30
O2-2248 - Template, wizards and dashboard design (P) | 5 | 40 | 28 | 3.5
O2-2380 - Non-Ebs Exp Calculations | 1 | 8 | 8 | 1
O2-2503 - Non-Ebs Advisory Calculations | 4 | 32 | 32 | 4 | 2026-04-27 | 2026-04-30
O2-2504 - Dispatch Advisory Methodology (P) | 4 | 32 | 32 | 4 | 2026-04-27 | 2026-04-30
O2-2506 - Process Testing (P) | 5 | 40 | 0 | 0 | 2026-05-13 | 2026-05-31
O2-2652 - Development (if required) | 0 | 0 | 0 | 0
O2-2653 - Asset Design, HB and Expected models (P) | 0 | 0 | 40 | 5 | 2026-05-01 | 2026-05-08
O2-2654 - APX Engine per Development (P) | 0 | 0 | 24 | 3 | 2026-05-04 | 2026-05-08
O2-2655 - Template, wizards and dashboard design (P) | 2 | 16 | 0 | 0 | 2026-05-11 | 2026-05-15
O2-2246 - APX AHU Performance | 0 | 0 | 187 | 23.38
O2-2249 - Initial Research | 1.5 | 12 | 12 | 1.5
O2-2251 - AHU Presentation | 1 | 8 | 8 | 1
O2-2252 - Asset Design, HB and Expected models (P) | 10 | 80 | 84 | 10.5
O2-2255 - Curves Digitalization | 5 | 40 | 40 | 5
O2-2461 - Implement and integrate hyperbolic functions (sinh, cosh, tanh, etc.) in both offline and online calculation flows, ensuring consistency and validating results through developer testing + Backfilling of missing data on Prod - AZ | 0.94 | 7.5 | 7 | 0.88 | 2026-04-14 | 2026-04-14
O2-2462 - Research and fix SOLVER formula calculation to return expected values | 0.25 | 2 | 2 | 0.25 | 2026-04-22 | 2026-04-22
O2-2502 - Process Testing (P) | 3 | 24 | 0 | 0
O2-2570 - Template, wizards and dashboard design (P) | 2 | 16 | 16 | 2 | 2026-04-14 | 2026-04-30
O2-2656 - Template, wizards and dashboard design (P) | 3 | 24 | 10 | 1.25 | 2026-05-05 | 2026-05-22
O2-2657 - Template, wizards and dashboard design (P) | 1 | 8 | 8 | 1
O2-2253 - APX AHU Health | 0 | 0 | 16 | 2
O2-2254 - Module Design (P) | 5 | 40 | 16 | 2
O2-199 - Technical Support | 124.81 | 998.5 | 1398.54 | 174.82 | 2026-01-01 | 2026-12-31
O2-1168 - Schedule Import OT wide support | 5 | 40 | 80 | 10 | 2026-02-02 | 2026-02-10
O2-1277 - SFTP OT wide support | 2 | 16 | 16 | 2 | 2026-02-02 | 2026-02-03
O2-1278 - RestApi OT wide support | 3 | 24 | 16 | 2 | 2026-02-04 | 2026-02-06
O2-1279 - SQL OT wide support | 2 | 16 | 16 | 2 | 2026-02-09 | 2026-02-10
O2-1288 - Add Support for Long-Format Response in Read API (Configurable via Flag) | 1 | 8 | 4 | 0.5 | 2026-02-11 | 2026-02-11
O2-1382 - Added Asset Dependency count in Tag Deletion | 0.88 | 7 | 7 | 0.88 | 2026-02-12 | 2026-02-12
O2-1778 - Technical support for Roshan Packages data extraction pipeline | 2 | 16 | 32 | 4
O2-1862 - Inhand Live | 1 | 8 | 8 | 1 | 2026-03-04 | 2026-03-04
O2-1863 - Cloud Connectivity | 1 | 8 | 8 | 1 | 2026-03-05 | 2026-03-05
O2-1945 - Export To SQL Pointer Lookback Window | 0 | 0 | 13 | 1.62
O2-1947 - Implementing Lookback for Pointer | 2.44 | 19.5 | 13 | 1.62 | 2026-03-06 | 2026-03-10
O2-200 - Collaboration with Implementation team on Tapal Project | 0 | 0 | 128 | 16
O2-2148 - Configure Manual DB/Table Mapping for SAP HANA Source | 3 | 24 | 24 | 3 | 2026-03-04 | 2026-03-06
O2-2149 - Implement manual DB/Table to bypass SAP HANA Connector | 0 | 0 | 24 | 3
O2-2335 - Login failing on Production Environment | 0.25 | 2 | 2 | 0.25 | 2026-04-14 | 2026-04-14
O2-2339 - Database connection failing - Due to VNET deletion | 0.25 | 2 | 2 | 0.25 | 2026-04-14 | 2026-04-14
O2-2514 - Support - Device Diagnostics Enhancement | 3.75 | 30 | 30 | 3.75 | 2026-04-14 | 2026-04-17
O2-2515 - Code Research + Understanding | 0.75 | 6 | 6 | 0.75 | 2026-04-14 | 2026-04-14
O2-2516 - Integration of graph and new tab(OPC Server) | 1 | 8 | 8 | 1 | 2026-04-15 | 2026-04-15
O2-2517 - Deployment to staging + Bug Fixing | 1 | 8 | 8 | 1 | 2026-04-16 | 2026-04-16
O2-2518 - Bug Fixing | 1 | 8 | 8 | 1 | 2026-04-17 | 2026-04-17
O2-2716 - Data Alarms are not working properly for Lusail FM | 17 | 136 | 0 | 0 | 2026-05-18 | 2026-06-12
O2-2717 - Schedule uploading and configurable engine running time | 30 | 240 | 0 | 0 | 2026-06-15 | 2026-07-24
O2-297 - Alarm Configuration Enhancement DDS | 0 | 0 | 14 | 1.75 | 2025-10-13
O2-317 - Import Site Layout Exception Handling | 0 | 0 | 6 | 0.75
O2-335 - test | 0 | 0 | 0 | 0
O2-433 - APX Template Support | 0 | 0 | 12 | 1.5 | 2025-10-23 | 2025-10-24
O2-561 - Ingestion_Time - Read API Documentation | 0 | 0 | 2 | 0.25
O2-586 - IOT Edge Installatation Guide | 0 | 0 | 16 | 2
O2-592 - User Manual Enhancement | 0 | 0 | 16 | 2
O2-589 - Enable APx assets in APx. Block Modification through ISL | 0 | 0 | 11 | 1.38
O2-607 - Alarm Configuration Enhancement Development | 1.5 | 12 | 12 | 1.5 | 2025-11-10 | 2026-01-01
O2-696 - MPN Migration | 8 | 64 | 0 | 0 | 2025-11-24 | 2025-11-28
O2-704 - QA Testing | 0 | 0 | 110.27 | 13.78
O2-706 - Test Case Updating | 15 | 120 | 110.27 | 13.78 | 2025-11-26 | 2025-12-23
O2-755 - OmniAgent Enhancement User guidance | 0 | 0 | 64 | 8
O2-764 - POC - IT to OT tags | 0 | 0 | 0 | 0
O2-802 - ReadAPI payloads handle milliseconds | 0 | 0 | 12 | 1.5
O2-828 - CSV Bulk Import v2 Research | 0 | 0 | 32 | 4
O2-850 - Export To SQL Support Tickets | 11 | 88 | 88 | 11 | 2026-01-05
O2-1157 - Working on pointer logic | 2 | 16 | 16 | 2 | 2026-01-05 | 2026-01-07
O2-1159 - Deduplication | 0 | 0 | 24 | 3
O2-1160 - Testing and Vaidation | 3 | 24 | 32 | 4 | 2026-01-06 | 2026-02-09
O2-1991 - WhatIf Visual Screens (Pump, Comp,Cond,Hex, Boiler) II | 52.05 | 416.4 | 218 | 27.25 | 2026-04-06 | 2026-04-29
O2-1992 - Research | 2.62 | 21 | 21 | 2.62 | 2026-04-06 | 2026-04-10
O2-2102 - Research on Adding the Image Support to HTML Template | 1.62 | 13 | 13 | 1.62 | 2026-04-06 | 2026-04-07
O2-2237 - Research for Slider, Radio Buttons, Inputs Support to HTML Template | 1 | 8 | 8 | 1 | 2026-04-10 | 2026-04-10
O2-1993 - Development | 10.2 | 81.6 | 64 | 8 | 2026-04-13 | 2026-04-23
O2-2239 - Image, Radio Button, Slider Incorporation in the HTML Template | 3 | 24 | 24 | 3 | 2026-04-13 | 2026-04-15
O2-2329 - User End dynamic HTML Rendering and id mappings | 2 | 16 | 16 | 2 | 2026-04-16 | 2026-04-17
O2-2381 - What-If call using dynamic controls | 2 | 16 | 16 | 2 | 2026-04-20 | 2026-04-23
O2-2490 - Unit Testing & Fixes | 1 | 8 | 8 | 1 | 2026-04-24 | 2026-04-24
O2-1994 - Handover Session | 0 | 0 | 0 | 0 | 2026-04-24 | 2026-04-24
O2-1995 - SQA | 3.1 | 24.8 | 24 | 3 | 2026-04-24 | 2026-04-28
O2-2651 - Testing by Zeeshan | 0 | 0 | 24 | 3
O2-1996 - Bugs Fixing | 0 | 0 | 0 | 0
O2-1997 - User Manual | 0 | 0 | 0 | 0
O2-1998 - Production Release | 3 | 24 | 0 | 0 | 2026-04-29 | 2026-04-29
O2-2 - Batch/BPM V4 – GitHub Integration | 76 | 608 | 1026.74 | 128.34
O2-3 - Research/URS | 8 | 64 | 64 | 8 | 2025-10-27 | 2025-10-31
O2-5 - Development | 20 | 160 | 152 | 19 | 2025-11-03 | 2025-11-17
O2-609 - UI Development | 0 | 0 | 24 | 3
O2-610 - Frontend End Development | 0 | 0 | 40 | 5
O2-611 - Backend Development | 0 | 0 | 72 | 9
O2-612 - End-to-end application testing | 0 | 0 | 16 | 2
O2-6 - SQA | 10 | 80 | 264.37 | 33.05 | 2025-11-18 | 2025-11-20
O2-653 - Sanity_Staging | 10 | 80 | 75.8 | 9.47 | 2025-11-19 | 2025-11-20
O2-657 - Bulk Fetch Connection String is not working as expected | 0 | 0 | 0 | 0
O2-659 - In Batch BPM, the output table column description limit is not applied, causing the API to crash while saving. | 0 | 0 | 0 | 0
O2-660 - When using a user-defined table as an existing table for a new Batch BPM job, the API does not return or display the column descriptions after importing the schema. | 0 | 0 | 0 | 0
O2-661 - In Batch BPM module, when a user clones a job, the system allows creating another job with the same name. | 0 | 0 | 0 | 0
O2-662 - Area dependency is displaying on assets even after cancelling the pop up display while deleting respective area. | 0 | 0 | 3 | 0.38
O2-663 - Calculated and Totalizer tag values are not updating, whereas the Real-time tag live values are populating. | 0 | 0 | 0 | 0
O2-664 - Incorrect Spelling of "Calculated" in Alarm Name Description on System Alarms Viewer Screen | 0 | 0 | 0 | 0
O2-665 - Error is displaying while configuring AHU APX performance asset. Dash should be automatically changed into underscore same as it is changing spaces. | 0 | 0 | 3 | 0.38
O2-667 - Totalizer tags values are not getting updated. | 0 | 0 | 1 | 0.12
O2-668 - When a user-defined function is used in BPM, the process validates successfully and the output is saved. However, when selecting “Execute All & Save Output,” the RUN STATUS shows ERROR. | 0 | 0 | 0 | 0
O2-669 - Huge gap is displaying between two real time tag Mapped names created through ISL. | 0 | 0 | 0 | 0
O2-672 - Unexcepted error is occurring after login, unless we refresh the application | 0 | 0 | 0 | 0
O2-673 - Sanity_Production | 20 | 160 | 121.57 | 15.2 | 2025-11-21 | 2025-11-17
O2-678 - After recent deployment of OC fast Publish Changes is not working for all sites | 0 | 0 | 0 | 0
O2-680 - Anomaly Results are not getting displayed, model was created successfully | 0 | 0 | 3 | 0.38
O2-682 - Critical Issue: Trending is showing an Error (400 bad request), while user selects real type tag directly on trending screen. | 0 | 0 | 1 | 0.12
O2-694 - Anomaly Fail: Error with success message is getting displayed and after that create model screen is not appearing its just keep on Processing | 0 | 0 | 0 | 0
O2-695 - Bulk Connection strings are not getting Fetched, | 0 | 0 | 0 | 0
O2-702 - Anomaly Analysis Failed Again | 0 | 0 | 0 | 0
O2-711 - Bug Fixing, Improvements and Tasks | 0 | 0 | 56 | 7
O2-7 - User Manual | 4 | 32 | 8 | 1 | 2025-11-18 | 2025-11-20
O2-679 - Fields - Update Write KQL Query Dialog Fields | 0 | 0 | 8 | 1
O2-8 - Production Release | 4 | 32 | 25 | 3.12 | 2025-11-21 | 2025-11-21
O2-686 - Prep Prod Planning /Tasks | 0 | 0 | 5 | 0.62
O2-687 - Production Green Release | 0 | 0 | 8 | 1
O2-688 - Production Blue Release | 0 | 0 | 4 | 0.5
O2-2001 - OmniAgent - Charting | 9.06 | 72.5 | 289 | 36.12
O2-2002 - Production Release | 0 | 0 | 0 | 0
O2-2003 - Development | 0 | 0 | 144.5 | 18.06
O2-2023 - Started Backend + Research on Code | 0.69 | 5.5 | 5.5 | 0.69 | 2026-03-18 | 2026-03-18
O2-2024 - Completed Backend(Responses + Request) Model | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-24
O2-2032 - Integrated Chart logic Frontend | 1 | 8 | 8 | 1 | 2026-03-26 | 2026-03-26
O2-2033 - UI Changes + Completed Integration of Charts logic | 1 | 8 | 8 | 1 | 2026-03-27 | 2026-03-27
O2-2055 - Fixed issues on Frontend and backend | 1 | 8 | 8 | 1 | 2026-03-30 | 2026-03-30
O2-2056 - Integrated OmniAgent Charts and Refresh Site API | 1 | 8 | 8 | 1 | 2026-03-31 | 2026-03-31
O2-2083 - Fixed Refresh Site issue + UI issue | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-01
O2-2095 - Testing Module + Deployed to staging | 1 | 8 | 8 | 1 | 2026-04-02 | 2026-04-02
O2-2104 - fixing issues | 1 | 8 | 8 | 1 | 2026-04-03 | 2026-04-03
O2-2183 - Fixed OmniAgent issue | 0.38 | 3 | 3 | 0.38 | 2026-04-06 | 2026-04-06
O2-2467 - Add charting to Output Schemas | 0 | 0 | 24 | 3
O2-2468 - Add Bar to charting | 0 | 0 | 8 | 1
O2-2469 - Add line to charting | 0 | 0 | 8 | 1
O2-2470 - Add column to charting | 0 | 0 | 8 | 1
O2-2471 - Collapse Resolver to Orchestrator | 0 | 0 | 16 | 2
O2-2474 - Improve Instructions for each agent | 0 | 0 | 8 | 1
O2-2004 - SQA | 0 | 0 | 0 | 0
O2-2009 - Research | 0 | 0 | 0 | 0
O2-2010 - User Manual | 0 | 0 | 0 | 0
O2-2011 - Read API Support | 0 | 0 | 0 | 0
O2-2012 - Handover | 0 | 0 | 0 | 0
O2-2005 - Read API - Analysis for SQL | 6 | 48 | 32 | 4 | 2026-03-25 | 2026-03-26
O2-2006 - Analysis | 2 | 16 | 16 | 2 | 2026-03-25 | 2026-03-26
O2-2007 - Analysis for APX hits | 1 | 8 | 8 | 1 | 2026-03-25 | 2026-03-25
O2-2008 - Analysis for Customer Hits | 1 | 8 | 8 | 1 | 2026-03-26 | 2026-03-26
O2-2034 - SUPPORT-tapal edge trouble shooting | 25 | 200 | 96 | 12 | 2026-03-23 | 2026-04-27
O2-2035 - Bug Fixing | 10 | 80 | 48 | 6 | 2026-03-23 | 2026-04-27
O2-2036 - support table edge trouble shooting - bug fixing - trouble shooting | 5 | 40 | 48 | 6 | 2026-03-30 | 2026-04-02
O2-2037 - troubleshoot edge | 0 | 0 | 0 | 0
O2-2105 - Read API - Rounding off the value | 10 | 80 | 40 | 5 | 2026-04-03 | 2026-04-07
O2-2111 - Development | 3 | 24 | 12 | 1.5 | 2026-04-03 | 2026-04-07
O2-2116 - Added feature to round off the value in Read API | 2 | 16 | 12 | 1.5 | 2026-04-03 | 2026-04-07
O2-2112 - SQA | 1 | 8 | 8 | 1 | 2026-04-16 | 2026-04-16
O2-2408 - Testing By M.Abbas | 1 | 8 | 8 | 1 | 2026-04-20 | 2026-04-20
O2-2113 - Production | 0 | 0 | 0 | 0
O2-2114 - Dev | 0 | 0 | 0 | 0
O2-2115 - SQA | 0 | 0 | 0 | 0
O2-2144 - Alarms in ReadAPI - OC Optimization | 5 | 40 | 0 | 0 | 2026-04-09 | 2026-04-15
O2-2186 - Tempate Tool Enhancement for WhatIf and Health | 37.69 | 301.5 | 83 | 10.38 | 2026-04-06 | 2026-04-27
O2-2187 - Development | 6.5 | 52 | 41.5 | 5.19 | 2026-04-09 | 2026-04-16
O2-2256 - Setup additional Property for health | 0.69 | 5.5 | 5.5 | 0.69 | 2026-04-10 | 2026-04-14
O2-2257 - Code review to incorporate changes | 0.62 | 5 | 6 | 0.75 | 2026-04-09 | 2026-04-10
O2-2259 - Add steps for health additional property | 0.44 | 3.5 | 3.5 | 0.44 | 2026-04-14 | 2026-04-15
O2-2260 - modify steps api to incorporate health additional properties | 0.31 | 2.5 | 2.5 | 0.31 | 2026-04-14 | 2026-04-14
O2-2261 - Modify the template code to incorporate changes | 0.38 | 3 | 3 | 0.38 | 2026-04-15 | 2026-04-15
O2-2262 - Modify health get steps api to call additional property template | 0.25 | 2 | 0 | 0 | 2026-04-15 | 2026-04-16
O2-2327 - Incorporate Additional propertty while configuring asset's Health | 0.38 | 3 | 3 | 0.38 | 2026-04-28 | 2026-04-28
O2-2328 - Incorporate additional property in VM calls for digital twin creation and Activation | 0.62 | 5 | 5 | 0.62 | 2026-04-27 | 2026-04-27
O2-2545 - Identify issues and fix during the testing flow in template | 0.62 | 5 | 5 | 0.62 | 2026-04-28 | 2026-04-30
O2-2546 - Thorough flow walk through and fixes additional property creation to asset activation | 0.38 | 3 | 3 | 0.38 | 2026-04-29 | 2026-04-30
O2-2571 - API Modification for Digital Twin Models | 1 | 8 | 5 | 0.62 | 2026-04-29 | 2026-04-30
O2-2195 - Handover | 0 | 0 | 0 | 0 | 2026-04-17 | 2026-04-17
O2-2198 - SQA | 0 | 0 | 0 | 0 | 2026-04-17 | 2026-04-24
O2-2202 - Production Release | 3 | 24 | 0 | 0 | 2026-04-27 | 2026-04-28
O2-2216 - Bug Fixing | 0 | 0 | 0 | 0 | 2026-04-17 | 2026-04-24
O2-2188 - Support for Wide tables from SQL Source | 40.42 | 323.4 | 144 | 18 | 2026-05-08 | 2026-05-19
O2-2191 - Research/URS | 0 | 0 | 0 | 0
O2-2192 - Research/DDS | 0 | 0 | 0 | 0
O2-2193 - Development | 4.3 | 34.4 | 48 | 6 | 2026-05-08 | 2026-05-14
O2-2519 - Meeting + Code Understanding | 0.5 | 4 | 4 | 0.5 | 2026-04-20 | 2026-04-20
O2-2589 - UI + API Changes | 0.5 | 4 | 4 | 0.5 | 2026-04-21 | 2026-04-21
O2-2590 - Integration of Wide Format(FrontEnd) | 0.5 | 4 | 4 | 0.5 | 2026-04-22 | 2026-04-22
O2-2592 - Testing+ Fixed Issues | 0.5 | 4 | 4 | 0.5 | 2026-04-23 | 2026-04-23
O2-2594 - Meeting with DE team + New Changes | 0.5 | 4 | 4 | 0.5 | 2026-04-24 | 2026-04-24
O2-2673 - Integrated new changes | 1 | 8 | 8 | 1 | 2026-04-27 | 2026-04-27
O2-2675 - Testing of New Changes +Meeting | 1 | 8 | 8 | 1 | 2026-04-29 | 2026-04-29
O2-2698 - New UI changes + Fixed Fetch Schema API | 1 | 8 | 8 | 1 | 2026-05-01 | 2026-05-01
O2-2710 - Final Testing + fixed issues | 0.5 | 4 | 4 | 0.5 | 2026-05-06 | 2026-05-06
O2-2196 - QA Handover | 1.12 | 9 | 0 | 0 | 2026-05-15 | 2026-05-15
O2-2199 - Production Release | 9 | 72 | 0 | 0 | 2026-05-19 | 2026-05-20
O2-2213 - SQA | 4 | 32 | 24 | 3 | 2026-05-15 | 2026-05-21
O2-2647 - Testing By Kamran | 4 | 32 | 24 | 3 | 2026-05-07 | 2026-05-13
O2-2189 - Support for Wide tables from API Source | 40.42 | 323.4 | 144 | 18 | 2026-05-22 | 2026-06-02
O2-2200 - Research/URS | 0 | 0 | 0 | 0
O2-2201 - Research/DDS | 0 | 0 | 0 | 0
O2-2203 - Development | 4.3 | 34.4 | 48 | 6 | 2026-05-22 | 2026-05-28
O2-2520 - Meeting + Code Understanding | 0.5 | 4 | 4 | 0.5 | 2026-04-20 | 2026-04-20
O2-2588 - UI + API Changes | 0.5 | 4 | 4 | 0.5 | 2026-04-21 | 2026-04-21
O2-2591 - Integration of Wide Format(FrontEnd) | 0.5 | 4 | 4 | 0.5 | 2026-04-22 | 2026-04-22
O2-2593 - Testing + Fixed Issues | 0.5 | 4 | 4 | 0.5 | 2026-04-23 | 2026-04-23
O2-2595 - Meeting with DE team + New Changes | 0.5 | 4 | 4 | 0.5 | 2026-04-24 | 2026-04-24
O2-2674 - Integrated new changes | 1 | 8 | 8 | 1 | 2026-04-28 | 2026-04-28
O2-2676 - Testing of new changes + Meeting | 1 | 8 | 8 | 1 | 2026-04-30 | 2026-04-30
O2-2699 - New UI changes + Fixed Fetch Schema API | 1 | 8 | 8 | 1 | 2026-05-04 | 2026-05-04
O2-2711 - Final Testing + Fixed Issues | 0.5 | 4 | 4 | 0.5 | 2026-05-06 | 2026-05-06
O2-2204 - QA Handover | 1.12 | 9 | 0 | 0 | 2026-05-29 | 2026-05-29
O2-2205 - Production Release | 9 | 72 | 0 | 0 | 2026-06-02 | 2026-06-03
O2-2214 - SQA | 4 | 32 | 24 | 3 | 2026-06-03 | 2026-06-08
O2-2650 - Testing By Waqar (8 -12 May) | 3 | 24 | 24 | 3 | 2026-05-08 | 2026-05-12
O2-2693 - Testing By Waqar (13 May) | 1 | 8 | 0 | 0 | 2026-05-13 | 2026-05-13
O2-2658 - Bug Fixing | 0 | 0 | 0 | 0
O2-2659 - On-Demand Pipeline Failing for OT Wide Data | 0 | 0 | 0 | 0
O2-2190 - Support for Wide tables from SFTP Source | 30.43 | 243.4 | 0 | 0 | 2026-06-03 | 2026-06-12
O2-2206 - Research/URS | 0 | 0 | 0 | 0
O2-2207 - Research/DDS | 0 | 0 | 0 | 0
O2-2208 - Development | 4.3 | 34.4 | 0 | 0 | 2026-06-03 | 2026-06-09
O2-2209 - QA Handover | 1.12 | 9 | 0 | 0 | 2026-06-10 | 2026-06-10
O2-2210 - Production Release | 9 | 72 | 0 | 0 | 2026-06-12 | 2026-06-15
O2-2215 - SQA | 4 | 32 | 0 | 0 | 2026-06-11 | 2026-06-16
O2-221 - ( Demo / Presentation) Assignments | 55.88 | 447 | 1576.2 | 197.02
O2-1015 - ADE utilisation on APX by OmniAgent Concept | 0 | 0 | 64 | 8
O2-1421 - ADE utilisation on APX by OmniAgent Concept | 8 | 64 | 64 | 8 | 2026-01-05 | 2026-01-29
O2-1016 - APX Performance Module Training Material | 0 | 0 | 68 | 8.5 | 2025-12-11 | 2026-01-30
O2-1430 - APX Performance Module Training Material | 5 | 40 | 40 | 5 | 2025-12-11 | 2026-01-30
O2-2620 - APX WIF Training Material | 2 | 16 | 12 | 1.5 | 2026-04-27 | 2026-04-30
O2-1066 - Process pre-sales support, Customer / Management Meetings | 0 | 0 | 107 | 13.38
O2-1256 - Process pre-sales support, Customer / Management Meetings | 4 | 32 | 31.5 | 3.94 | 2026-02-02 | 2026-02-27
O2-1492 - Process pre-sales support, Customer / Management Meetings | 4 | 32 | 26 | 3.25 | 2026-01-01 | 2026-01-30
O2-1676 - Process pre-sales support, Customer / Management Meetings | 2.12 | 17 | 16.5 | 2.06 | 2026-03-02 | 2026-03-31
O2-2235 - Process pre-sales support, Customer / Management Meetings | 4 | 32 | 31 | 3.88 | 2026-04-01 | 2026-04-30
O2-2604 - Process pre-sales support, Customer / Management Meetings | 0 | 0 | 2 | 0.25 | 2026-05-01
O2-1196 - APX (Perf, WIF, Health) implementation for 10 Ashghal VFP Pumps | 0 | 0 | 97 | 12.12
O2-1197 - APX implementation for 10 pumps | 5 | 40 | 35.5 | 4.44 | 2026-01-28 | 2026-02-03
O2-1198 - Work-around for missing tags | 2 | 16 | 16 | 2 | 2026-01-28 | 2026-01-30
O2-1220 - apx demo data preparation using OmniConnect csv bulk import | 4 | 32 | 32 | 4 | 2026-01-29 | 2026-01-31
O2-1221 - apx demo data preparation using OC batch compute and scheduled import | 0 | 0 | 0 | 0
O2-1283 - Check PS32A values scaling loss issue | 1 | 8 | 8 | 1 | 2026-02-10 | 2026-02-12
O2-1491 - check PS32A invalid tags issue | 0.38 | 3 | 3 | 0.38 | 2026-02-18 | 2026-02-18
O2-1635 - Check OC and APX issues | 0.31 | 2.5 | 2.5 | 0.31 | 2026-02-25 | 2026-02-26
O2-1247 - Parco Gunvor Demo | 0 | 0 | 12 | 1.5
O2-1404 - Fintech Fuel Demonstration | 1 | 8 | 12.5 | 1.56
O2-1725 - Fintech Fuel Demo Prep 17th Feb | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-17 | 2026-02-17
O2-1881 - Preping FintechFuel Product Review to Arsalan Avanceon | 0.31 | 2.5 | 2.5 | 0.31 | 2026-03-11 | 2026-03-12
O2-1882 - FintechFuel Product Review to Arsalan Avanceon | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-12 | 2026-03-12
O2-1978 - Fintech Fuel Demo to Mihir and Deepak | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-24
O2-1405 - Digital Log Demonstration | 0 | 0 | 1.5 | 0.19
O2-1724 - DL Demo Prep 17th Feb | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-17 | 2026-02-17
O2-2166 - ADE Stress Testing Support | 0 | 0 | 1 | 0.12
O2-2167 - ADE Stress Testing Support | 0.12 | 1 | 1 | 0.12 | 2026-04-07 | 2026-04-08
O2-223 - IP Meeting Preparation | 0 | 0 | 16 | 2
O2-337 - 1 | 0 | 0 | 0 | 0
O2-2597 - OEE Productisation Approach | 0 | 0 | 6 | 0.75
O2-2598 - Identify Productisable entities from implementation working | 0.62 | 5 | 5 | 0.62 | 2026-04-28 | 2026-04-30
O2-2599 - Develop Produstisation approach / areas | 0 | 0 | 1 | 0.12 | 2026-05-04
O2-428 - FuelAgent - value prop - ppt | 0 | 0 | 24 | 3 | 2025-10-21 | 2025-10-24
O2-483 - Fintech fuel with AI - value propt - ppt - GoAIHub.io | 0 | 0 | 17 | 2.12
O2-484 - FuelAgent - Competitive Landscape - Research PPT | 0 | 0 | 16 | 2
O2-566 - Fintech Fuel - Go AI Hub Write Up + Product Screenshots | 0 | 0 | 8 | 1
O2-613 - OmniChat Review | 0 | 0 | 24 | 3
O2-630 - Security Implementation Project Report | 0 | 0 | 8 | 1
O2-632 - Costing | 0 | 0 | 0 | 0
O2-670 - OmniAgent - Value Proposition PPT | 0 | 0 | 24 | 3
O2-671 - [Research] - OmniConnect Dashboarding Competitors | 0 | 0 | 64 | 8
O2-705 - OmniConnect Demonstration | 0 | 0 | 111.5 | 13.94
O2-1721 - OmniConnect Demo Prep 17th Feb | 0.25 | 2 | 2 | 0.25 | 2026-02-17 | 2026-02-17
O2-1722 - OmniConnect Demo Day 18th Feb | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
O2-1723 - Mihir Demo on OmniConnect | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-03 | 2026-03-03
O2-1726 - MPC Demo on OmniConnect | 0.5 | 4 | 4 | 0.5 | 2026-02-26 | 2026-02-26
O2-1729 - OmniConnect Demo prep 7th Jan | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
O2-1730 - OmniConnect Demo prep 8th Jan | 1 | 8 | 8 | 1 | 2026-01-08 | 2026-01-08
O2-1731 - OmniConnect Demo 28th Jan | 0.5 | 4 | 4 | 0.5 | 2026-01-28 | 2026-01-28
O2-1732 - OmniConnect Demo 30th Jan | 1 | 8 | 8 | 1 | 2026-01-30 | 2026-01-30
O2-1878 - Preping OmniConnect Product Review to Arsalan Avanceon | 0.38 | 3 | 3 | 0.38 | 2026-03-11 | 2026-03-12
O2-1879 - Preping APX Review to Arsalan Avanceon | 0.5 | 4 | 4 | 0.5 | 2026-03-11 | 2026-03-12
O2-1880 - OmniConnect + APX Review to Arsalan Avanceon | 0.12 | 1 | 1 | 0.12 | 2026-03-12 | 2026-03-12
O2-2258 - Product Demo 14th April | 2 | 16 | 11 | 1.38 | 2026-04-14 | 2026-04-14
O2-2508 - Product Demo to Kwang 24/04/26 | 1.5 | 12 | 12 | 1.5 | 2026-04-24 | 2026-04-24
O2-728 - OC competitive research. | 0 | 0 | 70.6 | 8.82 | 2025-12-04
O2-729 - [Research] - Fintech vs SM365 and others - Competitors | 0 | 0 | 24 | 3
O2-762 - [Presentation] - Octopus Digital Agentic IPs | 0 | 0 | 10 | 1.25
O2-763 - [Presentation] - [Diagram] - Fintech Fuel Concept | 0 | 0 | 2 | 0.25
O2-2269 - OmniEdge Diagnostics Metrics Collection | 6.12 | 49 | 50 | 6.25
O2-2270 - URS | 0 | 0 | 0 | 0
O2-2271 - DDS | 0 | 0 | 0 | 0
O2-2272 - Development | 0 | 0 | 0 | 0
O2-2273 - SQA Handover | 0 | 0 | 1 | 0.12
O2-2483 - Handover session - kamran | 0.12 | 1 | 1 | 0.12 | 2026-04-16 | 2026-04-16
O2-2274 - SQA | 3 | 24 | 24 | 3
O2-2484 - Testing BY Kamran | 3 | 24 | 24 | 3 | 2026-04-16 | 2026-04-20
O2-2275 - Production Release | 0 | 0 | 0 | 0
O2-2277 - Alarms for Batch IT Data | 80 | 640 | 368 | 46 | 2026-04-17 | 2026-04-30
O2-2281 - Research | 3 | 24 | 32 | 4 | 2026-04-17 | 2026-04-17
O2-2480 - Architecture Design | 1 | 8 | 8 | 1 | 2026-04-17 | 2026-04-17
O2-2692 - Architecture Design | 1 | 8 | 16 | 2 | 2026-04-17 | 2026-04-17
O2-2718 - Archiecture Design | 0 | 0 | 8 | 1 | 2026-04-17 | 2026-04-17
O2-2282 - Development | 24 | 192 | 152 | 19 | 2026-04-20 | 2026-04-29
O2-2481 - Batch Alarm Engine POC | 3 | 24 | 24 | 3 | 2026-04-20 | 2026-04-22
O2-2482 - Batch Alarm backend apis | 3 | 24 | 24 | 3 | 2026-04-20 | 2026-04-22
O2-2694 - Batch Alarm Backend Api Unit Testing | 2 | 16 | 16 | 2 | 2026-04-23 | 2026-04-24
O2-2695 - end to end testing and bug fixing | 2 | 16 | 16 | 2 | 2026-04-27 | 2026-04-28
O2-2719 - batch UI Design | 0 | 0 | 32 | 4 | 2026-04-20 | 2026-04-23
O2-2720 - Alarm Engine backend integration | 0 | 0 | 24 | 3 | 2026-04-24 | 2026-04-28
O2-2721 - testing and bug fixing | 0 | 0 | 16 | 2 | 2026-04-29 | 2026-04-30
O2-2283 - SQA | 2 | 16 | 0 | 0 | 2026-04-15 | 2026-04-16
O2-2284 - User Manual | 1 | 8 | 0 | 0
O2-2285 - Production Release | 0 | 0 | 0 | 0
O2-2287 - Handover | 0 | 0 | 0 | 0
O2-2288 - Bug Fixing | 0 | 0 | 0 | 0
O2-2278 - Alarms for BPM IT Data | 85 | 680 | 48 | 6 | 2026-05-04 | 2026-06-02
O2-2289 - Research | 6 | 48 | 16 | 2 | 2026-04-30 | 2026-05-04
O2-2696 - BPM alarm engine design | 2 | 16 | 16 | 2 | 2026-04-29 | 2026-04-30
O2-2290 - Development | 27 | 216 | 8 | 1 | 2026-05-05 | 2026-05-15
O2-2697 - backend api development | 0 | 0 | 8 | 1
O2-2291 - SQA | 5 | 40 | 0 | 0 | 2026-05-18 | 2026-05-22
O2-2292 - User Manual | 1 | 8 | 0 | 0
O2-2293 - Production Release | 0 | 0 | 0 | 0
O2-2294 - Handover | 0 | 0 | 0 | 0
O2-2295 - Bug Fixing | 0 | 0 | 0 | 0
O2-2279 - Alarms for Enterprise Connectors IT Data SQL | 51 | 408 | 0 | 0
O2-2298 - Research | 3 | 24 | 0 | 0
O2-2299 - Development | 15 | 120 | 0 | 0
O2-2300 - SQA | 5 | 40 | 0 | 0
O2-2301 - User Manual | 0 | 0 | 0 | 0
O2-2302 - Production Release | 0 | 0 | 0 | 0
O2-2303 - Handover | 0 | 0 | 0 | 0
O2-2304 - Bug Fixing | 0 | 0 | 0 | 0
O2-2280 - Alarms for Enterprise Connectors IT Data SAP | 51 | 408 | 0 | 0
O2-2305 - Research | 3 | 24 | 0 | 0
O2-2306 - Development | 15 | 120 | 0 | 0
O2-2307 - SQA | 5 | 40 | 0 | 0
O2-2308 - User Manual | 0 | 0 | 0 | 0
O2-2309 - Production Release | 0 | 0 | 0 | 0
O2-2310 - Handover | 0 | 0 | 0 | 0
O2-2311 - Bug Fixing | 0 | 0 | 0 | 0
O2-2296 - Alarms for Enterprise Connectors IT Data SFTP | 23.06 | 184.47 | 0 | 0
O2-2312 - Research | 3 | 24 | 0 | 0
O2-2313 - Development | 15 | 120 | 0 | 0
O2-2314 - SQA | 5 | 40 | 0 | 0
O2-2315 - User Manual | 0 | 0 | 0 | 0
O2-2316 - Production Release | 0 | 0 | 0 | 0
O2-2317 - Handover | 0 | 0 | 0 | 0
O2-2318 - Bug Fixing | 0 | 0 | 0 | 0
O2-2297 - Alarms for Enterprise Connectors IT Data Rest API | 51 | 408 | 0 | 0
O2-2319 - Research | 3 | 24 | 0 | 0
O2-2320 - Development | 15 | 120 | 0 | 0
O2-2321 - SQA | 5 | 40 | 0 | 0
O2-2322 - User Manual | 0 | 0 | 0 | 0
O2-2323 - Production Release | 0 | 0 | 0 | 0
O2-2324 - Handover | 0 | 0 | 0 | 0
O2-2325 - Bug Fixing | 0 | 0 | 0 | 0
O2-2340 - DOE Engro: Simulated Tags Experiment on Sandbox | 77.75 | 622 | 268 | 33.5 | 2026-04-03 | 2026-04-13
O2-2342 - Anomaly Detection Engine: Cost per Tag Simulation | 7 | 56 | 24 | 3 | 2026-04-03 | 2026-04-13
O2-2358 - Tag Groups Creation and Simulation | 2 | 16 | 16 | 2 | 2026-04-08 | 2026-04-09
O2-2359 - Cost per Tag Reporting | 1 | 8 | 8 | 1 | 2026-04-13 | 2026-04-13
O2-2344 - Calculated Tags Creation and Simulation | 7 | 56 | 6 | 0.75 | 2026-04-03 | 2026-04-13
O2-2679 - Testing By M.Abbas | 0.75 | 6 | 6 | 0.75 | 2026-04-11 | 2026-04-12
O2-2347 - Alarm Tags Creation and Simulation | 7 | 56 | 24 | 3 | 2026-04-03 | 2026-04-13
O2-2444 - Tags creation | 1 | 8 | 8 | 1 | 2026-04-10 | 2026-04-10
O2-2445 - Alarms configuration | 1 | 8 | 16 | 2 | 2026-04-13 | 2026-04-13
O2-2349 - Real Tags Creation and Simulation | 5 | 40 | 0 | 0 | 2026-04-03 | 2026-04-13
O2-2356 - Source Tag Creation and Setup | 0 | 0 | 0 | 0
O2-2357 - Real-time Tags Creation and Simulation | 0 | 0 | 0 | 0
O2-2350 - Read API Logic App Creation and Tags Retrieval | 0 | 0 | 36 | 4.5
O2-2360 - Logic App Creation and Simulation | 3 | 24 | 24 | 3 | 2026-04-03 | 2026-04-07
O2-2361 - Database Logs and Monitoring | 0 | 0 | 12 | 1.5
O2-2351 - Monitoring, Report Creation, and Cost Per Tag Estimation | 9 | 72 | 44 | 5.5 | 2026-04-03 | 2026-04-13
O2-2352 - Anomaly Detection ASP Experimentation Costing | 3 | 24 | 8 | 1 | 2026-04-03 | 2026-04-13
O2-2354 - Proposal and Azure Costs Estimations for 12000 Sites | 7 | 56 | 36 | 4.5 | 2026-04-03 | 2026-04-13
O2-2370 - ADE–OmniAgent AutoRCA URS (P) | 7.5 | 60 | 72 | 9
O2-2371 - ADE–OmniAgent AutoRCA URS (P) | 0 | 0 | 36 | 4.5
O2-2372 - ADE–OmniAgent AutoRCA URS (P) | 7.5 | 60 | 36 | 4.5 | 2026-04-08 | 2026-04-30
O2-2396 - Support - Totalizer Calculation Pipeline Re-do (EMF) | 13 | 104 | 424 | 53 | 2026-04-01 | 2026-05-08
O2-2397 - Documentation and Meetings | 0 | 0 | 116 | 14.5
O2-2404 - Support - Totalizer Calculation Pipeline Re-do (EMF)-Documentation and Meetings-subtask | 0 | 0 | 88 | 11
O2-2407 - Support- Read API Null and Missing Values Discussion | 0 | 0 | 28 | 3.5 | 2026-04-07 | 2026-04-17
O2-2398 - Development | 0 | 0 | 56 | 7
O2-2580 - development of landing pattern fix on totalizers | 6 | 48 | 56 | 7 | 2026-04-20 | 2026-05-10
O2-2399 - Read API Experiments and Updates | 0 | 0 | 40 | 5
O2-2409 - Experimentation to replicate the same issue | 1 | 8 | 5 | 0.62 | 2026-04-13 | 2026-04-13
O2-2410 - Totalizer tag added percentage | 4 | 32 | 24 | 3 | 2026-04-14 | 2026-04-17
O2-2411 - Logging for totalizer tags in SQL and in blob | 1 | 8 | 8 | 1 | 2026-04-17 | 2026-04-20
O2-2412 - SQL optimization and redo of tasks | 1 | 8 | 3 | 0.38 | 2026-04-13 | 2026-04-13
O2-2400 - Data Mart and ADX Comparisons | 0 | 0 | 0 | 0
O2-2401 - Unit Testing | 0 | 0 | 0 | 0
O2-2402 - SQA Handover | 0 | 0 | 0 | 0
O2-2403 - SQA | 0 | 0 | 0 | 0
O2-2496 - Streaming Pub/Sub Architecture | 48 | 384 | 0 | 0 | 2026-04-20 | 2026-05-29
O2-2497 - URS/DDS | 2 | 16 | 0 | 0 | 2026-05-04 | 2026-05-06
O2-2498 - Development | 14 | 112 | 0 | 0 | 2026-05-07 | 2026-05-25
O2-2499 - QA Handover | 1 | 8 | 0 | 0 | 2026-05-26 | 2026-05-26
O2-2500 - SQA | 0 | 0 | 0 | 0
O2-2501 - Production Release | 2 | 16 | 0 | 0 | 2026-05-28 | 2026-05-29
O2-2510 - GitHub Administration | 3 | 24 | 8 | 1 | 2026-04-01 | 2026-04-30
O2-2511 - GitHub Copilot Access and Administration | 1 | 8 | 4 | 0.5 | 2026-04-01 | 2026-04-30
O2-2512 - Copilot Access and Administration | 1 | 8 | 4 | 0.5 | 2026-04-01 | 2026-04-30
O2-2521 - Integrate Monaco Editor For SQL Support | 0 | 0 | 0 | 0
O2-2524 - Research | 0 | 0 | 0 | 0
O2-2525 - Development | 0 | 0 | 0 | 0
O2-2526 - SQA | 0 | 0 | 0 | 0
O2-2527 - User Manual | 0 | 0 | 0 | 0
O2-2528 - Production Release | 0 | 0 | 0 | 0
O2-2529 - Handover | 0 | 0 | 0 | 0
O2-2530 - Bug Fixing | 0 | 0 | 0 | 0
O2-2522 - Support for SQL Language in Batch(Features Supported by adx) | 0 | 0 | 0 | 0
O2-2531 - Research | 0 | 0 | 0 | 0
O2-2532 - Development | 0 | 0 | 0 | 0
O2-2533 - SQA | 0 | 0 | 0 | 0
O2-2534 - User Manual | 0 | 0 | 0 | 0
O2-2535 - Production Release | 0 | 0 | 0 | 0
O2-2536 - Handover | 0 | 0 | 0 | 0
O2-2537 - Bug Fixing | 0 | 0 | 0 | 0
O2-2523 - Support for SQL Language in BPM(Features Supported by adx) | 0 | 0 | 0 | 0
O2-2538 - Research | 0 | 0 | 0 | 0
O2-2539 - Development | 0 | 0 | 0 | 0
O2-2540 - SQA | 0 | 0 | 0 | 0
O2-2541 - User Manual | 0 | 0 | 0 | 0
O2-2542 - Production Release | 0 | 0 | 0 | 0
O2-2543 - Handover | 0 | 0 | 0 | 0
O2-2544 - Bug Fixing | 0 | 0 | 0 | 0
O2-2547 - ML-Based Tier 2 Diagnostics (Landing Pattern-based Alerts) | 60 | 480 | 0 | 0 | 2026-06-01 | 2026-07-10
O2-2560 - Research/URS | 10 | 80 | 0 | 0 | 2026-06-01 | 2026-06-12
O2-2561 - Development | 10 | 80 | 0 | 0 | 2026-06-15 | 2026-06-26
O2-2562 - SQA | 5 | 40 | 0 | 0 | 2026-06-29 | 2026-07-03
O2-2563 - Production Release | 5 | 40 | 0 | 0 | 2026-07-06 | 2026-07-10
O2-2549 - OmniConnect Revamped UI | 372 | 2976 | 64 | 8 | 2026-05-13 | 2026-09-21
O2-2550 - Research | 15 | 120 | 32 | 4 | 2026-05-13 | 2026-06-05
O2-2557 - Project Structure, Redux, Internationalization | 4 | 32 | 32 | 4 | 2026-04-27 | 2026-04-30
O2-2551 - Development | 92 | 736 | 0 | 0 | 2026-05-13 | 2026-08-17
O2-2552 - Handover Session | 10 | 80 | 0 | 0 | 2026-08-17 | 2026-08-17
O2-2553 - SQA | 55 | 440 | 0 | 0 | 2026-07-15 | 2026-09-24
O2-2554 - Bugs Fixing | 0 | 0 | 0 | 0
O2-2555 - User Manual | 0 | 0 | 0 | 0
O2-2556 - Production Release | 12 | 96 | 0 | 0 | 2026-09-25 | 2026-09-30
O2-2607 - APX Chiller (ChilloWatt) | 40.25 | 322 | 374 | 46.75 | 2026-05-04 | 2026-06-08
O2-2608 - Development | 0 | 0 | 180 | 22.5 | 2026-05-05
O2-2609 - Displaying Dynamic Headers for each KPI Step | 3.25 | 26 | 26 | 3.25 | 2026-05-04 | 2026-05-08
O2-2626 - API for Chillowat incorporation and APX configurational module enhancements | 0 | 0 | 32 | 4 | 2026-05-06
O2-2662 - Performance Dashboard UI for ChilloWatt | 3 | 24 | 16 | 2 | 2026-05-11 | 2026-05-13
O2-2663 - Implemented dynamic Excel Interop execution engine for ChilloWatt runtime calculations | 1 | 8 | 8 | 1 | 2026-05-05 | 2026-05-05
O2-2664 - Developed CSV-based Excel input and output mapping framework for configurable ChilloWatt models. | 1 | 8 | 8 | 1
O2-2665 - Integrated multi-chiller runtime input handling and automated Excel model population workflow. | 1 | 8 | 8 | 1 | 2026-05-07 | 2026-05-07
O2-2666 - Implemented curve data writing logic for dynamic chiller sheets using configurable CSV mappings. | 1 | 8 | 8 | 1 | 2026-05-08 | 2026-05-08
O2-2668 - Developed Excel runtime calculation and output extraction workflow for ChilloWatt execution engine. | 1 | 8 | 8 | 1 | 2026-05-11 | 2026-05-11
O2-2722 - Implemented temporary Excel model generation and runtime file handling for isolated execution processing. | 1 | 8 | 8 | 1 | 2026-05-12 | 2026-05-12
O2-2723 - Developed configurable multi-chiller asset structure and centralized CSV configuration management logic. | 1 | 8 | 8 | 1 | 2026-05-13 | 2026-05-13
O2-2731 - Updated application name, objects, logging and messages to use generic asset-based terminology for reusable multi-asset execution support instead of just ChilloWatt. | 1 | 8 | 8 | 1 | 2026-05-14 | 2026-05-14
O2-2742 - Performed comprehensive developer-level functional, integration, runtime, Excel automation, validation, and exception handling testing for the apx excel execution module. | 2 | 16 | 8 | 1 | 2026-05-15 | 2026-05-18
O2-2622 - Research | 2 | 16 | 32 | 4 | 2026-05-04 | 2026-05-06
O2-2623 - Research and evaluate approaches for integrating Excel-based calculations into C# (Interop vs alternative libraries) for ChilloWatt. | 1 | 8 | 8 | 1 | 2026-05-04 | 2026-05-04
O2-2624 - Research on Logic + Joint Discussion | 1 | 8 | 8 | 1
O2-2667 - Anomaly Detection Engine Knowledge Transfer Sessions (May 2026) | 23 | 184 | 32 | 4 | 2026-05-04 | 2026-05-08
O2-2669 - KT Session - Hamza Ali | 0 | 0 | 0 | 0
O2-2670 - KT Session - Hassan Wattoo | 3 | 24 | 16 | 2 | 2026-05-04 | 2026-05-08
O2-2671 - KT Session - Yousaf Qadri | 0 | 0 | 0 | 0
O2-2702 - Audit Trail in OmniConnect | 129.1 | 1032.8 | 0 | 0 | 2026-06-15 | 2026-10-02
O2-2703 - Research/URS | 12.5 | 100 | 0 | 0 | 2026-06-15 | 2026-09-08
O2-2704 - Development | 37.5 | 300 | 0 | 0 | 2026-06-22 | 2026-09-18
O2-2705 - SQA | 0 | 0 | 0 | 0 | 2026-07-06 | 2026-10-02
O2-33 - APX Template Enhancement | 179.88 | 1439 | 1515.34 | 189.42
O2-38 - Research/URS (P) | 0 | 0 | 0 | 0 | 2025-09-15 | 2025-09-19
O2-39 - Research/DDS | 18 | 144 | 119.67 | 14.96 | 2025-10-08 | 2025-11-19
O2-186 - Discussion for Solution | 0 | 0 | 16 | 2
O2-203 - Understanding The URS | 0 | 0 | 12 | 1.5
O2-252 - Design Document template creation using AI | 0 | 0 | 15 | 1.88
O2-268 - Content Generation for DDS Design Overview Using AI | 0 | 0 | 8 | 1
O2-280 - Generated Content Integration in the Document with Formatting | 0 | 0 | 14 | 1.75
O2-319 - New Asset Sub types setup for Template for process team | 0 | 0 | 2 | 0.25
O2-371 - Generate DDS Sequence diagram through AI | 0 | 0 | 1.67 | 0.21
O2-573 - Generate ERD Diagram using AI Plant UML | 0 | 0 | 5 | 0.62
O2-574 - Generate Flow Diagrams | 0 | 0 | 8 | 1
O2-575 - Finalize Content of DDS | 0 | 0 | 8 | 1
O2-639 - Finalizing and changes after review from lead | 0 | 0 | 22 | 2.75
O2-40 - Development | 90 | 720 | 451 | 56.38 | 2025-11-20 | 2026-01-02
O2-690 - Schema changes for Additional Property with Scaffolding | 0 | 0 | 3 | 0.38
O2-691 - API Developments CRUD for Additional Property | 0 | 0 | 36 | 4.5
O2-692 - Development + API Integrations + Unit Testing | 0 | 0 | 8 | 1
O2-693 - Dynamic Headers Table UI Development | 14 | 112 | 112 | 14 | 2025-11-21 | 2026-01-02
O2-725 - APx Step Template API Development Modification | 0 | 0 | 32 | 4
O2-726 - APx Asset API Modification to incorporate Additional Properties | 0 | 0 | 16 | 2
O2-766 - Schema Changes to add APx Curve Section | 0 | 0 | 4 | 0.5
O2-767 - APx Curve Template API modification , Include Sections as well | 0 | 0 | 20 | 2.5
O2-786 - APx Curve Modal APIs modification , Include Sections as well | 0 | 0 | 24 | 3
O2-795 - APX GetAllAsssets API optimization - Performance bottleneck | 0 | 0 | 24 | 3
O2-796 - APx Activation API Modification to incorporate Curve Data manipulation for IsAppendable and Sections | 0 | 0 | 13 | 1.62 |  | 2025-12-30
O2-834 - Unit Testing for APx Performance Modal | 0 | 0 | 8 | 1
O2-905 - APX Engine - Steam table integration in APX Performance via Ebsilon engine | 1 | 8 | 8 | 1 | 2026-01-13 | 2026-01-13
O2-41 - SQA | 45 | 360 | 159 | 19.88 | 2026-01-05 | 2026-01-15
O2-546 - OC Process Testing (P) | 3 | 24 | 24 | 3 | 2026-01-12 | 2026-01-14
O2-547 - Re-do for Existing Asset (P) | 1 | 8 | 5 | 0.62 | 2026-01-15 | 2026-01-15
O2-853 - Character Limit Missing on Property Name and Property value Field | 0 | 0 | 28 | 3.5
O2-854 - No Validation Message Shown When Adding Duplicate Property | 0 | 0 | 4 | 0.5
O2-855 - Asset type and subtype for which template is created, not displaying while creating an APX asset using that asset type and subtype. | 0 | 0 | 0 | 0
O2-874 - Input mapping rows added in template are not displaying in configuration of APX asset. | 0 | 0 | 5 | 0.62
O2-875 - Character limit is not implemented same as applied in old APX asset configurations. | 0 | 0 | 0 | 0
O2-876 - Row details are randomly swapping between its own fields in design data, input variable mapping and output variable mapping tabs while creating headers and rows. | 0 | 0 | 1 | 0.12
O2-877 - Deactivation or clear configuration against APX asset is not working. | 0 | 0 | 5 | 0.62
O2-878 - Added Steps Disappear After Saving in Template Configuration Tab | 0.38 | 3 | 3 | 0.38 | 2026-01-13 | 2026-01-13
O2-879 - Add Apx Additional properties in VM API Calls | 0 | 0 | 9 | 1.12
O2-880 - Bug Fixing | 0 | 0 | 12 | 1.5
O2-881 - Property names and options should be restricted in import site layout while creating APX asset using template also the property for which complete template is not defined they should be restricted as well from front end. | 0 | 0 | 0 | 0
O2-882 - The UI becomes misaligned on the Template Configuration tab when a dropdown field is selected. Upon selection, the dropdown field located beneath the selected dropdown unexpectedly shifts its position, causing layout disturbance. | 0 | 0 | 0 | 0
O2-883 - APX asset name is getting changed. | 0 | 0 | 0 | 0
O2-895 - Export Site Layout file is not downloading. | 0.5 | 4 | 1 | 0.12 | 2026-01-15 | 2026-01-15
O2-918 - Coordination with Process Team over APx Template | 0 | 0 | 5 | 0.62
O2-43 - Production Release | 5 | 40 | 12 | 1.5 | 2026-01-16 | 2026-01-19
O2-712 - User Manual | 2 | 16 | 16 | 2 | 2026-01-05 | 2026-01-15
O2-34 - Scheduled Pulls from Data Source (SQL OT) | 50 | 400 | 496 | 62
O2-48 - Research/URS | 1 | 8 | 8 | 1 | 2025-09-15 | 2025-09-15
O2-49 - Research/DDS | 1 | 8 | 8 | 1 | 2025-09-16 | 2025-09-16
O2-50 - Development | 40 | 320 | 164 | 20.5 | 2025-09-17 | 2025-09-26
O2-147 - Modify Existing API For Connectors | 0 | 0 | 8 | 1
O2-148 - Modify Existing API For Pipelines | 0 | 0 | 8 | 1
O2-149 - Modify Existing API For Triggers | 0 | 0 | 8 | 1
O2-150 - Modify Current SQL Schema | 0 | 0 | 0 | 0
O2-196 - Development OC Frontend | 0 | 0 | 40 | 5
O2-240 - Anomaly Detection V3 OCM Development | 0 | 0 | 36 | 4.5 |  | 2025-10-17
O2-74 - DB Design and Pipeline Design | 0 | 0 | 0 | 0
O2-75 - Implementation | 0 | 0 | 48 | 6
O2-76 - Dev Unit Testing | 0 | 0 | 0 | 0
O2-51 - SQA | 4 | 32 | 32 | 4 | 2025-09-29 | 2025-10-02
O2-52 - User Manual | 1 | 8 | 8 | 1 | 2025-10-01 | 2025-10-02
O2-53 - Production Release | 3 | 24 | 28 | 3.5 | 2025-10-03 | 2025-10-03
O2-35 - OmniAgent Phase 2.1 ( APX Perf, What-if, Health ) | 51 | 408 | 804 | 100.5
O2-377 - API Enrichment | 6 | 48 | 124 | 15.5 | 2025-10-23 | 2025-11-17
O2-395 - APx And BPM Discussion | 0 | 0 | 4 | 0.5
O2-634 - FE and BE Development - OmniAgent APX | 0 | 0 | 88 | 11
O2-731 - OmniAgent PPT for Tom and Some enrichments | 0 | 0 | 32 | 4
O2-57 - SQA | 20 | 160 | 122 | 15.25 | 2025-11-19 | 2025-11-20
O2-1017 - ADE / APXH Improvements Testing (P) | 3 | 24 | 24 | 3 | 2026-01-05 | 2026-01-30
O2-623 - Rmapped name is displaying instead of user selected tag names against parameters. | 0 | 0 | 24 | 3
O2-624 - Response is not correct for APX asset in omni agent. Whether it should display data or it should tell that only output cal tag data for performance asset can be seen. | 0 | 0 | 16 | 2
O2-625 - Wrong response is given as I have asked about health parameters and it has given me performance output parameters, omni agent is restricted for health APX asset so it should response accordingly. | 0 | 0 | 16 | 2
O2-629 - Table view is not created in omni agent APX. | 0 | 0 | 0 | 0
O2-640 - Downloaded CSV file and sheet name should be user friendly against APX data details in omni agent. | 0 | 0 | 0 | 0
O2-643 - User friendly error message should display on frontend when CSV file link is expired and it is clicked again rather than displaying backend error in a new tab. | 0 | 0 | 0 | 0
O2-654 - Response is not given against asked query in APX omni agent. | 0 | 0 | 0 | 0
O2-658 - Omni agent for APX is giving response for health asset as well where as it is restricted for now. | 0 | 0 | 0 | 0
O2-681 - Omni agent is not giving correct answer for APX health asset. | 0 | 0 | 0 | 0
O2-58 - User Manual | 20 | 160 | 24 | 3 | 2025-11-19 | 2025-11-20
O2-641 - How To - APX <> OmniAgent | 0 | 0 | 8 | 1
O2-642 - Fields - APX <> OmniAgent | 0 | 0 | 16 | 2
O2-59 - Production Release | 2 | 16 | 8 | 1 | 2025-11-21 | 2025-11-21
O2-36 - Unified Notification Engine | 37 | 296 | 16 | 2 | 2026-04-13 | 2026-05-06
O2-60 - Research/URS | 2 | 16 | 8 | 1 | 2026-04-13 | 2026-04-14
O2-2077 - Requirements gathering and finalizing | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-01
O2-61 - Research/DDS | 5 | 40 | 0 | 0 | 2026-04-15 | 2026-04-16
O2-62 - Development | 7 | 56 | 0 | 0 | 2026-04-17 | 2026-04-30
O2-63 - SQA | 3 | 24 | 0 | 0 | 2026-05-04 | 2026-05-06
O2-64 - Production Release | 0 | 0 | 0 | 0 | 2026-05-07 | 2026-05-08
O2-65 - User Manual | 0 | 0 | 0 | 0
O2-37 - Anomaly Detection Engine Enrichment | 152 | 1216 | 1869.14 | 233.64
O2-1171 - Optimizing Anomaly Results Data Insertion in ADX | 3 | 24 | 24 | 3 | 2026-01-19 | 2026-01-21
O2-1172 - Stopped insertion in SQL database in all function apps | 1 | 8 | 8 | 1 | 2026-01-19 | 2026-01-19
O2-1173 - Update Read API payload to fetch the data from ADX database tables | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
O2-1174 - Read APi integeration at omniconnect backend | 0.5 | 4 | 4 | 0.5 | 2026-01-21 | 2026-01-21
O2-1175 - Testing the Read API functionality from anomaly detection results module on omniconnect | 1 | 8 | 4 | 0.5 | 2026-01-21 | 2026-01-21
O2-1553 - Read API Support | 3 | 24 | 16.5 | 2.06 | 2026-01-12 | 2026-02-23
O2-1555 - Filtering Response for Anomaly Predictors Values | 1 | 8 | 2 | 0.25 | 2026-02-13 | 2026-02-13
O2-1556 - Updated Correlation Matrix for Anomaly Configuration | 1 | 8 | 8 | 1 | 2026-01-12 | 2026-01-12
O2-1581 - Filtering Response for Anomaly Predicted Values | 1 | 8 | 6.5 | 0.81 | 2026-02-23 | 2026-02-23
O2-497 - Research/URS (P) | 0 | 0 | 40 | 5 | 2025-09-15 | 2025-09-22
O2-2072 - ADE Enhancement rev 3.0 - March | 1.5 | 12 | 12 | 1.5 | 2026-03-30 | 2026-03-31
O2-2073 - ADE Enhancement rev 3.0 - April | 4 | 32 | 28 | 3.5 | 2026-04-01 | 2026-04-10
O2-502 - Make Training Material (P) | 25 | 200 | 192 | 24 | 2025-11-17 | 2025-12-31
O2-1415 - Make Training Material (P) | 10 | 80 | 64 | 8 | 2026-01-01 | 2026-01-30
O2-67 - Research/DDS | 3 | 24 | 24 | 3 | 2025-09-29 | 2025-10-01
O2-172 - Research/DDS | 3 | 24 | 24 | 3
O2-68 - Development | 33 | 264 | 132 | 16.5 | 2025-10-01 | 2025-10-13
O2-340 - OCM Frontend Integration Anomaly | 0 | 0 | 16 | 2 | 2025-10-01 | 2025-10-17
O2-370 - Handover to QA | 0 | 0 | 4 | 0.5
O2-374 - OCM Anomaly V3 Internal Bugs/Improvements | 0 | 0 | 32 | 4 | 2025-10-21 | 2025-10-30
O2-544 - OC Process Testing (P) | 0 | 0 | 0 | 0
O2-69 - SQA | 15 | 120 | 278.07 | 34.76 | 2025-10-20 | 2025-11-13
O2-568 - Anomaly Error: Failed to save the anomaly Data selection time slot. while we select multiple time slots to verify 720 hours to be available in timeslots. | 0 | 0 | 3 | 0.38
O2-570 - As mentioned in both info notes "You can select a maximum of 720 hours of data for training." we are not able to select 720 hours of data for training. | 0 | 0 | 2.5 | 0.31 | 2025-11-03
O2-571 - Float type tag values are not getting updated | 0 | 0 | 1 | 0.12
O2-580 - Correlation Matrix should not be disabled when model is running or stopped. | 0 | 0 | 8 | 1 | 2025-11-12 | 2025-11-12
O2-581 - There is duplication in anomaly group results on OmniConnect and in export file of anomaly also. | 0 | 0 | 0 | 0 | 2025-11-04
O2-588 - Error is displaying instead of data for anomaly Analysis, for the time when there was data available. | 0 | 0 | 34 | 4.25
O2-590 - Now its showing error on "Create Model" screen with success message, right after clicking the next button of data selection screen. and "Generated Models Summary" is also Missing. | 0 | 0 | 5 | 0.62
O2-595 - Error is getting displayed right after when user clicks on the next button Goes to the "Create Model" screen, and here is another issue now, this time Correlation Matrix is missing when we click on its button, Kindly look into it ⁠ | 0 | 0 | 1 | 0.12
O2-597 - Anomaly Results Are not getting displayed | 0 | 0 | 0 | 0
O2-598 - Correlation Matrix Values are overlapping while user clicks on its button, in LCD mood | 0 | 0 | 8.5 | 1.06 | 2025-11-07 | 2025-11-07
O2-626 - While using Cal tag in Anomaly group creation, NO data is getting displayed in "Correlation Matrix". | 0 | 0 | 0 | 0
O2-633 - Anomaly Groups are getting created while all permissions are off and Only read permission is allowed When Create permission is off and all other are allowed | 0 | 0 | 7 | 0.88 | 2025-11-13 | 2025-11-13
O2-635 - Production Sanity | 20 | 160 | 136.57 | 17.07 | 2025-11-13 | 2025-11-14
O2-637 - While stopping the model its giving an error " There is no model created for this group " while model is in running state. its on the group which is having call tag in it. | 0 | 0 | 0 | 0
O2-645 - Write back FAIL, NO Vales are getting fetched on front End, But Simulator is working properly. | 0 | 0 | 0 | 0
O2-646 - Anomaly Analysis are Failed | 0 | 0 | 1 | 0.12
O2-647 - OMNI Agent is returning non-existing tags. | 0 | 0 | 0 | 0
O2-649 - Anomaly Failed Again | 0 | 0 | 1 | 0.12
O2-650 - Stats Alarms are getting displayed for the time when site wasn't even created | 0 | 0 | 0 | 0
O2-70 - User Manual | 15 | 120 | 24 | 3 | 2025-10-20 | 2025-11-13
O2-173 - User Manual | 0 | 0 | 0 | 0
O2-365 - How to - Anomaly Detection Updates | 0 | 0 | 16 | 2
O2-366 - Fields - Anomaly Detection Updates | 0 | 0 | 8 | 1
O2-71 - Production Release | 1 | 8 | 16 | 2 | 2025-11-14 | 2025-11-14
O2-848 - Anomaly Detection Improvements | 0 | 0 | 152 | 19 | 2026-01-01 | 2026-01-06
O2-1569 - Integrated the new required changes | 1 | 8 | 8 | 1 | 2026-01-02 | 2026-01-02
O2-1570 - Requirement gathering + Meetings | 1 | 8 | 8 | 1 | 2026-01-01 | 2026-01-01
O2-1713 - updated the APIs | 5 | 40 | 0 | 0
O2-858 - Added Correlation Matrix on Data Selection + Testing | 1 | 8 | 8 | 1 | 2026-01-05 | 2026-01-05
O2-859 - Tested whole Flow, Deployed on Staging and Resolved Bugs | 1 | 8 | 8 | 1 | 2026-01-06 | 2026-01-06
O2-398 - Centrifugal Compressor (Fixed Speed) | 5.25 | 42 | 244 | 30.5 | 2025-06-30 | 2025-07-13
O2-399 - Asset Design, HB and Expected models (P) | 0 | 0 | 40 | 5 | 2025-06-30 | 2025-07-06
O2-400 - Development (if required) | 0 | 0 | 0 | 0
O2-401 - Template, wizards and dashboard design (P) | 0 | 0 | 40 | 5 | 2025-07-07 | 2025-07-13
O2-402 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-403 - OC Process testing (P) | 0 | 0 | 32 | 4 | 2026-01-15 | 2026-01-20
O2-1427 - OC Process testing (P) | 4 | 32 | 32 | 4 | 2026-01-15 | 2026-01-20
O2-404 - SQA | 0 | 0 | 0 | 0
O2-405 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-406 - User Manual | 0 | 0 | 0 | 0
O2-407 - Production Release | 0 | 0 | 10 | 1.25
O2-1611 - OC Template (P) | 1 | 8 | 8 | 1
O2-1612 - Process testing (P) | 0.25 | 2 | 2 | 0.25
O2-408 - Centrifugal Compressor (Multi Speed) | 5.25 | 42 | 264 | 33 | 2025-07-28 | 2025-08-10
O2-409 - Asset Design, HB and Expected models (P) | 0 | 0 | 40 | 5 | 2025-07-28 | 2025-08-03
O2-410 - Development (if required) | 0 | 0 | 0 | 0
O2-411 - Template, wizards and dashboard design (P) | 0 | 0 | 40 | 5 | 2025-08-04 | 2025-08-10
O2-412 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-413 - OC Process testing (P) | 0 | 0 | 32 | 4
O2-1426 - OC Process testing (P) | 4 | 32 | 32 | 4 | 2026-01-21 | 2026-01-26
O2-414 - SQA | 0 | 0 | 0 | 0
O2-415 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-416 - User Manual | 0 | 0 | 0 | 0
O2-417 - Production Release | 0 | 0 | 20 | 2.5
O2-1615 - OC Template (P)- Faiq | 0.5 | 4 | 8 | 1
O2-1616 - OC Template (P)- Wasi | 0.5 | 4 | 4 | 0.5 | 2026-02-25 | 2026-02-25
O2-1617 - Process testing (P)- Faiq | 0.12 | 1 | 7 | 0.88
O2-1618 - Process testing (P)- Wasi | 0.12 | 1 | 1 | 0.12 | 2026-02-25 | 2026-02-26
O2-418 - Simple Heat Exchangers | 11.38 | 91 | 202 | 25.25 |  | 2025-10-12
O2-419 - Asset Design, HB and Expected models (P) | 0 | 0 | 8 | 1 | 2025-09-15 | 2025-10-12
O2-420 - Development (if required) | 0 | 0 | 0 | 0
O2-421 - Template, wizards and dashboard design (P) | 0 | 0 | 3 | 0.38 | 2025-09-29 | 2025-10-06
O2-1761 - Template, wizards and dashboard design (P) | 0.5 | 4 | 3 | 0.38 | 2026-03-02 | 2026-03-28
O2-422 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-423 - OC Process testing (P) | 5 | 40 | 59.5 | 7.44 | 2026-01-19 | 2026-01-23
O2-1760 - OC Process testing (P) | 0.5 | 4 | 3.5 | 0.44 | 2026-03-02 | 2026-03-28
O2-1966 - OC Process testing (P) - Faiq | 0 | 0 | 6 | 0.75
O2-2070 - OC Process testing (P) - DA | 1.5 | 12 | 10 | 1.25
O2-424 - SQA | 0 | 0 | 0 | 0
O2-425 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-426 - User Manual | 0 | 0 | 0 | 0 | 2025-10-02 | 2025-10-03
O2-427 - Production Release | 0 | 0 | 30.5 | 3.81
O2-1590 - OC template (P) | 1.5 | 12 | 12 | 1.5 | 2026-02-23 | 2026-02-26
O2-1591 - Process Testing (P) | 0.38 | 3 | 6.5 | 0.81 | 2026-02-25 | 2026-03-03
O2-2168 - Data Prep for Demo (P) | 2 | 16 | 12 | 1.5
O2-441 - Water Cooled Steam Condenser | 6.62 | 53 | 66 | 8.25
O2-442 - Asset Design, HB and Expected models (P) | 0 | 0 | 0 | 0 | 2025-09-15 | 2025-09-26
O2-443 - Development (if required) | 0 | 0 | 0 | 0
O2-444 - Template, wizards and dashboard design (P) | 0 | 0 | 0 | 0 | 2025-09-29 | 2025-10-06
O2-445 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-446 - OC Process testing (P) | 3 | 24 | 24 | 3 | 2026-01-19 | 2026-01-21
O2-1417 - OC Process testing (P) | 3 | 24 | 24 | 3 | 2026-01-19 | 2026-01-21
O2-447 - SQA | 0 | 0 | 0 | 0
O2-448 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-449 - User Manual | 0 | 0 | 0 | 0
O2-450 - Production Release | 0 | 0 | 9 | 1.12
O2-1652 - OC Template (P) | 0.5 | 4 | 4 | 0.5
O2-1653 - Process Testing (P) | 0.12 | 1 | 5 | 0.62
O2-452 - Cooling Tower | 7.75 | 62 | 137 | 17.12
O2-465 - Asset Design, HB and Expected models (P) | 0 | 0 | 0 | 0 | 2025-09-15 | 2025-09-26
O2-466 - Development (if required) | 0 | 0 | 0 | 0
O2-467 - Template, wizards and dashboard design (P) | 0 | 0 | 12 | 1.5 | 2025-09-29 | 2025-10-06
O2-2062 - Template Optimizations | 0.5 | 4 | 4 | 0.5 | 2026-03-31 | 2026-03-31
O2-2067 - Template Optimizations | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-02
O2-468 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-469 - OC Process testing (P) | 0 | 0 | 40 | 5 | 2026-01-19 | 2026-01-23
O2-1431 - OC Process testing (P) | 5 | 40 | 40 | 5 | 2026-01-19 | 2026-01-23
O2-470 - SQA | 0 | 0 | 0 | 0
O2-471 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-472 - User Manual | 0 | 0 | 0 | 0
O2-473 - Production Release | 0 | 0 | 13 | 1.62
O2-1605 - OC template (P) | 1 | 8 | 8 | 1 | 2026-02-23 | 2026-02-25
O2-1606 - Process Testing (P) | 0.25 | 2 | 5 | 0.62 | 2026-02-24 | 2026-02-27
O2-453 - Boiler | 17.25 | 138 | 354 | 44.25 |  | 2025-10-16
O2-474 - Asset Design, HB and Expected models (P) | 11 | 88 | 104 | 13 | 2025-09-23 | 2025-10-12
O2-1428 - Asset Design, HB and Expected models (P) | 2 | 16 | 16 | 2
O2-475 - Development (if required) | 0 | 0 | 0 | 0
O2-476 - Template, wizards and dashboard design (P) | 0 | 0 | 32 | 4 | 2025-10-13 | 2025-10-16
O2-477 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-478 - OC Process testing (P) | 0 | 0 | 24 | 3
O2-1423 - OC Process Testing (P) | 3 | 24 | 24 | 3 | 2026-01-27 | 2026-01-29
O2-479 - SQA | 0 | 0 | 0 | 0
O2-480 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-481 - User Manual | 0 | 0 | 0 | 0
O2-482 - Production Release | 0 | 0 | 17 | 2.12
O2-1648 - OC Template - Coal (P) | 0.5 | 4 | 5 | 0.62
O2-1649 - OC Template - NG (P) | 0.5 | 4 | 4 | 0.5
O2-1650 - Process Testing - NG (P) | 0.12 | 1 | 4 | 0.5
O2-1651 - Process Testing - Coal (P) | 0.12 | 1 | 4 | 0.5
O2-456 - OC Trending V2 | 64 | 512 | 0 | 0 | 2026-09-28 | 2026-11-05
O2-505 - Research/URS (P) | 0 | 0 | 0 | 0
O2-506 - Research/DDS | 5 | 40 | 0 | 0 | 2026-09-28 | 2026-10-02
O2-507 - Development | 19 | 152 | 0 | 0 | 2026-10-05 | 2026-10-23
O2-509 - SQA | 5 | 40 | 0 | 0 | 2026-10-26 | 2026-10-30
O2-510 - Make Training Material | 0 | 0 | 0 | 0
O2-548 - Production Release | 3 | 24 | 0 | 0 | 2026-10-30 | 2026-11-05
O2-549 - User Manual | 0 | 0 | 0 | 0
O2-457 - APX Visualisations Enhancements | 145.56 | 1164.5 | 499 | 62.38 | 2026-01-26 | 2026-03-03
O2-1397 - QA-Handover | 0.62 | 5 | 5 | 0.62 | 2026-02-17 | 2026-02-17
O2-1398 - Kamran | 0.12 | 1 | 1 | 0.12 | 2026-02-17 | 2026-02-17
O2-1399 - Zeeshan | 0.12 | 1 | 1 | 0.12 | 2026-02-17 | 2026-02-17
O2-1400 - Abbas | 0.12 | 1 | 1 | 0.12 | 2026-02-17 | 2026-02-17
O2-1401 - Namra | 0.12 | 1 | 1 | 0.12 | 2026-02-17 | 2026-02-17
O2-1402 - waqar | 0.12 | 1 | 1 | 0.12 | 2026-02-17 | 2026-02-17
O2-513 - Research/URS (P) | 0 | 0 | 0 | 0 | 2025-10-06 | 2025-10-17
O2-514 - Research/DDS | 15 | 120 | 98 | 12.25 | 2026-01-26 | 2026-01-30
O2-1176 - Research/Discussion for Solution | 5 | 40 | 29 | 3.62 | 2026-01-26 | 2026-01-30
O2-1193 - Research on using different Dashboard | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
O2-1194 - Discussion on All PPT Dashboard Files | 1 | 8 | 8 | 1 | 2026-01-27 | 2026-01-27
O2-1267 - Backend API's Integration | 2 | 16 | 16 | 2 | 2026-01-28 | 2026-02-02
O2-1275 - Requirement gathering and management | 5 | 40 | 32 | 4 | 2026-02-02 | 2026-02-02
O2-1572 - Testing of API's | 0.62 | 5 | 5 | 0.62 | 2026-02-02 | 2026-02-02
O2-515 - Development | 15 | 120 | 61.5 | 7.69 | 2026-02-02 | 2026-02-23
O2-1232 - Dashboard Template Builder UI & API | 3 | 24 | 14 | 1.75 | 2026-02-02 | 2026-02-04
O2-1294 - API Update for Performance Dashboard | 1 | 8 | 5 | 0.62 | 2026-02-06 | 2026-02-06
O2-1295 - Structure for Dashboard from Template Dev OC Frontend | 3 | 24 | 18 | 2.25 | 2026-02-09 | 2026-02-11
O2-1296 - Read API integration for historic data display on dashboard graphs | 2 | 16 | 12.5 | 1.56 | 2026-02-12 | 2026-02-13
O2-1376 - Optimizing the chart rendering logic in html template | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
O2-1412 - Code Merging, Staging Deployment & Handover Session | 0.5 | 4 | 4 | 0.5 | 2026-02-17 | 2026-02-17
O2-551 - OC Process Testing (P) | 0 | 0 | 0 | 0
O2-517 - SQA | 5 | 40 | 50.5 | 6.31 | 2026-02-18 | 2026-02-27
O2-1368 - Testing By Zeeshan | 5 | 40 | 37.5 | 4.69 | 2026-02-23 | 2026-02-27
O2-1677 - Support | 2 | 16 | 13 | 1.62 | 2026-03-03 | 2026-03-05
O2-518 - Make Training Material (P) | 5 | 40 | 0 | 0 |  | 2026-02-27
O2-519 - User Manual | 3 | 24 | 0 | 0 | 2026-02-18 | 2026-02-27
O2-520 - Production Release | 10 | 80 | 34.5 | 4.31 | 2026-03-17 | 2026-03-19
O2-1925 - Testing by Zeeshan | 3 | 24 | 25 | 3.12 | 2026-03-17 | 2026-03-19
O2-1926 - Deployment + Unit Testing + DB Changes/Migrations | 0.44 | 3.5 | 3.5 | 0.44 | 2026-03-17 | 2026-03-17
O2-1927 - Production Green Deployment | 0.38 | 3 | 3 | 0.38 | 2026-03-17 | 2026-03-17
O2-2043 - Production Blue Environment | 0.38 | 3 | 3 | 0.38 | 2026-03-31 | 2026-03-31
O2-458 - APX Performance Module Enhancements | 0 | 0 | 40 | 5
O2-521 - Research/URS (P) | 0 | 0 | 20 | 2.5 | 2025-09-01 | 2025-09-07
O2-522 - Research/DDS | 0 | 0 | 0 | 0
O2-523 - Development | 0 | 0 | 0 | 0
O2-552 - OC Process Testing (P) | 0 | 0 | 0 | 0
O2-524 - SQA | 0 | 0 | 0 | 0
O2-526 - Make Training Material (P) | 0 | 0 | 0 | 0
O2-527 - User Manual | 0 | 0 | 0 | 0
O2-528 - Production Release | 0 | 0 | 0 | 0
O2-459 - Centrifugal Pump Health Module Update (P) | 46.4 | 371.17 | 463 | 57.88 | 2025-10-27 | 2026-05-10
O2-2068 - Development | 5 | 40 | 32.5 | 4.06 | 2026-03-30 | 2026-04-07
O2-2078 - Update Health Activation API | 0.88 | 7 | 7 | 0.88 | 2026-03-30 | 2026-03-31
O2-2079 - Update all Status Check APIs | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-02
O2-2080 - Update Health Model Creation Request API | 0 | 0 | 6 | 0.75 | 2026-04-02 | 2026-04-03
O2-2107 - Overview code to incorporate requirements | 0.38 | 3 | 3 | 0.38 | 2026-03-31 | 2026-03-31
O2-2173 - Update Digital twin APIs | 0.69 | 5.5 | 5.5 | 0.69 | 2026-04-06 | 2026-04-07
O2-2330 - Testing for VM calls with Process Team Coordination | 0.38 | 3 | 3 | 0.38 | 2026-04-15 | 2026-04-15
O2-2331 - Handover to QA | 0.06 | 0.5 | 0 | 0 | 2026-04-15 | 2026-04-15
O2-2332 - Production Release | 2 | 16 | 0 | 0
O2-2333 - Bug Fixing | 0 | 0 | 0 | 0
O2-2341 - SQA | 0 | 0 | 0 | 0 | 2026-04-15
O2-529 - Tags, Groups, FMEA, Alerts Update | 8 | 64 | 64 | 8 | 2025-12-26 | 2026-01-07
O2-1419 - Tags, Groups, FMEA, Alerts Update | 8 | 64 | 32 | 4 | 2025-12-26 | 2026-01-07
O2-530 - Template Update | 2 | 16 | 31 | 3.88 | 2026-01-12 | 2026-01-13
O2-1424 - Template Update | 2 | 16 | 31 | 3.88 | 2026-01-12 | 2026-01-13
O2-531 - OC testing | 3 | 24 | 24 | 3 | 2026-01-14 | 2026-01-16
O2-554 - OC Process Testing (P) | 3 | 24 | 24 | 3 | 2026-01-14 | 2026-01-16
O2-534 - Make Training Material | 0.02 | 0.17 | 80 | 10 | 2026-01-05 | 2026-01-30
O2-1002 - Create Assets, Tags, simulator, assign alerts | 5 | 40 | 40 | 5 | 2026-01-05 | 2026-01-09
O2-1003 - Make Training Material | 5 | 40 | 40 | 5 | 2026-01-22 | 2026-01-28
O2-460 - Auxiliary Load Advisor (OmniALA) | 20.19 | 161.5 | 335 | 41.88 | 2025-10-30 | 2025-11-07
O2-2124 - Research/DDS | 0 | 0 | 57.5 | 7.19 | 2026-04-06
O2-2125 - Walk-through session with process team | 1 | 8 | 8 | 1 | 2026-04-06 | 2026-04-06
O2-2128 - Omni Alla Walkthrough | 0.31 | 2.5 | 2.5 | 0.31 | 2026-04-06 | 2026-04-06
O2-2136 - Walk-through session with process team | 0.25 | 2 | 2 | 0.25 | 2026-04-06 | 2026-04-06
O2-2182 - OmniAla Walkthrough Session + Discussion | 0.62 | 5 | 5 | 0.62 | 2026-04-06 | 2026-04-06
O2-2184 - DDS Discussion + prepared OmniAla ERD | 1 | 8 | 8 | 1 | 2026-04-07 | 2026-04-07
O2-2185 - DDS(Added Content + Prepared Flowchart) | 1 | 8 | 8 | 1 | 2026-04-08 | 2026-04-08
O2-2250 - Walk-through session with process team (P) | 0.5 | 4 | 4 | 0.5
O2-2362 - DDS(Added Sequence Diagram +ERD) | 1 | 8 | 8 | 1 | 2026-04-09 | 2026-04-09
O2-2465 - Omni-ALA Walk through Sessions + Discussion | 1.5 | 12 | 12 | 1.5 | 2026-04-20 | 2026-04-21
O2-487 - User Requirement Specifications | 10 | 80 | 86 | 10.75 | 2025-10-30 | 2025-12-31
O2-488 - Pre-URS Engineering | 3 | 24 | 24 | 3 | 2025-09-08 | 2025-09-30
O2-461 - Cooling Tower Advisor | 5 | 40 | 32 | 4
O2-485 - Pre-URS Engineering | 5 | 40 | 16 | 2 | 2025-09-01
O2-486 - User Requirement Specifications | 0 | 0 | 0 | 0
O2-462 - Pumps Operating OC Advisor (like DEWA) | 0 | 0 | 0 | 0 | 2025-03-20 | 2025-04-10
O2-463 - Pre-URS Engineering | 0 | 0 | 0 | 0
O2-464 - User Requirement Specifications | 0 | 0 | 0 | 0
O2-600 - MPCL - APX | 0 | 0 | 2464 | 308 |  | 2025-11-30
O2-601 - APX Reliability | 0 | 0 | 704 | 88 | 2025-04-01 | 2025-11-30
O2-602 - APX - Strainer | 0 | 0 | 352 | 44 | 2025-06-02 | 2025-07-31
O2-603 - APX - Foaming | 0 | 0 | 176 | 22 | 2025-09-01 | 2025-09-30
O2-697 - Calculated Tags Enhancements (With No Code) | 116.7 | 933.6 | 373 | 46.62 | 2026-05-04 | 2026-05-29
O2-1362 - Development Web | 5 | 40 | 14.5 | 1.81 | 2026-05-04 | 2026-05-08
O2-1363 - cal tags no code - dev web - Dependency Matrix nested calculations | 0 | 0 | 0 | 0
O2-1364 - cal tags no code - dev - counter tag 2nd condition and reset condition | 0 | 0 | 0 | 0
O2-1379 - cal tags no code - dev - prepare data locally for nested tags | 2 | 16 | 14.5 | 1.81 | 2026-02-10 | 2026-02-20
O2-2211 - QA Handover | 1 | 8 | 0 | 0 | 2026-05-22 | 2026-05-22
O2-698 - SQA | 12 | 96 | 0 | 0 | 2026-05-22 | 2026-05-29
O2-1365 - Counter Tag | 3 | 24 | 0 | 0 | 2026-05-22 | 2026-05-26
O2-1366 - Timer Tag | 3 | 24 | 0 | 0 | 2026-05-27 | 2026-05-29
O2-1367 - Calculated Tag | 5 | 40 | 0 | 0 | 2026-05-22 | 2026-05-29
O2-700 - Development | 15 | 120 | 88 | 11 | 2026-02-16 | 2026-02-20
O2-1322 - cal tags no code - dev - Calculated tags unconditional | 0 | 0 | 0 | 0
O2-1323 - cal tags no code - dev - Calculated tags conditional | 0 | 0 | 0 | 0
O2-1324 - cal tags no code - dev - Timer Tags | 0 | 0 | 8 | 1
O2-1325 - cal tags no code - dev - Counter Tags | 0 | 0 | 0 | 0
O2-1326 - cal tags no code - dev - Totalizer Tags Real | 0 | 0 | 0 | 0
O2-1327 - cal tags no code - dev - Totalizer Tags Calc | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-20
O2-756 - OCM Development | 0 | 0 | 32 | 4
O2-701 - Production Release | 7 | 56 | 0 | 0 | 2026-03-10 | 2026-03-13
O2-1448 - Green Enviroment Deployment Preparation | 2 | 16 | 0 | 0 | 2026-03-10 | 2026-03-12
O2-1449 - test production sites before backward compatibility | 2 | 16 | 0 | 0 | 2026-03-12 | 2026-03-16
O2-1450 - making sites backward compatible | 2 | 16 | 0 | 0 | 2026-03-16 | 2026-03-17
O2-1451 - deployment on blue | 2 | 16 | 0 | 0 | 2026-03-11 | 2026-03-13
O2-703 - User Manual | 4 | 32 | 0 | 0 | 2025-12-22 | 2025-12-25
O2-794 - Counter Tag Reset | 10 | 80 | 80 | 10 | 2026-01-15 | 2026-01-26
O2-813 - OCM Development FrontEnd | 0 | 0 | 80 | 10
O2-713 - IT Table to OT Tag Conversion - Phase 1 | 67 | 536 | 272 | 34
O2-719 - Development | 30 | 240 | 80 | 10 | 2025-12-15 | 2026-01-09
O2-780 - UI/UX Design and Implementation | 0 | 0 | 16 | 2
O2-781 - Unit Testing (Frontend and Backend) | 0 | 0 | 0 | 0
O2-782 - Frontend Development | 0 | 0 | 0 | 0
O2-783 - End-to-End Application Testing | 0 | 0 | 0 | 0
O2-784 - Backend/API Development | 0 | 0 | 16 | 2
O2-907 - Research and Poc | 0 | 0 | 16 | 2
O2-720 - SQA | 25 | 200 | 0 | 0 | 2026-01-12 | 2026-01-16
O2-721 - User Manual | 5 | 40 | 0 | 0 | 2026-01-12 | 2026-01-16
O2-722 - Production Release | 7 | 56 | 0 | 0 | 2026-01-19 | 2026-01-19
O2-785 - Research/URS | 0 | 0 | 56 | 7
O2-714 - BPM Editable & Reusability Enhancement | 62 | 496 | 890 | 111.25 | 2025-12-01 | 2025-12-19
O2-715 - Development | 20 | 160 | 146.5 | 18.31 | 2025-12-01 | 2025-12-22
O2-758 - UI Development | 0 | 0 | 31 | 3.88
O2-759 - Frontend End Development | 0 | 0 | 38 | 4.75
O2-760 - Backend Development | 0 | 0 | 49.5 | 6.19
O2-761 - End-to-end application testing | 0 | 0 | 28 | 3.5
O2-716 - SQA | 16 | 128 | 24 | 3 | 2025-12-22 | 2026-01-01
O2-779 - Bug Fixing, Improvements and Tasks | 0 | 0 | 24 | 3
O2-717 - Production Release | 2 | 16 | 136.5 | 17.06 | 2026-01-02 | 2026-01-02
O2-836 - Testing by Kamran | 3 | 24 | 27 | 3.38 | 2026-01-02 | 2026-01-06
O2-837 - Testing by Namra | 1 | 8 | 8 | 1 | 2026-01-02 | 2026-01-02
O2-838 - Testing by Waqar | 2 | 16 | 16 | 2 | 2026-01-02 | 2026-01-05
O2-839 - Testing by Zeeshan | 3 | 24 | 24 | 3 | 2026-01-02 | 2026-01-06
O2-841 - Export To Excel is Fail to download the data | 0 | 0 | 12 | 1.5
O2-842 - Spaces in string conditional cal tag are removing itself after configuring respective tag. | 0 | 0 | 8 | 1
O2-843 - Unit is again displaying mandatory while creating calculated tag where as it is fixed on staging. | 0 | 0 | 0 | 0
O2-844 - Spaces are not accepted in String type Timer tag condition | 0 | 0 | 0 | 0
O2-845 - DOWNLOAD csv function is not working incase of "Reusable function" used in query in batch | 0 | 0 | 0 | 0
O2-846 - No data is getting exported to sql Schedule for IT Data | 0 | 0 | 0 | 0
O2-847 - Production Green Deployment | 0 | 0 | 8 | 1
O2-849 - Anomaly Results are not getting displayed | 0 | 0 | 1.5 | 0.19
O2-851 - Pipelines are getting created and data is also available but no tables are getting created in SQL DB and its showing error for Stats Alarms and Hours Data | 0 | 0 | 0 | 0
O2-852 - Production Blue Deployment | 0 | 0 | 8 | 1
O2-718 - User Manual | 4 | 32 | 16 | 2 | 2025-12-22 | 2026-01-01
O2-896 - OC-Sanity Green env 1/16/26 | 0 | 0 | 40 | 5
O2-897 - Testing By Kamran | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
O2-898 - Testing By Namra | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
O2-899 - Testing By M.Abbas | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
O2-900 - Testing By Zeeshan | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
O2-901 - Testing By Waqar | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
O2-902 - Correlation Matrix is getting vanished right after clicking on "Apply" button. | 0 | 0 | 0 | 0
O2-904 - Forgot Password Email Not Received | 0 | 0 | 0 | 0
O2-906 - Emails Not Received for User Activation, OTP, and Forgot Password | 0 | 0 | 0 | 0
O2-919 - OC-Sanity Blue env 1/19/26 | 0 | 0 | 74 | 9.25
O2-920 - Testing By Kamran | 1 | 8 | 17 | 2.12 | 2026-01-19 | 2026-01-19
O2-921 - Testing By M.Abbas | 1 | 8 | 16 | 2 | 2026-01-19 | 2026-01-19
O2-922 - Testing By Waqar | 2 | 16 | 16 | 2 | 2026-01-19 | 2026-01-20
O2-923 - Testing By Zeeshan | 1 | 8 | 16 | 2 | 2026-01-19 | 2026-01-19
O2-924 - Testing By Namra | 1 | 8 | 0 | 0 | 2026-01-19 | 2026-01-19
O2-940 - Anomaly Results are not getting displayed, Kindly Look into it. | 0 | 0 | 0 | 0
O2-964 - SQL: Displaying Invalid Error for Hours , Not on Staging, Only On Production | 0 | 0 | 1 | 0.12
O2-793 - Real-time Tag Streaming | 190.69 | 1525.5 | 1964 | 245.5 | 2025-12-23 | 2026-02-06
O2-788 - Research/URS | 16 | 128 | 96 | 12 | 2026-01-01 | 2026-01-16
O2-1314 - real streaming - urs - streaming RnD feasibility on ADX cluster | 2 | 16 | 16 | 2 | 2026-01-06 | 2026-01-07
O2-1315 - real streaming - urs - RnD of Function Apps working on streaming | 3 | 24 | 24 | 3 | 2026-01-01 | 2026-01-05
O2-1316 - real streaming - urs - Rnd of Azure Eventhubs related to streaming | 2 | 16 | 16 | 2 | 2026-01-08 | 2026-01-09
O2-1317 - real streaming - urs - Communication between Azure Eventhub - Functions Apps- ADX database | 3 | 24 | 24 | 3 | 2026-01-12 | 2026-01-14
O2-1334 - real streaming - urs - multiInstance scaling in function apps | 2 | 16 | 16 | 2 | 2026-01-15 | 2026-01-16
O2-789 - Development | 20 | 160 | 274.5 | 34.31 | 2026-01-16 | 2026-02-11
O2-1328 - real streaming - dev - function app just code testing with reals | 3 | 24 | 22.5 | 2.81 | 2026-02-04 | 2026-02-06
O2-1329 - real streaming - dev - function app python code optimization of data outgoing | 2 | 16 | 16 | 2 | 2026-02-09 | 2026-02-10
O2-1330 - real streaming - dev - function app just polars implementaion in real tags | 3 | 24 | 22.5 | 2.81 | 2026-02-11 | 2026-02-13
O2-1331 - real streaming - dev - function app OPC,IOT,MQTT device compatibility of real | 0 | 0 | 83.5 | 10.44
O2-1332 - real streaming - dev - function app handling datatypes of real tags | 0 | 0 | 58.5 | 7.31
O2-1333 - real streaming - dev - real tag implementation automation | 0 | 0 | 0 | 0 | 2026-02-02 | 2026-03-11
O2-1608 - real-streaming-dev-UnitTesting | 5 | 40 | 71.5 | 8.94 | 2026-02-25 | 2026-02-28
O2-790 - SQA | 6 | 48 | 253 | 31.62 | 2026-01-05 | 2026-01-09
O2-1004 - Latest Values Not Populating for Calculated Tag (Boolean Type) | 1 | 8 | 0 | 0
O2-1062 - Unable to view associated assets against single area after coming back from folder view in asset hierarchy. | 0.12 | 1 | 1 | 0.12 | 2026-02-04 | 2026-02-04
O2-1163 - Testing By Kamran | 3 | 24 | 34 | 4.25 | 2026-02-27 | 2026-03-03
O2-1167 - Data Points Not Displayed on Sites Screen While Creating a New Site Until Page Refresh | 0.12 | 1 | 0.5 | 0.06 | 2026-02-03 | 2026-02-03
O2-1178 - GPS Tag Live Values Are Not Populating | 0 | 0 | 0 | 0
O2-1190 - Live Values Not Populating for Real-Time Tags Created via Import Site Layout | 0 | 0 | 0 | 0
O2-1202 - Totalizer Tag Values Not Updating While Calculated Tag Values Are Updating | 0 | 0 | 0 | 0
O2-1284 - Testing By M.Abbas | 4 | 32 | 32 | 4 | 2026-02-11 | 2026-02-17
O2-1313 - Model is not getting created for anomaly "User train" group, its showing error. | 0 | 0 | 0 | 0
O2-1406 - Live Values Not Populating on Streaming for IoT and MQTT InHand Devices | 0 | 0 | 0 | 0
O2-1411 - Get latest values for both IOT and MQTT devices in write back module is not working | 0 | 0 | 0 | 0
O2-1689 - Testing By M.Abbas Rework | 3 | 24 | 30 | 3.75 | 2026-03-03 | 2026-03-05
O2-1758 - Testing By Zeeshan Rework | 3 | 24 | 13 | 1.62 | 2026-03-05 | 2026-03-09
O2-1800 - Output Cal tag latest values for APX performance asset are not displaying. | 0 | 0 | 0 | 0
O2-1807 - Alarms are not triggering after the recent release of Real-Time Tag Streaming | 0 | 0 | 0 | 0
O2-1809 - Batch jobs are failing on the staging environment and failure logs are not generated | 0 | 0 | 0 | 0
O2-1810 - BPM jobs are not executing | 0 | 0 | 0 | 0
O2-967 - Testing By Zeeshan | 1 | 8 | 8 | 1 | 2026-01-21 | 2026-01-21
O2-968 - Testing By Waqar | 5 | 40 | 38.5 | 4.81 | 2026-01-21 | 2026-01-26
O2-972 - Real-Time Tag Latest Values Are Not Displayed | 1 | 8 | 0 | 0
O2-973 - Docker containers are not loading. | 10 | 80 | 96 | 12
O2-791 - User manual | 0.5 | 4 | 1 | 0.12 | 2026-01-05 | 2026-01-09
O2-792 - Production Release | 10 | 80 | 257.5 | 32.19 | 2026-01-12 | 2026-01-15
O2-1407 - Testing By M.Abbas | 2 | 16 | 24 | 3 | 2026-02-18 | 2026-02-19
O2-1408 - Testing By Zeeshan | 2 | 16 | 14.5 | 1.81 | 2026-02-18 | 2026-02-19
O2-1409 - Testing By Waqar | 2 | 16 | 27.5 | 3.44 | 2026-02-18 | 2026-02-19
O2-1410 - Testing By Namra | 2 | 16 | 24 | 3 | 2026-02-18 | 2026-02-19
O2-1429 - Data Lake and Enterprise Connector in site status is not getting ready. | 0 | 0 | 0 | 0
O2-1434 - Green Environment resource creation | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
O2-1442 - SMS Opt-in: Number registration fails with a 403 Forbidden error. | 2 | 16 | 16 | 2 | 2026-02-18 | 2026-02-19
O2-1443 - Real-Time Tag Latest Values Not Showing | 1 | 8 | 0 | 0
O2-1445 - real tag streaming - production release - backward compatible (connecting IOThubs with evenhub and function app) so that original flow is not altered and monitor function apps | 2 | 16 | 43.5 | 5.44 | 2026-01-12 | 2026-01-15
O2-1452 - Write Back Is FAIL, Values are not getting updated | 1 | 8 | 6.5 | 0.81 | 2026-02-19 | 2026-02-19
O2-1457 - Calculated Tag Latest Values Not Populating | 0 | 0 | 0 | 0
O2-1471 - OPC Device Real-Time Tag Latest Values Not Updated but Diagnostics Alarms Auto-Resolved | 0 | 0 | 0 | 0
O2-1477 - GPS Tag Latest Values Not Populating | 0 | 0 | 0 | 0
O2-1483 - Loader Keeps Running After Clicking “Execute All and Save Output” and User Cannot Proceed | 0 | 0 | 0 | 0
O2-1484 - MQTT values are not getting Updated | 1 | 8 | 0 | 0 | 2026-02-19 | 2026-02-19
O2-1502 - Longitude's value is missing whish is mandatory and being used in GPS, Kindly fix completely | 0.12 | 1 | 0 | 0 | 2026-02-20 | 2026-02-20
O2-1515 - Unable to create ODBC pipeline system showing error "database not found" | 0 | 0 | 0 | 0
O2-1516 - Testing By Kamran | 1 | 8 | 7 | 0.88 | 2026-02-18 | 2026-02-19
O2-1519 - Latest Values not populating for tags created from import site layout | 0 | 0 | 0 | 0
O2-1577 - latest values are not being populated for MQTT (default format) and OPC devices. Real-time and GPS tags on the newly created site | 0 | 0 | 0 | 0
O2-1578 - IOT,MQTT inhand latest values are not populating | 0 | 0 | 0 | 0
O2-1844 - Testing By Kamran Prod Rework(Green) | 1 | 8 | 6.5 | 0.81 | 2026-03-11 | 2026-03-12
O2-1846 - Testing By Namra Prod Rework(Greeen) | 2 | 16 | 10.5 | 1.31 | 2026-03-11 | 2026-03-12
O2-1847 - Testing By Waqar Prod Rework(Greeen) | 2 | 16 | 9 | 1.12 | 2026-03-11 | 2026-03-12
O2-1848 - Testing By Zeeshan Prod Rework(Greeen) | 2 | 16 | 9 | 1.12 | 2026-03-11 | 2026-03-12
O2-1849 - Testing By M.Abbas Prod Rework(Greeen) | 2 | 16 | 16 | 2 | 2026-03-11 | 2026-03-12
O2-1857 - Monitoring Page Shows Error Even Though Table Schema and Query Schema Match | 0.81 | 6.5 | 0 | 0
O2-1867 - SAP HANA Connector – Tables Not Auto-Fetched During Pipeline Creation | 0 | 0 | 0 | 0
O2-1868 - Unable to Create ODBC connector | 0 | 0 | 0 | 0
O2-1891 - Testing By M.Abbas Prod Rework(Blue) | 2 | 16 | 16 | 2 | 2026-03-13 | 2026-03-16
O2-1892 - Testing By Zeeshan Prod Rework(Blue) | 1 | 8 | 6.5 | 0.81 | 2026-03-16 | 2026-03-16
O2-1979 - Backword Compatability | 0 | 0 | 13 | 1.62 | 2026-01-12 | 2026-01-15
O2-798 - Project Management | 111.23 | 889.84 | 703.34 | 87.92 | 2025-12-01 | 2026-02-27
O2-1181 - RMIs Project Management | 0 | 0 | 3 | 0.38
O2-1182 - Added details for IP Meeting , Coordination with Hassan Malik | 0.38 | 3 | 3 | 0.38 | 2026-01-28 | 2026-01-28
O2-1285 - Add and implement RMI Planned Field | 0 | 0 | 0 | 0
O2-1293 - Jira Logging and Setup | 4 | 32 | 43 | 5.38 | 2026-02-10 | 2026-03-13
O2-1393 - February 16, 2026 | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
O2-1446 - February 11, 2026 | 1 | 8 | 8 | 1 | 2026-02-11 | 2026-02-11
O2-1535 - February 19, 2026 | 1 | 8 | 6.5 | 0.81 | 2026-02-19 | 2026-02-19
O2-1537 - February 20, 2026 | 1 | 8 | 6.5 | 0.81 | 2026-02-20 | 2026-02-20
O2-1538 - February 23, 2026 | 1 | 8 | 6.5 | 0.81 | 2026-02-23 | 2026-02-23
O2-1607 - February 25,2026 | 0.12 | 1 | 1 | 0.12 | 2026-02-25 | 2026-02-25
O2-1934 - March 17, 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-17 | 2026-03-17
O2-1573 - JIRA Logging Issues Discussion | 0.21 | 1.67 | 1.67 | 0.21 | 2026-02-20 | 2026-02-20
O2-1893 - JIRA Logging Discussion | 0.21 | 1.67 | 1.67 | 0.21 | 2026-02-20 | 2026-02-20
O2-799 - EPR: Employee Productivity Report | 15 | 120 | 304 | 38 | 2025-12-01 | 2026-01-16
O2-1281 - February Productivity Report - Planning and Feedback | 0.5 | 4 | 4 | 0.5 | 2026-02-10 | 2026-02-10
O2-1394 - December EPR | 20 | 160 | 160 | 20 | 2025-12-01 | 2025-12-31
O2-925 - EPR - January 19, 2026 | 1 | 8 | 4 | 0.5 | 2026-01-19 | 2026-01-19
O2-926 - EPR - January 20, 2026 | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
O2-927 - EPR - January 21, 2026 | 1 | 8 | 4 | 0.5 | 2026-01-21 | 2026-01-21
O2-928 - EPR - January 1, 2026 | 1 | 8 | 8 | 1 | 2026-01-01 | 2026-01-01
O2-929 - EPR - January 2, 2026 | 1 | 8 | 8 | 1 | 2026-01-02 | 2026-01-02
O2-930 - EPR - January 5, 2026 | 1 | 8 | 8 | 1 | 2026-01-05 | 2026-01-05
O2-931 - EPR - January 6, 2026 | 1 | 8 | 8 | 1 | 2026-01-06 | 2026-01-06
O2-932 - EPR - January 7, 2026 | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
O2-933 - EPR - January 8, 2026 | 1 | 8 | 8 | 1 | 2026-01-08 | 2026-01-08
O2-934 - EPR - January 9, 2026 | 1 | 8 | 8 | 1 | 2026-01-09 | 2026-01-09
O2-935 - EPR - January 12, 2026 | 1 | 8 | 8 | 1 | 2026-01-12 | 2026-01-12
O2-936 - EPR - January 13, 2026 | 1 | 8 | 8 | 1 | 2026-01-13 | 2026-01-13
O2-937 - EPR - January 14, 2026 | 1 | 8 | 8 | 1 | 2026-01-14 | 2026-01-14
O2-938 - EPR - January 15, 2026 | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
O2-939 - EPR - January 16, 2026 | 1 | 8 | 8 | 1 | 2026-01-16 | 2026-01-16
O2-809 - Support for Job Priority in batch/bpm (high/Meduim/low) | 0 | 0 | 0 | 0
O2-810 - Batch/Bpm modify Existing ADX IT Table | 217.88 | 1743 | 1513 | 189.12 | 2025-12-30 | 2026-02-06
O2-1041 - Development | 24 | 192 | 256 | 32 | 2026-01-07 | 2026-01-19
O2-1053 - UI Development | 3 | 24 | 24 | 3 | 2026-01-07 | 2026-01-09
O2-1054 - Frontend Development | 0 | 0 | 24 | 3 | 2026-01-12 | 2026-01-14
O2-1055 - Backend Development | 17 | 136 | 64 | 8 | 2026-01-07 | 2026-01-19
O2-1056 - End to end Testing | 2 | 16 | 16 | 2 | 2026-02-09 | 2026-02-10
O2-1169 - Scripting and Planning for Backward Compatibility | 3 | 24 | 24 | 3
O2-1170 - Testing/ Bug Resolving | 2 | 16 | 16 | 2
O2-1747 - Add New Column BPM API Changes | 4 | 32 | 32 | 4 | 2026-01-07 | 2026-01-13
O2-1748 - Add New Column Batch API Changes | 4 | 32 | 32 | 4 | 2026-01-14 | 2026-01-19
O2-1749 - Add New Column in Custom Functions | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
O2-1750 - Frontend End to End Testing | 2 | 16 | 16 | 2 | 2026-01-16 | 2026-01-19
O2-1042 - User Manual | 6 | 48 | 16 | 2
O2-1043 - Production Release | 0 | 0 | 0 | 0
O2-1113 - Research/URS | 10 | 80 | 72 | 9 | 2025-12-31 | 2026-01-06
O2-1744 - Impact Analysis | 4 | 32 | 24 | 3 | 2025-12-31 | 2026-01-06
O2-1745 - Impact Analysis | 5 | 40 | 32 | 4 | 2025-12-31 | 2026-01-06
O2-1125 - OC-Regression 02/02/2026 | 4 | 32 | 133.5 | 16.69 | 2026-02-02 | 2026-02-05
O2-1127 - Testing By Kamran | 4 | 32 | 27 | 3.38 | 2026-02-02 | 2026-02-05
O2-1128 - Testing By M.Abbas | 4 | 32 | 32 | 4 | 2026-02-02 | 2026-02-06
O2-1129 - Testing By Waqar | 3 | 24 | 24 | 3 | 2026-02-02 | 2026-02-04
O2-1130 - Testing By Zeeshan | 4 | 32 | 32 | 4 | 2026-02-02 | 2026-02-06
O2-1222 - Tag Values Not Updating for MQTT Devices and Not Populating for IoT Devices | 0 | 0 | 0 | 0
O2-1223 - Unknown error is occurring multiple times please look into this | 0.25 | 2 | 2 | 0.25 | 2026-02-03 | 2026-02-03
O2-1224 - New Password Field Validation Message Mismatch on Reset Password Screen | 0.12 | 1 | 0.5 | 0.06 | 2026-02-03 | 2026-02-03
O2-1225 - GPS Tag Latest Values Not Populating for Any Device on Staging Sub-Site | 0 | 0 | 0 | 0
O2-1228 - Publish Changes Functionality Is Not Working | 0 | 0 | 0 | 0
O2-1229 - Spaces Removed Automatically When Pasting Text into Calculated Tag Condition | 0.25 | 2 | 2 | 0.25 | 2026-02-04 | 2026-02-04
O2-1230 - Make Unit Field Optional for Calculated Tags Across the Application | 0.25 | 2 | 2 | 0.25 | 2026-02-03 | 2026-02-03
O2-1231 - Timer Tag Alarms has not been triggered as values was populated | 0 | 0 | 0 | 0
O2-1233 - Unknown API failure occurs when navigating back to Site Listing page from Site home page | 0.25 | 2 | 2 | 0.25 | 2026-02-03 | 2026-02-03
O2-1234 - Latest tag values are populated for newly replicated IoT device created via Bulk Device Replication without getting configured | 0 | 0 | 0 | 0
O2-1235 - Internal Server Error Occurs While Creating a Conditional Calculated Tag | 0 | 0 | 0 | 0
O2-1237 - Write Back MQTT Simulator Is Not Working | 0 | 0 | 0 | 0
O2-1238 - Latest Values Not Updating for Parameters on Write Back and Bulk Write Back Screens | 0 | 0 | 0 | 0
O2-1239 - Complete list of mapped tags is not displaying against APX health asset as well as it is displaying some output cal tags against performance asset. | 0 | 0 | 0 | 0
O2-1240 - Unable to fetch data for a specific time period against health asset. | 0 | 0 | 0 | 0
O2-1241 - Real time tag values for both IOT, MQTT against flatten and inhand are not displaying. | 0 | 0 | 0 | 0
O2-1242 - Device Diagnostics Functionality Is Not Working | 0 | 0 | 0 | 0
O2-1243 - Anomaly results are not completely exported to excel file. | 0.25 | 2 | 2 | 0.25 | 2026-02-04 | 2026-02-04
O2-1244 - Need to display Is Global checkbox while editing a formula only in that SI where respective formula is created | 0 | 0 | 0 | 0
O2-1245 - User created Asset type, Subtype and variable in formula library should be restricted only for specific SI except for global asset type, sub type and variable that are uneditable. | 0 | 0 | 0 | 0
O2-1246 - Conditional Calculated Tag Cannot Be Deleted Due to Incorrect Dependency Validation | 0 | 0 | 0 | 0
O2-1248 - Certificate Expiry Notification Received but Email Not Delivered | 2 | 16 | 8 | 1 | 2026-02-11 | 2026-02-12
O2-1260 - OCM-Sanity-Testing-Green-09/02/2026 | 0 | 0 | 68 | 8.5
O2-1261 - Testing By Kamran | 1 | 8 | 16 | 2 | 2026-02-09 | 2026-02-09
O2-1262 - Testing By M.Abbas | 1 | 8 | 16 | 2 | 2026-02-09 | 2026-02-09
O2-1263 - Testing By Zeeshan | 1 | 8 | 16 | 2 | 2026-02-09 | 2026-02-09
O2-1264 - Testing By Namra | 1 | 8 | 16 | 2 | 2026-02-10 | 2026-02-10
O2-1268 - Failed to Login with microsoft | 0 | 0 | 0 | 0
O2-1270 - MQTT flatten real time tag values are not displaying. | 0 | 0 | 0 | 0
O2-1271 - Models are not creating in user defined anomaly group where as data for specified time duration is displaying. | 0.5 | 4 | 4 | 0.5 | 2026-02-17 | 2026-02-17
O2-1335 - OCM-Sanity-Testing-Blue-02/16/2026 | 4 | 32 | 49 | 6.12 | 2026-02-16 | 2026-02-16
O2-1336 - Testing By Kamran | 1 | 8 | 17 | 2.12 | 2026-02-16 | 2026-02-16
O2-1337 - Testing By Waqar | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
O2-1338 - Testing By Zeeshan | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
O2-1339 - Testing By Namra | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
O2-1383 - Area Count Mismatch for “Subs_Sanity_BL W” Site in OmniAgent Data Analysis | 0 | 0 | 8 | 1
O2-969 - SQA | 18 | 144 | 162 | 20.25 | 2026-01-20 | 2026-01-26
O2-1184 - Cloned batch job does not display the source (parent) job name after editing | 0 | 0 | 2 | 0.25
O2-1185 - CSV download generates an empty file in the Batch Compute module | 0 | 0 | 3 | 0.38
O2-1188 - User-defined function appears in Batch Query window but not on User Defined Function page | 1 | 8 | 8 | 1 | 2026-02-02 | 2026-02-02
O2-1189 - System does not restrict adding new entities to a user-defined table used by an active batch job | 0 | 0 | 11 | 1.38
O2-1192 - In BATCH /BPM Activity output or Batch job result is not showing updated results according to the query after 1 day | 0 | 0 | 8 | 1
O2-1280 - Bug Fixing, Improvements and Tasks | 5 | 40 | 40 | 5 | 2026-01-20 | 2026-01-26
O2-1754 - Bug Fixing, Improvements and Tasks | 0 | 0 | 24 | 3 | 2026-02-09 | 2026-02-11
O2-1763 - Bug Fixing, Improvements and Tasks | 6 | 48 | 8 | 1 | 2026-01-20 | 2026-01-26
O2-970 - Testing By Kamran | 3 | 24 | 26 | 3.25 | 2026-01-21 | 2026-01-23
O2-971 - Testing By M.Abbas | 3 | 24 | 32 | 4
O2-811 - Enterprise Connectors External Api Trigger Support (SAP,Azure Sql, ODBC) | 0 | 0 | 0 | 0
O2-812 - Enterprise connector (MySQL) | 0 | 0 | 0 | 0
O2-814 - Enterprise connector (Oracle) | 0 | 0 | 0 | 0
O2-815 - Enterprise Connector Enhancement (Support for upsert/injestion pointer) | 0 | 0 | 0 | 0
O2-816 - Enterprise connectors Enhancement (use existing IT Table) | 0 | 0 | 0 | 0
O2-817 - IT/OT Conversion for Enterprise Connectors | 0 | 0 | 0 | 0
O2-818 - Recompute for existing Batch/Bpm Jobs | 164.75 | 1318 | 810.6 | 101.33 | 2026-02-11 | 2026-03-13
O2-1381 - Research | 7 | 56 | 72 | 9 | 2026-02-11 | 2026-02-13
O2-1454 - Impact Analysis | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
O2-1455 - POC Template Variables | 2 | 16 | 16 | 2 | 2026-02-11 | 2026-02-12
O2-1456 - POC Template Variable Mapping | 1 | 8 | 8 | 1 | 2026-02-12 | 2026-02-12
O2-1458 - Impact Analysis | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
O2-1517 - Schema Changes | 2 | 16 | 16 | 2 | 2026-02-11 | 2026-02-12
O2-1518 - Bpm Batch Engine Impact | 2 | 16 | 16 | 2 | 2026-02-13 | 2026-02-16
O2-1437 - Development | 34 | 272 | 210 | 26.25 | 2026-02-16 | 2026-03-04
O2-1699 - UI Changes Batch RunOnDemand | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
O2-1700 - New UI BPM RunOnDemand | 1 | 8 | 8 | 1 | 2026-02-17 | 2026-02-17
O2-1701 - UI Changes Templates Variables Batch | 1 | 8 | 4 | 0.5 | 2026-02-25 | 2026-02-25
O2-1702 - UI Changes Template Variable BPM | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
O2-1703 - Database Tables and Changes for Batch | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
O2-1704 - Database Tables and ¦Changes BPM | 1 | 8 | 8 | 1 | 2026-02-17 | 2026-02-17
O2-1705 - Backend API Changes Batch Template | 2 | 16 | 16 | 2 | 2026-02-18 | 2026-02-19
O2-1706 - Backend API Changes BPM Template | 3 | 24 | 24 | 3 | 2026-02-19 | 2026-02-25
O2-1707 - Unit Testing frontend | 1 | 8 | 4 | 0.5 | 2026-02-25 | 2026-02-25
O2-1709 - UI Changes Integration with API | 2 | 16 | 16 | 2 | 2026-02-23 | 2026-02-24
O2-1711 - Backend Api Run on Demand in BPM | 1 | 8 | 8 | 1 | 2026-02-19 | 2026-02-19
O2-1714 - Backend Api Run on Demand in Batch | 1 | 8 | 8 | 1 | 2026-02-20 | 2026-02-20
O2-1715 - Unit Testing Backend | 1 | 8 | 8 | 1 | 2026-03-04 | 2026-03-04
O2-1716 - Backend Improvements and Bug fixing | 1 | 8 | 8 | 1 | 2026-02-26 | 2026-02-26
O2-1765 - Schema Changes | 2 | 16 | 16 | 2 | 2026-02-23 | 2026-02-25
O2-1766 - BPM Backend Development | 3 | 24 | 24 | 3 | 2026-02-25 | 2026-02-27
O2-2463 - Batch Backend Development | 4 | 32 | 26 | 3.25 | 2026-03-17 | 2026-03-25
O2-2464 - Unit Testing | 1 | 8 | 8 | 1 | 2026-03-26 | 2026-03-27
O2-1438 - SQA | 10 | 80 | 83 | 10.38 | 2026-03-17 | 2026-04-02
O2-1924 - Batch Run on demand | 4 | 32 | 32 | 4 | 2026-03-17 | 2026-03-25
O2-1946 - BPM Run on demand | 1 | 8 | 5.5 | 0.69 | 2026-03-18 | 2026-03-18
O2-2000 - Batch/BPM Trigger | 4 | 32 | 29.5 | 3.69 | 2026-03-26 | 2026-03-31
O2-2690 - Batch/BPM Apirl Testing | 2 | 16 | 16 | 2 | 2026-04-01 | 2026-04-02
O2-1439 - User Manual | 0 | 0 | 0 | 0
O2-1440 - Production Release | 0 | 0 | 22.17 | 2.77
O2-2142 - Batch/BPM Testing | 0.25 | 2 | 2 | 0.25 | 2026-04-07 | 2026-04-07
O2-2171 - Green production release | 1 | 8 | 8 | 1 | 2026-04-07 | 2026-04-07
O2-2172 - Production Green Release / Release Management | 1 | 8 | 8 | 1 | 2026-04-07 | 2026-04-07
O2-2222 - Bug Fixing | 0.38 | 3 | 2.17 | 0.27 | 2026-04-08 | 2026-04-08
O2-2223 - Production Blue Deployment / Release Management | 0.25 | 2 | 2 | 0.25 | 2026-04-09 | 2026-04-09
O2-1918 - Handover | 0.62 | 5 | 1.63 | 0.2 | 2026-03-17 | 2026-03-18
O2-1919 - Handover - Hassan Malik | 0.12 | 1 | 0.63 | 0.08 | 2026-03-17 | 2026-03-17
O2-1922 - Handover | 0 | 0 | 1 | 0.12 | 2026-03-17 | 2026-03-17
O2-1920 - Bug Fixing | 0 | 0 | 16 | 2
O2-1987 - Enhance Monitoring Logs for Batch/BPM Module to Include Variable Values | 0 | 0 | 0 | 0
O2-2031 - Cloned BPM Jobs Showing “Pending” Status on Monitoring Page | 1 | 8 | 8 | 1 | 2026-03-27 | 2026-03-27
O2-2415 - BPM RunOnDemand Bug Fix | 1 | 8 | 8 | 1 | 2026-03-30 | 2026-03-30
O2-1921 - QA Handover | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-17 | 2026-03-17
O2-1923 - Handover By Abbas | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-17 | 2026-03-17
O2-819 - Support for SQL Monaco IDE | 0 | 0 | 0 | 0
O2-820 - Support for SQL in Batch/Bpm | 0 | 0 | 0 | 0
O2-821 - Direct Value Comparison | 0 | 0 | 0 | 0
O2-822 - User Activity Logs + Dashboards | 0 | 0 | 0 | 0
O2-825 - CSV Bulk Import V2 | 0 | 0 | 0 | 0
O2-826 - Data Anomaly V2 | 0 | 0 | 0 | 0
O2-827 - Data Anomaly V3 | 0 | 0 | 0 | 0
O2-861 - Trending in OmniAgent | 4 | 32 | 32 | 4
O2-862 - Development | 2 | 16 | 16 | 2 | 2026-01-07 | 2026-01-08
O2-866 - Research work on visualization | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
O2-884 - Research on Code Integration of Backend and FrontEnd | 1 | 8 | 8 | 1 | 2026-01-08 | 2026-01-08
O2-863 - SQA | 0 | 0 | 0 | 0
O2-864 - User Manual | 0 | 0 | 0 | 0
O2-865 - Production Release | 0 | 0 | 0 | 0
O2-887 - APX Pump – Variable Speed Dashboard | 85.5 | 684 | 322 | 40.25 | 2025-12-23 | 2026-02-06
O2-1090 - Production Release Green | 6 | 48 | 12 | 1.5 | 2026-01-23 | 2026-01-26
O2-1091 - Production data mapping and bug fixing | 0 | 0 | 5 | 0.62
O2-1094 - OC Process Testing (staging & Production) | 0.5 | 4 | 4 | 0.5 | 2026-01-22 | 2026-01-26
O2-1107 - Support - Process team | 0 | 0 | 3 | 0.38
O2-1092 - User Manual/Guide | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
O2-1693 - Documentation | 1 | 8 | 8 | 1 | 2026-01-26 | 2026-01-26
O2-1093 - Production Deployment | 2 | 16 | 13 | 1.62 | 2026-01-23 | 2026-01-26
O2-1527 - Database Migration and Dashboard Mapping | 2 | 16 | 13 | 1.62 | 2026-01-23 | 2026-01-26
O2-1095 - Development of VFD Dashboard | 25 | 200 | 116 | 14.5 | 2026-01-09 | 2026-01-23
O2-1096 - KT of VFD Dashboard | 1 | 8 | 8 | 1 | 2026-01-09 | 2026-01-09
O2-1097 - Code Understanding(Research) | 1 | 8 | 8 | 1 | 2026-01-12 | 2026-01-12
O2-1098 - Code Understanding+ Created New Component | 1 | 8 | 8 | 1 | 2026-01-13 | 2026-01-13
O2-1099 - Code Understanding+ Started Integrated Dashboard | 1 | 8 | 8 | 1 | 2026-01-14 | 2026-01-14
O2-1100 - Integrated VFD Performance Dashboard | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
O2-1102 - Tested Complete VFD Dashboard + Fix Issues | 1 | 8 | 8 | 1 | 2026-01-21 | 2026-01-21
O2-1103 - Testing + QA Handover + Fix Issues | 1 | 8 | 8 | 1 | 2026-01-22 | 2026-01-22
O2-1186 - QA + Fix Issues | 1 | 8 | 8 | 1 | 2026-01-23 | 2026-01-23
O2-787 - Performance Dashboard for VFD Development | 7 | 56 | 24 | 3 | 2025-12-23 | 2026-01-21
O2-1110 - Ashghal Release Management / Deployment | 2 | 16 | 8 | 1 | 2026-01-27 | 2026-01-28
O2-1195 - OC Process Testing | 0.25 | 2 | 2 | 0.25 | 2026-01-26 | 2026-01-27
O2-1530 - Asghal Deployment /Release Management | 0.75 | 6 | 6 | 0.75 | 2026-01-27 | 2026-01-27
O2-1179 - SQA | 0 | 0 | 4 | 0.5
O2-1180 - APX Health Operating System not displaying appropriate values | 0 | 0 | 4 | 0.5
O2-892 - OC Intuitive UI/UX | 144.06 | 1152.5 | 1127 | 140.88 | 2026-01-15 | 2026-03-31
O2-893 - Information Architecure | 0 | 0 | 0 | 0
O2-894 - Revamping UI/UX | 42 | 336 | 563.5 | 70.44
O2-1585 - OmniConnect_Revamp_(UI/UX)_ Variation_01 | 7 | 56 | 56 | 7 | 2026-01-15 | 2026-01-24
O2-1586 - OmniConnect_ Revamp_(UI/UX)_ Variation_ 02_ Part A | 5 | 40 | 40 | 5 | 2026-01-26 | 2026-01-30
O2-1587 - OmniConnect_Revamp_(UI/UX)_ Changes | 5 | 40 | 40 | 5 | 2026-02-09 | 2026-02-16
O2-1589 - OmniConnect- Dashboard Design + 4 layers Design (UX/UI) | 4.06 | 32.5 | 32.5 | 4.06 | 2026-02-19 | 2026-02-25
O2-1757 - OmniConnect_Revamp_(UI/UX)_Main Dashboard (P) | 0 | 0 | 83 | 10.38
O2-1842 - OmniConnect_ Revamp_(UI/UX)_ Variation_ 02_ Part B | 5 | 40 | 40 | 5 | 2026-02-02 | 2026-02-06
O2-1858 - OmniConnect- Revamp- Site Dashboard and OmniAgent- UX/UI | 4.06 | 32.5 | 32.5 | 4.06 | 2026-02-26 | 2026-03-04
O2-1860 - OmniConnect-Revamp- (UI/UX) | 2.81 | 22.5 | 22.5 | 2.81
O2-2143 - OmniConnect_Revamp_(UI/UX)_URS (P) | 0 | 0 | 32 | 4
O2-2240 - OmniConnect- Site Dashboard UI + Plus Navigation | 4.06 | 32.5 | 32.5 | 4.06 | 2026-03-05 | 2026-03-11
O2-2241 - OmniConnect_ Feedback Incorporation | 4.06 | 32.5 | 32.5 | 4.06 | 2026-03-12 | 2026-03-18
O2-2242 - OmniConnect_ Organization Dashboard + Navigation changes | 5 | 40 | 40 | 5 | 2026-03-24 | 2026-03-30
O2-2243 - OmniConnect_ OmniAgent Revamp + Site Connectivity | 5 | 40 | 40 | 5 | 2026-03-31 | 2026-04-06
O2-2244 - OmniConnect_ Revamp Overall Feedback Incorportion | 5 | 40 | 40 | 5 | 2026-04-07 | 2026-04-13
O2-9 - Batch/BPM V3 (Box re-usable, Mix and Match) | 22 | 176 | 666 | 83.25
O2-15 - Development | 4 | 32 | 136 | 17 | 2025-10-06 | 2025-10-17
O2-180 - UI/UX | 0 | 0 | 24 | 3
O2-181 - Frontend | 0 | 0 | 32 | 4
O2-182 - API Development | 0 | 0 | 64 | 8
O2-183 - Unit Testing Backend | 0 | 0 | 8 | 1
O2-184 - Unit Testing frontend | 0 | 0 | 8 | 1
O2-16 - SQA | 0 | 0 | 149 | 18.62 | 2025-10-20 | 2025-10-23
O2-306 - Temp table is showing in Activity Query modal and when user select any temp table then it is showing error | 0 | 0 | 0 | 0
O2-363 - Bug Fixing, Improvements and Tasks | 0 | 0 | 32 | 4
O2-364 - Bug Fixing, Improvements and Tasks | 0 | 0 | 31.5 | 3.94
O2-392 - Once a user validates an activity with error, the system incorrectly sets the validation status to true and displays the “Save Output” button and upon clicking on “Save Output,” the system throws error “Failed to publish activity | 0 | 0 | 0 | 0
O2-394 - when user uses a temp table of another BPM Workflow activity it shows error | 0 | 0 | 0 | 0
O2-396 - when user using existing functionality uses a batch job with OT function and while validating its not showing the "Status Code" and "ID" column empty | 0 | 0 | 0 | 0
O2-434 - Smoke-Production | 10 | 80 | 58 | 7.25 | 2025-10-27 | 2025-10-28
O2-436 - Internal Server error is showing while creating conditional cal tag | 0 | 0 | 1 | 0.12
O2-437 - Internal Server error is showing while creating Timer Tag | 0 | 0 | 1 | 0.12
O2-438 - Totalizer Calculated tag live values are not showing | 0 | 0 | 0 | 0
O2-439 - Drop down options are not displaying in model relaxation factor of anomaly creation | 0 | 0 | 0 | 0
O2-451 - Import site layout failed. | 0 | 0 | 0 | 0
O2-537 - APX output calculated tags are not displaying on latest values screen even after hitting publish changes multiple times. | 0 | 0 | 0 | 0
O2-17 - Production Release | 2 | 16 | 8 | 1 | 2025-10-24 | 2025-10-24
O2-435 - Production Green Deployment | 0 | 0 | 8 | 1
O2-47 - User Manual | 6 | 48 | 40 | 5 | 2025-10-20 | 2025-10-23
O2-359 - How To - Batch | 0 | 0 | 16 | 2
O2-360 - How to - BPM | 0 | 0 | 16 | 2
O2-362 - Fields - BPM | 0 | 0 | 8 | 1
O2-94 - Scheduled Pulls from Data Source (REST API) | 260.5 | 2084 | 1596.76 | 199.59
O2-100 - User Manual | 18 | 144 | 44 | 5.5 | 2025-10-06 | 2025-10-14
O2-243 - Restructure Enterprise Connectors to reflect latest updates + AI Friendly | 0 | 0 | 20 | 2.5
O2-244 - REST API Fields and How Tos | 0 | 0 | 16 | 2
O2-101 - Production Release | 2 | 16 | 24 | 3 | 2025-10-15 | 2025-10-15
O2-355 - Productin Release Blue Env | 0 | 0 | 8 | 1
O2-98 - Development | 120 | 960 | 307 | 38.38 | 2025-09-22 | 2025-10-03
O2-187 - REST API Dev OC Frontend | 0 | 0 | 88 | 11
O2-192 - Modify Existing API For Connectors CRUD | 0 | 0 | 16 | 2
O2-193 - New Table and Database changes for Rest API | 0 | 0 | 8 | 1
O2-194 - Modify Existing API For Triggers CRUD | 0 | 0 | 16 | 2
O2-195 - Modify Existing API For Pipelines CRUD | 0 | 0 | 32 | 4
O2-320 - Creating Scanner For RestAPI Pulls | 0 | 0 | 24 | 3
O2-321 - Creating Generic API Caller | 0 | 0 | 80 | 10
O2-322 - OT Data Formatting and Ingestion to ADX | 0 | 0 | 40 | 5
O2-397 - Bug Fixing / Deployments | 0 | 0 | 3 | 0.38
O2-99 - SQA | 80 | 640 | 423.38 | 52.92 | 2025-10-06 | 2025-10-14
O2-137 - Regression testing | 25 | 200 | 190 | 23.75 | 2025-10-07 | 2025-10-14
O2-138 - Sanity testing | 10 | 80 | 79 | 9.88 | 2025-10-17 | 2025-10-20
O2-142 - Schedule Pull from Rest API | 5 | 40 | 52.55 | 6.57 | 2025-10-08 | 2025-10-15
O2-201 - Blocker: IOT HUB status is still in Progress. | 0 | 0 | 0 | 0
O2-202 - Un-necessary space is showing on Create and Edit Customer modal | 0 | 0 | 2 | 0.25 | 2025-10-08 | 2025-10-08
O2-204 - When user click on edit icon of Subscription/Demo site, then Publish Changes button is showing in side navigation bar | 0.25 | 2 | 2 | 0.25 | 2025-10-15 | 2025-10-15
O2-222 - Same OTP is received and not getting expired after using. This issue occur sometime and sometime it is working fine. | 0 | 0 | 1 | 0.12
O2-227 - When user selects the Notification group in the edit site and re-saves the configuration then the datapoints column for the respective site is getting empty | 0.25 | 2 | 2 | 0.25 | 2025-10-15 | 2025-10-15
O2-228 - Data is not being ingested into ADX for any site and device. | 0 | 0 | 0 | 0
O2-229 - Un-necessary space is showing on Create and Edit GPS modal | 0 | 0 | 2 | 0.25 | 2025-10-08 | 2025-10-08
O2-231 - IT Data Connector table not visible on Batch BPM Query page despite successful ingestion | 0 | 0 | 0 | 0
O2-232 - Duplicate table creation shows success in UI but only one table exists in ADX. | 0 | 0 | 0 | 0
O2-233 - Pipeline creation fails on GET method despite Read API supporting both GET and POST. | 0 | 0 | 0 | 0
O2-234 - Run on Demand is not working for IT Data pipelines. | 0 | 0 | 0 | 0
O2-235 - Duplicate Manual and Cal tags are being created. | 0 | 0 | 1 | 0.12
O2-236 - Perform API validations on Create Connector screen to improve user experience. | 0 | 0 | 0 | 0
O2-239 - Latest values of GPS tag are not landing | 0 | 0 | 0 | 0
O2-241 - After the recent release, the system is unable to create any type of connector — all API calls are failing. | 0 | 0 | 0 | 0
O2-245 - Latest values for some real time tags are not updating also other tag values are updating with 5 mins interval | 0 | 0 | 0 | 0
O2-247 - Real time totalizer tag values are not updated in latest values screen, where as cal tag totalizer values are updated. | 0 | 0 | 0 | 0
O2-248 - The development team needs to add support for REST APIs without time parameters. | 0 | 0 | 0 | 0
O2-249 - Enhance the system to support custom date-time formats while creating connectors. | 0 | 0 | 0 | 0
O2-250 - Trigger execution functionality should be separated from data fetching logic. | 0 | 0 | 0 | 0
O2-251 - Latest values not updating since yesterday but Diagnostics alarm not fired yet | 0 | 0 | 0 | 0
O2-256 - Latest value of calculated tag is not updating. | 0 | 0 | 0 | 0
O2-257 - Conditional cal tag latest values are not displaying. | 0 | 0 | 0 | 0
O2-258 - Bugs Fixing, Tasks, Improvements | 0 | 0 | 40 | 5
O2-259 - Latest values for MQTT device are not updating while Live Telemetry show latest values | 0 | 0 | 0 | 0
O2-260 - Values are not showing on Write back screen after clicking on Get latest values button | 0 | 0 | 0 | 0
O2-261 - Account activation link should valid for 24 hours and if user send new link after 24 hours from web front-end then old link should expire | 0 | 0 | 0 | 0
O2-262 - Development Tools permission are not working | 0 | 0 | 4 | 0.5
O2-263 - OT Pipeline is not executing — showing 404 error, even though Test API and Create Pipeline show success | 0 | 0 | 0 | 0
O2-264 - Unable to start OT Data Pipeline when running manually | 0 | 0 | 0 | 0
O2-265 - IT Data Pipeline stuck in “In Progress” state when run manually | 0 | 0 | 0 | 0
O2-266 - Test API validation for Start Time, End Time, and Time Format missing — system allows Connector creation without proper validation. | 0 | 0 | 0 | 0
O2-267 - Full log file is not showing for failed scheduled and manual triggers. The system should display and provide the failed JSON response file in a downloadable format for both IT and OT pipelines. | 0 | 0 | 0 | 0
O2-269 - Notification group selection drop down is displaying on import site layout screen as well as on login screen. | 0 | 0 | 0 | 0
O2-270 - Wrong error message is displaying when I tried to create 3 areas through import site layout. All records are added but empty records are displaying in fault file. | 0 | 0 | 4 | 0.5
O2-271 - Notification group is inactive error displaying in fault file where as data alarms notifications are enabled in site. | 0 | 0 | 0 | 0
O2-272 - Tags having notification groups added in import site layout file are not adding when only data alarms notification configurations are enabled in respective site but they are adding when both data alarms and APX notification configurations are enabled. | 0 | 0 | 0 | 0
O2-273 - Statistical alarms notification group configured through import site layout are not displaying in configurations of real time and calculated tags against 24 hour duration on front end. | 0 | 0 | 0 | 0
O2-274 - No character limit is applied while creating area from import site layout where as maximum 15 character limit is applied on front end, also wrong error message is displaying when character limit is reached on front end. | 0 | 0 | 2 | 0.25
O2-275 - Conditional cal tags in which simple cal tags are used, they are displaying in counter and timer tags listing while viewing dependencies of simple calculated tag. | 0 | 0 | 2 | 0.25 | 2025-10-15
O2-276 - All tag's values are not getting landing for IOT, Kindly look into it | 0 | 0 | 1 | 0.12
O2-277 - REST API OT Connector is failing during execution. | 0 | 0 | 0 | 0
O2-278 - String and Datetime tag data not displaying on Latest Value page after successful OT REST API data ingestion. | 0 | 0 | 4 | 0.5
O2-279 - OMNI Agent fails to return all tables with schema, whereas the Read API supports this functionality. | 0 | 0 | 0 | 0
O2-283 - Creation modal closes when user enters a duplicate name for Workflow or Trigger instead of remaining open after showing error | 0 | 0 | 4 | 0.5
O2-284 - if final table name is not defined then BPM should not be published and if name is defined but schema is not defined incase of new table then system should throw error on both | 0 | 0 | 8 | 1
O2-285 - Wrong fault records quantity is displaying in imports site layout screen after uploading a file. | 0 | 0 | 6 | 0.75
O2-286 - BPM validation job fails showing "The BPM Validation Job Failed" message, but the Activity Status does not display any corresponding error | 0 | 0 | 8 | 1
O2-287 - When user uses activity name as table name inside other activity then upon validation the result shows but when user runs triggers it shows error | 0 | 0 | 0 | 0
O2-288 - APX real time and calculated tag latest values are not displaying. | 0 | 0 | 0 | 0
O2-289 - Latest values of tags created through import site layout are not displaying. | 0 | 0 | 0 | 0
O2-290 - Real time tag latest values created using MQTT device are not displaying. | 0 | 0 | 0 | 0
O2-291 - Timer Tag's values are not getting landed in OmniConnect. | 0 | 0 | 0 | 0
O2-292 - Azure SQL (IT) connector is not getting created on sites where SAP HANA or ODBC connectors are already created. | 0 | 0 | 0 | 0
O2-293 - The user has created multiple tags from the IoT device using the same source tag. However, the live value is populating for only one tag, while the others are not updating. | 0 | 0 | 0 | 0
O2-294 - Data alarm not triggering for the IOT tag alarm as its value is populating | 0 | 0 | 0 | 0
O2-295 - Value is not displaying on the Query Validation screen in the Batch BPM module, whereas the same value appears correctly when the user downloads the CSV file. | 0 | 0 | 0 | 0
O2-296 - Integer type of tags have no values,IOT | 0 | 0 | 1 | 0.12
O2-298 - Tag values imported through CSV bulk import are not displaying accordingly in export to excel when resolution time is 30 days. | 0 | 0 | 0 | 0
O2-299 - In Batch BPM, query with semicolon (;) at the end shows data in preview but fails on execution | 0 | 0 | 0 | 0
O2-303 - CORS error occurs while calling REST API Connector using Bearer Token authentication | 0 | 0 | 0 | 0
O2-305 - Latest value of date time against DL tag is displaying in UTC where as DL organization as well as OC site is set to local time. | 0 | 0 | 0 | 0
O2-307 - Validate button in the query modal is showing Green tick "Query is successfully validated" on the same time the system is showing error | 0 | 0 | 0 | 0
O2-308 - Query with validation errors is still being saved upon clicking the Validate button when user closes the query modal and reopen it | 0 | 0 | 0 | 0
O2-318 - AI Chat fails to retrieve the latest record from the table in OMNI Data Analysis | 0 | 0 | 0 | 0
O2-323 - AI Chat fails to answer the query “Can you show me the edge metrics details of device ID 7950” | 0 | 0 | 0 | 0
O2-324 - Downloaded result CSV does not show full timestamp — only minutes and seconds are displayed | 0 | 0 | 0 | 0
O2-325 - Downloaded JOSN Txt file should only contain data and exclude return description, asset info, and other metadata | 0 | 0 | 0 | 0
O2-326 - Agent returns associated tag list with distorted UI in AI Chat | 0 | 0 | 1 | 0.12
O2-332 - AI Chat returns an error when analyzing tag hourly maximums and averages | 0 | 0 | 0 | 0
O2-334 - zee 127 | 0 | 0 | 0 | 0
O2-339 - AI Chat returns invalid data when comparing timestamps for two tags with expected values | 0 | 0 | 0 | 0
O2-346 - SQL Scheduled logs UI is Disturbed, Issue was fixed on staging | 0 | 0 | 5 | 0.62 | 2025-10-20 | 2025-10-20
O2-349 - Stats Alarm Schedule SQL: Showing failure in logs but data is displayed in SQL | 0 | 0 | 0 | 0
O2-354 - Industry "Transportation" is Duplicated in Site Creation and update | 0 | 0 | 1.83 | 0.23
O2-941 - Ashghal Release | 110.5 | 884 | 1648 | 206 | 2026-01-19 | 2026-01-27
O2-1069 - APX Engine VM Deployment Readiness | 2 | 16 | 8 | 1
O2-1078 - Sanity Testing + Bug Fixes | 1 | 8 | 8 | 1 | 2026-01-22 | 2026-01-22
O2-1085 - Function Apps KeyVault Integration | 0 | 0 | 2 | 0.25
O2-1086 - Function Apps Deployments | 0 | 0 | 11 | 1.38
O2-1087 - Backfilling Data from production Ashghal Database | 0 | 0 | 4 | 0.5
O2-1088 - Bug Fixing | 0 | 0 | 12 | 1.5
O2-1164 - Quality Code Alarms, Trending In OC Deployments and Key Vaults | 0 | 0 | 4 | 0.5
O2-1165 - Testing / Bug Fixing | 0 | 0 | 16 | 2
O2-1177 - Updating function app python stack | 3 | 24 | 24 | 3 | 2026-01-23 | 2026-01-27
O2-1183 - Resource Cleanup and Deletion | 0.5 | 4 | 4 | 0.5 | 2026-01-28 | 2026-01-28
O2-1212 - TLS Update and Data Backfill | 6 | 48 | 25 | 3.12 | 2026-01-29 | 2026-02-03
O2-1213 - Qatar Central ADX Retention Policy Restoration | 1 | 8 | 2 | 0.25 | 2026-01-29 | 2026-01-29
O2-1272 - Release management | 0 | 0 | 96 | 12
O2-1273 - Batch/Bpm/Connectors End to end Testing + Bug Fixes | 0 | 0 | 32 | 4
O2-1274 - Batch/BPM/Connectors Deployements | 0 | 0 | 16 | 2
O2-1751 - Batch/Bpm/Connectors End to end Testing + Bug Fixes | 0 | 0 | 40 | 5 | 2026-01-20 | 2026-01-27
O2-942 - Key Vault Setup and Integration | 11 | 88 | 72 | 9 | 2026-01-15 | 2026-01-16
O2-1162 - Key Vault Secret Retrieval Testing and Changes | 0 | 0 | 0 | 0
O2-953 - Key Vault Configuration and Secrets Creation | 1 | 8 | 8 | 1 | 2026-01-19 | 2026-01-19
O2-954 - Managed Identities RBAC to Key Vault | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
O2-955 - Key Vault Secret Retrieval Testing and Changes | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
O2-956 - Key Vault Secret Retrieval Testing and Changes | 0 | 0 | 8 | 1
O2-957 - Key Vault Secret Retrieval Testing and Changes | 1 | 8 | 8 | 1 | 2026-01-22 | 2026-01-22
O2-958 - Key Vault Secret Retrieval Testing and Changes | 0 | 0 | 8 | 1
O2-959 - Key Vault Secret Retrieval Testing and Changes | 0 | 0 | 8 | 1
O2-960 - Key Vault Secret Retrieval Testing and Changes | 0 | 0 | 0 | 0
O2-961 - Key Vault Secret Retrieval Testing and Changes | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
O2-962 - Key Vault Secret Retrieval Testing and Changes | 1 | 8 | 8 | 1 | 2026-01-20 | 2026-01-20
O2-963 - Key Vault Secret Retrieval Testing and Changes | 0 | 0 | 0 | 0
O2-943 - ADX Schema Changes and Verification | 0 | 0 | 24 | 3
O2-944 - OmniConnect DE Logs SQL Database Schema Changes and Verification | 1 | 8 | 32 | 4
O2-945 - BPM Batch Compute Deployments | 0 | 0 | 8 | 1
O2-1161 - Key Vaults and Deployments | 0 | 0 | 8 | 1
O2-946 - Log analytics | 0 | 0 | 16 | 2
O2-947 - OC Faster Deployments | 0 | 0 | 0 | 0
O2-948 - Diagnostics Deployments | 0 | 0 | 16 | 2
O2-949 - Stats Alarms Deployments | 0 | 0 | 4 | 0.5
O2-950 - Scheduled Pulls and Exports Deployments | 0 | 0 | 24 | 3
O2-951 - Read API Deployments | 2 | 16 | 16 | 2 | 2026-01-21 | 2026-01-22
O2-983 - Schema Changes in DE Logs Database | 1 | 8 | 8 | 1 | 2026-01-21 | 2026-01-21
O2-984 - Code changes for Ashghal | 1 | 8 | 8 | 1 | 2026-01-22 | 2026-01-22
O2-952 - Anamoly Detection Deployments | 0 | 0 | 0 | 0
O2-965 - Key Vaults, Secrets Generation for Web App service | 0 | 0 | 8 | 1
O2-966 - Database Comparer Overview | 0 | 0 | 4 | 0.5
O2-980 - All Code deployment with Merge Conflict Resolved | 0 | 0 | 6 | 0.75
O2-981 - Keyvault integration in App service | 0 | 0 | 4 | 0.5
O2-982 - DE Production Release to Ashghal | 1 | 8 | 8 | 1 | 2026-01-15 | 2026-01-15
O2-1497 - Production Release | 1 | 8 | 8 | 1 | 2026-01-23 | 2026-01-23
O2-986 - OC-VPC-Regression 01/22/2025 | 0 | 0 | 258 | 32.25
O2-1037 - All Countries Are Not Displayed in Country Dropdown While Creating or Editing Customer and Site | 0 | 0 | 0 | 0
O2-1038 - Tag Level Diagnostics Checkbox Missing in Notification Group | 0 | 0 | 0 | 0
O2-1039 - System Alarm Message Inconsistency Between Ashghal and Production Blue | 0 | 0 | 1 | 0.12
O2-1040 - System Alarms Not Displayed for UserDefinedFunctions and UserDefinedTables | 1 | 8 | 1 | 0.12 | 2026-01-23 | 2026-01-23
O2-1059 - Latest Values Not Updating for Real-Time Tags Even After Publishing Changes | 0 | 0 | 0 | 0
O2-1064 - Write back is FAIL. | 0 | 0 | 1 | 0.12
O2-1068 - Source tags of MQTT device are not displaying. | 5 | 40 | 72 | 9
O2-1071 - User Defined Notifications are not getting received. | 0 | 0 | 2 | 0.25
O2-1072 - Totalizer tag's values are not getting received | 0 | 0 | 1 | 0.12
O2-1073 - Unable to create timer and counter tags | 0 | 0 | 1 | 0.12
O2-1074 - Calculated tag latest values are not displaying. | 0 | 0 | 0 | 0
O2-1075 - Latest Values Not Populating for Ingestion Format Devices | 0 | 0 | 0 | 0
O2-1076 - Diagnostics Alarm Emails Are Not Being Received | 0 | 0 | 0 | 0
O2-1077 - User Defined Function" and "UserDefined Table" is missing from roles and permissions of ASHGHAL | 1 | 8 | 2 | 0.25 | 2026-01-23 | 2026-01-23
O2-1079 - Permissions are not working according to the given access for all types of users. showing the actions to be performed while permissions were off for Create and Update, Delete Both Userdefined Function and Userdefined Table | 0 | 0 | 2 | 0.25
O2-1080 - AM/PM Missing from Date-Time Filter on Diagnostics Screen | 0 | 0 | 0 | 0
O2-1081 - Csv Bulk Import Success in blobs but no update in file status | 0 | 0 | 2 | 0.25
O2-1084 - Tag Count Shows Zero After Scheduling Scan on IoT Flatten and MQTT InHand Devices | 0 | 0 | 0 | 0
O2-1089 - The "Single X,y-Axis Chart" is not available to be selected on Ashghal | 0 | 0 | 0 | 0
O2-1101 - Error is getting displayed with success message right after going to the "Data Selection" screen. only on VPC | 0 | 0 | 9 | 1.12
O2-1108 - SQL Fail, just pipelines are getting created, No monitoring results are here to show no Data in SQL server. | 0 | 0 | 2 | 0.25
O2-1114 - Invalid data is getting displayed in Site Hierarchy, against SQL pipelines | 0 | 0 | 1 | 0.12
O2-987 - Testing By Kamran | 4 | 32 | 33 | 4.12 | 2026-01-22 | 2026-01-27
O2-988 - Testing By M.Abbas | 4 | 32 | 32 | 4 | 2026-01-22 | 2026-01-26
O2-989 - Testing By Waqar | 4 | 32 | 32 | 4 | 2026-01-22 | 2026-01-27
O2-990 - Testing By Zeeshan | 4 | 32 | 32 | 4 | 2026-01-22 | 2026-01-27
O2-991 - Testing By Namra | 4 | 32 | 32 | 4 | 2026-01-22 | 2026-01-27
O2-95 - Scheduled Pulls from Data Source (SFTP) | 35 | 280 | 708 | 88.5
O2-104 - Development | 12 | 96 | 102 | 12.75 | 2025-10-20 | 2025-10-24
O2-343 - Frontend Development + Unit Testing | 0 | 0 | 38 | 4.75
O2-367 - Backend Connectors and Trigger APIs modifications | 0 | 0 | 10 | 1.25
O2-368 - New Schema changes for Pipeline | 0 | 0 | 1 | 0.12
O2-369 - SFTP Pipeline APIs development | 0 | 0 | 3 | 0.38
O2-375 - SFTP Development for JSON and CSV formats | 0 | 0 | 32 | 4
O2-430 - Backend APIs for Pipeline & Triggers | 0 | 0 | 18 | 2.25
O2-105 - SQA | 3 | 24 | 183 | 22.88 | 2025-10-27 | 2025-10-30
O2-553 - Bugs Fixing + Tasks + Improvements | 0 | 0 | 56 | 7
O2-591 - Production Release | 15 | 120 | 103 | 12.88 | 2025-11-05 | 2025-11-10
O2-594 - The system alarm name for live values should only be "Live Values Accessed" on Production, just like it is on staging. | 0 | 0 | 0 | 0
O2-599 - Duplication in Data Alarms for for all tags Timer, Totalizer and real | 0 | 0 | 0 | 0
O2-604 - Real Tag is not getting deleted in first attempt. | 0 | 0 | 6 | 0.75 | 2025-11-10 | 2025-11-10
O2-605 - Error is Reoccurring on Blue Prod for anomaly User train group | 0 | 0 | 0.5 | 0.06
O2-606 - After creation of model again "Correlation Matrix" data is missing | 0 | 0 | 0.5 | 0.06
O2-106 - User Manual | 3 | 24 | 29 | 3.62 | 2025-10-27 | 2025-10-30
O2-562 - SFTP - Create - Manual IR Configuration Guide | 0 | 0 | 8 | 1
O2-563 - How to - Create - Create New SFTP Connector | 0 | 0 | 16 | 2
O2-564 - Fields - Update - Create New Connector | 0 | 0 | 2 | 0.25
O2-565 - How to - Update - Add a table of Site-level Validations for Connectors | 0 | 0 | 3 | 0.38
O2-107 - Production Release | 2 | 16 | 40 | 5 | 2025-10-31 | 2025-10-31
O2-992 - Boiler What-If | 8 | 64 | 128 | 16
O2-1000 - Production Release | 0 | 0 | 0 | 0
O2-1001 - Add Training Material (P) | 0 | 0 | 0 | 0
O2-993 - Design What-If Model (P) | 5 | 40 | 40 | 5 | 2025-12-23 | 2026-01-02
O2-994 - Development (if required) | 0 | 0 | 0 | 0
O2-995 - Template, wizards and dashboard design (P) | 0 | 0 | 0 | 0
O2-996 - Dashboard development and Asset type addition | 0 | 0 | 0 | 0
O2-997 - OC Process testing (P) | 0 | 0 | 24 | 3
O2-1416 - OC Process testing (P) | 3 | 24 | 24 | 3 | 2026-02-06 | 2026-02-10
O2-998 - SQA | 0 | 0 | 0 | 0
O2-999 - User Manual | 0 | 0 | 0 | 0
OAM | 0 | 0 | 1408 | 176 | 2025-01-02 | 2025-03-31
ODL | 130.94 | 1047.5 | 1231 | 153.88 | 2025-09-25 | 2026-12-31
ODL-103 - Support Tickets: Avanceon Retail Team | 1.5 | 12 | 24 | 3
ODL-104 - Support Tickets | 0 | 0 | 12 | 1.5
ODL-105 - Datetime is getting disturbed while creating work orders in M365 from CBRE posted file | 1 | 8 | 8 | 1 | 2026-03-16 | 2026-03-16
ODL-106 - Work Order type is not saving as mentioned in CBRE posted sheet | 0.25 | 2 | 2 | 0.25 | 2026-03-17 | 2026-03-17
ODL-107 - Null target start and finish datetime exception handled | 0.25 | 2 | 2 | 0.25 | 2026-03-17 | 2026-03-17
ODL-119 - Organizational Trainings/Workshops/Drills | 1.5 | 12 | 24 | 3 | 2026-01-01 | 2026-12-31
ODL-120 - Mindset Training | 0 | 0 | 12 | 1.5 | 2026-03-31 | 2026-03-31
ODL-121 - Mindset training - AHK | 0.5 | 4 | 4 | 0.5 | 2026-03-31 | 2026-03-31
ODL-122 - Mindset training - MZ | 0.5 | 4 | 4 | 0.5 | 2026-03-31 | 2026-03-31
ODL-123 - Mindset Training - Taimur Zahid | 0.5 | 4 | 4 | 0.5 | 2026-03-31 | 2026-03-31
ODL-4 - DEWA Pumps Operating Philosophy | 26.62 | 213 | 399 | 49.88
ODL-84 - DEWA Pumps Operating Philosophy | 0 | 0 | 199 | 24.88
ODL-111 - 1. Proposal & PO | 3 | 24 | 24 | 3 | 2025-09-25 | 2025-10-09
ODL-112 - 2. ODL in-house tasks (engineering) | 14 | 112 | 104 | 13 | 2025-10-01
ODL-113 - 3. DEWA approval | 4 | 32 | 20 | 2.5 | 2025-11-03 | 2025-11-07
ODL-114 - 4. Hand-over to Avanceon | 3 | 24 | 24 | 3 | 2025-11-03 | 2025-11-28
ODL-115 - 5. PQ Documentation for DEWA approval | 2 | 16 | 16 | 2 | 2025-12-08
ODL-116 - 7. OCP document scope | 0.62 | 5 | 5 | 0.62 | 2026-03-04 | 2026-03-27
ODL-117 - Commissioning support | 0 | 0 | 0 | 0
ODL-85 - 6. Support Avanceon for development | 0 | 0 | 3 | 0.38 | 2025-12-01
ODL-46 - EPR Reporting | 6 | 48 | 92 | 11.5
ODL-47 - Taimur Zahid | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-20
ODL-51 - 13 Feb 2026 | 1 | 8 | 8 | 1 | 2026-02-13 | 2026-02-13
ODL-50 - Zain Munir | 0 | 0 | 2.5 | 0.31
ODL-52 - Scrum + Jira Activity 13 Feb 2026 | 0.31 | 2.5 | 2.5 | 0.31 | 2026-02-13 | 2026-02-13
ODL-54 - Arsalan Zafar Khan | 0 | 0 | 8 | 1
ODL-118 - Sprint Planning Activity March 31, 26. | 0.25 | 2 | 2 | 0.25
ODL-124 - Jira Time Log Activity 8 April 2026 | 0.25 | 2 | 2 | 0.25 | 2026-04-08 | 2026-04-08
ODL-55 - Jira Time Log Activity 13 Feb 2026 | 0.25 | 2 | 2 | 0.25 | 2026-02-13 | 2026-02-13
ODL-65 - Next Sprint Planning Activity 19 Feb. | 0.25 | 2 | 2 | 0.25 | 2026-02-19 | 2026-02-19
ODL-57 - Mohsin Junaid | 0 | 0 | 8 | 1
ODL-58 - 13 Feb 2026 | 0 | 0 | 8 | 1
ODL-59 - Faiza Nasir | 0 | 0 | 6 | 0.75
ODL-60 - Add planned dates and estimates for all assigned tasks / stories | 0.25 | 2 | 2 | 0.25 | 2026-02-13 | 2026-02-13
ODL-79 - Project Planning and Jira Management for team | 0.5 | 4 | 4 | 0.5 | 2026-02-13 | 2026-02-13
ODL-61 - Muhammad Ahmad Saleem | 0 | 0 | 3 | 0.38
ODL-62 - 13 February 2026 | 0.38 | 3 | 3 | 0.38 | 2026-02-13 | 2026-02-13
ODL-66 - Muhammad Abdullah | 0 | 0 | 2 | 0.25
ODL-67 - Next Sprint Planning Activity 19 Feb. | 0.25 | 2 | 2 | 0.25 | 2026-02-19 | 2026-02-19
ODL-76 - Nadeem Ahmed | 0.25 | 2 | 8.5 | 1.06 | 2026-02-19 | 2026-02-19
ODL-132 - Support, Bug fixing, meeting with clients/new customer and internal meeting with team | 0 | 0 | 0 | 0 | 2026-03-01
ODL-77 - Next sprint planning 2026 | 0 | 0 | 0 | 0
ODL-78 - Meeting with team to improve capability of LogChat | 0 | 0 | 0 | 0
ODL-90 - CDC review at CP-1 meeting with Colgate team | 0.25 | 2 | 2 | 0.25 | 2026-03-02 | 2026-03-02
ODL-93 - Digital Log road map meeting | 0.12 | 1 | 0 | 0 | 2026-03-04 | 2026-03-04
ODL-94 - Custom Report development for Zomco demo | 0.5 | 4 | 3 | 0.38 | 2026-03-10 | 2026-03-10
ODL-95 - Meeting with Zomco regarding Digital Log Demo - along with PreSale team | 0.19 | 1.5 | 1.5 | 0.19 | 2026-03-10 | 2026-03-10
ODL-63 - Handover Sessions | 12.56 | 100.5 | 214 | 26.75
ODL-130 - Knowledge Transfer | 0 | 0 | 4 | 0.5
ODL-131 - KT Session for Fuel-Chat and Omni-Chat | 0.5 | 4 | 4 | 0.5 | 2026-04-21 | 2026-04-21
ODL-5 - Ali Qumail - Handover sessions | 0 | 0 | 103 | 12.88
ODL-10 - Live Values+Tag Dependencies+Bulk Tag Deletion Handover Session | 0.19 | 1.5 | 3 | 0.38 | 2026-01-30 | 2026-01-30
ODL-11 - Data Alarms+Statistical Alarms+ Tag Diagnostics Handover Session | 1 | 8 | 3 | 0.38 | 2026-01-30 | 2026-01-30
ODL-12 - Real and GPS Handover Session | 0.25 | 2 | 2 | 0.25 | 2026-01-28 | 2026-01-28
ODL-13 - Calculated, Counter and Timer Tags Handover | 0.19 | 1.5 | 3 | 0.38 | 2026-01-29 | 2026-01-29
ODL-14 - Anomaly Detection Handover Session | 0.19 | 1.5 | 3 | 0.38 | 2026-02-03 | 2026-02-03
ODL-15 - Export Handover Session | 0.19 | 1.5 | 3 | 0.38 | 2026-02-03 | 2026-02-03
ODL-16 - Apx Template/Insights/Performance Handover Session | 0.38 | 3 | 3 | 0.38 | 2026-02-04 | 2026-02-04
ODL-17 - Handover - Site status screen , Read API notification , Data point management | 0.12 | 1 | 1 | 0.12 | 2026-02-06 | 2026-02-06
ODL-18 - Handover - Real API Dashboard | 0.31 | 2.5 | 2.5 | 0.31 | 2026-02-06 | 2026-02-06
ODL-19 - HANDOVER - Import Site Layout | 0.25 | 2 | 2 | 0.25 | 2026-02-09 | 2026-02-09
ODL-20 - Handover Session 11 - APX insights | 0.12 | 1 | 1 | 0.12
ODL-21 - Handover Session 7 - Create formula , Variable , Asset subtype , Asset type | 0.56 | 4.5 | 4.5 | 0.56 | 2026-02-02 | 2026-02-02
ODL-22 - Handover Session 6 - Bulk Device Replication , Connection strings (EDGE) | 0.31 | 2.5 | 2.5 | 0.31 | 2026-02-02 | 2026-02-02
ODL-23 - Handover - Setting | 0.38 | 3 | 3 | 0.38 | 2026-02-06 | 2026-02-06
ODL-25 - Handover -User Management + Authorization | 0.19 | 1.5 | 3 | 0.38 | 2026-02-10 | 2026-02-10
ODL-26 - Handover - Nested Cal Tag + Code Review | 0.81 | 6.5 | 7.5 | 0.94 | 2026-02-10 | 2026-02-10
ODL-27 - Handover - On Hold Modules | 0.38 | 3 | 4.5 | 0.56 | 2026-02-11 | 2026-02-11
ODL-28 - Handover - Final Queries + Resolved Concerns | 0.75 | 6 | 6 | 0.75 | 2026-02-11 | 2026-02-11
ODL-29 - Handover -User Management + Authorization | 0.25 | 2 | 2 | 0.25 | 2026-02-10 | 2026-02-10
ODL-30 - Handover - Device Diagnostics & Nested Cal Tag + Code Review | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-10 | 2026-02-10
ODL-31 - Handover - On Hold Modules | 0.12 | 1 | 1 | 0.12 | 2026-02-11 | 2026-02-11
ODL-32 - Handover - Final Queries + Resolved Concerns | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-11 | 2026-03-11
ODL-33 - Handover - Final Quiz and Queries | 0.12 | 1 | 1 | 0.12 | 2026-02-12 | 2026-02-12
ODL-34 - Real Time / GPS Tag Handover Session | 0.12 | 1 | 1 | 0.12 | 2026-01-28 | 2026-01-28
ODL-35 - Calculated+Timer+Counter Tags Handover Session | 0.12 | 1 | 1 | 0.12 | 2026-01-29 | 2026-01-29
ODL-36 - Calculated+Timer+Counter Tags Handover Session | 0.12 | 1 | 1 | 0.12 | 2026-01-30 | 2026-01-30
ODL-37 - Live Values+Tag Dependencies+Bulk Tag Deletion Handover Session | 0.12 | 1 | 1 | 0.12 | 2026-02-02 | 2026-02-02
ODL-38 - Anomaly Detection Handover Session | 0.12 | 1 | 1 | 0.12 | 2026-02-03 | 2026-02-03
ODL-39 - Export Handover Session | 0.12 | 1 | 1 | 0.12 | 2026-02-03 | 2026-02-03
ODL-40 - Apx Template/Insights/Performance Handover Session | 0.12 | 1 | 1 | 0.12 | 2026-02-04 | 2026-02-04
ODL-41 - Handover -User Management + Authorization | 0.12 | 1 | 1 | 0.12 | 2026-02-06 | 2026-02-06
ODL-42 - Handover - Nested Cal Tag + Code Review | 0.12 | 1 | 1 | 0.12 | 2026-03-09 | 2026-02-09
ODL-43 - Handover - On Hold Modules | 0.12 | 1 | 1 | 0.12 | 2026-02-10 | 2026-02-10
ODL-44 - Handover - Final Queries + Resolved Concerns | 0.12 | 1 | 1 | 0.12 | 2026-02-12 | 2026-02-12
ODL-45 - Handover Quiz | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-12 | 2026-02-12
ODL-48 - Handover : Queries related to Anomaly and Tags | 0.62 | 5 | 5 | 0.62 | 2026-02-06 | 2026-02-06
ODL-49 - Handover Quiz | 0.12 | 1 | 1 | 0.12 | 2026-02-12 | 2026-02-12
ODL-6 - Real Time / GPS Tag Handover Session | 0.25 | 2 | 2 | 0.25 | 2026-01-28 | 2026-01-28
ODL-68 - Live Values,Tag Dependencies,Bulk Tag Deletion Handover Session | 0.19 | 1.5 | 1.5 | 0.19 | 2026-01-30 | 2026-01-30
ODL-69 - Manual,Totalizer Tags Handover Session | 0.19 | 1.5 | 1.5 | 0.19 | 2026-01-29 | 2026-01-29
ODL-7 - Real Time and GPS Tags handover Session | 0.12 | 1 | 1 | 0.12
ODL-70 - Data Alarms,Statistical Alarms, Tag Diagnostics Handover Session | 0.19 | 1.5 | 1.5 | 0.19 | 2026-01-30 | 2026-01-30
ODL-71 - Anomaly Detection Handover | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-03 | 2026-02-03
ODL-72 - Export Handover | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-03 | 2026-02-03
ODL-73 - Apx Template,Insights,Performance Handover Session | 0.38 | 3 | 3 | 0.38 | 2026-02-04 | 2026-02-04
ODL-74 - Real API Dashboard - Handover | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-06 | 2026-02-06
ODL-75 - Handover Session- Bulk Device Replication , Connection strings (EDGE) | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-02 | 2026-02-02
ODL-8 - Calculated+Timer+Counter Tags Handover Session | 0.19 | 1.5 | 1.5 | 0.19 | 2026-01-29 | 2026-01-29
ODL-9 - Manual+Totalizer Tags Handover Session | 0.19 | 1.5 | 3 | 0.38 | 2026-01-29 | 2026-01-29
ODL-64 - General Research work | 2 | 16 | 96 | 12
ODL-125 - Chillowatt product review and understanding | 0 | 0 | 16 | 2 | 2026-04-07 | 2026-04-09
ODL-126 - Chillowatt Process Understanding | 0 | 0 | 8 | 1 | 2026-04-07 | 2026-04-07
ODL-127 - Chillowatt Handover Code Understanding | 0 | 0 | 8 | 1 | 2026-04-09 | 2026-04-09
ODL-128 - OEE URS Understanding and review leading to DDS | 0 | 0 | 16 | 2 | 2026-04-02 | 2026-04-03
ODL-129 - URS review OEE | 0 | 0 | 16 | 2 | 2026-04-02 | 2026-04-03
ODL-133 - Perform ChilloWatt requirement analysis followed by architecture design, workflow discussion, and technical implementation planning - AZ | 2 | 16 | 16 | 2 | 2026-04-30 | 2026-04-30
ODL-80 - Project Management - EPR Reports Building | 80.75 | 646 | 382 | 47.75 | 2026-02-03 | 2026-03-13
ODL-108 - Handover | 0 | 0 | 0 | 0
ODL-109 - Bug Fixing | 0 | 0 | 0 | 0
ODL-110 - TK approved Employee Performance Dashboard & Metrics | 0 | 0 | 0 | 0
ODL-81 - Custom Reports (non power bi) | 24.88 | 199 | 191 | 23.88 | 2026-02-03 | 2026-03-13
ODL-100 - Unified Jira projects manager | 3.25 | 26 | 26 | 3.25 | 2026-03-02 | 2026-03-05
ODL-101 - Epics Planner for Leadership Budgeting | 0.12 | 1 | 1 | 0.12 | 2026-03-16 | 2026-03-16
ODL-102 - Employee Performance Dashboard (Simple/Advanced scoring) | 0.12 | 1 | 1 | 0.12 | 2026-03-16 | 2026-03-16
ODL-82 - Audit of Power BI and Requirements analysis | 5 | 40 | 24 | 3 | 2026-02-03 | 2026-02-09
ODL-86 - Basic Report Structuring | 5 | 40 | 40 | 5 | 2026-02-10 | 2026-02-16
ODL-87 - Advanced Report Structuring | 4.25 | 34 | 34 | 4.25 | 2026-02-17 | 2026-02-23
ODL-88 - Adding Data Story Reports | 3.25 | 26 | 26 | 3.25 | 2026-02-24 | 2026-02-27
ODL-91 - Improving Employee Performance Report | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-10 | 2026-03-10
ODL-92 - Improving Score Card Report - Nested Report | 1.62 | 13 | 13 | 1.62 | 2026-03-06 | 2026-03-09
ODL-96 - Building Colossal Refresh | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-11 | 2026-03-11
ODL-97 - Unified Data Refresh for All Reports | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-13 | 2026-03-13
ODL-98 - Fixing data sync issues across reports | 0.5 | 4 | 4 | 0.5 | 2026-03-12 | 2026-03-12
ODL-99 - Building IPP Planner and IPP Dashboard | 0.31 | 2.5 | 2.5 | 0.31 | 2026-03-12 | 2026-03-12
ODL-83 - SQA | 0 | 0 | 0 | 0
RLT | 374.38 | 2995 | 8615.13 | 1076.89 | 2024-04-29 | 2028-12-31
SUBS | 287.33 | 2298.64 | 2246.15 | 280.77 | 2026-01-07 | 2026-04-29
SUBS-236 - Subscription Management V2 | 34.05 | 272.42 | 488.84 | 61.1
SUBS-238 - Demo / Handover / Discussions | 0 | 0 | 46.42 | 5.8
SUBS-243 - Demo with Management + Internal Team Discussion | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-24
SUBS-260 - Demo with Management / Feedback | 0.62 | 5 | 5 | 0.62 | 2026-03-24 | 2026-03-24
SUBS-267 - Demo with TOM | 0.25 | 2 | 2 | 0.25 | 2026-03-31 | 2026-03-31
SUBS-269 - Demo with TOM | 0.25 | 2 | 2 | 0.25 | 2026-03-31 | 2026-03-31
SUBS-275 - Pricing Demo to TOM | 0.25 | 2 | 2 | 0.25 | 2026-03-31 | 2026-03-31
SUBS-276 - Internal review after incorporating all feedbacks | 1.5 | 12 | 12 | 1.5 | 2026-04-02 | 2026-04-03
SUBS-277 - OmniConnect's Pricing Review with Asmar | 0.12 | 1 | 1 | 0.12 | 2026-04-07 | 2026-04-07
SUBS-278 - 2nd Pricing review with TOM | 0.19 | 1.5 | 1.5 | 0.19 | 2026-04-07 | 2026-04-07
SUBS-279 - Changes Overview with Asmar | 0.08 | 0.67 | 0.67 | 0.08 | 2026-04-07 | 2026-04-07
SUBS-280 - Second Demo to Tom | 0.19 | 1.5 | 1.5 | 0.19 | 2026-04-07 | 2026-04-07
SUBS-282 - Pricing overview with Asmar | 0.12 | 1 | 1 | 0.12 | 2026-04-07 | 2026-04-07
SUBS-284 - 2nd Pricing review with Tom | 0.19 | 1.5 | 1.5 | 0.19 | 2026-04-07 | 2026-04-07
SUBS-290 - 3rd Pricing Review with Tom | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-09 | 2026-04-09
SUBS-291 - 3rd Pricing Review with Tom | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-09 | 2026-04-09
SUBS-292 - 3rd Pricing Review with Tom | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-09 | 2026-04-09
SUBS-293 - IP meeting Demo | 0.12 | 1 | 1 | 0.12 | 2026-04-10 | 2026-04-10
SUBS-294 - Pre Launch Demo with Sales Team | 0.25 | 2 | 2 | 0.25 | 2026-04-21 | 2026-04-21
SUBS-295 - Pre-Launch Demo Sales Team | 0.19 | 1.5 | 1.5 | 0.19 | 2026-04-21 | 2026-04-21
SUBS-299 - Meeting with KM for OmniDocs Pricing | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-23 | 2026-04-23
SUBS-300 - Meeting with Khurram Mir over Pricing | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-23 | 2026-04-23
SUBS-301 - Meeting with Khurram Mir for OmniDocs Pricing | 0.06 | 0.5 | 0.5 | 0.06 | 2026-04-23 | 2026-04-23
SUBS-303 - Meeting with Asmar for Omni Connect Pricing and Sales feedback | 0.09 | 0.75 | 0.75 | 0.09 | 2026-04-28 | 2026-04-28
SUBS-239 - Development | 0 | 0 | 80 | 10
SUBS-244 - Updated Product Configs + Info Update | 1 | 8 | 8 | 1 | 2026-03-25 | 2026-03-25
SUBS-249 - Added Discount Field + Integrated New Tier price logic | 1 | 8 | 8 | 1 | 2026-03-25 | 2026-03-25
SUBS-258 - Added In-app Reset Password Module | 0.5 | 4 | 4 | 0.5 | 2026-03-26 | 2026-03-26
SUBS-259 - Add discount in Qoutes | 0.62 | 5 | 5 | 0.62 | 2026-03-25 | 2026-03-25
SUBS-266 - Configuring OmniConnect + Moving Data to Production | 1 | 8 | 8 | 1 | 2026-03-31 | 2026-03-31
SUBS-268 - Incorporating Changes by TOM | 1 | 8 | 8 | 1 | 2026-04-01 | 2026-04-01
SUBS-272 - Added MeterType Update Feature + Unit Testing + Deployments on Staging | 1 | 8 | 8 | 1 | 2026-04-02 | 2026-04-02
SUBS-281 - Add sorting mechanism for products and features | 0.38 | 3 | 3 | 0.38 | 2026-04-08 | 2026-04-10
SUBS-285 - Incorporate Sorting, Info Icons and UI adjustments in review from Tom | 1.94 | 15.5 | 15.5 | 1.94 | 2026-04-09 | 2026-04-08
SUBS-287 - Manage Onetime total in quotations | 0.25 | 2 | 2 | 0.25 | 2026-04-08 | 2026-04-08
SUBS-297 - CRM Id Addition & Pre Launch Review Modifications | 1.31 | 10.5 | 10.5 | 1.31 | 2026-04-22 | 2026-04-23
SUBS-240 - SQA | 3 | 24 | 64.5 | 8.06 | 2026-03-25 | 2026-03-27
SUBS-245 - Testing By Waqar | 3 | 24 | 24 | 3 | 2026-03-25 | 2026-03-27
SUBS-265 - Omni Connect Configuration (April) | 1 | 8 | 8 | 1 | 2026-03-31 | 2026-03-31
SUBS-296 - CRM ID Verification | 0.12 | 1 | 1 | 0.12 | 2026-04-22 | 2026-04-22
SUBS-298 - Verification of Sales Team Configuration Requirements | 0.44 | 3.5 | 3.5 | 0.44 | 2026-04-23 | 2026-04-23
SUBS-302 - Omni Docs Configuration | 1 | 8 | 8 | 1 | 2026-04-27 | 2026-04-27
SUBS-304 - Incorporate Omni Connect Enhancements | 0.5 | 4 | 4 | 0.5 | 2026-04-29 | 2026-04-29
SUBS-305 - Omni Connect Configuration (May) | 2 | 16 | 16 | 2 | 2026-04-01 | 2026-04-02
SUBS-241 - Bug Fixing | 0 | 0 | 19.5 | 2.44
SUBS-246 - Old Forgot Password Link Remains Valid After New Reset Email and Even After Use | 0 | 0 | 0 | 0
SUBS-247 - User is able to set current password as new password. | 0 | 0 | 0 | 0
SUBS-248 - Eye Icon on New Password Field Also Affects Confirm Password Field | 0 | 0 | 0 | 0
SUBS-250 - Feature Code Validation Incorrectly Applied Across Products | 0 | 0 | 0 | 0
SUBS-251 - “Back to Login” Link Missing on Set New Password Screen | 0 | 0 | 0 | 0
SUBS-252 - Implement Reset Password Option Within the Application | 0 | 0 | 0 | 0
SUBS-253 - Final Bundle Rate Not Applied Correctly Across All Sites at Maximum Threshold | 0 | 0 | 0 | 0
SUBS-254 - Added Discount Not Reflected in Subscription Summary on Viewing Quotation | 0 | 0 | 0 | 0
SUBS-255 - Discount Not Retained and Price Changes When Opening Quotation in Edit Mode | 0 | 0 | 0 | 0
SUBS-256 - Meter Type Label Not Displayed on Calculator Screen (OmniChat) | 0 | 0 | 0 | 0
SUBS-257 - QA reported Bugs for Auth and Admin Flow | 0.5 | 4 | 4 | 0.5 | 2026-03-26 | 2026-03-26
SUBS-261 - QA Reported Bugs for Calculator and Quotations | 1 | 8 | 8 | 1 | 2026-03-27 | 2026-03-27
SUBS-263 - User Unable to Save Quotation on Production | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-30 | 2026-03-30
SUBS-270 - Price is not showing for Report Builder and Offline Mode features in DL | 0 | 0 | 0 | 0
SUBS-271 - Final reviewing after bugs fixing and before IA/Tom's review | 1 | 8 | 4 | 0.5 | 2026-03-31 | 2026-03-31
SUBS-273 - Bug Fixing and Discussions | 0.31 | 2.5 | 2.5 | 0.31 | 2026-03-30 | 2026-03-31
SUBS-286 - Calculator Screen Not Reset When Changing Product While Editing Quotation | 0 | 0 | 0 | 0
SUBS-288 - Products Not Loading on Production | 0.06 | 0.5 | 0.5 | 0.06
SUBS-242 - Production Release | 0 | 0 | 34 | 4.25
SUBS-262 - Testing By Waqar | 1 | 8 | 8 | 1 | 2026-03-30 | 2026-03-30
SUBS-264 - FE & BE Deployments + DB Migrations and Cleanup | 1 | 8 | 8 | 1 | 2026-03-30 | 2026-03-30
SUBS-274 - Deployments + Data Migration + Product Info Updates | 1 | 8 | 8 | 1 | 2026-04-03 | 2026-04-03
SUBS-283 - Testing by Waqar After Changes incorporated as per TOM’s feedback. | 1 | 8 | 8 | 1 | 2026-04-09 | 2026-04-09
SUBS-289 - Production Deployment - Tom's Feedback | 0.25 | 2 | 2 | 0.25 | 2026-04-09 | 2026-04-09
SUBS-237 - Technical Support | 0 | 0 | 0 | 0
SUBS-5 - Subscription Management | 253.28 | 2026.22 | 1757.31 | 219.66 | 2026-01-07 | 2026-03-06
SUBS-10 - Handover | 1.38 | 11 | 13.37 | 1.67 | 2026-02-27 | 2026-02-27
SUBS-165 - Handover By Kamran | 0.12 | 1 | 0 | 0 | 2026-02-27 | 2026-02-27
SUBS-166 - Handover By Namra | 0.12 | 1 | 2.22 | 0.28 | 2026-02-27 | 2026-02-27
SUBS-167 - Handover By Zeeshan | 0.12 | 1 | 2 | 0.25 | 2026-02-27 | 2026-02-27
SUBS-168 - Handover By M.Abbas | 0.12 | 1 | 2.22 | 0.28 | 2026-02-27 | 2026-02-27
SUBS-169 - Handover By Waqar | 0.12 | 1 | 2.22 | 0.28 | 2026-02-27 | 2026-02-27
SUBS-170 - Handover To QA - Faiza | 0.28 | 2.22 | 2.22 | 0.28 | 2026-02-27 | 2026-02-27
SUBS-171 - Handover To QA - Sarmad | 0.31 | 2.5 | 2.5 | 0.31 | 2026-02-27 | 2026-02-27
SUBS-11 - SQA | 20 | 160 | 177.5 | 22.19 | 2026-03-02 | 2026-03-11
SUBS-64 - OMNI- Chat Testing | 4 | 32 | 30 | 3.75 | 2026-03-06 | 2026-03-11
SUBS-65 - Digital Log Testing | 4 | 32 | 32 | 4 | 2026-03-02 | 2026-03-05
SUBS-66 - Fintech Testing | 5 | 40 | 52 | 6.5 | 2026-03-06 | 2026-03-11
SUBS-67 - OMNI Connect Testing | 5 | 40 | 39 | 4.88 | 2026-03-02 | 2026-03-05
SUBS-68 - Product Mapping | 2 | 16 | 14 | 1.75 | 2026-02-27 | 2026-03-02
SUBS-69 - Testing by Zeeshan | 2 | 16 | 10.5 | 1.31 | 2026-03-09 | 2026-03-10
SUBS-12 - Bug-Fixing | 0 | 0 | 208.5 | 26.06 | 2026-03-02 | 2026-03-11
SUBS-175 - A Duplicate version name is being generated. | 0.25 | 2 | 2 | 0.25 | 2026-03-02 | 2026-03-02
SUBS-176 - Bad Request Error 400, Is being displayed while Entering Decimal Version Number. | 0.12 | 1 | 0.5 | 0.06 | 2026-03-02 | 2026-03-02
SUBS-177 - 400 Bad Request Error occurred, when you clicked the Create button after entering only a space in the name field. | 0 | 0 | 0 | 0 | 2026-03-02
SUBS-178 - The created version's table does not have a change summary column to verify the information the user provided during version creation. | 0 | 0 | 0 | 0
SUBS-179 - The name and Change Summary fields are unrestricted. Additionally, it gives 400 Bad Requests for long characters length . | 0 | 0 | 0 | 0
SUBS-180 - Meter Code Cannot Be Re-Added After Deletion or Used Across Different Versions | 0 | 0 | 0 | 0 | 2026-03-02
SUBS-181 - Version is getting created only with a single space in the Change Summary field.with success message. | 0 | 0 | 0 | 0 | 2026-03-02
SUBS-182 - Versions are not being approved from the front end or the back end. | 0 | 0 | 0 | 0
SUBS-183 - Bug: The system allows entering a long version number, but upon clicking the Create button, the API fails with a 400 Bad Request error. | 0 | 0 | 0 | 0 | 2026-03-03
SUBS-184 - Pagination is missing in Versions table | 0 | 0 | 0 | 0
SUBS-185 - "About" and "Support" links in footer are not redirecting. | 0 | 0 | 0 | 0
SUBS-186 - Search field is missing for Versions. | 0 | 0 | 0 | 0 | 2026-03-03
SUBS-187 - Error Message Displayed When Creating Tier, but Tier Is Created Successfully. | 0 | 0 | 0 | 0 | 2026-03-03
SUBS-188 - 400 Bad Request Error When Creating Tier with Min Value = 0 and Max Value = Infinity | 0 | 0 | 0 | 0 | 2026-03-03
SUBS-189 - Error Shown When Meter Type Is Set to 0 on Calculator Screen During Quotation Save | 0 | 0 | 0 | 0
SUBS-19 - Same name plans, versions, meter types should not be allowed. | 0.5 | 4 | 4 | 0.5 | 2026-03-02 | 2026-03-02
SUBS-190 - Multiple approval popups and API calls triggered on rapid clicks of “Send for Approval” | 0 | 0 | 0 | 0 | 2026-03-03
SUBS-191 - UI layout breaks when entering long characters in Name and Change Summary fields | 0 | 0 | 0 | 0 | 2026-03-04
SUBS-192 - Missing Validation When Name or Email Starts/Ends with Space on Calculator Screen | 0 | 0 | 0 | 0
SUBS-193 - Submit and Cancel buttons disappear in approval popup for versions with long names | 0 | 0 | 0 | 0
SUBS-194 - Support Icon Not Clickable at Bottom Right | 0 | 0 | 0 | 0
SUBS-195 - Product duplication allowed in Product Creation | 0.25 | 2 | 1 | 0.12 | 2026-03-04
SUBS-196 - Incorrect error message displayed when duplicate Product Code is entered | 0.25 | 2 | 1 | 0.12 | 2026-03-04 | 2026-03-04
SUBS-197 - Product card UI breaks & missing Controls with long Product Name/Code/Description causing toggle and button functionalities to disappear | 0 | 0 | 0 | 0 | 2026-03-04
SUBS-198 - Long Product name effects all screens: Feature, Plan,Tier, Product menu etc | 0 | 0 | 0 | 0
SUBS-199 - Focus moves outside the modal to background page elements, Keyboard focus is not trapped inside Create Product modal | 0 | 0 | 0 | 0 | 2026-03-05
SUBS-20 - Implement Minimum and Maximum Character Limit on Name Field (Calculator Screen) | 0 | 0 | 0 | 0
SUBS-200 - Need to display validation messages on all modules where validation is applied but message is missing. | 0 | 0 | 0 | 0
SUBS-201 - No search bar or search functionality is available to search for a product. | 0 | 0 | 0 | 0
SUBS-202 - “More Filters” Button Not Functional on My Quotation Screen | 0.12 | 1 | 1 | 0.12 | 2026-03-09 | 2026-03-09
SUBS-203 - The system allows Deletion of a product when its status is Active. Active products should not be deleted directly as they may be linked with other configurations (features, plans, pricing) etc. | 0 | 0 | 0 | 0
SUBS-204 - Feature name is getting duplicated. | 0 | 0 | 0 | 0
SUBS-205 - Calculator Screen Data Does Not Clear After Updating a Quotation | 0.12 | 1 | 1 | 0.12 | 2026-03-10 | 2026-03-10
SUBS-206 - No Data Displayed When Updating a Quotation | 0 | 0 | 0 | 0
SUBS-207 - Incorrect Product Selection After Page Refresh | 0 | 0 | 0 | 0
SUBS-208 - One Feature Not Deleted When Deleting Multiple Features – “Invalid Network Error” Displayed | 0.12 | 1 | 1 | 0.12 | 2026-03-10 | 2026-03-10
SUBS-209 - Meter Type Text Overlaps with Supporting Text When Editing Tier | 0 | 0 | 0 | 0
SUBS-21 - Show Validation Messages Inline (Below Fields) Instead of Top-Right Toast — Apply Across Application | 0 | 0 | 0 | 0
SUBS-210 - Tier Code Case Inconsistency and Missing Validation on Tiers Screen | 0 | 0 | 0 | 0
SUBS-211 - Export Document UI Is Disturbed | 0 | 0 | 0 | 0
SUBS-212 - Logged-In User Is Also Displayed in Share Quotation List | 0 | 0 | 0 | 0
SUBS-213 - Token is not received on email | 0 | 0 | 0 | 0
SUBS-214 - Incorrect Button/Text Label Displayed as “Send Reset Instruction” Instead of “Send Reset Token” | 0 | 0 | 0 | 0
SUBS-215 - Unable to Login with Newly Created User | 0.12 | 1 | 1 | 0.12 | 2026-03-12 | 2026-03-12
SUBS-216 - HTTP 401 Unauthorized Error Displayed When Logging Out from Plans and Tiers Screens | 0 | 0 | 0 | 0
SUBS-217 - Status Column Displayed Without Actions Column on Versions Screen | 0 | 0 | 0 | 0
SUBS-218 - Plan is getting created with 0 Base Price. | 0.01 | 0.08 | 0.08 | 0.01
SUBS-219 - Incorrect Currency Symbol Displayed on Plan Card for EUR and GBP | 0 | 0 | 0 | 0
SUBS-22 - Bugs Fixing + Improvement in the Admin Screens | 2.44 | 19.5 | 19.5 | 2.44 | 2026-03-02 | 2026-03-04
SUBS-220 - If super admin block any user the message login page should User blocked please contact admin | 0.12 | 1 | 1 | 0.12 | 2026-03-12 | 2026-03-12
SUBS-221 - Long Plan Description Breaks Plan Card Layout and Causes Misalignment | 0 | 0 | 0 | 0
SUBS-222 - Base Price Field Accepts Extremely Large Values and Shows Inconsistent Behavior (Scientific Notation / Infinity / 0) | 0 | 0 | 0 | 0
SUBS-223 - Generic Network Error Displayed When Using Same Plan Code Across Different Products | 0.12 | 1 | 1 | 0.12 | 2026-03-16 | 2026-03-16
SUBS-224 - Success Message Shown When Re-Sharing Quotation Back to Original User, but Quotation Is Not Actually Shared | 0.12 | 1 | 1 | 0.12 | 2026-03-13 | 2026-03-13
SUBS-225 - Calculator Screen Not Reset When Changing Plan | 0.12 | 1 | 1 | 0.12 | 2026-03-13 | 2026-03-13
SUBS-226 - Total Amount on Quotation Screen Is Incorrect After Editing Quotation | 0.12 | 1 | 1 | 0.12 | 2026-03-13 | 2026-03-13
SUBS-227 - Inactive Product Becomes Active Automatically After Update | 0.12 | 1 | 1 | 0.12 | 2026-03-13 | 2026-03-16
SUBS-228 - User Can Re-Share Quotation Even When Edit Permission Is Disabled | 0.38 | 3 | 3 | 0.38 | 2026-03-16 | 2026-03-16
SUBS-229 - The Plan Code field accepts lowercase characters (aa).However, based on the validation rules used for Product Code, Feature Code, only uppercase letters, numbers and underscores should be allowed.secondly Plan Code Field Accepts Invalid Special Characters | 0 | 0 | 0 | 0
SUBS-23 - Add Scrollbar to Price Summary and Subscription Configuration Sections on Calculator Screen | 0.12 | 1 | 1 | 0.12 | 2026-03-04 | 2026-03-04
SUBS-230 - Base Price Field Does Not Accept Decimal Values | 0 | 0 | 0 | 0
SUBS-231 - Plan Code Not Displayed on Plan Card After Plan Creation | 0 | 0 | 0 | 0
SUBS-232 - Edit Status Message Persists Unnecessarily on Plans Screen | 0 | 0 | 0 | 0
SUBS-233 - Preview Screen Displays Only One Feature While Multiple Active Features Exist | 0 | 0 | 0 | 0
SUBS-234 - Plan is not getting Inactive | 0.12 | 1 | 1 | 0.12 | 2026-03-17 | 2026-03-17
SUBS-235 - Invalid Pricing Format Displayed for Non-USD Currencies in Preview | 0 | 0 | 0 | 0
SUBS-24 - Duplicate Product , Pricing Config fixed | 0.25 | 2 | 2 | 0.25
SUBS-25 - Add “Created At” Column on My Quotation Screen and Correct "Last Modified" column Behavior | 0.25 | 2 | 1 | 0.12
SUBS-26 - Implement validation to restrict numeric-only values in Product Name | 0 | 0 | 0 | 0
SUBS-27 - Bug fixing | 3 | 24 | 9 | 1.12 | 2026-03-02 | 2026-03-04
SUBS-28 - DO not delete any plan or product if it is being used in Qoutations | 0.5 | 4 | 4 | 0.5 | 2026-03-05 | 2026-03-05
SUBS-29 - Setup 1 active pricing configuration per Product | 0.75 | 6 | 6 | 0.75 | 2026-03-05 | 2026-03-09
SUBS-30 - Admin Improvements + One Time Payment Implementation | 1.62 | 13 | 13 | 1.62 | 2026-03-05 | 2026-03-06
SUBS-31 - Special Characters Not Handled Correctly in Feature Name Field | 0 | 0 | 0 | 0
SUBS-32 - Meter Type UI Fix + Tiers validations | 0.19 | 1.5 | 1.5 | 0.19 | 2026-03-10 | 2026-03-10
SUBS-33 - On Save and Update Quotation, redirect the user to My Quotation page | 0.12 | 1 | 1 | 0.12 | 2026-03-10 | 2026-03-10
SUBS-34 - Created by, Updated By, Created On, Column Should be implemented in the Application. | 0 | 0 | 0 | 0
SUBS-35 - UI improvement for Plans screen | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-10 | 2026-03-10
SUBS-36 - UI improvement for tiers screen | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-10 | 2026-03-10
SUBS-37 - UI improvement for Preview screen | 0.04 | 0.33 | 0.33 | 0.04 | 2026-03-10 | 2026-03-10
SUBS-38 - UI improvement for Parameters Screen | 0.08 | 0.67 | 0.67 | 0.08 | 2026-03-10 | 2026-03-10
SUBS-39 - UI improvement for Versions screen | 0.12 | 1 | 1 | 0.12 | 2026-03-10 | 2026-03-10
SUBS-40 - UI improvement for Products and Features screen | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-10
SUBS-41 - Change “Platform Fees” Text to “Subscription Fee” on Viewing Quotation Screen | 0 | 0 | 0 | 0
SUBS-42 - Implement Search Functionality on Share Quotation Popup | 0.12 | 1 | 1 | 0.12 | 2026-03-12 | 2026-03-12
SUBS-43 - QA Reported Bugs related to Admin screens | 1.62 | 13 | 13 | 1.62 | 2026-03-10 | 2026-03-11
SUBS-44 - Project Demo | 0.25 | 2 | 2 | 0.25 | 2026-03-09 | 2026-03-09
SUBS-45 - Export Document UI Fix + Subscription fee text | 0.12 | 1 | 1 | 0.12 | 2026-03-10 | 2026-03-10
SUBS-46 - Share functionality fixed for quotations | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-10 | 2026-03-10
SUBS-47 - Bugs, from QA and findings during unit testing, fixing | 6 | 48 | 48 | 6 | 2026-03-02 | 2026-03-12
SUBS-48 - Bugs, from QA and findings during unit testing, fixing | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-12 | 2026-03-12
SUBS-49 - Product Demo Discussion + Preparation | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-13 | 2026-03-13
SUBS-50 - Update Brochures of Configured Products with Latest Information | 0 | 0 | 0 | 0
SUBS-51 - Demo Preparation | 1 | 8 | 5.5 | 0.69 | 2026-03-13 | 2026-03-13
SUBS-52 - Bug Fixing | 2 | 16 | 11 | 1.38 | 2026-03-12 | 2026-03-16
SUBS-53 - QA Reported Bugs Fix for Plans Screen | 0.31 | 2.5 | 2.5 | 0.31 | 2026-03-16 | 2026-03-16
SUBS-54 - QA Reported Bugs Fix for Tiers Screen | 0.25 | 2 | 2 | 0.25 | 2026-03-16 | 2026-03-16
SUBS-55 - Demo Prep / Data Prep / Bugs Fixing for Demo | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-13 | 2026-03-13
SUBS-56 - Add “Created At” Column on My Quotation Screen and Correct "Last Modified" column Behavior | 0.12 | 1 | 1 | 0.12 | 2026-03-05 | 2026-03-05
SUBS-57 - Discussions on KT | 0.05 | 0.42 | 0.42 | 0.05 | 2026-03-11 | 2026-03-11
SUBS-58 - Task Implementations and Bugs Fixing | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-16 | 2026-03-16
SUBS-59 - Figuring out issues for preview screen on logout | 0.25 | 2 | 2 | 0.25 | 2026-03-16 | 2026-03-16
SUBS-60 - Preview stale cache fix for runtime count | 0.38 | 3 | 3 | 0.38 | 2026-03-17
SUBS-61 - Currency issues on plans and preview page | 0.12 | 1 | 1 | 0.12 | 2026-03-17 | 2026-03-17
SUBS-62 - Fixed Issues of My Quotation and Calculator screen | 0.44 | 3.5 | 3.5 | 0.44 | 2026-03-16 | 2026-03-16
SUBS-63 - Bug fixing | 0.12 | 1 | 1 | 0.12 | 2026-03-17 | 2026-03-17
SUBS-13 - Development | 36 | 288 | 437.28 | 54.66 | 2026-01-09 | 2026-02-23
SUBS-100 - Products + Features Frontend, API Modification & Integration | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-19 | 2026-02-19
SUBS-101 - Account Activation Page UI | 0.5 | 4 | 3 | 0.38 | 2026-02-19 | 2026-02-19
SUBS-102 - Account Activation API Integration | 0.25 | 2 | 2 | 0.25 | 2026-02-25 | 2026-02-25
SUBS-103 - Super Admin - Plans API Integration | 0.81 | 6.5 | 6 | 0.75 | 2026-02-19 | 2026-02-20
SUBS-104 - Super Admin - Tiers API Integration | 0 | 0 | 0 | 0
SUBS-105 - SM Meetings | 0.5 | 4 | 4 | 0.5 | 2026-02-20 | 2026-02-20
SUBS-106 - Config Version Screen + Version Compatibility & APIs Integration | 2 | 16 | 14 | 1.75 | 2026-02-20 | 2026-02-23
SUBS-107 - User Managemnet APIs integration | 0.25 | 2 | 1.5 | 0.19 | 2026-02-16 | 2026-02-16
SUBS-108 - Plans Tiers API Integration | 0.75 | 6 | 6 | 0.75 | 2026-02-20 | 2026-02-20
SUBS-109 - Overall development team discussions / Coordinations | 0.38 | 3 | 3 | 0.38 | 2026-02-20 | 2026-02-20
SUBS-110 - Quotation Understanding + Meetings | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-20 | 2026-02-20
SUBS-111 - Qoutations API Logic revision | 1.62 | 13 | 13 | 1.62 | 2026-02-23 | 2026-02-26
SUBS-112 - Product Information Screen | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-24 | 2026-02-24
SUBS-113 - Integrated Quotation API + Calculations | 0.94 | 7.5 | 7.5 | 0.94 | 2026-02-24 | 2026-02-24
SUBS-114 - Changes with Plans and Tiers APIs | 0.62 | 5 | 4.5 | 0.56 | 2026-02-24 | 2026-02-24
SUBS-115 - Preview page diagram for Admin | 0.5 | 4 | 2 | 0.25 | 2026-02-24 | 2026-02-24
SUBS-116 - Integrated Save Quote Api + Modified Calculator | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-25 | 2026-02-25
SUBS-117 - Audit Logs integration in all modules CRUD operation | 0.62 | 5 | 5 | 0.62 | 2026-02-25 | 2026-02-26
SUBS-118 - Get Quotes for Sales Person API Integration | 0.38 | 3 | 3 | 0.38 | 2026-02-25 | 2026-02-25
SUBS-119 - Redesigned the Login Page | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-25 | 2026-02-25
SUBS-120 - Flow testing | 0.38 | 3 | 3 | 0.38 | 2026-02-26 | 2026-02-26
SUBS-121 - Bug Fix for Tiers Tab (Admin) | 0.12 | 1 | 1 | 0.12 | 2026-02-26 | 2026-02-26
SUBS-122 - Production Deployment | 0.19 | 1.5 | 1.5 | 0.19 | 2026-02-26 | 2026-02-26
SUBS-123 - Code Merging, Final Run Down Changes + Handover Session | 2 | 16 | 13 | 1.62 | 2026-02-26 | 2026-02-27
SUBS-124 - Flow Testing + Issue Fixing | 0.81 | 6.5 | 7.5 | 0.94 | 2026-02-26 | 2026-02-26
SUBS-125 - Staging Release plus bug fixing on staging | 0.62 | 5 | 5 | 0.62 | 2026-02-27 | 2026-03-02
SUBS-126 - Update Layout for Plans | 0.31 | 2.5 | 2.5 | 0.31 | 2026-03-02 | 2026-03-02
SUBS-127 - Pagination across the admin side | 0.25 | 2 | 2 | 0.25 | 2026-03-02 | 2026-03-02
SUBS-128 - Bug Fixing before QA | 0.12 | 1 | 1 | 0.12 | 2026-03-02 | 2026-03-02
SUBS-129 - Added View and Export Quotation Functionality | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-02 | 2026-03-02
SUBS-130 - Plans UI + Preview Page UI Fix | 0.38 | 3 | 3 | 0.38 | 2026-03-04 | 2026-03-04
SUBS-131 - Activate Account API Fix + Account Activation Screen fallback for staging | 0.44 | 3.5 | 3.5 | 0.44 | 2026-03-04 | 2026-03-04
SUBS-132 - Post Handover feedback Integration Discussions | 0.25 | 2 | 1.28 | 0.16 | 2026-02-27 | 2026-02-27
SUBS-133 - Account Activation Email | 0.38 | 3 | 3 | 0.38 | 2026-02-26 | 2026-02-27
SUBS-134 - Validation for Plans screen | 0.25 | 2 | 2 | 0.25 | 2026-03-05 | 2026-03-05
SUBS-135 - Edit tier functionality changed | 0.38 | 3 | 3 | 0.38 | 2026-03-05 | 2026-03-05
SUBS-136 - Preparing DL and Fintech Data for Demo | 0.19 | 1.5 | 1.5 | 0.19 | 2026-03-05 | 2026-03-05
SUBS-137 - Added Edit Quotation Funtionality +Enhance Template | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-03 | 2026-03-03
SUBS-138 - Added Pagination and Fix Issues in User and Sales Screen | 0.69 | 5.5 | 5.5 | 0.69 | 2026-03-04 | 2026-03-04
SUBS-139 - Make quotation sharable for User | 0.38 | 3 | 3 | 0.38 | 2026-03-09 | 2026-03-10
SUBS-140 - Demo with TK & Asmar + Post Demo Discussions | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-09 | 2026-03-09
SUBS-141 - POST API changes for versions | 0.44 | 3.5 | 3.5 | 0.44 | 2026-03-06 | 2026-03-06
SUBS-142 - UI adjustments for Plan and Tiers | 0.38 | 3 | 3 | 0.38 | 2026-03-06 | 2026-03-06
SUBS-143 - On submit Set all plans, products, plan teirs , pricing version, etc Status = APPROVED | 0.25 | 2 | 2 | 0.25 | 2026-03-10 | 2026-03-10
SUBS-144 - Make Quotation Invalid in case of pricing change of plan or plan tiers | 0.38 | 3 | 3 | 0.38 | 2026-03-09 | 2026-03-10
SUBS-145 - Do not allow Plan, Plan tiers, Meters to be deleted if used in Quotations | 0.19 | 1.5 | 1.5 | 0.19 | 2026-03-09 | 2026-03-10
SUBS-146 - Feature should not delete that is used in Plan | 0.12 | 1 | 1 | 0.12 | 2026-03-10 | 2026-03-10
SUBS-147 - Post Demo Discussion to Incorporate Feedback | 0.19 | 1.5 | 1.5 | 0.19 | 2026-03-09 | 2026-03-09
SUBS-148 - Added Export API+ Fixed User Update Issue+ Discussion | 0.56 | 4.5 | 4.5 | 0.56 | 2026-03-09 | 2026-03-09
SUBS-149 - Added Share Functionality + Fix Issues | 0.56 | 4.5 | 4.5 | 0.56 | 2026-03-10 | 2026-03-10
SUBS-150 - Make all newly created qoutes marked as approved | 0.12 | 1 | 1 | 0.12 | 2026-03-11 | 2026-03-11
SUBS-151 - Set quote status as Void on any change in plan and plan tier pricings | 0.25 | 2 | 2 | 0.25 | 2026-03-11 | 2026-03-11
SUBS-152 - Remove all checks in quotes that checks statuses in CRUD Operations | 0.25 | 2 | 2 | 0.25 | 2026-03-11 | 2026-03-11
SUBS-153 - Add base price of chosen plan in Quotations | 0.12 | 1 | 1 | 0.12 | 2026-03-11 | 2026-03-11
SUBS-154 - Fixed Currency in Calculator and View Quotation + User issue | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-05 | 2026-03-05
SUBS-155 - Complete flow test + Handover to QA + Post Handover Meeting | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-27 | 2026-02-27
SUBS-156 - Requirement gathering and team management | 5 | 40 | 40 | 5 | 2026-02-23 | 2026-02-27
SUBS-157 - Added Revise,Invalid Quotation Functionality | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-11 | 2026-03-11
SUBS-158 - Set ONE Default plan feature | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-12 | 2026-03-12
SUBS-159 - Email confirmation status in User Table | 0.06 | 0.5 | 0.5 | 0.06 | 2026-03-12 | 2026-03-12
SUBS-160 - Implement Resend Email in User Table | 0.19 | 1.5 | 1.5 | 0.19 | 2026-03-12 | 2026-03-12
SUBS-161 - UI Fix for Users Page | 0 | 0 | 0 | 0
SUBS-162 - Preparing data for Demo + Sanity Check with Excel Sheet | 0 | 0 | 0 | 0
SUBS-163 - Testing for demo + Fixed Some issue | 0.44 | 3.5 | 3.5 | 0.44 | 2026-03-13 | 2026-03-13
SUBS-164 - Modified Share Functionality +Revise UI + Fixed Invalid Quotation | 0.69 | 5.5 | 5.5 | 0.69 | 2026-03-12 | 2026-03-12
SUBS-70 - Frontend Setup & Requirements Discussion | 1 | 8 | 8 | 1 | 2026-01-07 | 2026-01-07
SUBS-71 - Frontend Setup | 0.25 | 2 | 2 | 0.25 | 2026-01-09 | 2026-01-09
SUBS-72 - Pages for Sales Person | 0 | 0 | 0 | 0
SUBS-73 - Backend Project Setup | 1.06 | 8.5 | 8.5 | 1.06 | 2026-01-08 | 2026-02-03
SUBS-74 - Pages for super-admin | 0.5 | 4 | 4 | 0.5 | 2026-01-22 | 2026-01-22
SUBS-75 - Static pages for sales-agent | 0.25 | 2 | 2 | 0.25 | 2026-01-21 | 2026-01-21
SUBS-76 - Static pages for approver | 0.25 | 2 | 2 | 0.25 | 2026-01-21 | 2026-01-21
SUBS-77 - Dark mode | 0.5 | 4 | 4 | 0.5 | 2026-01-23 | 2026-01-23
SUBS-78 - Azure setup + Deployment | 0.5 | 4 | 4 | 0.5 | 2026-01-23 | 2026-01-23
SUBS-79 - Designing KT To Sarmad | 0.38 | 3 | 3 | 0.38 | 2026-02-03 | 2026-02-04
SUBS-80 - Entity Framework Code first approach setup | 0.25 | 2 | 2 | 0.25 | 2026-02-06 | 2026-02-06
SUBS-81 - Initial Migration Creation | 0.38 | 3 | 3 | 0.38 | 2026-02-04 | 2026-02-04
SUBS-82 - Installing required Dependencies | 0.38 | 3 | 3 | 0.38 | 2026-02-04 | 2026-02-04
SUBS-83 - User Management API Development | 1.12 | 9 | 9 | 1.12 | 2026-02-06 | 2026-02-18
SUBS-84 - Login / Authentication APIs Development | 0.5 | 4 | 4 | 0.5 | 2026-02-09 | 2026-02-10
SUBS-85 - Pricing Configuration / PRICING_CONFIG_APPROVAL_EVENTS / Products / Features API Development | 1.25 | 10 | 9.5 | 1.19 | 2026-02-10 | 2026-02-11
SUBS-86 - Plans / Plan Tiers / PLAN_TIER_SKUS / Allowance / SKU_ALLOWANCES API Development | 1.19 | 9.5 | 9.5 | 1.19 | 2026-02-11 | 2026-02-23
SUBS-87 - QUOTES / QUOTE_EXPORTS /QUOTE_LINE_ITEMS / QUOTE_NOTES / QOUTE STATUS API Development | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-17 | 2026-02-19
SUBS-88 - AUDIT_LOGS APIs Development | 0.88 | 7 | 7 | 0.88 | 2026-02-13 | 2026-02-16
SUBS-89 - METER_TYPES API Development | 0.88 | 7 | 7 | 0.88 | 2026-02-16 | 2026-02-19
SUBS-90 - APIs Creation to view products along with plans | 0.25 | 2 | 1.5 | 0.19 | 2026-02-11 | 2026-02-11
SUBS-91 - Frontend and Backend setup | 0.62 | 5 | 5 | 0.62 | 2026-02-13 | 2026-02-13
SUBS-92 - Login Page API Integration | 0.5 | 4 | 2 | 0.25 | 2026-02-16 | 2026-02-16
SUBS-93 - Products API Integration (Super Admin) | 0.5 | 4 | 3 | 0.38 | 2026-02-17 | 2026-02-17
SUBS-94 - Reset Pwd Email & JWT Bearer Token | 0.5 | 4 | 4 | 0.5 | 2026-02-17 | 2026-02-17
SUBS-95 - Login API Integration + Authorization | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
SUBS-96 - User + Product API Integration | 1 | 8 | 8 | 1 | 2026-02-17 | 2026-02-17
SUBS-97 - Meter Types Frontend, API Modification & Integration | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
SUBS-98 - Roles, Forgot, Reset, User API Integration | 1 | 8 | 8 | 1 | 2026-02-18 | 2026-02-18
SUBS-99 - Completed User, Roles Frontend and API Integration | 0.81 | 6.5 | 6.5 | 0.81 | 2026-02-19 | 2026-02-19
SUBS-6 - Research/URS | 4 | 32 | 18 | 2.25 | 2026-01-07 | 2026-01-08
SUBS-172 - Brainstorming Structure / Tools | 1 | 8 | 8 | 1 | 2026-01-29 | 2026-02-03
SUBS-173 - Discussion on Requirements | 1 | 8 | 2 | 0.25 | 2026-01-07 | 2026-01-07
SUBS-174 - ERD Diagram Creation | 2 | 16 | 8 | 1 | 2026-01-09 | 2026-01-12
SUBS-7 - DDS | 0 | 0 | 0 | 0 | 2026-04-04 | 2026-04-17
SUBS-8 - User Manual | 5 | 40 | 0 | 0
SUBS-9 - Production Release | 6 | 48 | 24 | 3
SUBS-14 - Resource Management | 0.25 | 2 | 1.5 | 0.19 | 2026-03-17 | 2026-03-18
SUBS-15 - Azure Resource management | 0.5 | 4 | 4 | 0.5 | 2026-03-17 | 2026-03-17
SUBS-16 - Testing By Waqar | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-24
SUBS-17 - FE Deployment + Unit Testing + DB Cleanup | 1.19 | 9.5 | 9.5 | 1.19 | 2026-03-17 | 2026-03-18
SUBS-18 - Unit Testing | 0.12 | 1 | 1 | 0.12 | 2026-03-18 | 2026-03-18
WOM | 462.02 | 3696.16 | 560 | 70 | 2026-01-01 | 2026-12-31
WOM-134 - Field Service Configuration Maintenance 2026 | 250.5 | 2004 | 472 | 59 | 2026-01-01 | 2026-12-31
WOM-135 - Field Service Maintenance | 12 | 96 | 30.5 | 3.81 | 2026-01-01 | 2026-12-31
WOM-136 - Field Service Maintenance February 2026 | 1 | 8 | 8 | 1 | 2026-02-02 | 2026-02-02
WOM-148 - Field Service Maintenance March 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-06 | 2026-03-06
WOM-155 - Field Service Configuration and Testing April 2026 | 1 | 8 | 8 | 1 | 2026-04-06 | 2026-04-06
WOM-163 - Field Service Configuration and Testing May 2026 | 1 | 8 | 8 | 1 | 2026-05-11 | 2026-05-11
WOM-137 - Field Service Configuration | 12 | 96 | 30.5 | 3.81 | 2026-01-01 | 2026-12-31
WOM-138 - Field Service Configuration February 2026 | 1 | 8 | 8 | 1 | 2026-02-03 | 2026-02-03
WOM-149 - Field Service Configuration March 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-03 | 2026-03-03
WOM-156 - Field Service Configuration and Testing April 2026 | 1 | 8 | 8 | 1 | 2026-04-07 | 2026-04-07
WOM-164 - Field Service Configuration and Testing May 2026 | 1 | 8 | 8 | 1 | 2026-05-12 | 2026-05-12
WOM-139 - Field Service Configuration | 24 | 192 | 45 | 5.62 | 2026-01-01 | 2026-12-31
WOM-144 - Field Service Configuration February 2026 | 2 | 16 | 16 | 2 | 2026-02-09 | 2026-02-10
WOM-150 - Field Service Configuration March 2026 | 1.62 | 13 | 13 | 1.62 | 2026-03-09 | 2026-03-10
WOM-157 - Field Service Configuration and Testing April 2026 | 2 | 16 | 16 | 2 | 2026-04-13 | 2026-04-14
WOM-165 - Field Service Configuration and Testing May 2026 | 2 | 16 | 0 | 0 | 2026-05-14 | 2026-05-15
WOM-140 - Field Service Configuration | 12 | 96 | 22.5 | 2.81 | 2026-01-01 | 2026-12-31
WOM-145 - Field Service Configuration February 2026 | 1 | 8 | 8 | 1 | 2026-02-16 | 2026-02-16
WOM-151 - Field Service Configuration March 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-16 | 2026-03-16
WOM-158 - Field Service Configuration and Testing April 2026 | 1 | 8 | 8 | 1 | 2026-04-20 | 2026-04-20
WOM-166 - Field Service Configuration and Testing May 2026 | 1 | 8 | 0 | 0 | 2026-05-18 | 2026-05-18
WOM-141 - Field Service Configuration | 12 | 96 | 22.5 | 2.81 | 2026-01-01 | 2026-12-31
WOM-146 - Field Service Configuration February 2026 | 1 | 8 | 8 | 1 | 2026-02-17 | 2026-02-17
WOM-152 - Field Service Configuration March 2026 | 0.81 | 6.5 | 6.5 | 0.81 | 2026-03-17 | 2026-03-17
WOM-159 - CRM AMS Configuration and Testing April 2026 | 1 | 8 | 8 | 1 | 2026-04-21 | 2026-04-21
WOM-167 - Field Service Configuration and Testing May 2026 | 1 | 8 | 0 | 0 | 2026-05-19 | 2026-05-19
WOM-142 - Field Service Configuration | 24 | 192 | 45 | 5.62 | 2026-01-01 | 2026-12-31
WOM-147 - Field Service Configuration February 2026 | 1.62 | 13 | 13 | 1.62 | 2026-02-23 | 2026-02-24
WOM-154 - Field Service Configuration March 2026 | 2 | 16 | 16 | 2 | 2026-03-30 | 2026-03-31
WOM-160 - Field Service Configuration and Testing April 2026 | 2 | 16 | 16 | 2 | 2026-04-27 | 2026-04-28
WOM-168 - Field Service Configuration and Testing May 2026 | 2 | 16 | 0 | 0 | 2026-05-21 | 2026-05-22
WOM-143 - Field Service Configuration | 24 | 192 | 40 | 5 | 2026-01-01 | 2026-12-31
WOM-153 - Field Service Configuration March 2026 | 1 | 8 | 8 | 1 | 2026-03-24 | 2026-03-24
WOM-161 - Field Service Configuration and Testing April 2026 | 2 | 16 | 16 | 2 | 2026-04-02 | 2026-04-03
WOM-162 - Field Service Configuration and Testing May 2026 | 2 | 16 | 16 | 2 | 2026-05-04 | 2026-05-05
WOM-169 - Test, created from EPR Tool | 211.52 | 1692.16 | 0 | 0 | 2026-03-29 | 2026-05-15
WOM-170 - Process Design | 2 | 16 | 0 | 0 | 2026-03-29 | 2026-03-31
WOM-171 - URS | 5 | 40 | 0 | 0 | 2026-03-31 | 2026-04-04
WOM-172 - Mar effort | 1 | 8 | 0 | 0 | 2026-03-31 | 2026-03-31
WOM-173 - Apr effort | 4 | 32 | 0 | 0 | 2026-04-01 | 2026-04-04
WOM-174 - DDS | 8 | 64 | 0 | 0 | 2026-04-01 | 2026-04-18
WOM-175 - Development | 45 | 360 | 0 | 0 | 2026-04-15 | 2026-04-25
WOM-176 - Handover | 0.5 | 4 | 0 | 0 | 2026-04-30 | 2026-04-30
WOM-177 - SQA | 5 | 40 | 0 | 0 | 2026-04-30 | 2026-05-07
WOM-178 - Apr effort | 0.62 | 4.97 | 0 | 0 | 2026-04-30 | 2026-04-30
WOM-179 - May effort | 4.38 | 35.03 | 0 | 0 | 2026-05-01 | 2026-05-07
WOM-180 - Bug Fixing | 6.51 | 52.08 | 0 | 0 | 2026-04-30 | 2026-05-07
WOM-181 - Apr effort | 0.81 | 6.48 | 0 | 0 | 2026-04-30 | 2026-04-30
WOM-182 - May effort | 5.7 | 45.6 | 0 | 0 | 2026-05-01 | 2026-05-07
WOM-183 - Process QA Testing | 6 | 48 | 0 | 0 | 2026-05-01 | 2026-05-07
WOM-184 - Doc / User Manual | 11 | 88 | 0 | 0 | 2026-05-05 | 2026-05-07
WOM-185 - Regression SQA Testing | 11 | 88 | 0 | 0 | 2026-05-07 | 2026-05-08
WOM-186 - Production Release | 2 | 16 | 0 | 0 | 2026-05-08 | 2026-05-15