## Rollup
issue_link | issue_id | issue_title | issue_type | parent_story_link | parent_story_id | parent_epic_id | issue_assignee | Latest IPP Meeting | Jira IPP RMI Dates Altered | IPP Actual Date (Production Date) | IPP Remarks | IPP Actual Date Matches Jira End Date | planned start date | planned end date | actual start date | actual end date | total hours_logged
https://octopusdtlsupport.atlassian.net/browse/CRM-188 | CRM-188 | CRM Handover February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/CRM-189 | CRM-189 | CRM Handover February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5
https://octopusdtlsupport.atlassian.net/browse/CRM-190 | CRM-190 | CRM Handover March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6.5
https://octopusdtlsupport.atlassian.net/browse/CRM-191 | CRM-191 | CRM Handover March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/CRM-192 | CRM-192 | CRM Handover February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 6.5
https://octopusdtlsupport.atlassian.net/browse/CRM-193 | CRM-193 | CRM AMS Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/CRM-194 | CRM-194 | CRM AMS Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/CRM-195 | CRM-195 | CRM AMS Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 8
https://octopusdtlsupport.atlassian.net/browse/CRM-196 | CRM-196 | CRM AMS Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 8
https://octopusdtlsupport.atlassian.net/browse/CRM-197 | CRM-197 | CRM AMS Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-05-08 | 2026-05-08 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/CRM-198 | CRM-198 | CRM AMS Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-05-13 | 2026-05-13 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/CRM-199 | CRM-199 | CRM AMS Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | CRM-187 | CRM-186 | Muhammad Imran Aslam | [5 empty] | 2026-05-25 | 2026-05-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-10 | DIGITALLOG-10 | Able to change status of holiday toggle in checklist builder while respective checklist is active. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-100 | DIGITALLOG-100 | Get hierarchy nodes with their associated tags. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-102 | DIGITALLOG-102 | Get tag data for multiple tags within a date range - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-103 | DIGITALLOG-103 | UI Wrapper - Get tag data for multiple tags within a date range - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-104 | DIGITALLOG-104 | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 1 - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Arsalan Zafar Khan | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 6
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-105 | DIGITALLOG-105 | Get tag data for multiple tags within a date range - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-106 | DIGITALLOG-106 | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 2 - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Arsalan Zafar Khan | [5 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-107 | DIGITALLOG-107 | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 3 - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Arsalan Zafar Khan | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-108 | DIGITALLOG-108 | Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-11 | DIGITALLOG-11 | No character limit is applied on name field of custom weekend in holidays. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-111 | DIGITALLOG-111 | URS and DDS Formatting for Digital Log Read API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-72 | DIGITALLOG-72 | DIGITALLOG-65 | Hassan Malik | [7 empty] | 2026-01-27 | 2026-01-27 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-114 | DIGITALLOG-114 | SQL Database Development for Log Chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-07 | 2026-01-09 | 2026-01-07 | 2026-01-09 | 40
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-115 | DIGITALLOG-115 | Creating API for fetching all chats for each thread | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-116 | DIGITALLOG-116 | Creating API for fetching all threads of the specific user | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-13 | 2026-01-15 | 2026-01-13 | 2026-01-15 | 12
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-117 | DIGITALLOG-117 | Creating API for Deleting chat thread | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-01-13 | 2026-01-13 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-118 | DIGITALLOG-118 | adjusting timestamps in LLM tools to UTC time according to organization timezone dynamically from DB | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-14 | 2026-01-16 | 2026-01-14 | 2026-01-16 | 32
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-119 | DIGITALLOG-119 | SQA-Log Chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Zeeshan Sarwar | [5 empty] | 2026-01-22 | 2026-02-19 | 2026-01-29 | 2026-02-12 | 24
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-12 | DIGITALLOG-12 | Unable to save changes in organization holidays. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-120 | DIGITALLOG-120 | SQA-Read API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Zeeshan Sarwar | [5 empty] | 2026-01-22 | 2026-01-30 | 2026-01-28 | 2026-01-30 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-121 | DIGITALLOG-121 | Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-122 | DIGITALLOG-122 | Implement JPA entities for all journal-related tables following existing standards. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-123 | DIGITALLOG-123 | Wrong organization is displaying against my user ID and due to this issue all data is wrong. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-124 | DIGITALLOG-124 | Requirements analysis, UX flow finalization, and R&D for Journal module - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-125 | DIGITALLOG-125 | Design Journal Template UI - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-126 | DIGITALLOG-126 | Integrate Journal Template backend APIs and implement dynamic template persistence - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-127 | DIGITALLOG-127 | Develop Journal Builder CRUD UI using templates - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-128 | DIGITALLOG-128 | Integrate Journal Builder APIs and implement user/group assignment workflows - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-129 | DIGITALLOG-129 | Build Journal Collector – Assigned Journals listing and data-fetch APIs - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-13 | DIGITALLOG-13 | Unable to select only Sundays after selecting weekends in organization holidays. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-130 | DIGITALLOG-130 | Implement journal submission UI with validation and submit APIs (Web) - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-131 | DIGITALLOG-131 | Develop Review Journals UI and integrate journal detail & comment APIs - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-06 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-134 | DIGITALLOG-134 | Create repository interfaces and required queries for journals, entries, and filtering. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-135 | DIGITALLOG-135 | Read API is displaying other organization checklist data which is not present in my organization. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Arsalan Zafar Khan | [7 empty] | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-136 | DIGITALLOG-136 | Integerating confluence documentation in log chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-28 | 2026-02-03 | 2026-01-28 | 2026-02-03 | 32
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-137 | DIGITALLOG-137 | updating SQL and code for multi tenant database configuration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-138 | DIGITALLOG-138 | Displaying data is not user friendly. It is displaying with programming language. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-139 | DIGITALLOG-139 | Implement backend logic and APIs to manage template fields. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-14 | DIGITALLOG-14 | Able to enter and set holidays in previous months by manually entering start date in custom weekend selection. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-140 | DIGITALLOG-140 | Implement journal creation and enforce group-based access and visibility rules. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-141 | DIGITALLOG-141 | Develop services and APIs for submitting journal entries with dynamic field data. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-142 | DIGITALLOG-142 | Need to remove Template column when asking about all assets and locations in an organization. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-143 | DIGITALLOG-143 | Wrong list of templates are displaying in log chat. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-144 | DIGITALLOG-144 | Implement multi-user remarks and commenting support for journal entries. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-15 | DIGITALLOG-15 | Able to select previous date by manually entering after click on any specific date slot. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-156 | DIGITALLOG-156 | Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-157 | DIGITALLOG-157 | Get All Checklists API - Retrieves a complete list of checklists accessible to the authenticated user. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-158 | DIGITALLOG-158 | Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-159 | DIGITALLOG-159 | Implement filtering by department, section, and fields, and perform functional validation. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-16 | DIGITALLOG-16 | The application does not prompt for confirmation when removing weekends, whereas it does show a confirmation and the ‘Save Changes’ button enabled as well while adding weekends. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-160 | DIGITALLOG-160 | Get Tag Data by Date Range with Tags Filter API - Retrieves tag data for a defined date range filtered by selected tag(s). - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-161 | DIGITALLOG-161 | User Authorization for Read API (Backend) - Implements backend-level authorization to control and validate user access to Read APIs. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-162 | DIGITALLOG-162 | Get hierarchy nodes with their associated tags. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-163 | DIGITALLOG-163 | Tenant & Domain Mapping Preparation. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Arsalan Zafar Khan | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-164 | DIGITALLOG-164 | Microservices Configuration & Routing Update. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Arsalan Zafar Khan | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-165 | DIGITALLOG-165 | Get tag data for multiple tags within a date range - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-166 | DIGITALLOG-166 | Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-167 | DIGITALLOG-167 | Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-168 | DIGITALLOG-168 | Development for new tool call to add template details in chatbot | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-04 | 2026-02-09 | 2026-02-04 | 2026-02-09 | 24
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-169 | DIGITALLOG-169 | Implement JPA entities for all journal-related tables following existing standards. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-01-28 | 2026-01-28 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-17 | DIGITALLOG-17 | Upon trying to save changes in organization management, application is just loading to implement changes for multiple minutes. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-170 | DIGITALLOG-170 | Tenant & Domain Mapping Preparation. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Muhammad Abdullah | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-171 | DIGITALLOG-171 | Create repository interfaces and required queries for journals, entries, and filtering. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-01-29 | 2026-01-29 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-172 | DIGITALLOG-172 | Implement backend logic and APIs to manage template fields. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-01-30 | 2026-01-30 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-173 | DIGITALLOG-173 | Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-174 | DIGITALLOG-174 | Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-175 | DIGITALLOG-175 | Requirement Understanding & Analysis - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | nadeem ahmed | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-176 | DIGITALLOG-176 | Implement journal creation and enforce group-based access and visibility rules. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-177 | DIGITALLOG-177 | Develop services and APIs for submitting journal entries with dynamic field data. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-178 | DIGITALLOG-178 | Implement multi-user remarks and commenting support for journal entries. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-179 | DIGITALLOG-179 | Implement filtering by department, section, and fields, and perform functional validation. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | nadeem ahmed | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-18 | DIGITALLOG-18 | Able to submit a checklist on holiday. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-182 | DIGITALLOG-182 | Wrong data is displaying against active checklists in log chat. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-183 | DIGITALLOG-183 | No excel file is downloaded in log chat after waiting. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-184 | DIGITALLOG-184 | Authentication, CORS & Inter-Service Validation. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Arsalan Zafar Khan | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 6
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-185 | DIGITALLOG-185 | Wrong data is displaying against those checklists in which attachments are added. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-186 | DIGITALLOG-186 | No data is displaying against returned checklists assigned to specific user. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-187 | DIGITALLOG-187 | No data is displaying against specific checklist with a due date as well. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-188 | DIGITALLOG-188 | No values in exported file is displaying against time frames. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-189 | DIGITALLOG-189 | Unable to give answer on predictive question. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-19 | DIGITALLOG-19 | Schedule is creating against checklist 5 hours previous from current time when only frequency changes and it does not create in previous 5 hours when start time is changed. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-190 | DIGITALLOG-190 | Chat returns procedure instead of performing calculation. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-191 | DIGITALLOG-191 | No response is given against highest and lowest average against specific parameter data. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-194 | DIGITALLOG-194 | Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application, and create and verify analytical questions to ensure accurate and reliable results. 1 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Arsalan Zafar Khan | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-195 | DIGITALLOG-195 | Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application, and create and verify analytical questions to ensure accurate and reliable results. 2 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Arsalan Zafar Khan | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-197 | DIGITALLOG-197 | Tenant & Domain Mapping Preparation. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | nadeem ahmed | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-198 | DIGITALLOG-198 | SSL Post-Implementation Verification for octopusdtl Domain. -AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Arsalan Zafar Khan | [5 empty] | 2026-02-16 | 2026-02-17 | 2026-02-16 | 2026-02-17 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-199 | DIGITALLOG-199 | SQA-Journal | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Zeeshan Sarwar | [5 empty] | 2026-02-13 | 2026-02-19 | 2026-02-17 | 2026-02-20 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-20 | DIGITALLOG-20 | Manual Checklist is not activating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-200 | DIGITALLOG-200 | Assigned module access is not correct. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Abdullah | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-201 | DIGITALLOG-201 | No department or section is displaying in drop down while creating journal. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Abdullah | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-203 | DIGITALLOG-203 | Microservices Configuration & Routing Update. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | nadeem ahmed | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-204 | DIGITALLOG-204 | Authentication, CORS & Inter-Service Validation. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | nadeem ahmed | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-205 | DIGITALLOG-205 | Microservices Configuration & Routing Update. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Muhammad Abdullah | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-207 | DIGITALLOG-207 | SSL Post-Implementation Verification for octopusdtl Domain. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | nadeem ahmed | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-209 | DIGITALLOG-209 | Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | nadeem ahmed | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-21 | DIGITALLOG-21 | Performed analysis of all time entries submitted in DL across different time zones. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-210 | DIGITALLOG-210 | Authentication, CORS & Inter-Service Validation. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Muhammad Abdullah | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-211 | DIGITALLOG-211 | LogChat UI/UX Improvements & Usability Enhancement - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Muhammad Abdullah | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-212 | DIGITALLOG-212 | Fix Performance & Loading Issues in Highcharts Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Muhammad Abdullah | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-213 | DIGITALLOG-213 | Unable to activate my initial version of journal template again after creating and activating its second version. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Arsalan Zafar Khan | [7 empty] | 2026-02-19 | 2026-02-19 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-214 | DIGITALLOG-214 | Separating the data analysis and user manual part from the chatbot | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-215 | DIGITALLOG-215 | Preparing Demo questions and testing log chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-216 | DIGITALLOG-216 | Journal template is not deleting where as success message is displayed. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Muhammad Abdullah | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-217 | DIGITALLOG-217 | SSL Post-Implementation Verification for octopusdtl Domain. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | Muhammad Abdullah | [5 empty] | 2026-02-16 | 2026-02-17 | 2026-02-16 | 2026-02-17 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-224 | DIGITALLOG-224 | Error display when activating a previous version of journal template. It only displays when performing this activity first time. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | Arsalan Zafar Khan | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-226 | DIGITALLOG-226 | LogChat Demo Internal And Bug RCAs. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-225 | DIGITALLOG-225 | DIGITALLOG-218 | Arsalan Zafar Khan | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-227 | DIGITALLOG-227 | Production Deployment & Post-Deployment Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-153 | DIGITALLOG-153 | DIGITALLOG-150 | Arsalan Zafar Khan | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2.75
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-229 | DIGITALLOG-229 | Production Deployment & Post-Deployment Verification. MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-153 | DIGITALLOG-153 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 3.25
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-230 | DIGITALLOG-230 | Production Deployment & Post-Deployment Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-149 | DIGITALLOG-149 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2.75
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-231 | DIGITALLOG-231 | Production Deployment & Post-Deployment Verification. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-149 | DIGITALLOG-149 | DIGITALLOG-146 | nadeem ahmed | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-232 | DIGITALLOG-232 | Production Deployment & Post-Deployment Verification. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-149 | DIGITALLOG-149 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 3.25
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-233 | DIGITALLOG-233 | Make improvements as well as fix reported issues by team member During testing of Journals Module after completion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | DIGITALLOG-69 | DIGITALLOG-150 | Muhammad Abdullah | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-236 | DIGITALLOG-236 | Research & Validation: Confirm Default Reports generation capability through LogChat 1/3 - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-235 | DIGITALLOG-235 | DIGITALLOG-234 | nadeem ahmed | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-238 | DIGITALLOG-238 | Checklists are not triggered (day was specified as holiday) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | nadeem ahmed | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-269 | DIGITALLOG-269 | Retraining of LLM to resolve issues related to logchat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | DIGITALLOG-113 | DIGITALLOG-65 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-18 | 2026-02-20 | 2026-02-18 | 2026-02-20 | 21
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-275 | DIGITALLOG-275 | Implement Journal module bottom tabs (My Journal(s) & Review Journal(s)) with icons, navigation routing, and base screen layouts. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-276 | DIGITALLOG-276 | Integrate backend API to fetch My Journal(s) list, implement FlatList with pagination/loading states and Redux/offline state handling. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-277 | DIGITALLOG-277 | Implement Journal Detail screen, integrate API to load journal template version fields dynamically, render dynamic form components. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-278 | DIGITALLOG-278 | Implement form state management, validation logic, input handling (text, dropdowns, date, etc.), and attachment picker integration. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-279 | DIGITALLOG-279 | Implement journal submission API integration, attachment upload handling (online), success flow navigation back to My Journal(s), error handling. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-280 | DIGITALLOG-280 | Implement offline support for My Journal(s) (SQLite schema, save draft entries, attachment queue, sync queue structure). - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-281 | DIGITALLOG-281 | Implement Review Journal(s) base UI with advanced filters (Department, Section, Users, Date Range, All Journals dropdown). - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-282 | DIGITALLOG-282 | Integrate APIs for Journals dropdown, load selected Journal versions dynamically, and render dynamic filterable template fields. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-283 | DIGITALLOG-283 | Implement advancedFilter API integration to fetch review entries, implement default loading of all entries with filter badges (Open, Closed, Attachments). - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-284 | DIGITALLOG-284 | Implement Review Detail screen to load filled entries, integrate remarks APIs (view, add, update, delete own remarks). - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-286 | DIGITALLOG-286 | Implement Close/Reopen journal entry functionality with remarks, integrate APIs, update list state and badge counts dynamically. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-287 | DIGITALLOG-287 | Implement full offline support for Review module (cache entries, remarks, attachments, close/reopen queue), sync mechanism, testing, performance optimization, and bug fixing. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-288 | DIGITALLOG-288 | Design lightweight mobile-specific REST endpoints and DTOs to minimize payload size and improve performance. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-289 | DIGITALLOG-289 | Implement APIs to fetch lightweight journals and journal entries for mobile listing screens. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-290 | DIGITALLOG-290 | Extend the JournalEntry entity to include metadata timestamps for attachments and remarks and update business logic to auto-maintain them. -AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-291 | DIGITALLOG-291 | Develop a bulk API to retrieve attachments and remarks metadata for multiple journal entries in a single request. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-292 | DIGITALLOG-292 | Implement a delta API to return journal entries modified after a given last sync timestamp. -AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-293 | DIGITALLOG-293 | Enforce role-based and organization-level access validation for all mobile journal and entry APIs. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-294 | DIGITALLOG-294 | Implement structured audit logging for mobile-based journal entry creation operations. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-299 | DIGITALLOG-299 | Integrating Inactive logs and Latest log Report | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-300 | DIGITALLOG-300 | Integrating capability to fetch tags based on Units and field type | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-301 | DIGITALLOG-301 | Research & Validation: Confirm Default Reports generation capability through LogChat 2/3 - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-235 | DIGITALLOG-235 | DIGITALLOG-234 | nadeem ahmed | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-303 | DIGITALLOG-303 | Writing DDS (Document Design Specification) for Journal Mobile App - 1 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-271 | DIGITALLOG-271 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-304 | DIGITALLOG-304 | Writing DDS (Document Design Specification) for Journal Mobile App - 2 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-271 | DIGITALLOG-271 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-305 | DIGITALLOG-305 | Writing and review of DDS (Document Design Specification) for Journal Mobile App - 3 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-271 | DIGITALLOG-271 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-306 | DIGITALLOG-306 | Develop a bulk API to retrieve attachments and remarks metadata for multiple journal entries in a single request. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-307 | DIGITALLOG-307 | Integrating capability to fetch the logs and tags/items with remarks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | 13
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-308 | DIGITALLOG-308 | Update database schema to add holiday start_datetime and end_datetime fields with proper indexing and non-overlapping range constraints per organization. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 5.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-309 | DIGITALLOG-309 | Modify Holiday JPA entity, DTOs, and repository layer to support CRUD operations for holiday date-time ranges. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-310 | DIGITALLOG-310 | Implement REST APIs to create and update holiday ranges with validation (start < end, no overlapping holidays, timezone normalization to UTC). - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-311 | DIGITALLOG-311 | Develop API to retrieve holidays with filtering by date range and organization, including pagination support. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-312 | DIGITALLOG-312 | Enhance checklist scheduler service logic to check current execution time against configured holiday ranges and skip triggering if within range. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-313 | DIGITALLOG-313 | Perform developer testing to validate holiday CRUD operations, overlapping range validations, and scheduler suppression behaviour during defined holiday periods. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-314 | DIGITALLOG-314 | Update scheduler logging and monitoring to record skipped executions due to holidays, finalize Swagger documentation, and deploy changes to development for QA testing. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-315 | DIGITALLOG-315 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-240 | DIGITALLOG-240 | DIGITALLOG-219 | Zeeshan Sarwar | [5 empty] | 2026-03-20 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 10
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-316 | DIGITALLOG-316 | Working XY Plot and multi-line graph in chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | 13
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-318 | DIGITALLOG-318 | Digital Log - Product/Platform Orientation Training | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | DIGITALLOG-317 | DIGITALLOG-218 | Arsalan Zafar Khan | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-320 | DIGITALLOG-320 | Modify Holiday JPA entity, DTOs, and repository layer to support CRUD operations for holiday date-time ranges. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | nadeem ahmed | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-321 | DIGITALLOG-321 | Implement a delta API to return journal entries modified after a given last sync timestamp. -NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | DIGITALLOG-239 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-322 | DIGITALLOG-322 | SSL Post-Implementation Verification for octopusdtl Domain - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | DIGITALLOG-70 | DIGITALLOG-154 | nadeem ahmed | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-323 | DIGITALLOG-323 | Read API is displaying other organization checklist data which is not present in my organization. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | DIGITALLOG-71 | DIGITALLOG-65 | nadeem ahmed | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-324 | DIGITALLOG-324 | LogChat testing and evaluation - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-225 | DIGITALLOG-225 | DIGITALLOG-218 | nadeem ahmed | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-325 | DIGITALLOG-325 | Implement REST APIs to create and update holiday ranges with validation (start < end, no overlapping holidays, timezone normalization to UTC). - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | nadeem ahmed | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-326 | DIGITALLOG-326 | Develop API to retrieve holidays with filtering by date range and organization - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | nadeem ahmed | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-327 | DIGITALLOG-327 | Upcoming checklist Activities report | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-09 | 19.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-328 | DIGITALLOG-328 | Add start and end time selection, select and unselect Saturdays as well as other improvements done for holiday module - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | Muhammad Abdullah | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-329 | DIGITALLOG-329 | Digital Log - Product/Platform Orientation Training March 11 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | DIGITALLOG-317 | DIGITALLOG-218 | Arsalan Zafar Khan | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-330 | DIGITALLOG-330 | Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-331 | DIGITALLOG-331 | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-332 | DIGITALLOG-332 | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-333 | DIGITALLOG-333 | Develop and test APIs for retrieving journal entry field data and remarks data by entry IDs. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2026-03-25 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-334 | DIGITALLOG-334 | UI Wrapper - Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-335 | DIGITALLOG-335 | UI Wrapper - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-336 | DIGITALLOG-336 | UI-Wrapper - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. Develop and test APIs for retrieving journal entry field data and remarks data by entry IDs. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-337 | DIGITALLOG-337 | Testing and Retraining of LLM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-18 | 19.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-338 | DIGITALLOG-338 | Integrating comparison of tags reports | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-339 | DIGITALLOG-339 | Research: Testing Omnichat with Postgress SQL | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-235 | DIGITALLOG-235 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-10 | 2026-03-12 | 2026-03-10 | 2026-03-12 | 19.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-340 | DIGITALLOG-340 | Email Notifications should be sending actual domain url | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | Arsalan Zafar Khan | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-341 | DIGITALLOG-341 | Testing by Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-244 | DIGITALLOG-244 | DIGITALLOG-220 | Zeeshan Sarwar | [5 empty] | 2026-03-25 | 2026-03-27 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-342 | DIGITALLOG-342 | Able to select previous time in current day, where as it should be restricted to create a holiday in past dates or past time in current date. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-298 | DIGITALLOG-298 | DIGITALLOG-220 | Muhammad Abdullah | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-343 | DIGITALLOG-343 | Read API is only displaying active journals where as it should also display pending journals. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | DIGITALLOG-297 | DIGITALLOG-219 | Arsalan Zafar Khan | [7 empty] | 2026-03-26 | 2026-03-26 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-344 | DIGITALLOG-344 | Mobile App Octopusdtl Domain Switching Issue RCA - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | DIGITALLOG-297 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-27 | 15
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-345 | DIGITALLOG-345 | Allow Same Section Name With Different Department | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | Arsalan Zafar Khan | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-346 | DIGITALLOG-346 | Input field in remarks option is not displaying properly to enter text in it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | DIGITALLOG-297 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-347 | DIGITALLOG-347 | Count on review tab of journal is not displaying when opening application. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | DIGITALLOG-297 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-348 | DIGITALLOG-348 | Open and closed journal status entries are not displaying with its previous and current values on web application. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | DIGITALLOG-297 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-349 | DIGITALLOG-349 | Digital Log: Inhouse Training Session - 2 - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | DIGITALLOG-317 | DIGITALLOG-218 | Arsalan Zafar Khan | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-350 | DIGITALLOG-350 | Digital Log: Inhouse Training Session - 2 - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | DIGITALLOG-317 | DIGITALLOG-218 | nadeem ahmed | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-351 | DIGITALLOG-351 | Perform developer testing to validate holiday CRUD operations, overlapping range validations, and scheduler suppression behaviour during defined holiday periods. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | nadeem ahmed | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-352 | DIGITALLOG-352 | Update scheduler logging and monitoring to record skipped executions due to holidays, finalize Swagger documentation, and deploy changes to development for QA testing. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | nadeem ahmed | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-353 | DIGITALLOG-353 | Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-354 | DIGITALLOG-354 | Enhance checklist scheduler service logic to check current execution time against configured holiday ranges and skip triggering if within range. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | DIGITALLOG-243 | DIGITALLOG-220 | nadeem ahmed | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-355 | DIGITALLOG-355 | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-03-16 | 2026-03-17 | 2026-03-16 | 2026-03-17 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-356 | DIGITALLOG-356 | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | DIGITALLOG-270 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-357 | DIGITALLOG-357 | Email Notifications should be sending actual domain url & Allow Same Section Name With Different Department - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | nadeem ahmed | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 7
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-358 | DIGITALLOG-358 | Mobile App Octopusdtl Domain Switching Issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | DIGITALLOG-297 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-359 | DIGITALLOG-359 | Mobile App Octopusdtl Domain Switching Issue RCA - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | DIGITALLOG-297 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-24 | 2026-03-26 | 2026-03-24 | 2026-03-26 | 22.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-360 | DIGITALLOG-360 | Creation of DDS for Holidays Management Module | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-273 | DIGITALLOG-273 | DIGITALLOG-220 | nadeem ahmed | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-361 | DIGITALLOG-361 | Production Deployment & Post-Deployment Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | DIGITALLOG-242 | DIGITALLOG-219 | Arsalan Zafar Khan | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-362 | DIGITALLOG-362 | Production Deployment & Post-Deployment Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-246 | DIGITALLOG-246 | DIGITALLOG-220 | Arsalan Zafar Khan | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-363 | DIGITALLOG-363 | Production Deployment & Post-Deployment Verification. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | DIGITALLOG-242 | DIGITALLOG-219 | Muhammad Abdullah | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-364 | DIGITALLOG-364 | Production Deployment & Post-Deployment Verification. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-246 | DIGITALLOG-246 | DIGITALLOG-220 | Muhammad Abdullah | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-365 | DIGITALLOG-365 | Production Deployment & Post-Deployment Verification. - NA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | DIGITALLOG-242 | DIGITALLOG-219 | nadeem ahmed | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-379 | DIGITALLOG-379 | Training Session ¦ Power of Mindset - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-378 | DIGITALLOG-378 | DIGITALLOG-218 | Arsalan Zafar Khan | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-380 | DIGITALLOG-380 | Allow Same Section Name With Different Department - Hot Fix Production Release and Post Production Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | Arsalan Zafar Khan | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-381 | DIGITALLOG-381 | Training Session ¦ Power of Mindset - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-378 | DIGITALLOG-378 | DIGITALLOG-218 | Muhammad Abdullah | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-382 | DIGITALLOG-382 | Allow Same Section Name With Different Department - Hot Fix Production Release and Post Production Verification. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | Muhammad Abdullah | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-387 | DIGITALLOG-387 | Design database schema changes to store return and re-approval parameter values along with comments history and traceability metadata. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-388 | DIGITALLOG-388 | Implement backend entities, DTOs, and repository layer to support storing and retrieving return and re-approval data. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-389 | DIGITALLOG-389 | Develop APIs to capture return actions with parameter values and user comments, including audit fields (user, timestamp). - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-390 | DIGITALLOG-390 | Implement APIs for re-approval workflow capturing updated parameter values and associated comments with version tracking. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-391 | DIGITALLOG-391 | Build service-layer logic to maintain full traceability history (who, when, what changes) for return and re-approval actions. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-392 | DIGITALLOG-392 | Perform developer testing to validate end-to-end traceability, data consistency, and audit history retrieval across return and re-approval scenarios. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 6
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-393 | DIGITALLOG-393 | Announcement Email Compilation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | DIGITALLOG-242 | DIGITALLOG-219 | Hassan Malik | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-04-01 | 2026-04-01 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-395 | DIGITALLOG-395 | Analyze UI requirements for Return/Re-Approval old vs new param value traceability across web and mobile applications. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-396 | DIGITALLOG-396 | Identify Return/Re-Approval fields required for change comparison in web and mobile UI. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-397 | DIGITALLOG-397 | Implement changed-field comparison logic for Return/Re-Approval params in web and mobile applications. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-398 | DIGITALLOG-398 | Build traceability UI section to display old vs new parameter values in web and mobile applications. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-399 | DIGITALLOG-399 | Render comments with corresponding Return/Re-Approval param changes in web and mobile UI. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-400 | DIGITALLOG-400 | Validate web and mobile UI rendering for Return/Re-Approval value comparison and comments traceability. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | DIGITALLOG-247 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-401 | DIGITALLOG-401 | Update the pie chart logic in logchat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-402 | DIGITALLOG-402 | Adding statistical analysis in logchat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-27 | 24
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-403 | DIGITALLOG-403 | Creating dataset (checklists) and testing on production | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | DIGITALLOG-272 | DIGITALLOG-234 | Muhammad Zeeshan Aslam | [5 empty] | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-404 | DIGITALLOG-404 | User Manual | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-245 | DIGITALLOG-245 | DIGITALLOG-220 | Hassan Malik | [5 empty] | 2026-03-25 | 2026-03-27 | 2026-04-02 | 2026-04-02 | 1
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-405 | DIGITALLOG-405 | Design and implement backend data model and APIs to support digital signature requests, signer details, and document status tracking. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | DIGITALLOG-255 | DIGITALLOG-223 | Arsalan Zafar Khan | [5 empty] | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-406 | DIGITALLOG-406 | Update existing submit and approver endpoints to incorporate digital signature validation, capture signer details, and persist signature metadata with audit trail. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | DIGITALLOG-255 | DIGITALLOG-223 | Arsalan Zafar Khan | [5 empty] | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-13 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-407 | DIGITALLOG-407 | Perform developer testing and integrate digital signature workflow with checklist modules ensuring security, validation, and end-to-end traceability. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | DIGITALLOG-255 | DIGITALLOG-223 | Arsalan Zafar Khan | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-408 | DIGITALLOG-408 | Handover to QA - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-373 | DIGITALLOG-373 | DIGITALLOG-223 | Arsalan Zafar Khan | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-409 | DIGITALLOG-409 | Handover to QA - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-367 | DIGITALLOG-367 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-410 | DIGITALLOG-410 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-248 | DIGITALLOG-248 | DIGITALLOG-221 | kamran khalid | [5 empty] | 2026-04-13 |  | 2026-04-13 | 2026-04-29 | 44
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-414 | DIGITALLOG-414 | Handover session Digital Log | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-367 | DIGITALLOG-367 | DIGITALLOG-221 | kamran khalid | [7 empty] | 2026-04-09 | 2026-04-09 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-416 | DIGITALLOG-416 | Design database schema and backend models to support user-defined checklist scheduling with configurable execution times and frequency - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-417 | DIGITALLOG-417 | Implement APIs to create and update checklist schedules with user-specified time, timezone handling, and validation rules - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-418 | DIGITALLOG-418 | Develop API to retrieve checklist schedules with filtering and organization-level configuration support - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-419 | DIGITALLOG-419 | Enhance scheduler service to trigger checklists based on user-defined times and integrate with existing scheduling framework - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-420 | DIGITALLOG-420 | Perform developer testing to validate scheduling accuracy, timezone consistency, and edge cases (missed triggers, overlaps, holiday conflicts) - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 13.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-421 | DIGITALLOG-421 | Implement e-signature enablement on Web including checklist builder toggle, list filters/badges, submission & review modals with signature capture, and signature display via API. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | DIGITALLOG-255 | DIGITALLOG-223 | Muhammad Abdullah | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 9.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-422 | DIGITALLOG-422 | Implement e-signature functionality on Mobile (React Native) including checklist filters/badges, submission & review modals with signature capture, and signature display via API. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | DIGITALLOG-255 | DIGITALLOG-223 | Muhammad Abdullah | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 11
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-423 | DIGITALLOG-423 | Integrate e-signature APIs across Web and Mobile, ensuring payload handling, signature retrieval, and visualization in checklist and data modules. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | DIGITALLOG-255 | DIGITALLOG-223 | Muhammad Abdullah | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-424 | DIGITALLOG-424 | Handover to QA - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-367 | DIGITALLOG-367 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-425 | DIGITALLOG-425 | Code to fetch the Confluence File and store in vector store | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-260 | DIGITALLOG-260 | DIGITALLOG-259 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 24
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-426 | DIGITALLOG-426 | Integrate User manual/confluence file vector store in the Log chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-260 | DIGITALLOG-260 | DIGITALLOG-259 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-07 | 16
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-427 | DIGITALLOG-427 | Investigate and resolve SSL compatibility issues affecting backward compatibility on older Android mobile app versions. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | Arsalan Zafar Khan | [5 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-428 | DIGITALLOG-428 | Investigate and resolve SSL compatibility issues affecting backward compatibility on older Android mobile app versions. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | Muhammad Abdullah | [5 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-429 | DIGITALLOG-429 | Refactor checklist builder UI by replacing Scheduled/Non-Scheduled checkboxes with a dropdown (Scheduled, Non-Scheduled, Time-based) and default to Non-Scheduled. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Muhammad Abdullah | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 7
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-430 | DIGITALLOG-430 | Implement dynamic UI behavior to show/hide scheduling controls based on selected dropdown option, including new time-based inputs. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Muhammad Abdullah | [5 empty] | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-431 | DIGITALLOG-431 | Update scheduling API payload to support the new Time-based option and ensure proper data handling for all scheduling types. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | DIGITALLOG-251 | DIGITALLOG-222 | Muhammad Abdullah | [5 empty] | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-432 | DIGITALLOG-432 | Checklist Name is appearing instead of Approver Name | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | kamran khalid | [7 empty] | 2026-04-24 | 2026-04-24 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-433 | DIGITALLOG-433 | HEADER NOT RESPONSIVE | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 1.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-434 | DIGITALLOG-434 | Refresh button is not loading latest data into the list | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-435 | DIGITALLOG-435 | Permission issue for my user as i installed the new version of the mobile app | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-437 | DIGITALLOG-437 | Handover to QA - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-368 | DIGITALLOG-368 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-438 | DIGITALLOG-438 | Newly created checklists do not appear at the top, and there is no filter available to sort by creation time. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-439 | DIGITALLOG-439 | Time-based scheduled checklist activation fails on the first attempt. However, after changing the checklist type from "Time Based" to "Scheduled", the activation succeeds, including validation through developer testing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 4
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-440 | DIGITALLOG-440 | Time-based checklist is not triggering according to the 24-hour format, even after multiple screen refresh attempts. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Arsalan Zafar Khan | [7 empty] | 2026-04-27 | 2026-04-27 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-441 | DIGITALLOG-441 | E-Signature field should be Mandatory on web and mobile | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Muhammad Abdullah | [7 empty] | 2026-04-27 | 2026-04-27 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-442 | DIGITALLOG-442 | Checklist gets activated when Start Time and End Time are identical (zero-duration window not validated) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | DIGITALLOG-376 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-46 | DIGITALLOG-46 | Correct list of checklist are not displaying when they are returned in bulk through mobile app. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-26 | DIGITALLOG-26 | DIGITALLOG-27 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-466 | DIGITALLOG-466 | Update checklist scheduling logic to ensure triggers occur only after the configured checklist start time, including validation and developer testing for edge cases - AZ | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-370 | DIGITALLOG-370 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 7.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-467 | DIGITALLOG-467 | Fix checklist scheduling logic to preserve original start time and prevent schedule shifts during checklist deactivation and reactivation, including validation through developer testing - AZ | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-370 | DIGITALLOG-370 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 6
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-468 | DIGITALLOG-468 | Production Deployment & Post-Deployment Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-250 | DIGITALLOG-250 | DIGITALLOG-221 | Arsalan Zafar Khan | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-469 | DIGITALLOG-469 | Production Deployment & Post-Deployment Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-254 | DIGITALLOG-254 | DIGITALLOG-222 | Arsalan Zafar Khan | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-47 | DIGITALLOG-47 | Date format parameter value is displaying in data visualizer with some random long integer value. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-32 | DIGITALLOG-32 | DIGITALLOG-27 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-470 | DIGITALLOG-470 | Production Deployment & Post-Deployment Verification. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-258 | DIGITALLOG-258 | DIGITALLOG-223 | Arsalan Zafar Khan | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-471 | DIGITALLOG-471 | Production Deployment & Post-Deployment Verification. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-258 | DIGITALLOG-258 | DIGITALLOG-223 | Muhammad Abdullah | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-472 | DIGITALLOG-472 | Production Deployment & Post-Deployment Verification. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-254 | DIGITALLOG-254 | DIGITALLOG-222 | Muhammad Abdullah | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-473 | DIGITALLOG-473 | Production Deployment & Post-Deployment Verification. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-250 | DIGITALLOG-250 | DIGITALLOG-221 | Muhammad Abdullah | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-474 | DIGITALLOG-474 | Handover to QA - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-368 | DIGITALLOG-368 | DIGITALLOG-222 | Muhammad Abdullah | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-478 | DIGITALLOG-478 | Bug fixing, communication with clients/customers and meeting within team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | DIGITALLOG-237 | DIGITALLOG-196 | nadeem ahmed | [7 empty] | 2026-05-05 | 2026-05-05 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-49 | DIGITALLOG-49 | Irrelevant information is displaying in tabs of count present on starting of activity stats page. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-50 | DIGITALLOG-50 | Backend programming language is displaying against update activity of template structure. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-51 | DIGITALLOG-51 | Format of date and time in any activity update is not correct. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-52 | DIGITALLOG-52 | Module name that is created, updated or deleted should display first and then its entity should display in brackets while viewing its details. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-53 | DIGITALLOG-53 | Department name is not displaying correct after creating a section. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-54 | DIGITALLOG-54 | Checklist update activity is automatically triggered where as only group is updated. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-55 | DIGITALLOG-55 | Dept and section for data visualization checkbox is not selected when clicking on select all option while creating or updating role. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-56 | DIGITALLOG-56 | Role ID and other details are displaying while viewing user create activity. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-57 | DIGITALLOG-57 | Holiday declared in organizational management is not displaying with its date in activity stats screen. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-58 | DIGITALLOG-58 | Activity detail done in hierarchy builder is not displaying where as its count is displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-59 | DIGITALLOG-59 | Activity of parameter creation in asset builder is displaying as creating it in template. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Arsalan Zafar Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-60 | DIGITALLOG-60 | Required toggle activate/deactivate activity is with only type change description where as input type is not changed. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-61 | DIGITALLOG-61 | Location or asset is not displaying for selection again while configuring checklist after it is removed one time. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-62 | DIGITALLOG-62 | Start and end date as well as frequency changings are not displaying in checklist details on activity stats screen. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | DIGITALLOG-38 | DIGITALLOG-35 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-7 | DIGITALLOG-7 | Confluence Migration - Web App | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-6 | DIGITALLOG-6 | DIGITALLOG-1 | Maria Sharafat | [5 empty] | 2025-10-01 | 2025-10-03 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-8 | DIGITALLOG-8 | Confluence - Mobile App | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-6 | DIGITALLOG-6 | DIGITALLOG-1 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-82 | DIGITALLOG-82 | Get All Checklists API - Retrieves a complete list of checklists accessible to the authenticated user. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-83 | DIGITALLOG-83 | Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-84 | DIGITALLOG-84 | Get Tag Data by Date Range API - Returns historical tag data within a specified start and end date range. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-85 | DIGITALLOG-85 | Get Tag Data by Date Range with Tags Filter API - Retrieves tag data for a defined date range filtered by selected tag(s). - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-86 | DIGITALLOG-86 | User Authorization for Read API (Backend) - Implements backend-level authorization to control and validate user access to Read APIs. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Arsalan Zafar Khan | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-87 | DIGITALLOG-87 | User Authorization for Read API (Frontend) - Enforces frontend access control to expose Read API features based on user roles and permissions. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-88 | DIGITALLOG-88 | UI Wrapper - Get All Checklists – Implement frontend wrapper/service to securely call and display data from the Get All Checklists API via public domain. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-89 | DIGITALLOG-89 | UI Wrapper - Get Tags for Multiple Checklists – Develop frontend wrapper to invoke the API and present tags for selected multiple checklists. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-9 | DIGITALLOG-9 | No option is selected by default when organizational management is selected in creating or editing a role. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | DIGITALLOG-2 | DIGITALLOG-1 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-90 | DIGITALLOG-90 | UI Wrapper - Get Tag Data by Date Range – Create UI wrapper to fetch and visualize tag data based on user-selected date range. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-91 | DIGITALLOG-91 | UI Wrapper - Get Tag Data by Date Range with Tags Filter – Implement frontend wrapper to call the API with date range and tag filters and render filtered results. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-92 | DIGITALLOG-92 | Requirement Understanding & Analysis - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Arsalan Zafar Khan | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-93 | DIGITALLOG-93 | UI/UX Design & Architecture - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Muhammad Abdullah | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-94 | DIGITALLOG-94 | Core UI Development - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Muhammad Abdullah | [5 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-95 | DIGITALLOG-95 | Integration of Log Chat Apis - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Muhammad Abdullah | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-96 | DIGITALLOG-96 | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Muhammad Abdullah | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-97 | DIGITALLOG-97 | Creation of read-only users to securely access client databases without modification privileges. - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Arsalan Zafar Khan | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-98 | DIGITALLOG-98 | UI Wrapper - Get All Tags Hierarchy – Implement frontend wrapper/service to securely call and display data from the Get Hierarchy Tags API via public domain. - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | DIGITALLOG-68 | DIGITALLOG-146 | Muhammad Abdullah | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-99 | DIGITALLOG-99 | Requirement Understanding & Analysis - MA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | DIGITALLOG-66 | DIGITALLOG-192 | Muhammad Abdullah | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-100 | FF-100 | The Filter on the Transaction page is not working correctly as i have applied filter the data for "PUMP_4" but its showing data of other pumps too | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-101 | FF-101 | ON the Nozzle usage page in the table the customer name is showing instead of site in the column "site name" | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-102 | FF-102 | The filter functionality is not consistent across pages. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-103 | FF-103 | The purpose of the filter on the Loss Gain Chart page is unclear, as it’s currently not functioning. The filter appears inactive, while the Loss Gain Chart itself is working correctly and displaying data. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-104 | FF-104 | 1. Remove datetime range control 2. Show respective tank name 3. Control to toggle view between tank / product wise display in Stock Level pages Pages | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-105 | FF-105 | Floating value display on column and show units as well like PKR, Ltr etc 1. Volume, 2. Money, and 3. PPU in Transaction page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-106 | FF-106 | Icon needs to be replaced with appropriate icon in "per week target", "Daily average target" cards, | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-107 | FF-107 | Mock targets are being displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-108 | FF-108 | FuelChat - DE API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-97 | FF-97 | FF-16 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-109 | FF-109 | Manual Tank Delivery Recon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-17 | FF-17 | FF-16 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-110 | FF-110 | On the Loss Gain Chart page the tank level filter is not working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [5 empty] | 2025-10-16 | 2025-10-17 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-111 | FF-111 | User Manual | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-127 | FF-127 | Dashboard> Hi Super and Excellium colors do not match between the tank display and the graph. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-128 | FF-128 | Dashboard> No character limit is applied on Username/Email and Password fields across the application. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2025-12-02 | 2025-12-02 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-129 | FF-129 | Expire time and Resend code button is not showing on OTP popup | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2025-12-02 | 2025-12-03 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-130 | FF-130 | OTP is not expired even after 3 minutes | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2025-12-02 | 2025-12-03 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-131 | FF-131 | Spelling mistake "Occurred" should be, instead of "Occured". | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-132 | FF-132 | Dashboard> Update password validation message and add view/hide icon on Reset Password screen wherever there are password fields | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-133 | FF-133 | Dashboard> Current Password field is missing on the Reset password screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-134 | FF-134 | Portal Forgot Password: Current password is getting saved as in New Password and Confirm Password | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-135 | FF-135 | User is redirected to Reset Password page after clicking the Activate Account button | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-136 | FF-136 | When a user access the forgot password feature of the portal,they are landed on a page where their password is changed for the dashboard.After logging in, the dashboard is accessible,but not the portal.“Signing up,also changing the password for both. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-137 | FF-137 | Replace Site ID with Site Name across the application and add Product Name with Tank Name on the Alarms screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-138 | FF-138 | Remove "Resolved" option from Status dropdown on Alarms screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-139 | FF-139 | The staging dashboard is not loading correctly. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-140 | FF-140 | Unable to Configure a site Kindly check, Blocker for us | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-142 | FF-142 | PPT for management for Current usage of azure | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-141 | FF-141 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-143 | FF-143 | Transactions: While selecting Pum_16 , Its allowing user to select Pump_1,2,3 with nozzle and so on. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-144 | FF-144 | User is Unable to change a Customer, after assigning a custom role, FOR EVERY SCREEN OF Dashboard. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [5 empty] | 2025-12-09 | 2025-12-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-145 | FF-145 | Non Existing Role : "Submit Portal" | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-146 | FF-146 | While View Permissions are off and Create Permission is on, It is displaying all menu options of dashboard. Same For All Edit Permissions as on view permissions | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [5 empty] | 2025-12-09 | 2025-12-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-147 | FF-147 | Inactive Customer is being available or selected which we didn't assigned to this user. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-148 | FF-148 | ‘Select Role’ Field Is Not Marked as Required on User Create/Update | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-149 | FF-149 | Old Logo Is Displaying on System Emails (Account Activation, OTP Verification, Forgot Password) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-15 | FF-15 | SP modification (Bug reported) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-10 | FF-10 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-150 | FF-150 | Critical : Day End Sales Summary on Transactions. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [5 empty] | 2025-12-11 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-151 | FF-151 | Configuration Portal Updates | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-118 | FF-118 | FF-16 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-152 | FF-152 | Error message is not displayed under the respective field while creating a user. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-153 | FF-153 | All cities should be shown under respective region while creating or editing a site | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-154 | FF-154 | For Adnan Chaudhary’s customer site Palace View FS, the products do not have any color set on the portal, but on the dashboard the products of Palace View FS are displayed with colors. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-155 | FF-155 | For CALTEX_BE’s customer site Pine Avenue, the Diesel product color is blue on the portal, but it appears orange on the dashboard. The color should be consistent on both. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-156 | FF-156 | The date on the X-axis gets hidden when the user hovers over the chart. This issue occurs on all charts across the dashboard. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-158 | FF-158 | While editing a pump and reconfigure its mapping, mapping gets removed after saving it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-159 | FF-159 | Login Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-160 | FF-160 | Forgot Password Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-06 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-161 | FF-161 | Dashboard Home Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-03 | 2025-12-04 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-162 | FF-162 | Alarms Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-08 | 2025-12-09 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-163 | FF-163 | Deliveries Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-10 | 2025-12-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-164 | FF-164 | Transactions Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-12 | 2025-12-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-165 | FF-165 | Reconciliation Report Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-18 | 2025-12-19 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-166 | FF-166 | Loss & Gain Charts Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-22 | 2025-12-23 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-167 | FF-167 | Sales Target Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-26 | 2025-12-29 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-168 | FF-168 | Stock Management Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-05 | 2025-12-05 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-169 | FF-169 | Nozzle Usage Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-16 | 2025-12-16 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-170 | FF-170 | FuelChat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-24 | 2025-12-24 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-171 | FF-171 | Crash Fixes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-30 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-172 | FF-172 | Optimization for Responsiveness | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2025-12-31 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-173 | FF-173 | For site Coco 5 LHR, the sales of products DI and PF are showing in the Sales Transaction tab of the Reconciliation Report, but in the Reconciliation Report tab, the sales for DI and PF are showing as 0 (zero). | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-174 | FF-174 | Multiple tenants access should not be allowed for (Dashboard user) while creating, editing. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-175 | FF-175 | UI Issues with Dropdown Colors and Date Visibility in Night Mode | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-26 | 0.75
https://octopusdtlsupport.atlassian.net/browse/FF-176 | FF-176 | Side Navigation and Header Color Mismatch with Body Background in Night mode | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-177 | FF-177 | Tagline is Not same on Web And Mobile Application, Moreover it should be "Welcome To" Instead of "welcome Back" | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-178 | FF-178 | In Footer rights should be reserved for 2026 instead of 2025,The link to OctopusDigital should be included on the dashboard and throughout all other screens of the application. and the link should take users back to its original page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-179 | FF-179 | Symmetry in icons and colors: Mentioned in the description | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-180 | FF-180 | "Username" is missing from Placeholder, Need to add it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-181 | FF-181 | "Sign in With Microsoft" is missing from Fintech Fuel Mobile Application. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-08 | 2026-01-08 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-182 | FF-182 | Unable to Reset the Password. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-183 | FF-183 | “The eye icon should be updated to its inverse version.” on dashboard and Portal. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-09 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-184 | FF-184 | Customer “Adnan Chaudhary” Disappeared from Customer List | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Ameer Hamza Khan | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-185 | FF-185 | “An expired OTP is being validated, allowing the user to log in and access the dashboard.” | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-186 | FF-186 | need to implement an error message on character limit | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-187 | FF-187 | Days and dates should be displayed as on dashboard, if both aren't manageable because of UI, Date must be displayed in Sales vs Target(Dashboard). | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-188 | FF-188 | Invalid OTP is being validated, allowing the user to log in and access the dashboard. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2.5
https://octopusdtlsupport.atlassian.net/browse/FF-189 | FF-189 | Need to Remove upper extra section, Moreover all the highlighted values need to be displayed same as its on web | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-190 | FF-190 | 1.Profile menu is not getting vanished while clicking anywhere on the dashboard screen, 2. Dashboard: Tagline need to be same | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-191 | FF-191 | Forgot Password: Check the description | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-192 | FF-192 | Week Fuel Trend is not Interactive Left Side Values are not same with web dashboard, Secondly Product colors are not same. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-193 | FF-193 | User Is Not Automatically Logged Out When Session Expires | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-01-27 | 2026-01-30 | 2026-01-27 | 2026-02-25 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-194 | FF-194 | Selected Customer's logo is not getting displayed in the top menu. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-195 | FF-195 | Dashboard Left menu amendments in text and missing pages, including Sequence of left Menu. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-196 | FF-196 | Remove Timestamp from Date-Time Filter on Recon Report and Loss/Gain Charts | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-02-16 | 2026-02-17 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-197 | FF-197 | Application doesn't blocks multiple failed login attempts | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-198 | FF-198 | Same web's error messages need to be displayed on mobile app, need to be fixed on all error messages. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-199 | FF-199 | Play Store Deployment for Testers | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-20 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-200 | FF-200 | Alarms Issues: | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-201 | FF-201 | Alarms and their Icons and colors need to be matched with web dashboard. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-202 | FF-202 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-97 | FF-97 | FF-16 | kamran khalid | [7 empty] | 2026-01-12 | 2026-01-13 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-203 | FF-203 | Search Placeholder is not visible completely, nor Icons and descriptions are same, alarm types Are missing also. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-204 | FF-204 | User should Search/ Filter alarms on the basis of their: Title, Description, Severity | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-205 | FF-205 | While filtering multiple sites, or single site "Other" Alarm type is missing and its showing invalid count for that | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-206 | FF-206 | Severity Filter dropdown not implemented and functional. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-207 | FF-207 | Selected Site/Customer name should be displayed. (on all screens) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-208 | FF-208 | Date Range is limited to 2 weeks, Any 2 months for selection should be allowed to view data. It should be flexible that user can select data of 2 weeks or 1 month of any year, or 2 months or 1 day. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-209 | FF-209 | The Application does not load data after login, Until we click the Refresh button. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-210 | FF-210 | fuel chat testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | kamran khalid | [7 empty] | 2026-01-13 | 2026-01-15 | 26
https://octopusdtlsupport.atlassian.net/browse/FF-211 | FF-211 | "Reconciliation Report" issues | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-212 | FF-212 | Missing Columns from Recon table: | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-213 | FF-213 | The Excel button for downloading the file is not implemented. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-214 | FF-214 | Pagination needs to be implemented. on all the required pages as on web dashboard | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-215 | FF-215 | The Excel button for downloading the file is not implemented on Nozzle Usage, and description is not mentioned. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-216 | FF-216 | All necessary columns must include IDs as well as inactive hours. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-217 | FF-217 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-01-19 | 2026-01-23 | 2026-01-19 | 2026-01-23 | 40
https://octopusdtlsupport.atlassian.net/browse/FF-218 | FF-218 | Low Stock Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-219 | FF-219 | Select All functionality is missing, It should be implemented on all the filters as on web dashboard. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-220 | FF-220 | Inactive hours should not be less than 0 | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-221 | FF-221 | Overall Active Hours of Last 7 days are not available on the nozzle usage screen. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-222 | FF-222 | The values on the column should match against the Column names in the table | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-223 | FF-223 | Failed to load Nozzle Usage Data for 2 days | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-224 | FF-224 | Stock Levels Issues | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-225 | FF-225 | All the Values must be same On Stock Levels. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-226 | FF-226 | "Confirmed Quantity" and "Bill of Lading Reference" is missing from Deliveries Table, Moreover there must be some space in between Tank and Timestamp column. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-227 | FF-227 | The Excel button for downloading the file is not implemented on Deliveries | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-230 | FF-230 | Aramco 7-7 Recon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-229 | FF-229 |  | Hassan Saeed Wattoo | [5 empty] | 2026-01-23 | 2026-01-27 | 2026-01-23 | 2026-01-27 | 22
https://octopusdtlsupport.atlassian.net/browse/FF-231 | FF-231 | FuelChat - Summarized Version | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-157 | FF-157 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-232 | FF-232 | POC on cost comparison (summarized vs. non-summarized versions) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-157 | FF-157 |  | Hassan Saeed Wattoo | [5 empty] | 2026-01-15 | 2026-01-22 | 2026-01-14 | 2026-01-22 | 38
https://octopusdtlsupport.atlassian.net/browse/FF-233 | FF-233 | Presentation on All models comparison | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-157 | FF-157 |  | Hassan Saeed Wattoo | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 6
https://octopusdtlsupport.atlassian.net/browse/FF-234 | FF-234 | POC on all models comparison | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-157 | FF-157 |  | Hassan Saeed Wattoo | [5 empty] | 2026-01-09 | 2026-01-14 | 2026-01-09 | 2026-01-13 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-235 | FF-235 | Bug fixes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-157 | FF-157 |  | Hassan Saeed Wattoo | [5 empty] | 2026-01-01 | 2026-01-05 | 2026-01-01 | 2026-01-06 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-236 | FF-236 | Enhancement request from SQA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-157 | FF-157 |  | Hassan Saeed Wattoo | [5 empty] | 2026-01-02 | 2026-01-08 | 2026-01-02 | 2026-01-08 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-239 | FF-239 | Low Stocks Issues which need to be fixed: | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-240 | FF-240 | Low Stocks: When choosing multiple sites, some values do not match, and Total Alerts should also be shown (for multiple sites/single sites). | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-241 | FF-241 | Low Stocks (Tank View ) : Alerts and Status column and Stock levels are missing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-242 | FF-242 | Current Levels and Days Left should be same as implemented on Web Dashboard | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-243 | FF-243 | Grade View : | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-244 | FF-244 | Incorrect Stock Level Displayed for Product PF on Low Stock Screen (Coco 2 LHR) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-245 | FF-245 | Site Level Alerts Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-120 | FF-120 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-246 | FF-246 | All values of Deliveries page and all other screen need to be same, and .00 should be removed as we don't have much space in the mobile app nor it is implemented on web dashboard. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-247 | FF-247 | Contact Support button need to be implemented on Mobile application | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-248 | FF-248 | Sales Target is not same as on web, values sales trend analysis: line charts and bar charts Daily sales summary fields and values Performance Summary (need to remove Extra) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-249 | FF-249 | Missing Alerts and invalid total alerts for single and multiple sites On both Tank view and Grade view of low stocks | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-250 | FF-250 | Grade view values are not same while selecting single or multiple sites | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-251 | FF-251 | Card view should be same as table view of transactions , (Day end Sales), ⁠Pump and Hose Filter dropdowns are missing from transaction page. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-252 | FF-252 | Excel button should be available and functional to be downloaded for transaction screen (Day end Sales) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-253 | FF-253 | (Day end sales Summary) title need to be correct and extra columns should be removed, | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-254 | FF-254 | Card view should be same as table view of transactions , ("Day End Sales Summary"). | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-255 | FF-255 | Excel button should be available and Functional for the types of reports of transaction | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-256 | FF-256 | Need to remove unstable pagination from Transactions level sales and wherever else it is implemented as we are using (Load more button previously) So Load more button should be implemented now on every screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-257 | FF-257 | Transaction level sales : Title should complete. Padding must be added in between "Row Number" and "Site Name" | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-258 | FF-258 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-259 | FF-259 | Loss & Gain Chart : dates are mismatched. and need discussion on other graph values | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-260 | FF-260 | Invalid values for Daily Deliveries chart (Loss Gain Charts) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-261 | FF-261 | Critical : Application is Crashing while changing the customer and transaction type, on Loss & Gain screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-262 | FF-262 | headings should be same while selecting any chart type on Loss Gain | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-263 | FF-263 | Selected date for filtration is from 26 but data is filtered from 25 (Sales target). | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-264 | FF-264 | Daily sales summary is getting displayed in weekly sales Summary | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-265 | FF-265 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-266 | FF-266 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-267 | FF-267 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-268 | FF-268 | While filtering the results for "92" which should be only 2 records its displaying 6 records, for card view of transactions | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-269 | FF-269 | those nozzles which are associated to the Pump2 should be filtered out, when user has specified the pump (Day end sales -Transactions ) instead of all the nozzles to be selected | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-272 | FF-272 | Transaction , Recon Report Booked: minus sign with zero is being displayed in mobile app | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-273 | FF-273 | Displaying Invalid Count while selecting multiple or all the sites of a customer (Low Stocks) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-279 | FF-279 | Frontend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-280 | FF-280 | Backend API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-02-19 | 2026-02-25 | 2026-02-09 | 2026-02-23 | 40
https://octopusdtlsupport.atlassian.net/browse/FF-281 | FF-281 | R&D | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-275 | FF-275 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-01-21 | 2026-01-23 | 2026-02-05 | 2026-02-05 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-282 | FF-282 | Swagger API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-275 | FF-275 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 32
https://octopusdtlsupport.atlassian.net/browse/FF-283 | FF-283 | Unable to Delete any chat from FuelCHat | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-284 | FF-284 | Unable to Edit any chat from FuelCHat | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-285 | FF-285 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-286 | FF-286 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-287 | FF-287 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-288 | FF-288 | Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-20 | FF-20 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-29 | FF-29 | After 10:43 AM utc time The Data for (PARCO GUNOVER) Gardenia Filling Station and (Adnan Chaudary) Palace View FS the Files are getting landed From the Un Processed Folder to the "Exceptional Folder". | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | Muhammad Usman Javed | [5 empty] | 2025-10-02 | 2025-10-02 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-30 | FF-30 | Again 2 files has been missed in the Processed folder for "Gardenia Filling Station" found in "Exception Folder". | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-307 | FF-307 | Fuelchat Modification for 7-7 Recon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-229 | FF-229 |  | Hassan Saeed Wattoo | [5 empty] | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-308 | FF-308 | Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-229 | FF-229 |  | Hassan Saeed Wattoo | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-31 | FF-31 | The Forgot password screen is the old screen and is not responsive and does not align with the new layout. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-318 | FF-318 | Designing Database Schema | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-319 | FF-319 | Backend API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-06 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-32 | FF-32 | Kindly update the email validation check upon forgot password screen as we have currently encounter client emails such as "Nida.wasif@parcogunvor.com.pk" as currently its not accepting. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-320 | FF-320 | Need to modify finchat to "FuelChat" | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-321 | FF-321 | FuelChat is showing invalid results while we ask for sites of a tenant | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-322 | FF-322 | Site name, Cite and Province is missing from the table | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-323 | FF-323 | While we login with portal user, Customer is not changeable on mobile application | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-324 | FF-324 | When dashboard user is assigned only one customer, and asking question related to another customer which is not assigned to it, the system shows information related to the assigned customer without displaying any restriction message. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-326 | FF-326 | User can not Export chat in PDF by clicking on the "Export Chat" button. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-327 | FF-327 | Bar Charts, Line Charts, Pie Chart are not available in Fuel chat | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-328 | FF-328 | Creating Notification Group Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-329 | FF-329 | Creating Alarms Configurations Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-33 | FF-33 | The links in the email for Forgot Password not working. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-330 | FF-330 | Integrating APIs (Notifications Group Page) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 7
https://octopusdtlsupport.atlassian.net/browse/FF-331 | FF-331 | Integrating APIs (Alarm Configurations Page) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 7
https://octopusdtlsupport.atlassian.net/browse/FF-332 | FF-332 | Sanity and Bug Fixes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-11 | 2026-02-16 | 2026-02-11 | 2026-02-16 | 23
https://octopusdtlsupport.atlassian.net/browse/FF-333 | FF-333 | Creation of Demo Customer for Demo Purpose - Clone of Aramco Customer | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-334 | FF-334 | Duplication of Sale ID in fintech transaction table | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-335 | FF-335 | Create a logic app for duplicate rows in Fintech raw tables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2025-12-21 | 2026-01-22 | 2026-01-21 | 2026-01-23 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-336 | FF-336 | Flushing of data for COCO 5 LHR site as per Affan's instructions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-125 | FF-125 |  | Muhammad Usman Javed | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-338 | FF-338 | Integrating new APIs for Alarms page with Acknowledge functionality | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-339 | FF-339 | Alarm Triggering Logic | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-34 | FF-34 | Login with Microsoft button not clickable | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-340 | FF-340 | SQL Triggers for Alarm Triggering | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-341 | FF-341 | Logic App Development for Email Notifications | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-12 | 2026-02-16 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-342 | FF-342 | Fintech Mobile App (Fuel Chat) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Namra Zahid | [5 empty] | 2026-02-13 | 2026-02-18 | 2026-02-13 | 2026-02-17 | 12.83
https://octopusdtlsupport.atlassian.net/browse/FF-344 | FF-344 | Requirement finalizing, unit testing, task management and staging release preparation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Ameer Hamza Khan | [5 empty] | 2026-02-11 | 2026-02-18 | 2026-02-11 | 2026-02-18 | 48
https://octopusdtlsupport.atlassian.net/browse/FF-345 | FF-345 | Improvements in SQL Alarm Triggering Logic | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-346 | FF-346 | Alarm triggering logic + Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Hassan Saeed Wattoo | [5 empty] | 2026-01-28 | 2026-01-30 | 2026-01-28 | 2026-01-30 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-349 | FF-349 | Deployment of Backend on Staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-348 | FF-348 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 6
https://octopusdtlsupport.atlassian.net/browse/FF-35 | FF-35 | Data does not align with the Fuel Transaction trend as selected in the filter applied | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-350 | FF-350 | Deployment of Frontend on Staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-348 | FF-348 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-351 | FF-351 | QA Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-348 | FF-348 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-352 | FF-352 | Unit Testing with web team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-353 | FF-353 | Dashboard and Portal users are not getting logged in on staging environment,Unable to change password through forgot password even , giving this Error. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-124 | FF-124 |  | Muhammad Usman Javed | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-354 | FF-354 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | kamran khalid | [5 empty] | 2026-02-18 | 2026-02-23 | 2026-02-18 | 2026-02-26 | 39.5
https://octopusdtlsupport.atlassian.net/browse/FF-356 | FF-356 | Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-355 | FF-355 | FF-314 | Namra Zahid | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 0.67
https://octopusdtlsupport.atlassian.net/browse/FF-357 | FF-357 | M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-355 | FF-355 | FF-314 | Muhammad Abbas | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 0.58
https://octopusdtlsupport.atlassian.net/browse/FF-358 | FF-358 | Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-355 | FF-355 | FF-314 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-359 | FF-359 | Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-355 | FF-355 | FF-314 | kamran khalid | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-36 | FF-36 | width of the selected option (selected Site) as the UI is disturbed in the filter modal | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-360 | FF-360 | Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-355 | FF-355 | FF-314 | Waqar Rasheed | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-361 | FF-361 | QA Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-348 | FF-348 | FF-314 | Sarmad Sabir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-362 | FF-362 | User is able to create alarms with empty conditions | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-363 | FF-363 | Alarms permissions missing for Create, Edit and Delete | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-364 | FF-364 | Delivery Arrival time for alarms mismatch with the original deliveries landed in the prod env | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-365 | FF-365 | Add the Setpoints for Alarms triggered such as variance, Tanks Levels and others alarms too where suitable | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-19 | 5
https://octopusdtlsupport.atlassian.net/browse/FF-366 | FF-366 | While Configuring Condition based alarms if user selects a condition, no option is available to revert it i.e reverting back to single state | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-367 | FF-367 | Remove ID's along with entities on all pages | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-368 | FF-368 | Inactive Customer still showing on staging | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-19 | 2026-02-19 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-369 | FF-369 | LOGIN with Microsoft not working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-37 | FF-37 | Multiple Customers are showing in the customer dropdown in the filter modal | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | Muhammad Usman Javed | [5 empty] | 2025-09-30 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-370 | FF-370 | Making fuelchat compatible | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-02-17 | 2026-02-20 | 2026-02-17 | 2026-02-19 | 19
https://octopusdtlsupport.atlassian.net/browse/FF-371 | FF-371 | "<=" amd ">=" conditions missing for Tank Level Alarms & Recon Alarms | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-372 | FF-372 | Integration of backend and frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Hassan Saeed Wattoo | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-375 | FF-375 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-427 | FF-427 | FF-373 | Namra Zahid | [5 empty] | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-02-27 | 36.78
https://octopusdtlsupport.atlassian.net/browse/FF-376 | FF-376 | Current Value For Delivery Arrival Alarm triggered is showing value in Percentages% | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-377 | FF-377 | Acknowledge Alarm should show the user name by which it is Acknowledge and the acknowledge time also | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-378 | FF-378 | Variance Alarms Not Triggering Despite Condition Match | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-379 | FF-379 | User type is not getting changed to AAD User, and showing the error while user tries to login with Microsoft. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-23 | 2026-02-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-38 | FF-38 | The Recon report which was working earlier just data not matched is now not working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-380 | FF-380 | Site Dropdown Inactive and doesn't show site name in Alarm Configuration When Single Site Selected in Main Filter | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-382 | FF-382 | Forgot Password Functionality if Failed with this error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-383 | FF-383 | After turning on the OTP, Instead of letting the user to be logged in, its showing the Error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-384 | FF-384 | login with Microsoft functionality should be implemented for dashboard user also. TASK | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-385 | FF-385 | Unable to delete alarms | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-386 | FF-386 | Inactive (Unacknowledged) Alarms Not Visible in Historical Tab as its showing inthe Data base | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-25 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-387 | FF-387 | Pagination is not applied on alarms screen on configured alarms table | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-388 | FF-388 | Application Not Redirecting to Login Page (MAIN URL) After Session Timeout on Refresh | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 0.75
https://octopusdtlsupport.atlassian.net/browse/FF-389 | FF-389 | System Allows Creation of Duplicate Notification Groups | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-39 | FF-39 | For specific time filter Day End sales filter is showing data but on the same time duration Day End Sales Summary is not working. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-390 | FF-390 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-427 | FF-427 | FF-373 | Waqar Rasheed | [5 empty] | 2026-02-23 | 2026-02-26 | 2026-02-24 | 2026-02-27 | 25.5
https://octopusdtlsupport.atlassian.net/browse/FF-391 | FF-391 | Unit testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Hassan Saeed Wattoo | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 4.5
https://octopusdtlsupport.atlassian.net/browse/FF-392 | FF-392 | “Account Does Not Exist” Error on Staging and Forgot Password Failure | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-393 | FF-393 | Selected Sites Not Displayed in Site Field (Deliveries Screen) — Implement Fix Across Application | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [7 empty] | 2026-02-24 | 2026-02-24 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-394 | FF-394 | Search Functionality Limited to Site Name and Article Columns on Deliveries Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [7 empty] | 2026-02-26 | 2026-02-26 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-395 | FF-395 | Date Filter on Deliveries Screen Returns Data Outside Selected Date Range | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-396 | FF-396 | Validation Error Placement and Value Reset Issue When Entering Quantity Greater Than Capacity on Deliveries screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-397 | FF-397 | Updated Time Field Not Refreshing on Alarm Activation/Deactivation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-398 | FF-398 | “Submit Values” Button Enabled by Default on Deliveries Screen even when the Confirmed Quantity field and Bill of Lading Reference field is empty | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-26 | 0.75
https://octopusdtlsupport.atlassian.net/browse/FF-399 | FF-399 | Warning Status Displayed for 3 Days Remaining on Low Stock Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-40 | FF-40 | kindly remove the user profile image selecting option as its no longer required | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-400 | FF-400 | Improvements after unit testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Hassan Saeed Wattoo | [5 empty] | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-03-02 | 16.5
https://octopusdtlsupport.atlassian.net/browse/FF-401 | FF-401 | Support Icon Overlapping with “Next” Pagination Text on Low Stock Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-402 | FF-402 | While Editing an existing alarm, the fields Customer, Sites, Alarm Type, and Sub Alarm Type should not be editable. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-403 | FF-403 | Search and Filter Functionality Not Working Correctly on Deliveries Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-404 | FF-404 | Summary Metrics Not Updating According to Applied Search on Deliveries Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-405 | FF-405 | Inconsistent Timestamp Format on Deliveries Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-406 | FF-406 | Diagnostics Dashboard is loading data for sites other than the customer selected and this user has not access to Aramco sites | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-407 | FF-407 | Tooltip Color Mismatch on Loss/Gain Chart Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 1.5
https://octopusdtlsupport.atlassian.net/browse/FF-408 | FF-408 | Stock Volume Mismatch Between Loss/Gain Chart and Recon Report (Hi Super & Excellium) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Hassan Saeed Wattoo | [7 empty] | 2026-03-27 | 2026-03-27 | 4
https://octopusdtlsupport.atlassian.net/browse/FF-409 | FF-409 | ADD Scroll functionality for Notification Group Section | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.02
https://octopusdtlsupport.atlassian.net/browse/FF-41 | FF-41 | Kindly update the Update button name to generate report | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-410 | FF-410 | ADD pagination in the following screens 1. Recipients Groups 2. Diagnostic Configuration tabs in the Notifications group | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.25
https://octopusdtlsupport.atlassian.net/browse/FF-411 | FF-411 | Opening Level Field Not Editable for Non-Consecutive Days on Submit Data Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Sarmad Sabir | [5 empty] | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-18 | 5
https://octopusdtlsupport.atlassian.net/browse/FF-412 | FF-412 | Side Menu “Submit Data” Tab Not Highlighted on Day Submission Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-413 | FF-413 | Actual Closing Field Should Auto-Populate and Be Non-Editable on Submit Data Screen. Also add respective unit with each column | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Muhammad Usman Javed | [5 empty] | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-417 | FF-417 | Testing for fuelchat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-418 | FF-418 | Pagination malfunction on Deliveries page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-374 | FF-374 | FF-373 | Sarmad Sabir | [5 empty] | 2026-03-05 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-419 | FF-419 | Diagnostic Dashboard displaying timestamps in UTC instead of Local Time Zone | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-42 | FF-42 | When user apply the filter for 6 days and calculate the recon the data is not fetched. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-420 | FF-420 | Active and Inactive Site Status Count should not Dependent on Grid Pagination | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-421 | FF-421 | “Per Site” Tab on Diagnostic Dashboard Displays Only Inactive Sites | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-03-05 | 2026-03-09 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-422 | FF-422 | Notification Groups Can Be Created Using Only Numbers or Special Characters | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-423 | FF-423 | The Diagnostic Icon on the Top right bar shows notification number as "3" but in actual the customer has only one site and two activities in total | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-03-04 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-424 | FF-424 | The SITE LEVEL ALARM (Connectivity / Disconnectivity) email should not contain Tank ID and Tank Capacity and Current Value | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-425 | FF-425 | Integrate Additional Modules into Fuel Chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-426 | FF-426 | Testing by Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-278 | FF-278 | FF-274 | kamran khalid | [7 empty] | 2026-02-25 | 2026-03-05 | 39.5
https://octopusdtlsupport.atlassian.net/browse/FF-428 | FF-428 | Testing by Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-121 | FF-121 | FF-119 | Namra Zahid | [5 empty] | 2026-01-08 | 2026-02-12 | 2026-02-02 | 2026-02-12 | 48
https://octopusdtlsupport.atlassian.net/browse/FF-429 | FF-429 | Connectivity Alarms Not Visible on Dashboard Despite Email Notifications | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-277 | FF-277 | FF-274 | Muhammad Usman Javed | [5 empty] | 2026-03-05 | 2026-03-09 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-43 | FF-43 | API Failure error when user tries to visit to Nozzle usage link while the Main Filter Modal is open. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-430 | FF-430 | Mismatch in Configured Alarms for ROSE MOUNT Between Dashboard and Fuel Chat | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-431 | FF-431 | Created Date and Updated Date format is not correct in the CSV downloaded from FUEL chat for Configured Alarms | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-432 | FF-432 | Updated time is missing for some alarms on Fuel Chat | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-433 | FF-433 | Some of Inactive Alarms Missing in Fuel Chat Despite Being Present on Dashboard | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-434 | FF-434 | Fuel Chat Missed Disconnectivity Event Displayed on Dashboard | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-435 | FF-435 | Fuel Chat Not Displaying Tank-Wise Delivery Alarms as Shown on Dashboard | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [7 empty] | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-436 | FF-436 | Fuel Chat Not Retrieving Alarm Trigger Conditions | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1.5
https://octopusdtlsupport.atlassian.net/browse/FF-437 | FF-437 | Fuel Chat Not Displaying Only Active Notification Groups Used in Alarm Configuration | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-438 | FF-438 | Fuel Chat Session Does Not Expire After Inactivity | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Muhammad Usman Javed | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-439 | FF-439 | Alson Device Integration R&D | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | Muhammad Usman Javed | [5 empty] | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-03-04 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-44 | FF-44 | The SMTP email issue, Emails not sending to users through both the “Forgot Password” and new user activation emails depend on it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-440 | FF-440 | Duplicates found in terms of Notification groups in Fuel Chat | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-315 | FF-315 | FF-314 | Hassan Saeed Wattoo | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 0.5
https://octopusdtlsupport.atlassian.net/browse/FF-441 | FF-441 | R&D: ALSONS device data format & ingestion approach | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-02-01 |  | 2026-02-02 | 2026-03-03 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-442 | FF-442 | R&D on Tank Level Data and Delivery Detection Logic | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | Hassan Saeed Wattoo | [5 empty] | 2026-03-03 | 2026-03-06 | 2026-03-03 | 2026-03-06 | 19.5
https://octopusdtlsupport.atlassian.net/browse/FF-443 | FF-443 | Design & Develop: Ingestion MQTT Broker service | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-02-05 | 2026-02-12 | 2026-02-05 | 2026-03-12 | 56
https://octopusdtlsupport.atlassian.net/browse/FF-444 | FF-444 | Implement: Buffering & backpressure (MQTT-ETL) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-02-16 | 2026-02-20 | 2026-02-16 | 2026-03-20 | 41
https://octopusdtlsupport.atlassian.net/browse/FF-445 | FF-445 | Build: ETL flow to land raw data on SFTP | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-02-21 | 2026-02-28 | 2026-03-21 | 2026-03-26 | 40
https://octopusdtlsupport.atlassian.net/browse/FF-448 | FF-448 | Database Schema Design | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-447 | FF-447 | FF-446 | Muhammad Usman Javed | [5 empty] | 2026-02-02 | 2026-02-03 | 2026-02-02 | 2026-02-02 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-449 | FF-449 | Backend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-447 | FF-447 | FF-446 | Muhammad Usman Javed | [5 empty] | 2026-02-09 | 2026-02-12 | 2026-02-10 | 2026-02-12 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-45 | FF-45 | The issue is arising for Newly created users as the activation links redirects to 404 Error page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-5 | FF-5 | FF-1 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-450 | FF-450 | SQA Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-447 | FF-447 | FF-446 | Muhammad Usman Javed | [5 empty] | 2026-03-06 | 2026-03-06 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-451 | FF-451 | Develop VM ETL to transform incoming files/data - PART B | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-06 | 40
https://octopusdtlsupport.atlassian.net/browse/FF-452 | FF-452 | Implement and Test Logic on Dummy Delivery Table | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | Hassan Saeed Wattoo | [5 empty] | 2026-03-10 | 2026-03-12 | 2026-03-10 | 2026-03-12 | 19.5
https://octopusdtlsupport.atlassian.net/browse/FF-453 | FF-453 | SP for Product-wise and Tank-wise Reconciliation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-275 | FF-275 | FF-271 | Hassan Saeed Wattoo | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-454 | FF-454 | Integrate Logic with Logic App and Validate | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | Hassan Saeed Wattoo | [5 empty] | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-16 | 13
https://octopusdtlsupport.atlassian.net/browse/FF-455 | FF-455 | Incorrect Side Navigation and Message Box Visibility Issue on Fuel Chat Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-316 | FF-316 | FF-314 | Sarmad Sabir | [5 empty] | 2026-03-18 | 2026-03-18 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-457 | FF-457 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-456 | FF-456 | FF-373 | kamran khalid | [5 empty] | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-10 | 6.5
https://octopusdtlsupport.atlassian.net/browse/FF-458 | FF-458 | API Development Architecture Rework | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-275 | FF-275 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-03-12 | 35
https://octopusdtlsupport.atlassian.net/browse/FF-459 | FF-459 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-289 | FF-289 | FF-271 | kamran khalid | [5 empty] | 2026-03-11 |  | 2026-03-11 | 2026-03-25 | 49
https://octopusdtlsupport.atlassian.net/browse/FF-460 | FF-460 | QA Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-276 | FF-276 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-461 | FF-461 | Create a Demo Web Application for PGL | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | Muhammad Usman Javed | [5 empty] | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-17 | 20
https://octopusdtlsupport.atlassian.net/browse/FF-462 | FF-462 | Initial requirements gathering and finalizing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-311 | FF-311 | FF-274 | Ameer Hamza Khan | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-463 | FF-463 | Screen Designing and UI/UX creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-311 | FF-311 | FF-274 | Ameer Hamza Khan | [5 empty] | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-05 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-464 | FF-464 | Database schema designing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-311 | FF-311 | FF-274 | Ameer Hamza Khan | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-465 | FF-465 | Finalizing development and unit testing with team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-311 | FF-311 | FF-274 | Ameer Hamza Khan | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-466 | FF-466 | Preparing for staging release and handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-311 | FF-311 | FF-274 | Ameer Hamza Khan | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-467 | FF-467 | Develop VM ETL to transform incoming files/data - PART A | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-03-27 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-468 | FF-468 | Develop VM ETL to transform incoming files/data - PART C | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 40
https://octopusdtlsupport.atlassian.net/browse/FF-469 | FF-469 | SQL Insertion Pipeline for PGL Demo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | yousha.agha | [5 empty] | 2026-03-16 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-471 | FF-471 | Product Availability Percentage showing 0 despite Available Volume having value in API response | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-291 | FF-291 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-472 | FF-472 | Read API not returning all deliveries within the specified 'FromDate' and 'ToDate' range | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-291 | FF-291 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-473 | FF-473 | Read API (Get Tank Levels) returning data for Customer and Site not assigned to the authenticated user | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-291 | FF-291 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 3
https://octopusdtlsupport.atlassian.net/browse/FF-474 | FF-474 | The API accepts multiple parameters with the same name in the request but processes only the first parameter value while ignoring the remaining values without validation or error response. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-291 | FF-291 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-475 | FF-475 | Enhance Read API to support multiple site inputs for a single customer | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-291 | FF-291 | FF-271 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-477 | FF-477 | Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-476 | FF-476 | FF-343 | Hassan Malik | [5 empty] | 2026-03-16 | 2026-03-17 | 2026-03-16 | 2026-03-17 | 10
https://octopusdtlsupport.atlassian.net/browse/FF-478 | FF-478 | Kindly provide Formula to calculate Variance and Variance Percentage only in Tank Levels | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-291 | FF-291 | FF-271 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-479 | FF-479 | Alson data understanding to modify the SP accordingly | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-293 | FF-293 | FF-292 | Hassan Saeed Wattoo | [5 empty] | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-24 | 20
https://octopusdtlsupport.atlassian.net/browse/FF-48 | FF-48 | Update the unit From Dollars to PKR as highlighted in the screenshot | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-480 | FF-480 | The Get Transaction Summarized By Product API does not return aggregated (summarized) results for the provided date range. Instead of combining the data, the API response includes separate entries for each day within the range. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-291 | FF-291 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-03-25 | 2026-03-25 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-481 | FF-481 | Addressing client's queries, review and finalizing documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-476 | FF-476 | FF-343 | Ameer Hamza Khan | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-482 | FF-482 | Internal data source backup and restoring(on local machine) practice | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-476 | FF-476 | FF-343 | Ameer Hamza Khan | [5 empty] | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2026-03-25 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-484 | FF-484 | Requirements understanding and analyzing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-483 | FF-483 | FF-297 | Ameer Hamza Khan | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-485 | FF-485 | Requirements gathering | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-483 | FF-483 | FF-297 | Muhammad Usman Javed | [5 empty] | 2026-03-26 | 2026-03-30 | 2026-03-26 | 2026-04-01 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-486 | FF-486 | Database schema design planning | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-483 | FF-483 | FF-297 | Muhammad Usman Javed | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-488 | FF-488 | Fintech Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-487 | FF-487 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-489 | FF-489 | Fintech Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-487 | FF-487 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-49 | FF-49 | Generate button is containing string (DEBUG :FALSE) and its not working for Daily Stock chart for the same time period as selected for Daily sales chart | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-490 | FF-490 | Fintech Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-487 | FF-487 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-491 | FF-491 | Fintech Fuel Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-487 | FF-487 | FF-16 | Muhammad Imran Aslam | [5 empty] | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-492 | FF-492 | Alson requirements gathering | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-483 | FF-483 | FF-297 | Hassan Saeed Wattoo | [5 empty] | 2026-03-27 | 2026-04-10 | 2026-03-27 | 2026-04-07 | 38
https://octopusdtlsupport.atlassian.net/browse/FF-493 | FF-493 | Schema design validation and rectification | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-483 | FF-483 | FF-297 | Ameer Hamza Khan | [5 empty] | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-496 | FF-496 | Renaming site name, marking site inactive and verifying reactivation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-495 | FF-495 | FF-343 | Ameer Hamza Khan | [5 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 1
https://octopusdtlsupport.atlassian.net/browse/FF-497 | FF-497 | Updated Site Configuration for Alson Devices | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-298 | FF-298 | FF-297 | Muhammad Usman Javed | [5 empty] | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-10 | 48
https://octopusdtlsupport.atlassian.net/browse/FF-50 | FF-50 | when i change the option from "Daily Sales Chart" to "Daily Stock Chart", then the system generates error Timeout expired | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-501 | FF-501 | Research on Multi Language Support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-499 | FF-499 | FF-498 | Sarmad Sabir | [5 empty] | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-502 | FF-502 | Research on Angular i18n for LS | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-499 | FF-499 | FF-498 | Sarmad Sabir | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-504 | FF-504 | QA Reported UI Bugs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-503 | FF-503 | FF-373 | Sarmad Sabir | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-51 | FF-51 | While reviewing the Daily Sales chart for the one-month period, the report shows a total loss of 17.9k liters. This value appears incorrect and suggests an issue with the calculation or data representation. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-511 | FF-511 | ETL Modification for Alson | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-298 | FF-298 | FF-297 | Muhammad Usman Javed | [5 empty] | 2026-04-10 | 2026-04-16 | 2026-04-13 | 2026-04-15 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-52 | FF-52 | kindly change the Arrow position downwards as its reflecting LOSS not Gain | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-528 | FF-528 | Sp modification to insert Alson data into current TankDelivery | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-483 | FF-483 | FF-297 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-529 | FF-529 | Current SP Modification + New SP for Tank Deliveries Calculation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-298 | FF-298 | FF-297 | Hassan Saeed Wattoo | [5 empty] | 2026-04-08 | 2026-04-13 | 2026-04-08 | 2026-04-09 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-53 | FF-53 | Upon Checking the Deliveries chart From Time Period 1 may to 30th may 2025 for Site COCO-Liberty as compared to the Data with the same Filter Applied on SM 360 Web Application. The Data Mismatch | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-530 | FF-530 | Testing By waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-456 | FF-456 | FF-373 | Waqar Rasheed | [5 empty] | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-535 | FF-535 | Dashboard POC Implementation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-499 | FF-499 | FF-498 | Sarmad Sabir | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-54 | FF-54 | Daily Stock Level Mismatch as of 1st May 2025 as compared to SM 360 for site COCO Liberty | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-543 | FF-543 | Email and db structure modification | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-527 | FF-527 | FF-274 | Hassan Saeed Wattoo | [5 empty] | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-15 | 29
https://octopusdtlsupport.atlassian.net/browse/FF-544 | FF-544 | Testing the SP and integrating the logic into the current tank delivery table. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-298 | FF-298 | FF-297 | Hassan Saeed Wattoo | [5 empty] | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-04-20 | 24
https://octopusdtlsupport.atlassian.net/browse/FF-545 | FF-545 | Pointer table changes and Integration with web team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-298 | FF-298 | FF-297 | Hassan Malik | [5 empty] | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-22 | 16
https://octopusdtlsupport.atlassian.net/browse/FF-546 | FF-546 | Add Rate Limiting for ReadAPI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-275 | FF-275 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 12
https://octopusdtlsupport.atlassian.net/browse/FF-547 | FF-547 | Add API Logs for ReadAPI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-275 | FF-275 | FF-271 | Muhammad Usman Javed | [5 empty] | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 12
https://octopusdtlsupport.atlassian.net/browse/FF-548 | FF-548 | Add a new API User type | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-275 | FF-275 | FF-271 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-55 | FF-55 | Loader is missing on the Loss Gain Charts | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-551 | FF-551 | Integrating i18n + 8 Languages Support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-500 | FF-500 | FF-498 | Sarmad Sabir | [5 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 8
https://octopusdtlsupport.atlassian.net/browse/FF-552 | FF-552 | Dashboard Language Change | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-500 | FF-500 | FF-498 | Sarmad Sabir | [5 empty] | 2026-05-28 | 2026-05-28 | 2026-04-28 | 2026-04-28 | 2
https://octopusdtlsupport.atlassian.net/browse/FF-553 | FF-553 | Alarms/Daily Deliveries/ Recon Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-500 | FF-500 | FF-498 | Sarmad Sabir | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 6
https://octopusdtlsupport.atlassian.net/browse/FF-554 | FF-554 | Nozzle/Stock/ Low Stock Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-500 | FF-500 | FF-498 | Sarmad Sabir | [5 empty] | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 6
https://octopusdtlsupport.atlassian.net/browse/FF-555 | FF-555 | Transactions/ Sales Target/Target Setup Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-500 | FF-500 | FF-498 | Sarmad Sabir | [5 empty] | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-30 | 10
https://octopusdtlsupport.atlassian.net/browse/FF-556 | FF-556 | Submit Data/ Daily Sales/ Loss Gain Charts Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-500 | FF-500 | FF-498 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-557 | FF-557 | My Profile/ Site Diag/ Notifications Group Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-500 | FF-500 | FF-498 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-56 | FF-56 | AS compared to SM 360 when user applies the Daily Sales filter the Fintech App showing values on the Loss Gain Chart in term of Money and on the other hand the SM 360 shows it in terms of Liters | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-57 | FF-57 | Kindly update the Date Time Filter as compared to SM 360 as currently it does not help the users | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-58 | FF-58 | The Tank filter should be dependent on Grade filter it should show only the tanks of the product selected. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-59 | FF-59 | Dashboard data for Revenue does not match with the Production data for Same time period applied on both environments | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-60 | FF-60 | In Recon Report every column should not be displayed in floating please verify it from Production as retail team has specified some column to be round off | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-61 | FF-61 | There is no such thing as Low Stock Alert Management as we do not manage any alerts regarding low stocks and secondly the columns mismatch as Capacity is missing Date column is missing threshold missing. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-62 | FF-62 | Sales data is not getting loaded against tank levels in Sales Target Module. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-63 | FF-63 | I have Applied Filter for Weekly Sales but the error is showing for Daily Sales | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-64 | FF-64 | I have set the Target for 10 days up to "500000" liters but the total target showing "5,150,000" Liters as in SM 360 the target is the total volume for the selected period not for a single day | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-65 | FF-65 | I Have set Target for Aramco Site but when i changed the filter to Total site the same targeted data is shown for Total as i have not set any targets for Total | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-66 | FF-66 | Success messages are not properly handled, please look into it | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-67 | FF-67 | Filter is not available for Recon Page and Nozzle Page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-68 | FF-68 | Username Field on login page accepts spaces which is in correct, please restrict it as its restricted while creating user. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-69 | FF-69 | Reset Password Validations are missing on Password and Confirm Password Fields, kindly apply validations | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-70 | FF-70 | new Sites for Total Parco got configured but some of the file of the sites landed in the exceptional folder, please look into it | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-71 | FF-71 | Increase the font size of the filter heading and dropdown text to ensure consistency with the other elements on the dashboard.” | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-72 | FF-72 | Never saw this column in Recon Report named "Variances" containing "Nan" values, please remove this and look into it why this appear | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-73 | FF-73 | Variance % and Cumulative Variances % column does not match with the Columns data for recon report with Production | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-74 | FF-74 | Spelling Mistake, please update cancel button spellings on the date Time Filter. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-75 | FF-75 | user is able to select the future Dates from the calendar in the filter, kindly restrict selecting future dates. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-76 | FF-76 | Export to excel is downloading empty file for Nozzle usage | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-77 | FF-77 | There are duplicate tanks named with "Site ID" With all the products in the stock level page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-78 | FF-78 | When user Clicks on the Deliveries page the page loads with a filter error "Please select both From and to date/time | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-79 | FF-79 | Kindly remove the Debug Info section from deliveries page. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-80 | FF-80 | kindly remove the floating datatype conversion from tanks column in the deliveries page. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-81 | FF-81 | Product names does not match with the Total Parco "gardenia filling station" Products in Low Stock Page. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-82 | FF-82 | The Low Stock page is not displaying accurate predictions under the “Product Wise” filter. Please review this issue, and also update the label from “Grade View” to “Product View”, along with updating the product names accordingly. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-83 | FF-83 | Bug: Alarms for the Aramco site “COCO-Liberty” are not being displayed. Muhammad Usman Javed has already processed the Aramco site data on the Staging ETL. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-84 | FF-84 | Kindly finalize which filter will be applicable on the Sales Target page — the first or the second — as discussed. One of the filters was supposed to be removed, but currently both are still visible. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-85 | FF-85 | The sales showing in the graph for "SALES and TARGET" GRAPH for the day "30 SEPT" is not matching with the sales data on the production | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-86 | FF-86 | Day End Sale Summary and Recon again not working as new filter is added previously it was working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-87 | FF-87 | Tank Filter is not working for Loss Gain Charts as its showing total sum of deliveries of a single product | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/FF-13 | FF-13 | FF-7 | kamran khalid | [5 empty] | 2025-10-16 | 2025-10-16 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/FF-96 | FF-96 | Features and Functionalities - Word/PDF Doc | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-95 | FF-95 | FF-1 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-98 | FF-98 | FuelChat - Development( Frontend + Backend) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-97 | FF-97 | FF-16 | Muhammad Ahmad Saleem | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/FF-99 | FF-99 | FuelChat - Visualization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/FF-97 | FF-97 | FF-16 | Muhammad Ahmad Saleem | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-10 | MN-10 | Keeps loading if you click integrations and no option to stop | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-104 | MN-104 | LoginPage | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-100 | MN-100 | MN-94 | Muhammad Abbas | [5 empty] | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 16
https://octopusdtlsupport.atlassian.net/browse/MN-106 | MN-106 | Login with Microsoft is Not Working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/MN-100 | MN-100 | MN-94 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-107 | MN-107 | User Management Module is Not Working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/MN-100 | MN-100 | MN-94 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-108 | MN-108 | Forgot Password Module is Failing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/MN-55 | MN-55 | MN-53 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-109 | MN-109 | 2FA is Not Implemented for All Users in Omni Chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-100 | MN-100 | MN-94 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-11 | MN-11 | Explanations button not working in chat page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1
https://octopusdtlsupport.atlassian.net/browse/MN-111 | MN-111 | Please change the Settings icon to a User Profile button and label it "User Profile. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-100 | MN-100 | MN-94 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-112 | MN-112 | MCP server architecture | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-110 | MN-110 | MN-1 | Hamza Ali | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-113 | MN-113 | Import mechanisms. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-110 | MN-110 | MN-1 | Hamza Ali | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-114 | MN-114 | Direct connection model | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-110 | MN-110 | MN-1 | Hamza Ali | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-117 | MN-117 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-86 | MN-86 | MN-78 | Muhammad Abbas | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-118 | MN-118 | Text adjustment in chat input (Known Bug) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/MN-119 | MN-119 | Keeps loading if you click integrations and no option to stop (Known Bug) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2.5
https://octopusdtlsupport.atlassian.net/browse/MN-12 | MN-12 | Cant connect tables with spaces in Direct Connection | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-120 | MN-120 | Cant connect tables with spaces in Direct Connection (Known Bug) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 4
https://octopusdtlsupport.atlassian.net/browse/MN-122 | MN-122 | Meeting - March 5, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-121 | MN-121 | MN-78 | Taimur Zahid | [7 empty] | 2026-03-05 | 2026-03-05 | 2
https://octopusdtlsupport.atlassian.net/browse/MN-123 | MN-123 | Meeting - March 5, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-121 | MN-121 | MN-78 | Aiza Hamid | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2
https://octopusdtlsupport.atlassian.net/browse/MN-124 | MN-124 | Meeting - March 5, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-121 | MN-121 | MN-78 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-125 | MN-125 | Meeting - March 5, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-121 | MN-121 | MN-78 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-126 | MN-126 | Meeting - March 5, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-121 | MN-121 | MN-78 | Muhammad Abbas | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 1
https://octopusdtlsupport.atlassian.net/browse/MN-127 | MN-127 | Staging Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-95 | MN-95 | MN-78 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-128 | MN-128 | Delete chats | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-3 | MN-3 | MN-137 | Hamza Ali | [5 empty] | 2026-02-16 | 2026-02-17 | 2026-02-16 | 2026-02-17 | 16
https://octopusdtlsupport.atlassian.net/browse/MN-129 | MN-129 | User testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-3 | MN-3 | MN-137 | Hamza Ali | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-13 | MN-13 | Background Image changed | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 7
https://octopusdtlsupport.atlassian.net/browse/MN-130 | MN-130 | Missing Hierarchy Structure in UM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-5 | MN-5 | MN-139 | Hamza Ali | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-131 | MN-131 | Explanation button not working (Known bug) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 6.5
https://octopusdtlsupport.atlassian.net/browse/MN-133 | MN-133 | Staging Release Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-95 | MN-95 | MN-78 | Aiza Hamid | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 4.5
https://octopusdtlsupport.atlassian.net/browse/MN-138 | MN-138 | Yousaf's Onboarding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-2 | MN-2 | MN-1 | Syed Yousaf Qadri | [5 empty] | 2026-02-16 | 2026-02-27 | 2026-02-17 | 2026-02-20 | 32
https://octopusdtlsupport.atlassian.net/browse/MN-14 | MN-14 | Chat and icons changed | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-149 | MN-149 | Forgot Password Module Regression | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-148 | MN-148 | MN-147 | Namra Zahid | [5 empty] | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-15 | 16
https://octopusdtlsupport.atlassian.net/browse/MN-15 | MN-15 | KT session for code | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-150 | MN-150 | Login Module Regression | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-148 | MN-148 | MN-147 | Muhammad Abbas | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-151 | MN-151 | System accepts unregistered email and does not display proper error message | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/MN-148 | MN-148 | MN-147 | Aiza Hamid | [5 empty] | 2026-04-15 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/MN-152 | MN-152 | Input field does not enforce min/max length constraints | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/MN-148 | MN-148 | MN-147 | Aiza Hamid | [5 empty] | 2026-04-15 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/MN-154 | MN-154 | Mismatch in reset link expiration time between application and email | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/MN-148 | MN-148 | MN-147 | Aiza Hamid | [5 empty] | 2026-04-15 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/MN-155 | MN-155 | Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-144 | MN-144 | MN-142 | Aiza Hamid | [5 empty] | 2026-03-10 | 2026-03-27 | 2026-03-10 | 2026-03-24 | 53.5
https://octopusdtlsupport.atlassian.net/browse/MN-156 | MN-156 | Implementation of Forgot Password Module in Omni Chat Application | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-54 | MN-54 | MN-53 | Aiza Hamid | [7 empty] | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-16 | MN-16 | Understading of how the code works | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-160 | MN-160 | Graph resizing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-158 | MN-158 | MN-153 | Aiza Hamid | [5 empty] | 2026-04-16 | 2026-04-22 | 2026-04-20 | 2026-04-21 | 16
https://octopusdtlsupport.atlassian.net/browse/MN-17 | MN-17 | Flask and Jinja training | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-18 | MN-18 | Refactor code structure for improved readability and maintainability | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-19 | MN-19 | update SweetAlert2 color scheme to use a green palette | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-20 | MN-20 | Update and add image assets in static directory | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-21 | MN-21 | Handled navigation bar in Data and SOPs field for chat mode | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 4
https://octopusdtlsupport.atlassian.net/browse/MN-22 | MN-22 | Edited Feedback Report and Response Report | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 7
https://octopusdtlsupport.atlassian.net/browse/MN-23 | MN-23 | Positive Feedback also gets saved to be presented in Feedback Report page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-24 | MN-24 | Dark mode and Light mode color changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-25 | MN-25 | Separated navigation items for SOPs and Data | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5
https://octopusdtlsupport.atlassian.net/browse/MN-26 | MN-26 | Enhance UI elements and add keyboard shortcuts for improved user interaction | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 4
https://octopusdtlsupport.atlassian.net/browse/MN-27 | MN-27 | Enhance styling for FAQs and VM Manager | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 6
https://octopusdtlsupport.atlassian.net/browse/MN-28 | MN-28 | Enhanced file for Data Warehouse steps | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-44 | MN-44 | Requirement Gathering from URS | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-43 | MN-43 | MN-1 | Taimur Zahid | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-47 | MN-47 | Front-end Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-34 | MN-34 | MN-29 | Aiza Hamid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-48 | MN-48 | Function-App Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-34 | MN-34 | MN-29 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-49 | MN-49 | Open AI Integration and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-34 | MN-34 | MN-29 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-56 | MN-56 | Password Reset Functionality | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-54 | MN-54 | MN-53 | Aiza Hamid | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5
https://octopusdtlsupport.atlassian.net/browse/MN-57 | MN-57 | Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-54 | MN-54 | MN-53 | Aiza Hamid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-7 | MN-7 | Main Logo changed | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-70 | MN-70 | Password Reset through ACS functionality | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-71 | MN-71 | Meetings and Requirements finalization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-43 | MN-43 | MN-1 | Taimur Zahid | [5 empty] | 2026-02-17 | 2026-02-18 | 2026-02-17 | 2026-02-18 | 13
https://octopusdtlsupport.atlassian.net/browse/MN-72 | MN-72 | Ibhrahim's Onboarding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-2 | MN-2 | MN-1 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-73 | MN-73 | Hamza's Onboarding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-2 | MN-2 | MN-1 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-74 | MN-74 | Aiza's Onboarding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-2 | MN-2 | MN-1 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/MN-8 | MN-8 | LogIn page color scheme altered | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/MN-89 | MN-89 | OmniAgent logo addition | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 6.5
https://octopusdtlsupport.atlassian.net/browse/MN-9 | MN-9 | Text adjustment in chat input | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-6 | MN-6 | MN-78 | Aiza Hamid | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 4
https://octopusdtlsupport.atlassian.net/browse/MN-93 | MN-93 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-55 | MN-55 | MN-53 | Muhammad Abbas | [5 empty] | 2026-02-24 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/MN-96 | MN-96 | Staging Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-95 | MN-95 | MN-78 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 12
https://octopusdtlsupport.atlassian.net/browse/MN-97 | MN-97 | Staging Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-95 | MN-95 | MN-78 | Aiza Hamid | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2.5
https://octopusdtlsupport.atlassian.net/browse/MN-98 | MN-98 | Staging Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-95 | MN-95 | MN-78 | Taimur Zahid | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 6.5
https://octopusdtlsupport.atlassian.net/browse/MN-99 | MN-99 | SQA Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/MN-95 | MN-95 | MN-78 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1002 | O2-1002 | Create Assets, Tags, simulator, assign alerts | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-534 | O2-534 | O2-459 | Faiq Butt | [5 empty] | 2026-01-05 | 2026-01-09 | 2026-01-05 | 2026-01-05 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1003 | O2-1003 | Make Training Material | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-534 | O2-534 | O2-459 | Danish Rashid | [5 empty] | 2026-01-22 | 2026-01-28 | 2026-01-26 | 2026-01-30 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1004 | O2-1004 | Latest Values Not Populating for Calculated Tag (Boolean Type) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1017 | O2-1017 | ADE / APXH Improvements Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Muhammad Abdul Wasi | [5 empty] | 2026-01-05 | 2026-01-30 | 2026-02-06 | 2026-02-10 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1037 | O2-1037 | All Countries Are Not Displayed in Country Dropdown While Creating or Editing Customer and Site | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1038 | O2-1038 | Tag Level Diagnostics Checkbox Missing in Notification Group | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1039 | O2-1039 | System Alarm Message Inconsistency Between Ashghal and Production Blue | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Faiza Nasir | [7 empty] | 2026-01-22 | 2026-01-22 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1040 | O2-1040 | System Alarms Not Displayed for UserDefinedFunctions and UserDefinedTables | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Muhammad Usman Javed | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1053 | O2-1053 | UI Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Arslan sohail | [5 empty] | 2026-01-07 | 2026-01-09 | 2026-01-07 | 2026-01-09 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1054 | O2-1054 | Frontend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Arslan sohail | [5 empty] | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1055 | O2-1055 | Backend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Syed Yousaf Qadri | [5 empty] | 2026-01-07 | 2026-01-19 | 2026-01-08 | 2026-01-19 | 64
https://octopusdtlsupport.atlassian.net/browse/O2-1056 | O2-1056 | End to end Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Syed Yousaf Qadri | [5 empty] | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1057 | O2-1057 | Finalise Taglist | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1045 | O2-1045 | O2-1044 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1059 | O2-1059 | Latest Values Not Updating for Real-Time Tags Even After Publishing Changes | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1062 | O2-1062 | Unable to view associated assets against single area after coming back from folder view in asset hierarchy. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1064 | O2-1064 | Write back is FAIL. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Mohsin Junaid | [7 empty] | 2026-01-26 | 2026-01-26 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1068 | O2-1068 | Source tags of MQTT device are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Muhammad Yousha Agha | [7 empty] | 2026-01-12 | 2026-01-30 | 72
https://octopusdtlsupport.atlassian.net/browse/O2-1071 | O2-1071 | User Defined Notifications are not getting received. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Faiza Nasir | [7 empty] | 2026-01-26 | 2026-01-26 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1072 | O2-1072 | Totalizer tag's values are not getting received | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Mohsin Junaid | [7 empty] | 2026-01-26 | 2026-01-26 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1073 | O2-1073 | Unable to create timer and counter tags | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Mohsin Junaid | [7 empty] | 2026-01-23 | 2026-01-23 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1074 | O2-1074 | Calculated tag latest values are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1075 | O2-1075 | Latest Values Not Populating for Ingestion Format Devices | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1076 | O2-1076 | Diagnostics Alarm Emails Are Not Being Received | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1077 | O2-1077 | User Defined Function" and "UserDefined Table" is missing from roles and permissions of ASHGHAL | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Muhammad Usman Javed | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1079 | O2-1079 | Permissions are not working according to the given access for all types of users. showing the actions to be performed while permissions were off for Create and Update, Delete Both Userdefined Function and Userdefined Table | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Arslan sohail | [7 empty] | 2026-01-23 | 2026-01-26 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1080 | O2-1080 | AM/PM Missing from Date-Time Filter on Diagnostics Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1081 | O2-1081 | Csv Bulk Import Success in blobs but no update in file status | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Hassan Saeed Wattoo | [7 empty] | 2026-01-23 | 2026-01-23 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1084 | O2-1084 | Tag Count Shows Zero After Scheduling Scan on IoT Flatten and MQTT InHand Devices | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1089 | O2-1089 | The "Single X,y-Axis Chart" is not available to be selected on Ashghal | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1091 | O2-1091 | Production data mapping and bug fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1090 | O2-1090 | O2-887 | Faiza Nasir | [7 empty] | 2026-01-23 | 2026-01-24 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-1094 | O2-1094 | OC Process Testing (staging & Production) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1090 | O2-1090 | O2-887 | Mariam Zulfiqar | [5 empty] | 2026-01-22 | 2026-01-26 | 2026-01-23 | 2026-01-26 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1096 | O2-1096 | KT of VFD Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1097 | O2-1097 | Code Understanding(Research) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1098 | O2-1098 | Code Understanding+ Created New Component | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1099 | O2-1099 | Code Understanding+ Started Integrated Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1100 | O2-1100 | Integrated VFD Performance Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1101 | O2-1101 | Error is getting displayed with success message right after going to the "Data Selection" screen. only on VPC | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Ali Qumail | [7 empty] | 2026-01-27 | 2026-01-27 | 9
https://octopusdtlsupport.atlassian.net/browse/O2-1102 | O2-1102 | Tested Complete VFD Dashboard + Fix Issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1103 | O2-1103 | Testing + QA Handover + Fix Issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1107 | O2-1107 | Support - Process team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1090 | O2-1090 | O2-887 | Faiza Nasir | [7 empty] | 2026-01-26 | 2026-01-26 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-1108 | O2-1108 | SQL Fail, just pipelines are getting created, No monitoring results are here to show no Data in SQL server. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Syed Yousaf Qadri | [7 empty] | 2026-01-27 | 2026-01-27 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1114 | O2-1114 | Invalid data is getting displayed in Site Hierarchy, against SQL pipelines | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Aiza Hamid | [7 empty] | 2026-01-27 | 2026-01-27 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1127 | O2-1127 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | kamran khalid | [5 empty] | 2026-02-02 | 2026-02-05 | 2026-02-02 | 2026-02-04 | 27
https://octopusdtlsupport.atlassian.net/browse/O2-1128 | O2-1128 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Abbas | [5 empty] | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1129 | O2-1129 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Waqar Rasheed | [5 empty] | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1130 | O2-1130 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Zeeshan Sarwar | [5 empty] | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1157 | O2-1157 | Working on pointer logic | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-850 | O2-850 | O2-199 | Syed Yousaf Qadri | [5 empty] | 2026-01-05 | 2026-01-07 | 2026-01-05 | 2026-01-06 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1159 | O2-1159 | Deduplication | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-850 | O2-850 | O2-199 | awais akhter | [7 empty] | 2026-01-01 | 2026-01-05 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1160 | O2-1160 | Testing and Vaidation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-850 | O2-850 | O2-199 | kamran khalid | [5 empty] | 2026-01-06 | 2026-02-09 | 2026-01-06 | 2026-01-08 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1161 | O2-1161 | Key Vaults and Deployments | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-945 | O2-945 | O2-941 | Syed Yousaf Qadri | [7 empty] | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1162 | O2-1162 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1163 | O2-1163 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | kamran khalid | [5 empty] | 2026-02-27 | 2026-03-03 | 2026-01-28 | 2026-02-13 | 34
https://octopusdtlsupport.atlassian.net/browse/O2-1167 | O2-1167 | Data Points Not Displayed on Sites Screen While Creating a New Site Until Page Refresh | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Zain Munir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-1169 | O2-1169 | Scripting and Planning for Backward Compatibility | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Syed Yousaf Qadri | [7 empty] | 2026-01-28 | 2026-02-02 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1170 | O2-1170 | Testing/ Bug Resolving | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Syed Yousaf Qadri | [7 empty] | 2026-01-30 | 2026-02-06 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1172 | O2-1172 | Stopped insertion in SQL database in all function apps | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | O2-1171 | O2-37 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1173 | O2-1173 | Update Read API payload to fetch the data from ADX database tables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | O2-1171 | O2-37 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1174 | O2-1174 | Read APi integeration at omniconnect backend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | O2-1171 | O2-37 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1175 | O2-1175 | Testing the Read API functionality from anomaly detection results module on omniconnect | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | O2-1171 | O2-37 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1176 | O2-1176 | Research/Discussion for Solution | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-514 | O2-514 | O2-457 | Zain Munir | [5 empty] | 2026-01-26 | 2026-01-30 | 2026-01-26 | 2026-01-30 | 29
https://octopusdtlsupport.atlassian.net/browse/O2-1178 | O2-1178 | GPS Tag Live Values Are Not Populating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1180 | O2-1180 | APX Health Operating System not displaying appropriate values | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1179 | O2-1179 | O2-887 | Faiza Nasir | [7 empty] | 2026-01-28 | 2026-01-28 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1182 | O2-1182 | Added details for IP Meeting , Coordination with Hassan Malik | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1181 | O2-1181 | O2-798 | Faiza Nasir | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-1184 | O2-1184 | Cloned batch job does not display the source (parent) job name after editing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Arslan sohail | [7 empty] | 2026-02-03 | 2026-02-03 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1185 | O2-1185 | CSV download generates an empty file in the Batch Compute module | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Arslan sohail | [7 empty] | 2026-02-03 | 2026-02-03 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-1186 | O2-1186 | QA + Fix Issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1188 | O2-1188 | User-defined function appears in Batch Query window but not on User Defined Function page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Arslan sohail | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1189 | O2-1189 | System does not restrict adding new entities to a user-defined table used by an active batch job | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Arslan sohail | [7 empty] | 2026-02-03 | 2026-02-04 | 11
https://octopusdtlsupport.atlassian.net/browse/O2-1190 | O2-1190 | Live Values Not Populating for Real-Time Tags Created via Import Site Layout | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1192 | O2-1192 | In BATCH /BPM Activity output or Batch job result is not showing updated results according to the query after 1 day | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Arslan sohail | [7 empty] | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1193 | O2-1193 | Research on using different Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-514 | O2-514 | O2-457 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1194 | O2-1194 | Discussion on All PPT Dashboard Files | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-514 | O2-514 | O2-457 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1195 | O2-1195 | OC Process Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1110 | O2-1110 | O2-887 | Mariam Zulfiqar | [5 empty] | 2026-01-26 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1197 | O2-1197 | APX implementation for 10 pumps | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | O2-1196 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-01-28 | 2026-02-03 | 2026-01-26 | 2026-02-04 | 35.5
https://octopusdtlsupport.atlassian.net/browse/O2-1198 | O2-1198 | Work-around for missing tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | O2-1196 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-01-28 | 2026-01-30 | 2026-01-28 | 2026-02-03 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1202 | O2-1202 | Totalizer Tag Values Not Updating While Calculated Tag Values Are Updating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1220 | O2-1220 | apx demo data preparation using OmniConnect csv bulk import | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | O2-1196 | O2-221 | Mohsin Junaid | [5 empty] | 2026-01-29 | 2026-01-31 | 2026-01-29 | 2026-02-03 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1221 | O2-1221 | apx demo data preparation using OC batch compute and scheduled import | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | O2-1196 | O2-221 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1222 | O2-1222 | Tag Values Not Updating for MQTT Devices and Not Populating for IoT Devices | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1223 | O2-1223 | Unknown error is occurring multiple times please look into this | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1224 | O2-1224 | New Password Field Validation Message Mismatch on Reset Password Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Zain Munir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-1225 | O2-1225 | GPS Tag Latest Values Not Populating for Any Device on Staging Sub-Site | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1228 | O2-1228 | Publish Changes Functionality Is Not Working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1229 | O2-1229 | Spaces Removed Automatically When Pasting Text into Calculated Tag Condition | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1230 | O2-1230 | Make Unit Field Optional for Calculated Tags Across the Application | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1231 | O2-1231 | Timer Tag Alarms has not been triggered as values was populated | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1232 | O2-1232 | Dashboard Template Builder UI & API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-515 | O2-515 | O2-457 | Zain Munir | [5 empty] | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 14
https://octopusdtlsupport.atlassian.net/browse/O2-1233 | O2-1233 | Unknown API failure occurs when navigating back to Site Listing page from Site home page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1234 | O2-1234 | Latest tag values are populated for newly replicated IoT device created via Bulk Device Replication without getting configured | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1235 | O2-1235 | Internal Server Error Occurs While Creating a Conditional Calculated Tag | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1237 | O2-1237 | Write Back MQTT Simulator Is Not Working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Yousha Agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1238 | O2-1238 | Latest Values Not Updating for Parameters on Write Back and Bulk Write Back Screens | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1239 | O2-1239 | Complete list of mapped tags is not displaying against APX health asset as well as it is displaying some output cal tags against performance asset. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1240 | O2-1240 | Unable to fetch data for a specific time period against health asset. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1241 | O2-1241 | Real time tag values for both IOT, MQTT against flatten and inhand are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1242 | O2-1242 | Device Diagnostics Functionality Is Not Working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Yousha Agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1243 | O2-1243 | Anomaly results are not completely exported to excel file. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1244 | O2-1244 | Need to display Is Global checkbox while editing a formula only in that SI where respective formula is created | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1245 | O2-1245 | User created Asset type, Subtype and variable in formula library should be restricted only for specific SI except for global asset type, sub type and variable that are uneditable. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1246 | O2-1246 | Conditional Calculated Tag Cannot Be Deleted Due to Incorrect Dependency Validation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1248 | O2-1248 | Certificate Expiry Notification Received but Email Not Delivered | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | O2-1125 | O2-810 | Muhammad Usman Javed | [5 empty] | 2026-02-11 | 2026-02-12 | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1256 | O2-1256 | Process pre-sales support, Customer / Management Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | O2-1066 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-02-02 | 2026-02-27 | 2026-02-02 | 2026-02-27 | 31.5
https://octopusdtlsupport.atlassian.net/browse/O2-1261 | O2-1261 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | O2-1260 | O2-810 | kamran khalid | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1262 | O2-1262 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | O2-1260 | O2-810 | Muhammad Abbas | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1263 | O2-1263 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | O2-1260 | O2-810 | Zeeshan Sarwar | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1264 | O2-1264 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | O2-1260 | O2-810 | Namra Zahid | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1267 | O2-1267 | Backend API's Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-514 | O2-514 | O2-457 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-28 | 2026-02-02 | 2026-01-28 | 2026-01-30 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1268 | O2-1268 | Failed to Login with microsoft | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | O2-1260 | O2-810 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1270 | O2-1270 | MQTT flatten real time tag values are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | O2-1260 | O2-810 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1271 | O2-1271 | Models are not creating in user defined anomaly group where as data for specified time duration is displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | O2-1260 | O2-810 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1275 | O2-1275 | Requirement gathering and management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-514 | O2-514 | O2-457 | Ameer Hamza Khan | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-01-28 | 2026-02-02 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1277 | O2-1277 | SFTP OT wide support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1168 | O2-1168 | O2-199 | Hamza Ali | [5 empty] | 2026-02-02 | 2026-02-03 | 2026-02-02 | 2026-02-03 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1278 | O2-1278 | RestApi OT wide support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1168 | O2-1168 | O2-199 | Hamza Ali | [5 empty] | 2026-02-04 | 2026-02-06 | 2026-02-04 | 2026-02-06 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1279 | O2-1279 | SQL OT wide support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1168 | O2-1168 | O2-199 | Hamza Ali | [5 empty] | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1280 | O2-1280 | Bug Fixing, Improvements and Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | ahad omer | [5 empty] | 2026-01-20 | 2026-01-26 | 2026-02-02 | 2026-02-10 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1281 | O2-1281 | February Productivity Report - Planning and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1283 | O2-1283 | Check PS32A values scaling loss issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | O2-1196 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-02-10 | 2026-02-12 | 2026-02-10 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1284 | O2-1284 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Muhammad Abbas | [5 empty] | 2026-02-11 | 2026-02-17 | 2026-02-11 | 2026-02-17 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1294 | O2-1294 | API Update for Performance Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-515 | O2-515 | O2-457 | Zain Munir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-1295 | O2-1295 | Structure for Dashboard from Template Dev OC Frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-515 | O2-515 | O2-457 | Zain Munir | [5 empty] | 2026-02-09 | 2026-02-11 | 2026-02-09 | 2026-02-11 | 18
https://octopusdtlsupport.atlassian.net/browse/O2-1296 | O2-1296 | Read API integration for historic data display on dashboard graphs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-515 | O2-515 | O2-457 | Zain Munir | [5 empty] | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-13 | 12.5
https://octopusdtlsupport.atlassian.net/browse/O2-1313 | O2-1313 | Model is not getting created for anomaly "User train" group, its showing error. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1314 | O2-1314 | real streaming - urs - streaming RnD feasibility on ADX cluster | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-788 | O2-788 | O2-793 | Mohsin Junaid | [5 empty] | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-07 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1315 | O2-1315 | real streaming - urs - RnD of Function Apps working on streaming | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-788 | O2-788 | O2-793 | Mohsin Junaid | [5 empty] | 2026-01-01 | 2026-01-05 | 2026-01-01 | 2026-01-05 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1316 | O2-1316 | real streaming - urs - Rnd of Azure Eventhubs related to streaming | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-788 | O2-788 | O2-793 | Mohsin Junaid | [5 empty] | 2026-01-08 | 2026-01-09 | 2026-01-08 | 2026-01-09 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1317 | O2-1317 | real streaming - urs - Communication between Azure Eventhub - Functions Apps- ADX database | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-788 | O2-788 | O2-793 | Mohsin Junaid | [5 empty] | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1322 | O2-1322 | cal tags no code - dev - Calculated tags unconditional | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-700 | O2-700 | O2-697 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1323 | O2-1323 | cal tags no code - dev - Calculated tags conditional | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-700 | O2-700 | O2-697 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1324 | O2-1324 | cal tags no code - dev - Timer Tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-700 | O2-700 | O2-697 | Mohsin Junaid | [7 empty] | 2026-02-19 | 2026-02-19 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1325 | O2-1325 | cal tags no code - dev - Counter Tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-700 | O2-700 | O2-697 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1326 | O2-1326 | cal tags no code - dev - Totalizer Tags Real | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-700 | O2-700 | O2-697 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1327 | O2-1327 | cal tags no code - dev - Totalizer Tags Calc | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-700 | O2-700 | O2-697 | Mohsin Junaid | [5 empty] | 2026-02-16 | 2026-02-20 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1328 | O2-1328 | real streaming - dev - function app just code testing with reals | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-789 | O2-789 | O2-793 | Mohsin Junaid | [5 empty] | 2026-02-04 | 2026-02-06 | 2026-02-04 | 2026-02-24 | 22.5
https://octopusdtlsupport.atlassian.net/browse/O2-1329 | O2-1329 | real streaming - dev - function app python code optimization of data outgoing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-789 | O2-789 | O2-793 | Mohsin Junaid | [5 empty] | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1330 | O2-1330 | real streaming - dev - function app just polars implementaion in real tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-789 | O2-789 | O2-793 | Mohsin Junaid | [5 empty] | 2026-02-11 | 2026-02-13 | 2026-02-11 | 2026-02-23 | 22.5
https://octopusdtlsupport.atlassian.net/browse/O2-1331 | O2-1331 | real streaming - dev - function app OPC,IOT,MQTT device compatibility of real | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-789 | O2-789 | O2-793 | Ayyan Babar | [7 empty] | 2026-02-13 | 2026-02-27 | 83.5
https://octopusdtlsupport.atlassian.net/browse/O2-1332 | O2-1332 | real streaming - dev - function app handling datatypes of real tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-789 | O2-789 | O2-793 | Mohsin Junaid | [7 empty] | 2026-03-03 | 2026-03-13 | 58.5
https://octopusdtlsupport.atlassian.net/browse/O2-1333 | O2-1333 | real streaming - dev - real tag implementation automation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-789 | O2-789 | O2-793 | Ayyan Babar | [5 empty] | 2026-02-02 | 2026-03-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1334 | O2-1334 | real streaming - urs - multiInstance scaling in function apps | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-788 | O2-788 | O2-793 | Mohsin Junaid | [5 empty] | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-16 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1336 | O2-1336 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | O2-1335 | O2-810 | kamran khalid | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 17
https://octopusdtlsupport.atlassian.net/browse/O2-1337 | O2-1337 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | O2-1335 | O2-810 | Waqar Rasheed | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1338 | O2-1338 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | O2-1335 | O2-810 | Zeeshan Sarwar | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1339 | O2-1339 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | O2-1335 | O2-810 | Namra Zahid | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1346 | O2-1346 | Site Configuration Manager API: Tag Catalog | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1347 | O2-1347 | Researching against OpenAI practices | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1344 | O2-1344 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1348 | O2-1348 | Researching Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1344 | O2-1344 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-05 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1349 | O2-1349 | Site Configuration Manager API: Custom Table Catalog | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1350 | O2-1350 | Site Configuration Manager API: Anomaly Catalog | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1352 | O2-1352 | Tag Data Agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-10 | 2026-02-12 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1353 | O2-1353 | Custom Table Agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-10 | 2026-02-12 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1354 | O2-1354 | Security Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | O2-1219 | O2-133 | Taimur Zahid | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1355 | O2-1355 | Security Documentation Review and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | O2-1219 | O2-133 | Taimur Zahid | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1356 | O2-1356 | Security Architecture | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | O2-1219 | O2-133 | Taimur Zahid | [5 empty] | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-05 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1357 | O2-1357 | Security Architecture Review and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | O2-1219 | O2-133 | Taimur Zahid | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1363 | O2-1363 | cal tags no code - dev web - Dependency Matrix nested calculations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1362 | O2-1362 | O2-697 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1364 | O2-1364 | cal tags no code - dev - counter tag 2nd condition and reset condition | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1362 | O2-1362 | O2-697 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1365 | O2-1365 | Counter Tag | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-698 | O2-698 | O2-697 | Waqar Rasheed | [5 empty] | 2026-05-22 | 2026-05-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1366 | O2-1366 | Timer Tag | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-698 | O2-698 | O2-697 | Waqar Rasheed | [5 empty] | 2026-05-27 | 2026-05-29 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1367 | O2-1367 | Calculated Tag | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-698 | O2-698 | O2-697 | Muhammad Abbas | [5 empty] | 2026-05-22 | 2026-05-29 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1368 | O2-1368 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-517 | O2-517 | O2-457 | Zeeshan Sarwar | [5 empty] | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-03-02 | 37.5
https://octopusdtlsupport.atlassian.net/browse/O2-137 | O2-137 | Regression testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zeeshan Sarwar | [5 empty] | 2025-10-07 | 2025-10-14 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1376 | O2-1376 | Optimizing the chart rendering logic in html template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-515 | O2-515 | O2-457 | Zain Munir | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1379 | O2-1379 | cal tags no code - dev - prepare data locally for nested tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1362 | O2-1362 | O2-697 | Mohsin Junaid | [5 empty] | 2026-02-10 | 2026-02-20 | 2026-02-17 | 2026-02-20 | 14.5
https://octopusdtlsupport.atlassian.net/browse/O2-138 | O2-138 | Sanity testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [5 empty] | 2025-10-17 | 2025-10-20 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1383 | O2-1383 | Area Count Mismatch for “Subs_Sanity_BL W” Site in OmniAgent Data Analysis | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | O2-1335 | O2-810 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-03-09 | 2026-03-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1385 | O2-1385 | Reservation Activity | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1111 | O2-1111 | O2-1109 | Taimur Zahid | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1386 | O2-1386 | Kick-off Meeting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1115 | O2-1115 | O2-1109 | Taimur Zahid | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1387 | O2-1387 | Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1116 | O2-1116 | O2-1109 | Taimur Zahid | [5 empty] | 2026-01-27 | 2026-01-30 | 2026-01-27 | 2026-01-27 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1388 | O2-1388 | Utilization Management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1276 | O2-1276 | O2-1109 | Taimur Zahid | [5 empty] | 2026-02-06 | 2026-02-13 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1389 | O2-1389 | Key Vault Setup and Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Taimur Zahid | [5 empty] | 2025-10-01 | 2025-11-28 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1390 | O2-1390 | Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1203 | O2-1203 | O2-133 | Taimur Zahid | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1391 | O2-1391 | Diagram | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1203 | O2-1203 | O2-133 | Taimur Zahid | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1393 | O2-1393 | February 16, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | O2-1293 | O2-798 | Taimur Zahid | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1394 | O2-1394 | December EPR | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2025-12-01 | 2025-12-31 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1398 | O2-1398 | Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | O2-1397 | O2-457 | kamran khalid | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1399 | O2-1399 | Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | O2-1397 | O2-457 | Zeeshan Sarwar | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1400 | O2-1400 | Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | O2-1397 | O2-457 | Muhammad Abbas | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1401 | O2-1401 | Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | O2-1397 | O2-457 | Namra Zahid | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1402 | O2-1402 | waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | O2-1397 | O2-457 | Waqar Rasheed | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1406 | O2-1406 | Live Values Not Populating on Streaming for IoT and MQTT InHand Devices | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1407 | O2-1407 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Muhammad Abbas | [5 empty] | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-20 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1408 | O2-1408 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Zeeshan Sarwar | [5 empty] | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-20 | 14.5
https://octopusdtlsupport.atlassian.net/browse/O2-1409 | O2-1409 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Waqar Rasheed | [5 empty] | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-23 | 27.5
https://octopusdtlsupport.atlassian.net/browse/O2-1410 | O2-1410 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Namra Zahid | [5 empty] | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-20 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1411 | O2-1411 | Get latest values for both IOT and MQTT devices in write back module is not working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1412 | O2-1412 | Code Merging, Staging Deployment & Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-515 | O2-515 | O2-457 | Zain Munir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1414 | O2-1414 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1308 | O2-1308 | O2-1303 | Faiq Butt | [7 empty] | 2026-02-11 | 2026-02-20 | 39
https://octopusdtlsupport.atlassian.net/browse/O2-1415 | O2-1415 | Make Training Material (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-502 | O2-502 | O2-37 | DANIYAL AHMAD | [5 empty] | 2026-01-01 | 2026-01-30 | 2026-01-05 | 2026-01-14 | 64
https://octopusdtlsupport.atlassian.net/browse/O2-1416 | O2-1416 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-997 | O2-997 | O2-992 | Faiq Butt | [5 empty] | 2026-02-06 | 2026-02-10 | 2026-02-06 | 2026-02-10 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1417 | O2-1417 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-446 | O2-446 | O2-441 | Danish Rashid | [5 empty] | 2026-01-19 | 2026-01-21 | 2026-01-21 | 2026-01-23 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1418 | O2-1418 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1010 | O2-1010 | O2-1005 | Faiq Butt | [5 empty] | 2026-01-30 | 2026-02-04 | 2026-01-30 | 2026-02-04 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1419 | O2-1419 | Tags, Groups, FMEA, Alerts Update | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-529 | O2-529 | O2-459 | Danish Rashid | [5 empty] | 2025-12-26 | 2026-01-07 | 2026-01-01 | 2026-01-09 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-142 | O2-142 | Schedule Pull from Rest API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [5 empty] | 2025-10-08 | 2025-10-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1420 | O2-1420 | Module Design Induction (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1029 | O2-1029 | O2-1028 | DANIYAL AHMAD | [5 empty] | 2026-01-15 | 2026-02-28 | 2026-01-15 | 2026-02-26 | 94
https://octopusdtlsupport.atlassian.net/browse/O2-1421 | O2-1421 | ADE utilisation on APX by OmniAgent Concept | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1015 | O2-1015 | O2-221 | Muhammad Abdul Wasi | [5 empty] | 2026-01-05 | 2026-01-29 | 2026-01-05 | 2026-01-16 | 64
https://octopusdtlsupport.atlassian.net/browse/O2-1422 | O2-1422 | Module Design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1045 | O2-1045 | O2-1044 | Danish Rashid | [5 empty] | 2025-12-15 | 2026-02-10 | 2026-02-02 | 2026-02-11 | 48
https://octopusdtlsupport.atlassian.net/browse/O2-1423 | O2-1423 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-478 | O2-478 | O2-453 | Faiq Butt | [5 empty] | 2026-01-27 | 2026-01-29 | 2026-01-27 | 2026-01-29 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1424 | O2-1424 | Template Update | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-530 | O2-530 | O2-459 | Danish Rashid | [5 empty] | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-03-02 | 31
https://octopusdtlsupport.atlassian.net/browse/O2-1425 | O2-1425 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1306 | O2-1306 | O2-1303 | DANIYAL AHMAD | [5 empty] | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-12 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1426 | O2-1426 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-413 | O2-413 | O2-408 | Faiq Butt | [5 empty] | 2026-01-21 | 2026-01-26 | 2026-01-21 | 2026-01-26 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1427 | O2-1427 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-403 | O2-403 | O2-398 | Faiq Butt | [5 empty] | 2026-01-15 | 2026-01-20 | 2026-01-15 | 2026-01-20 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1428 | O2-1428 | Asset Design, HB and Expected models (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-474 | O2-474 | O2-453 | Faiq Butt | [7 empty] | 2026-01-01 | 2026-01-02 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1429 | O2-1429 | Data Lake and Enterprise Connector in site status is not getting ready. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1430 | O2-1430 | APX Performance Module Training Material | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1016 | O2-1016 | O2-221 | Muhammad Abdul Wasi | [5 empty] | 2025-12-11 | 2026-01-30 | 2026-01-12 | 2026-02-13 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1431 | O2-1431 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-469 | O2-469 | O2-452 | Muhammad Abdul Wasi | [5 empty] | 2026-01-19 | 2026-01-23 | 2026-01-19 | 2026-01-23 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1432 | O2-1432 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1023 | O2-1023 | O2-1018 | Muhammad Abdul Wasi | [5 empty] | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-04 | 22
https://octopusdtlsupport.atlassian.net/browse/O2-1434 | O2-1434 | Green Environment resource creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1436 | O2-1436 | OmniOEE Pre-URS working (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1375 | O2-1375 | O2-1302 | Muhammad Abdul Wasi | [5 empty] | 2026-02-11 | 2026-02-23 | 2026-02-11 | 2026-02-19 | 38.5
https://octopusdtlsupport.atlassian.net/browse/O2-1442 | O2-1442 | SMS Opt-in: Number registration fails with a 403 Forbidden error. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Ameer Hamza Khan | [5 empty] | 2026-02-18 | 2026-02-19 | 2026-02-19 | 2026-02-20 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1443 | O2-1443 | Real-Time Tag Latest Values Not Showing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1445 | O2-1445 | real tag streaming - production release - backward compatible (connecting IOThubs with evenhub and function app) so that original flow is not altered and monitor function apps | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [5 empty] | 2026-01-12 | 2026-01-15 | 2026-03-16 | 2026-03-26 | 43.5
https://octopusdtlsupport.atlassian.net/browse/O2-1446 | O2-1446 | February 11, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | O2-1293 | O2-798 | Taimur Zahid | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1448 | O2-1448 | Green Enviroment Deployment Preparation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-701 | O2-701 | O2-697 | Mohsin Junaid | [5 empty] | 2026-03-10 | 2026-03-12 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1449 | O2-1449 | test production sites before backward compatibility | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-701 | O2-701 | O2-697 | Mohsin Junaid | [5 empty] | 2026-03-12 | 2026-03-16 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1450 | O2-1450 | making sites backward compatible | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-701 | O2-701 | O2-697 | Mohsin Junaid | [5 empty] | 2026-03-16 | 2026-03-17 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1451 | O2-1451 | deployment on blue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-701 | O2-701 | O2-697 | Mohsin Junaid | [5 empty] | 2026-03-11 | 2026-03-13 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1452 | O2-1452 | Write Back Is FAIL, Values are not getting updated | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-27 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1454 | O2-1454 | Impact Analysis | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | O2-1381 | O2-818 | ahad omer | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1455 | O2-1455 | POC Template Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | O2-1381 | O2-818 | ahad omer | [5 empty] | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1456 | O2-1456 | POC Template Variable Mapping | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | O2-1381 | O2-818 | Arslan sohail | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1457 | O2-1457 | Calculated Tag Latest Values Not Populating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1458 | O2-1458 | Impact Analysis | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | O2-1381 | O2-818 | Arslan sohail | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-147 | O2-147 | Modify Existing API For Connectors | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1471 | O2-1471 | OPC Device Real-Time Tag Latest Values Not Updated but Diagnostics Alarms Auto-Resolved | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1473 | O2-1473 | RBAC for OmniChat (aligned with OmniConnect/ReadAPI) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Aiza Hamid | [5 empty] | 2026-03-12 | 2026-03-16 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1474 | O2-1474 | OmniChat Database Changes to save OmniAgent Conversation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-03-09 | 2026-03-12 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1475 | O2-1475 | OmniAgent Payload Support for Clean Response - Part B | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-12 | 2026-03-13 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1476 | O2-1476 | OmniAgent Payload Support for Clean Response - Part A | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-02 | 2026-03-04 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1477 | O2-1477 | GPS Tag Latest Values Not Populating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1478 | O2-1478 | OmniAgent Database Changes to save OmniChat Conversations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-05 | 2026-03-10 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1479 | O2-1479 | Front-end Development - Chat window modifications | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Aiza Hamid | [5 empty] | 2026-02-26 | 2026-02-27 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-148 | O2-148 | Modify Existing API For Pipelines | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1480 | O2-1480 | Front-end Development - OmniAgent Button | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Aiza Hamid | [5 empty] | 2026-03-02 | 2026-03-10 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1481 | O2-1481 | Back-end Integration - Part A | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1482 | O2-1482 | Back-end Integration - Part B | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-03-16 | 2026-03-31 | 2026-03-16 | 2026-03-31 | 59.5
https://octopusdtlsupport.atlassian.net/browse/O2-1483 | O2-1483 | Loader Keeps Running After Clicking “Execute All and Save Output” and User Cannot Proceed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1484 | O2-1484 | MQTT values are not getting Updated | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Ayyan Babar | [5 empty] | 2026-02-19 | 2026-02-19 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1485 | O2-1485 | Dev Work | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-577 | O2-577 | O2-130 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1486 | O2-1486 | Cost Estimation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-254 | O2-254 | O2-133 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1487 | O2-1487 | Estimation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-253 | O2-253 | O2-1460 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1488 | O2-1488 | Authentication and Authorization Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-165 | O2-165 | O2-164 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-149 | O2-149 | Modify Existing API For Triggers | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1491 | O2-1491 | check PS32A invalid tags issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | O2-1196 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-1492 | O2-1492 | Process pre-sales support, Customer / Management Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | O2-1066 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-01-01 | 2026-01-30 | 2026-01-07 | 2026-01-30 | 26
https://octopusdtlsupport.atlassian.net/browse/O2-1497 | O2-1497 | Production Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-982 | O2-982 | O2-941 | Taimur Zahid | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1498 | O2-1498 | Process Eng. tasks: working, review and management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | O2-1254 | O2-1070 | Mariam Zulfiqar | [5 empty] | 2026-01-01 | 2026-01-30 | 2026-01-01 | 2026-01-30 | 131
https://octopusdtlsupport.atlassian.net/browse/O2-1499 | O2-1499 | Process Eng. tasks: working, review and management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | O2-1254 | O2-1070 | Mariam Zulfiqar | [5 empty] | 2026-02-02 | 2026-02-27 | 2026-02-02 | 2026-02-27 | 77
https://octopusdtlsupport.atlassian.net/browse/O2-150 | O2-150 | Modify Current SQL Schema | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1502 | O2-1502 | Longitude's value is missing whish is mandatory and being used in GPS, Kindly fix completely | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Mohsin Junaid | [5 empty] | 2026-02-20 | 2026-02-20 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1503 | O2-1503 | OmniChat Integration with OmniAgent DDS - Hamza Ali | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1462 | O2-1462 | O2-1461 | Hamza Ali | [5 empty] | 2026-02-23 | 2026-02-26 | 2026-02-23 | 2026-02-26 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1504 | O2-1504 | OmniChat Integration with OmniAgent DDS - Aiza Hamid | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1462 | O2-1462 | O2-1461 | Aiza Hamid | [5 empty] | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 10
https://octopusdtlsupport.atlassian.net/browse/O2-1507 | O2-1507 | Production Release - Hamza Ali | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | O2-1506 | O2-1461 | Hamza Ali | [5 empty] | 2026-03-25 | 2026-03-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1508 | O2-1508 | Production Release - Aiza Hamid | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | O2-1506 | O2-1461 | Aiza Hamid | [5 empty] | 2026-03-25 | 2026-03-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1509 | O2-1509 | Production Release - Ibrahim A. Qureshi | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | O2-1506 | O2-1461 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-25 | 2026-03-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1510 | O2-1510 | SQA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1469 | O2-1469 | O2-1461 | Namra Zahid | [5 empty] | 2026-03-17 | 2026-03-23 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1511 | O2-1511 | Documentation Task | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1470 | O2-1470 | O2-1461 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1512 | O2-1512 | Production Release Testing - Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | O2-1506 | O2-1461 | Muhammad Abbas | [5 empty] | 2026-03-24 | 2026-03-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1513 | O2-1513 | Production Release - Taimur | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | O2-1506 | O2-1461 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1514 | O2-1514 | Production Release Testing - Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | O2-1506 | O2-1461 | kamran khalid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1515 | O2-1515 | Unable to create ODBC pipeline system showing error "database not found" | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1516 | O2-1516 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | kamran khalid | [5 empty] | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-20 | 7
https://octopusdtlsupport.atlassian.net/browse/O2-1517 | O2-1517 | Schema Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | O2-1381 | O2-818 | Syed Yousaf Qadri | [5 empty] | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1518 | O2-1518 | Bpm Batch Engine Impact | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | O2-1381 | O2-818 | Syed Yousaf Qadri | [5 empty] | 2026-02-13 | 2026-02-16 | 2026-02-13 | 2026-02-16 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1519 | O2-1519 | Latest Values not populating for tags created from import site layout | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1527 | O2-1527 | Database Migration and Dashboard Mapping | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1093 | O2-1093 | O2-887 | Zain Munir | [5 empty] | 2026-01-23 | 2026-01-26 | 2026-01-23 | 2026-01-26 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1530 | O2-1530 | Asghal Deployment /Release Management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1110 | O2-1110 | O2-887 | Faiza Nasir | [5 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-1533 | O2-1533 | Optimized queries for Read API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | O2-1532 | O2-1525 | Aiza Hamid | [5 empty] | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1534 | O2-1534 | Updated stored procedure for hierarchies | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | O2-1532 | O2-1525 | Aiza Hamid | [5 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1535 | O2-1535 | February 19, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | O2-1293 | O2-798 | Taimur Zahid | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1536 | O2-1536 | Updated custom table schemas query to add description | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | O2-1532 | O2-1525 | Aiza Hamid | [5 empty] | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1537 | O2-1537 | February 20, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | O2-1293 | O2-798 | Taimur Zahid | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1538 | O2-1538 | February 23, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | O2-1293 | O2-798 | Taimur Zahid | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1539 | O2-1539 | Read API ADX Query Optimization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | O2-1532 | O2-1525 | Aiza Hamid | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1541 | O2-1541 | Added support for wide and long response layouts | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1134 | O2-1134 | O2-1523 | Aiza Hamid | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1542 | O2-1542 | Added support for nanoseconds and micro seconds in timestamps (start and end timestamps) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1133 | O2-1133 | O2-1521 | Aiza Hamid | [5 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1544 | O2-1544 | Handling API Calls for Deleted Sites | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | O2-1500 | O2-1453 | Aiza Hamid | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1547 | O2-1547 | APX Health multiple asset configuration (ADE) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | O2-1546 | O2-1545 | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1548 | O2-1548 | APX Health multiple asset configuration (APXE) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | O2-1546 | O2-1545 | Arsalan Zafar Khan | [5 empty] | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1551 | O2-1551 | Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | O2-1546 | O2-1545 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1552 | O2-1552 | Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | O2-1546 | O2-1545 | Danish Rashid | [5 empty] | 2026-02-23 | 2026-02-25 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1554 | O2-1554 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1501 | O2-1501 | O2-1453 | Muhammad Abbas | [5 empty] | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-24 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1555 | O2-1555 | Filtering Response for Anomaly Predictors Values | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1553 | O2-1553 | O2-37 | Aiza Hamid | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1556 | O2-1556 | Updated Correlation Matrix for Anomaly Configuration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1553 | O2-1553 | O2-37 | Aiza Hamid | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1557 | O2-1557 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1522 | O2-1522 | O2-1521 | Muhammad Abbas | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1558 | O2-1558 | Testing By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1540 | O2-1540 | O2-1525 | Muhammad Abbas | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1559 | O2-1559 | Testing By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1524 | O2-1524 | O2-1523 | Muhammad Abbas | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1561 | O2-1561 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1560 | O2-1560 | O2-1453 | Muhammad Abbas | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1563 | O2-1563 | Added host in ReadAPI and response format for all tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1562 | O2-1562 | O2-1340 | Aiza Hamid | [5 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1564 | O2-1564 | Read API is Returning internal server error after latest deployment | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | O2-1500 | O2-1453 | Aiza Hamid | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1565 | O2-1565 | Code Refactoring | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | O2-1532 | O2-1525 | Aiza Hamid | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1567 | O2-1567 | Dev | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1566 | O2-1566 | O2-1525 | Aiza Hamid | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1568 | O2-1568 | SQA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1566 | O2-1566 | O2-1525 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1569 | O2-1569 | Integrated the new required changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-848 | O2-848 | O2-37 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1570 | O2-1570 | Requirement gathering + Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-848 | O2-848 | O2-37 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1572 | O2-1572 | Testing of API's | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-514 | O2-514 | O2-457 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-1574 | O2-1574 | Incase of Real-Stat Read API is returning R-Mapped name instead of user-friendly name even user-friendly parameter is set to true | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | O2-1500 | O2-1453 | Aiza Hamid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1577 | O2-1577 | latest values are not being populated for MQTT (default format) and OPC devices. Real-time and GPS tags on the newly created site | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1578 | O2-1578 | IOT,MQTT inhand latest values are not populating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1579 | O2-1579 | Reservation task | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1214 | O2-1214 | O2-1109 | Usama Tariq | [7 empty] | 2026-01-30 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1580 | O2-1580 | Rservation Renewel | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1214 | O2-1214 | O2-1109 | Taimur Zahid | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1581 | O2-1581 | Filtering Response for Anomaly Predicted Values | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1553 | O2-1553 | O2-37 | Aiza Hamid | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1582 | O2-1582 | Unauthorized Tag Data Accessible via Read API | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | O2-1500 | O2-1453 | Aiza Hamid | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1583 | O2-1583 | Site Configuration Manager: Alarm Catalog | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1584 | O2-1584 | Anomaly Data Agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-16 | 2026-02-20 | 2026-02-19 | 2026-02-25 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-1585 | O2-1585 | OmniConnect_Revamp_(UI/UX)_ Variation_01 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-01-15 | 2026-01-24 | 2026-01-15 | 2026-01-23 | 56
https://octopusdtlsupport.atlassian.net/browse/O2-1586 | O2-1586 | OmniConnect_ Revamp_(UI/UX)_ Variation_ 02_ Part A | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-01-26 | 2026-01-30 | 2026-01-26 | 2026-01-30 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1587 | O2-1587 | OmniConnect_Revamp_(UI/UX)_ Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-02-09 | 2026-02-16 | 2026-02-09 | 2026-02-13 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1589 | O2-1589 | OmniConnect- Dashboard Design + 4 layers Design (UX/UI) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-02-19 | 2026-02-25 | 2026-02-19 | 2026-02-25 | 32.5
https://octopusdtlsupport.atlassian.net/browse/O2-1590 | O2-1590 | OC template (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-427 | O2-427 | O2-418 | DANIYAL AHMAD | [5 empty] | 2026-02-23 | 2026-02-26 | 2026-02-23 | 2026-02-25 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-1591 | O2-1591 | Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-427 | O2-427 | O2-418 | DANIYAL AHMAD | [5 empty] | 2026-02-25 | 2026-03-03 | 2026-02-25 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1592 | O2-1592 | Deleted Sites' Record | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | O2-1500 | O2-1453 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-17 | 2026-02-18 | 2026-02-17 | 2026-02-18 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1597 | O2-1597 | Ashghal demo support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1596 | O2-1596 | O2-1595 | Danish Rashid | [5 empty] | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1599 | O2-1599 | Marketing team support for APX | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | O2-1598 | O2-1595 | Danish Rashid | [5 empty] | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-04 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1600 | O2-1600 | Health module marketing video update | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | O2-1598 | O2-1595 | Danish Rashid | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1601 | O2-1601 | MPCL ADE demo support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | O2-1598 | O2-1595 | DANIYAL AHMAD | [5 empty] | 2026-02-05 | 2026-02-27 | 2026-02-06 | 2026-02-19 | 10
https://octopusdtlsupport.atlassian.net/browse/O2-1602 | O2-1602 | MPCL data review for demo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | O2-1598 | O2-1595 | Muhammad Abdul Wasi | [5 empty] | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-04 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1605 | O2-1605 | OC template (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-473 | O2-473 | O2-452 | Muhammad Abdul Wasi | [5 empty] | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1606 | O2-1606 | Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-473 | O2-473 | O2-452 | Muhammad Abdul Wasi | [5 empty] | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-27 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-1607 | O2-1607 | February 25,2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | O2-1293 | O2-798 | Aiza Hamid | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1608 | O2-1608 | real-streaming-dev-UnitTesting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-789 | O2-789 | O2-793 | Mohsin Junaid | [5 empty] | 2026-02-25 | 2026-02-28 | 2026-02-25 | 2026-03-13 | 71.5
https://octopusdtlsupport.atlassian.net/browse/O2-1609 | O2-1609 | Deployment to Production and Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1560 | O2-1560 | O2-1453 | Aiza Hamid | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1610 | O2-1610 | Alarm Data Agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-03-04 | 36
https://octopusdtlsupport.atlassian.net/browse/O2-1611 | O2-1611 | OC Template (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-407 | O2-407 | O2-398 | Faiq Butt | [7 empty] | 2026-02-24 | 2026-02-25 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1612 | O2-1612 | Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-407 | O2-407 | O2-398 | Faiq Butt | [7 empty] | 2026-02-24 | 2026-02-25 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1615 | O2-1615 | OC Template (P)- Faiq | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-417 | O2-417 | O2-408 | Faiq Butt | [7 empty] | 2026-02-25 | 2026-02-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1616 | O2-1616 | OC Template (P)- Wasi | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-417 | O2-417 | O2-408 | Muhammad Abdul Wasi | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1617 | O2-1617 | Process testing (P)- Faiq | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-417 | O2-417 | O2-408 | Faiq Butt | [7 empty] | 2026-02-26 | 2026-02-27 | 7
https://octopusdtlsupport.atlassian.net/browse/O2-1618 | O2-1618 | Process testing (P)- Wasi | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-417 | O2-417 | O2-408 | Hassan Malik | [5 empty] | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-25 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1623 | O2-1623 | OmniEMS pre-URS working (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1622 | O2-1622 | O2-1621 | Faiq Butt | [7 empty] | 2026-03-13 | 2026-03-18 | 24.5
https://octopusdtlsupport.atlassian.net/browse/O2-1635 | O2-1635 | Check OC and APX issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | O2-1196 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 2.5
https://octopusdtlsupport.atlassian.net/browse/O2-1648 | O2-1648 | OC Template - Coal (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-482 | O2-482 | O2-453 | Danish Rashid | [7 empty] | 2026-02-23 | 2026-02-24 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-1649 | O2-1649 | OC Template - NG (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-482 | O2-482 | O2-453 | Danish Rashid | [7 empty] | 2026-02-23 | 2026-02-23 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1650 | O2-1650 | Process Testing - NG (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-482 | O2-482 | O2-453 | Danish Rashid | [7 empty] | 2026-02-26 | 2026-02-27 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1651 | O2-1651 | Process Testing - Coal (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-482 | O2-482 | O2-453 | Danish Rashid | [7 empty] | 2026-02-26 | 2026-02-27 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1652 | O2-1652 | OC Template (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-450 | O2-450 | O2-441 | Danish Rashid | [7 empty] | 2026-02-25 | 2026-02-25 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1653 | O2-1653 | Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-450 | O2-450 | O2-441 | Danish Rashid | [7 empty] | 2026-02-26 | 2026-02-27 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-1672 | O2-1672 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1021 | O2-1021 | O2-1018 | Muhammad Abdul Wasi | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1673 | O2-1673 | Template (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1030 | O2-1030 | O2-1028 | DANIYAL AHMAD | [5 empty] | 2026-02-25 | 2026-02-28 | 2026-02-26 | 2026-02-27 | 7
https://octopusdtlsupport.atlassian.net/browse/O2-1675 | O2-1675 | Process Eng. tasks: working, review and management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | O2-1254 | O2-1070 | Mariam Zulfiqar | [5 empty] | 2026-03-02 | 2026-03-31 | 2026-03-02 | 2026-03-31 | 103
https://octopusdtlsupport.atlassian.net/browse/O2-1676 | O2-1676 | Process pre-sales support, Customer / Management Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | O2-1066 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-03-02 | 2026-03-31 | 2026-03-02 | 2026-03-26 | 16.5
https://octopusdtlsupport.atlassian.net/browse/O2-1677 | O2-1677 | Support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-517 | O2-517 | O2-457 | Zeeshan Sarwar | [5 empty] | 2026-03-03 | 2026-03-05 | 2026-03-03 | 2026-03-04 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1688 | O2-1688 | Monitoring and Reporting - February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1684 | O2-1684 | O2-1109 | Taimur Zahid | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 19.5
https://octopusdtlsupport.atlassian.net/browse/O2-1689 | O2-1689 | Testing By M.Abbas Rework | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Muhammad Abbas | [5 empty] | 2026-03-03 | 2026-03-05 | 2026-03-04 | 2026-03-10 | 30
https://octopusdtlsupport.atlassian.net/browse/O2-1693 | O2-1693 | Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1092 | O2-1092 | O2-887 | Hassan Malik | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1699 | O2-1699 | UI Changes Batch RunOnDemand | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1700 | O2-1700 | New UI BPM RunOnDemand | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1701 | O2-1701 | UI Changes Templates Variables Batch | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1702 | O2-1702 | UI Changes Template Variable BPM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1703 | O2-1703 | Database Tables and Changes for Batch | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | ahad omer | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1704 | O2-1704 | Database Tables and ¦Changes BPM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | ahad omer | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1705 | O2-1705 | Backend API Changes Batch Template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | ahad omer | [5 empty] | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-19 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1706 | O2-1706 | Backend API Changes BPM Template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | ahad omer | [5 empty] | 2026-02-19 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1707 | O2-1707 | Unit Testing frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1709 | O2-1709 | UI Changes Integration with API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1711 | O2-1711 | Backend Api Run on Demand in BPM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1713 | O2-1713 | updated the APIs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-848 | O2-848 | O2-37 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1714 | O2-1714 | Backend Api Run on Demand in Batch | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1715 | O2-1715 | Unit Testing Backend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Arslan sohail | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-02-26 | 2026-02-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1716 | O2-1716 | Backend Improvements and Bug fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | ahad omer | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-172 | O2-172 | Research/DDS | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-67 | O2-67 | O2-37 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1721 | O2-1721 | OmniConnect Demo Prep 17th Feb | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1722 | O2-1722 | OmniConnect Demo Day 18th Feb | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1723 | O2-1723 | Mihir Demo on OmniConnect | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1724 | O2-1724 | DL Demo Prep 17th Feb | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1405 | O2-1405 | O2-221 | Sarmad Sabir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1.5
https://octopusdtlsupport.atlassian.net/browse/O2-1725 | O2-1725 | Fintech Fuel Demo Prep 17th Feb | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | O2-1404 | O2-221 | Sarmad Sabir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1.5
https://octopusdtlsupport.atlassian.net/browse/O2-1726 | O2-1726 | MPC Demo on OmniConnect | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1729 | O2-1729 | OmniConnect Demo prep 7th Jan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-173 | O2-173 | User Manual | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-70 | O2-70 | O2-37 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1730 | O2-1730 | OmniConnect Demo prep 8th Jan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1731 | O2-1731 | OmniConnect Demo 28th Jan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1732 | O2-1732 | OmniConnect Demo 30th Jan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1744 | O2-1744 | Impact Analysis | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1113 | O2-1113 | O2-810 | Arslan sohail | [5 empty] | 2025-12-31 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1745 | O2-1745 | Impact Analysis | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1113 | O2-1113 | O2-810 | ahad omer | [5 empty] | 2025-12-31 | 2026-01-06 | 2026-01-01 | 2026-01-06 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1747 | O2-1747 | Add New Column BPM API Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | ahad omer | [5 empty] | 2026-01-07 | 2026-01-13 | 2026-01-07 | 2026-01-13 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1748 | O2-1748 | Add New Column Batch API Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | ahad omer | [5 empty] | 2026-01-14 | 2026-01-19 | 2026-01-14 | 2026-01-19 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1749 | O2-1749 | Add New Column in Custom Functions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Arslan sohail | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1750 | O2-1750 | Frontend End to End Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | O2-1041 | O2-810 | Arslan sohail | [5 empty] | 2026-01-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1752 | O2-1752 | Initial Research OEE NO CODE | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1378 | O2-1378 | O2-1318 | ahad omer | [5 empty] | 2026-01-28 | 2026-01-30 | 2026-01-28 | 2026-01-30 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1753 | O2-1753 | Initial Research OEE NO CODE | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1378 | O2-1378 | O2-1318 | Arslan sohail | [5 empty] | 2026-01-28 |  | 2026-01-28 | 2026-01-30 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1754 | O2-1754 | Bug Fixing, Improvements and Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Arslan sohail | [5 empty] | 2026-02-09 | 2026-02-11 | 2026-02-09 | 2026-02-11 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1756 | O2-1756 | Create Training data set | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | O2-1048 | O2-1044 | Muhammad Abdul Wasi | [7 empty] | 2026-03-03 | 2026-03-03 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1757 | O2-1757 | OmniConnect_Revamp_(UI/UX)_Main Dashboard (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Danish Rashid | [7 empty] | 2026-02-20 | 2026-04-01 | 83
https://octopusdtlsupport.atlassian.net/browse/O2-1758 | O2-1758 | Testing By Zeeshan Rework | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Zeeshan Sarwar | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-10 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-176 | O2-176 | How to | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-154 | O2-154 | O2-151 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1760 | O2-1760 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-423 | O2-423 | O2-418 | DANIYAL AHMAD | [5 empty] | 2026-03-02 | 2026-03-28 | 2026-03-02 | 2026-03-02 | 3.5
https://octopusdtlsupport.atlassian.net/browse/O2-1761 | O2-1761 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-421 | O2-421 | O2-418 | DANIYAL AHMAD | [5 empty] | 2026-03-02 | 2026-03-28 | 2026-03-02 | 2026-03-02 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-1762 | O2-1762 | Data Prep. & Offline testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1032 | O2-1032 | O2-1028 | DANIYAL AHMAD | [5 empty] | 2026-03-02 | 2026-03-31 | 2026-03-03 | 2026-03-12 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1763 | O2-1763 | Bug Fixing, Improvements and Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Syed Yousaf Qadri | [5 empty] | 2026-01-20 | 2026-01-26 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1765 | O2-1765 | Schema Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Syed Yousaf Qadri | [5 empty] | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-24 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1766 | O2-1766 | BPM Backend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Syed Yousaf Qadri | [5 empty] | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-1768 | O2-1768 | Monitoring and Reporting - March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1684 | O2-1684 | O2-1109 | Taimur Zahid | [5 empty] | 2026-03-02 | 2026-03-30 | 2026-03-03 | 2026-03-05 | 17.5
https://octopusdtlsupport.atlassian.net/browse/O2-177 | O2-177 | Fields | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-154 | O2-154 | O2-151 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1785 | O2-1785 | Read API Client Secrete Bearer Token Regeneration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | O2-1784 | O2-1109 | Taimur Zahid | [5 empty] | 2026-03-07 | 2026-03-08 | 2026-03-07 | 2026-03-07 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1786 | O2-1786 | Write API Client Secrete Bearer Token Regeneration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | O2-1784 | O2-1109 | Taimur Zahid | [5 empty] | 2026-03-07 | 2026-03-08 | 2026-03-07 | 2026-03-07 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1787 | O2-1787 | SQA Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | O2-1784 | O2-1109 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1788 | O2-1788 | Read API Validation and Monitoring | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | O2-1784 | O2-1109 | Aiza Hamid | [5 empty] | 2026-03-07 | 2026-03-08 | 2026-03-07 | 2026-03-07 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-1789 | O2-1789 | Write API Validation and Monitoring | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | O2-1784 | O2-1109 | Hassan Saeed Wattoo | [7 empty] | 2026-03-07 | 2026-03-07 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-179 | O2-179 | API Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-178 | O2-178 | O2-164 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1791 | O2-1791 | Key Vault Integration and Updates | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | O2-1784 | O2-1109 | Taimur Zahid | [5 empty] | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 19.5
https://octopusdtlsupport.atlassian.net/browse/O2-1792 | O2-1792 | Fintech Fuel For PGL Leadership - Documentation and Diagram | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | O2-1219 | O2-133 | Taimur Zahid | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-180 | O2-180 | UI/UX | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-15 | O2-15 | O2-9 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1800 | O2-1800 | Output Cal tag latest values for APX performance asset are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1807 | O2-1807 | Alarms are not triggering after the recent release of Real-Time Tag Streaming | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1809 | O2-1809 | Batch jobs are failing on the staging environment and failure logs are not generated | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-181 | O2-181 | Frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-15 | O2-15 | O2-9 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1810 | O2-1810 | BPM jobs are not executing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-182 | O2-182 | API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-15 | O2-15 | O2-9 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-183 | O2-183 | Unit Testing Backend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-15 | O2-15 | O2-9 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1832 | O2-1832 | OmniOEE Pre-URS working (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1375 | O2-1375 | O2-1302 | Muhammad Abdul Wasi | [5 empty] | 2026-03-02 | 2026-03-11 | 2026-03-02 | 2026-03-11 | 47
https://octopusdtlsupport.atlassian.net/browse/O2-1833 | O2-1833 | OmniOEE Pre-URS working (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1375 | O2-1375 | O2-1302 | Muhammad Abdul Wasi | [5 empty] | 2026-02-18 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 11
https://octopusdtlsupport.atlassian.net/browse/O2-1834 | O2-1834 | User Management for Omni Connect through Omni Agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Aiza Hamid | [5 empty] | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-03-09 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1835 | O2-1835 | OC Process testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1023 | O2-1023 | O2-1018 | Muhammad Abdul Wasi | [5 empty] | 2026-01-29 | 2026-01-30 | 2026-01-29 | 2026-01-30 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1839 | O2-1839 | Template (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1030 | O2-1030 | O2-1028 | DANIYAL AHMAD | [5 empty] | 2026-03-09 | 2026-03-25 | 2026-03-09 | 2026-03-13 | 14.5
https://octopusdtlsupport.atlassian.net/browse/O2-184 | O2-184 | Unit Testing frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-15 | O2-15 | O2-9 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1842 | O2-1842 | OmniConnect_ Revamp_(UI/UX)_ Variation_ 02_ Part B | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1844 | O2-1844 | Testing By Kamran Prod Rework(Green) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | kamran khalid | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1846 | O2-1846 | Testing By Namra Prod Rework(Greeen) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Namra Zahid | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 10.5
https://octopusdtlsupport.atlassian.net/browse/O2-1847 | O2-1847 | Testing By Waqar Prod Rework(Greeen) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Waqar Rasheed | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 9
https://octopusdtlsupport.atlassian.net/browse/O2-1848 | O2-1848 | Testing By Zeeshan Prod Rework(Greeen) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Zeeshan Sarwar | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 9
https://octopusdtlsupport.atlassian.net/browse/O2-1849 | O2-1849 | Testing By M.Abbas Prod Rework(Greeen) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Muhammad Abbas | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-185 | O2-185 | Production Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-114 | O2-114 | O2-108 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1854 | O2-1854 | Changed Data Analysis API Format | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1857 | O2-1857 | Monitoring Page Shows Error Even Though Table Schema and Query Schema Match | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1858 | O2-1858 | OmniConnect- Revamp- Site Dashboard and OmniAgent- UX/UI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-02-26 | 2026-03-04 | 2026-02-26 | 2026-03-04 | 32.5
https://octopusdtlsupport.atlassian.net/browse/O2-186 | O2-186 | Discussion for Solution | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1860 | O2-1860 | OmniConnect-Revamp- (UI/UX) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [7 empty] | 2026-02-16 | 2026-03-18 | 22.5
https://octopusdtlsupport.atlassian.net/browse/O2-1862 | O2-1862 | Inhand Live | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1778 | O2-1778 | O2-199 | yousha.agha | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1863 | O2-1863 | Cloud Connectivity | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1778 | O2-1778 | O2-199 | yousha.agha | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1867 | O2-1867 | SAP HANA Connector – Tables Not Auto-Fetched During Pipeline Creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1868 | O2-1868 | Unable to Create ODBC connector | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1869 | O2-1869 | Testing the data analysis flow | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-187 | O2-187 | REST API Dev OC Frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1871 | O2-1871 | OmniOEE URS (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | O2-1855 | O2-1302 | Muhammad Abdul Wasi | [5 empty] | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-16 | 18.5
https://octopusdtlsupport.atlassian.net/browse/O2-1878 | O2-1878 | Preping OmniConnect Product Review to Arsalan Avanceon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-1879 | O2-1879 | Preping APX Review to Arsalan Avanceon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-188 | O2-188 | Code Review and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-132 | O2-132 | O2-130 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1880 | O2-1880 | OmniConnect + APX Review to Arsalan Avanceon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1881 | O2-1881 | Preping FintechFuel Product Review to Arsalan Avanceon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | O2-1404 | O2-221 | Sarmad Sabir | [5 empty] | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 2.5
https://octopusdtlsupport.atlassian.net/browse/O2-1882 | O2-1882 | FintechFuel Product Review to Arsalan Avanceon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | O2-1404 | O2-221 | Sarmad Sabir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-189 | O2-189 | Code Review and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-159 | O2-159 | O2-130 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1891 | O2-1891 | Testing By M.Abbas Prod Rework(Blue) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Muhammad Abbas | [5 empty] | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-16 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1892 | O2-1892 | Testing By Zeeshan Prod Rework(Blue) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Zeeshan Sarwar | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1893 | O2-1893 | JIRA Logging Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1573 | O2-1573 | O2-798 | Faiza Nasir | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 1.67
https://octopusdtlsupport.atlassian.net/browse/O2-1897 | O2-1897 | Module Design - Fixed Speed (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1045 | O2-1045 | O2-1044 | Unassigned | [7 empty] | 2026-03-12 | 2026-03-13 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-190 | O2-190 | Code Review and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-131 | O2-131 | O2-130 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-191 | O2-191 | Discussion and Review | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-158 | O2-158 | O2-130 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1913 | O2-1913 | OmniOEE Method Selection & Formulae Setup (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | O2-1855 | O2-1302 | Muhammad Abdul Wasi | [5 empty] | 2026-03-17 | 2026-03-31 | 2026-03-17 | 2026-03-18 | 8.5
https://octopusdtlsupport.atlassian.net/browse/O2-1919 | O2-1919 | Handover - Hassan Malik | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1918 | O2-1918 | O2-818 | Hassan Malik | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 0.63
https://octopusdtlsupport.atlassian.net/browse/O2-192 | O2-192 | Modify Existing API For Connectors CRUD | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1922 | O2-1922 | Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1918 | O2-1918 | O2-818 | Arslan sohail | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1923 | O2-1923 | Handover By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1921 | O2-1921 | O2-818 | Muhammad Abbas | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-1924 | O2-1924 | Batch Run on demand | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | O2-1438 | O2-818 | Muhammad Abbas | [5 empty] | 2026-03-17 | 2026-03-25 | 2026-03-17 | 2026-03-26 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-1925 | O2-1925 | Testing by Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-520 | O2-520 | O2-457 | Zeeshan Sarwar | [5 empty] | 2026-03-17 | 2026-03-19 | 2026-03-17 | 2026-03-30 | 25
https://octopusdtlsupport.atlassian.net/browse/O2-1926 | O2-1926 | Deployment + Unit Testing + DB Changes/Migrations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-520 | O2-520 | O2-457 | Zain Munir | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 3.5
https://octopusdtlsupport.atlassian.net/browse/O2-1927 | O2-1927 | Production Green Deployment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-520 | O2-520 | O2-457 | Faiza Nasir | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-193 | O2-193 | New Table and Database changes for Rest API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1932 | O2-1932 | Meetings and Discussions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Taimur Zahid | [5 empty] | 2026-03-11 | 2026-03-13 | 2026-03-12 | 2026-03-13 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1933 | O2-1933 | Code Merge + Testing + Deployement to staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1934 | O2-1934 | March 17, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | O2-1293 | O2-798 | Taimur Zahid | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1938 | O2-1938 | Handover By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | O2-1937 | O2-1340 | Namra Zahid | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1939 | O2-1939 | Handover By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | O2-1937 | O2-1340 | Waqar Rasheed | [7 empty] | 2026-03-18 | 2026-03-18 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-194 | O2-194 | Modify Existing API For Triggers CRUD | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1940 | O2-1940 | Handover By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | O2-1937 | O2-1340 | Zeeshan Sarwar | [7 empty] | 2026-03-18 | 2026-03-18 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1941 | O2-1941 | Handover By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | O2-1937 | O2-1340 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1942 | O2-1942 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Namra Zahid | [5 empty] | 2026-03-18 | 2026-03-30 | 2026-03-18 | 2026-04-13 | 37.5
https://octopusdtlsupport.atlassian.net/browse/O2-1944 | O2-1944 | Handover - Hassan Saeed Wattoo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | O2-1937 | O2-1340 | Hassan Saeed Wattoo | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-1946 | O2-1946 | BPM Run on demand | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | O2-1438 | O2-818 | Waqar Rasheed | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 5.5
https://octopusdtlsupport.atlassian.net/browse/O2-1947 | O2-1947 | Implementing Lookback for Pointer | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1945 | O2-1945 | O2-199 | Syed Yousaf Qadri | [5 empty] | 2026-03-06 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1949 | O2-1949 | Orchestrator Agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-04 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-195 | O2-195 | Modify Existing API For Pipelines CRUD | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1950 | O2-1950 | Handover - Hassan Malik | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | O2-1937 | O2-1340 | Hassan Malik | [7 empty] | 2026-03-18 | 2026-03-18 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-196 | O2-196 | Development OC Frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1962 | O2-1962 | SQL/Databse Layers including SPs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-06 | 32.5
https://octopusdtlsupport.atlassian.net/browse/O2-1963 | O2-1963 | Backend Endpoints OmniChat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 32.5
https://octopusdtlsupport.atlassian.net/browse/O2-1964 | O2-1964 | Metadata Linkage for Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1965 | O2-1965 | Module Design (P) Review | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1029 | O2-1029 | O2-1028 | Unassigned | [7 empty] | 2026-03-16 | 2026-03-17 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-1966 | O2-1966 | OC Process testing (P) - Faiq | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-423 | O2-423 | O2-418 | Faiq Butt | [7 empty] | 2026-02-23 | 2026-02-23 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-1968 | O2-1968 | Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1969 | O2-1969 | Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-197 | O2-197 | Code Review and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-166 | O2-166 | O2-164 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1970 | O2-1970 | Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1971 | O2-1971 | Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1972 | O2-1972 | Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1973 | O2-1973 | Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-1974 | O2-1974 | Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1975 | O2-1975 | QA Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Muhammad Abdul Wasi | [5 empty] | 2026-03-18 | 2026-03-31 | 2026-03-18 | 2026-03-31 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1978 | O2-1978 | Fintech Fuel Demo to Mihir and Deepak | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | O2-1404 | O2-221 | Sarmad Sabir | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-1979 | O2-1979 | Backword Compatability | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-792 | O2-792 | O2-793 | Ayyan Babar | [5 empty] | 2026-01-12 | 2026-01-15 | 2026-03-16 | 2026-03-17 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-198 | O2-198 | Code Review and Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-167 | O2-167 | O2-164 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1980 | O2-1980 | Code Setup + Understanding of the repo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-18 | 9
https://octopusdtlsupport.atlassian.net/browse/O2-1983 | O2-1983 | Kick-off meetings (DR) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | O2-1982 | O2-1981 | Danish Rashid | [7 empty] | 2026-03-24 | 2026-03-27 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-1984 | O2-1984 | Kick-off meetings (MAW) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | O2-1982 | O2-1981 | Muhammad Abdul Wasi | [5 empty] | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-03-25 | 8.5
https://octopusdtlsupport.atlassian.net/browse/O2-1985 | O2-1985 | Kick-off meetings (DA) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | O2-1982 | O2-1981 | DANIYAL AHMAD | [5 empty] | 2026-03-24 |  | 2026-03-24 | 2026-03-24 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-1986 | O2-1986 | Module Design Synchronous (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1029 | O2-1029 | O2-1028 | DANIYAL AHMAD | [7 empty] | 2026-03-10 | 2026-04-29 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-1987 | O2-1987 | Enhance Monitoring Logs for Batch/BPM Module to Include Variable Values | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1920 | O2-1920 | O2-818 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-1989 | O2-1989 | Create Scheduled Trigger API -With AI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-03-18 | 2026-03-26 | 2026-03-18 | 2026-03-18 | 3.5
https://octopusdtlsupport.atlassian.net/browse/O2-1999 | O2-1999 | Batch On Demand Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Syed Yousaf Qadri | [5 empty] | 2026-03-31 | 2026-04-02 | 2026-03-31 | 2026-04-02 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2000 | O2-2000 | Batch/BPM Trigger | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | O2-1438 | O2-818 | Muhammad Abbas | [5 empty] | 2026-03-26 | 2026-03-31 | 2026-03-26 | 2026-04-02 | 44.5
https://octopusdtlsupport.atlassian.net/browse/O2-2007 | O2-2007 | Analysis for APX hits | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2006 | O2-2006 | O2-2005 | Aiza Hamid | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2008 | O2-2008 | Analysis for Customer Hits | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2006 | O2-2006 | O2-2005 | Aiza Hamid | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-201 | O2-201 | Blocker: IOT HUB status is still in Progress. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2013 | O2-2013 | Re-Develop Create Trigger API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 7
https://octopusdtlsupport.atlassian.net/browse/O2-2014 | O2-2014 | Modify Create Apis | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2017 | O2-2017 | Create hello world function app and app service on seperate ASPs and analyze utilization of asp | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2016 | O2-2016 |  | Ayyan Babar | [5 empty] | 2026-03-30 | 2026-03-31 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2019 | O2-2019 | Code Understanding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-03-18 | 2026-03-25 | 2026-03-18 | 2026-03-24 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-202 | O2-202 | Un-necessary space is showing on Create and Edit Customer modal | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ali Qumail | [5 empty] | 2025-10-08 | 2025-10-08 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2021 | O2-2021 | hello world of function apps and app service on azure app service plan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2020 | O2-2020 | O2-1783 | Ayyan Babar | [5 empty] | 2026-03-30 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2023 | O2-2023 | Started Backend + Research on Code | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 5.5
https://octopusdtlsupport.atlassian.net/browse/O2-2024 | O2-2024 | Completed Backend(Responses + Request) Model | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2026 | O2-2026 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2025 | O2-2025 | O2-1395 | kamran khalid | [5 empty] | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2028 | O2-2028 | Get all triggers API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-2029 | O2-2029 | Fixes, while API integrations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-03-27 | 2026-03-31 | 2026-03-27 | 2026-03-27 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-203 | O2-203 | Understanding The URS | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2031 | O2-2031 | Cloned BPM Jobs Showing “Pending” Status on Monitoring Page | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1920 | O2-1920 | O2-818 | Arslan sohail | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2032 | O2-2032 | Integrated Chart logic Frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2033 | O2-2033 | UI Changes + Completed Integration of Charts logic | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2036 | O2-2036 | support table edge trouble shooting - bug fixing - trouble shooting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2035 | O2-2035 | O2-2034 | Mohsin Junaid | [5 empty] | 2026-03-30 | 2026-04-02 | 2026-03-27 | 2026-04-03 | 48
https://octopusdtlsupport.atlassian.net/browse/O2-2037 | O2-2037 | troubleshoot edge | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2035 | O2-2035 | O2-2034 | Usama Tariq | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2039 | O2-2039 | Training By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2038 | O2-2038 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-03-30 | 2026-04-03 | 2026-03-30 | 2026-04-01 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-204 | O2-204 | When user click on edit icon of Subscription/Demo site, then Publish Changes button is showing in side navigation bar | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ali Qumail | [5 empty] | 2025-10-15 | 2025-10-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2040 | O2-2040 | End Date is not working on when specified on Trigger while creating a trigger as it does not stopped on the date specified | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2025 | O2-2025 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2041 | O2-2041 | validation update in Validate button on entering Complex Query while creating sap HANA and ODBC Connector | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2025 | O2-2025 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2042 | O2-2042 | OmniConnect Testing Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2043 | O2-2043 | Production Blue Environment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-520 | O2-520 | O2-457 | Faiza Nasir | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2044 | O2-2044 | OmniConnect Testing Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2045 | O2-2045 | When querying “how many total areas/assets are in this site (with names)”, the OmniAgent Data Analysis module returns only one area/asset and does not display the complete list or count. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-31 |  | 2026-04-06 | 2026-04-06 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2046 | O2-2046 | OmniConnect Testing Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2047 | O2-2047 | Omni Agent fail to answer this question Which machine experienced the most downtime and how long did it last? | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2048 | O2-2048 | Bug: Instead of devices name omni agent is returning asset names | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-31 |  | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2049 | O2-2049 | Bug: Omni Agent showing zero tag incase deadband and persistence | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Hassan Saeed Wattoo | [7 empty] | 2026-03-31 | 2026-04-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2050 | O2-2050 | Bug: Omni Agent is not fetching only acknowledge alarm | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Hassan Saeed Wattoo | [7 empty] | 2026-03-31 | 2026-03-31 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2051 | O2-2051 | Bug: Omni Agent fail to fetch suppress alarms name, and Omni Agent fail to fetch suppress time duration of tag alarm | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Hassan Saeed Wattoo | [5 empty] | 2026-03-31 |  | 2026-03-31 | 2026-04-07 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-2053 | O2-2053 | Incorrect asset types displayed in OmniAgent query response | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-03-31 |  | 2026-04-06 | 2026-04-06 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2054 | O2-2054 | OmniConnect Testing Automation Learning Coding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | O2-1967 | O2-1755 | Muhammad Imran Aslam | [5 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2055 | O2-2055 | Fixed issues on Frontend and backend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2056 | O2-2056 | Integrated OmniAgent Charts and Refresh Site API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2058 | O2-2058 | Initial Research (DR) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2057 | O2-2057 | O2-1981 | Unassigned | [7 empty] | 2026-03-30 | 2026-04-07 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2059 | O2-2059 | Removing trigger fields from Export to SQL | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-206 | O2-206 | Moving Read API Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Aiza Hamid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2060 | O2-2060 | Creating a new triggers page for Export to SQL | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2061 | O2-2061 | Integrating NEW APIs for Triggers page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2062 | O2-2062 | Template Optimizations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-467 | O2-467 | O2-452 | Muhammad Abdul Wasi | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2063 | O2-2063 | Deleted chats reappear after navigation or logout in OmniAgent | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2064 | O2-2064 | Timer tag value not retrieved; schema error shown instead of value and timestamp | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-04-01 |  | 2026-04-03 | 2026-04-03 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2065 | O2-2065 | Duplicate information displayed in OmniAgent response (text + scrollable error) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-04-01 |  | 2026-04-03 | 2026-04-03 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2066 | O2-2066 | Not showing complete data for all tags and incorrect missing tags list on re-query | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-04-01 |  | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2067 | O2-2067 | Template Optimizations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-467 | O2-467 | O2-452 | Muhammad Abdul Wasi | [5 empty] | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2069 | O2-2069 | Publish Changes version is not getting updated | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Ameer Hamza Khan | [5 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-207 | O2-207 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2070 | O2-2070 | OC Process testing (P) - DA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-423 | O2-423 | O2-418 | DANIYAL AHMAD | [7 empty] | 2026-03-26 | 2026-03-27 | 10
https://octopusdtlsupport.atlassian.net/browse/O2-2071 | O2-2071 | Data Prep. & Offline testing - Sync Motor | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1032 | O2-1032 | O2-1028 | DANIYAL AHMAD | [5 empty] | 2026-03-27 | 2026-04-30 | 2026-03-27 | 2026-04-30 | 35.5
https://octopusdtlsupport.atlassian.net/browse/O2-2072 | O2-2072 | ADE Enhancement rev 3.0 - March | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-497 | O2-497 | O2-37 | DANIYAL AHMAD | [5 empty] | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2073 | O2-2073 | ADE Enhancement rev 3.0 - April | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-497 | O2-497 | O2-37 | DANIYAL AHMAD | [5 empty] | 2026-04-01 | 2026-04-10 | 2026-04-01 | 2026-04-06 | 28
https://octopusdtlsupport.atlassian.net/browse/O2-2074 | O2-2074 | Kick-off working | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | O2-1982 | O2-1981 | Mariam Zulfiqar | [7 empty] | 2026-03-24 | 2026-03-26 | 9
https://octopusdtlsupport.atlassian.net/browse/O2-2075 | O2-2075 | Duplicate tags created on single tag creation and reflected in Latest Values screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Ameer Hamza Khan | [5 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2076 | O2-2076 | Set up Start And End Pull time for each trigger | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-02 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-2077 | O2-2077 | Requirements gathering and finalizing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-60 | O2-60 | O2-36 | Ameer Hamza Khan | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2078 | O2-2078 | Update Health Activation API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | O2-2068 | O2-459 | Faiza Nasir | [5 empty] | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 7
https://octopusdtlsupport.atlassian.net/browse/O2-2079 | O2-2079 | Update all Status Check APIs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | O2-2068 | O2-459 | Faiza Nasir | [5 empty] | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-208 | O2-208 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2080 | O2-2080 | Update Health Model Creation Request API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | O2-2068 | O2-459 | Faiza Nasir | [5 empty] | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-2081 | O2-2081 | OmniAgent fails to detect configured and fired Statistical Alarms | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Unassigned | [5 empty] | 2026-04-02 |  | 2026-04-02 | 2026-04-02 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-2082 | O2-2082 | OmniAgent gets stuck on “Please wait for response” after network interruption and does not recover | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | O2-2022 | O2-1340 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-04-02 |  | 2026-04-02 | 2026-04-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2083 | O2-2083 | Fixed Refresh Site issue + UI issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2085 | O2-2085 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | kamran khalid | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-06 | 18
https://octopusdtlsupport.atlassian.net/browse/O2-2086 | O2-2086 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Waqar Rasheed | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-06 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2087 | O2-2087 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Namra Zahid | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-06 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2088 | O2-2088 | Testing By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-06 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-209 | O2-209 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2090 | O2-2090 | Latest Values are not populating for real tags on Staging. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Ayyan Babar | [5 empty] | 2026-04-03 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2092 | O2-2092 | Update Create trigger api, Check for unique names only | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2093 | O2-2093 | modify get trigger api, bring trigger name and is enabled | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2094 | O2-2094 | Version is not getting updated again. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2095 | O2-2095 | Testing Module + Deployed to staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2096 | O2-2096 | Initial Research (FB) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2057 | O2-2057 | O2-1981 | Faiq Butt | [7 empty] | 2026-04-01 | 2026-04-03 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2097 | O2-2097 | Kick-off meetings (FB) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | O2-1982 | O2-1981 | Unassigned | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2098 | O2-2098 | OmniOEE Method Selection & Formulae Setup (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | O2-1855 | O2-1302 | Muhammad Abdul Wasi | [5 empty] | 2026-04-06 | 2026-04-30 | 2026-04-17 | 2026-04-28 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2099 | O2-2099 | QA Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | O2-1343 | O2-1340 | Muhammad Abdul Wasi | [5 empty] | 2026-04-02 | 2026-04-17 | 2026-04-02 | 2026-04-08 | 39
https://octopusdtlsupport.atlassian.net/browse/O2-210 | O2-210 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2100 | O2-2100 | API Changes for Triggers | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2101 | O2-2101 | Bug Fixes Dev Side | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-04-03 | 2026-04-06 | 2026-04-02 | 2026-04-06 | 20
https://octopusdtlsupport.atlassian.net/browse/O2-2102 | O2-2102 | Research on Adding the Image Support to HTML Template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1992 | O2-1992 | O2-1991 | Zain Munir | [5 empty] | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-07 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-2103 | O2-2103 | Anomaly Group Model is not getting created. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-06 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2104 | O2-2104 | fixing issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2107 | O2-2107 | Overview code to incorporate requirements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | O2-2068 | O2-459 | Faiza Nasir | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-211 | O2-211 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2114 | O2-2114 | Dev | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2113 | O2-2113 | O2-2105 | Aiza Hamid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2115 | O2-2115 | SQA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2113 | O2-2113 | O2-2105 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2116 | O2-2116 | Added feature to round off the value in Read API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2111 | O2-2111 | O2-2105 | Aiza Hamid | [5 empty] | 2026-04-03 | 2026-04-07 | 2026-04-03 | 2026-04-07 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2117 | O2-2117 | “Get Latest Values” Not Working for Single and Bulk Write Back | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2118 | O2-2118 | Unable to create SAP HANA and ODBC Connector | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2119 | O2-2119 | Diagnostics Email Alerts Are Not Being Received | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-212 | O2-212 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Muhammad Yousha Agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2120 | O2-2120 | Data center Specified module failed on staging | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2121 | O2-2121 | Asset and Real , Manual and Cal tags are getting duplicated, while we create Asset Built In, and double click on the save button | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Ameer Hamza Khan | [5 empty] | 2026-04-06 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2125 | O2-2125 | Walk-through session with process team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Ameer Hamza Khan | [5 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2127 | O2-2127 | Anomaly Group results are not getting displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-06 |  | 2026-04-06 | 2026-04-06 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2128 | O2-2128 | Omni Alla Walkthrough | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Faiza Nasir | [5 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2.5
https://octopusdtlsupport.atlassian.net/browse/O2-213 | O2-213 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2132 | O2-2132 | Unable to verify phone number using SMS OPT-IN feature | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2133 | O2-2133 | MQTT Default Simulator for Ingestion Transfection is getting closed with this error , right after running it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Muhammad Yousha Agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2134 | O2-2134 | EMAIL Alerts for alarms notifications are not triggering | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | O2-2084 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2136 | O2-2136 | Walk-through session with process team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Zain Munir | [7 empty] | 2026-04-06 | 2026-04-06 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2138 | O2-2138 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | kamran khalid | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2139 | O2-2139 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Waqar Rasheed | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 15
https://octopusdtlsupport.atlassian.net/browse/O2-214 | O2-214 | Moving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Usama Tariq | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2140 | O2-2140 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Namra Zahid | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2141 | O2-2141 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 14
https://octopusdtlsupport.atlassian.net/browse/O2-2142 | O2-2142 | Batch/BPM Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | O2-1440 | O2-818 | Muhammad Abbas | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2143 | O2-2143 | OmniConnect_Revamp_(UI/UX)_URS (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Unassigned | [7 empty] | 2026-04-01 | 2026-04-17 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-2145 | O2-2145 | Changes in BPM Engine | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Syed Yousaf Qadri | [5 empty] | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | 19.5
https://octopusdtlsupport.atlassian.net/browse/O2-2146 | O2-2146 | Changes in Batch Engine | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Syed Yousaf Qadri | [5 empty] | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-03-12 | 19.5
https://octopusdtlsupport.atlassian.net/browse/O2-2147 | O2-2147 | End To End testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Syed Yousaf Qadri | [5 empty] | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-16 | 13
https://octopusdtlsupport.atlassian.net/browse/O2-2149 | O2-2149 | Implement manual DB/Table to bypass SAP HANA Connector | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2148 | O2-2148 | O2-199 | Arslan sohail | [7 empty] | 2026-03-04 | 2026-03-07 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-215 | O2-215 | usamaMoving Configurations to Environment Variables | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2150 | O2-2150 | Latest Values are not getting populated (Green Production) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ayyan Babar | [5 empty] | 2026-04-07 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2151 | O2-2151 | UI Changes Batch Trigger | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2152 | O2-2152 | UI Changes BPM Trigger | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2153 | O2-2153 | Batch Variable Mapping | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-09 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2154 | O2-2154 | BPM Variable Mapping | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-11 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2155 | O2-2155 | Design and implement SQL tables for BPM/Batch variable mapping | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2156 | O2-2156 | Unit Testing Frontend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2157 | O2-2157 | Unit Testing Backend | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2158 | O2-2158 | UI Integrate With API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | Arslan sohail | [5 empty] | 2026-03-13 | 2026-03-18 | 2026-03-13 | 2026-03-18 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-2159 | O2-2159 | Data center module fail on prod green env | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-216 | O2-216 | Trigger API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Taimur Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2160 | O2-2160 | Unable to create Enterprise Connectors on Production (Green). The issue was recently fixed on the staging environment but the fix has not yet been deployed to production. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2161 | O2-2161 | Request A Format For Ingestion Transformation is not getting created, Showing this error. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ameer Hamza Khan | [5 empty] | 2026-04-07 |  | 2026-04-08 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2162 | O2-2162 | Initial POC | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-19 | O2-19 | O2-10 | ahad omer | [5 empty] | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-03 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2163 | O2-2163 | BATCH and BPM Trigger Design Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | ahad omer | [5 empty] | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-16 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-2164 | O2-2164 | Instance api Development Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | ahad omer | [7 empty] | 2026-03-17 | 2026-03-18 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2165 | O2-2165 | Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-20 | O2-20 | O2-10 | ahad omer | [5 empty] | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2167 | O2-2167 | ADE Stress Testing Support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2166 | O2-2166 | O2-221 | Muhammad Abdul Wasi | [5 empty] | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2168 | O2-2168 | Data Prep for Demo (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-427 | O2-427 | O2-418 | DANIYAL AHMAD | [7 empty] | 2026-04-06 | 2026-04-07 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2169 | O2-2169 | “Get Latest Values” Not Working for Single and Bulk Write Back | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2170 | O2-2170 | Site Changes Refresh button is not working. as its not showing newly created Real tag even after clicking on refresh button. Prod green | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ibrahim Ahmed Qureshi | [5 empty] | 2026-04-08 |  | 2026-04-09 | 2026-04-09 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2171 | O2-2171 | Green production release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | O2-1440 | O2-818 | Ameer Hamza Khan | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2172 | O2-2172 | Production Green Release / Release Management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | O2-1440 | O2-818 | Faiza Nasir | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2173 | O2-2173 | Update Digital twin APIs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | O2-2068 | O2-459 | Faiza Nasir | [5 empty] | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-06 | 5.5
https://octopusdtlsupport.atlassian.net/browse/O2-2174 | O2-2174 | Schedule Scanning not Woking for Digital LOG Device | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Arsalan Zafar Khan | [5 empty] | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2175 | O2-2175 | Publish Changes version is not getting updated Again (Production Green) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ameer Hamza Khan | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2176 | O2-2176 | Application is getting logout While we Create model for Anomaly group. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ameer Hamza Khan | [5 empty] | 2026-04-08 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2180 | O2-2180 | Data Alarms and Stats Alarms are configured and getting fired, but OmniAgent is not Showing records. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-04-08 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2181 | O2-2181 | Real Time tags are getting Duplicated while we create from Wizard | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Ameer Hamza Khan | [7 empty] | 2026-04-08 | 2026-04-08 | 0.17
https://octopusdtlsupport.atlassian.net/browse/O2-2182 | O2-2182 | OmniAla Walkthrough Session + Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-2183 | O2-2183 | Fixed OmniAgent issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2184 | O2-2184 | DDS Discussion + prepared OmniAla ERD | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2185 | O2-2185 | DDS(Added Content + Prepared Flowchart) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2212 | O2-2212 | APX Asset Creation – Next Button Creates Tag but Does Not Navigate, Causes Duplication Error on Re-click | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | O2-2137 | O2-1395 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2218 | O2-2218 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | kamran khalid | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 17
https://octopusdtlsupport.atlassian.net/browse/O2-222 | O2-222 | Same OTP is received and not getting expired after using. This issue occur sometime and sometime it is working fine. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2220 | O2-2220 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Namra Zahid | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2221 | O2-2221 | Testing By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2222 | O2-2222 | Bug Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | O2-1440 | O2-818 | Faiza Nasir | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2.17
https://octopusdtlsupport.atlassian.net/browse/O2-2223 | O2-2223 | Production Blue Deployment / Release Management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | O2-1440 | O2-818 | Faiza Nasir | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2226 | O2-2226 | Values are not populating for newly created sites, Second time In a day, and we will be creating all the site third time now | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Ayyan Babar | [5 empty] | 2026-04-09 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2227 | O2-2227 | Unable to Create connectors | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2231 | O2-2231 | “Get Latest Values” Not Working for Single and Bulk Write Back | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2232 | O2-2232 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Waqar Rasheed | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2233 | O2-2233 | Anomaly Group Results are not getting displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-09 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2234 | O2-2234 | Process Eng. tasks: working, review and management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | O2-1254 | O2-1070 | Mariam Zulfiqar | [5 empty] | 2026-04-01 | 2026-04-30 | 2026-04-02 | 2026-04-30 | 119.5
https://octopusdtlsupport.atlassian.net/browse/O2-2235 | O2-2235 | Process pre-sales support, Customer / Management Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | O2-1066 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-04-01 | 2026-04-30 | 2026-04-03 | 2026-04-29 | 31
https://octopusdtlsupport.atlassian.net/browse/O2-2236 | O2-2236 | Failed to refresh with button and we cant proceed with OmniAgent Testing Prod Blue | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-04-10 | 2026-04-10 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2237 | O2-2237 | Research for Slider, Radio Buttons, Inputs Support to HTML Template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1992 | O2-1992 | O2-1991 | Zain Munir | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2238 | O2-2238 | State Duplication in Data Alarms for Totalizer Tags | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | O2-2217 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2239 | O2-2239 | Image, Radio Button, Slider Incorporation in the HTML Template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | O2-1993 | O2-1991 | Zain Munir | [5 empty] | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-15 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-224 | O2-224 | Event-based Real-Time Tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-111 | O2-111 | O2-108 | Ayyan Babar | [5 empty] | 2025-09-15 | 2025-10-07 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2240 | O2-2240 | OmniConnect- Site Dashboard UI + Plus Navigation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-03-05 | 2026-03-11 | 2026-03-05 | 2026-03-11 | 32.5
https://octopusdtlsupport.atlassian.net/browse/O2-2241 | O2-2241 | OmniConnect_ Feedback Incorporation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-03-12 | 2026-03-18 | 2026-03-12 | 2026-03-18 | 32.5
https://octopusdtlsupport.atlassian.net/browse/O2-2242 | O2-2242 | OmniConnect_ Organization Dashboard + Navigation changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-03-24 | 2026-03-30 | 2026-03-24 | 2026-03-30 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-2243 | O2-2243 | OmniConnect_ OmniAgent Revamp + Site Connectivity | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-03-31 | 2026-04-06 | 2026-03-31 | 2026-04-06 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-2244 | O2-2244 | OmniConnect_ Revamp Overall Feedback Incorportion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-894 | O2-894 | O2-892 | Hassan Wali | [5 empty] | 2026-04-07 | 2026-04-13 | 2026-04-07 | 2026-04-13 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-2247 | O2-2247 | Asset Design, HB and Expected models (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Danish Rashid | [5 empty] | 2026-04-09 | 2026-04-30 | 2026-04-09 | 2026-04-24 | 48
https://octopusdtlsupport.atlassian.net/browse/O2-2248 | O2-2248 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Unassigned | [7 empty] | 2026-04-17 | 2026-04-22 | 28
https://octopusdtlsupport.atlassian.net/browse/O2-2249 | O2-2249 | Initial Research | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | Faiq Butt | [7 empty] | 2026-04-06 | 2026-04-07 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-225 | O2-225 | Timer-based Processed Tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-111 | O2-111 | O2-108 | Mohsin Junaid | [5 empty] | 2025-09-15 | 2025-10-07 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2250 | O2-2250 | Walk-through session with process team (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Faiq Butt | [7 empty] | 2026-04-06 | 2026-04-06 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2251 | O2-2251 | AHU Presentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | Faiq Butt | [7 empty] | 2026-04-08 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2252 | O2-2252 | Asset Design, HB and Expected models (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | Faiq Butt | [7 empty] | 2026-04-09 | 2026-04-23 | 84
https://octopusdtlsupport.atlassian.net/browse/O2-2254 | O2-2254 | Module Design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2253 | O2-2253 | O2-1981 | Unassigned | [7 empty] | 2026-04-13 | 2026-04-17 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2255 | O2-2255 | Curves Digitalization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | DANIYAL AHMAD | [7 empty] | 2026-04-08 | 2026-04-20 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-2256 | O2-2256 | Setup additional Property for health | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-10 | 2026-04-14 | 2026-04-10 | 2026-04-10 | 5.5
https://octopusdtlsupport.atlassian.net/browse/O2-2257 | O2-2257 | Code review to incorporate changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-2258 | O2-2258 | Product Demo 14th April | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 11
https://octopusdtlsupport.atlassian.net/browse/O2-2259 | O2-2259 | Add steps for health additional property | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | 3.5
https://octopusdtlsupport.atlassian.net/browse/O2-2260 | O2-2260 | modify steps api to incorporate health additional properties | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2.5
https://octopusdtlsupport.atlassian.net/browse/O2-2261 | O2-2261 | Modify the template code to incorporate changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2262 | O2-2262 | Modify health get steps api to call additional property template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-15 | 2026-04-16 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2263 | O2-2263 | Export To Sql | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2179 | O2-2179 | O2-1976 | Namra Zahid | [5 empty] | 2026-04-16 | 2026-04-22 | 2026-04-16 | 2026-04-29 | 77
https://octopusdtlsupport.atlassian.net/browse/O2-2266 | O2-2266 | Handover By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | O2-2265 | O2-1976 | Muhammad Abbas | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2267 | O2-2267 | Handover Taken By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | O2-2265 | O2-1976 | kamran khalid | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2268 | O2-2268 | Handover By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | O2-2265 | O2-1976 | Namra Zahid | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-227 | O2-227 | When user selects the Notification group in the edit site and re-saves the configuration then the datapoints column for the respective site is getting empty | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ali Qumail | [5 empty] | 2025-10-15 | 2025-10-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-228 | O2-228 | Data is not being ingested into ADX for any site and device. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-229 | O2-229 | Un-necessary space is showing on Create and Edit GPS modal | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ali Qumail | [5 empty] | 2025-10-08 | 2025-10-08 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-231 | O2-231 | IT Data Connector table not visible on Batch BPM Query page despite successful ingestion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-232 | O2-232 | Duplicate table creation shows success in UI but only one table exists in ADX. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2327 | O2-2327 | Incorporate Additional propertty while configuring asset's Health | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2328 | O2-2328 | Incorporate additional property in VM calls for digital twin creation and Activation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-2329 | O2-2329 | User End dynamic HTML Rendering and id mappings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | O2-1993 | O2-1991 | Zain Munir | [5 empty] | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-17 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-233 | O2-233 | Pipeline creation fails on GET method despite Read API supporting both GET and POST. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2330 | O2-2330 | Testing for VM calls with Process Team Coordination | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | O2-2068 | O2-459 | Faiza Nasir | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2334 | O2-2334 | BPM On Demand Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Syed Yousaf Qadri | [5 empty] | 2026-04-03 | 2026-04-07 | 2026-04-03 | 2026-04-07 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2336 | O2-2336 | BPM Job Tracking Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Syed Yousaf Qadri | [5 empty] | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2337 | O2-2337 | Batch Job Tracking Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Syed Yousaf Qadri | [5 empty] | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-13 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2338 | O2-2338 | Authorization Implementation for BPM/Batch | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Syed Yousaf Qadri | [5 empty] | 2026-04-14 | 2026-04-16 | 2026-04-14 | 2026-04-16 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2339 | O2-2339 | Database connection failing - Due to VNET deletion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2335 | O2-2335 | O2-199 | Faiza Nasir | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-234 | O2-234 | Run on Demand is not working for IT Data pipelines. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2343 | O2-2343 | Handover to QA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | O2-2265 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-2345 | O2-2345 | Delete Trigger API Creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 1.5
https://octopusdtlsupport.atlassian.net/browse/O2-2346 | O2-2346 | Post Handover feedback Incorporated | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2348 | O2-2348 | Resolve Update Pipeline API Issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-16 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-235 | O2-235 | Duplicate Manual and Cal tags are being created. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2352 | O2-2352 | Anomaly Detection ASP Experimentation Costing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2351 | O2-2351 | O2-2340 | Taimur Zahid | [5 empty] | 2026-04-03 | 2026-04-13 | 2026-04-03 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2354 | O2-2354 | Proposal and Azure Costs Estimations for 12000 Sites | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2351 | O2-2351 | O2-2340 | Taimur Zahid | [5 empty] | 2026-04-03 | 2026-04-13 | 2026-04-07 | 2026-04-14 | 36
https://octopusdtlsupport.atlassian.net/browse/O2-2356 | O2-2356 | Source Tag Creation and Setup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2349 | O2-2349 | O2-2340 | yousha.agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2357 | O2-2357 | Real-time Tags Creation and Simulation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2349 | O2-2349 | O2-2340 | yousha.agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2358 | O2-2358 | Tag Groups Creation and Simulation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2342 | O2-2342 | O2-2340 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2359 | O2-2359 | Cost per Tag Reporting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2342 | O2-2342 | O2-2340 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-236 | O2-236 | Perform API validations on Create Connector screen to improve user experience. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2360 | O2-2360 | Logic App Creation and Simulation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2350 | O2-2350 | O2-2340 | Aiza Hamid | [5 empty] | 2026-04-03 | 2026-04-07 | 2026-04-03 | 2026-04-06 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2361 | O2-2361 | Database Logs and Monitoring | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2350 | O2-2350 | O2-2340 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-04-10 | 2026-04-13 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2362 | O2-2362 | DDS(Added Sequence Diagram +ERD) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2363 | O2-2363 | Values are not getting displayed (Staging) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ayyan Babar | [5 empty] | 2026-04-16 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2364 | O2-2364 | Add Quality Codes in Export pipeline table , update all crud operations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2367 | O2-2367 | Trigger AP returns “Variable 'StartTime' not found” error despite variable being configured | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2365 | O2-2365 | O2-1953 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2369 | O2-2369 | PPX marketing presentation for gas processing plant | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2368 | O2-2368 | O2-1595 | Muhammad Abdul Wasi | [5 empty] | 2026-04-15 | 2026-04-23 | 2026-04-15 | 2026-04-23 | 30
https://octopusdtlsupport.atlassian.net/browse/O2-2372 | O2-2372 | ADE–OmniAgent AutoRCA URS (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2371 | O2-2371 | O2-2370 | Muhammad Abdul Wasi | [5 empty] | 2026-04-08 | 2026-04-30 | 2026-04-09 | 2026-04-21 | 36
https://octopusdtlsupport.atlassian.net/browse/O2-2374 | O2-2374 | Handover By Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2373 | O2-2373 | O2-1953 | Muhammad Abbas | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2375 | O2-2375 | SQL Manual pipeline is not getting started and Showing An ERROR | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-04-17 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2376 | O2-2376 | Manual and Scheduled Export to SQL are not aligned in terms of data export. Please align both manual and scheduled export types for SQL export. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2377 | O2-2377 | On all types of SQL(Scheduled, Manual) This Error is getting displayed while we Stop or Start the Pipelie | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2378 | O2-2378 | Trigger Name Minimum Length Validation Not Implemented | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2379 | O2-2379 | Trigger-API-Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2326 | O2-2326 | O2-1953 | Muhammad Abbas | [5 empty] | 2026-04-16 | 2026-04-20 | 2026-04-17 | 2026-04-29 | 48
https://octopusdtlsupport.atlassian.net/browse/O2-2380 | O2-2380 | Non-Ebs Exp Calculations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Faiq Butt | [7 empty] | 2026-04-15 | 2026-04-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2381 | O2-2381 | What-If call using dynamic controls | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | O2-1993 | O2-1991 | Zain Munir | [5 empty] | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2382 | O2-2382 | Bug fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-20 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-239 | O2-239 | Latest values of GPS tag are not landing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2390 | O2-2390 | Pagination, footer, and grid UI get disturbed after creating multiple triggers | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-23 | 2026-04-21 | 2026-04-22 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2391 | O2-2391 | Batch Job On Demand API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Arslan sohail | [5 empty] | 2026-04-02 | 2026-04-06 | 2026-04-02 | 2026-04-06 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2392 | O2-2392 | BPM Job On Demand API | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Arslan sohail | [5 empty] | 2026-04-07 | 2026-04-09 | 2026-04-07 | 2026-04-09 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2393 | O2-2393 | Variables Mapping | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Arslan sohail | [5 empty] | 2026-04-10 | 2026-04-14 | 2026-04-10 | 2026-04-14 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2394 | O2-2394 | End to End Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | Arslan sohail | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2395 | O2-2395 | Trigger is not getting deleted and an error is displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 |  | 2026-04-20 | 2026-04-20 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-240 | O2-240 | Anomaly Detection V3 OCM Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Ali Qumail | [6 empty] | 2025-10-17 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2404 | O2-2404 | Support - Totalizer Calculation Pipeline Re-do (EMF)-Documentation and Meetings-subtask | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2397 | O2-2397 | O2-2396 | Mohsin Junaid | [7 empty] | 2026-04-06 | 2026-04-20 | 88
https://octopusdtlsupport.atlassian.net/browse/O2-2405 | O2-2405 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2385 | O2-2385 |  | Muhammad Abbas | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2406 | O2-2406 | Create Trigger API fails on decimal Recurrence input and shows multiple errors instead of a single validation message. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-20 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2407 | O2-2407 | Support- Read API Null and Missing Values Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2397 | O2-2397 | O2-2396 | Aiza Hamid | [5 empty] | 2026-04-07 | 2026-04-17 | 2026-04-07 | 2026-04-10 | 28
https://octopusdtlsupport.atlassian.net/browse/O2-2408 | O2-2408 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2112 | O2-2112 | O2-2105 | Muhammad Abbas | [5 empty] | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2409 | O2-2409 | Experimentation to replicate the same issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | O2-2399 | O2-2396 | Aiza Hamid | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-241 | O2-241 | After the recent release, the system is unable to create any type of connector — all API calls are failing. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2410 | O2-2410 | Totalizer tag added percentage | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | O2-2399 | O2-2396 | Aiza Hamid | [5 empty] | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-04-16 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2411 | O2-2411 | Logging for totalizer tags in SQL and in blob | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | O2-2399 | O2-2396 | Aiza Hamid | [5 empty] | 2026-04-17 | 2026-04-20 | 2026-04-17 | 2026-04-17 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2412 | O2-2412 | SQL optimization and redo of tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | O2-2399 | O2-2396 | Aiza Hamid | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2413 | O2-2413 | 🚫Blocker: Trigger creation fails in UTC and data export fails in Local time due to incorrect time validation handling | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-04-23 | 1.33
https://octopusdtlsupport.atlassian.net/browse/O2-2414 | O2-2414 | Implement info icon for time fields indicating all times should be in UTC | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2415 | O2-2415 | BPM RunOnDemand Bug Fix | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1920 | O2-1920 | O2-818 | Arslan sohail | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2417 | O2-2417 | Republish Job With Updated variable value | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2416 | O2-2416 | O2-10 | Arslan sohail | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2418 | O2-2418 | Bug Fixing Batch/Bpm Schedule | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2416 | O2-2416 | O2-10 | Arslan sohail | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2419 | O2-2419 | Design Review and Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | ahad omer | [5 empty] | 2026-04-06 | 2026-04-16 | 2026-04-06 | 2026-04-13 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-242 | O2-242 | How To | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-113 | O2-113 | O2-108 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2420 | O2-2420 | Trigger cannot be restarted after being stopped before first execution (of time. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Zain Munir | [5 empty] | 2026-04-20 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2421 | O2-2421 | Batch/BPM Code Improvements and testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | O2-1955 | O2-1953 | ahad omer | [5 empty] | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2422 | O2-2422 | Bug: I created an IT data pipeline, but when I edit the same pipeline, the pipeline type is shown as OT instead of IT. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2423 | O2-2423 | Bug: IT data is successfully exported to SQL, but the logs are not appearing on the Monitoring page. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2424 | O2-2424 | Bug: Trigger delete System Alarm is not available | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-23 | 2026-04-21 | 2026-04-23 | 1.33
https://octopusdtlsupport.atlassian.net/browse/O2-2425 | O2-2425 | Critical Bug: When the pipeline is stopped and restarted, it does not export data. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2426 | O2-2426 | Bug: While associating tags from the wizard, the asset list is not being displayed. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2427 | O2-2427 | Bug: After stopping and restarting the trigger, system alarms are not being triggered. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-23 | 2026-04-22 | 2026-04-23 | 1.83
https://octopusdtlsupport.atlassian.net/browse/O2-2428 | O2-2428 | Bug: Permissions for Trigger Start/Stop, Create, Update, Delete, and Read are not available in the Roles and Permissions module. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Muhammad Usman Javed | [5 empty] | 2026-04-20 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2429 | O2-2429 | Task: Error message should be only Pipeline name is duplicated or A Pipeline with this name already exist | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-243 | O2-243 | Restructure Enterprise Connectors to reflect latest updates + AI Friendly | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-100 | O2-100 | O2-94 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2430 | O2-2430 | Read the title below | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2431 | O2-2431 | Bug: The pipeline can still be edited while its associated trigger is turned on. The system should restrict users from editing a pipeline if any associated trigger is in the running state. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2432 | O2-2432 | Bug: Trigger names should not be allowed to consist of only numbers. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-22 | 2026-04-22 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-2433 | O2-2433 | Bug: In the case of minute-based recurrence, the minimum allowed limit should be 5 minutes, as it was implemented in this module before this enhancement. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-20 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-2434 | O2-2434 | Bug: Trigger should not create with only underscore in the name | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 0.5
https://octopusdtlsupport.atlassian.net/browse/O2-2435 | O2-2435 | An undefined/empty space is displayed at the bottom of the Trigger list page. Scrollbar is not properly implemented on the Trigger list page, resulting in a large empty space at the bottom. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2436 | O2-2436 | Bug (Security Concern): Password field can be exposed via DOM manipulation Issue: | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2437 | O2-2437 | Bug: Trigger name is not visible on the Monitoring page, which is necessary because multiple triggers can be associated with a single pipeline. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-22 | 2026-04-24 | 2026-04-22 | 2026-04-23 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2438 | O2-2438 | Task: This should be Site name | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 0.17
https://octopusdtlsupport.atlassian.net/browse/O2-2439 | O2-2439 | Bug: Unable to export Site Hierarchy | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-244 | O2-244 | REST API Fields and How Tos | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-100 | O2-100 | O2-94 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2440 | O2-2440 | Bug: In the case of Data, Stat, and Quality Code alarms, the following options should not be displayed: Resolution Value Data Quality Filter Aggregate | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2441 | O2-2441 | Bug: Unable to export alarms | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2442 | O2-2442 | Site Hierarchy trigger created successfully but data is not exported to SQL | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2443 | O2-2443 | QA Reported Bugs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Zain Munir | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2444 | O2-2444 | Tags creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2347 | O2-2347 | O2-2340 | Ameer Hamza Khan | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2445 | O2-2445 | Alarms configuration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2347 | O2-2347 | O2-2340 | Ameer Hamza Khan | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2446 | O2-2446 | Changings are not getting saved and Showing Error after deleting few tags from SQL pipeline | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-22 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2447 | O2-2447 | Mapped name of tags are not getting displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2449 | O2-2449 | Testing by kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | kamran khalid | [5 empty] | 2026-04-21 | 2026-04-23 | 2026-04-21 | 2026-04-23 | 19
https://octopusdtlsupport.atlassian.net/browse/O2-245 | O2-245 | Latest values for some real time tags are not updating also other tag values are updating with 5 mins interval | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Unassigned | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2450 | O2-2450 | Testing by Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Waqar Rasheed | [5 empty] | 2026-04-22 | 2026-04-24 | 2026-04-22 | 2026-04-29 | 26.25
https://octopusdtlsupport.atlassian.net/browse/O2-2451 | O2-2451 | Diagnostics Alarm Not Triggered Despite No Latest Values Since 10:55 | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Mohsin Junaid | [5 empty] | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-22 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2452 | O2-2452 | Data center Specified module failed on staging | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Faiza Nasir | [7 empty] | 2026-04-22 | 2026-04-22 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2455 | O2-2455 | “Get Latest Values” Not Working for Single and Bulk Write Back | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2456 | O2-2456 | IT table and Time stamp column name is getting removed , While editing IT pipelines. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2457 | O2-2457 | State duplication occurred in Totalizer tags Alarms | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2458 | O2-2458 | Unable to Verify Phone number for SMS alerts | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2459 | O2-2459 | Diagnostics Email Alerts Are Not Being Received | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2460 | O2-2460 | Scheduled scanning is unable to retrieve new parameters in the case of Digital Log. Additionally, on multiple scan triggers, it is duplicating the newly added parameters. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Muhammad Usman Javed | [7 empty] | 2026-04-22 | 2026-04-22 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2461 | O2-2461 | Implement and integrate hyperbolic functions (sinh, cosh, tanh, etc.) in both offline and online calculation flows, ensuring consistency and validating results through developer testing + Backfilling of missing data on Prod - AZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | Arsalan Zafar Khan | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 7
https://octopusdtlsupport.atlassian.net/browse/O2-2462 | O2-2462 | Research and fix SOLVER formula calculation to return expected values | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | Arsalan Zafar Khan | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2463 | O2-2463 | Batch Backend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Syed Yousaf Qadri | [5 empty] | 2026-03-17 | 2026-03-25 | 2026-03-17 | 2026-03-25 | 26
https://octopusdtlsupport.atlassian.net/browse/O2-2464 | O2-2464 | Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | O2-1437 | O2-818 | Syed Yousaf Qadri | [5 empty] | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2465 | O2-2465 | Omni-ALA Walk through Sessions + Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | O2-2124 | O2-460 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2467 | O2-2467 | Add charting to Output Schemas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-03-25 | 2026-03-27 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2468 | O2-2468 | Add Bar to charting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-03-23 | 2026-03-23 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2469 | O2-2469 | Add line to charting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-247 | O2-247 | Real time totalizer tag values are not updated in latest values screen, where as cal tag totalizer values are updated. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2470 | O2-2470 | Add column to charting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2471 | O2-2471 | Collapse Resolver to Orchestrator | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-04-15 | 2026-04-17 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2472 | O2-2472 | Integration Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-03-10 | 2026-03-18 | 40.5
https://octopusdtlsupport.atlassian.net/browse/O2-2473 | O2-2473 | Agent Improvements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | O2-1342 | O2-1340 | Unassigned | [7 empty] | 2026-03-16 | 2026-03-16 | 6.5
https://octopusdtlsupport.atlassian.net/browse/O2-2474 | O2-2474 | Improve Instructions for each agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | O2-2003 | O2-2001 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-04-20 | 2026-04-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2478 | O2-2478 | No data is getting exported to SQL nor Monitoring logs are getting displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2479 | O2-2479 | Code Review | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2475 | O2-2475 | O2-1953 | Syed Yousaf Qadri | [5 empty] | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-248 | O2-248 | The development team needs to add support for REST APIs without time parameters. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2480 | O2-2480 | Architecture Design | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2281 | O2-2281 | O2-2277 | Syed Yousaf Qadri | [5 empty] | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2481 | O2-2481 | Batch Alarm Engine POC | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2282 | O2-2282 | O2-2277 | Syed Yousaf Qadri | [5 empty] | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-22 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2482 | O2-2482 | Batch Alarm Engine Design | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2282 | O2-2282 | O2-2277 | Unassigned | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2483 | O2-2483 | Handover session - kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2273 | O2-2273 | O2-2269 | Unassigned | [7 empty] | 2026-04-16 | 2026-04-16 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2484 | O2-2484 | Testing BY Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2274 | O2-2274 | O2-2269 | Unassigned | [7 empty] | 2026-04-16 | 2026-04-20 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2485 | O2-2485 | Handover to QA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | O2-2265 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2486 | O2-2486 | Requirements Change / Rework | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | O2-1977 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-04-15 | 2026-04-24 | 2026-04-15 | 2026-04-23 | 39
https://octopusdtlsupport.atlassian.net/browse/O2-2487 | O2-2487 | Need to remove the extra stats alarms related to Schedule SQL start and stop | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-23 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-2488 | O2-2488 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-27 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2489 | O2-2489 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Zeeshan Sarwar | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-29 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-249 | O2-249 | Enhance the system to support custom date-time formats while creating connectors. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2490 | O2-2490 | Unit Testing & Fixes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | O2-1993 | O2-1991 | Zain Munir | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2491 | O2-2491 | Weekly Scheduled export to SQL FAILED, NO monitoring no export | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2492 | O2-2492 | Schedule Type as Monthly Export is also Failed with Data Alarm | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2493 | O2-2493 | Bugs Fixing and management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ameer Hamza Khan | [5 empty] | 2026-04-15 | 2026-04-29 | 2026-04-15 | 2026-04-29 | 64
https://octopusdtlsupport.atlassian.net/browse/O2-2494 | O2-2494 | Task | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2495 | O2-2495 | Bug Fixing and Discussions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-250 | O2-250 | Trigger execution functionality should be separated from data fetching logic. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2502 | O2-2502 | Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | Faiq Butt | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2503 | O2-2503 | Non-Ebs Advisory Calculations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Faiq Butt | [5 empty] | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-30 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-2504 | O2-2504 | Dispatch Advisory Methodology (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Danish Rashid | [5 empty] | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-30 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-2505 | O2-2505 | Cost Review and Optimizations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1990 | O2-1990 | O2-1109 | Taimur Zahid | [5 empty] | 2026-03-16 | 2026-03-31 | 2026-03-18 | 2026-03-25 | 14.5
https://octopusdtlsupport.atlassian.net/browse/O2-2506 | O2-2506 | Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Danish Rashid | [5 empty] | 2026-05-13 | 2026-05-31 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2508 | O2-2508 | Product Demo to Kwang 24/04/26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-705 | O2-705 | O2-221 | Sarmad Sabir | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-251 | O2-251 | Latest values not updating since yesterday but Diagnostics alarm not fired yet | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2512 | O2-2512 | Copilot Access and Administration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2511 | O2-2511 | O2-2510 | Taimur Zahid | [5 empty] | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-01 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2515 | O2-2515 | Code Research + Understanding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | O2-2514 | O2-199 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-2516 | O2-2516 | Integration of graph and new tab(OPC Server) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | O2-2514 | O2-199 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2517 | O2-2517 | Deployment to staging + Bug Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | O2-2514 | O2-199 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2518 | O2-2518 | Bug Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | O2-2514 | O2-199 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2519 | O2-2519 | Meeting + Code Understanding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | O2-2193 | O2-2188 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-252 | O2-252 | Design Document template creation using AI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2520 | O2-2520 | Meeting + Code Understanding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | O2-2203 | O2-2189 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2545 | O2-2545 | Identify issues and fix during the testing flow in template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-28 | 2026-04-30 | 2026-04-28 | 2026-04-28 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-2546 | O2-2546 | Thorough flow walk through and fixes additional property creation to asset activation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2548 | O2-2548 | Real-time tag latest values are not populating for any device type on the newly created site. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | O2-2448 | O2-1395 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2557 | O2-2557 | Project Structure, Redux, Internationalization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2550 | O2-2550 | O2-2549 | Zain Munir | [5 empty] | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-30 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-2558 | O2-2558 | Invalid error message persists and blocks trigger creation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Sarmad Sabir | [5 empty] | 2026-04-28 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2559 | O2-2559 | Weekly and Monthly triggers are still FAILED for SQL Pipelines | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-256 | O2-256 | Latest value of calculated tag is not updating. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2564 | O2-2564 | Support for Omniagent Charting (AMcharts) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-27 | 48
https://octopusdtlsupport.atlassian.net/browse/O2-2565 | O2-2565 | Sync Site configuration Button and API integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-04-13 | 2026-04-17 | 2026-04-13 | 2026-04-17 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-2566 | O2-2566 | Back-end Integration- Part C | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [5 empty] | 2026-04-01 | 2026-04-10 | 2026-04-01 | 2026-04-10 | 56
https://octopusdtlsupport.atlassian.net/browse/O2-2567 | O2-2567 | Code Merge (OmniAgent Feature and Prod) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | O2-1472 | O2-1461 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2568 | O2-2568 | Schedule SQL is Failed when Granularity =Day, Job Start Time = Day | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2569 | O2-2569 | Template issues and configuration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1030 | O2-1030 | O2-1028 | DANIYAL AHMAD | [5 empty] | 2026-04-22 | 2026-04-30 | 2026-04-23 | 2026-04-24 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-257 | O2-257 | Conditional cal tag latest values are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2570 | O2-2570 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | DANIYAL AHMAD | [5 empty] | 2026-04-14 | 2026-04-30 | 2026-04-21 | 2026-04-22 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2571 | O2-2571 | API Modification for Digital Twin Models | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | O2-2187 | O2-2186 | Faiza Nasir | [5 empty] | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-2572 | O2-2572 | Bug Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-27 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2575 | O2-2575 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Namra Zahid | [5 empty] | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-05 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2576 | O2-2576 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | kamran khalid | [5 empty] | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-05 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2577 | O2-2577 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Zeeshan Sarwar | [5 empty] | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-05 | 25.5
https://octopusdtlsupport.atlassian.net/browse/O2-2578 | O2-2578 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Waqar Rasheed | [5 empty] | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-05 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2579 | O2-2579 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-05 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-258 | O2-258 | Bugs Fixing, Tasks, Improvements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2580 | O2-2580 | development of landing pattern fix on totalizers | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2398 | O2-2398 | O2-2396 | Unassigned | [5 empty] | 2026-04-20 | 2026-05-10 | 2026-04-21 | 2026-04-30 | 56
https://octopusdtlsupport.atlassian.net/browse/O2-2581 | O2-2581 | Production Green Release Management / Deployment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2573 | O2-2573 | O2-1976 | Faiza Nasir | [5 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2582 | O2-2582 | Live values of real/ cal tags are not getting populated. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ayyan Babar | [5 empty] | 2026-04-30 | 2026-05-01 | 2026-04-30 | 2026-04-30 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2583 | O2-2583 | “Get Latest Values” Not Working for Single and Bulk Write Back | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2584 | O2-2584 | Model is not getting created for Anomaly Group | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2585 | O2-2585 | Unable to verify number for SMS_OPT_IN | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2586 | O2-2586 | SQL pipelines are getting displayed with triggers in monitoring logs | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2587 | O2-2587 | Invalid Critical Errors are getting displayed of un-authorization and Read API Issue of Customer and site not found, In logs. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2588 | O2-2588 | UI + API Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | O2-2203 | O2-2189 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2589 | O2-2589 | UI + API Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | O2-2193 | O2-2188 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-259 | O2-259 | Latest values for MQTT device are not updating while Live Telemetry show latest values | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2590 | O2-2590 | Integration of Wide Format(FrontEnd) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | O2-2193 | O2-2188 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2591 | O2-2591 | Integration of Wide Format(FrontEnd) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | O2-2203 | O2-2189 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2592 | O2-2592 | Testing+ Fixed Issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | O2-2193 | O2-2188 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2593 | O2-2593 | Testing + Fixed Issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | O2-2203 | O2-2189 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2594 | O2-2594 | Meeting with DE team + New Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | O2-2193 | O2-2188 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2595 | O2-2595 | Meeting with DE team + New Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | O2-2203 | O2-2189 | Muhammad Ahmad Saleem | [5 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-2596 | O2-2596 | NO Values for these tags Calculated, Timer, Counter, Totalizer Real, Totalizer Cal. With New Site. Only Real and GPS values are here. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2598 | O2-2598 | Identify Productisable entities from implementation working | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2597 | O2-2597 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-04-28 | 2026-04-30 | 2026-04-28 | 2026-04-30 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-2599 | O2-2599 | Develop Produstisation approach / areas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2597 | O2-2597 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-05-04 |  | 2026-05-05 | 2026-05-05 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-260 | O2-260 | Values are not showing on Write back screen after clicking on Get latest values button | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2600 | O2-2600 | The System Alarms need to be updated in the green environment to align with the staging environment. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ameer Hamza Khan | [7 empty] | 2026-05-04 | 2026-05-04 | 1.5
https://octopusdtlsupport.atlassian.net/browse/O2-2601 | O2-2601 | The SQL has failed again. No data is being displayed in the logs or in the SQL database tables. Please investigate and resolve the issue. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2602 | O2-2602 | An issue has been observed where state duplication occurs along with multiple states being triggered at the same timestamp for a single tag. This results in conflicting state entries and inconsistent system behavior | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2603 | O2-2603 | The Watchdog module is missing in the Docker deployment on Green Production. Due to this, critical metrics including Upload Speed, Download Speed, and OPC Server metrics are not being populated in the system. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Muhammad Yousha Agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2604 | O2-2604 | Process pre-sales support, Customer / Management Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | O2-1066 | O2-221 | Mariam Zulfiqar | [5 empty] | 2026-05-01 |  | 2026-05-05 | 2026-05-05 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2605 | O2-2605 | Process Eng. tasks: working, review and management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | O2-1254 | O2-1070 | Mariam Zulfiqar | [5 empty] | 2026-05-01 | 2026-05-29 | 2026-05-04 | 2026-05-05 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2606 | O2-2606 | Email Notifications are not getting received as alarms are triggering | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2609 | O2-2609 | Displaying Dynamic Headers for each KPI Step | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2608 | O2-2608 | O2-2607 | Zain Munir | [5 empty] | 2026-05-04 | 2026-05-08 | 2026-05-05 | 2026-05-08 | 26
https://octopusdtlsupport.atlassian.net/browse/O2-261 | O2-261 | Account activation link should valid for 24 hours and if user send new link after 24 hours from web front-end then old link should expire | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2610 | O2-2610 | The Run On Demand popup for Batch and BPM jobs is behaving incorrectly across environments | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2611 | O2-2611 | Release Support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2573 | O2-2573 | O2-1976 | Zain Munir | [5 empty] | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 6
https://octopusdtlsupport.atlassian.net/browse/O2-2612 | O2-2612 | Duplicated real tags Bug Reproduced again, Kindly Check | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2613 | O2-2613 | Variable Speed Compressor Template (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1046 | O2-1046 | O2-1044 | Muhammad Abdul Wasi | [5 empty] | 2026-04-01 | 2026-04-30 | 2026-04-28 | 2026-04-29 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2614 | O2-2614 | Omni Agent Invalid response: Show my Assets with asset type and asset names | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2615 | O2-2615 | Tooltip Spacing Issue on Green Prod Compared to Prod Blue | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | O2-2574 | O2-1395 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2616 | O2-2616 | OC Process Testing RCA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | O2-1048 | O2-1044 | DANIYAL AHMAD | [5 empty] | 2026-05-04 | 2026-05-20 | 2026-05-04 | 2026-05-06 | 20
https://octopusdtlsupport.atlassian.net/browse/O2-2617 | O2-2617 | Data Prep. & Offline testing - Sync Motor | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1032 | O2-1032 | O2-1028 | DANIYAL AHMAD | [5 empty] | 2026-05-01 | 2026-05-22 | 2026-05-04 | 2026-05-07 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2618 | O2-2618 | OC process Testing RCA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | O2-1048 | O2-1044 | DANIYAL AHMAD | [5 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2
https://octopusdtlsupport.atlassian.net/browse/O2-2619 | O2-2619 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | O2-1048 | O2-1044 | Muhammad Abdul Wasi | [5 empty] | 2026-04-28 | 2026-04-30 | 2026-04-29 | 2026-04-30 | 11
https://octopusdtlsupport.atlassian.net/browse/O2-262 | O2-262 | Development Tools permission are not working | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2620 | O2-2620 | APX WIF Training Material | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1016 | O2-1016 | O2-221 | Muhammad Abdul Wasi | [5 empty] | 2026-04-27 | 2026-04-30 | 2026-04-24 | 2026-04-27 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-2621 | O2-2621 | OmniOEE Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | O2-1855 | O2-1302 | Muhammad Abdul Wasi | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-2623 | O2-2623 | Research and evaluate approaches for integrating Excel-based calculations into C# (Interop vs alternative libraries) for ChilloWatt. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2622 | O2-2622 | O2-2607 | Arsalan Zafar Khan | [5 empty] | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2624 | O2-2624 | Research on Logic + Joint Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2622 | O2-2622 | O2-2607 | Zain Munir | [7 empty] | 2026-05-04 | 2026-05-05 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2625 | O2-2625 | Release bugs fixing, and release management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | O2-2276 | O2-1976 | Ameer Hamza Khan | [5 empty] | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2626 | O2-2626 | API for Chillowat incorporation and APX configurational module enhancements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2608 | O2-2608 | O2-2607 | Ameer Hamza Khan | [5 empty] | 2026-05-06 |  | 2026-05-06 | 2026-05-07 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2628 | O2-2628 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | kamran khalid | [5 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2629 | O2-2629 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Waqar Rasheed | [5 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-263 | O2-263 | OT Pipeline is not executing — showing 404 error, even though Test API and Create Pipeline show success | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2630 | O2-2630 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Zeeshan Sarwar | [5 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2631 | O2-2631 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Namra Zahid | [5 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-08 | 21
https://octopusdtlsupport.atlassian.net/browse/O2-2632 | O2-2632 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2633 | O2-2633 | CRITICAL: False alarms triggered for Boolean tag — TRUE-configured alarm firing on FALSE state and condition set by default & not editable | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2634 | O2-2634 | Read API fail to fetch False Alarm against Boolean tag | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Aiza Hamid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2635 | O2-2635 | Different Alarm states are triggering for a single totalizer Tag on same timestamp | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2636 | O2-2636 | Anomaly Group Results screen is displaying Error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2637 | O2-2637 | Omni Agent displays False results in response. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2638 | O2-2638 | Invalid response for assets types again | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | O2-2627 | O2-1395 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-264 | O2-264 | Unable to start OT Data Pipeline when running manually | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2640 | O2-2640 | Extra Space Displayed Between Tooltip Icon and Tooltip Popup | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | O2-2639 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2641 | O2-2641 | Different Alarm states are triggering for a single totalizer Tag on same timestamp | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | O2-2639 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2642 | O2-2642 | An issue has been observed where state duplication occurs along with multiple states being triggered at the same timestamp for a single tag. This results in conflicting state entries and inconsistent system behavior | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | O2-2639 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2643 | O2-2643 | Email Notifications are not getting received as alarms are triggering from "alerts@octopusdtl.com" account | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | O2-2639 | O2-1395 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2644 | O2-2644 | The Watchdog module is missing in the Docker deployment on Green Production. Due to this, critical metrics including Upload Speed, Download Speed, and OPC Server metrics are not being populated in the system. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | O2-2639 | O2-1395 | Muhammad Yousha Agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2645 | O2-2645 | Table Conflict Detected popup appears when user tries to publish a BPM job in a new site. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | O2-2639 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2646 | O2-2646 | when user selects an existing table while creating a BPM job an error occurs that "NO publish Columns Found in the request" | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | O2-2639 | O2-1395 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2647 | O2-2647 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2213 | O2-2213 | O2-2188 | kamran khalid | [5 empty] | 2026-05-07 | 2026-05-13 | 2026-05-07 | 2026-05-08 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-2649 | O2-2649 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2648 | O2-2648 | O2-1395 | Muhammad Abbas | [5 empty] | 2026-05-07 | 2026-05-11 | 2026-05-07 | 2026-05-08 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-265 | O2-265 | IT Data Pipeline stuck in “In Progress” state when run manually | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2650 | O2-2650 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2214 | O2-2214 | O2-2189 | Waqar Rasheed | [5 empty] | 2026-05-08 | 2026-05-13 | 2026-05-08 | 2026-05-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2651 | O2-2651 | Testing by Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1995 | O2-1995 | O2-1991 | Zeeshan Sarwar | [7 empty] | 2026-05-08 | 2026-05-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-2652 | O2-2652 | Development (if required) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Unassigned | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2653 | O2-2653 | Asset Design, HB and Expected models (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Danish Rashid | [5 empty] | 2026-05-01 | 2026-05-08 | 2026-05-04 | 2026-05-08 | 40
https://octopusdtlsupport.atlassian.net/browse/O2-2654 | O2-2654 | APX Engine per Development (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Faiq Butt | [5 empty] | 2026-05-04 | 2026-05-08 | 2026-05-04 | 2026-05-07 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-2655 | O2-2655 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | O2-2245 | O2-1981 | Danish Rashid | [5 empty] | 2026-05-11 | 2026-05-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-2656 | O2-2656 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | DANIYAL AHMAD | [5 empty] | 2026-05-05 | 2026-05-22 | 2026-05-07 | 2026-05-08 | 10
https://octopusdtlsupport.atlassian.net/browse/O2-2657 | O2-2657 | Template, wizards and dashboard design (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | O2-2246 | O2-1981 | Faiq Butt | [7 empty] | 2026-05-08 | 2026-05-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-266 | O2-266 | Test API validation for Start Time, End Time, and Time Format missing — system allows Connector creation without proper validation. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-267 | O2-267 | Full log file is not showing for failed scheduled and manual triggers. The system should display and provide the failed JSON response file in a downloadable format for both IT and OT pipelines. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-268 | O2-268 | Content Generation for DDS Design Overview Using AI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-269 | O2-269 | Notification group selection drop down is displaying on import site layout screen as well as on login screen. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-270 | O2-270 | Wrong error message is displaying when I tried to create 3 areas through import site layout. All records are added but empty records are displaying in fault file. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-271 | O2-271 | Notification group is inactive error displaying in fault file where as data alarms notifications are enabled in site. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-272 | O2-272 | Tags having notification groups added in import site layout file are not adding when only data alarms notification configurations are enabled in respective site but they are adding when both data alarms and APX notification configurations are enabled. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-273 | O2-273 | Statistical alarms notification group configured through import site layout are not displaying in configurations of real time and calculated tags against 24 hour duration on front end. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-274 | O2-274 | No character limit is applied while creating area from import site layout where as maximum 15 character limit is applied on front end, also wrong error message is displaying when character limit is reached on front end. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-275 | O2-275 | Conditional cal tags in which simple cal tags are used, they are displaying in counter and timer tags listing while viewing dependencies of simple calculated tag. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ali Qumail | [5 empty] | 2025-10-15 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-276 | O2-276 | All tag's values are not getting landing for IOT, Kindly look into it | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-277 | O2-277 | REST API OT Connector is failing during execution. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-278 | O2-278 | String and Datetime tag data not displaying on Latest Value page after successful OT REST API data ingestion. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-279 | O2-279 | OMNI Agent fails to return all tables with schema, whereas the Read API supports this functionality. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-280 | O2-280 | Generated Content Integration in the Document with Formatting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-283 | O2-283 | Creation modal closes when user enters a duplicate name for Workflow or Trigger instead of remaining open after showing error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-284 | O2-284 | if final table name is not defined then BPM should not be published and if name is defined but schema is not defined incase of new table then system should throw error on both | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-285 | O2-285 | Wrong fault records quantity is displaying in imports site layout screen after uploading a file. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-286 | O2-286 | BPM validation job fails showing "The BPM Validation Job Failed" message, but the Activity Status does not display any corresponding error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-287 | O2-287 | When user uses activity name as table name inside other activity then upon validation the result shows but when user runs triggers it shows error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-288 | O2-288 | APX real time and calculated tag latest values are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-289 | O2-289 | Latest values of tags created through import site layout are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-290 | O2-290 | Real time tag latest values created using MQTT device are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-291 | O2-291 | Timer Tag's values are not getting landed in OmniConnect. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Namra Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-292 | O2-292 | Azure SQL (IT) connector is not getting created on sites where SAP HANA or ODBC connectors are already created. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-293 | O2-293 | The user has created multiple tags from the IoT device using the same source tag. However, the live value is populating for only one tag, while the others are not updating. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-294 | O2-294 | Data alarm not triggering for the IOT tag alarm as its value is populating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-295 | O2-295 | Value is not displaying on the Query Validation screen in the Batch BPM module, whereas the same value appears correctly when the user downloads the CSV file. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-296 | O2-296 | Integer type of tags have no values,IOT | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-298 | O2-298 | Tag values imported through CSV bulk import are not displaying accordingly in export to excel when resolution time is 30 days. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-299 | O2-299 | In Batch BPM, query with semicolon (;) at the end shows data in preview but fails on execution | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-300 | O2-300 | Logic App Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-301 | O2-301 | Data Factory Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-302 | O2-302 | IoT Hub Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-303 | O2-303 | CORS error occurs while calling REST API Connector using Bearer Token authentication | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-304 | O2-304 | iothub data is stored from iothub as is | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-111 | O2-111 | O2-108 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-305 | O2-305 | Latest value of date time against DL tag is displaying in UTC where as DL organization as well as OC site is set to local time. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-306 | O2-306 | Temp table is showing in Activity Query modal and when user select any temp table then it is showing error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-307 | O2-307 | Validate button in the query modal is showing Green tick "Query is successfully validated" on the same time the system is showing error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-308 | O2-308 | Query with validation errors is still being saved upon clicking the Validate button when user closes the query modal and reopen it | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-318 | O2-318 | AI Chat fails to retrieve the latest record from the table in OMNI Data Analysis | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-319 | O2-319 | New Asset Sub types setup for Template for process team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-320 | O2-320 | Creating Scanner For RestAPI Pulls | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-321 | O2-321 | Creating Generic API Caller | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-322 | O2-322 | OT Data Formatting and Ingestion to ADX | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-323 | O2-323 | AI Chat fails to answer the query “Can you show me the edge metrics details of device ID 7950” | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-324 | O2-324 | Downloaded result CSV does not show full timestamp — only minutes and seconds are displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-325 | O2-325 | Downloaded JOSN Txt file should only contain data and exclude return description, asset info, and other metadata | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-326 | O2-326 | Agent returns associated tag list with distorted UI in AI Chat | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-332 | O2-332 | AI Chat returns an error when analyzing tag hourly maximums and averages | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-334 | O2-334 | zee 127 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-335 | O2-335 | test | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-317 | O2-317 | O2-199 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-337 | O2-337 | 1 | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-223 | O2-223 | O2-221 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-339 | O2-339 | AI Chat returns invalid data when comparing timestamps for two tags with expected values | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-340 | O2-340 | OCM Frontend Integration Anomaly | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-68 | O2-68 | O2-37 | Ali Qumail | [5 empty] | 2025-10-01 | 2025-10-17 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-343 | O2-343 | Frontend Development + Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-104 | O2-104 | O2-95 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-346 | O2-346 | SQL Scheduled logs UI is Disturbed, Issue was fixed on staging | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Namra Zahid | [5 empty] | 2025-10-20 | 2025-10-20 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-349 | O2-349 | Stats Alarm Schedule SQL: Showing failure in logs but data is displayed in SQL | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-354 | O2-354 | Industry "Transportation" is Duplicated in Site Creation and update | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-99 | O2-99 | O2-94 | Namra Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-355 | O2-355 | Productin Release Blue Env | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-101 | O2-101 | O2-94 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-357 | O2-357 | OCM-Regression | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Abbas | [5 empty] | 2025-10-21 | 2025-11-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-358 | O2-358 | Umair Iftikhar - Quick Security Questions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-356 | O2-356 | O2-133 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-359 | O2-359 | How To - Batch | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-47 | O2-47 | O2-9 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-360 | O2-360 | How to - BPM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-47 | O2-47 | O2-9 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-362 | O2-362 | Fields - BPM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-47 | O2-47 | O2-9 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-363 | O2-363 | Bug Fixing, Improvements and Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-364 | O2-364 | Bug Fixing, Improvements and Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-365 | O2-365 | How to - Anomaly Detection Updates | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-70 | O2-70 | O2-37 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-366 | O2-366 | Fields - Anomaly Detection Updates | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-70 | O2-70 | O2-37 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-367 | O2-367 | Backend Connectors and Trigger APIs modifications | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-104 | O2-104 | O2-95 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-368 | O2-368 | New Schema changes for Pipeline | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-104 | O2-104 | O2-95 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-369 | O2-369 | SFTP Pipeline APIs development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-104 | O2-104 | O2-95 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-370 | O2-370 | Handover to QA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-68 | O2-68 | O2-37 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-371 | O2-371 | Generate DDS Sequence diagram through AI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-374 | O2-374 | OCM Anomaly V3 Internal Bugs/Improvements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-68 | O2-68 | O2-37 | Ali Qumail | [5 empty] | 2025-10-21 | 2025-10-30 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-375 | O2-375 | SFTP Development for JSON and CSV formats | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-104 | O2-104 | O2-95 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-376 | O2-376 | Read AI Update for Device Diagnostics | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-154 | O2-154 | O2-151 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-378 | O2-378 | Deleted Cal Tag Duplicating While we access the dependencies of any type of tag which is used in this cal tag | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Namra Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-379 | O2-379 | Ingestion Format unusual behavior | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Waqar Rasheed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-380 | O2-380 | When user tries to set datapoints using floating values the validation is missing i.e (only numeric values ) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Waqar Rasheed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-381 | O2-381 | User unable to create same name notification group in different SIs. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-382 | O2-382 | Resource creation ticket for data center specificity is not getting created when the site is created in a data center other than Southeast Asia. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-383 | O2-383 | Omni Agent Chat responds to queries from other sites even when the user has selected a different site. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-384 | O2-384 | Agent returns data when user shares a Read API payload — which is not a valid implementation. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-387 | O2-387 | User has created multiple tags from the IoT device using the same source tag. However, the live value is populating for only one tag, while the others are not updating.# | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-388 | O2-388 | While updating the Data Points of a specific site, all other sites are getting system alarms of it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-389 | O2-389 | Counter tag latest values are not updating. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-390 | O2-390 | Timer Tag latest values are not showing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Waqar Rasheed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-391 | O2-391 | Latest values for AHU and variable pump speed performance APX asset are not updating. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-392 | O2-392 | Once a user validates an activity with error, the system incorrectly sets the validation status to true and displays the “Save Output” button and upon clicking on “Save Output,” the system throws error “Failed to publish activity | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-393 | O2-393 | The GPS tag is not displaying the Longitude and Latitude values — only the Altitude value is being shown. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Namra Zahid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-394 | O2-394 | when user uses a temp table of another BPM Workflow activity it shows error | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-395 | O2-395 | APx And BPM Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-377 | O2-377 | O2-35 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-396 | O2-396 | when user using existing functionality uses a batch job with OT function and while validating its not showing the "Status Code" and "ID" column empty | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-397 | O2-397 | Bug Fixing / Deployments | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-98 | O2-98 | O2-94 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-429 | O2-429 | Cal tags values are not getting updated | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Namra Zahid | [5 empty] | 2025-10-24 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-430 | O2-430 | Backend APIs for Pipeline & Triggers | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-104 | O2-104 | O2-95 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-431 | O2-431 | Update option is not showing when user open saved trending graph and click on Save as button | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ali Qumail | [5 empty] | 2025-10-27 | 2025-10-29 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-432 | O2-432 | Invalid modeled tags count is getting displayed for user Trained anomaly group, Kindly look into it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Zeeshan Aslam | [5 empty] | 2025-10-24 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-434 | O2-434 | Smoke-Production | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Muhammad Abbas | [5 empty] | 2025-10-27 | 2025-10-28 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-435 | O2-435 | Production Green Deployment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-17 | O2-17 | O2-9 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-436 | O2-436 | Internal Server error is showing while creating conditional cal tag | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Waqar Rasheed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-437 | O2-437 | Internal Server error is showing while creating Timer Tag | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Waqar Rasheed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-438 | O2-438 | Totalizer Calculated tag live values are not showing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Waqar Rasheed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-439 | O2-439 | Drop down options are not displaying in model relaxation factor of anomaly creation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-440 | O2-440 | Analyzing KeyVault integration in OC | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Faiza Nasir | [5 empty] | 2025-10-27 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-451 | O2-451 | Import site layout failed. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-537 | O2-537 | APX output calculated tags are not displaying on latest values screen even after hitting publish changes multiple times. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-16 | O2-16 | O2-9 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-541 | O2-541 | When import data toggle in role management is disabled in edge configuration then it should be restricted from IOT and MQTT establish connection option as well. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-542 | O2-542 | GPS latest values for both IOT and MQTT devices are not displaying. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-544 | O2-544 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-68 | O2-68 | O2-37 | Mariam Zulfiqar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-545 | O2-545 | Unable to search real time tag while creating totalizer tag. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-546 | O2-546 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Mariam Zulfiqar | [5 empty] | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-547 | O2-547 | Re-do for Existing Asset (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Mariam Zulfiqar | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-550 | O2-550 | Latest values for write back and Bulk write are not getting displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-551 | O2-551 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-515 | O2-515 | O2-457 | Mariam Zulfiqar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-552 | O2-552 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-523 | O2-523 | O2-458 | Mariam Zulfiqar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-553 | O2-553 | Bugs Fixing + Tasks + Improvements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-105 | O2-105 | O2-95 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-554 | O2-554 | OC Process Testing (P) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-531 | O2-531 | O2-459 | Danish Rashid | [5 empty] | 2026-01-14 | 2026-01-16 | 2026-01-14 | 2026-01-16 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-555 | O2-555 | Repetition is displaying against selected single tag in results of user-trained anomaly. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-556 | O2-556 | Real time tag names are not displaying in results of user trained anomaly. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-557 | O2-557 | all types of tags values are not getting landed because there are no values for real time tags, kindly look into it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-558 | O2-558 | GPS listing screen is not loading. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-559 | O2-559 | All tags are selected in waiting to transfer screen when page record is only set to 50 where as its working fine in import data point screen. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-560 | O2-560 | Totalizer Tag creation popup is not closed after tag creation also created tag shows on listing screen after manual refresh | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ali Qumail | [5 empty] | 2025-11-04 | 2025-11-05 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-562 | O2-562 | SFTP - Create - Manual IR Configuration Guide | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-106 | O2-106 | O2-95 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-563 | O2-563 | How to - Create - Create New SFTP Connector | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-106 | O2-106 | O2-95 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-564 | O2-564 | Fields - Update - Create New Connector | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-106 | O2-106 | O2-95 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-565 | O2-565 | How to - Update - Add a table of Site-level Validations for Connectors | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-106 | O2-106 | O2-95 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-567 | O2-567 | User is able to create Batch/BPM workflow and Batch/BPM Trigger with only numeric characters. It should be Alpha-numeric | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-568 | O2-568 | Anomaly Error: Failed to save the anomaly Data selection time slot. while we select multiple time slots to verify 720 hours to be available in timeslots. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Ahmad Saleem | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-569 | O2-569 | Create/Edit modal of Real Time and Calculated tag of type Boolean is showing error on Set points field | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ali Qumail | [5 empty] | 2025-11-04 | 2025-11-04 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-570 | O2-570 | As mentioned in both info notes "You can select a maximum of 720 hours of data for training." we are not able to select 720 hours of data for training. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Ahmad Saleem | [5 empty] | 2025-11-03 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-571 | O2-571 | Float type tag values are not getting updated | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-572 | O2-572 | Selected tags from the fields disappeared when user Edit the Time and Counter Tags | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ali Qumail | [5 empty] | 2025-11-06 | 2025-11-06 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-573 | O2-573 | Generate ERD Diagram using AI Plant UML | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [7 empty] | 2026-01-30 | 2026-01-30 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-574 | O2-574 | Generate Flow Diagrams | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-575 | O2-575 | Finalize Content of DDS | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-576 | O2-576 | BPM Activity Deletion system alarm is not triggering | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-578 | O2-578 | When the user clicks Save and Publish after executing all and saving the output, an error appears saying "Table is required." However, when the user clicks on End Activity to add a table, the Save button does not appear. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-579 | O2-579 | Again Live Values are not getting updated. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Mohsin Junaid | [5 empty] | 2025-11-04 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-580 | O2-580 | Correlation Matrix should not be disabled when model is running or stopped. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ali Qumail | [5 empty] | 2025-11-12 | 2025-11-12 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-581 | O2-581 | There is duplication in anomaly group results on OmniConnect and in export file of anomaly also. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Zeeshan Aslam | [5 empty] | 2025-11-04 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-582 | O2-582 | The user changed the subtype of one APX asset, and after importing the file, errors are appearing for all APX assets in the fault file. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-583 | O2-583 | Scheduled Raw: Table is created but all log records are fail and no data is available in tables. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-584 | O2-584 | Export To SQL : Displaying an Invalid error "User is not Authorized" with all failure log results No Data Availability in sql. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-585 | O2-585 | Schedule Site Hierarchy is displaying success with 0 Effected Rows in Log details but no data or table is created in sql db. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Syed Yousaf Qadri | [5 empty] | 2025-11-04 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-587 | O2-587 | Batch Monitoring is displaying error instead of results | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-588 | O2-588 | Error is displaying instead of data for anomaly Analysis, for the time when there was data available. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-590 | O2-590 | Now its showing error on "Create Model" screen with success message, right after clicking the next button of data selection screen. and "Generated Models Summary" is also Missing. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Ahmad Saleem | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-591 | O2-591 | Production Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-105 | O2-105 | O2-95 | Muhammad Abbas | [5 empty] | 2025-11-05 | 2025-11-10 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-592 | O2-592 | User Manual Enhancement | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-586 | O2-586 | O2-199 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-593 | O2-593 | Statistical Alarms Are not getting triggered, these were configured 3 hours ago | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-594 | O2-594 | The system alarm name for live values should only be "Live Values Accessed" on Production, just like it is on staging. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-105 | O2-105 | O2-95 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-595 | O2-595 | Error is getting displayed right after when user clicks on the next button Goes to the "Create Model" screen, and here is another issue now, this time Correlation Matrix is missing when we click on its button, Kindly look into it ⁠ | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-596 | O2-596 | Schedule for Stats: Giving FAILURE in logs with 4 effected rows and the message "No data available for this execution". Hence Data is shown in the SQL DB's Table | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-597 | O2-597 | Anomaly Results Are not getting displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-598 | O2-598 | Correlation Matrix Values are overlapping while user clicks on its button, in LCD mood | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ali Qumail | [5 empty] | 2025-11-07 | 2025-11-07 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-599 | O2-599 | Duplication in Data Alarms for for all tags Timer, Totalizer and real | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-105 | O2-105 | O2-95 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-604 | O2-604 | Real Tag is not getting deleted in first attempt. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-105 | O2-105 | O2-95 | Ali Qumail | [5 empty] | 2025-11-10 | 2025-11-10 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-605 | O2-605 | Error is Reoccurring on Blue Prod for anomaly User train group | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-105 | O2-105 | O2-95 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-606 | O2-606 | After creation of model again "Correlation Matrix" data is missing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-105 | O2-105 | O2-95 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-608 | O2-608 | Add a column named "Tag Type" in the Data Not Landing Alert emails. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-609 | O2-609 | UI Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-5 | O2-5 | O2-2 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-610 | O2-610 | Frontend End Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-5 | O2-5 | O2-2 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-611 | O2-611 | Backend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-5 | O2-5 | O2-2 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-612 | O2-612 | End-to-end application testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-5 | O2-5 | O2-2 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-614 | O2-614 | Formula Validation API is getting failed , Unable to create Call tag | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-615 | O2-615 | IOT Values are not getting updated again. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-616 | O2-616 | Storage Accounts Deletion - 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-135 | O2-135 | O2-1459 | Taimur Zahid | [5 empty] | 2025-11-01 | 2025-11-25 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-617 | O2-617 | Duplication in Calculated tag | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-618 | O2-618 | Product Related Security Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-356 | O2-356 | O2-133 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-619 | O2-619 | Organization Related Security Documentation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-356 | O2-356 | O2-133 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-620 | O2-620 | In Enterprise Connectors, the trigger should automatically start upon first-time creation; when the user stops and restarts it, the system should prompt for a new start time in UTC. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-621 | O2-621 | Duplicate calculated tags are creating through import site layout. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-622 | O2-622 | Unknown error occurs during CAL tag creation via Import Site Layout when importing 400–500 tags; resources fail to load (not related to internet connection). | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-623 | O2-623 | Rmapped name is displaying instead of user selected tag names against parameters. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-624 | O2-624 | Response is not correct for APX asset in omni agent. Whether it should display data or it should tell that only output cal tag data for performance asset can be seen. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-625 | O2-625 | Wrong response is given as I have asked about health parameters and it has given me performance output parameters, omni agent is restricted for health APX asset so it should response accordingly. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-626 | O2-626 | While using Cal tag in Anomaly group creation, NO data is getting displayed in "Correlation Matrix". | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-627 | O2-627 | Totalizer Calculated tag Live values are not landing where as Calculated tag used in Totalizer condition live values are populating | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-629 | O2-629 | Table view is not created in omni agent APX. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Muhammad Ahmad Saleem | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-632 | O2-632 | Costing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-630 | O2-630 | O2-221 | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-633 | O2-633 | Anomaly Groups are getting created while all permissions are off and Only read permission is allowed When Create permission is off and all other are allowed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ali Qumail | [5 empty] | 2025-11-13 | 2025-11-13 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-634 | O2-634 | FE and BE Development - OmniAgent APX | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-377 | O2-377 | O2-35 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-635 | O2-635 | Production Sanity | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Abbas | [5 empty] | 2025-11-13 | 2025-11-14 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-637 | O2-637 | While stopping the model its giving an error " There is no model created for this group " while model is in running state. its on the group which is having call tag in it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-638 | O2-638 | Key Vault Integration in OC | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-639 | O2-639 | Finalizing and changes after review from lead | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-39 | O2-39 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-640 | O2-640 | Downloaded CSV file and sheet name should be user friendly against APX data details in omni agent. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-641 | O2-641 | How To - APX <> OmniAgent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-58 | O2-58 | O2-35 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-642 | O2-642 | Fields - APX <> OmniAgent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-58 | O2-58 | O2-35 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-643 | O2-643 | User friendly error message should display on frontend when CSV file link is expired and it is clicked again rather than displaying backend error in a new tab. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-645 | O2-645 | Write back FAIL, NO Vales are getting fetched on front End, But Simulator is working properly. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-646 | O2-646 | Anomaly Analysis are Failed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-01-02 | 2026-01-02 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-647 | O2-647 | OMNI Agent is returning non-existing tags. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-648 | O2-648 | ODL-PD-110 - Identity and Access Management Procedures | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-356 | O2-356 | O2-133 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-649 | O2-649 | Anomaly Failed Again | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-650 | O2-650 | Stats Alarms are getting displayed for the time when site wasn't even created | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-69 | O2-69 | O2-37 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-651 | O2-651 | Circular dependency in formula is present due to which selected formula calculation is not ending where it is applied. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-652 | O2-652 | UI Disturbed for all dropdowns of Settings | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-112 | O2-112 | O2-108 | Muhammad Abdullah | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-653 | O2-653 | Sanity_Staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Muhammad Abbas | [5 empty] | 2025-11-19 | 2025-11-20 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-654 | O2-654 | Response is not given against asked query in APX omni agent. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-657 | O2-657 | Bulk Fetch Connection String is not working as expected | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-658 | O2-658 | Omni agent for APX is giving response for health asset as well where as it is restricted for now. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-659 | O2-659 | In Batch BPM, the output table column description limit is not applied, causing the API to crash while saving. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-660 | O2-660 | When using a user-defined table as an existing table for a new Batch BPM job, the API does not return or display the column descriptions after importing the schema. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-661 | O2-661 | In Batch BPM module, when a user clones a job, the system allows creating another job with the same name. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-662 | O2-662 | Area dependency is displaying on assets even after cancelling the pop up display while deleting respective area. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-663 | O2-663 | Calculated and Totalizer tag values are not updating, whereas the Real-time tag live values are populating. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-664 | O2-664 | Incorrect Spelling of "Calculated" in Alarm Name Description on System Alarms Viewer Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-665 | O2-665 | Error is displaying while configuring AHU APX performance asset. Dash should be automatically changed into underscore same as it is changing spaces. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-667 | O2-667 | Totalizer tags values are not getting updated. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-668 | O2-668 | When a user-defined function is used in BPM, the process validates successfully and the output is saved. However, when selecting “Execute All & Save Output,” the RUN STATUS shows ERROR. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-669 | O2-669 | Huge gap is displaying between two real time tag Mapped names created through ISL. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-672 | O2-672 | Unexcepted error is occurring after login, unless we refresh the application | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-673 | O2-673 | Sanity_Production | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Muhammad Abbas | [5 empty] | 2025-11-21 | 2025-11-17 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-678 | O2-678 | After recent deployment of OC fast Publish Changes is not working for all sites | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-679 | O2-679 | Fields - Update Write KQL Query Dialog Fields | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-7 | O2-7 | O2-2 | Maria Sharafat | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-680 | O2-680 | Anomaly Results are not getting displayed, model was created successfully | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-681 | O2-681 | Omni agent is not giving correct answer for APX health asset. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-57 | O2-57 | O2-35 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-682 | O2-682 | Critical Issue: Trending is showing an Error (400 bad request), while user selects real type tag directly on trending screen. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-686 | O2-686 | Prep Prod Planning /Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-8 | O2-8 | O2-2 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-687 | O2-687 | Production Green Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-8 | O2-8 | O2-2 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-688 | O2-688 | Production Blue Release | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-8 | O2-8 | O2-2 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-689 | O2-689 | Moving all Web Appsettings and Function Apps secrets in Production Green to Key Vault | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-134 | O2-134 | O2-1460 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-690 | O2-690 | Schema changes for Additional Property with Scaffolding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-691 | O2-691 | API Developments CRUD for Additional Property | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-692 | O2-692 | Development + API Integrations + Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Zain Munir | [7 empty] | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-693 | O2-693 | Dynamic Headers Table UI Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Ali Qumail | [5 empty] | 2025-11-21 | 2026-01-02 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-694 | O2-694 | Anomaly Fail: Error with success message is getting displayed and after that create model screen is not appearing its just keep on Processing | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-695 | O2-695 | Bulk Connection strings are not getting Fetched, | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Muhammad Yousha Agha | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-702 | O2-702 | Anomaly Analysis Failed Again | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Ibrahim Ahmed Qureshi | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-706 | O2-706 | Test Case Updating | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-704 | O2-704 | O2-199 | Muhammad Abbas | [5 empty] | 2025-11-26 | 2025-12-23 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-711 | O2-711 | Bug Fixing, Improvements and Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-6 | O2-6 | O2-2 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-723 | O2-723 | UI Issue on Login Page After Updating a User With Multiple Site Assignments (Logged-in User Auto Logout) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-724 | O2-724 | Login Module | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-708 | O2-708 |  | Muhammad Abbas | [5 empty] | 2025-12-02 | 2025-12-03 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-725 | O2-725 | APx Step Template API Development Modification | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-726 | O2-726 | APx Asset API Modification to incorporate Additional Properties | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-730 | O2-730 | User Manual - API Guide | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-727 | O2-727 | O2-130 | Maria Sharafat | [5 empty] | 2025-12-04 | 2025-12-08 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-731 | O2-731 | OmniAgent PPT for Tom and Some enrichments | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-377 | O2-377 | O2-35 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-74 | O2-74 | DB Design and Pipeline Design | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-75 | O2-75 | Implementation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-756 | O2-756 | OCM Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-700 | O2-700 | O2-697 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-757 | O2-757 | Update Password Validation Error Message Displayed on Setup new password screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Zain Munir | [5 empty] | 2026-01-21 | 2026-01-21 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-758 | O2-758 | UI Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-715 | O2-715 | O2-714 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-759 | O2-759 | Frontend End Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-715 | O2-715 | O2-714 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-76 | O2-76 | Dev Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-50 | O2-50 | O2-34 | Hamza Ali | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-760 | O2-760 | Backend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-715 | O2-715 | O2-714 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-761 | O2-761 | End-to-end application testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-715 | O2-715 | O2-714 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-766 | O2-766 | Schema Changes to add APx Curve Section | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-767 | O2-767 | APx Curve Template API modification , Include Sections as well | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-771 | O2-771 | No tag of string type is being created—neither conditional cal, nor timer, nor counter. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-772 | O2-772 | Anomaly Analysis are failed to load again. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Aiza Hamid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-773 | O2-773 | Error is displaying in all condition based tags, when a condition is defined between two tags but one tag is in first line and second is entered in second line of condition expression field. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-774 | O2-774 | Unit mandatory check should be removed from all calculated, conditional calculated and totalizer tags. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-775 | O2-775 | SMS OPT IN Showing this Error while verifying the number. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-776 | O2-776 | It has been more than 40 minutes of checking the notify me button but still no Alarm SMS are getting received till now. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ameer Hamza Khan | [7 empty] | 2026-01-07 | 2026-01-07 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-777 | O2-777 | While creating/editing a site, spaces should also be allowed on Staging, just like they are allowed on Production | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-778 | O2-778 | Output Table Name popup is not closed after success message | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-779 | O2-779 | Bug Fixing, Improvements and Tasks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-716 | O2-716 | O2-714 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-780 | O2-780 | UI/UX Design and Implementation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-719 | O2-719 | O2-713 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-781 | O2-781 | Unit Testing (Frontend and Backend) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-719 | O2-719 | O2-713 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-782 | O2-782 | Frontend Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-719 | O2-719 | O2-713 | Arslan sohail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-783 | O2-783 | End-to-End Application Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-719 | O2-719 | O2-713 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-784 | O2-784 | Backend/API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-719 | O2-719 | O2-713 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-786 | O2-786 | APx Curve Modal APIs modification , Include Sections as well | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-787 | O2-787 | Performance Dashboard for VFD Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | O2-1095 | O2-887 | Zain Munir | [5 empty] | 2025-12-23 | 2026-01-21 | 2026-01-02 | 2026-01-21 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-795 | O2-795 | APX GetAllAsssets API optimization - Performance bottleneck | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-796 | O2-796 | APx Activation API Modification to incorporate Curve Data manipulation for IsAppendable and Sections | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [6 empty] | 2025-12-30 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-813 | O2-813 | OCM Development FrontEnd | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-794 | O2-794 | O2-697 | Muhammad Ahmad Saleem | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-834 | O2-834 | Unit Testing for APx Performance Modal | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Faiza Nasir | [7 empty] | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-835 | O2-835 | Unable to delete Boolean tag? and clear all is also not working for Boolean tag in export to SQL (schedule) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | Ali Qumail | [5 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-836 | O2-836 | Testing by Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | kamran khalid | [5 empty] | 2026-01-02 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 27
https://octopusdtlsupport.atlassian.net/browse/O2-837 | O2-837 | Testing by Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Namra Zahid | [5 empty] | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-838 | O2-838 | Testing by Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Waqar Rasheed | [5 empty] | 2026-01-02 | 2026-01-05 | 2026-01-02 | 2026-01-06 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-839 | O2-839 | Testing by Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Zeeshan Sarwar | [5 empty] | 2026-01-02 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 24
https://octopusdtlsupport.atlassian.net/browse/O2-840 | O2-840 | User is not able to update the site. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-707 | O2-707 |  | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-841 | O2-841 | Export To Excel is Fail to download the data | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Ali Qumail | [7 empty] | 2026-01-02 | 2026-01-26 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-842 | O2-842 | Spaces in string conditional cal tag are removing itself after configuring respective tag. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Muhammad Ahmad Saleem | [7 empty] | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-843 | O2-843 | Unit is again displaying mandatory while creating calculated tag where as it is fixed on staging. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-844 | O2-844 | Spaces are not accepted in String type Timer tag condition | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Ameer Hamza Khan | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-845 | O2-845 | DOWNLOAD csv function is not working incase of "Reusable function" used in query in batch | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | ahad omer | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-846 | O2-846 | No data is getting exported to sql Schedule for IT Data | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-847 | O2-847 | Production Green Deployment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Faiza Nasir | [7 empty] | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-849 | O2-849 | Anomaly Results are not getting displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Muhammad Zeeshan Aslam | [7 empty] | 2026-01-02 | 2026-01-05 | 1.5
https://octopusdtlsupport.atlassian.net/browse/O2-851 | O2-851 | Pipelines are getting created and data is also available but no tables are getting created in SQL DB and its showing error for Stats Alarms and Hours Data | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-852 | O2-852 | Production Blue Deployment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-717 | O2-717 | O2-714 | Faiza Nasir | [7 empty] | 2026-01-05 | 2026-01-05 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-853 | O2-853 | Character Limit Missing on Property Name and Property value Field | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Ali Qumail | [7 empty] | 2026-01-08 | 2026-01-30 | 28
https://octopusdtlsupport.atlassian.net/browse/O2-854 | O2-854 | No Validation Message Shown When Adding Duplicate Property | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Ali Qumail | [7 empty] | 2026-01-08 | 2026-01-08 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-855 | O2-855 | Asset type and subtype for which template is created, not displaying while creating an APX asset using that asset type and subtype. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-858 | O2-858 | Added Correlation Matrix on Data Selection + Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-848 | O2-848 | O2-37 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-859 | O2-859 | Tested whole Flow, Deployed on Staging and Resolved Bugs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-848 | O2-848 | O2-37 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-866 | O2-866 | Research work on visualization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-862 | O2-862 | O2-861 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-874 | O2-874 | Input mapping rows added in template are not displaying in configuration of APX asset. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Faiza Nasir | [7 empty] | 2026-01-13 | 2026-01-13 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-875 | O2-875 | Character limit is not implemented same as applied in old APX asset configurations. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-876 | O2-876 | Row details are randomly swapping between its own fields in design data, input variable mapping and output variable mapping tabs while creating headers and rows. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Ali Qumail | [7 empty] | 2026-01-26 | 2026-01-26 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-877 | O2-877 | Deactivation or clear configuration against APX asset is not working. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Faiza Nasir | [7 empty] | 2026-01-14 | 2026-01-14 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-878 | O2-878 | Added Steps Disappear After Saving in Template Configuration Tab | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Faiza Nasir | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 3
https://octopusdtlsupport.atlassian.net/browse/O2-879 | O2-879 | Add Apx Additional properties in VM API Calls | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Faiza Nasir | [7 empty] | 2026-01-12 | 2026-01-14 | 9
https://octopusdtlsupport.atlassian.net/browse/O2-880 | O2-880 | Bug Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Faiza Nasir | [7 empty] | 2026-01-07 | 2026-01-15 | 12
https://octopusdtlsupport.atlassian.net/browse/O2-881 | O2-881 | Property names and options should be restricted in import site layout while creating APX asset using template also the property for which complete template is not defined they should be restricted as well from front end. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-882 | O2-882 | The UI becomes misaligned on the Template Configuration tab when a dropdown field is selected. Upon selection, the dropdown field located beneath the selected dropdown unexpectedly shifts its position, causing layout disturbance. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-883 | O2-883 | APX asset name is getting changed. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Ali Qumail | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-884 | O2-884 | Research on Code Integration of Backend and FrontEnd | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-862 | O2-862 | O2-861 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-895 | O2-895 | Export Site Layout file is not downloading. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Muhammad Usman Javed | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-897 | O2-897 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | kamran khalid | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-898 | O2-898 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | Namra Zahid | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-899 | O2-899 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | Muhammad Abbas | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-900 | O2-900 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | Zeeshan Sarwar | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-901 | O2-901 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | Waqar Rasheed | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-902 | O2-902 | Correlation Matrix is getting vanished right after clicking on "Apply" button. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | Muhammad Ahmad Saleem | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-904 | O2-904 | Forgot Password Email Not Received | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-905 | O2-905 | APX Engine - Steam table integration in APX Performance via Ebsilon engine | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-40 | O2-40 | O2-33 | Arsalan Zafar Khan | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-906 | O2-906 | Emails Not Received for User Activation, OTP, and Forgot Password | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-896 | O2-896 | O2-714 | Muhammad Usman Javed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-907 | O2-907 | Research and Poc | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-719 | O2-719 | O2-713 | Syed Yousaf Qadri | [7 empty] | 2026-01-01 | 2026-01-02 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-918 | O2-918 | Coordination with Process Team over APx Template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-41 | O2-41 | O2-33 | Faiza Nasir | [7 empty] | 2026-01-08 | 2026-01-08 | 5
https://octopusdtlsupport.atlassian.net/browse/O2-920 | O2-920 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-919 | O2-919 | O2-714 | kamran khalid | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 17
https://octopusdtlsupport.atlassian.net/browse/O2-921 | O2-921 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-919 | O2-919 | O2-714 | Muhammad Abbas | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-922 | O2-922 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-919 | O2-919 | O2-714 | Waqar Rasheed | [5 empty] | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-923 | O2-923 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-919 | O2-919 | O2-714 | Zeeshan Sarwar | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 16
https://octopusdtlsupport.atlassian.net/browse/O2-924 | O2-924 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-919 | O2-919 | O2-714 | Namra Zahid | [5 empty] | 2026-01-19 | 2026-01-19 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/O2-925 | O2-925 | EPR - January 19, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-21 | 2026-01-21 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-926 | O2-926 | EPR - January 20, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-927 | O2-927 | EPR - January 21, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-28 | 2026-01-28 | 4
https://octopusdtlsupport.atlassian.net/browse/O2-928 | O2-928 | EPR - January 1, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-929 | O2-929 | EPR - January 2, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-930 | O2-930 | EPR - January 5, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-931 | O2-931 | EPR - January 6, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-932 | O2-932 | EPR - January 7, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-933 | O2-933 | EPR - January 8, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-934 | O2-934 | EPR - January 9, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-935 | O2-935 | EPR - January 12, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-936 | O2-936 | EPR - January 13, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-937 | O2-937 | EPR - January 14, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-938 | O2-938 | EPR - January 15, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-939 | O2-939 | EPR - January 16, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-799 | O2-799 | O2-798 | Taimur Zahid | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-940 | O2-940 | Anomaly Results are not getting displayed, Kindly Look into it. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-919 | O2-919 | O2-714 | Muhammad Zeeshan Aslam | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-953 | O2-953 | Key Vault Configuration and Secrets Creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Taimur Zahid | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-954 | O2-954 | Managed Identities RBAC to Key Vault | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Taimur Zahid | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-955 | O2-955 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Aiza Hamid | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-956 | O2-956 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Hamza Ali | [7 empty] | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-957 | O2-957 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Muhammad Zeeshan Aslam | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-958 | O2-958 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Mohsin Junaid | [7 empty] | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-959 | O2-959 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Ibrahim Ahmed Qureshi | [7 empty] | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-960 | O2-960 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Syed Yousaf Qadri | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-961 | O2-961 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Hassan Saeed Wattoo | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-962 | O2-962 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Muhammad Yousha Agha | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-963 | O2-963 | Key Vault Secret Retrieval Testing and Changes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-942 | O2-942 | O2-941 | Ayyan Babar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-964 | O2-964 | SQL: Displaying Invalid Error for Hours , Not on Staging, Only On Production | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-919 | O2-919 | O2-714 | Ali Qumail | [7 empty] | 2026-01-01 | 2026-01-01 | 1
https://octopusdtlsupport.atlassian.net/browse/O2-967 | O2-967 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Zeeshan Sarwar | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-968 | O2-968 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Waqar Rasheed | [5 empty] | 2026-01-21 | 2026-01-26 | 2026-01-21 | 2026-02-17 | 38.5
https://octopusdtlsupport.atlassian.net/browse/O2-970 | O2-970 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | kamran khalid | [5 empty] | 2026-01-21 | 2026-01-23 | 2026-01-21 | 2026-01-30 | 26
https://octopusdtlsupport.atlassian.net/browse/O2-971 | O2-971 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-969 | O2-969 | O2-810 | Muhammad Abbas | [7 empty] | 2026-01-21 | 2026-01-30 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-972 | O2-972 | Real-Time Tag Latest Values Are Not Displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Mohsin Junaid | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/O2-973 | O2-973 | Docker containers are not loading. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/O2-790 | O2-790 | O2-793 | Muhammad Yousha Agha | [7 empty] | 2026-01-01 | 2026-01-21 | 96
https://octopusdtlsupport.atlassian.net/browse/O2-983 | O2-983 | Schema Changes in DE Logs Database | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-951 | O2-951 | O2-941 | Aiza Hamid | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-984 | O2-984 | Code changes for Ashghal | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-951 | O2-951 | O2-941 | Aiza Hamid | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/O2-987 | O2-987 | Testing By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | kamran khalid | [5 empty] | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 33
https://octopusdtlsupport.atlassian.net/browse/O2-988 | O2-988 | Testing By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Muhammad Abbas | [5 empty] | 2026-01-22 | 2026-01-26 | 2026-01-22 | 2026-01-27 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-989 | O2-989 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Waqar Rasheed | [5 empty] | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-990 | O2-990 | Testing By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Zeeshan Sarwar | [5 empty] | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 32
https://octopusdtlsupport.atlassian.net/browse/O2-991 | O2-991 | Testing By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/O2-986 | O2-986 | O2-941 | Namra Zahid | [5 empty] | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 32
https://octopusdtlsupport.atlassian.net/browse/OAM-45 | OAM-45 | Testing status code with QA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/OAM-44 | OAM-44 |  | awais akhter | [5 empty] | 2025-01-02 | 2025-03-31 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/OAM-50 | OAM-50 | Power BI Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/OAM-4 | OAM-4 |  | awais akhter | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-10 | ODL-10 | Live Values+Tag Dependencies+Bulk Tag Deletion Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-100 | ODL-100 | Unified Jira projects manager | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | 26
https://octopusdtlsupport.atlassian.net/browse/ODL-101 | ODL-101 | Epics Planner for Leadership Budgeting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-102 | ODL-102 | Employee Performance Dashboard (Simple/Advanced scoring) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-105 | ODL-105 | Datetime is getting disturbed while creating work orders in M365 from CBRE posted file | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-104 | ODL-104 | ODL-103 | Ameer Hamza Khan | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 8
https://octopusdtlsupport.atlassian.net/browse/ODL-106 | ODL-106 | Work Order type is not saving as mentioned in CBRE posted sheet | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-104 | ODL-104 | ODL-103 | Ameer Hamza Khan | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-107 | ODL-107 | Null target start and finish datetime exception handled | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-104 | ODL-104 | ODL-103 | Ameer Hamza Khan | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-11 | ODL-11 | Data Alarms+Statistical Alarms+ Tag Diagnostics Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-111 | ODL-111 | 1. Proposal & PO | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [5 empty] | 2025-09-25 | 2025-10-09 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-112 | ODL-112 | 2. ODL in-house tasks (engineering) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [5 empty] | 2025-10-01 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-113 | ODL-113 | 3. DEWA approval | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [5 empty] | 2025-11-03 | 2025-11-07 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-114 | ODL-114 | 4. Hand-over to Avanceon | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [5 empty] | 2025-11-03 | 2025-11-28 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-115 | ODL-115 | 5. PQ Documentation for DEWA approval | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [5 empty] | 2025-12-08 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-116 | ODL-116 | 7. OCP document scope | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [5 empty] | 2026-03-04 | 2026-03-27 | 2026-03-09 | 2026-03-25 | 5
https://octopusdtlsupport.atlassian.net/browse/ODL-117 | ODL-117 | Commissioning support | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-118 | ODL-118 | Sprint Planning Activity March 31, 26. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | ODL-54 | ODL-46 | Arsalan Zafar Khan | [7 empty] | 2026-03-31 | 2026-03-31 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-12 | ODL-12 | Real and GPS Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-121 | ODL-121 | Mindset training - AHK | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-120 | ODL-120 | ODL-119 | Ameer Hamza Khan | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/ODL-122 | ODL-122 | Mindset training - MZ | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-120 | ODL-120 | ODL-119 | Mariam Zulfiqar | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-02 | 4
https://octopusdtlsupport.atlassian.net/browse/ODL-123 | ODL-123 | Mindset Training - Taimur Zahid | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-120 | ODL-120 | ODL-119 | Taimur Zahid | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/ODL-124 | ODL-124 | Jira Time Log Activity 8 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | ODL-54 | ODL-46 | Arsalan Zafar Khan | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-126 | ODL-126 | Chillowatt Process Understanding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-125 | ODL-125 | ODL-64 | ahad omer | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/ODL-127 | ODL-127 | Chillowatt Handover Code Understanding | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-125 | ODL-125 | ODL-64 | ahad omer | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8
https://octopusdtlsupport.atlassian.net/browse/ODL-129 | ODL-129 | URS review OEE | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-128 | ODL-128 | ODL-64 | ahad omer | [5 empty] | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 16
https://octopusdtlsupport.atlassian.net/browse/ODL-13 | ODL-13 | Calculated, Counter and Timer Tags Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-131 | ODL-131 | KT Session for Fuel-Chat and Omni-Chat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-130 | ODL-130 | ODL-63 | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 4
https://octopusdtlsupport.atlassian.net/browse/ODL-132 | ODL-132 | Support, Bug fixing, meeting with clients/new customer and internal meeting with team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | ODL-76 | ODL-46 | Unassigned | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-14 | ODL-14 | Anomaly Detection Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-15 | ODL-15 | Export Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-16 | ODL-16 | Apx Template/Insights/Performance Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-17 | ODL-17 | Handover - Site status screen , Read API notification , Data point management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-18 | ODL-18 | Handover - Real API Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2.5
https://octopusdtlsupport.atlassian.net/browse/ODL-19 | ODL-19 | HANDOVER - Import Site Layout | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-20 | ODL-20 | Handover Session 11 - APX insights | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [7 empty] | 2026-02-04 | 2026-02-04 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-21 | ODL-21 | Handover Session 7 - Create formula , Variable , Asset subtype , Asset type | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 4.5
https://octopusdtlsupport.atlassian.net/browse/ODL-22 | ODL-22 | Handover Session 6 - Bulk Device Replication , Connection strings (EDGE) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2.5
https://octopusdtlsupport.atlassian.net/browse/ODL-23 | ODL-23 | Handover - Setting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-25 | ODL-25 | Handover -User Management + Authorization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-26 | ODL-26 | Handover - Nested Cal Tag + Code Review | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 7.5
https://octopusdtlsupport.atlassian.net/browse/ODL-27 | ODL-27 | Handover - On Hold Modules | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 4.5
https://octopusdtlsupport.atlassian.net/browse/ODL-28 | ODL-28 | Handover - Final Queries + Resolved Concerns | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 6
https://octopusdtlsupport.atlassian.net/browse/ODL-29 | ODL-29 | Handover -User Management + Authorization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-30 | ODL-30 | Handover - Device Diagnostics & Nested Cal Tag + Code Review | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-31 | ODL-31 | Handover - On Hold Modules | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-32 | ODL-32 | Handover - Final Queries + Resolved Concerns | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-02-11 | 2026-02-11 | 0.5
https://octopusdtlsupport.atlassian.net/browse/ODL-33 | ODL-33 | Handover - Final Quiz and Queries | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-34 | ODL-34 | Real Time / GPS Tag Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-35 | ODL-35 | Calculated+Timer+Counter Tags Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-36 | ODL-36 | Calculated+Timer+Counter Tags Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-37 | ODL-37 | Live Values+Tag Dependencies+Bulk Tag Deletion Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-38 | ODL-38 | Anomaly Detection Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-39 | ODL-39 | Export Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-40 | ODL-40 | Apx Template/Insights/Performance Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-41 | ODL-41 | Handover -User Management + Authorization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-42 | ODL-42 | Handover - Nested Cal Tag + Code Review | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-03-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-43 | ODL-43 | Handover - On Hold Modules | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-44 | ODL-44 | Handover - Final Queries + Resolved Concerns | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Sarmad Sabir | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-45 | ODL-45 | Handover Quiz | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-48 | ODL-48 | Handover : Queries related to Anomaly and Tags | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 5
https://octopusdtlsupport.atlassian.net/browse/ODL-49 | ODL-49 | Handover Quiz | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-51 | ODL-51 | 13 Feb 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-47 | ODL-47 | ODL-46 | Taimur Zahid | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/ODL-52 | ODL-52 | Scrum + Jira Activity 13 Feb 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-50 | ODL-50 | ODL-46 | Zain Munir | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2.5
https://octopusdtlsupport.atlassian.net/browse/ODL-55 | ODL-55 | Jira Time Log Activity 13 Feb 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | ODL-54 | ODL-46 | Arsalan Zafar Khan | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-58 | ODL-58 | 13 Feb 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-57 | ODL-57 | ODL-46 | Mohsin Junaid | [7 empty] | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/ODL-6 | ODL-6 | Real Time / GPS Tag Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-60 | ODL-60 | Add planned dates and estimates for all assigned tasks / stories | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-59 | ODL-59 | ODL-46 | Faiza Nasir | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-62 | ODL-62 | 13 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-61 | ODL-61 | ODL-46 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-65 | ODL-65 | Next Sprint Planning Activity 19 Feb. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | ODL-54 | ODL-46 | Arsalan Zafar Khan | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-67 | ODL-67 | Next Sprint Planning Activity 19 Feb. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-66 | ODL-66 | ODL-46 | Muhammad Abdullah | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-68 | ODL-68 | Live Values,Tag Dependencies,Bulk Tag Deletion Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-69 | ODL-69 | Manual,Totalizer Tags Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-7 | ODL-7 | Real Time and GPS Tags handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Faiza Nasir | [7 empty] | 2026-01-28 | 2026-01-28 | 1
https://octopusdtlsupport.atlassian.net/browse/ODL-70 | ODL-70 | Data Alarms,Statistical Alarms, Tag Diagnostics Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-71 | ODL-71 | Anomaly Detection Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-72 | ODL-72 | Export Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-73 | ODL-73 | Apx Template,Insights,Performance Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-74 | ODL-74 | Real API Dashboard - Handover | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-75 | ODL-75 | Handover Session- Bulk Device Replication , Connection strings (EDGE) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-77 | ODL-77 | Next sprint planning 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | ODL-76 | ODL-46 | Unassigned | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-78 | ODL-78 | Meeting with team to improve capability of LogChat | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | ODL-76 | ODL-46 | nadeem ahmed | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-79 | ODL-79 | Project Planning and Jira Management for team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-59 | ODL-59 | ODL-46 | Faiza Nasir | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 4
https://octopusdtlsupport.atlassian.net/browse/ODL-8 | ODL-8 | Calculated+Timer+Counter Tags Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-82 | ODL-82 | Audit of Power BI and Requirements analysis | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-02-03 | 2026-02-09 | 2026-02-04 | 2026-02-09 | 24
https://octopusdtlsupport.atlassian.net/browse/ODL-85 | ODL-85 | 6. Support Avanceon for development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | ODL-84 | ODL-4 | Mariam Zulfiqar | [5 empty] | 2025-12-01 |  | 2026-01-28 | 2026-02-27 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-86 | ODL-86 | Basic Report Structuring | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-02-10 | 2026-02-16 | 2026-02-10 | 2026-02-16 | 40
https://octopusdtlsupport.atlassian.net/browse/ODL-87 | ODL-87 | Advanced Report Structuring | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-02-17 | 2026-02-23 | 2026-02-17 | 2026-02-23 | 34
https://octopusdtlsupport.atlassian.net/browse/ODL-88 | ODL-88 | Adding Data Story Reports | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-27 | 26
https://octopusdtlsupport.atlassian.net/browse/ODL-9 | ODL-9 | Manual+Totalizer Tags Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | ODL-5 | ODL-63 | Zain Munir | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-90 | ODL-90 | CDC review at CP-1 meeting with Colgate team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | ODL-76 | ODL-46 | nadeem ahmed | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2
https://octopusdtlsupport.atlassian.net/browse/ODL-91 | ODL-91 | Improving Employee Performance Report | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 6.5
https://octopusdtlsupport.atlassian.net/browse/ODL-92 | ODL-92 | Improving Score Card Report - Nested Report | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-03-09 | 13
https://octopusdtlsupport.atlassian.net/browse/ODL-93 | ODL-93 | Digital Log road map meeting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | ODL-76 | ODL-46 | Unassigned | [5 empty] | 2026-03-04 | 2026-03-04 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/ODL-94 | ODL-94 | Custom Report development for Zomco demo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | ODL-76 | ODL-46 | nadeem ahmed | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 3
https://octopusdtlsupport.atlassian.net/browse/ODL-95 | ODL-95 | Meeting with Zomco regarding Digital Log Demo - along with PreSale team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | ODL-76 | ODL-46 | nadeem ahmed | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1.5
https://octopusdtlsupport.atlassian.net/browse/ODL-96 | ODL-96 | Building Colossal Refresh | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6.5
https://octopusdtlsupport.atlassian.net/browse/ODL-97 | ODL-97 | Unified Data Refresh for All Reports | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/ODL-98 | ODL-98 | Fixing data sync issues across reports | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 4
https://octopusdtlsupport.atlassian.net/browse/ODL-99 | ODL-99 | Building IPP Planner and IPP Dashboard | Sub-task | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | ODL-81 | ODL-80 | Hassan Malik | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2.5
https://octopusdtlsupport.atlassian.net/browse/RLT-100 | RLT-100 | Leave for one day 19-12-25 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-101 | RLT-101 | Leave for one day 26-12-25 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-102 | RLT-102 | Annual leave 23 December | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-103 | RLT-103 | Annual leave 24 December | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-104 | RLT-104 | Annual leave 26 December | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-105 | RLT-105 | Annual leave 29 December | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-106 | RLT-106 | Annual leave 30 December | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-107 | RLT-107 | Annual leave 31 December | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-108 | RLT-108 | Annual leave 01 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-109 | RLT-109 | Annual leave 02 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-110 | RLT-110 | Annual leave 05 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-05 | 2026-01-05 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-111 | RLT-111 | Annual leave 06 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-06 | 2026-01-06 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-112 | RLT-112 | Annual leave 07 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-113 | RLT-113 | Annual leave 08 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-08 | 2026-01-08 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-114 | RLT-114 | Annual leave 09 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-115 | RLT-115 | Annual leave 12 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-116 | RLT-116 | Annual Leaves | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-121 | RLT-121 | Planned Leave 30th January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | RLT-26 |  | Muhammad Imran Aslam | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-122 | RLT-122 | Planned Leave on 5 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-123 | RLT-123 | Planned Leave on 6 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-124 | RLT-124 | Planned Leave on 7 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-125 | RLT-125 | Planned Leave on 8 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-126 | RLT-126 | Planned Leave on 9 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-127 | RLT-127 | Planned Leave on 12 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-128 | RLT-128 | Planned Leave on 13 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-129 | RLT-129 | Planned Leave on 14 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-130 | RLT-130 | Planned Leave on 15 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-131 | RLT-131 | Planned Leave on 16 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-132 | RLT-132 | Planned Leave on 19 Jan 26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | RLT-61 |  | Zain Munir | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-133 | RLT-133 | 23 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-135 | RLT-135 | Leave - December 26, 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [5 empty] | 2025-12-26 | 2025-12-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-136 | RLT-136 | Leave - January 15, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-137 | RLT-137 | 16 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-138 | RLT-138 | 19 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-139 | RLT-139 | 20 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-140 | RLT-140 | 22 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-141 | RLT-141 | Casual Leave 30 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | RLT-32 |  | Muhammad Abdullah | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-142 | RLT-142 | 20 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-143 | RLT-143 | 16 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-144 | RLT-144 | 2 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-145 | RLT-145 | 1 January 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-146 | RLT-146 | 1st January medical emergency leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-147 | RLT-147 | 12th January medical emergency leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-148 | RLT-148 | 13th January medical emergency leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-149 | RLT-149 | 14th January medical emergency leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-150 | RLT-150 | 15th January medical emergency leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-151 | RLT-151 | 16th January medical emergency leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-152 | RLT-152 | 9 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-153 | RLT-153 | 10 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-154 | RLT-154 | 11 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-155 | RLT-155 | 12 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-156 | RLT-156 | 13 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-158 | RLT-158 | 11 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-11 | 2025-12-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-159 | RLT-159 | 12 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-12 | 2025-12-12 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-160 | RLT-160 | 15 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-15 | 2025-12-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-161 | RLT-161 | 16 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-16 | 2025-12-16 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-162 | RLT-162 | 17 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-17 | 2025-12-17 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-163 | RLT-163 | 18 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-18 | 2025-12-18 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-164 | RLT-164 | 19 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-19 | 2025-12-19 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-165 | RLT-165 | 22 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-22 | 2025-12-22 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-166 | RLT-166 | 23 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-23 | 2025-12-23 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-167 | RLT-167 | 24 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-24 | 2025-12-24 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-169 | RLT-169 | 26 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-26 | 2025-12-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-170 | RLT-170 | 30 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-30 | 2025-12-30 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-171 | RLT-171 | 31 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-31 | 2025-12-31 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-172 | RLT-172 | Maternity Leaves 1 Jan - 31 March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2026-01-01 | 2026-03-31 | 2026-01-01 | 2026-03-01 | 528
https://octopusdtlsupport.atlassian.net/browse/RLT-173 | RLT-173 | Annual Leaves 1 April - 30 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-01 | 176
https://octopusdtlsupport.atlassian.net/browse/RLT-174 | RLT-174 | 29 Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | RLT-8 |  | Maria Sharafat | [5 empty] | 2025-12-29 | 2025-12-29 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-175 | RLT-175 | Planned Leave 2nd March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | RLT-26 |  | Muhammad Imran Aslam | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-176 | RLT-176 | Planned Leave 7th May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | RLT-26 |  | Muhammad Imran Aslam | [5 empty] | 2026-05-07 | 2026-05-07 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-177 | RLT-177 | 6 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-178 | RLT-178 | planned leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-6 | RLT-6 |  | awais akhter | [7 empty] | 2026-01-31 | 2026-01-31 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-179 | RLT-179 | Leave - Febuary 9, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-180 | RLT-180 | Unplanned Leave (29 January 2026) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-37 | RLT-37 |  | awais akhter | [5 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-181 | RLT-181 | 9 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-182 | RLT-182 | Leave for one day 07-01-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [7 empty] | 2026-01-07 | 2026-01-07 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-184 | RLT-184 | Planned Leave 12-01-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | awais akhter | [7 empty] | 2026-01-12 | 2026-01-12 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-185 | RLT-185 | Planned Leave 13-01-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | awais akhter | [7 empty] | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-186 | RLT-186 | Unplanned Leave 26-01-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | awais akhter | [7 empty] | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-187 | RLT-187 | Annual leave 13 Jan 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-01-13 | 2026-01-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-188 | RLT-188 | Annual Leaves | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-22 | RLT-22 |  | Muhammad Usman Javed | [7 empty] | 2026-01-01 | 2026-01-09 | 56
https://octopusdtlsupport.atlassian.net/browse/RLT-189 | RLT-189 | Casual & Sick Leaves | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-22 | RLT-22 |  | Muhammad Usman Javed | [7 empty] | 2026-03-03 | 2026-03-03 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-190 | RLT-190 | Leave for one day 13-02-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [7 empty] | 2026-02-13 | 2026-02-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-191 | RLT-191 | Sick Leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | RLT-13 |  | Faiza Nasir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-192 | RLT-192 | Casual Leave 16 Feb 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-193 | RLT-193 | 23 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-194 | RLT-194 | Unplanned Leave 19-02-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-195 | RLT-195 | Sick Leave 23 Feb 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | RLT-32 |  | Muhammad Abdullah | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-196 | RLT-196 | 25 February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-197 | RLT-197 | Leave - March 2, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-198 | RLT-198 | Leave 23rd Feb | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-199 | RLT-199 | Kashmir Day 5th Feb | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-200 | RLT-200 | Leave Jan 5th | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-201 | RLT-201 | Leave Jan 26th | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-202 | RLT-202 | Sick Leave- 4th March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-40 | RLT-40 |  | Hassan Malik | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-203 | RLT-203 | Casual Leave 6 march 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-03-06 | 2026-03-06 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-204 | RLT-204 | Sick leave for one day 06-03-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [7 empty] | 2026-03-06 | 2026-03-06 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-205 | RLT-205 | Leave 9th March | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-207 | RLT-207 | 16-02-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | RLT-206 |  | Muhammad Zeeshan Aslam | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-208 | RLT-208 | 4th March compassionate leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-209 | RLT-209 | 5th March compassionate leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-210 | RLT-210 | 6th March compassionate leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-211 | RLT-211 | 10th March compassionate leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-212 | RLT-212 | Leave for one day 13-03-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [7 empty] | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-213 | RLT-213 | Sick Leaves | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-92 | RLT-92 |  | Faiq Butt | [7 empty] | 2026-02-16 | 2026-05-06 | 24
https://octopusdtlsupport.atlassian.net/browse/RLT-214 | RLT-214 | Annual Leaves | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-92 | RLT-92 |  | Faiq Butt | [7 empty] | 2026-03-09 | 2026-03-09 | 32
https://octopusdtlsupport.atlassian.net/browse/RLT-215 | RLT-215 | Compassionate Leaves | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-92 | RLT-92 |  | Faiq Butt | [7 empty] | 2026-02-17 | 2026-03-03 | 32
https://octopusdtlsupport.atlassian.net/browse/RLT-216 | RLT-216 | Leave - March 16, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [7 empty] | 2026-03-16 | 2026-03-16 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-217 | RLT-217 | Casual Leave 17 March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | RLT-32 |  | Muhammad Abdullah | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-218 | RLT-218 | Sick Leave March 16, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-11 | RLT-11 |  | Arsalan Zafar Khan | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5
https://octopusdtlsupport.atlassian.net/browse/RLT-219 | RLT-219 | Leave - March 24, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-220 | RLT-220 | Planned Leave 15th Apr 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | RLT-26 |  | Muhammad Imran Aslam | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-221 | RLT-221 | Hajj Leaves - 4 May to 26 May | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | RLT-13 |  | Faiza Nasir | [5 empty] | 2026-05-04 | 2026-05-26 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-222 | RLT-222 | Hajj Leaves - 1 June to 19 June | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | RLT-13 |  | Faiza Nasir | [5 empty] | 2026-06-01 | 2026-06-19 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-223 | RLT-223 | Unplanned Leaves 25th,26th march 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [7 empty] | 2026-03-25 | 2026-03-26 | 16
https://octopusdtlsupport.atlassian.net/browse/RLT-224 | RLT-224 | Leave for one day 27-03-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [7 empty] | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-225 | RLT-225 | Annual Leave 31-03-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-226 | RLT-226 | Annual Leave 01-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-227 | RLT-227 | Annual Leave 02-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-228 | RLT-228 | Annual Leave 03-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-229 | RLT-229 | Annual Leave 06-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-230 | RLT-230 | Annual Leave 07-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-231 | RLT-231 | Annual Leave 08-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-232 | RLT-232 | Annual Leave 09-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-233 | RLT-233 | Annual Leave 10-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-234 | RLT-234 | Annual Leave 13-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-235 | RLT-235 | Annual Leave 14-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-236 | RLT-236 | Annual Leave 15-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-237 | RLT-237 | Annual Leave 16-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-238 | RLT-238 | Annual Leave 17-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-239 | RLT-239 | Annual Leave 20-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-240 | RLT-240 | Annual Leave 21-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-241 | RLT-241 | Annual Leave 22-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-242 | RLT-242 | Annual Leave 23-04-26 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Hassan Malik | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-243 | RLT-243 | Leave - March 26, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-244 | RLT-244 | Leave - March 27, 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | RLT-118 |  | Taimur Zahid | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-245 | RLT-245 | Unplanned Leave 24-03-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [7 empty] | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-246 | RLT-246 | Casual/Sick Leaves (March) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-91 | RLT-91 |  | Hassan Malik | [7 empty] | 2026-03-31 | 2026-03-31 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-247 | RLT-247 | Sick Leave 30th March | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-248 | RLT-248 | Sick Leave 31st March | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-249 | RLT-249 | 24-March-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | RLT-15 |  | Namra Zahid | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-250 | RLT-250 | 25-March-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | RLT-15 |  | Namra Zahid | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-251 | RLT-251 | 26-March-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | RLT-15 |  | Namra Zahid | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-252 | RLT-252 | 27-March-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | RLT-15 |  | Namra Zahid | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-253 | RLT-253 | 30-March-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | RLT-15 |  | Namra Zahid | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-254 | RLT-254 | 30 March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-255 | RLT-255 | 31 March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-256 | RLT-256 | 3 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-257 | RLT-257 | Sick Leave April | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-34 | RLT-34 |  | Mariam Zulfiqar | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-258 | RLT-258 | Annual Leaves April | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-34 | RLT-34 |  | Mariam Zulfiqar | [5 empty] | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-13 | 16
https://octopusdtlsupport.atlassian.net/browse/RLT-259 | RLT-259 | Annual Leaves (April) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-91 | RLT-91 |  | Danish Rashid | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-15 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-260 | RLT-260 | Annual Leaves (March) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-93 | RLT-93 |  | DANIYAL AHMAD | [5 empty] | 2026-04-10 | 2026-04-10 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-261 | RLT-261 | 11 May 2026 - 30 May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | RLT-206 |  | Muhammad Zeeshan Aslam | [5 empty] | 2026-05-11 | 2026-05-26 | 2026-05-11 | 2026-05-26 | 96
https://octopusdtlsupport.atlassian.net/browse/RLT-262 | RLT-262 | 1 Jun 2026 - 26 Jun 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | RLT-206 |  | Muhammad Zeeshan Aslam | [5 empty] | 2026-06-01 | 2026-06-26 | 2026-06-01 | 2026-06-23 | 136
https://octopusdtlsupport.atlassian.net/browse/RLT-263 | RLT-263 | 10 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | RLT-206 |  | Muhammad Zeeshan Aslam | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-264 | RLT-264 | Unplanned Leave 08-04-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-265 | RLT-265 | 15 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-266 | RLT-266 | 16 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-267 | RLT-267 | 17 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-268 | RLT-268 | 20 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-269 | RLT-269 | 21 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | RLT-66 |  | Waqar Rasheed | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-270 | RLT-270 | Sick Leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | RLT-13 |  | Faiza Nasir | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-271 | RLT-271 | Casula Leave 13 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-04-13 | 2026-04-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-272 | RLT-272 | Casual Leave 9 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | RLT-32 |  | Muhammad Abdullah | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 3
https://octopusdtlsupport.atlassian.net/browse/RLT-273 | RLT-273 | 10th April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-274 | RLT-274 | 13th April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | RLT-134 |  | Muhammad Ahmad Saleem | [5 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-275 | RLT-275 | Annual Leaves 23rd April till 30th march | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [5 empty] | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-30 | 48
https://octopusdtlsupport.atlassian.net/browse/RLT-276 | RLT-276 | Casual Leaves (April) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-93 | RLT-93 |  | DANIYAL AHMAD | [7 empty] | 2026-04-10 | 2026-04-16 | 16
https://octopusdtlsupport.atlassian.net/browse/RLT-277 | RLT-277 | Casula Leave 21 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-04-21 | 2026-04-21 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-278 | RLT-278 | Casula Leave 22 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [7 empty] | 2026-04-22 | 2026-04-22 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-279 | RLT-279 | Planned Leave 20th May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | RLT-26 |  | Muhammad Imran Aslam | [5 empty] | 2026-05-20 | 2026-05-20 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-280 | RLT-280 | Leave 20th April | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-281 | RLT-281 | Leave 21st April | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8
https://octopusdtlsupport.atlassian.net/browse/RLT-282 | RLT-282 | 4 April 2026 - 8 April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2026-05-04 | 2026-05-08 | 2026-04-24 | 2026-05-08 | 40
https://octopusdtlsupport.atlassian.net/browse/RLT-283 | RLT-283 | Traveling out of town to attend a marriage ceremony | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | RLT-23 |  | Ameer Hamza Khan | [5 empty] | 2026-04-22 | 2026-04-24 | 2026-04-22 | 2026-04-24 | 24
https://octopusdtlsupport.atlassian.net/browse/RLT-284 | RLT-284 | Planned Leave 11-05-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [5 empty] | 2026-05-11 | 2026-05-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-285 | RLT-285 | Planned Leave 12-05-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [5 empty] | 2026-05-12 | 2026-05-12 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-286 | RLT-286 | Planned Leave 13-05-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [5 empty] | 2026-05-13 | 2026-05-13 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-287 | RLT-287 | Planned Leave 14-05-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [5 empty] | 2026-05-14 | 2026-05-14 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-288 | RLT-288 | Planned Leave 15-05-2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | RLT-183 |  | Hamza Ali | [5 empty] | 2026-05-15 | 2026-05-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-289 | RLT-289 | Labour Day | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | RLT-73 |  | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-290 | RLT-290 | Casual Leaves (April) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-94 | RLT-94 |  | Muhammad Abdul Wasi | [5 empty] | 2026-04-01 | 2026-04-30 | 2026-04-24 | 2026-04-24 | 4
https://octopusdtlsupport.atlassian.net/browse/RLT-291 | RLT-291 | Annual Leaves May | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-34 | RLT-34 |  | Mariam Zulfiqar | [5 empty] | 2026-05-18 | 2026-05-20 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-43 | RLT-43 | Planned Leave 15th May 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [5 empty] | 2024-05-15 | 2024-05-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-44 | RLT-44 | Leaves Faiza | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | RLT-13 |  | Faiza Nasir | [5 empty] | 2024-05-29 | 2024-05-31 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-45 | RLT-45 | Leave for one day 05-06-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-46 | RLT-46 | Planned Leave 20th June 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-47 | RLT-47 | Leave for two days 20 and 21-06-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-49 | RLT-49 | Emergency leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | RLT-13 |  | Faiza Nasir | [5 empty] | 2024-07-11 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-50 | RLT-50 | Sick leave for one day 22-07-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-52 | RLT-52 | Urgent work leave 05-08-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-53 | RLT-53 | Planned Leave 15th Aug 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-54 | RLT-54 | Leave for one day 30-08-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-55 | RLT-55 | Leave for one day 02-09-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-56 | RLT-56 | Sick leave 28th Aug 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-57 | RLT-57 | Sick Leave 13th Sept 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-58 | RLT-58 | Leave for one day 14-11-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-59 | RLT-59 | Planned Leave 8th Nov 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-60 | RLT-60 | Planned Leave 19th Nov 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-62 | RLT-62 | Sick leave for one day 30-12-24 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-63 | RLT-63 | Planned Leave 29th Nov 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-64 | RLT-64 | Planned Leave 16th Dec 2024 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-65 | RLT-65 | Annual Leave 23rd Dec, 24th Dec, 26th Dec, 27th Dec | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-67 | RLT-67 | Casual Leave for half day 02-01-25 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-68 | RLT-68 | Leave for one day 03-01-25 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-71 | RLT-71 | Leave for one day 27-02-25 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-72 | RLT-72 | Annual leave 31 Jan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-74 | RLT-74 | Planned Leave 21st Feb 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-77 | RLT-77 | Planned Leave 3rd April 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-78 | RLT-78 | Planned Leave 4th April 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-79 | RLT-79 | Sick leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-80 | RLT-80 | 16 may 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | RLT-5 |  | Hassan Malik | [5 empty] | 2025-05-16 | 2025-05-16 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-81 | RLT-81 | Annual leave 22 May | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-82 | RLT-82 | Planned Leave 5th June 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-83 | RLT-83 | Annual leave 07 July | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-84 | RLT-84 | Casual leave | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-85 | RLT-85 | Casual leave 10 sept 25 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | RLT-17 |  | Muhammad Abbas | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-86 | RLT-86 | Planned Leave 15th July 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-87 | RLT-87 | Planned 1st Sept 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-88 | RLT-88 | Planned Leave 15th Aug 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-89 | RLT-89 | Compassionate Leave 29th Sept, 30th Sept, 1st Oct | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-90 | RLT-90 | Planned Leave 5th Nov 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-95 | RLT-95 | Sick Leave 18th Nov 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-96 | RLT-96 | Compassionate Leaves 24th Nov, 25th Nov 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-97 | RLT-97 | 3rd Dec 2025 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | RLT-39 |  | Hassan Saeed Wattoo | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/RLT-99 | RLT-99 | Leave for one day 05-12-25 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | RLT-35 |  | Zeeshan Sarwar | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-100 | SUBS-100 | Products + Features Frontend, API Modification & Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-101 | SUBS-101 | Account Activation Page UI | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-102 | SUBS-102 | Account Activation API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-103 | SUBS-103 | Super Admin - Plans API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-02-20 | 6
https://octopusdtlsupport.atlassian.net/browse/SUBS-104 | SUBS-104 | Super Admin - Tiers API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-105 | SUBS-105 | SM Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-106 | SUBS-106 | Config Version Screen + Version Compatibility & APIs Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-02-23 | 14
https://octopusdtlsupport.atlassian.net/browse/SUBS-107 | SUBS-107 | User Managemnet APIs integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-108 | SUBS-108 | Plans Tiers API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-25 | 6
https://octopusdtlsupport.atlassian.net/browse/SUBS-109 | SUBS-109 | Overall development team discussions / Coordinations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-110 | SUBS-110 | Quotation Understanding + Meetings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-111 | SUBS-111 | Qoutations API Logic revision | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-23 | 2026-02-26 | 2026-02-23 | 2026-02-26 | 13
https://octopusdtlsupport.atlassian.net/browse/SUBS-112 | SUBS-112 | Product Information Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-113 | SUBS-113 | Integrated Quotation API + Calculations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 7.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-114 | SUBS-114 | Changes with Plans and Tiers APIs | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 4.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-115 | SUBS-115 | Preview page diagram for Admin | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-116 | SUBS-116 | Integrated Save Quote Api + Modified Calculator | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-117 | SUBS-117 | Audit Logs integration in all modules CRUD operation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 5
https://octopusdtlsupport.atlassian.net/browse/SUBS-118 | SUBS-118 | Get Quotes for Sales Person API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-119 | SUBS-119 | Redesigned the Login Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-120 | SUBS-120 | Flow testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-121 | SUBS-121 | Bug Fix for Tiers Tab (Admin) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-122 | SUBS-122 | Production Deployment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-123 | SUBS-123 | Code Merging, Final Run Down Changes + Handover Session | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-27 | 13
https://octopusdtlsupport.atlassian.net/browse/SUBS-124 | SUBS-124 | Flow Testing + Issue Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 7.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-125 | SUBS-125 | Staging Release plus bug fixing on staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | 5
https://octopusdtlsupport.atlassian.net/browse/SUBS-126 | SUBS-126 | Update Layout for Plans | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-127 | SUBS-127 | Pagination across the admin side | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-128 | SUBS-128 | Bug Fixing before QA | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-129 | SUBS-129 | Added View and Export Quotation Functionality | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-130 | SUBS-130 | Plans UI + Preview Page UI Fix | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-131 | SUBS-131 | Activate Account API Fix + Account Activation Screen fallback for staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 3.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-132 | SUBS-132 | Post Handover feedback Integration Discussions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 1.28
https://octopusdtlsupport.atlassian.net/browse/SUBS-133 | SUBS-133 | Account Activation Email | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-134 | SUBS-134 | Validation for Plans screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-135 | SUBS-135 | Edit tier functionality changed | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-136 | SUBS-136 | Preparing DL and Fintech Data for Demo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-137 | SUBS-137 | Added Edit Quotation Funtionality +Enhance Template | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-138 | SUBS-138 | Added Pagination and Fix Issues in User and Sales Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 5.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-139 | SUBS-139 | Make quotation sharable for User | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-09 | 2026-03-10 | 2026-03-06 | 2026-03-10 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-14 | SUBS-14 | Resource Management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | SUBS-9 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-17 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-140 | SUBS-140 | Demo with TK & Asmar + Post Demo Discussions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-141 | SUBS-141 | POST API changes for versions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 3.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-142 | SUBS-142 | UI adjustments for Plan and Tiers | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-143 | SUBS-143 | On submit Set all plans, products, plan teirs , pricing version, etc Status = APPROVED | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-144 | SUBS-144 | Make Quotation Invalid in case of pricing change of plan or plan tiers | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-145 | SUBS-145 | Do not allow Plan, Plan tiers, Meters to be deleted if used in Quotations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-146 | SUBS-146 | Feature should not delete that is used in Plan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-147 | SUBS-147 | Post Demo Discussion to Incorporate Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-148 | SUBS-148 | Added Export API+ Fixed User Update Issue+ Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 4.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-149 | SUBS-149 | Added Share Functionality + Fix Issues | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 4.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-15 | SUBS-15 | Azure Resource management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | SUBS-9 | SUBS-5 | Ameer Hamza Khan | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-150 | SUBS-150 | Make all newly created qoutes marked as approved | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-151 | SUBS-151 | Set quote status as Void on any change in plan and plan tier pricings | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-152 | SUBS-152 | Remove all checks in quotes that checks statuses in CRUD Operations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-153 | SUBS-153 | Add base price of chosen plan in Quotations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-154 | SUBS-154 | Fixed Currency in Calculator and View Quotation + User issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-155 | SUBS-155 | Complete flow test + Handover to QA + Post Handover Meeting | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-156 | SUBS-156 | Requirement gathering and team management | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Ameer Hamza Khan | [5 empty] | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-02-27 | 40
https://octopusdtlsupport.atlassian.net/browse/SUBS-157 | SUBS-157 | Added Revise,Invalid Quotation Functionality | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-158 | SUBS-158 | Set ONE Default plan feature | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-159 | SUBS-159 | Email confirmation status in User Table | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-16 | SUBS-16 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | SUBS-9 | SUBS-5 | Waqar Rasheed | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-160 | SUBS-160 | Implement Resend Email in User Table | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-161 | SUBS-161 | UI Fix for Users Page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-162 | SUBS-162 | Preparing data for Demo + Sanity Check with Excel Sheet | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-163 | SUBS-163 | Testing for demo + Fixed Some issue | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 3.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-164 | SUBS-164 | Modified Share Functionality +Revise UI + Fixed Invalid Quotation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 5.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-165 | SUBS-165 | Handover By Kamran | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | SUBS-10 | SUBS-5 | kamran khalid | [5 empty] | 2026-02-27 | 2026-02-27 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-166 | SUBS-166 | Handover By Namra | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | SUBS-10 | SUBS-5 | Namra Zahid | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2.22
https://octopusdtlsupport.atlassian.net/browse/SUBS-167 | SUBS-167 | Handover By Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | SUBS-10 | SUBS-5 | Zeeshan Sarwar | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-168 | SUBS-168 | Handover By M.Abbas | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | SUBS-10 | SUBS-5 | Muhammad Abbas | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2.22
https://octopusdtlsupport.atlassian.net/browse/SUBS-169 | SUBS-169 | Handover By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | SUBS-10 | SUBS-5 | Waqar Rasheed | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2.22
https://octopusdtlsupport.atlassian.net/browse/SUBS-17 | SUBS-17 | FE Deployment + Unit Testing + DB Cleanup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | SUBS-9 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-18 | 9.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-170 | SUBS-170 | Handover To QA - Faiza | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | SUBS-10 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2.22
https://octopusdtlsupport.atlassian.net/browse/SUBS-171 | SUBS-171 | Handover To QA - Sarmad | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | SUBS-10 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-172 | SUBS-172 | Brainstorming Structure / Tools | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-6 | SUBS-6 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-01-29 | 2026-02-03 | 2026-01-29 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-173 | SUBS-173 | Discussion on Requirements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-6 | SUBS-6 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-174 | SUBS-174 | ERD Diagram Creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-6 | SUBS-6 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-01-09 | 2026-01-12 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-175 | SUBS-175 | A Duplicate version name is being generated. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-176 | SUBS-176 | Bad Request Error 400, Is being displayed while Entering Decimal Version Number. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-177 | SUBS-177 | 400 Bad Request Error occurred, when you clicked the Create button after entering only a space in the name field. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-02 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-178 | SUBS-178 | The created version's table does not have a change summary column to verify the information the user provided during version creation. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-179 | SUBS-179 | The name and Change Summary fields are unrestricted. Additionally, it gives 400 Bad Requests for long characters length . | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-18 | SUBS-18 | Unit Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | SUBS-9 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-180 | SUBS-180 | Meter Code Cannot Be Re-Added After Deletion or Used Across Different Versions | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-02 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-181 | SUBS-181 | Version is getting created only with a single space in the Change Summary field.with success message. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-02 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-182 | SUBS-182 | Versions are not being approved from the front end or the back end. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-183 | SUBS-183 | Bug: The system allows entering a long version number, but upon clicking the Create button, the API fails with a 400 Bad Request error. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-03 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-184 | SUBS-184 | Pagination is missing in Versions table | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-185 | SUBS-185 | "About" and "Support" links in footer are not redirecting. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-186 | SUBS-186 | Search field is missing for Versions. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-03 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-187 | SUBS-187 | Error Message Displayed When Creating Tier, but Tier Is Created Successfully. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-03 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-188 | SUBS-188 | 400 Bad Request Error When Creating Tier with Min Value = 0 and Max Value = Infinity | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-03 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-189 | SUBS-189 | Error Shown When Meter Type Is Set to 0 on Calculator Screen During Quotation Save | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-19 | SUBS-19 | Same name plans, versions, meter types should not be allowed. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-190 | SUBS-190 | Multiple approval popups and API calls triggered on rapid clicks of “Send for Approval” | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-03 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-191 | SUBS-191 | UI layout breaks when entering long characters in Name and Change Summary fields | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-04 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-192 | SUBS-192 | Missing Validation When Name or Email Starts/Ends with Space on Calculator Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-193 | SUBS-193 | Submit and Cancel buttons disappear in approval popup for versions with long names | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-194 | SUBS-194 | Support Icon Not Clickable at Bottom Right | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-195 | SUBS-195 | Product duplication allowed in Product Creation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-04 |  | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-196 | SUBS-196 | Incorrect error message displayed when duplicate Product Code is entered | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-197 | SUBS-197 | Product card UI breaks & missing Controls with long Product Name/Code/Description causing toggle and button functionalities to disappear | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-04 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-198 | SUBS-198 | Long Product name effects all screens: Feature, Plan,Tier, Product menu etc | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-199 | SUBS-199 | Focus moves outside the modal to background page elements, Keyboard focus is not trapped inside Create Product modal | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-05 |  |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-20 | SUBS-20 | Implement Minimum and Maximum Character Limit on Name Field (Calculator Screen) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-200 | SUBS-200 | Need to display validation messages on all modules where validation is applied but message is missing. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-201 | SUBS-201 | No search bar or search functionality is available to search for a product. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-202 | SUBS-202 | “More Filters” Button Not Functional on My Quotation Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-203 | SUBS-203 | The system allows Deletion of a product when its status is Active. Active products should not be deleted directly as they may be linked with other configurations (features, plans, pricing) etc. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-204 | SUBS-204 | Feature name is getting duplicated. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-205 | SUBS-205 | Calculator Screen Data Does Not Clear After Updating a Quotation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-206 | SUBS-206 | No Data Displayed When Updating a Quotation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-207 | SUBS-207 | Incorrect Product Selection After Page Refresh | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-208 | SUBS-208 | One Feature Not Deleted When Deleting Multiple Features – “Invalid Network Error” Displayed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-209 | SUBS-209 | Meter Type Text Overlaps with Supporting Text When Editing Tier | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-21 | SUBS-21 | Show Validation Messages Inline (Below Fields) Instead of Top-Right Toast — Apply Across Application | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-210 | SUBS-210 | Tier Code Case Inconsistency and Missing Validation on Tiers Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-211 | SUBS-211 | Export Document UI Is Disturbed | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-212 | SUBS-212 | Logged-In User Is Also Displayed in Share Quotation List | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-213 | SUBS-213 | Token is not received on email | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-214 | SUBS-214 | Incorrect Button/Text Label Displayed as “Send Reset Instruction” Instead of “Send Reset Token” | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-215 | SUBS-215 | Unable to Login with Newly Created User | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-216 | SUBS-216 | HTTP 401 Unauthorized Error Displayed When Logging Out from Plans and Tiers Screens | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-217 | SUBS-217 | Status Column Displayed Without Actions Column on Versions Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-218 | SUBS-218 | Plan is getting created with 0 Base Price. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [7 empty] | 2026-03-11 | 2026-03-11 | 0.08
https://octopusdtlsupport.atlassian.net/browse/SUBS-219 | SUBS-219 | Incorrect Currency Symbol Displayed on Plan Card for EUR and GBP | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-22 | SUBS-22 | Bugs Fixing + Improvement in the Admin Screens | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 19.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-220 | SUBS-220 | If super admin block any user the message login page should User blocked please contact admin | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-221 | SUBS-221 | Long Plan Description Breaks Plan Card Layout and Causes Misalignment | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-222 | SUBS-222 | Base Price Field Accepts Extremely Large Values and Shows Inconsistent Behavior (Scientific Notation / Infinity / 0) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-223 | SUBS-223 | Generic Network Error Displayed When Using Same Plan Code Across Different Products | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-224 | SUBS-224 | Success Message Shown When Re-Sharing Quotation Back to Original User, but Quotation Is Not Actually Shared | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-225 | SUBS-225 | Calculator Screen Not Reset When Changing Plan | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-226 | SUBS-226 | Total Amount on Quotation Screen Is Incorrect After Editing Quotation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-227 | SUBS-227 | Inactive Product Becomes Active Automatically After Update | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-228 | SUBS-228 | User Can Re-Share Quotation Even When Edit Permission Is Disabled | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-229 | SUBS-229 | The Plan Code field accepts lowercase characters (aa).However, based on the validation rules used for Product Code, Feature Code, only uppercase letters, numbers and underscores should be allowed.secondly Plan Code Field Accepts Invalid Special Characters | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-23 | SUBS-23 | Add Scrollbar to Price Summary and Subscription Configuration Sections on Calculator Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-230 | SUBS-230 | Base Price Field Does Not Accept Decimal Values | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-231 | SUBS-231 | Plan Code Not Displayed on Plan Card After Plan Creation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-232 | SUBS-232 | Edit Status Message Persists Unnecessarily on Plans Screen | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-233 | SUBS-233 | Preview Screen Displays Only One Feature While Multiple Active Features Exist | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-234 | SUBS-234 | Plan is not getting Inactive | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-235 | SUBS-235 | Invalid Pricing Format Displayed for Non-USD Currencies in Preview | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-24 | SUBS-24 | Duplicate Product , Pricing Config fixed | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [7 empty] | 2026-03-03 | 2026-03-03 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-243 | SUBS-243 | Demo with Management + Internal Team Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-244 | SUBS-244 | Updated Product Configs + Info Update | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-245 | SUBS-245 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | SUBS-240 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-27 | 24
https://octopusdtlsupport.atlassian.net/browse/SUBS-246 | SUBS-246 | Old Forgot Password Link Remains Valid After New Reset Email and Even After Use | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-247 | SUBS-247 | User is able to set current password as new password. | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-248 | SUBS-248 | Eye Icon on New Password Field Also Affects Confirm Password Field | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-249 | SUBS-249 | Added Discount Field + Integrated New Tier price logic | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-25 | SUBS-25 | Add “Created At” Column on My Quotation Screen and Correct "Last Modified" column Behavior | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [7 empty] | 2026-03-05 | 2026-03-05 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-250 | SUBS-250 | Feature Code Validation Incorrectly Applied Across Products | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-251 | SUBS-251 | “Back to Login” Link Missing on Set New Password Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-252 | SUBS-252 | Implement Reset Password Option Within the Application | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-253 | SUBS-253 | Final Bundle Rate Not Applied Correctly Across All Sites at Maximum Threshold | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-254 | SUBS-254 | Added Discount Not Reflected in Subscription Summary on Viewing Quotation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-255 | SUBS-255 | Discount Not Retained and Price Changes When Opening Quotation in Edit Mode | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-256 | SUBS-256 | Meter Type Label Not Displayed on Calculator Screen (OmniChat) | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-257 | SUBS-257 | QA reported Bugs for Auth and Admin Flow | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-258 | SUBS-258 | Added In-app Reset Password Module | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-259 | SUBS-259 | Add discount in Qoutes | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 5
https://octopusdtlsupport.atlassian.net/browse/SUBS-26 | SUBS-26 | Implement validation to restrict numeric-only values in Product Name | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-260 | SUBS-260 | Demo with Management / Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 5
https://octopusdtlsupport.atlassian.net/browse/SUBS-261 | SUBS-261 | QA Reported Bugs for Calculator and Quotations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-262 | SUBS-262 | Testing By Waqar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | SUBS-242 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-263 | SUBS-263 | User Unable to Save Quotation on Production | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-264 | SUBS-264 | FE & BE Deployments + DB Migrations and Cleanup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | SUBS-242 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-265 | SUBS-265 | Omni Connect Configuration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | SUBS-240 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-03-31 | 2026-04-02 | 2026-03-31 | 2026-04-02 | 24
https://octopusdtlsupport.atlassian.net/browse/SUBS-266 | SUBS-266 | Configuring OmniConnect + Moving Data to Production | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-267 | SUBS-267 | Demo with TOM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Zain Munir | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-268 | SUBS-268 | Incorporating Changes by TOM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Zain Munir | [5 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-269 | SUBS-269 | Demo with TOM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-27 | SUBS-27 | Bug fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-04 | 9
https://octopusdtlsupport.atlassian.net/browse/SUBS-270 | SUBS-270 | Price is not showing for Report Builder and Offline Mode features in DL | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-271 | SUBS-271 | Final reviewing after bugs fixing and before IA/Tom's review | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Ameer Hamza Khan | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-272 | SUBS-272 | Added MeterType Update Feature + Unit Testing + Deployments on Staging | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Zain Munir | [5 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-273 | SUBS-273 | Bug Fixing and Discussions | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 2.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-274 | SUBS-274 | Deployments + Data Migration + Product Info Updates | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | SUBS-242 | SUBS-236 | Zain Munir | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-275 | SUBS-275 | Pricing Demo to TOM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-276 | SUBS-276 | Internal review after incorporating all feedbacks | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Ameer Hamza Khan | [5 empty] | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 12
https://octopusdtlsupport.atlassian.net/browse/SUBS-277 | SUBS-277 | OmniConnect's Pricing Review with Asmar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Zain Munir | [7 empty] | 2026-04-07 | 2026-04-07 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-278 | SUBS-278 | 2nd Pricing review with TOM | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-279 | SUBS-279 | Changes Overview with Asmar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 0.67
https://octopusdtlsupport.atlassian.net/browse/SUBS-28 | SUBS-28 | DO not delete any plan or product if it is being used in Qoutations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-280 | SUBS-280 | Second Demo to Tom | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-281 | SUBS-281 | Add sorting mechanism for products and features | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-08 | 2026-04-10 | 2026-04-08 | 2026-04-08 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-282 | SUBS-282 | Pricing overview with Asmar | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-283 | SUBS-283 | Testing by Waqar After Changes incorporated as per TOM’s feedback. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | SUBS-242 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-284 | SUBS-284 | 2nd Pricing review with Tom | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Zain Munir | [7 empty] | 2026-04-07 | 2026-04-07 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-285 | SUBS-285 | Incorporate Sorting, Info Icons and UI adjustments in review from Tom | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Zain Munir | [7 empty] | 2026-04-08 | 2026-04-09 | 15.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-286 | SUBS-286 | Calculator Screen Not Reset When Changing Product While Editing Quotation | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-287 | SUBS-287 | Manage Onetime total in quotations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-288 | SUBS-288 | Products Not Loading on Production | Bug Subtask | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | SUBS-241 | SUBS-236 | Faiza Nasir | [7 empty] | 2026-04-09 | 2026-04-09 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-289 | SUBS-289 | Production Deployment - Tom's Feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | SUBS-242 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-29 | SUBS-29 | Setup 1 active pricing configuration per Product | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-06 | 6
https://octopusdtlsupport.atlassian.net/browse/SUBS-290 | SUBS-290 | 3rd Pricing Review with Tom | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Zain Munir | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-291 | SUBS-291 | 3rd Pricing Review with Tom | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-292 | SUBS-292 | 3rd Pricing Review with Tom | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-293 | SUBS-293 | IP meeting Demo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-294 | SUBS-294 | Pre Launch Demo with Sales Team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Zain Munir | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-295 | SUBS-295 | Pre-Launch Demo Sales Team | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-296 | SUBS-296 | CRM ID Verification | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | SUBS-240 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-297 | SUBS-297 | CRM Id Addition & Pre Launch Review Modifications | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | SUBS-239 | SUBS-236 | Zain Munir | [5 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 10.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-298 | SUBS-298 | Verification of Sales Team Configuration Requirements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | SUBS-240 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 3.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-299 | SUBS-299 | Meeting with KM for OmniDocs Pricing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Zain Munir | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-30 | SUBS-30 | Admin Improvements + One Time Payment Implementation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 13
https://octopusdtlsupport.atlassian.net/browse/SUBS-300 | SUBS-300 | Meeting with Khurram Mir over Pricing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Faiza Nasir | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-301 | SUBS-301 | Meeting with Khurram Mir for OmniDocs Pricing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-302 | SUBS-302 | Omni Docs Configuration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | SUBS-240 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-303 | SUBS-303 | Meeting with Asmar for Omni Connect Pricing and Sales feedback | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | SUBS-238 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.75
https://octopusdtlsupport.atlassian.net/browse/SUBS-304 | SUBS-304 | Incorporate Omni Connect Enhancements | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | SUBS-240 | SUBS-236 | Waqar Rasheed | [5 empty] | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-31 | SUBS-31 | Special Characters Not Handled Correctly in Feature Name Field | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-32 | SUBS-32 | Meter Type UI Fix + Tiers validations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-33 | SUBS-33 | On Save and Update Quotation, redirect the user to My Quotation page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-34 | SUBS-34 | Created by, Updated By, Created On, Column Should be implemented in the Application. | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-35 | SUBS-35 | UI improvement for Plans screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-36 | SUBS-36 | UI improvement for tiers screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-37 | SUBS-37 | UI improvement for Preview screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.33
https://octopusdtlsupport.atlassian.net/browse/SUBS-38 | SUBS-38 | UI improvement for Parameters Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.67
https://octopusdtlsupport.atlassian.net/browse/SUBS-39 | SUBS-39 | UI improvement for Versions screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-40 | SUBS-40 | UI improvement for Products and Features screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 |  | 2026-03-10 | 2026-03-10 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-41 | SUBS-41 | Change “Platform Fees” Text to “Subscription Fee” on Viewing Quotation Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-42 | SUBS-42 | Implement Search Functionality on Share Quotation Popup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-43 | SUBS-43 | QA Reported Bugs related to Admin screens | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-11 | 13
https://octopusdtlsupport.atlassian.net/browse/SUBS-44 | SUBS-44 | Project Demo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-45 | SUBS-45 | Export Document UI Fix + Subscription fee text | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-46 | SUBS-46 | Share functionality fixed for quotations | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-47 | SUBS-47 | Bugs, from QA and findings during unit testing, fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Ameer Hamza Khan | [5 empty] | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-03-13 | 48
https://octopusdtlsupport.atlassian.net/browse/SUBS-48 | SUBS-48 | Bugs, from QA and findings during unit testing, fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-49 | SUBS-49 | Product Demo Discussion + Preparation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-50 | SUBS-50 | Update Brochures of Configured Products with Latest Information | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-51 | SUBS-51 | Demo Preparation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 5.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-52 | SUBS-52 | Bug Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-16 | 11
https://octopusdtlsupport.atlassian.net/browse/SUBS-53 | SUBS-53 | QA Reported Bugs Fix for Plans Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-54 | SUBS-54 | QA Reported Bugs Fix for Tiers Screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-55 | SUBS-55 | Demo Prep / Data Prep / Bugs Fixing for Demo | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-56 | SUBS-56 | Add “Created At” Column on My Quotation Screen and Correct "Last Modified" column Behavior | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-57 | SUBS-57 | Discussions on KT | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 0.42
https://octopusdtlsupport.atlassian.net/browse/SUBS-58 | SUBS-58 | Task Implementations and Bugs Fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Zain Munir | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-59 | SUBS-59 | Figuring out issues for preview screen on logout | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-60 | SUBS-60 | Preview stale cache fix for runtime count | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-17 |  | 2026-03-17 | 2026-03-17 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-61 | SUBS-61 | Currency issues on plans and preview page | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-62 | SUBS-62 | Fixed Issues of My Quotation and Calculator screen | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 3.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-63 | SUBS-63 | Bug fixing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | SUBS-12 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1
https://octopusdtlsupport.atlassian.net/browse/SUBS-64 | SUBS-64 | OMNI- Chat Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | SUBS-11 | SUBS-5 | Waqar Rasheed | [5 empty] | 2026-03-06 | 2026-03-11 | 2026-03-09 | 2026-03-16 | 30
https://octopusdtlsupport.atlassian.net/browse/SUBS-65 | SUBS-65 | Digital Log Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | SUBS-11 | SUBS-5 | Namra Zahid | [5 empty] | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | 32
https://octopusdtlsupport.atlassian.net/browse/SUBS-66 | SUBS-66 | Fintech Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | SUBS-11 | SUBS-5 | Namra Zahid | [5 empty] | 2026-03-06 | 2026-03-11 | 2026-03-06 | 2026-03-17 | 52
https://octopusdtlsupport.atlassian.net/browse/SUBS-67 | SUBS-67 | OMNI Connect Testing | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | SUBS-11 | SUBS-5 | Waqar Rasheed | [5 empty] | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-17 | 39
https://octopusdtlsupport.atlassian.net/browse/SUBS-68 | SUBS-68 | Product Mapping | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | SUBS-11 | SUBS-5 | Muhammad Abbas | [5 empty] | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | 14
https://octopusdtlsupport.atlassian.net/browse/SUBS-69 | SUBS-69 | Testing by Zeeshan | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | SUBS-11 | SUBS-5 | Zeeshan Sarwar | [5 empty] | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-11 | 10.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-70 | SUBS-70 | Frontend Setup & Requirements Discussion | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Ali Qumail | [5 empty] | 2026-01-07 | 2026-01-07 | 2026-01-09 | 2026-01-09 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-71 | SUBS-71 | Frontend Setup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-72 | SUBS-72 | Pages for Sales Person | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [9 empty] | 0
https://octopusdtlsupport.atlassian.net/browse/SUBS-73 | SUBS-73 | Backend Project Setup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-01-08 | 2026-02-03 | 2026-01-08 | 2026-02-02 | 8.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-74 | SUBS-74 | Pages for super-admin | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-75 | SUBS-75 | Static pages for sales-agent | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-76 | SUBS-76 | Static pages for approver | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-77 | SUBS-77 | Dark mode | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-78 | SUBS-78 | Azure setup + Deployment | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-79 | SUBS-79 | Designing KT To Sarmad | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-04 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-80 | SUBS-80 | Entity Framework Code first approach setup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-81 | SUBS-81 | Initial Migration Creation | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-82 | SUBS-82 | Installing required Dependencies | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-83 | SUBS-83 | User Management API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-06 | 2026-02-18 | 2026-02-06 | 2026-02-18 | 9
https://octopusdtlsupport.atlassian.net/browse/SUBS-84 | SUBS-84 | Login / Authentication APIs Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-09 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-85 | SUBS-85 | Pricing Configuration / PRICING_CONFIG_APPROVAL_EVENTS / Products / Features API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-10 | 2026-02-11 | 2026-02-10 | 2026-02-11 | 9.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-86 | SUBS-86 | Plans / Plan Tiers / PLAN_TIER_SKUS / Allowance / SKU_ALLOWANCES API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-11 | 2026-02-23 | 2026-02-12 | 2026-02-23 | 9.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-87 | SUBS-87 | QUOTES / QUOTE_EXPORTS /QUOTE_LINE_ITEMS / QUOTE_NOTES / QOUTE STATUS API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-17 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-88 | SUBS-88 | AUDIT_LOGS APIs Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-13 | 2026-02-16 | 2026-02-13 | 2026-02-16 | 7
https://octopusdtlsupport.atlassian.net/browse/SUBS-89 | SUBS-89 | METER_TYPES API Development | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-16 | 2026-02-19 | 2026-02-16 | 2026-02-18 | 7
https://octopusdtlsupport.atlassian.net/browse/SUBS-90 | SUBS-90 | APIs Creation to view products along with plans | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Faiza Nasir | [5 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 1.5
https://octopusdtlsupport.atlassian.net/browse/SUBS-91 | SUBS-91 | Frontend and Backend setup | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 5
https://octopusdtlsupport.atlassian.net/browse/SUBS-92 | SUBS-92 | Login Page API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2
https://octopusdtlsupport.atlassian.net/browse/SUBS-93 | SUBS-93 | Products API Integration (Super Admin) | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Sarmad Sabir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 3
https://octopusdtlsupport.atlassian.net/browse/SUBS-94 | SUBS-94 | Reset Pwd Email & JWT Bearer Token | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4
https://octopusdtlsupport.atlassian.net/browse/SUBS-95 | SUBS-95 | Login API Integration + Authorization | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-96 | SUBS-96 | User + Product API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-97 | SUBS-97 | Meter Types Frontend, API Modification & Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Zain Munir | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-98 | SUBS-98 | Roles, Forgot, Reset, User API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8
https://octopusdtlsupport.atlassian.net/browse/SUBS-99 | SUBS-99 | Completed User, Roles Frontend and API Integration | Sub-task | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | SUBS-13 | SUBS-5 | Muhammad Ahmad Saleem | [5 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5
https://octopusdtlsupport.atlassian.net/browse/WOM-136 | WOM-136 | Field Service Maintenance February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | WOM-135 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-138 | WOM-138 | Field Service Configuration February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | WOM-137 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-144 | WOM-144 | Field Service Configuration February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | WOM-139 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16
https://octopusdtlsupport.atlassian.net/browse/WOM-145 | WOM-145 | Field Service Configuration February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | WOM-140 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-146 | WOM-146 | Field Service Configuration February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | WOM-141 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-147 | WOM-147 | Field Service Configuration February 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | WOM-142 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 13
https://octopusdtlsupport.atlassian.net/browse/WOM-148 | WOM-148 | Field Service Maintenance March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | WOM-135 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5
https://octopusdtlsupport.atlassian.net/browse/WOM-149 | WOM-149 | Field Service Configuration March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | WOM-137 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5
https://octopusdtlsupport.atlassian.net/browse/WOM-150 | WOM-150 | Field Service Configuration March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | WOM-139 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 13
https://octopusdtlsupport.atlassian.net/browse/WOM-151 | WOM-151 | Field Service Configuration March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | WOM-140 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5
https://octopusdtlsupport.atlassian.net/browse/WOM-152 | WOM-152 | Field Service Configuration March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | WOM-141 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5
https://octopusdtlsupport.atlassian.net/browse/WOM-153 | WOM-153 | Field Service Configuration March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-143 | WOM-143 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-154 | WOM-154 | Field Service Configuration March 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | WOM-142 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 16
https://octopusdtlsupport.atlassian.net/browse/WOM-155 | WOM-155 | Field Service Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | WOM-135 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-156 | WOM-156 | Field Service Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | WOM-137 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-157 | WOM-157 | Field Service Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | WOM-139 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 16
https://octopusdtlsupport.atlassian.net/browse/WOM-158 | WOM-158 | Field Service Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | WOM-140 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-159 | WOM-159 | CRM AMS Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | WOM-141 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8
https://octopusdtlsupport.atlassian.net/browse/WOM-160 | WOM-160 | Field Service Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | WOM-142 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-28 | 16
https://octopusdtlsupport.atlassian.net/browse/WOM-161 | WOM-161 | Field Service Configuration and Testing April 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-143 | WOM-143 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 16
https://octopusdtlsupport.atlassian.net/browse/WOM-162 | WOM-162 | Field Service Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-143 | WOM-143 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 16
https://octopusdtlsupport.atlassian.net/browse/WOM-163 | WOM-163 | Field Service Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | WOM-135 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-05-11 | 2026-05-11 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-164 | WOM-164 | Field Service Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | WOM-137 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-05-12 | 2026-05-12 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-165 | WOM-165 | Field Service Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | WOM-139 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-05-14 | 2026-05-15 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-166 | WOM-166 | Field Service Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | WOM-140 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-05-18 | 2026-05-18 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-167 | WOM-167 | Field Service Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | WOM-141 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-05-19 | 2026-05-19 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-168 | WOM-168 | Field Service Configuration and Testing May 2026 | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | WOM-142 | WOM-134 | Muhammad Imran Aslam | [5 empty] | 2026-05-21 | 2026-05-22 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-172 | WOM-172 | Mar effort | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-171 | WOM-171 | WOM-169 | Unassigned | [5 empty] | 2026-03-31 | 2026-03-31 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-173 | WOM-173 | Apr effort | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-171 | WOM-171 | WOM-169 | Unassigned | [5 empty] | 2026-04-01 | 2026-04-04 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-178 | WOM-178 | Apr effort | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-177 | WOM-177 | WOM-169 | Unassigned | [5 empty] | 2026-04-30 | 2026-04-30 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-179 | WOM-179 | May effort | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-177 | WOM-177 | WOM-169 | Unassigned | [5 empty] | 2026-05-01 | 2026-05-07 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-181 | WOM-181 | Apr effort | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-180 | WOM-180 | WOM-169 | Unassigned | [5 empty] | 2026-04-30 | 2026-04-30 |  |  | 0
https://octopusdtlsupport.atlassian.net/browse/WOM-182 | WOM-182 | May effort | Sub-task | https://octopusdtlsupport.atlassian.net/browse/WOM-180 | WOM-180 | WOM-169 | Unassigned | [5 empty] | 2026-05-01 | 2026-05-07 |  |  | 0