## IPP Phase Breakdown
Source Sheet | Row Number | Product | Epic/RMI | Epic/RMI Jira Link | Epic Planned Start Date | Epic Planned End Date | Epic Actual Date (Production Date) | Remarks | Research/URS Planned Start Date | Research/URS Planned End Date | Research/URS Planned Man-days | Research/URS Raw Planned Range | Research/URS Planning State | Research/URS Parse Warning | DDS Planned Start Date | DDS Planned End Date | DDS Planned Man-days | DDS Raw Planned Range | DDS Planning State | DDS Parse Warning | Development Planned Start Date | Development Planned End Date | Development Planned Man-days | Development Raw Planned Range | Development Planning State | Development Parse Warning | SQA Planned Start Date | SQA Planned End Date | SQA Planned Man-days | SQA Raw Planned Range | SQA Planning State | SQA Parse Warning | User Manual Planned Start Date | User Manual Planned End Date | User Manual Planned Man-days | User Manual Raw Planned Range | User Manual Planning State | User Manual Parse Warning | Production Planned Start Date | Production Planned End Date | Production Planned Man-days | Production Raw Planned Range | Production Planning State | Production Parse Warning | Any Phase Parse Warning | Any No Entry | Any Not Planned | Any Skipped | Computed Total Phase Man-days | Computed Has Valid Epic Plan | Computed Epic Planned Start ISO | Computed Epic Planned End ISO | Computed Epic Actual ISO
Latest - 25 Feb 2026 | 2 | OmniConnect | Batch/Bpm modify Existing ADX IT Table | https://octopusdtlsupport.atlassian.net/browse/O2-810 | 2025-12-30 | 2026-02-06 | 2026-02-19 | Requires confirmation from IMPL team | 2025-12-30 | 2026-01-06 | 12 | 30-Dec-2025 <> 6-Jan-2026 ¦ 12 mandays | planned |  |  |  |  | Skipped | skipped |  | 2026-01-07 | 2026-01-16 | 24 | 7-Jan-2026 <> 16-Jan-2026 ¦ 24 mandays | planned |  | 2026-01-19 | 2026-01-26 | 18 | 19-Jan-2026 <> 26-Jan-2026 ¦ 18 mandays | planned |  | 2026-01-19 | 2026-01-26 | 6 | 19-Jan-2026 <> 26-Jan-2026 ¦ 6 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 60 | Yes | 2025-12-30 | 2026-02-06 | 2026-02-19
Latest - 25 Feb 2026 | 3 | OmniConnect | APX Pump – Variable Speed Dashboard | https://octopusdtlsupport.atlassian.net/browse/O2-887 | 2025-12-23 | 2026-02-06 | 2026-02-19 | Linked with no release of Batch/BPM | 2025-12-23 | 2026-01-12 | 5 | 23-Dec-2025 <> 12-Jan-2026 ¦ 5 mandays | planned |  |  |  |  | Skipped | skipped |  | 2026-01-13 | 2026-01-21 | 10 | 13-Jan-2026 <> 21-Jan-2026 ¦ 10 mandays | planned |  | 2026-01-22 | 2026-01-23 | 4 | 22-Jan-2026 <> 23-Jan-2026 ¦ 4 mandays | planned |  | 2026-01-22 | 2026-01-23 | 2 | 22-Jan-2026 <> 23-Jan-2026 ¦ 2 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 21 | Yes | 2025-12-23 | 2026-02-06 | 2026-02-19
Latest - 25 Feb 2026 | 4 | OmniConnect | Real-time Tag Streaming | https://octopusdtlsupport.atlassian.net/browse/O2-793 | 2025-12-23 | 2026-02-06 | 2026-03-13 | Ashghal required attention, rolled back | 2025-12-11 | 2026-01-22 |  | 11-Dec-2025 <> 22-Jan-2026 ¦ Not Planned mandays | not_planned |  |  |  |  | Not planned | not_planned |  | 2025-12-23 | 2026-01-31 | 15 | 23-Dec-2025 <> 31-Jan-2026 ¦ 15 mandays | planned |  |  |  |  | Not planned | not_planned |  |  |  |  | Not planned | not_planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | No | 15 | Yes | 2025-12-23 | 2026-02-06 | 2026-03-13
Latest - 25 Feb 2026 | 5 | OmniConnect | Calculated Tag Enrich with no code (Nested Calculation) | https://octopusdtlsupport.atlassian.net/browse/O2-697 | 2026-01-28 | 2026-02-27 | 2026-02-19 |  |  |  |  | Skipped | skipped |  |  |  |  | Skipped | skipped |  | 2025-12-04 | 2026-01-20 | 34 | 4-Dec-2025 <> 20-Jan-2026 ¦ 34 mandays | planned |  | 2026-01-21 | 2026-01-30 | 16 | 21-Jan-2026 <> 30-Jan-2026 ¦ 16 mandays | planned |  | 2026-01-21 | 2026-01-30 | 5 | 21-Jan-2026 <> 30-Jan-2026 ¦ 5 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 55 | Yes | 2026-01-28 | 2026-02-27 | 2026-02-19
Latest - 25 Feb 2026 | 6 | OmniConnect | APX Performance Visualization Enhancements | https://octopusdtlsupport.atlassian.net/browse/O2-457 | 2026-01-26 | 2026-02-26 | 2026-03-03 |  | 2026-01-26 | 2026-01-30 | 15 | 26-Jan-2026 <> 30-Jan-2026 ¦ 15 mandays | planned |  |  |  |  | Skipped | skipped |  | 2026-02-02 | 2026-02-23 | 15 | 2-Feb-2026 <> 23-Feb-2026 ¦ 15 mandays | planned |  | 2026-02-24 | 2026-03-03 | 10 | 24-Feb-2026 <> 3-Mar-2026 ¦ 10 mandays | planned |  | 2026-02-24 | 2026-03-03 | 5 | 24-Feb-2026 <> 3-Mar-2026 ¦ 5 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 45 | Yes | 2026-01-26 | 2026-02-26 | 2026-03-03
Latest - 25 Feb 2026 | 7 | OmniConnect | Subscription Management | https://octopusdtlsupport.atlassian.net/browse/O2-857 | 2026-01-07 | 2026-03-06 | 2026-03-06 |  | 2026-01-07 | 2026-01-08 | 4 | 7-Jan-2026 <> 8-Jan-2026 ¦ 4 mandays | planned |  | 2026-01-08 | 2026-01-08 | 1 | 8-Jan-2026 <> 8-Jan-2026 ¦ 1 mandays | planned |  | 2026-02-02 | 2026-02-20 | 36 | 2-Feb-2026 <> 20-Feb-2026 ¦ 36 mandays | planned |  | 2026-02-23 | 2026-03-06 | 20 | 23-Feb-2026 <> 6-Mar-2026 ¦ 20 mandays | planned |  | 2026-02-23 | 2026-03-06 | 20 | 23-Feb-2026 <> 6-Mar-2026 ¦ 20 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | No | 81 | Yes | 2026-01-07 | 2026-03-06 | 2026-03-06
Latest - 25 Feb 2026 | 8 | Digital Log | Read API (Programmatic Data Access) | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-146 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  |  |  |  | Skipped | skipped |  |  |  |  | Skipped | skipped |  | 2026-01-28 | 2026-02-06 | 21 | 28-Jan-2026 <> 6-Feb-2026 ¦ 21 mandays | planned |  | 2026-02-09 | 2026-02-12 | 4 | 9-Feb-2026 <> 12-Feb-2026 ¦ 4 mandays | planned |  | 2026-02-09 | 2026-02-12 | 4 | 9-Feb-2026 <> 12-Feb-2026 ¦ 4 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 29 | Yes | 2026-01-07 | 2026-02-20 | 2026-02-20
Latest - 25 Feb 2026 | 9 | Digital Log | Digital Log - Journal Log (Web & Mobile) | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  |  |  |  | Skipped | skipped |  |  |  |  | Skipped | skipped |  | 2026-01-12 | 2026-01-27 | 30 | 12-Jan-2026 <> 27-Jan-2026 ¦ 30 mandays | planned |  | 2026-01-28 | 2026-02-03 | 5 | 28-Jan-2026 <> 3-Feb-2026 ¦ 5 mandays | planned |  | 2026-01-28 | 2026-02-03 | 5 | 28-Jan-2026 <> 3-Feb-2026 ¦ 5 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 40 | Yes | 2026-01-07 | 2026-02-20 | 2026-02-20
Latest - 25 Feb 2026 | 10 | Digital Log | Digital Log - Domain Migration to Brand Octopus Digital | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  |  |  |  | Skipped | skipped |  |  |  |  | Skipped | skipped |  | 2026-02-09 | 2026-02-12 | 12 | 9-Feb-2026 <> 12-Feb-2026 ¦ 12 mandays | planned |  | 2026-02-13 | 2026-02-19 | 4 | 13-Feb-2026 <> 19-Feb-2026 ¦ 4 mandays | planned |  | 2026-02-13 | 2026-02-19 | 4 | 13-Feb-2026 <> 19-Feb-2026 ¦ 4 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 20 | Yes | 2026-01-07 | 2026-02-20 | 2026-02-20
Latest - 25 Feb 2026 | 11 | Digital Log | Log Chat Integration | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-192 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  |  |  |  | Skipped | skipped |  |  |  |  | Skipped | skipped |  | 2026-01-07 | 2026-01-13 | 10 | 7-Jan-2026 <> 13-Jan-2026 ¦ 10 mandays | planned |  | 2026-01-14 | 2026-01-21 | 6 | 14-Jan-2026 <> 21-Jan-2026 ¦ 6 mandays | planned |  | 2026-01-14 | 2026-01-21 | 6 | 14-Jan-2026 <> 21-Jan-2026 ¦ 6 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 22 | Yes | 2026-01-07 | 2026-02-20 | 2026-02-20
Latest - 25 Feb 2026 | 12 | Fintech Fuel | Mobile Application | https://octopusdtlsupport.atlassian.net/browse/FF-119 | 2025-11-17 | 2026-02-12 | 2026-02-12 |  |  |  |  | Not Planned | not_planned |  |  |  |  | Not Planned | not_planned |  |  |  |  | Not Planned | not_planned |  |  |  |  | Not Planned | not_planned |  |  |  |  | Not Planned | not_planned |  |  |  |  | Not Planned | not_planned |  | No | No | Yes | No | 0 | Yes | 2025-11-17 | 2026-02-12 | 2026-02-12
Latest - 25 Feb 2026 | 13 | Fintech Fuel | Fintech Fuel Read API | https://octopusdtlsupport.atlassian.net/browse/FF-271 | 2026-01-12 | 2026-02-09 | 2026-02-09 |  | 2026-01-12 | 2026-01-14 | 3 | 12-Jan-2026 <> 14-Jan-2026 ¦ 3 mandays | planned |  |  |  |  | Skipped | skipped |  | 2026-01-28 | 2026-02-03 | 10 | 28-Jan-2026 <> 3-Feb-2026 ¦ 10 mandays | planned |  | 2026-02-04 | 2026-02-09 | 5 | 4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays | planned |  | 2026-02-04 | 2026-02-09 | 5 | 4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays | planned |  |  |  |  | Not Planned | not_planned |  | No | No | Yes | Yes | 23 | Yes | 2026-01-12 | 2026-02-09 | 2026-02-09
Latest - 25 Feb 2026 | 14 | Fintech Fuel | Fintech Diagnostics Dashboard | https://octopusdtlsupport.atlassian.net/browse/FF-274 | 2026-01-28 | 2026-02-09 | 2026-02-09 |  |  |  |  | Skipped | skipped |  |  |  |  | Skipped | skipped |  | 2026-01-28 | 2026-02-03 | 10 | 28-Jan-2026 <> 3-Feb-2026 ¦ 10 mandays | planned |  | 2026-02-04 | 2026-02-09 | 5 | 4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays | planned |  | 2026-02-04 | 2026-02-09 | 5 | 4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays | planned |  |  |  |  | Not Planned | not_planned |  | No | No | Yes | Yes | 20 | Yes | 2026-01-28 | 2026-02-09 | 2026-02-09
Latest - 25 Feb 2026 | 15 | Fintech Fuel | ALSONs device integration (read only) | https://octopusdtlsupport.atlassian.net/browse/FF-292 | [8 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry |  | No | Yes | No | No | 0 | No
Latest - 25 Feb 2026 | 16 | Fintech Fuel | Automated Site Configuration | https://octopusdtlsupport.atlassian.net/browse/FF-297 | [8 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry |  | No | Yes | No | No | 0 | No
Latest - 25 Feb 2026 | 17 | Fintech Fuel | Fuel price write back | https://octopusdtlsupport.atlassian.net/browse/FF-302 | [8 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry |  | No | Yes | No | No | 0 | No
Latest - 25 Feb 2026 | 18 | OmniChat | OmniChat Known Bugs Fixing | https://octopusdtlsupport.atlassian.net/browse/MN-78 | [8 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry | [5 empty] | no_entry |  | No | Yes | No | No | 0 | No
Latest - 25 Feb 2026 | 19 | OmniChat | Integration with OmniAgent | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | 2026-02-23 | 2026-03-26 | 2026-03-26 |  |  |  |  | Skipped | skipped |  | 2026-02-23 | 2026-02-25 | 4 | 23-Feb-2026 <> 25-Feb-2026 ¦ 4 mandays | planned |  | 2026-02-26 | 2026-03-16 | 33 | 26-Feb-2026 <> 16-Mar-2026 ¦ 33 mandays | planned |  | 2026-03-17 | 2026-03-24 | 5 | 17-Mar-2026 <> 24-Mar-2026 ¦ 5 mandays | planned |  | 2026-03-17 | 2026-03-24 | 3 | 17-Mar-2026 <> 24-Mar-2026 ¦ 3 mandays | planned |  | 2026-03-25 | 2026-03-26 | 14 | 25-Mar-2026 <> 26-Mar-2026 ¦ 14 mandays | planned |  | No | No | No | Yes | 59 | Yes | 2026-02-23 | 2026-03-26 | 2026-03-26

## IPP Dashboard Computed
Source Sheet | Row Number | Product | Epic/RMI | Epic/RMI Jira Link | Epic Planned Start Date | Epic Planned End Date | Epic Actual Date (Production Date) | Remarks | Computed Total Phase Man-days | Computed Roadmap Valid | Computed Roadmap Axis Start ISO | Computed Roadmap Axis End ISO | Computed Roadmap Axis Span Days | Computed Roadmap Today In Range | Computed Roadmap Today Left Pct | Computed Roadmap Bar Left Pct | Computed Roadmap Bar Width Pct | Computed Roadmap Actual Left Pct | Computed Roadmap Week Ticks JSON | Computed MiniGantt Has Dated Phases | Computed MiniGantt Axis Start ISO | Computed MiniGantt Axis End ISO | Computed MiniGantt Axis Span Days | Computed MiniGantt Timeline Width Px | Computed MiniGantt Scroll Enabled | Computed MiniGantt Week Ticks JSON | Computed MiniGantt Today In Range | Computed MiniGantt Today Left Pct | Computed Phase Geometry JSON
Latest - 25 Feb 2026 | 2 | OmniConnect | Batch/Bpm modify Existing ADX IT Table | https://octopusdtlsupport.atlassian.net/browse/O2-810 | 2025-12-30 | 2026-02-06 | 2026-02-19 | Requires confirmation from IMPL team | 60 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 40.1826 | 17.3516 | 63.4703 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2025-12-20 | 2026-02-05 | 48 | 1152 | Yes | [{"iso": "2025-12-20", "label": "20-Dec-2025", "left_pct": 0.0}, {"iso": "2025-12-27", "label": "27-Dec-2025", "left_pct": 14.8936}, {"iso": "2026-01-03", "label": "03-Jan-2026", "left_pct": 29.7872}, {"iso": "2026-01-10", "label": "10-Jan-2026", "left_pct": 44.6809}, {"iso": "2026-01-17", "label": "17-Jan-2026", "left_pct": 59.5745}, {"iso": "2026-01-24", "label": "24-Jan-2026", "left_pct": 74.4681}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 89.3617}] | No |  | {"Research/URS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2025-12-30", "end_iso": "2026-01-06", "mandays_text": "12", "mandays_num": 12.0, "raw": "30-Dec-2025 <> 6-Jan-2026 ¦ 12 mandays", "valid": true, "bar_left_pct": 21.2766, "bar_width_pct": 14.8936, "bar_thickness_px": 12.6667, "bar_top_offset_px": 8.6667, "start_label": "30-Dec-2025", "end_label": "06-Jan-2026", "bar_label": "12 md", "show_no_bar": false}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-07", "end_iso": "2026-01-16", "mandays_text": "24", "mandays_num": 24.0, "raw": "7-Jan-2026 <> 16-Jan-2026 ¦ 24 mandays", "valid": true, "bar_left_pct": 38.2979, "bar_width_pct": 19.1489, "bar_thickness_px": 17.3333, "bar_top_offset_px": 6.3333, "start_label": "07-Jan-2026", "end_label": "16-Jan-2026", "bar_label": "24 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-19", "end_iso": "2026-01-26", "mandays_text": "18", "mandays_num": 18.0, "raw": "19-Jan-2026 <> 26-Jan-2026 ¦ 18 mandays", "valid": true, "bar_left_pct": 63.8298, "bar_width_pct": 14.8936, "bar_thickness_px": 15.0, "bar_top_offset_px": 7.5, "start_label": "19-Jan-2026", "end_label": "26-Jan-2026", "bar_label": "18 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-19", "end_iso": "2026-01-26", "mandays_text": "6", "mandays_num": 6.0, "raw": "19-Jan-2026 <> 26-Jan-2026 ¦ 6 mandays", "valid": true, "bar_left_pct": 63.8298, "bar_width_pct": 14.8936, "bar_thickness_px": 10.3333, "bar_top_offset_px": 9.8333, "start_label": "19-Jan-2026", "end_label": "26-Jan-2026", "bar_label": "6 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 3 | OmniConnect | APX Pump – Variable Speed Dashboard | https://octopusdtlsupport.atlassian.net/browse/O2-887 | 2025-12-23 | 2026-02-06 | 2026-02-19 | Linked with no release of Batch/BPM | 21 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 36.9863 | 20.5479 | 63.4703 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2025-12-13 | 2026-02-02 | 52 | 1248 | Yes | [{"iso": "2025-12-13", "label": "13-Dec-2025", "left_pct": 0.0}, {"iso": "2025-12-20", "label": "20-Dec-2025", "left_pct": 13.7255}, {"iso": "2025-12-27", "label": "27-Dec-2025", "left_pct": 27.451}, {"iso": "2026-01-03", "label": "03-Jan-2026", "left_pct": 41.1765}, {"iso": "2026-01-10", "label": "10-Jan-2026", "left_pct": 54.902}, {"iso": "2026-01-17", "label": "17-Jan-2026", "left_pct": 68.6275}, {"iso": "2026-01-24", "label": "24-Jan-2026", "left_pct": 82.3529}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 96.0784}] | No |  | {"Research/URS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2025-12-23", "end_iso": "2026-01-12", "mandays_text": "5", "mandays_num": 5.0, "raw": "23-Dec-2025 <> 12-Jan-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 19.6078, "bar_width_pct": 39.2157, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "23-Dec-2025", "end_label": "12-Jan-2026", "bar_label": "5 md", "show_no_bar": false}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-13", "end_iso": "2026-01-21", "mandays_text": "10", "mandays_num": 10.0, "raw": "13-Jan-2026 <> 21-Jan-2026 ¦ 10 mandays", "valid": true, "bar_left_pct": 60.7843, "bar_width_pct": 15.6863, "bar_thickness_px": 11.8889, "bar_top_offset_px": 9.0556, "start_label": "13-Jan-2026", "end_label": "21-Jan-2026", "bar_label": "10 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-22", "end_iso": "2026-01-23", "mandays_text": "4", "mandays_num": 4.0, "raw": "22-Jan-2026 <> 23-Jan-2026 ¦ 4 mandays", "valid": true, "bar_left_pct": 78.4314, "bar_width_pct": 1.9608, "bar_thickness_px": 9.5556, "bar_top_offset_px": 10.2222, "start_label": "22-Jan-2026", "end_label": "23-Jan-2026", "bar_label": "4 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-22", "end_iso": "2026-01-23", "mandays_text": "2", "mandays_num": 2.0, "raw": "22-Jan-2026 <> 23-Jan-2026 ¦ 2 mandays", "valid": true, "bar_left_pct": 78.4314, "bar_width_pct": 1.9608, "bar_thickness_px": 8.7778, "bar_top_offset_px": 10.6111, "start_label": "22-Jan-2026", "end_label": "23-Jan-2026", "bar_label": "2 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 4 | OmniConnect | Real-time Tag Streaming | https://octopusdtlsupport.atlassian.net/browse/O2-793 | 2025-12-23 | 2026-02-06 | 2026-03-13 | Ashghal required attention, rolled back | 15 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 36.9863 | 20.5479 | 73.516 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2025-12-01 | 2026-02-10 | 72 | 1728 | Yes | [{"iso": "2025-12-01", "label": "01-Dec-2025", "left_pct": 0.0}, {"iso": "2025-12-08", "label": "08-Dec-2025", "left_pct": 9.8592}, {"iso": "2025-12-15", "label": "15-Dec-2025", "left_pct": 19.7183}, {"iso": "2025-12-22", "label": "22-Dec-2025", "left_pct": 29.5775}, {"iso": "2025-12-29", "label": "29-Dec-2025", "left_pct": 39.4366}, {"iso": "2026-01-05", "label": "05-Jan-2026", "left_pct": 49.2958}, {"iso": "2026-01-12", "label": "12-Jan-2026", "left_pct": 59.1549}, {"iso": "2026-01-19", "label": "19-Jan-2026", "left_pct": 69.0141}, {"iso": "2026-01-26", "label": "26-Jan-2026", "left_pct": 78.8732}, {"iso": "2026-02-02", "label": "02-Feb-2026", "left_pct": 88.7324}, {"iso": "2026-02-09", "label": "09-Feb-2026", "left_pct": 98.5915}] | No |  | {"Research/URS": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "2025-12-11", "end_iso": "2026-01-22", "mandays_text": "", "mandays_num": null, "raw": "11-Dec-2025 <> 22-Jan-2026 ¦ Not Planned mandays", "valid": true, "bar_left_pct": 14.0845, "bar_width_pct": 59.1549, "bar_thickness_px": 8.0, "bar_top_offset_px": 11.0, "start_label": "11-Dec-2025", "end_label": "22-Jan-2026", "bar_label": "-", "show_no_bar": false}, "DDS": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2025-12-23", "end_iso": "2026-01-31", "mandays_text": "15", "mandays_num": 15.0, "raw": "23-Dec-2025 <> 31-Jan-2026 ¦ 15 mandays", "valid": true, "bar_left_pct": 30.9859, "bar_width_pct": 54.9296, "bar_thickness_px": 13.8333, "bar_top_offset_px": 8.0833, "start_label": "23-Dec-2025", "end_label": "31-Jan-2026", "bar_label": "15 md", "show_no_bar": false}, "SQA": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "User Manual": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 5 | OmniConnect | Calculated Tag Enrich with no code (Nested Calculation) | https://octopusdtlsupport.atlassian.net/browse/O2-697 | 2026-01-28 | 2026-02-27 | 2026-02-19 |  | 55 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 53.4247 | 13.6986 | 63.4703 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2025-11-24 | 2026-02-09 | 78 | 1872 | Yes | [{"iso": "2025-11-24", "label": "24-Nov-2025", "left_pct": 0.0}, {"iso": "2025-12-01", "label": "01-Dec-2025", "left_pct": 9.0909}, {"iso": "2025-12-08", "label": "08-Dec-2025", "left_pct": 18.1818}, {"iso": "2025-12-15", "label": "15-Dec-2025", "left_pct": 27.2727}, {"iso": "2025-12-22", "label": "22-Dec-2025", "left_pct": 36.3636}, {"iso": "2025-12-29", "label": "29-Dec-2025", "left_pct": 45.4545}, {"iso": "2026-01-05", "label": "05-Jan-2026", "left_pct": 54.5455}, {"iso": "2026-01-12", "label": "12-Jan-2026", "left_pct": 63.6364}, {"iso": "2026-01-19", "label": "19-Jan-2026", "left_pct": 72.7273}, {"iso": "2026-01-26", "label": "26-Jan-2026", "left_pct": 81.8182}, {"iso": "2026-02-02", "label": "02-Feb-2026", "left_pct": 90.9091}, {"iso": "2026-02-09", "label": "09-Feb-2026", "left_pct": 100.0}] | No |  | {"Research/URS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2025-12-04", "end_iso": "2026-01-20", "mandays_text": "34", "mandays_num": 34.0, "raw": "4-Dec-2025 <> 20-Jan-2026 ¦ 34 mandays", "valid": true, "bar_left_pct": 12.987, "bar_width_pct": 61.039, "bar_thickness_px": 21.2222, "bar_top_offset_px": 4.3889, "start_label": "04-Dec-2025", "end_label": "20-Jan-2026", "bar_label": "34 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-21", "end_iso": "2026-01-30", "mandays_text": "16", "mandays_num": 16.0, "raw": "21-Jan-2026 <> 30-Jan-2026 ¦ 16 mandays", "valid": true, "bar_left_pct": 75.3247, "bar_width_pct": 11.6883, "bar_thickness_px": 14.2222, "bar_top_offset_px": 7.8889, "start_label": "21-Jan-2026", "end_label": "30-Jan-2026", "bar_label": "16 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-21", "end_iso": "2026-01-30", "mandays_text": "5", "mandays_num": 5.0, "raw": "21-Jan-2026 <> 30-Jan-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 75.3247, "bar_width_pct": 11.6883, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "21-Jan-2026", "end_label": "30-Jan-2026", "bar_label": "5 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 6 | OmniConnect | APX Performance Visualization Enhancements | https://octopusdtlsupport.atlassian.net/browse/O2-457 | 2026-01-26 | 2026-02-26 | 2026-03-03 |  | 45 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 52.5114 | 14.1553 | 68.9498 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2026-01-16 | 2026-03-13 | 57 | 1368 | Yes | [{"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 0.0}, {"iso": "2026-01-23", "label": "23-Jan-2026", "left_pct": 12.5}, {"iso": "2026-01-30", "label": "30-Jan-2026", "left_pct": 25.0}, {"iso": "2026-02-06", "label": "06-Feb-2026", "left_pct": 37.5}, {"iso": "2026-02-13", "label": "13-Feb-2026", "left_pct": 50.0}, {"iso": "2026-02-20", "label": "20-Feb-2026", "left_pct": 62.5}, {"iso": "2026-02-27", "label": "27-Feb-2026", "left_pct": 75.0}, {"iso": "2026-03-06", "label": "06-Mar-2026", "left_pct": 87.5}, {"iso": "2026-03-13", "label": "13-Mar-2026", "left_pct": 100.0}] | Yes | 82.1429 | {"Research/URS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-26", "end_iso": "2026-01-30", "mandays_text": "15", "mandays_num": 15.0, "raw": "26-Jan-2026 <> 30-Jan-2026 ¦ 15 mandays", "valid": true, "bar_left_pct": 17.8571, "bar_width_pct": 7.1429, "bar_thickness_px": 13.8333, "bar_top_offset_px": 8.0833, "start_label": "26-Jan-2026", "end_label": "30-Jan-2026", "bar_label": "15 md", "show_no_bar": false}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-02", "end_iso": "2026-02-23", "mandays_text": "15", "mandays_num": 15.0, "raw": "2-Feb-2026 <> 23-Feb-2026 ¦ 15 mandays", "valid": true, "bar_left_pct": 30.3571, "bar_width_pct": 37.5, "bar_thickness_px": 13.8333, "bar_top_offset_px": 8.0833, "start_label": "02-Feb-2026", "end_label": "23-Feb-2026", "bar_label": "15 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-24", "end_iso": "2026-03-03", "mandays_text": "10", "mandays_num": 10.0, "raw": "24-Feb-2026 <> 3-Mar-2026 ¦ 10 mandays", "valid": true, "bar_left_pct": 69.6429, "bar_width_pct": 12.5, "bar_thickness_px": 11.8889, "bar_top_offset_px": 9.0556, "start_label": "24-Feb-2026", "end_label": "03-Mar-2026", "bar_label": "10 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-24", "end_iso": "2026-03-03", "mandays_text": "5", "mandays_num": 5.0, "raw": "24-Feb-2026 <> 3-Mar-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 69.6429, "bar_width_pct": 12.5, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "24-Feb-2026", "end_label": "03-Mar-2026", "bar_label": "5 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 7 | OmniConnect | Subscription Management | https://octopusdtlsupport.atlassian.net/browse/O2-857 | 2026-01-07 | 2026-03-06 | 2026-03-06 |  | 81 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 43.8356 | 26.484 | 70.3196 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2025-12-28 | 2026-03-16 | 79 | 1896 | Yes | [{"iso": "2025-12-28", "label": "28-Dec-2025", "left_pct": 0.0}, {"iso": "2026-01-04", "label": "04-Jan-2026", "left_pct": 8.9744}, {"iso": "2026-01-11", "label": "11-Jan-2026", "left_pct": 17.9487}, {"iso": "2026-01-18", "label": "18-Jan-2026", "left_pct": 26.9231}, {"iso": "2026-01-25", "label": "25-Jan-2026", "left_pct": 35.8974}, {"iso": "2026-02-01", "label": "01-Feb-2026", "left_pct": 44.8718}, {"iso": "2026-02-08", "label": "08-Feb-2026", "left_pct": 53.8462}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 62.8205}, {"iso": "2026-02-22", "label": "22-Feb-2026", "left_pct": 71.7949}, {"iso": "2026-03-01", "label": "01-Mar-2026", "left_pct": 80.7692}, {"iso": "2026-03-08", "label": "08-Mar-2026", "left_pct": 89.7436}, {"iso": "2026-03-15", "label": "15-Mar-2026", "left_pct": 98.7179}] | Yes | 83.3333 | {"Research/URS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-07", "end_iso": "2026-01-08", "mandays_text": "4", "mandays_num": 4.0, "raw": "7-Jan-2026 <> 8-Jan-2026 ¦ 4 mandays", "valid": true, "bar_left_pct": 12.8205, "bar_width_pct": 1.2821, "bar_thickness_px": 9.5556, "bar_top_offset_px": 10.2222, "start_label": "07-Jan-2026", "end_label": "08-Jan-2026", "bar_label": "4 md", "show_no_bar": false}, "DDS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-08", "end_iso": "2026-01-08", "mandays_text": "1", "mandays_num": 1.0, "raw": "8-Jan-2026 <> 8-Jan-2026 ¦ 1 mandays", "valid": true, "bar_left_pct": 14.1026, "bar_width_pct": 0.8, "bar_thickness_px": 8.3889, "bar_top_offset_px": 10.8056, "start_label": "08-Jan-2026", "end_label": "08-Jan-2026", "bar_label": "1 md", "show_no_bar": false}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-02", "end_iso": "2026-02-20", "mandays_text": "36", "mandays_num": 36.0, "raw": "2-Feb-2026 <> 20-Feb-2026 ¦ 36 mandays", "valid": true, "bar_left_pct": 46.1538, "bar_width_pct": 23.0769, "bar_thickness_px": 22.0, "bar_top_offset_px": 4.0, "start_label": "02-Feb-2026", "end_label": "20-Feb-2026", "bar_label": "36 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-23", "end_iso": "2026-03-06", "mandays_text": "20", "mandays_num": 20.0, "raw": "23-Feb-2026 <> 6-Mar-2026 ¦ 20 mandays", "valid": true, "bar_left_pct": 73.0769, "bar_width_pct": 14.1026, "bar_thickness_px": 15.7778, "bar_top_offset_px": 7.1111, "start_label": "23-Feb-2026", "end_label": "06-Mar-2026", "bar_label": "20 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-23", "end_iso": "2026-03-06", "mandays_text": "20", "mandays_num": 20.0, "raw": "23-Feb-2026 <> 6-Mar-2026 ¦ 20 mandays", "valid": true, "bar_left_pct": 73.0769, "bar_width_pct": 14.1026, "bar_thickness_px": 15.7778, "bar_top_offset_px": 7.1111, "start_label": "23-Feb-2026", "end_label": "06-Mar-2026", "bar_label": "20 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 8 | Digital Log | Read API (Programmatic Data Access) | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-146 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  | 29 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 43.8356 | 20.0913 | 63.9269 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2026-01-18 | 2026-02-22 | 36 | 864 | Yes | [{"iso": "2026-01-18", "label": "18-Jan-2026", "left_pct": 0.0}, {"iso": "2026-01-25", "label": "25-Jan-2026", "left_pct": 20.0}, {"iso": "2026-02-01", "label": "01-Feb-2026", "left_pct": 40.0}, {"iso": "2026-02-08", "label": "08-Feb-2026", "left_pct": 60.0}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 80.0}, {"iso": "2026-02-22", "label": "22-Feb-2026", "left_pct": 100.0}] | No |  | {"Research/URS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-28", "end_iso": "2026-02-06", "mandays_text": "21", "mandays_num": 21.0, "raw": "28-Jan-2026 <> 6-Feb-2026 ¦ 21 mandays", "valid": true, "bar_left_pct": 28.5714, "bar_width_pct": 25.7143, "bar_thickness_px": 16.1667, "bar_top_offset_px": 6.9167, "start_label": "28-Jan-2026", "end_label": "06-Feb-2026", "bar_label": "21 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-09", "end_iso": "2026-02-12", "mandays_text": "4", "mandays_num": 4.0, "raw": "9-Feb-2026 <> 12-Feb-2026 ¦ 4 mandays", "valid": true, "bar_left_pct": 62.8571, "bar_width_pct": 8.5714, "bar_thickness_px": 9.5556, "bar_top_offset_px": 10.2222, "start_label": "09-Feb-2026", "end_label": "12-Feb-2026", "bar_label": "4 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-09", "end_iso": "2026-02-12", "mandays_text": "4", "mandays_num": 4.0, "raw": "9-Feb-2026 <> 12-Feb-2026 ¦ 4 mandays", "valid": true, "bar_left_pct": 62.8571, "bar_width_pct": 8.5714, "bar_thickness_px": 9.5556, "bar_top_offset_px": 10.2222, "start_label": "09-Feb-2026", "end_label": "12-Feb-2026", "bar_label": "4 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 9 | Digital Log | Digital Log - Journal Log (Web & Mobile) | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  | 40 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 43.8356 | 20.0913 | 63.9269 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2026-01-02 | 2026-02-13 | 43 | 1032 | Yes | [{"iso": "2026-01-02", "label": "02-Jan-2026", "left_pct": 0.0}, {"iso": "2026-01-09", "label": "09-Jan-2026", "left_pct": 16.6667}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 33.3333}, {"iso": "2026-01-23", "label": "23-Jan-2026", "left_pct": 50.0}, {"iso": "2026-01-30", "label": "30-Jan-2026", "left_pct": 66.6667}, {"iso": "2026-02-06", "label": "06-Feb-2026", "left_pct": 83.3333}, {"iso": "2026-02-13", "label": "13-Feb-2026", "left_pct": 100.0}] | No |  | {"Research/URS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-12", "end_iso": "2026-01-27", "mandays_text": "30", "mandays_num": 30.0, "raw": "12-Jan-2026 <> 27-Jan-2026 ¦ 30 mandays", "valid": true, "bar_left_pct": 23.8095, "bar_width_pct": 35.7143, "bar_thickness_px": 19.6667, "bar_top_offset_px": 5.1667, "start_label": "12-Jan-2026", "end_label": "27-Jan-2026", "bar_label": "30 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-28", "end_iso": "2026-02-03", "mandays_text": "5", "mandays_num": 5.0, "raw": "28-Jan-2026 <> 3-Feb-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 61.9048, "bar_width_pct": 14.2857, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "28-Jan-2026", "end_label": "03-Feb-2026", "bar_label": "5 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-28", "end_iso": "2026-02-03", "mandays_text": "5", "mandays_num": 5.0, "raw": "28-Jan-2026 <> 3-Feb-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 61.9048, "bar_width_pct": 14.2857, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "28-Jan-2026", "end_label": "03-Feb-2026", "bar_label": "5 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 10 | Digital Log | Digital Log - Domain Migration to Brand Octopus Digital | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  | 20 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 43.8356 | 20.0913 | 63.9269 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2026-01-30 | 2026-03-01 | 31 | 744 | Yes | [{"iso": "2026-01-30", "label": "30-Jan-2026", "left_pct": 0.0}, {"iso": "2026-02-06", "label": "06-Feb-2026", "left_pct": 23.3333}, {"iso": "2026-02-13", "label": "13-Feb-2026", "left_pct": 46.6667}, {"iso": "2026-02-20", "label": "20-Feb-2026", "left_pct": 70.0}, {"iso": "2026-02-27", "label": "27-Feb-2026", "left_pct": 93.3333}] | No |  | {"Research/URS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-09", "end_iso": "2026-02-12", "mandays_text": "12", "mandays_num": 12.0, "raw": "9-Feb-2026 <> 12-Feb-2026 ¦ 12 mandays", "valid": true, "bar_left_pct": 33.3333, "bar_width_pct": 10.0, "bar_thickness_px": 12.6667, "bar_top_offset_px": 8.6667, "start_label": "09-Feb-2026", "end_label": "12-Feb-2026", "bar_label": "12 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-13", "end_iso": "2026-02-19", "mandays_text": "4", "mandays_num": 4.0, "raw": "13-Feb-2026 <> 19-Feb-2026 ¦ 4 mandays", "valid": true, "bar_left_pct": 46.6667, "bar_width_pct": 20.0, "bar_thickness_px": 9.5556, "bar_top_offset_px": 10.2222, "start_label": "13-Feb-2026", "end_label": "19-Feb-2026", "bar_label": "4 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-13", "end_iso": "2026-02-19", "mandays_text": "4", "mandays_num": 4.0, "raw": "13-Feb-2026 <> 19-Feb-2026 ¦ 4 mandays", "valid": true, "bar_left_pct": 46.6667, "bar_width_pct": 20.0, "bar_thickness_px": 9.5556, "bar_top_offset_px": 10.2222, "start_label": "13-Feb-2026", "end_label": "19-Feb-2026", "bar_label": "4 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 11 | Digital Log | Log Chat Integration | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-192 | 2026-01-07 | 2026-02-20 | 2026-02-20 |  | 22 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 43.8356 | 20.0913 | 63.9269 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2025-12-28 | 2026-01-31 | 35 | 840 | Yes | [{"iso": "2025-12-28", "label": "28-Dec-2025", "left_pct": 0.0}, {"iso": "2026-01-04", "label": "04-Jan-2026", "left_pct": 20.5882}, {"iso": "2026-01-11", "label": "11-Jan-2026", "left_pct": 41.1765}, {"iso": "2026-01-18", "label": "18-Jan-2026", "left_pct": 61.7647}, {"iso": "2026-01-25", "label": "25-Jan-2026", "left_pct": 82.3529}] | No |  | {"Research/URS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-07", "end_iso": "2026-01-13", "mandays_text": "10", "mandays_num": 10.0, "raw": "7-Jan-2026 <> 13-Jan-2026 ¦ 10 mandays", "valid": true, "bar_left_pct": 29.4118, "bar_width_pct": 17.6471, "bar_thickness_px": 11.8889, "bar_top_offset_px": 9.0556, "start_label": "07-Jan-2026", "end_label": "13-Jan-2026", "bar_label": "10 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-14", "end_iso": "2026-01-21", "mandays_text": "6", "mandays_num": 6.0, "raw": "14-Jan-2026 <> 21-Jan-2026 ¦ 6 mandays", "valid": true, "bar_left_pct": 50.0, "bar_width_pct": 20.5882, "bar_thickness_px": 10.3333, "bar_top_offset_px": 9.8333, "start_label": "14-Jan-2026", "end_label": "21-Jan-2026", "bar_label": "6 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-14", "end_iso": "2026-01-21", "mandays_text": "6", "mandays_num": 6.0, "raw": "14-Jan-2026 <> 21-Jan-2026 ¦ 6 mandays", "valid": true, "bar_left_pct": 50.0, "bar_width_pct": 20.5882, "bar_thickness_px": 10.3333, "bar_top_offset_px": 9.8333, "start_label": "14-Jan-2026", "end_label": "21-Jan-2026", "bar_label": "6 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 12 | Fintech Fuel | Mobile Application | https://octopusdtlsupport.atlassian.net/browse/FF-119 | 2025-11-17 | 2026-02-12 | 2026-02-12 |  | 0 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 20.5479 | 39.726 | 60.274 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | No |  |  | 0 | 520 | No | [] | No |  | {"Research/URS": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "SQA": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "User Manual": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 13 | Fintech Fuel | Fintech Fuel Read API | https://octopusdtlsupport.atlassian.net/browse/FF-271 | 2026-01-12 | 2026-02-09 | 2026-02-09 |  | 23 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 46.1187 | 12.7854 | 58.9041 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2026-01-02 | 2026-02-19 | 49 | 1176 | Yes | [{"iso": "2026-01-02", "label": "02-Jan-2026", "left_pct": 0.0}, {"iso": "2026-01-09", "label": "09-Jan-2026", "left_pct": 14.5833}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 29.1667}, {"iso": "2026-01-23", "label": "23-Jan-2026", "left_pct": 43.75}, {"iso": "2026-01-30", "label": "30-Jan-2026", "left_pct": 58.3333}, {"iso": "2026-02-06", "label": "06-Feb-2026", "left_pct": 72.9167}, {"iso": "2026-02-13", "label": "13-Feb-2026", "left_pct": 87.5}] | No |  | {"Research/URS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-12", "end_iso": "2026-01-14", "mandays_text": "3", "mandays_num": 3.0, "raw": "12-Jan-2026 <> 14-Jan-2026 ¦ 3 mandays", "valid": true, "bar_left_pct": 20.8333, "bar_width_pct": 4.1667, "bar_thickness_px": 9.1667, "bar_top_offset_px": 10.4167, "start_label": "12-Jan-2026", "end_label": "14-Jan-2026", "bar_label": "3 md", "show_no_bar": false}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-28", "end_iso": "2026-02-03", "mandays_text": "10", "mandays_num": 10.0, "raw": "28-Jan-2026 <> 3-Feb-2026 ¦ 10 mandays", "valid": true, "bar_left_pct": 54.1667, "bar_width_pct": 12.5, "bar_thickness_px": 11.8889, "bar_top_offset_px": 9.0556, "start_label": "28-Jan-2026", "end_label": "03-Feb-2026", "bar_label": "10 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-04", "end_iso": "2026-02-09", "mandays_text": "5", "mandays_num": 5.0, "raw": "4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 68.75, "bar_width_pct": 10.4167, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "04-Feb-2026", "end_label": "09-Feb-2026", "bar_label": "5 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-04", "end_iso": "2026-02-09", "mandays_text": "5", "mandays_num": 5.0, "raw": "4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 68.75, "bar_width_pct": 10.4167, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "04-Feb-2026", "end_label": "09-Feb-2026", "bar_label": "5 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 14 | Fintech Fuel | Fintech Diagnostics Dashboard | https://octopusdtlsupport.atlassian.net/browse/FF-274 | 2026-01-28 | 2026-02-09 | 2026-02-09 |  | 20 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 53.4247 | 5.4795 | 58.9041 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2026-01-18 | 2026-02-19 | 33 | 792 | Yes | [{"iso": "2026-01-18", "label": "18-Jan-2026", "left_pct": 0.0}, {"iso": "2026-01-25", "label": "25-Jan-2026", "left_pct": 21.875}, {"iso": "2026-02-01", "label": "01-Feb-2026", "left_pct": 43.75}, {"iso": "2026-02-08", "label": "08-Feb-2026", "left_pct": 65.625}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 87.5}] | No |  | {"Research/URS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-28", "end_iso": "2026-02-03", "mandays_text": "10", "mandays_num": 10.0, "raw": "28-Jan-2026 <> 3-Feb-2026 ¦ 10 mandays", "valid": true, "bar_left_pct": 31.25, "bar_width_pct": 18.75, "bar_thickness_px": 11.8889, "bar_top_offset_px": 9.0556, "start_label": "28-Jan-2026", "end_label": "03-Feb-2026", "bar_label": "10 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-04", "end_iso": "2026-02-09", "mandays_text": "5", "mandays_num": 5.0, "raw": "4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 53.125, "bar_width_pct": 15.625, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "04-Feb-2026", "end_label": "09-Feb-2026", "bar_label": "5 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-04", "end_iso": "2026-02-09", "mandays_text": "5", "mandays_num": 5.0, "raw": "4-Feb-2026 <> 9-Feb-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 53.125, "bar_width_pct": 15.625, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "04-Feb-2026", "end_label": "09-Feb-2026", "bar_label": "5 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not Planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 15 | Fintech Fuel | ALSONs device integration (read only) | https://octopusdtlsupport.atlassian.net/browse/FF-292 |  |  |  |  | 0 | No | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 |  |  |  | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | No |  |  | 0 | 520 | No | [] | No |  | {"Research/URS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "SQA": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "User Manual": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Production": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 16 | Fintech Fuel | Automated Site Configuration | https://octopusdtlsupport.atlassian.net/browse/FF-297 |  |  |  |  | 0 | No | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 |  |  |  | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | No |  |  | 0 | 520 | No | [] | No |  | {"Research/URS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "SQA": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "User Manual": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Production": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 17 | Fintech Fuel | Fuel price write back | https://octopusdtlsupport.atlassian.net/browse/FF-302 |  |  |  |  | 0 | No | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 |  |  |  | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | No |  |  | 0 | 520 | No | [] | No |  | {"Research/URS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "SQA": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "User Manual": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Production": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 18 | OmniChat | OmniChat Known Bugs Fixing | https://octopusdtlsupport.atlassian.net/browse/MN-78 |  |  |  |  | 0 | No | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 |  |  |  | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | No |  |  | 0 | 520 | No | [] | No |  | {"Research/URS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "SQA": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "User Manual": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Production": {"state": "no_entry", "state_label": "no entry", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}
Latest - 25 Feb 2026 | 19 | OmniChat | Integration with OmniAgent | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | 2026-02-23 | 2026-03-26 | 2026-03-26 |  | 59 | Yes | 2025-10-03 | 2026-05-10 | 220 | Yes | 68.9498 | 65.2968 | 14.1553 | 79.4521 | [{"iso": "2025-10-03", "label": "03-Oct-2025", "left_pct": 0.0}, {"iso": "2025-10-18", "label": "18-Oct-2025", "left_pct": 6.8493}, {"iso": "2025-11-02", "label": "02-Nov-2025", "left_pct": 13.6986}, {"iso": "2025-11-17", "label": "17-Nov-2025", "left_pct": 20.5479}, {"iso": "2025-12-02", "label": "02-Dec-2025", "left_pct": 27.3973}, {"iso": "2025-12-17", "label": "17-Dec-2025", "left_pct": 34.2466}, {"iso": "2026-01-01", "label": "01-Jan-2026", "left_pct": 41.0959}, {"iso": "2026-01-16", "label": "16-Jan-2026", "left_pct": 47.9452}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 54.7945}, {"iso": "2026-02-15", "label": "15-Feb-2026", "left_pct": 61.6438}, {"iso": "2026-03-02", "label": "02-Mar-2026", "left_pct": 68.4932}, {"iso": "2026-03-17", "label": "17-Mar-2026", "left_pct": 75.3425}, {"iso": "2026-04-01", "label": "01-Apr-2026", "left_pct": 82.1918}, {"iso": "2026-04-16", "label": "16-Apr-2026", "left_pct": 89.0411}, {"iso": "2026-05-01", "label": "01-May-2026", "left_pct": 95.8904}] | Yes | 2026-02-13 | 2026-04-05 | 52 | 1248 | Yes | [{"iso": "2026-02-13", "label": "13-Feb-2026", "left_pct": 0.0}, {"iso": "2026-02-20", "label": "20-Feb-2026", "left_pct": 13.7255}, {"iso": "2026-02-27", "label": "27-Feb-2026", "left_pct": 27.451}, {"iso": "2026-03-06", "label": "06-Mar-2026", "left_pct": 41.1765}, {"iso": "2026-03-13", "label": "13-Mar-2026", "left_pct": 54.902}, {"iso": "2026-03-20", "label": "20-Mar-2026", "left_pct": 68.6275}, {"iso": "2026-03-27", "label": "27-Mar-2026", "left_pct": 82.3529}, {"iso": "2026-04-03", "label": "03-Apr-2026", "left_pct": 96.0784}] | Yes | 35.2941 | {"Research/URS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "DDS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-23", "end_iso": "2026-02-25", "mandays_text": "4", "mandays_num": 4.0, "raw": "23-Feb-2026 <> 25-Feb-2026 ¦ 4 mandays", "valid": true, "bar_left_pct": 19.6078, "bar_width_pct": 3.9216, "bar_thickness_px": 9.5556, "bar_top_offset_px": 10.2222, "start_label": "23-Feb-2026", "end_label": "25-Feb-2026", "bar_label": "4 md", "show_no_bar": false}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-02-26", "end_iso": "2026-03-16", "mandays_text": "33", "mandays_num": 33.0, "raw": "26-Feb-2026 <> 16-Mar-2026 ¦ 33 mandays", "valid": true, "bar_left_pct": 25.4902, "bar_width_pct": 35.2941, "bar_thickness_px": 20.8333, "bar_top_offset_px": 4.5833, "start_label": "26-Feb-2026", "end_label": "16-Mar-2026", "bar_label": "33 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-03-17", "end_iso": "2026-03-24", "mandays_text": "5", "mandays_num": 5.0, "raw": "17-Mar-2026 <> 24-Mar-2026 ¦ 5 mandays", "valid": true, "bar_left_pct": 62.7451, "bar_width_pct": 13.7255, "bar_thickness_px": 9.9444, "bar_top_offset_px": 10.0278, "start_label": "17-Mar-2026", "end_label": "24-Mar-2026", "bar_label": "5 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-03-17", "end_iso": "2026-03-24", "mandays_text": "3", "mandays_num": 3.0, "raw": "17-Mar-2026 <> 24-Mar-2026 ¦ 3 mandays", "valid": true, "bar_left_pct": 62.7451, "bar_width_pct": 13.7255, "bar_thickness_px": 9.1667, "bar_top_offset_px": 10.4167, "start_label": "17-Mar-2026", "end_label": "24-Mar-2026", "bar_label": "3 md", "show_no_bar": false}, "Production": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-03-25", "end_iso": "2026-03-26", "mandays_text": "14", "mandays_num": 14.0, "raw": "25-Mar-2026 <> 26-Mar-2026 ¦ 14 mandays", "valid": true, "bar_left_pct": 78.4314, "bar_width_pct": 1.9608, "bar_thickness_px": 13.4444, "bar_top_offset_px": 8.2778, "start_label": "25-Mar-2026", "end_label": "26-Mar-2026", "bar_label": "14 md", "show_no_bar": false}}

## Metadata
Generated At | 2026-03-03 14:14:08 UTC
Source Workbook | C:\Users\hmalik\OneDrive - Octopus Digital\ALL DOCS\IPP Meeting\all ipp meetings.xlsx
Source Sheet | Latest - 25 Feb 2026
Output Mode | timestamped
Data Row Count | 18
Phase Count | 6
Computed Sheet Name | IPP Dashboard Computed
Global Max Man-days Benchmark | 36
Computation Timestamp UTC | 2026-03-03 14:14:08 UTC
Computation Rules Version | v2