## IPP Phase Breakdown
Source Sheet | Row Number | Product | Epic/RMI | Epic/RMI Jira Link | Epic Planned Start Date | Epic Planned End Date | Epic Actual Date (Production Date) | Remarks | Research/URS Planned Start Date | Research/URS Planned End Date | Research/URS Planned Man-days | Research/URS Raw Planned Range | Research/URS Planning State | Research/URS Parse Warning | DDS Planned Start Date | DDS Planned End Date | DDS Planned Man-days | DDS Raw Planned Range | DDS Planning State | DDS Parse Warning | Development Planned Start Date | Development Planned End Date | Development Planned Man-days | Development Raw Planned Range | Development Planning State | Development Parse Warning | SQA Planned Start Date | SQA Planned End Date | SQA Planned Man-days | SQA Raw Planned Range | SQA Planning State | SQA Parse Warning | User Manual Planned Start Date | User Manual Planned End Date | User Manual Planned Man-days | User Manual Raw Planned Range | User Manual Planning State | User Manual Parse Warning | Production Planned Start Date | Production Planned End Date | Production Planned Man-days | Production Raw Planned Range | Production Planning State | Production Parse Warning | Any Phase Parse Warning | Any No Entry | Any Not Planned | Any Skipped | Computed Total Phase Man-days | Computed Has Valid Epic Plan | Computed Epic Planned Start ISO | Computed Epic Planned End ISO | Computed Epic Actual ISO
Latest - 17 Feb 2026 | 2 | OmniConnect | RMI-1 | https://octopusdtlsupport.atlassian.net/browse/ABC-123 | 2025-12-30 | 2026-01-26 | 2026-01-28 | Sample | 2025-12-30 | 2026-01-06 | 12 | 30-Dec-2025 <> 06-Jan-2026 ¦ 12 mandays | planned |  |  |  |  | Skipped | skipped |  | 2026-01-07 | 2026-01-16 | 24 | 07-Jan-2026 <> 16-Jan-2026 ¦ 24 mandays | planned |  | 2026-01-19 | 2026-01-26 | 18 | 19-Jan-2026 <> 26-Jan-2026 ¦ 18 mandays | planned |  | 2026-01-19 | 2026-01-26 | 6 | 19-Jan-2026 <> 26-Jan-2026 ¦ 6 mandays | planned |  |  |  |  | Not planned | not_planned |  | No | No | Yes | Yes | 60 | Yes | 2025-12-30 | 2026-01-26 | 2026-01-28

## IPP Dashboard Computed
Source Sheet | Row Number | Product | Epic/RMI | Epic/RMI Jira Link | Epic Planned Start Date | Epic Planned End Date | Epic Actual Date (Production Date) | Remarks | Computed Total Phase Man-days | Computed Roadmap Valid | Computed Roadmap Axis Start ISO | Computed Roadmap Axis End ISO | Computed Roadmap Axis Span Days | Computed Roadmap Today In Range | Computed Roadmap Today Left Pct | Computed Roadmap Bar Left Pct | Computed Roadmap Bar Width Pct | Computed Roadmap Actual Left Pct | Computed Roadmap Week Ticks JSON | Computed MiniGantt Has Dated Phases | Computed MiniGantt Axis Start ISO | Computed MiniGantt Axis End ISO | Computed MiniGantt Axis Span Days | Computed MiniGantt Timeline Width Px | Computed MiniGantt Scroll Enabled | Computed MiniGantt Week Ticks JSON | Computed MiniGantt Today In Range | Computed MiniGantt Today Left Pct | Computed Phase Geometry JSON
Latest - 17 Feb 2026 | 2 | OmniConnect | RMI-1 | https://octopusdtlsupport.atlassian.net/browse/ABC-123 | 2025-12-30 | 2026-01-26 | 2026-01-28 | Sample | 60 | Yes | 2025-12-20 | 2026-02-05 | 48 | No |  | 21.2766 | 57.4468 | 82.9787 | [{"iso": "2025-12-20", "label": "20-Dec-2025", "left_pct": 0.0}, {"iso": "2026-01-03", "label": "03-Jan-2026", "left_pct": 29.7872}, {"iso": "2026-01-17", "label": "17-Jan-2026", "left_pct": 59.5745}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 89.3617}] | Yes | 2025-12-20 | 2026-02-05 | 48 | 1152 | Yes | [{"iso": "2025-12-20", "label": "20-Dec-2025", "left_pct": 0.0}, {"iso": "2025-12-27", "label": "27-Dec-2025", "left_pct": 14.8936}, {"iso": "2026-01-03", "label": "03-Jan-2026", "left_pct": 29.7872}, {"iso": "2026-01-10", "label": "10-Jan-2026", "left_pct": 44.6809}, {"iso": "2026-01-17", "label": "17-Jan-2026", "left_pct": 59.5745}, {"iso": "2026-01-24", "label": "24-Jan-2026", "left_pct": 74.4681}, {"iso": "2026-01-31", "label": "31-Jan-2026", "left_pct": 89.3617}] | No |  | {"Research/URS": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2025-12-30", "end_iso": "2026-01-06", "mandays_text": "12", "mandays_num": 12.0, "raw": "30-Dec-2025 <> 06-Jan-2026 ¦ 12 mandays", "valid": true, "bar_left_pct": 21.2766, "bar_width_pct": 14.8936, "bar_thickness_px": 15.0, "bar_top_offset_px": 7.5, "start_label": "30-Dec-2025", "end_label": "06-Jan-2026", "bar_label": "12 md", "show_no_bar": false}, "DDS": {"state": "skipped", "state_label": "skipped", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Skipped", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}, "Development": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-07", "end_iso": "2026-01-16", "mandays_text": "24", "mandays_num": 24.0, "raw": "07-Jan-2026 <> 16-Jan-2026 ¦ 24 mandays", "valid": true, "bar_left_pct": 38.2979, "bar_width_pct": 19.1489, "bar_thickness_px": 22.0, "bar_top_offset_px": 4.0, "start_label": "07-Jan-2026", "end_label": "16-Jan-2026", "bar_label": "24 md", "show_no_bar": false}, "SQA": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-19", "end_iso": "2026-01-26", "mandays_text": "18", "mandays_num": 18.0, "raw": "19-Jan-2026 <> 26-Jan-2026 ¦ 18 mandays", "valid": true, "bar_left_pct": 63.8298, "bar_width_pct": 14.8936, "bar_thickness_px": 18.5, "bar_top_offset_px": 5.75, "start_label": "19-Jan-2026", "end_label": "26-Jan-2026", "bar_label": "18 md", "show_no_bar": false}, "User Manual": {"state": "planned", "state_label": "planned", "warning": "", "start_iso": "2026-01-19", "end_iso": "2026-01-26", "mandays_text": "6", "mandays_num": 6.0, "raw": "19-Jan-2026 <> 26-Jan-2026 ¦ 6 mandays", "valid": true, "bar_left_pct": 63.8298, "bar_width_pct": 14.8936, "bar_thickness_px": 11.5, "bar_top_offset_px": 9.25, "start_label": "19-Jan-2026", "end_label": "26-Jan-2026", "bar_label": "6 md", "show_no_bar": false}, "Production": {"state": "not_planned", "state_label": "not planned", "warning": "", "start_iso": "", "end_iso": "", "mandays_text": "", "mandays_num": null, "raw": "Not planned", "valid": false, "bar_left_pct": "", "bar_width_pct": "", "bar_thickness_px": "", "bar_top_offset_px": "", "start_label": "-", "end_label": "-", "bar_label": "-", "show_no_bar": true}}

## Metadata
Generated At | 2026-02-17 12:47:58 UTC
Source Workbook | E:\JIRA SCRIPT\temp_ipp_source.xlsx
Source Sheet | Latest - 17 Feb 2026
Output Mode | fixed
Data Row Count | 1
Phase Count | 6
Computed Sheet Name | IPP Dashboard Computed
Global Max Man-days Benchmark | 24
Computation Timestamp UTC | 2026-02-17 12:47:58 UTC
Computation Rules Version | v2