## Page1_Scorecard
page_name | from_date | to_date | capacity_hours | planned_hours | actual_hours | hours_required_to_complete_projects
Total work by projects | 2026-01-01 | 2026-02-28 | 0 | 10320.17 | 8008.8 | 2311.37

## Page1_ProjectCompare
project_key | planned_hours | actual_hours | hours_required_to_complete | benchmark_hours_due_date | project_due_date | completion_pct
O2 | 7208.17 | 5441.8 | 1766.37 | 7208.17 | 2026-01-23 | 75.49
FF | 1744 | 1011 | 733 | 1744 | 2026-02-12 | 57.97
DIGITALLOG | 928 | 1441 | -513 | 928 | 2026-02-20 | 155.28
MN | 440 | 112 | 328 | 440 | 2026-01-30 | 25.45
ODL | 0 | 3 | -3 | 0 |  | 0