## Latest - 30 Jan 2026
Product | Epic/RMI | Jira Task ID | Planned Date | Actual Date (Production Date) | Sprint | Work Status | RMI-on-track-or-not Status
OmniConnect | Ashghal Deployment | https://octopusdtlsupport.atlassian.net/browse/O2-941 | 19-Jan-2026 - 27-Jan-2026 | 2026-01-27 | Sprint 7 → Rel. 3.27.0 | Done | Yes
OmniConnect | Batch/Bpm modify Existing ADX IT Table | https://octopusdtlsupport.atlassian.net/browse/O2-810 | 30-Dec-2025 - 6-Feb-2026 | 2026-02-06 | Sprint 10 → Rel. 3.28.0 | In progress | Yes
OmniConnect | APX Pump – Variable Speed Dashboard | https://octopusdtlsupport.atlassian.net/browse/O2-887 | 23-Dec-2025 - 6-Feb-2026 | 2026-02-06 | Sprint 10 → Rel. 3.28.0 | In progress | Yes
OmniConnect | Real-time Tag Streaming | https://octopusdtlsupport.atlassian.net/browse/O2-793 | 23-Dec-2025 - 6-Feb-2026 | 2026-02-06 | Sprint 10 → Rel. 3.28.0 | In progress | Yes
OmniConnect | Calculated Tag Enrich with no code (Nested Calculation) | https://octopusdtlsupport.atlassian.net/browse/O2-697 | 28-Jan-2026 - 27-Feb-2026 | 2026-02-27 | Sprint 11 → Rel. 3.29.0 | On Hold | Yes
OmniConnect | APX Performance Visualization Enhancements (Compressor, Heat Exchanger, Condenser, Cooling Tower, Boiler) | https://octopusdtlsupport.atlassian.net/browse/O2-457 | 26-Jan-2026 - 26-Feb-2026 | 2026-03-03 | Sprint 12 → Rel. 3.3.0 | On Hold | No
OmniConnect | Subscription Management | https://octopusdtlsupport.atlassian.net/browse/O2-857 | 7-Jan-2026 - 6-Mar-2026 | 2026-03-06 | Sprint 13 → Rel. 1.0.0 | In progress | No
Digital Log | Read API (Programmatic Data Access) | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | 7-Jan-2026 - 20-Feb-2026 | 2026-02-20 | Sprint 4→ Rel. 9.3.0 | In progress | Yes
Digital Log | Digital Log - Journal Log (Web & Mobile) | https://octopusdtlsupport.atlassian.net/jira/software/c/projects/DIGITALLOG/boards/332/timeline?selectedIssue=DIGITALLOG-69 | 7-Jan-2026 - 20-Feb-2026 | 2026-02-20 | Sprint 4→ Rel. 9.3.0 | In progress | Yes
Digital Log | Digital Log - Domain Migration to Brand Octopus Digital | https://octopusdtlsupport.atlassian.net/jira/software/c/projects/DIGITALLOG/boards/332/timeline?selectedIssue=DIGITALLOG-70 | 7-Jan-2026 - 20-Feb-2026 | 2026-02-20 | Sprint 4→ Rel. 9.3.0 | Not started | Yes
Digital Log | Log Chat Integration | https://octopusdtlsupport.atlassian.net/jira/software/c/projects/DIGITALLOG/boards/332/timeline?selectedIssue=DIGITALLOG-66 | 7-Jan-2026 - 20-Feb-2026 | 2026-02-20 | Sprint 4→ Re.l 9.3.0 | In progress | Yes
Fintech Fuel | Mobile Application | https://octopusdtlsupport.atlassian.net/browse/FF-119 | 17-Nov-2025 - 12-Feb-2026 | 2026-02-12 | Sprint 4→ Rel. FF-Mob 1.0.0 | In progress | Yes
Fintech Fuel | Fintech Fuel Read API |  | 12-Jan-2026 - 9-Feb-2026 | 2026-02-09 | Sprint 5→ Rel. 1.1.0 |  | Yes
Fintech Fuel | Fintech Diagnostics Dashboard |  | 28-Jan-2026 - 9-Feb-2026 | 2026-02-09 | Sprint 5→ Rel. 1.2.0 |  | Yes
Fintech Fuel | ALSONs device integration (read only) |  | 9-Feb-2026 - 6-Mar-2026 | 2026-03-06 | Sprint 6→ Rel. 1.3.0 |  | Yes
Fintech Fuel | Automated Site Configuration
Fintech Fuel | Fuel price write back