## Latest - 17 Feb 2026
Product | Epic/RMI | Jira Task ID | Planned Start Date | Planned End Date | Actual Date (Production Date) | Remarks | Research/URS - Planned Range | DDS - Planned Range | Development - Planned Range | SQA - Planned Range | User Manual - Planned Range | Production - Planned Range
OmniConnect | RMI-1 | ABC-123 | 2025-12-30 | 2026-01-26 | 2026-01-28 | Sample | 30-Dec-2025 <> 06-Jan-2026 ¦ 12 mandays | Skipped | 07-Jan-2026 <> 16-Jan-2026 ¦ 24 mandays | 19-Jan-2026 <> 26-Jan-2026 ¦ 18 mandays | 19-Jan-2026 <> 26-Jan-2026 ¦ 6 mandays | Not planned