## Page1_Scorecard
page_name | from_date | to_date | capacity_hours | planned_hours | actual_hours | hours_required_to_complete_projects
Total work by projects | 2026-05-01 | 2026-06-23 | 0 | 10776 | 8661.23 | 2114.77

## Page1_ProjectCompare
project_key | planned_hours | actual_hours | hours_required_to_complete | benchmark_hours_due_date | project_due_date | completion_pct
O2 | 4958.4 | 5663.13 | -704.73 | 4958.4 | 2026-05-04 | 114.21
FF | 3688 | 1055.5 | 2632.5 | 3688 | 2026-02-18 | 28.62
DIGITALLOG | 1297.6 | 1730 | -432.4 | 1297.6 | 2026-05-08 | 133.32
MN | 832 | 152 | 680 | 832 | 2026-05-01 | 18.27
WOM | 0 | 0 | 0 | 0 |  | 0
SUBS | 0 | 0 | 0 | 0 |  | 0
ODL | 0 | 36.6 | -36.6 | 0 | 2026-05-31 | 0
OAM | 0 | 24 | -24 | 0 |  | 0
CRM | 0 | 0 | 0 | 0 |  | 0