## WorkItems
project_key | issue_key | work_item_id | work_item_type | jira_issue_type | fix_type | summary | status | start_date | end_date | actual_start_date | actual_end_date | original_estimate | original_estimate_hours | assignee | total_hours_logged | priority | parent_issue_key | parent_work_item_id | parent_jira_url | jira_url | Latest IPP Meeting | Jira IPP RMI Dates Altered | IPP Actual Date (Production Date) | IPP Remarks | IPP Actual Date Matches Jira End Date | created | updated
CRM | CRM-185 | CRM-185 | Story | Story |  | CRM Handover | Resolved! | 2026-01-26 | 2026-01-29 | 2026-01-26 | 2026-01-29 | 0 | 0 | Muhammad Imran Aslam | 32 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/CRM-185 | [5 empty] | 2026-01-21T12:21:43.209+0500 | 2026-01-29T11:42:27.060+0500
CRM | CRM-186 | CRM-186 | Epic | Epic |  | CRM Configuration Maintenance 2026 | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 192 | 192 | Muhammad Imran Aslam | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/CRM-186 | [5 empty] | 2026-02-03T15:04:53.196+0500 | 2026-03-05T09:51:19.566+0500
CRM | CRM-187 | CRM-187 | Story | Story |  | CRM Configuration | Considered in Roadmap & Queued | 2026-02-02 | 2026-05-31 |  |  | 96 | 96 | Muhammad Imran Aslam | 67.5 |  | CRM-186 | CRM-186 | https://octopusdtlsupport.atlassian.net/browse/CRM-186 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | [5 empty] | 2026-02-03T15:05:18.429+0500 | 2026-04-23T11:54:57.346+0500
CRM | CRM-188 | CRM-188 | Sub-task | Sub-task |  | CRM Handover February 2026 | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Muhammad Imran Aslam | 8 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-188 | [5 empty] | 2026-02-03T15:10:14.357+0500 | 2026-02-23T13:51:50.844+0500
CRM | CRM-189 | CRM-189 | Sub-task | Sub-task |  | CRM Handover February 2026 | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-189 | [5 empty] | 2026-02-03T15:14:39.110+0500 | 2026-02-25T14:52:39.351+0500
CRM | CRM-190 | CRM-190 | Sub-task | Sub-task |  | CRM Handover March 2026 | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-190 | [5 empty] | 2026-02-09T12:12:13.168+0500 | 2026-03-11T12:50:37.981+0500
CRM | CRM-191 | CRM-191 | Sub-task | Sub-task |  | CRM Handover March 2026 | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8 | 8 | Muhammad Imran Aslam | 8 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-191 | [5 empty] | 2026-02-09T12:14:10.124+0500 | 2026-03-26T14:19:04.726+0500
CRM | CRM-192 | CRM-192 | Sub-task | Sub-task |  | CRM Handover February 2026 | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-192 | [5 empty] | 2026-02-19T10:28:28.935+0500 | 2026-02-24T13:19:12.670+0500
CRM | CRM-193 | CRM-193 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing April 2026 | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Muhammad Imran Aslam | 8 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-193 | [5 empty] | 2026-03-30T12:21:30.104+0500 | 2026-04-01T12:36:06.790+0500
CRM | CRM-194 | CRM-194 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing April 2026 | Resolved! | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8 | 8 | Muhammad Imran Aslam | 8 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-194 | [5 empty] | 2026-03-31T12:36:09.198+0500 | 2026-04-13T14:32:40.549+0500
CRM | CRM-195 | CRM-195 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing May 2026 | Resolved! | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 8 | 8 | Muhammad Imran Aslam | 8 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-195 | [5 empty] | 2026-03-31T14:36:08.425+0500 | 2026-05-06T12:23:03.565+0500
CRM | CRM-196 | CRM-196 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing April 2026 | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 8 | 8 | Muhammad Imran Aslam | 8 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-196 | [5 empty] | 2026-03-31T14:51:12.605+0500 | 2026-04-27T12:31:33.076+0500
CRM | CRM-197 | CRM-197 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-08 | 2026-05-08 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-197 | [5 empty] | 2026-04-20T11:36:47.837+0500 | 2026-05-05T14:17:46.285+0500
CRM | CRM-198 | CRM-198 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-13 | 2026-05-13 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-198 | [5 empty] | 2026-04-23T11:37:37.589+0500 | 2026-04-23T11:38:20.424+0500
CRM | CRM-199 | CRM-199 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-25 | 2026-05-26 |  |  | 16 | 16 | Muhammad Imran Aslam | 0 |  | CRM-187 | CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-187 | https://octopusdtlsupport.atlassian.net/browse/CRM-199 | [5 empty] | 2026-04-23T11:52:56.785+0500 | 2026-04-23T11:53:56.472+0500
DIGITALLOG | DIGITALLOG-1 | DIGITALLOG-1 | Epic | Epic |  | Holidays Feature / Mobile App SSO Integration | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 260 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-1 | [5 empty] | 2025-10-03T19:45:32.831+0500 | 2026-02-26T14:59:01.346+0500
DIGITALLOG | DIGITALLOG-10 | DIGITALLOG-10 | Bug Subtask | Bug Subtask |  | Able to change status of holiday toggle in checklist builder while respective checklist is active. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.25 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-10 | [5 empty] | 2025-10-07T14:21:31.381+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-100 | DIGITALLOG-100 | Sub-task | Sub-task |  | Get hierarchy nodes with their associated tags. - AZ | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-100 | [5 empty] | 2026-01-22T10:21:36.165+0500 | 2026-02-10T11:33:14.925+0500
DIGITALLOG | DIGITALLOG-102 | DIGITALLOG-102 | Sub-task | Sub-task |  | Get tag data for multiple tags within a date range - AZ | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-102 | [5 empty] | 2026-01-22T10:22:07.742+0500 | 2026-01-23T10:03:29.586+0500
DIGITALLOG | DIGITALLOG-103 | DIGITALLOG-103 | Sub-task | Sub-task |  | UI Wrapper - Get tag data for multiple tags within a date range - MA | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-103 | [5 empty] | 2026-01-22T10:22:19.661+0500 | 2026-01-23T08:35:56.105+0500
DIGITALLOG | DIGITALLOG-104 | DIGITALLOG-104 | Sub-task | Sub-task |  | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 1 - AZ | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 6 | 6 | Arsalan Zafar Khan | 6 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-104 | [5 empty] | 2026-01-22T10:25:03.402+0500 | 2026-02-10T11:29:48.514+0500
DIGITALLOG | DIGITALLOG-105 | DIGITALLOG-105 | Sub-task | Sub-task |  | Get tag data for multiple tags within a date range - NA | Resolved! |  |  |  |  | 8 | 8 | nadeem ahmed | 0 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-105 | [5 empty] | 2026-01-22T10:27:58.255+0500 | 2026-02-10T12:04:30.890+0500
DIGITALLOG | DIGITALLOG-106 | DIGITALLOG-106 | Sub-task | Sub-task |  | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 2 - AZ | Resolved! | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-106 | [5 empty] | 2026-01-22T10:41:25.085+0500 | 2026-01-22T10:44:19.107+0500
DIGITALLOG | DIGITALLOG-107 | DIGITALLOG-107 | Sub-task | Sub-task |  | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application 3 - AZ | Resolved! | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-107 | [5 empty] | 2026-01-22T10:41:33.469+0500 | 2026-01-22T10:45:02.992+0500
DIGITALLOG | DIGITALLOG-108 | DIGITALLOG-108 | Sub-task | Sub-task |  | Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - AZ | Resolved! | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-108 | [5 empty] | 2026-01-23T10:13:35.223+0500 | 2026-02-10T11:26:12.846+0500
DIGITALLOG | DIGITALLOG-109 | DIGITALLOG-109 | Story | Story |  | URS | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 0 |  | DIGITALLOG-65 | DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-109 | [5 empty] | 2026-01-27T14:28:31.897+0500 | 2026-02-03T09:30:28.400+0500
DIGITALLOG | DIGITALLOG-11 | DIGITALLOG-11 | Bug Subtask | Bug Subtask |  | No character limit is applied on name field of custom weekend in holidays. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.25 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-11 | [5 empty] | 2025-10-07T14:35:50.225+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-110 | DIGITALLOG-110 | Story | Story |  | DDS | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | DIGITALLOG-65 | DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-110 | [5 empty] | 2026-01-27T14:29:24.215+0500 | 2026-01-27T14:29:31.048+0500
DIGITALLOG | DIGITALLOG-111 | DIGITALLOG-111 | Sub-task | Sub-task |  | URS and DDS Formatting for Digital Log Read API | Resolved! |  |  | 2026-01-27 | 2026-01-27 | 0 | 0 | Hassan Malik | 8 |  | DIGITALLOG-72 | DIGITALLOG-72 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-72 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-111 | [5 empty] | 2026-01-27T14:42:36.292+0500 | 2026-02-11T09:38:35.769+0500
DIGITALLOG | DIGITALLOG-113 | DIGITALLOG-113 | Story | Story |  | DEV: Log Chat Development | Resolved! | 2026-01-07 | 2026-02-20 |  |  | 256 | 256 | Muhammad Zeeshan Aslam | 201 |  | DIGITALLOG-65 | DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | [5 empty] | 2026-01-28T12:07:00.363+0500 | 2026-02-18T09:35:42.447+0500
DIGITALLOG | DIGITALLOG-114 | DIGITALLOG-114 | Sub-task | Sub-task |  | SQL Database Development for Log Chat | Resolved! | 2026-01-07 | 2026-01-09 | 2026-01-07 | 2026-01-09 | 24 | 24 | Muhammad Zeeshan Aslam | 40 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-114 | [5 empty] | 2026-01-28T12:22:48.506+0500 | 2026-03-04T10:41:15.696+0500
DIGITALLOG | DIGITALLOG-115 | DIGITALLOG-115 | Sub-task | Sub-task |  | Creating API for fetching all chats for each thread | Resolved! | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 16 | 16 | Muhammad Zeeshan Aslam | 16 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-115 | [5 empty] | 2026-01-28T12:24:26.424+0500 | 2026-03-04T10:42:51.410+0500
DIGITALLOG | DIGITALLOG-116 | DIGITALLOG-116 | Sub-task | Sub-task |  | Creating API for fetching all threads of the specific user | Resolved! | 2026-01-13 | 2026-01-15 | 2026-01-13 | 2026-01-15 | 16 | 16 | Muhammad Zeeshan Aslam | 12 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-116 | [5 empty] | 2026-01-28T12:25:05.380+0500 | 2026-03-04T10:43:52.335+0500
DIGITALLOG | DIGITALLOG-117 | DIGITALLOG-117 | Sub-task | Sub-task |  | Creating API for Deleting chat thread | Resolved! | 2026-03-13 | 2026-03-13 | 2026-01-13 | 2026-01-13 | 4 | 4 | Muhammad Zeeshan Aslam | 4 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-117 | [5 empty] | 2026-01-28T12:25:37.624+0500 | 2026-03-04T10:44:34.283+0500
DIGITALLOG | DIGITALLOG-118 | DIGITALLOG-118 | Sub-task | Sub-task |  | adjusting timestamps in LLM tools to UTC time according to organization timezone dynamically from DB | Resolved! | 2026-01-14 | 2026-01-16 | 2026-01-14 | 2026-01-16 | 32 | 32 | Muhammad Zeeshan Aslam | 32 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-118 | [5 empty] | 2026-01-28T12:30:16.825+0500 | 2026-03-04T10:46:01.822+0500
DIGITALLOG | DIGITALLOG-119 | DIGITALLOG-119 | Sub-task | Sub-task |  | SQA-Log Chat | Resolved! | 2026-01-22 | 2026-02-19 | 2026-01-29 | 2026-02-12 | 24 | 24 | Zeeshan Sarwar | 24 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-119 | [5 empty] | 2026-01-28T13:07:15.527+0500 | 2026-03-02T17:29:28.011+0500
DIGITALLOG | DIGITALLOG-12 | DIGITALLOG-12 | Bug Subtask | Bug Subtask |  | Unable to save changes in organization holidays. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1.5 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-12 | [5 empty] | 2025-10-07T14:47:29.987+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-120 | DIGITALLOG-120 | Sub-task | Sub-task |  | SQA-Read API | Resolved! | 2026-01-22 | 2026-01-30 | 2026-01-28 | 2026-01-30 | 16 | 16 | Zeeshan Sarwar | 16 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-120 | [5 empty] | 2026-01-28T13:07:30.783+0500 | 2026-03-10T10:34:45.858+0500
DIGITALLOG | DIGITALLOG-121 | DIGITALLOG-121 | Sub-task | Sub-task |  | Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - AZ | Resolved! | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-121 | [5 empty] | 2026-01-28T16:24:26.557+0500 | 2026-02-10T11:26:33.589+0500
DIGITALLOG | DIGITALLOG-122 | DIGITALLOG-122 | Sub-task | Sub-task |  | Implement JPA entities for all journal-related tables following existing standards. - AZ | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-122 | [5 empty] | 2026-01-28T16:25:36.735+0500 | 2026-01-29T15:21:44.666+0500
DIGITALLOG | DIGITALLOG-123 | DIGITALLOG-123 | Bug Subtask | Bug Subtask |  | Wrong organization is displaying against my user ID and due to this issue all data is wrong. | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-123 | [5 empty] | 2026-01-29T09:57:38.567+0500 | 2026-02-20T10:33:29.257+0500
DIGITALLOG | DIGITALLOG-124 | DIGITALLOG-124 | Sub-task | Sub-task |  | Requirements analysis, UX flow finalization, and R&D for Journal module - MA | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-124 | [5 empty] | 2026-01-29T10:49:26.172+0500 | 2026-02-10T10:50:10.269+0500
DIGITALLOG | DIGITALLOG-125 | DIGITALLOG-125 | Sub-task | Sub-task |  | Design Journal Template UI - MA | Resolved! | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-125 | [5 empty] | 2026-01-29T10:52:54.955+0500 | 2026-02-10T10:50:22.620+0500
DIGITALLOG | DIGITALLOG-126 | DIGITALLOG-126 | Sub-task | Sub-task |  | Integrate Journal Template backend APIs and implement dynamic template persistence - MA | Resolved! | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-126 | [5 empty] | 2026-01-29T10:53:21.258+0500 | 2026-02-10T10:51:48.002+0500
DIGITALLOG | DIGITALLOG-127 | DIGITALLOG-127 | Sub-task | Sub-task |  | Develop Journal Builder CRUD UI using templates - MA | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-127 | [5 empty] | 2026-01-29T10:54:00.551+0500 | 2026-02-10T10:54:15.891+0500
DIGITALLOG | DIGITALLOG-128 | DIGITALLOG-128 | Sub-task | Sub-task |  | Integrate Journal Builder APIs and implement user/group assignment workflows - MA | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-128 | [5 empty] | 2026-01-29T10:54:43.721+0500 | 2026-02-10T10:55:25.284+0500
DIGITALLOG | DIGITALLOG-129 | DIGITALLOG-129 | Sub-task | Sub-task |  | Build Journal Collector – Assigned Journals listing and data-fetch APIs - MA | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-129 | [5 empty] | 2026-01-29T10:55:21.718+0500 | 2026-02-10T10:57:33.529+0500
DIGITALLOG | DIGITALLOG-13 | DIGITALLOG-13 | Bug Subtask | Bug Subtask |  | Unable to select only Sundays after selecting weekends in organization holidays. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-13 | [5 empty] | 2025-10-08T11:07:42.159+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-130 | DIGITALLOG-130 | Sub-task | Sub-task |  | Implement journal submission UI with validation and submit APIs (Web) - MA | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-130 | [5 empty] | 2026-01-29T10:55:49.114+0500 | 2026-03-05T09:37:08.957+0500
DIGITALLOG | DIGITALLOG-131 | DIGITALLOG-131 | Sub-task | Sub-task |  | Develop Review Journals UI and integrate journal detail & comment APIs - MA | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-06 | 16 | 16 | Muhammad Abdullah | 16 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-131 | [5 empty] | 2026-01-29T10:56:12.547+0500 | 2026-03-05T09:38:07.431+0500
DIGITALLOG | DIGITALLOG-134 | DIGITALLOG-134 | Sub-task | Sub-task |  | Create repository interfaces and required queries for journals, entries, and filtering. - AZ | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-134 | [5 empty] | 2026-01-29T15:22:52.814+0500 | 2026-02-03T16:37:52.159+0500
DIGITALLOG | DIGITALLOG-135 | DIGITALLOG-135 | Bug Subtask | Bug Subtask |  | Read API is displaying other organization checklist data which is not present in my organization. | Resolved |  |  | 2026-02-18 | 2026-02-18 | 0 | 0 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-135 | [5 empty] | 2026-01-30T10:45:03.437+0500 | 2026-02-20T10:33:45.651+0500
DIGITALLOG | DIGITALLOG-136 | DIGITALLOG-136 | Sub-task | Sub-task |  | Integerating confluence documentation in log chat | Resolved! | 2026-01-28 | 2026-02-03 | 2026-01-28 | 2026-02-03 | 32 | 32 | Muhammad Zeeshan Aslam | 32 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-136 | [5 empty] | 2026-01-30T12:20:26.844+0500 | 2026-03-04T10:13:53.130+0500
DIGITALLOG | DIGITALLOG-137 | DIGITALLOG-137 | Sub-task | Sub-task |  | updating SQL and code for multi tenant database configuration | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-137 | [5 empty] | 2026-01-30T12:21:33.142+0500 | 2026-03-04T10:47:24.243+0500
DIGITALLOG | DIGITALLOG-138 | DIGITALLOG-138 | Bug Subtask | Bug Subtask |  | Displaying data is not user friendly. It is displaying with programming language. | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-138 | [5 empty] | 2026-02-02T09:54:17.270+0500 | 2026-02-20T10:34:02.222+0500
DIGITALLOG | DIGITALLOG-139 | DIGITALLOG-139 | Sub-task | Sub-task |  | Implement backend logic and APIs to manage template fields. - AZ | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-139 | [5 empty] | 2026-02-03T16:38:43.858+0500 | 2026-02-03T16:39:47.973+0500
DIGITALLOG | DIGITALLOG-14 | DIGITALLOG-14 | Bug Subtask | Bug Subtask |  | Able to enter and set holidays in previous months by manually entering start date in custom weekend selection. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-14 | [5 empty] | 2025-10-08T11:11:24.804+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-140 | DIGITALLOG-140 | Sub-task | Sub-task |  | Implement journal creation and enforce group-based access and visibility rules. - AZ | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-140 | [5 empty] | 2026-02-03T16:41:16.379+0500 | 2026-02-03T16:44:05.686+0500
DIGITALLOG | DIGITALLOG-141 | DIGITALLOG-141 | Sub-task | Sub-task |  | Develop services and APIs for submitting journal entries with dynamic field data. - AZ | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-141 | [5 empty] | 2026-02-03T16:44:44.100+0500 | 2026-02-03T16:45:34.210+0500
DIGITALLOG | DIGITALLOG-142 | DIGITALLOG-142 | Sub-task | Sub-task |  | Need to remove Template column when asking about all assets and locations in an organization. | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4 | 4 | Muhammad Zeeshan Aslam | 4 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-142 | [5 empty] | 2026-02-04T14:43:18.099+0500 | 2026-03-11T16:27:29.931+0500
DIGITALLOG | DIGITALLOG-143 | DIGITALLOG-143 | Bug Subtask | Bug Subtask |  | Wrong list of templates are displaying in log chat. | Resolved | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4 | 4 | Muhammad Zeeshan Aslam | 4 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-143 | [5 empty] | 2026-02-04T14:47:42.145+0500 | 2026-03-11T16:28:00.084+0500
DIGITALLOG | DIGITALLOG-144 | DIGITALLOG-144 | Sub-task | Sub-task |  | Implement multi-user remarks and commenting support for journal entries. | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-144 | [5 empty] | 2026-02-04T16:44:22.400+0500 | 2026-02-10T11:35:06.254+0500
DIGITALLOG | DIGITALLOG-146 | DIGITALLOG-146 | Epic | Epic |  | Digital Log Read API | Resolved! | 2026-01-07 | 2026-02-20 |  |  | 168 | 168 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-146 | [5 empty] | 2026-02-10T09:26:13.462+0500 | 2026-02-26T10:54:58.311+0500
DIGITALLOG | DIGITALLOG-147 | DIGITALLOG-147 | Story | Story |  | SQA | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | DIGITALLOG-146 | DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-147 | [5 empty] | 2026-02-10T09:27:39.818+0500 | 2026-02-13T13:39:29.841+0500
DIGITALLOG | DIGITALLOG-148 | DIGITALLOG-148 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | DIGITALLOG-146 | DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-148 | [5 empty] | 2026-02-10T09:29:44.935+0500 | 2026-02-12T11:06:11.304+0500
DIGITALLOG | DIGITALLOG-149 | DIGITALLOG-149 | Story | Story |  | Production Release | Resolved! | 2026-02-20 | 2026-02-20 |  |  | 24 | 24 | Arsalan Zafar Khan | 14 |  | DIGITALLOG-146 | DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-149 | [5 empty] | 2026-02-10T09:30:01.080+0500 | 2026-02-24T12:06:52.149+0500
DIGITALLOG | DIGITALLOG-15 | DIGITALLOG-15 | Bug Subtask | Bug Subtask |  | Able to select previous date by manually entering after click on any specific date slot. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.17 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-15 | [5 empty] | 2025-10-08T11:33:11.350+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-150 | DIGITALLOG-150 | Epic | Epic |  | Digital Log Journal Operator | Resolved! | 2026-01-07 | 2026-02-20 |  |  | 240 | 240 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | [5 empty] | 2026-02-10T09:30:36.301+0500 | 2026-02-26T10:56:11.970+0500
DIGITALLOG | DIGITALLOG-151 | DIGITALLOG-151 | Story | Story |  | SQA | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | DIGITALLOG-150 | DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-151 | [5 empty] | 2026-02-10T09:31:10.203+0500 | 2026-02-26T11:06:20.247+0500
DIGITALLOG | DIGITALLOG-152 | DIGITALLOG-152 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | DIGITALLOG-150 | DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-152 | [5 empty] | 2026-02-10T09:31:44.119+0500 | 2026-02-12T11:14:02.813+0500
DIGITALLOG | DIGITALLOG-153 | DIGITALLOG-153 | Story | Story |  | Production Release | Resolved! | 2026-02-20 | 2026-02-20 |  |  | 24 | 24 | Arsalan Zafar Khan | 6 |  | DIGITALLOG-150 | DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-153 | [5 empty] | 2026-02-10T09:32:07.036+0500 | 2026-02-24T12:06:41.084+0500
DIGITALLOG | DIGITALLOG-154 | DIGITALLOG-154 | Epic | Epic |  | Domain Migration to Branded Domain of ODL | On Hold | 2026-01-07 | 2026-02-20 |  |  | 96 | 96 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-154 | [5 empty] | 2026-02-10T09:33:04.323+0500 | 2026-02-20T12:30:47.404+0500
DIGITALLOG | DIGITALLOG-155 | DIGITALLOG-155 | Story | Story |  | SQA | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | DIGITALLOG-154 | DIGITALLOG-154 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-154 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-155 | [5 empty] | 2026-02-10T09:34:15.382+0500 | 2026-02-13T13:39:56.296+0500
DIGITALLOG | DIGITALLOG-156 | DIGITALLOG-156 | Sub-task | Sub-task |  | Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - NA | Resolved! |  |  |  |  | 0 | 0 | nadeem ahmed | 0 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-156 | [5 empty] | 2026-02-10T10:48:40.197+0500 | 2026-02-10T12:06:16.335+0500
DIGITALLOG | DIGITALLOG-157 | DIGITALLOG-157 | Sub-task | Sub-task |  | Get All Checklists API - Retrieves a complete list of checklists accessible to the authenticated user. - NA | Resolved! | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-157 | [5 empty] | 2026-02-10T10:50:02.714+0500 | 2026-02-10T12:04:40.887+0500
DIGITALLOG | DIGITALLOG-158 | DIGITALLOG-158 | Sub-task | Sub-task |  | Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - NA | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-158 | [5 empty] | 2026-02-10T10:52:12.483+0500 | 2026-02-10T12:04:51.689+0500
DIGITALLOG | DIGITALLOG-159 | DIGITALLOG-159 | Sub-task | Sub-task |  | Implement filtering by department, section, and fields, and perform functional validation. - AZ | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-159 | [5 empty] | 2026-02-10T10:53:18.641+0500 | 2026-02-10T10:54:45.505+0500
DIGITALLOG | DIGITALLOG-16 | DIGITALLOG-16 | Bug Subtask | Bug Subtask |  | The application does not prompt for confirmation when removing weekends, whereas it does show a confirmation and the ‘Save Changes’ button enabled as well while adding weekends. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-16 | [5 empty] | 2025-10-08T11:45:25.882+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-160 | DIGITALLOG-160 | Sub-task | Sub-task |  | Get Tag Data by Date Range with Tags Filter API - Retrieves tag data for a defined date range filtered by selected tag(s). - NA | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-160 | [5 empty] | 2026-02-10T10:54:25.002+0500 | 2026-02-10T12:05:00.963+0500
DIGITALLOG | DIGITALLOG-161 | DIGITALLOG-161 | Sub-task | Sub-task |  | User Authorization for Read API (Backend) - Implements backend-level authorization to control and validate user access to Read APIs. - NA | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-161 | [5 empty] | 2026-02-10T10:55:59.196+0500 | 2026-02-10T12:05:11.217+0500
DIGITALLOG | DIGITALLOG-162 | DIGITALLOG-162 | Sub-task | Sub-task |  | Get hierarchy nodes with their associated tags. - NA | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-162 | [5 empty] | 2026-02-10T10:57:16.731+0500 | 2026-02-10T12:05:20.354+0500
DIGITALLOG | DIGITALLOG-163 | DIGITALLOG-163 | Sub-task | Sub-task |  | Tenant & Domain Mapping Preparation. - AZ | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-163 | [5 empty] | 2026-02-10T10:58:21.921+0500 | 2026-02-10T10:59:59.994+0500
DIGITALLOG | DIGITALLOG-164 | DIGITALLOG-164 | Sub-task | Sub-task |  | Microservices Configuration & Routing Update. - AZ | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-164 | [5 empty] | 2026-02-10T10:58:41.255+0500 | 2026-02-16T16:08:00.256+0500
DIGITALLOG | DIGITALLOG-165 | DIGITALLOG-165 | Sub-task | Sub-task |  | Get tag data for multiple tags within a date range - NA | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-165 | [5 empty] | 2026-02-10T10:58:48.282+0500 | 2026-02-10T12:05:34.971+0500
DIGITALLOG | DIGITALLOG-166 | DIGITALLOG-166 | Sub-task | Sub-task |  | Review existing application structure to align the journal implementation with current architecture. Define validation rules for journals and entries. - NA | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-166 | [5 empty] | 2026-02-10T11:00:34.744+0500 | 2026-02-10T12:06:30.731+0500
DIGITALLOG | DIGITALLOG-167 | DIGITALLOG-167 | Sub-task | Sub-task |  | Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - NA | Resolved! | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-167 | [5 empty] | 2026-02-10T11:03:01.055+0500 | 2026-02-10T12:06:41.518+0500
DIGITALLOG | DIGITALLOG-168 | DIGITALLOG-168 | Sub-task | Sub-task |  | Development for new tool call to add template details in chatbot | Resolved! | 2026-02-04 | 2026-02-09 | 2026-02-04 | 2026-02-09 | 24 | 24 | Muhammad Zeeshan Aslam | 24 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-168 | [5 empty] | 2026-02-10T11:04:11.719+0500 | 2026-03-10T15:36:45.129+0500
DIGITALLOG | DIGITALLOG-169 | DIGITALLOG-169 | Sub-task | Sub-task |  | Implement JPA entities for all journal-related tables following existing standards. - NA | Resolved! | 2026-01-28 | 2026-01-28 |  |  | 8 | 8 | nadeem ahmed | 0 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-169 | [5 empty] | 2026-02-10T11:04:28.524+0500 | 2026-02-10T12:06:53.458+0500
DIGITALLOG | DIGITALLOG-17 | DIGITALLOG-17 | Bug Subtask | Bug Subtask |  | Upon trying to save changes in organization management, application is just loading to implement changes for multiple minutes. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1.5 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-17 | [5 empty] | 2025-10-08T14:08:36.515+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-170 | DIGITALLOG-170 | Sub-task | Sub-task |  | Tenant & Domain Mapping Preparation. - MA | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-170 | [5 empty] | 2026-02-10T11:04:56.731+0500 | 2026-02-10T11:07:29.061+0500
DIGITALLOG | DIGITALLOG-171 | DIGITALLOG-171 | Sub-task | Sub-task |  | Create repository interfaces and required queries for journals, entries, and filtering. - NA | Resolved! | 2026-01-29 | 2026-01-29 |  |  | 8 | 8 | nadeem ahmed | 0 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-171 | [5 empty] | 2026-02-10T11:09:47.005+0500 | 2026-02-10T12:07:03.370+0500
DIGITALLOG | DIGITALLOG-172 | DIGITALLOG-172 | Sub-task | Sub-task |  | Implement backend logic and APIs to manage template fields. - NA | Resolved! | 2026-01-30 | 2026-01-30 |  |  | 8 | 8 | nadeem ahmed | 0 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-172 | [5 empty] | 2026-02-10T11:11:51.622+0500 | 2026-02-10T12:07:15.594+0500
DIGITALLOG | DIGITALLOG-173 | DIGITALLOG-173 | Sub-task | Sub-task |  | Design and prepare database schema for journals, template fields, entries, remarks, and access mapping. - NA | Resolved! | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-173 | [5 empty] | 2026-02-10T11:29:55.886+0500 | 2026-02-10T12:07:30.866+0500
DIGITALLOG | DIGITALLOG-174 | DIGITALLOG-174 | Sub-task | Sub-task |  | Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - NA | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-174 | [5 empty] | 2026-02-10T11:32:30.463+0500 | 2026-02-10T12:05:45.859+0500
DIGITALLOG | DIGITALLOG-175 | DIGITALLOG-175 | Sub-task | Sub-task |  | Requirement Understanding & Analysis - NA | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-175 | [5 empty] | 2026-02-10T11:41:16.543+0500 | 2026-02-18T09:24:01.683+0500
DIGITALLOG | DIGITALLOG-176 | DIGITALLOG-176 | Sub-task | Sub-task |  | Implement journal creation and enforce group-based access and visibility rules. - NA | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-176 | [5 empty] | 2026-02-10T11:45:27.917+0500 | 2026-02-10T12:08:05.865+0500
DIGITALLOG | DIGITALLOG-177 | DIGITALLOG-177 | Sub-task | Sub-task |  | Develop services and APIs for submitting journal entries with dynamic field data. - NA | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-177 | [5 empty] | 2026-02-10T11:47:01.746+0500 | 2026-02-10T12:08:17.243+0500
DIGITALLOG | DIGITALLOG-178 | DIGITALLOG-178 | Sub-task | Sub-task |  | Implement multi-user remarks and commenting support for journal entries. - NA | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-178 | [5 empty] | 2026-02-10T11:48:33.436+0500 | 2026-02-10T12:08:28.108+0500
DIGITALLOG | DIGITALLOG-179 | DIGITALLOG-179 | Sub-task | Sub-task |  | Implement filtering by department, section, and fields, and perform functional validation. - NA | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-179 | [5 empty] | 2026-02-10T11:50:07.305+0500 | 2026-02-10T12:08:37.292+0500
DIGITALLOG | DIGITALLOG-18 | DIGITALLOG-18 | Bug Subtask | Bug Subtask |  | Able to submit a checklist on holiday. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0.5 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-18 | [5 empty] | 2025-10-09T10:08:24.794+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-182 | DIGITALLOG-182 | Bug Subtask | Bug Subtask |  | Wrong data is displaying against active checklists in log chat. | Resolved | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-182 | [5 empty] | 2026-02-11T10:31:52.426+0500 | 2026-03-11T16:28:24.534+0500
DIGITALLOG | DIGITALLOG-183 | DIGITALLOG-183 | Bug Subtask | Bug Subtask |  | No excel file is downloaded in log chat after waiting. | Request received |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-183 | [5 empty] | 2026-02-11T10:42:20.117+0500 | 2026-02-11T12:26:27.629+0500
DIGITALLOG | DIGITALLOG-184 | DIGITALLOG-184 | Sub-task | Sub-task |  | Authentication, CORS & Inter-Service Validation. - AZ | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Arsalan Zafar Khan | 6 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-184 | [5 empty] | 2026-02-11T10:46:09.639+0500 | 2026-02-13T16:54:50.926+0500
DIGITALLOG | DIGITALLOG-185 | DIGITALLOG-185 | Bug Subtask | Bug Subtask |  | Wrong data is displaying against those checklists in which attachments are added. | Request received |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-185 | [5 empty] | 2026-02-11T10:53:55.508+0500 | 2026-02-11T12:26:27.629+0500
DIGITALLOG | DIGITALLOG-186 | DIGITALLOG-186 | Bug Subtask | Bug Subtask |  | No data is displaying against returned checklists assigned to specific user. | Request received |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-186 | [5 empty] | 2026-02-11T11:00:45.177+0500 | 2026-02-11T12:26:27.629+0500
DIGITALLOG | DIGITALLOG-187 | DIGITALLOG-187 | Bug Subtask | Bug Subtask |  | No data is displaying against specific checklist with a due date as well. | Request received |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-187 | [5 empty] | 2026-02-11T11:21:22.113+0500 | 2026-02-11T12:26:27.629+0500
DIGITALLOG | DIGITALLOG-188 | DIGITALLOG-188 | Bug Subtask | Bug Subtask |  | No values in exported file is displaying against time frames. | Request received |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-188 | [5 empty] | 2026-02-11T11:49:47.395+0500 | 2026-02-11T12:26:27.629+0500
DIGITALLOG | DIGITALLOG-189 | DIGITALLOG-189 | Bug Subtask | Bug Subtask |  | Unable to give answer on predictive question. | Request received |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-189 | [5 empty] | 2026-02-11T12:34:57.267+0500 | 2026-02-11T12:36:20.401+0500
DIGITALLOG | DIGITALLOG-19 | DIGITALLOG-19 | Bug Subtask | Bug Subtask |  | Schedule is creating against checklist 5 hours previous from current time when only frequency changes and it does not create in previous 5 hours when start time is changed. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 1 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-19 | [5 empty] | 2025-10-09T10:13:46.449+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-190 | DIGITALLOG-190 | Bug Subtask | Bug Subtask |  | Chat returns procedure instead of performing calculation. | Resolved | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-190 | [5 empty] | 2026-02-11T12:38:18.240+0500 | 2026-03-11T16:29:21.913+0500
DIGITALLOG | DIGITALLOG-191 | DIGITALLOG-191 | Bug Subtask | Bug Subtask |  | No response is given against highest and lowest average against specific parameter data. | Request received |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-191 | [5 empty] | 2026-02-11T12:51:00.119+0500 | 2026-02-11T12:53:06.191+0500
DIGITALLOG | DIGITALLOG-192 | DIGITALLOG-192 | Epic | Epic |  | Log Chat Integration | Resolved! | 2026-01-07 | 2026-02-20 |  |  | 80 | 80 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-192 | [5 empty] | 2026-02-11T16:58:12.376+0500 | 2026-02-24T12:02:36.423+0500
DIGITALLOG | DIGITALLOG-193 | DIGITALLOG-193 | Story | Story |  | SQA | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | DIGITALLOG-192 | DIGITALLOG-192 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-192 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-193 | [5 empty] | 2026-02-12T11:12:45.668+0500 | 2026-02-26T11:05:42.368+0500
DIGITALLOG | DIGITALLOG-194 | DIGITALLOG-194 | Sub-task | Sub-task |  | Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application, and create and verify analytical questions to ensure accurate and reliable results. 1 | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-194 | [5 empty] | 2026-02-12T16:02:09.513+0500 | 2026-02-12T16:03:20.655+0500
DIGITALLOG | DIGITALLOG-195 | DIGITALLOG-195 | Sub-task | Sub-task |  | Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application, and create and verify analytical questions to ensure accurate and reliable results. 2 | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-195 | [5 empty] | 2026-02-12T16:03:47.809+0500 | 2026-02-13T15:42:14.807+0500
DIGITALLOG | DIGITALLOG-196 | DIGITALLOG-196 | Epic | Epic |  | Technical Support | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-196 | [5 empty] | 2026-02-13T15:39:38.738+0500 | 2026-02-24T12:04:48.560+0500
DIGITALLOG | DIGITALLOG-197 | DIGITALLOG-197 | Sub-task | Sub-task |  | Tenant & Domain Mapping Preparation. - NA | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-197 | [5 empty] | 2026-02-13T15:50:56.861+0500 | 2026-02-13T16:05:39.836+0500
DIGITALLOG | DIGITALLOG-198 | DIGITALLOG-198 | Sub-task | Sub-task |  | SSL Post-Implementation Verification for octopusdtl Domain. -AZ | Resolved! | 2026-02-16 | 2026-02-17 | 2026-02-16 | 2026-02-17 | 16 | 16 | Arsalan Zafar Khan | 16 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-198 | [5 empty] | 2026-02-16T09:55:02.404+0500 | 2026-02-19T12:19:58.421+0500
DIGITALLOG | DIGITALLOG-199 | DIGITALLOG-199 | Sub-task | Sub-task |  | SQA-Journal | Resolved! | 2026-02-13 | 2026-02-19 | 2026-02-17 | 2026-02-20 | 16 | 16 | Zeeshan Sarwar | 16 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-199 | [5 empty] | 2026-02-16T11:00:32.476+0500 | 2026-03-02T17:29:55.863+0500
DIGITALLOG | DIGITALLOG-2 | DIGITALLOG-2 | Story | Story |  | Holiday Feature Integration | Resolved! | 2025-09-22 | 2025-09-26 |  |  | 120 | 120 | nadeem ahmed | 156.5 |  | DIGITALLOG-1 | DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | [5 empty] | 2025-10-03T19:45:46.987+0500 | 2026-02-26T14:53:28.036+0500
DIGITALLOG | DIGITALLOG-20 | DIGITALLOG-20 | Bug Subtask | Bug Subtask |  | Manual Checklist is not activating | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.33 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-20 | [5 empty] | 2025-10-09T12:26:58.911+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-200 | DIGITALLOG-200 | Bug Subtask | Bug Subtask |  | Assigned module access is not correct. | Resolved | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1.5 | 1.5 | Muhammad Abdullah | 1.5 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-200 | [5 empty] | 2026-02-16T11:01:05.524+0500 | 2026-02-23T09:32:25.662+0500
DIGITALLOG | DIGITALLOG-201 | DIGITALLOG-201 | Bug Subtask | Bug Subtask |  | No department or section is displaying in drop down while creating journal. | Resolved | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1.5 | 1.5 | Muhammad Abdullah | 1.5 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-201 | [5 empty] | 2026-02-16T11:26:53.434+0500 | 2026-02-23T09:32:34.698+0500
DIGITALLOG | DIGITALLOG-203 | DIGITALLOG-203 | Sub-task | Sub-task |  | Microservices Configuration & Routing Update. - NA | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-203 | [5 empty] | 2026-02-16T16:09:14.620+0500 | 2026-02-16T16:20:15.510+0500
DIGITALLOG | DIGITALLOG-204 | DIGITALLOG-204 | Sub-task | Sub-task |  | Authentication, CORS & Inter-Service Validation. - NA | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-204 | [5 empty] | 2026-02-16T16:09:39.741+0500 | 2026-02-16T16:20:56.312+0500
DIGITALLOG | DIGITALLOG-205 | DIGITALLOG-205 | Sub-task | Sub-task |  | Microservices Configuration & Routing Update. - MA | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-205 | [5 empty] | 2026-02-16T16:10:14.189+0500 | 2026-02-16T16:11:11.983+0500
DIGITALLOG | DIGITALLOG-207 | DIGITALLOG-207 | Sub-task | Sub-task |  | SSL Post-Implementation Verification for octopusdtl Domain. - NA | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-207 | [5 empty] | 2026-02-16T16:16:42.399+0500 | 2026-03-30T09:26:15.313+0500
DIGITALLOG | DIGITALLOG-209 | DIGITALLOG-209 | Sub-task | Sub-task |  | Perform development testing to ensure all features function correctly, validate that statistical data matches the Digital Log (DL) application - NA | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-209 | [5 empty] | 2026-02-16T16:32:38.888+0500 | 2026-02-18T09:24:23.351+0500
DIGITALLOG | DIGITALLOG-21 | DIGITALLOG-21 | Sub-task | Sub-task |  | Performed analysis of all time entries submitted in DL across different time zones. | Resolved! |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 14.5 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-21 | [5 empty] | 2025-10-10T11:46:08.037+0500 | 2025-10-10T11:48:32.243+0500
DIGITALLOG | DIGITALLOG-210 | DIGITALLOG-210 | Sub-task | Sub-task |  | Authentication, CORS & Inter-Service Validation. - MA | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-210 | [5 empty] | 2026-02-16T16:43:39.854+0500 | 2026-02-16T16:55:45.593+0500
DIGITALLOG | DIGITALLOG-211 | DIGITALLOG-211 | Sub-task | Sub-task |  | LogChat UI/UX Improvements & Usability Enhancement - MA | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-211 | [5 empty] | 2026-02-16T16:51:05.661+0500 | 2026-02-16T16:52:24.782+0500
DIGITALLOG | DIGITALLOG-212 | DIGITALLOG-212 | Sub-task | Sub-task |  | Fix Performance & Loading Issues in Highcharts Integration | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-212 | [5 empty] | 2026-02-16T16:51:30.624+0500 | 2026-02-16T16:55:25.061+0500
DIGITALLOG | DIGITALLOG-213 | DIGITALLOG-213 | Bug Subtask | Bug Subtask |  | Unable to activate my initial version of journal template again after creating and activating its second version. | Development |  |  | 2026-02-19 | 2026-02-19 | 0 | 0 | Arsalan Zafar Khan | 2 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-213 | [5 empty] | 2026-02-17T10:29:54.313+0500 | 2026-02-19T14:48:32.719+0500
DIGITALLOG | DIGITALLOG-214 | DIGITALLOG-214 | Sub-task | Sub-task |  | Separating the data analysis and user manual part from the chatbot | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | Muhammad Zeeshan Aslam | 4 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-214 | [5 empty] | 2026-02-17T17:15:08.539+0500 | 2026-03-11T16:29:51.080+0500
DIGITALLOG | DIGITALLOG-215 | DIGITALLOG-215 | Sub-task | Sub-task |  | Preparing Demo questions and testing log chat | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-215 | [5 empty] | 2026-02-17T17:30:39.254+0500 | 2026-03-11T16:28:57.360+0500
DIGITALLOG | DIGITALLOG-216 | DIGITALLOG-216 | Bug Subtask | Bug Subtask |  | Journal template is not deleting where as success message is displayed. | Resolved | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1.5 | 1.5 | Muhammad Abdullah | 1.5 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-216 | [5 empty] | 2026-02-18T11:09:03.018+0500 | 2026-02-23T09:32:41.421+0500
DIGITALLOG | DIGITALLOG-217 | DIGITALLOG-217 | Sub-task | Sub-task |  | SSL Post-Implementation Verification for octopusdtl Domain. - MA | Resolved! | 2026-02-16 | 2026-02-17 | 2026-02-16 | 2026-02-17 | 16 | 16 | Muhammad Abdullah | 16 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-217 | [5 empty] | 2026-02-18T16:48:07.232+0500 | 2026-02-20T15:39:30.350+0500
DIGITALLOG | DIGITALLOG-218 | DIGITALLOG-218 | Epic | Epic |  | PowerPoint/Demo | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-218 | [5 empty] | 2026-02-19T14:35:31.385+0500 | 2026-02-24T12:01:53.830+0500
DIGITALLOG | DIGITALLOG-219 | DIGITALLOG-219 | Epic | Epic |  | Journal for Mobile App | Resolved! | 2026-02-23 | 2026-03-30 |  |  | 464 | 464 | Arsalan Zafar Khan | 5.5 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | [5 empty] | 2026-02-19T14:40:03.991+0500 | 2026-04-02T10:08:32.706+0500
DIGITALLOG | DIGITALLOG-220 | DIGITALLOG-220 | Epic | Epic |  | Holidays Management – manage the start and end time for the holiday | Resolved! | 2026-02-23 | 2026-03-30 |  |  | 184 | 184 | Arsalan Zafar Khan | 8.5 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | [5 empty] | 2026-02-19T14:40:42.311+0500 | 2026-04-02T16:38:56.946+0500
DIGITALLOG | DIGITALLOG-221 | DIGITALLOG-221 | Epic | Epic |  | Return & Re-Approval param values and comments traceability | Resolved! | 2026-04-01 | 2026-04-27 |  |  | 200 | 200 | Arsalan Zafar Khan | 9 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | [5 empty] | 2026-02-19T14:41:20.028+0500 | 2026-04-29T14:04:16.712+0500
DIGITALLOG | DIGITALLOG-222 | DIGITALLOG-222 | Epic | Epic |  | User Specified Time based Checklist Scheduling | Resolved! | 2026-04-01 | 2026-04-27 |  |  | 130.4 | 130.4 | Arsalan Zafar Khan | 12 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | [5 empty] | 2026-02-19T14:41:55.695+0500 | 2026-04-29T14:05:10.501+0500
DIGITALLOG | DIGITALLOG-223 | DIGITALLOG-223 | Epic | Epic |  | Digital Signatures (Like DocuSign idea) | Resolved! | 2026-04-01 | 2026-04-27 |  |  | 84 | 84 | Arsalan Zafar Khan | 12 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | [5 empty] | 2026-02-19T14:42:37.842+0500 | 2026-04-29T14:06:07.544+0500
DIGITALLOG | DIGITALLOG-224 | DIGITALLOG-224 | Bug Subtask | Bug Subtask |  | Error display when activating a previous version of journal template. It only displays when performing this activity first time. | Resolved | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 0 | 0 | Arsalan Zafar Khan | 1 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-224 | [5 empty] | 2026-02-20T10:45:13.843+0500 | 2026-03-11T10:26:22.609+0500
DIGITALLOG | DIGITALLOG-225 | DIGITALLOG-225 | Story | Story |  | LogChat Demo | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 8.5 |  | DIGITALLOG-218 | DIGITALLOG-218 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-218 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-225 | [5 empty] | 2026-02-20T12:05:28.315+0500 | 2026-02-20T12:05:36.457+0500
DIGITALLOG | DIGITALLOG-226 | DIGITALLOG-226 | Sub-task | Sub-task |  | LogChat Demo Internal And Bug RCAs. - AZ | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2.5 | 2.5 | Arsalan Zafar Khan | 2.5 |  | DIGITALLOG-225 | DIGITALLOG-225 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-225 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-226 | [5 empty] | 2026-02-20T12:06:40.927+0500 | 2026-02-24T12:00:06.900+0500
DIGITALLOG | DIGITALLOG-227 | DIGITALLOG-227 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - AZ | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2.75 | 2.75 | Arsalan Zafar Khan | 2.75 |  | DIGITALLOG-153 | DIGITALLOG-153 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-153 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-227 | [5 empty] | 2026-02-20T14:38:57.602+0500 | 2026-03-13T11:00:16.496+0500
DIGITALLOG | DIGITALLOG-229 | DIGITALLOG-229 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. MA | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | Muhammad Abdullah | 3.25 |  | DIGITALLOG-153 | DIGITALLOG-153 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-153 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-229 | [5 empty] | 2026-02-20T14:39:35.267+0500 | 2026-02-20T15:54:23.159+0500
DIGITALLOG | DIGITALLOG-230 | DIGITALLOG-230 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - AZ | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2.75 | 2.75 | Arsalan Zafar Khan | 2.75 |  | DIGITALLOG-149 | DIGITALLOG-149 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-149 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-230 | [5 empty] | 2026-02-20T14:40:14.898+0500 | 2026-03-13T10:59:18.355+0500
DIGITALLOG | DIGITALLOG-231 | DIGITALLOG-231 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - NA | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-149 | DIGITALLOG-149 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-149 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-231 | [5 empty] | 2026-02-20T14:40:23.599+0500 | 2026-03-05T15:29:47.948+0500
DIGITALLOG | DIGITALLOG-232 | DIGITALLOG-232 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - MA | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | Muhammad Abdullah | 3.25 |  | DIGITALLOG-149 | DIGITALLOG-149 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-149 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-232 | [5 empty] | 2026-02-20T14:40:35.063+0500 | 2026-02-20T15:54:03.298+0500
DIGITALLOG | DIGITALLOG-233 | DIGITALLOG-233 | Sub-task | Sub-task |  | Make improvements as well as fix reported issues by team member During testing of Journals Module after completion | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-69 | DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-233 | [5 empty] | 2026-02-20T16:03:21.477+0500 | 2026-02-20T16:04:38.128+0500
DIGITALLOG | DIGITALLOG-234 | DIGITALLOG-234 | Epic | Epic |  | Default Reports Generation Via LogChat | In-Progress | 2026-02-23 | 2026-03-30 |  |  | 104 | 104 | nadeem ahmed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-234 | [5 empty] | 2026-02-23T14:35:23.700+0500 | 2026-03-02T15:11:19.144+0500
DIGITALLOG | DIGITALLOG-235 | DIGITALLOG-235 | Story | Story |  | RND | In-Progress | 2026-02-23 | 2026-03-30 |  |  | 8 | 8 | nadeem ahmed | 35.5 |  | DIGITALLOG-234 | DIGITALLOG-234 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-234 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-235 | [5 empty] | 2026-02-23T14:36:11.586+0500 | 2026-03-02T15:08:25.431+0500
DIGITALLOG | DIGITALLOG-236 | DIGITALLOG-236 | Sub-task | Sub-task |  | Research & Validation: Confirm Default Reports generation capability through LogChat 1/3 - NA | Resolved! | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-235 | DIGITALLOG-235 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-235 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-236 | [5 empty] | 2026-02-23T14:37:56.908+0500 | 2026-03-02T15:15:21.943+0500
DIGITALLOG | DIGITALLOG-237 | DIGITALLOG-237 | Story | Story |  | Technical Support to clients | To Do |  |  |  |  | 0 | 0 | nadeem ahmed | 50 |  | DIGITALLOG-196 | DIGITALLOG-196 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-196 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | [5 empty] | 2026-02-23T14:52:07.679+0500 | 2026-02-23T14:55:09.766+0500
DIGITALLOG | DIGITALLOG-238 | DIGITALLOG-238 | Sub-task | Sub-task |  | Checklists are not triggered (day was specified as holiday) | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-238 | [5 empty] | 2026-02-23T14:53:50.816+0500 | 2026-02-23T14:59:27.432+0500
DIGITALLOG | DIGITALLOG-239 | DIGITALLOG-239 | Story | Story |  | Development | Resolved! | 2026-02-23 | 2026-03-12 |  |  | 224 | 224 | Arsalan Zafar Khan | 124.5 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | [5 empty] | 2026-02-24T12:05:51.679+0500 | 2026-03-25T12:31:25.415+0500
DIGITALLOG | DIGITALLOG-240 | DIGITALLOG-240 | Story | Story |  | SQA | Resolved! | 2026-03-25 | 2026-03-27 |  |  | 24 | 24 | Zeeshan Sarwar | 10 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-240 | [5 empty] | 2026-02-24T12:06:08.316+0500 | 2026-03-30T11:56:25.280+0500
DIGITALLOG | DIGITALLOG-241 | DIGITALLOG-241 | Story | Story |  | User Manual - Textual Guide (no screenshots) | Resolved! | 2026-03-25 | 2026-03-27 | 2026-04-01 | 2026-04-01 | 4 | 4 | Hassan Malik | 3 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-241 | [5 empty] | 2026-02-24T12:06:32.444+0500 | 2026-04-02T09:55:03.180+0500
DIGITALLOG | DIGITALLOG-242 | DIGITALLOG-242 | Story | Story |  | Production Release | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 16 | 16 | Arsalan Zafar Khan | 19 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | [5 empty] | 2026-02-24T12:07:25.910+0500 | 2026-03-30T16:53:23.736+0500
DIGITALLOG | DIGITALLOG-243 | DIGITALLOG-243 | Story | Story |  | Development | Resolved! | 2026-03-04 | 2026-03-12 |  |  | 104 | 104 | Arsalan Zafar Khan | 92.5 |  | DIGITALLOG-220 | DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | [5 empty] | 2026-02-24T12:09:15.217+0500 | 2026-03-27T17:04:04.521+0500
DIGITALLOG | DIGITALLOG-244 | DIGITALLOG-244 | Story | Story |  | SQA | Resolved! | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-26 | 32 | 32 | Zeeshan Sarwar | 6 |  | DIGITALLOG-220 | DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-244 | [5 empty] | 2026-02-24T12:09:25.682+0500 | 2026-03-30T11:55:40.228+0500
DIGITALLOG | DIGITALLOG-245 | DIGITALLOG-245 | Story | Story |  | User Manual | Resolved! | 2026-03-25 | 2026-03-27 |  |  | 4 | 4 | Hassan Malik | 1 |  | DIGITALLOG-220 | DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-245 | [5 empty] | 2026-02-24T12:09:34.547+0500 | 2026-04-02T16:37:58.212+0500
DIGITALLOG | DIGITALLOG-246 | DIGITALLOG-246 | Story | Story |  | Production Release | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 16 | 16 | Arsalan Zafar Khan | 10 |  | DIGITALLOG-220 | DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-246 | [5 empty] | 2026-02-24T12:09:44.255+0500 | 2026-03-30T16:53:42.557+0500
DIGITALLOG | DIGITALLOG-247 | DIGITALLOG-247 | Story | Story |  | Development | Resolved! | 2026-04-01 | 2026-04-08 |  |  | 144 | 144 | Arsalan Zafar Khan | 94 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | [5 empty] | 2026-02-24T12:24:47.918+0500 | 2026-04-09T09:13:12.335+0500
DIGITALLOG | DIGITALLOG-248 | DIGITALLOG-248 | Story | Story |  | SQA | Resolved! | 2026-04-10 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 20 | 20 | kamran khalid | 54 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-248 | [5 empty] | 2026-02-24T12:24:58.675+0500 | 2026-04-29T10:45:38.222+0500
DIGITALLOG | DIGITALLOG-249 | DIGITALLOG-249 | Story | Story |  | User Manual | On Hold |  |  |  |  | 8 | 8 | Hassan Malik | 0 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-249 | [5 empty] | 2026-02-24T12:25:06.871+0500 | 2026-04-29T14:08:01.031+0500
DIGITALLOG | DIGITALLOG-25 | DIGITALLOG-25 | Story | Story |  | Ensure consistent UTC time usage across the application & checklist scheduling creation according org time zone | Resolved! | 2025-10-13 | 2025-10-17 |  |  | 120 | 120 | Zeeshan Sarwar | 84 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-25 | [5 empty] | 2025-10-20T10:12:03.315+0500 | 2025-12-08T13:26:27.630+0500
DIGITALLOG | DIGITALLOG-250 | DIGITALLOG-250 | Story | Story |  | Production Release | Resolved! | 2026-05-27 | 2026-04-27 |  |  | 8 | 8 | Arsalan Zafar Khan | 5.33 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-250 | [5 empty] | 2026-02-24T12:25:13.455+0500 | 2026-04-29T14:04:04.832+0500
DIGITALLOG | DIGITALLOG-251 | DIGITALLOG-251 | Story | Story |  | Development | Resolved! | 2026-04-15 | 2026-04-20 |  |  | 69 | 69 | Arsalan Zafar Khan | 68.5 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | [5 empty] | 2026-02-24T12:26:40.731+0500 | 2026-04-24T12:12:26.154+0500
DIGITALLOG | DIGITALLOG-252 | DIGITALLOG-252 | Story | Story |  | SQA | Resolved! | 2026-04-21 | 2026-04-23 |  |  | 20 | 20 | Zeeshan Sarwar | 0 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-252 | [5 empty] | 2026-02-24T12:26:49.166+0500 | 2026-04-29T14:06:55.826+0500
DIGITALLOG | DIGITALLOG-253 | DIGITALLOG-253 | Story | Story |  | User manual | On Hold |  |  |  |  | 8 | 8 | Hassan Malik | 0 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-253 | [5 empty] | 2026-02-24T12:27:00.988+0500 | 2026-04-29T14:07:24.686+0500
DIGITALLOG | DIGITALLOG-254 | DIGITALLOG-254 | Story | Story |  | Production release | Resolved! | 2026-04-27 | 2026-04-27 |  |  | 8 | 8 | Arsalan Zafar Khan | 5.33 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-254 | [5 empty] | 2026-02-24T12:27:10.573+0500 | 2026-04-29T14:05:05.928+0500
DIGITALLOG | DIGITALLOG-255 | DIGITALLOG-255 | Story | Story |  | Development | Resolved! | 2026-04-09 | 2026-04-13 |  |  | 42 | 42 | Arsalan Zafar Khan | 52.5 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | [5 empty] | 2026-02-24T12:28:21.201+0500 | 2026-04-24T11:30:35.261+0500
DIGITALLOG | DIGITALLOG-256 | DIGITALLOG-256 | Story | Story |  | SQA | Resolved! | 2026-04-14 | 2026-04-16 |  |  | 12 | 12 | Zeeshan Sarwar | 0 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-256 | [5 empty] | 2026-02-24T12:28:29.524+0500 | 2026-04-29T14:06:25.409+0500
DIGITALLOG | DIGITALLOG-257 | DIGITALLOG-257 | Story | Story |  | User Manual | On Hold |  |  |  |  | 4 | 4 | Hassan Malik | 0 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-257 | [5 empty] | 2026-02-24T12:28:38.808+0500 | 2026-04-29T14:07:12.937+0500
DIGITALLOG | DIGITALLOG-258 | DIGITALLOG-258 | Story | Story |  | Production Release | Resolved! | 2026-04-27 | 2026-04-27 |  |  | 8 | 8 | Arsalan Zafar Khan | 5.33 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-258 | [5 empty] | 2026-02-24T12:28:48.327+0500 | 2026-04-29T14:05:58.983+0500
DIGITALLOG | DIGITALLOG-259 | DIGITALLOG-259 | Epic | Epic |  | LogChat - User Help, Journals | In-Progress | 2026-04-01 | 2026-04-27 |  |  | 88 | 88 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | [5 empty] | 2026-02-24T12:32:16.743+0500 | 2026-04-24T10:40:55.380+0500
DIGITALLOG | DIGITALLOG-26 | DIGITALLOG-26 | Story | Story |  | Consolidated View implementation in Mobile App + Checklist Search View + Filters +Sorting | Resolved! | 2025-10-13 | 2025-10-17 |  |  | 120 | 120 | Zeeshan Sarwar | 68 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-26 | [5 empty] | 2025-10-20T10:12:07.108+0500 | 2025-11-10T15:50:17.455+0500
DIGITALLOG | DIGITALLOG-260 | DIGITALLOG-260 | Story | Story |  | Development | In-Progress | 2026-04-01 | 2026-04-16 |  |  | 44.8 | 44.8 | Muhammad Zeeshan Aslam | 40 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-260 | [5 empty] | 2026-02-24T12:33:01.996+0500 | 2026-04-24T10:41:01.914+0500
DIGITALLOG | DIGITALLOG-261 | DIGITALLOG-261 | Story | Story |  | SQA | To Do | 2026-04-17 | 2026-04-21 |  |  | 24 | 24 | Zeeshan Sarwar | 0 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-261 | [5 empty] | 2026-02-24T12:33:11.514+0500 | 2026-04-08T16:55:03.581+0500
DIGITALLOG | DIGITALLOG-262 | DIGITALLOG-262 | Story | Story |  | User Manual | To Do |  |  |  |  | 8 | 8 | Hassan Malik | 0 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-262 | [5 empty] | 2026-02-24T12:33:20.614+0500 | 2026-04-01T11:01:22.886+0500
DIGITALLOG | DIGITALLOG-263 | DIGITALLOG-263 | Story | Story |  | Production Release | To Do | 2026-04-27 | 2026-04-27 |  |  | 8 | 8 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-263 | [5 empty] | 2026-02-24T12:33:29.430+0500 | 2026-04-08T16:35:57.903+0500
DIGITALLOG | DIGITALLOG-265 | DIGITALLOG-265 | Task | Task |  | SQA | To Do |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-265 | [5 empty] | 2026-02-24T12:35:08.645+0500 | 2026-02-24T12:35:53.003+0500
DIGITALLOG | DIGITALLOG-266 | DIGITALLOG-266 | Task | Task |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-266 | [5 empty] | 2026-02-24T12:35:08.677+0500 | 2026-02-24T12:35:09.123+0500
DIGITALLOG | DIGITALLOG-267 | DIGITALLOG-267 | Task | Task |  | Production Release | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-267 | [5 empty] | 2026-02-24T12:35:08.870+0500 | 2026-02-24T12:35:54.761+0500
DIGITALLOG | DIGITALLOG-268 | DIGITALLOG-268 | Task | Task |  | Development | To Do |  |  |  |  | 96 | 96 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-268 | [5 empty] | 2026-02-24T12:35:09.006+0500 | 2026-02-24T12:35:56.254+0500
DIGITALLOG | DIGITALLOG-269 | DIGITALLOG-269 | Sub-task | Sub-task |  | Retraining of LLM to resolve issues related to logchat | Resolved! | 2026-02-18 | 2026-02-20 | 2026-02-18 | 2026-02-20 | 24 | 24 | Muhammad Zeeshan Aslam | 21 |  | DIGITALLOG-113 | DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-113 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-269 | [5 empty] | 2026-02-25T10:19:43.918+0500 | 2026-03-10T15:44:51.424+0500
DIGITALLOG | DIGITALLOG-27 | DIGITALLOG-27 | Epic | Epic |  | Dashboard, Data & Mobile Improvements | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 496 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | [5 empty] | 2025-10-20T10:16:40.494+0500 | 2026-02-26T10:55:49.309+0500
DIGITALLOG | DIGITALLOG-270 | DIGITALLOG-270 | Story | Story |  | ReadApi | Resolved! | 2026-03-13 | 2026-03-24 |  |  | 96 | 96 | Arsalan Zafar Khan | 79 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | [5 empty] | 2026-02-25T13:09:45.022+0500 | 2026-03-25T15:46:02.270+0500
DIGITALLOG | DIGITALLOG-271 | DIGITALLOG-271 | Story | Story |  | DDS | Resolved! | 2026-02-26 | 2026-03-02 |  |  | 23 | 23 | nadeem ahmed | 24 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-271 | [5 empty] | 2026-02-25T13:55:17.732+0500 | 2026-03-30T15:37:45.229+0500
DIGITALLOG | DIGITALLOG-272 | DIGITALLOG-272 | Story | Story |  | Development | Resolved! | 2026-02-25 | 2026-03-31 |  |  | 80 | 80 | Muhammad Zeeshan Aslam | 132.5 |  | DIGITALLOG-234 | DIGITALLOG-234 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-234 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | [5 empty] | 2026-02-25T14:01:24.681+0500 | 2026-04-02T11:56:59.420+0500
DIGITALLOG | DIGITALLOG-273 | DIGITALLOG-273 | Story | Story |  | DDS | Resolved! | 2026-03-04 | 2026-03-04 |  |  | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-220 | DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-273 | [5 empty] | 2026-02-25T14:10:24.903+0500 | 2026-03-30T15:41:49.736+0500
DIGITALLOG | DIGITALLOG-275 | DIGITALLOG-275 | Sub-task | Sub-task |  | Implement Journal module bottom tabs (My Journal(s) & Review Journal(s)) with icons, navigation routing, and base screen layouts. - MA | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-275 | [5 empty] | 2026-02-26T10:11:44.148+0500 | 2026-03-02T09:09:54.958+0500
DIGITALLOG | DIGITALLOG-276 | DIGITALLOG-276 | Sub-task | Sub-task |  | Integrate backend API to fetch My Journal(s) list, implement FlatList with pagination/loading states and Redux/offline state handling. - MA | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-276 | [5 empty] | 2026-02-26T10:13:09.158+0500 | 2026-03-02T09:10:56.807+0500
DIGITALLOG | DIGITALLOG-277 | DIGITALLOG-277 | Sub-task | Sub-task |  | Implement Journal Detail screen, integrate API to load journal template version fields dynamically, render dynamic form components. - MA | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-277 | [5 empty] | 2026-02-26T10:14:17.305+0500 | 2026-03-02T09:11:38.869+0500
DIGITALLOG | DIGITALLOG-278 | DIGITALLOG-278 | Sub-task | Sub-task |  | Implement form state management, validation logic, input handling (text, dropdowns, date, etc.), and attachment picker integration. - MA | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-278 | [5 empty] | 2026-02-26T10:15:20.058+0500 | 2026-03-02T09:12:36.565+0500
DIGITALLOG | DIGITALLOG-279 | DIGITALLOG-279 | Sub-task | Sub-task |  | Implement journal submission API integration, attachment upload handling (online), success flow navigation back to My Journal(s), error handling. - MA | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-279 | [5 empty] | 2026-02-26T10:17:23.909+0500 | 2026-03-04T15:14:19.144+0500
DIGITALLOG | DIGITALLOG-28 | DIGITALLOG-28 | Story | Story |  | Improved Legends in Data Visualization | Resolved! | 2025-10-20 | 2025-10-22 |  |  | 72 | 72 | Zeeshan Sarwar | 88 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-28 | [5 empty] | 2025-10-20T14:27:47.610+0500 | 2025-11-06T10:08:34.655+0500
DIGITALLOG | DIGITALLOG-280 | DIGITALLOG-280 | Sub-task | Sub-task |  | Implement offline support for My Journal(s) (SQLite schema, save draft entries, attachment queue, sync queue structure). - MA | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-280 | [5 empty] | 2026-02-26T10:18:43.153+0500 | 2026-03-04T15:14:54.792+0500
DIGITALLOG | DIGITALLOG-281 | DIGITALLOG-281 | Sub-task | Sub-task |  | Implement Review Journal(s) base UI with advanced filters (Department, Section, Users, Date Range, All Journals dropdown). - MA | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-281 | [5 empty] | 2026-02-26T10:20:07.305+0500 | 2026-03-05T15:01:37.270+0500
DIGITALLOG | DIGITALLOG-282 | DIGITALLOG-282 | Sub-task | Sub-task |  | Integrate APIs for Journals dropdown, load selected Journal versions dynamically, and render dynamic filterable template fields. - MA | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-282 | [5 empty] | 2026-02-26T10:21:42.475+0500 | 2026-03-09T09:11:28.347+0500
DIGITALLOG | DIGITALLOG-283 | DIGITALLOG-283 | Sub-task | Sub-task |  | Implement advancedFilter API integration to fetch review entries, implement default loading of all entries with filter badges (Open, Closed, Attachments). - MA | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-283 | [5 empty] | 2026-02-26T10:22:48.873+0500 | 2026-03-09T09:12:10.006+0500
DIGITALLOG | DIGITALLOG-284 | DIGITALLOG-284 | Sub-task | Sub-task |  | Implement Review Detail screen to load filled entries, integrate remarks APIs (view, add, update, delete own remarks). - MA | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-284 | [5 empty] | 2026-02-26T10:23:58.274+0500 | 2026-03-12T12:35:49.072+0500
DIGITALLOG | DIGITALLOG-286 | DIGITALLOG-286 | Sub-task | Sub-task |  | Implement Close/Reopen journal entry functionality with remarks, integrate APIs, update list state and badge counts dynamically. - MA | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-286 | [5 empty] | 2026-02-26T10:26:30.742+0500 | 2026-03-12T12:37:29.478+0500
DIGITALLOG | DIGITALLOG-287 | DIGITALLOG-287 | Sub-task | Sub-task |  | Implement full offline support for Review module (cache entries, remarks, attachments, close/reopen queue), sync mechanism, testing, performance optimization, and bug fixing. - MA | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-287 | [5 empty] | 2026-02-26T10:27:32.143+0500 | 2026-03-18T12:36:58.751+0500
DIGITALLOG | DIGITALLOG-288 | DIGITALLOG-288 | Sub-task | Sub-task |  | Design lightweight mobile-specific REST endpoints and DTOs to minimize payload size and improve performance. - AZ | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 8 | 8 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-288 | [5 empty] | 2026-02-26T11:00:08.434+0500 | 2026-03-02T09:15:25.484+0500
DIGITALLOG | DIGITALLOG-289 | DIGITALLOG-289 | Sub-task | Sub-task |  | Implement APIs to fetch lightweight journals and journal entries for mobile listing screens. - AZ | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 8 | 8 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-289 | [5 empty] | 2026-02-26T11:00:29.272+0500 | 2026-03-02T09:15:47.433+0500
DIGITALLOG | DIGITALLOG-29 | DIGITALLOG-29 | Story | Story |  | Alert not deleting | Resolved! | 2025-10-23 | 2025-10-24 |  |  | 48 | 48 | nadeem ahmed | 48 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-29 | [5 empty] | 2025-10-20T14:27:53.370+0500 | 2025-11-10T15:50:31.472+0500
DIGITALLOG | DIGITALLOG-290 | DIGITALLOG-290 | Sub-task | Sub-task |  | Extend the JournalEntry entity to include metadata timestamps for attachments and remarks and update business logic to auto-maintain them. -AZ | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8 | 8 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-290 | [5 empty] | 2026-02-26T11:00:43.631+0500 | 2026-03-02T09:16:16.899+0500
DIGITALLOG | DIGITALLOG-291 | DIGITALLOG-291 | Sub-task | Sub-task |  | Develop a bulk API to retrieve attachments and remarks metadata for multiple journal entries in a single request. - AZ | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 8 | 8 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-291 | [5 empty] | 2026-02-26T11:00:59.523+0500 | 2026-03-04T09:41:35.079+0500
DIGITALLOG | DIGITALLOG-292 | DIGITALLOG-292 | Sub-task | Sub-task |  | Implement a delta API to return journal entries modified after a given last sync timestamp. -AZ | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 8 | 8 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-292 | [5 empty] | 2026-02-26T11:01:09.417+0500 | 2026-03-04T09:42:14.507+0500
DIGITALLOG | DIGITALLOG-293 | DIGITALLOG-293 | Sub-task | Sub-task |  | Enforce role-based and organization-level access validation for all mobile journal and entry APIs. - AZ | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-293 | [5 empty] | 2026-02-26T11:01:17.595+0500 | 2026-02-26T11:01:57.477+0500
DIGITALLOG | DIGITALLOG-294 | DIGITALLOG-294 | Sub-task | Sub-task |  | Implement structured audit logging for mobile-based journal entry creation operations. - AZ | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-294 | [5 empty] | 2026-02-26T11:01:26.830+0500 | 2026-02-26T11:01:59.357+0500
DIGITALLOG | DIGITALLOG-295 | DIGITALLOG-295 | Story | Story |  | QA Handover | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 1 | 1 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-295 | [5 empty] | 2026-02-26T11:19:23.568+0500 | 2026-03-27T12:20:28.233+0500
DIGITALLOG | DIGITALLOG-296 | DIGITALLOG-296 | Story | Story |  | QA Handover | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 1 | 1 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-220 | DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-296 | [5 empty] | 2026-02-26T11:23:11.099+0500 | 2026-03-27T12:27:57.740+0500
DIGITALLOG | DIGITALLOG-297 | DIGITALLOG-297 | Story | Story |  | Bug Fixing | Resolved! | 2026-03-20 | 2026-03-27 |  |  | 56 | 56 | Arsalan Zafar Khan | 50 |  | DIGITALLOG-219 | DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-219 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | [5 empty] | 2026-02-26T13:19:50.989+0500 | 2026-03-27T16:35:33.508+0500
DIGITALLOG | DIGITALLOG-298 | DIGITALLOG-298 | Story | Story |  | Bug Fixing | Resolved! | 2026-03-17 | 2026-03-27 |  |  | 7 | 7 | Arsalan Zafar Khan | 1 |  | DIGITALLOG-220 | DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-220 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-298 | [5 empty] | 2026-02-26T13:30:13.284+0500 | 2026-03-27T16:35:40.591+0500
DIGITALLOG | DIGITALLOG-299 | DIGITALLOG-299 | Sub-task | Sub-task |  | Integrating Inactive logs and Latest log Report | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5 | 6.5 | Muhammad Zeeshan Aslam | 6.5 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-299 | [5 empty] | 2026-02-26T15:01:52.093+0500 | 2026-03-10T15:47:18.896+0500
DIGITALLOG | DIGITALLOG-3 | DIGITALLOG-3 | Story | Story |  | Mobile App SSO Integration | Resolved! | 2025-09-29 | 2025-10-03 |  |  | 80 | 80 | nadeem ahmed | 88 |  | DIGITALLOG-1 | DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-3 | [5 empty] | 2025-10-03T19:45:57.479+0500 | 2026-02-26T14:58:44.150+0500
DIGITALLOG | DIGITALLOG-30 | DIGITALLOG-30 | Story | Story |  | Tables on Dashboard | Resolved! | 2025-10-27 | 2025-10-28 |  |  | 48 | 48 | nadeem ahmed | 32 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-30 | [5 empty] | 2025-10-20T14:27:57.640+0500 | 2025-11-04T16:37:35.595+0500
DIGITALLOG | DIGITALLOG-300 | DIGITALLOG-300 | Sub-task | Sub-task |  | Integrating capability to fetch tags based on Units and field type | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 6.5 | 6.5 | Muhammad Zeeshan Aslam | 6.5 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-300 | [5 empty] | 2026-02-26T15:04:25.498+0500 | 2026-03-11T16:30:41.431+0500
DIGITALLOG | DIGITALLOG-301 | DIGITALLOG-301 | Sub-task | Sub-task |  | Research & Validation: Confirm Default Reports generation capability through LogChat 2/3 - NA | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-235 | DIGITALLOG-235 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-235 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-301 | [5 empty] | 2026-03-02T15:04:08.538+0500 | 2026-03-02T15:15:00.415+0500
DIGITALLOG | DIGITALLOG-303 | DIGITALLOG-303 | Sub-task | Sub-task |  | Writing DDS (Document Design Specification) for Journal Mobile App - 1 | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-271 | DIGITALLOG-271 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-271 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-303 | [5 empty] | 2026-03-03T10:06:11.583+0500 | 2026-03-30T09:41:00.037+0500
DIGITALLOG | DIGITALLOG-304 | DIGITALLOG-304 | Sub-task | Sub-task |  | Writing DDS (Document Design Specification) for Journal Mobile App - 2 | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-271 | DIGITALLOG-271 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-271 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-304 | [5 empty] | 2026-03-03T10:06:21.084+0500 | 2026-03-30T09:39:29.892+0500
DIGITALLOG | DIGITALLOG-305 | DIGITALLOG-305 | Sub-task | Sub-task |  | Writing and review of DDS (Document Design Specification) for Journal Mobile App - 3 | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-271 | DIGITALLOG-271 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-271 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-305 | [5 empty] | 2026-03-03T10:06:49.300+0500 | 2026-03-30T09:42:17.669+0500
DIGITALLOG | DIGITALLOG-306 | DIGITALLOG-306 | Sub-task | Sub-task |  | Develop a bulk API to retrieve attachments and remarks metadata for multiple journal entries in a single request. - NA | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 8 | 8 | nadeem ahmed | 6 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-306 | [5 empty] | 2026-03-03T13:15:06.239+0500 | 2026-03-30T09:28:53.557+0500
DIGITALLOG | DIGITALLOG-307 | DIGITALLOG-307 | Sub-task | Sub-task |  | Integrating capability to fetch the logs and tags/items with remarks | Resolved! | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | 13 | 13 | Muhammad Zeeshan Aslam | 13 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-307 | [5 empty] | 2026-03-03T14:39:36.133+0500 | 2026-03-10T15:48:57.582+0500
DIGITALLOG | DIGITALLOG-308 | DIGITALLOG-308 | Sub-task | Sub-task |  | Update database schema to add holiday start_datetime and end_datetime fields with proper indexing and non-overlapping range constraints per organization. - AZ | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8 | 8 | Arsalan Zafar Khan | 5.5 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-308 | [5 empty] | 2026-03-04T09:55:31.771+0500 | 2026-03-05T14:16:38.629+0500
DIGITALLOG | DIGITALLOG-309 | DIGITALLOG-309 | Sub-task | Sub-task |  | Modify Holiday JPA entity, DTOs, and repository layer to support CRUD operations for holiday date-time ranges. - AZ | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8 | 8 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-309 | [5 empty] | 2026-03-04T09:56:05.469+0500 | 2026-03-06T09:55:25.835+0500
DIGITALLOG | DIGITALLOG-31 | DIGITALLOG-31 | Story | Story |  | Template Duplication (clone) Feature & Checklist Duplicate (clone) Feature | Resolved! | 2025-10-27 | 2025-10-31 |  |  | 120 | 120 | nadeem ahmed | 136 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-31 | [5 empty] | 2025-10-20T14:28:05.992+0500 | 2025-12-08T13:25:57.778+0500
DIGITALLOG | DIGITALLOG-310 | DIGITALLOG-310 | Sub-task | Sub-task |  | Implement REST APIs to create and update holiday ranges with validation (start < end, no overlapping holidays, timezone normalization to UTC). - AZ | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-310 | [5 empty] | 2026-03-04T09:56:21.343+0500 | 2026-03-06T16:10:30.562+0500
DIGITALLOG | DIGITALLOG-311 | DIGITALLOG-311 | Sub-task | Sub-task |  | Develop API to retrieve holidays with filtering by date range and organization, including pagination support. - AZ | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-311 | [5 empty] | 2026-03-04T09:56:30.894+0500 | 2026-03-10T11:13:54.075+0500
DIGITALLOG | DIGITALLOG-312 | DIGITALLOG-312 | Sub-task | Sub-task |  | Enhance checklist scheduler service logic to check current execution time against configured holiday ranges and skip triggering if within range. - AZ | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-312 | [5 empty] | 2026-03-04T09:56:40.414+0500 | 2026-03-11T09:12:07.123+0500
DIGITALLOG | DIGITALLOG-313 | DIGITALLOG-313 | Sub-task | Sub-task |  | Perform developer testing to validate holiday CRUD operations, overlapping range validations, and scheduler suppression behaviour during defined holiday periods. - AZ | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6 | 6 | Arsalan Zafar Khan | 6 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-313 | [5 empty] | 2026-03-04T09:56:49.119+0500 | 2026-03-12T09:58:56.020+0500
DIGITALLOG | DIGITALLOG-314 | DIGITALLOG-314 | Sub-task | Sub-task |  | Update scheduler logging and monitoring to record skipped executions due to holidays, finalize Swagger documentation, and deploy changes to development for QA testing. - AZ | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-314 | [5 empty] | 2026-03-04T09:57:03.289+0500 | 2026-03-13T10:56:53.444+0500
DIGITALLOG | DIGITALLOG-315 | DIGITALLOG-315 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-03-20 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 40 | 40 | Zeeshan Sarwar | 10 |  | DIGITALLOG-240 | DIGITALLOG-240 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-240 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-315 | [5 empty] | 2026-03-04T10:12:57.646+0500 | 2026-03-30T11:55:50.083+0500
DIGITALLOG | DIGITALLOG-316 | DIGITALLOG-316 | Sub-task | Sub-task |  | Working XY Plot and multi-line graph in chat | Resolved! | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-04 | 13 | 13 | Muhammad Zeeshan Aslam | 13 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-316 | [5 empty] | 2026-03-04T10:30:51.546+0500 | 2026-03-10T15:51:46.309+0500
DIGITALLOG | DIGITALLOG-317 | DIGITALLOG-317 | Story | Story |  | DL Demo | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 3.5 |  | DIGITALLOG-218 | DIGITALLOG-218 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-218 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | [5 empty] | 2026-03-05T14:14:27.204+0500 | 2026-04-01T09:35:11.450+0500
DIGITALLOG | DIGITALLOG-318 | DIGITALLOG-318 | Sub-task | Sub-task |  | Digital Log - Product/Platform Orientation Training | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1 | 1 | Arsalan Zafar Khan | 1 |  | DIGITALLOG-317 | DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-318 | [5 empty] | 2026-03-05T14:15:24.335+0500 | 2026-03-13T11:03:45.357+0500
DIGITALLOG | DIGITALLOG-32 | DIGITALLOG-32 | Story | Story |  | SQA | Resolved! | 2025-11-03 | 2025-11-07 |  |  | 160 | 160 | Zeeshan Sarwar | 24 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-32 | [5 empty] | 2025-10-20T14:30:09.511+0500 | 2025-11-10T10:41:26.231+0500
DIGITALLOG | DIGITALLOG-320 | DIGITALLOG-320 | Sub-task | Sub-task |  | Modify Holiday JPA entity, DTOs, and repository layer to support CRUD operations for holiday date-time ranges. - NA | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-320 | [5 empty] | 2026-03-05T15:02:49.219+0500 | 2026-03-30T09:34:48.989+0500
DIGITALLOG | DIGITALLOG-321 | DIGITALLOG-321 | Sub-task | Sub-task |  | Implement a delta API to return journal entries modified after a given last sync timestamp. -NA | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-239 | DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-239 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-321 | [5 empty] | 2026-03-05T15:11:20.138+0500 | 2026-03-30T09:34:25.988+0500
DIGITALLOG | DIGITALLOG-322 | DIGITALLOG-322 | Sub-task | Sub-task |  | SSL Post-Implementation Verification for octopusdtl Domain - NA | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-70 | DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-322 | [5 empty] | 2026-03-05T15:17:22.565+0500 | 2026-03-05T15:18:19.277+0500
DIGITALLOG | DIGITALLOG-323 | DIGITALLOG-323 | Sub-task | Sub-task |  | Read API is displaying other organization checklist data which is not present in my organization. - NA | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-71 | DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-323 | [5 empty] | 2026-03-05T15:20:02.644+0500 | 2026-03-30T09:26:05.082+0500
DIGITALLOG | DIGITALLOG-324 | DIGITALLOG-324 | Sub-task | Sub-task |  | LogChat testing and evaluation - NA | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 8 | 8 | nadeem ahmed | 6 |  | DIGITALLOG-225 | DIGITALLOG-225 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-225 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-324 | [5 empty] | 2026-03-05T15:25:43.513+0500 | 2026-03-30T09:25:54.873+0500
DIGITALLOG | DIGITALLOG-325 | DIGITALLOG-325 | Sub-task | Sub-task |  | Implement REST APIs to create and update holiday ranges with validation (start < end, no overlapping holidays, timezone normalization to UTC). - NA | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-325 | [5 empty] | 2026-03-10T15:11:06.548+0500 | 2026-03-10T15:11:55.189+0500
DIGITALLOG | DIGITALLOG-326 | DIGITALLOG-326 | Sub-task | Sub-task |  | Develop API to retrieve holidays with filtering by date range and organization - NA | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-326 | [5 empty] | 2026-03-10T15:12:55.558+0500 | 2026-03-10T15:13:50.730+0500
DIGITALLOG | DIGITALLOG-327 | DIGITALLOG-327 | Sub-task | Sub-task |  | Upcoming checklist Activities report | Resolved! | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-09 | 24 | 24 | Muhammad Zeeshan Aslam | 19.5 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-327 | [5 empty] | 2026-03-10T15:54:23.259+0500 | 2026-03-24T11:41:05.313+0500
DIGITALLOG | DIGITALLOG-328 | DIGITALLOG-328 | Sub-task | Sub-task |  | Add start and end time selection, select and unselect Saturdays as well as other improvements done for holiday module - MA | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-328 | [5 empty] | 2026-03-11T11:01:48.740+0500 | 2026-03-11T11:03:20.729+0500
DIGITALLOG | DIGITALLOG-329 | DIGITALLOG-329 | Sub-task | Sub-task |  | Digital Log - Product/Platform Orientation Training March 11 | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 0.5 | 0.5 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-317 | DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-329 | [5 empty] | 2026-03-12T09:57:17.172+0500 | 2026-03-12T09:58:02.951+0500
DIGITALLOG | DIGITALLOG-330 | DIGITALLOG-330 | Sub-task | Sub-task |  | Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - AZ | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-330 | [5 empty] | 2026-03-13T10:54:15.425+0500 | 2026-03-13T15:33:45.934+0500
DIGITALLOG | DIGITALLOG-331 | DIGITALLOG-331 | Sub-task | Sub-task |  | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - AZ | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-331 | [5 empty] | 2026-03-13T10:54:23.195+0500 | 2026-03-18T09:31:18.163+0500
DIGITALLOG | DIGITALLOG-332 | DIGITALLOG-332 | Sub-task | Sub-task |  | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - AZ | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-332 | [5 empty] | 2026-03-13T10:54:28.475+0500 | 2026-03-24T09:34:16.465+0500
DIGITALLOG | DIGITALLOG-333 | DIGITALLOG-333 | Sub-task | Sub-task |  | Develop and test APIs for retrieving journal entry field data and remarks data by entry IDs. - AZ | Resolved! | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2026-03-25 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-333 | [5 empty] | 2026-03-13T10:54:33.952+0500 | 2026-03-25T15:45:44.906+0500
DIGITALLOG | DIGITALLOG-334 | DIGITALLOG-334 | Sub-task | Sub-task |  | UI Wrapper - Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - MA | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-334 | [5 empty] | 2026-03-18T12:27:34.127+0500 | 2026-03-18T12:29:14.617+0500
DIGITALLOG | DIGITALLOG-335 | DIGITALLOG-335 | Sub-task | Sub-task |  | UI Wrapper - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - MA | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-335 | [5 empty] | 2026-03-18T12:31:23.499+0500 | 2026-03-18T12:32:37.585+0500
DIGITALLOG | DIGITALLOG-336 | DIGITALLOG-336 | Sub-task | Sub-task |  | UI-Wrapper - Develop and validate APIs for fetching template version fields and template version field data with date range filtering. Develop and test APIs for retrieving journal entry field data and remarks data by entry IDs. - MA | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 8 | 8 | Muhammad Abdullah | 6.5 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-336 | [5 empty] | 2026-03-24T09:36:50.020+0500 | 2026-03-24T09:38:39.990+0500
DIGITALLOG | DIGITALLOG-337 | DIGITALLOG-337 | Sub-task | Sub-task |  | Testing and Retraining of LLM | Resolved! | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-18 | 24 | 24 | Muhammad Zeeshan Aslam | 19.5 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-337 | [5 empty] | 2026-03-24T11:16:40.134+0500 | 2026-04-02T11:46:33.139+0500
DIGITALLOG | DIGITALLOG-338 | DIGITALLOG-338 | Sub-task | Sub-task |  | Integrating comparison of tags reports | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 8 | 8 | Muhammad Zeeshan Aslam | 6.5 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-338 | [5 empty] | 2026-03-24T11:23:35.358+0500 | 2026-03-24T11:37:17.973+0500
DIGITALLOG | DIGITALLOG-339 | DIGITALLOG-339 | Sub-task | Sub-task |  | Research: Testing Omnichat with Postgress SQL | Resolved! | 2026-03-10 | 2026-03-12 | 2026-03-10 | 2026-03-12 | 24 | 24 | Muhammad Zeeshan Aslam | 19.5 |  | DIGITALLOG-235 | DIGITALLOG-235 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-235 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-339 | [5 empty] | 2026-03-24T11:33:25.980+0500 | 2026-03-24T11:35:45.359+0500
DIGITALLOG | DIGITALLOG-34 | DIGITALLOG-34 | Story | Story |  | Production Release | Resolved! | 2025-11-10 | 2025-11-10 |  |  | 32 | 32 | nadeem ahmed | 16 |  | DIGITALLOG-27 | DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-27 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-34 | [5 empty] | 2025-10-20T14:31:18.066+0500 | 2025-11-12T15:45:20.620+0500
DIGITALLOG | DIGITALLOG-340 | DIGITALLOG-340 | Sub-task | Sub-task |  | Email Notifications should be sending actual domain url | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2.5 | 2.5 | Arsalan Zafar Khan | 2.5 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-340 | [5 empty] | 2026-03-24T14:29:04.166+0500 | 2026-03-27T11:17:19.773+0500
DIGITALLOG | DIGITALLOG-341 | DIGITALLOG-341 | Sub-task | Sub-task |  | Testing by Zeeshan | Resolved! | 2026-03-25 | 2026-03-27 |  |  | 24 | 24 | Zeeshan Sarwar | 0 |  | DIGITALLOG-244 | DIGITALLOG-244 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-244 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-341 | [5 empty] | 2026-03-25T10:06:50.137+0500 | 2026-03-30T11:55:30.363+0500
DIGITALLOG | DIGITALLOG-342 | DIGITALLOG-342 | Bug Subtask | Bug Subtask |  | Able to select previous time in current day, where as it should be restricted to create a holiday in past dates or past time in current date. | Resolved | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 1 | 1 | Muhammad Abdullah | 1 |  | DIGITALLOG-298 | DIGITALLOG-298 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-298 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-342 | [5 empty] | 2026-03-25T10:41:35.305+0500 | 2026-03-26T11:57:51.989+0500
DIGITALLOG | DIGITALLOG-343 | DIGITALLOG-343 | Bug Subtask | Bug Subtask |  | Read API is only displaying active journals where as it should also display pending journals. | Resolved |  |  | 2026-03-26 | 2026-03-26 | 2 | 2 | Arsalan Zafar Khan | 2 |  | DIGITALLOG-297 | DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-343 | [5 empty] | 2026-03-25T14:50:50.680+0500 | 2026-03-30T11:57:23.277+0500
DIGITALLOG | DIGITALLOG-344 | DIGITALLOG-344 | Sub-task | Sub-task |  | Mobile App Octopusdtl Domain Switching Issue RCA - AZ | Resolved! | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-27 | 15 | 15 | Arsalan Zafar Khan | 15 |  | DIGITALLOG-297 | DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-344 | [5 empty] | 2026-03-26T14:58:17.010+0500 | 2026-03-27T16:34:43.709+0500
DIGITALLOG | DIGITALLOG-345 | DIGITALLOG-345 | Sub-task | Sub-task |  | Allow Same Section Name With Different Department | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2.5 | 2.5 | Arsalan Zafar Khan | 2.5 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-345 | [5 empty] | 2026-03-26T15:49:17.927+0500 | 2026-03-27T11:17:04.947+0500
DIGITALLOG | DIGITALLOG-346 | DIGITALLOG-346 | Bug Subtask | Bug Subtask |  | Input field in remarks option is not displaying properly to enter text in it. | Resolved | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 0.5 | 0.5 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-297 | DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-346 | [5 empty] | 2026-03-26T16:04:24.363+0500 | 2026-03-26T16:35:23.639+0500
DIGITALLOG | DIGITALLOG-347 | DIGITALLOG-347 | Bug Subtask | Bug Subtask |  | Count on review tab of journal is not displaying when opening application. | Resolved | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 1 | 1 | Muhammad Abdullah | 1 |  | DIGITALLOG-297 | DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-347 | [5 empty] | 2026-03-26T16:09:11.063+0500 | 2026-03-30T11:57:32.897+0500
DIGITALLOG | DIGITALLOG-348 | DIGITALLOG-348 | Bug Subtask | Bug Subtask |  | Open and closed journal status entries are not displaying with its previous and current values on web application. | Resolved | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 1 | 1 | Muhammad Abdullah | 1 |  | DIGITALLOG-297 | DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-348 | [5 empty] | 2026-03-26T16:24:00.782+0500 | 2026-03-30T11:57:35.364+0500
DIGITALLOG | DIGITALLOG-349 | DIGITALLOG-349 | Sub-task | Sub-task |  | Digital Log: Inhouse Training Session - 2 - AZ | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1 | 1 | Arsalan Zafar Khan | 1 |  | DIGITALLOG-317 | DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-349 | [5 empty] | 2026-03-27T11:12:26.437+0500 | 2026-03-27T11:13:05.901+0500
DIGITALLOG | DIGITALLOG-35 | DIGITALLOG-35 | Epic | Epic |  | Checklist Stats Enhancements + Dashboard User Activity Logs | Resolved! |  |  |  |  | 126.4 | 126.4 | nadeem ahmed | 669 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-35 | [5 empty] | 2025-10-20T14:36:30.354+0500 | 2026-04-27T16:43:05.656+0500
DIGITALLOG | DIGITALLOG-350 | DIGITALLOG-350 | Sub-task | Sub-task |  | Digital Log: Inhouse Training Session - 2 - NA | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 1 | 1 | nadeem ahmed | 1 |  | DIGITALLOG-317 | DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-317 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-350 | [5 empty] | 2026-03-27T16:47:42.726+0500 | 2026-03-30T09:29:20.727+0500
DIGITALLOG | DIGITALLOG-351 | DIGITALLOG-351 | Sub-task | Sub-task |  | Perform developer testing to validate holiday CRUD operations, overlapping range validations, and scheduler suppression behaviour during defined holiday periods. - NA | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-351 | [5 empty] | 2026-03-27T17:03:47.343+0500 | 2026-03-27T17:05:19.696+0500
DIGITALLOG | DIGITALLOG-352 | DIGITALLOG-352 | Sub-task | Sub-task |  | Update scheduler logging and monitoring to record skipped executions due to holidays, finalize Swagger documentation, and deploy changes to development for QA testing. - NA | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-352 | [5 empty] | 2026-03-27T17:06:26.173+0500 | 2026-03-27T17:07:23.443+0500
DIGITALLOG | DIGITALLOG-353 | DIGITALLOG-353 | Sub-task | Sub-task |  | Implement and test read APIs for retrieving all journal templates and template versions by template IDs. - NA | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-353 | [5 empty] | 2026-03-27T17:08:18.831+0500 | 2026-03-27T17:09:05.170+0500
DIGITALLOG | DIGITALLOG-354 | DIGITALLOG-354 | Sub-task | Sub-task |  | Enhance checklist scheduler service logic to check current execution time against configured holiday ranges and skip triggering if within range. - NA | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2 | 2 | nadeem ahmed | 2 |  | DIGITALLOG-243 | DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-243 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-354 | [5 empty] | 2026-03-27T17:10:37.916+0500 | 2026-03-27T17:11:31.351+0500
DIGITALLOG | DIGITALLOG-355 | DIGITALLOG-355 | Sub-task | Sub-task |  | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - NA | Resolved! | 2026-03-16 | 2026-03-17 | 2026-03-16 | 2026-03-17 | 16 | 16 | nadeem ahmed | 16 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-355 | [5 empty] | 2026-03-27T17:13:23.699+0500 | 2026-03-27T17:15:09.849+0500
DIGITALLOG | DIGITALLOG-356 | DIGITALLOG-356 | Sub-task | Sub-task |  | Develop and validate APIs for fetching template version fields and template version field data with date range filtering. - NA | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-270 | DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-270 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-356 | [5 empty] | 2026-03-27T17:16:26.146+0500 | 2026-03-27T17:17:24.055+0500
DIGITALLOG | DIGITALLOG-357 | DIGITALLOG-357 | Sub-task | Sub-task |  | Email Notifications should be sending actual domain url & Allow Same Section Name With Different Department - NA | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 7 | 7 | nadeem ahmed | 7 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-357 | [5 empty] | 2026-03-27T17:20:53.598+0500 | 2026-03-27T17:21:37.501+0500
DIGITALLOG | DIGITALLOG-358 | DIGITALLOG-358 | Sub-task | Sub-task |  | Mobile App Octopusdtl Domain Switching Issue | Resolved! | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-297 | DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-358 | [5 empty] | 2026-03-27T17:22:23.166+0500 | 2026-03-27T17:23:02.850+0500
DIGITALLOG | DIGITALLOG-359 | DIGITALLOG-359 | Sub-task | Sub-task |  | Mobile App Octopusdtl Domain Switching Issue RCA - MA | Resolved! | 2026-03-24 | 2026-03-26 | 2026-03-24 | 2026-03-26 | 24 | 24 | Muhammad Abdullah | 22.5 |  | DIGITALLOG-297 | DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-297 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-359 | [5 empty] | 2026-03-30T09:26:26.753+0500 | 2026-03-30T09:30:37.562+0500
DIGITALLOG | DIGITALLOG-36 | DIGITALLOG-36 | Story | Story |  | Checklist Stats Optimization and enhancement | Resolved! | 2025-11-11 | 2025-11-19 |  |  | 168 | 168 | nadeem ahmed | 136 |  | DIGITALLOG-35 | DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-36 | [5 empty] | 2025-10-20T14:37:03.567+0500 | 2025-12-26T09:57:30.865+0500
DIGITALLOG | DIGITALLOG-360 | DIGITALLOG-360 | Sub-task | Sub-task |  | Creation of DDS for Holidays Management Module | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-273 | DIGITALLOG-273 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-273 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-360 | [5 empty] | 2026-03-30T16:44:18.781+0500 | 2026-03-30T16:57:28.387+0500
DIGITALLOG | DIGITALLOG-361 | DIGITALLOG-361 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - AZ | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4 | 4 | Arsalan Zafar Khan | 4 |  | DIGITALLOG-242 | DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-361 | [5 empty] | 2026-03-30T16:45:52.131+0500 | 2026-03-30T16:46:40.618+0500
DIGITALLOG | DIGITALLOG-362 | DIGITALLOG-362 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - AZ | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4 | 4 | Arsalan Zafar Khan | 4 |  | DIGITALLOG-246 | DIGITALLOG-246 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-246 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-362 | [5 empty] | 2026-03-30T16:46:58.109+0500 | 2026-03-30T16:47:31.486+0500
DIGITALLOG | DIGITALLOG-363 | DIGITALLOG-363 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - MA | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4 | 4 | Muhammad Abdullah | 4 |  | DIGITALLOG-242 | DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-363 | [5 empty] | 2026-03-30T16:49:34.099+0500 | 2026-03-30T16:50:44.480+0500
DIGITALLOG | DIGITALLOG-364 | DIGITALLOG-364 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - MA | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4 | 4 | Muhammad Abdullah | 4 |  | DIGITALLOG-246 | DIGITALLOG-246 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-246 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-364 | [5 empty] | 2026-03-30T16:50:41.771+0500 | 2026-03-30T16:51:24.783+0500
DIGITALLOG | DIGITALLOG-365 | DIGITALLOG-365 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - NA | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-242 | DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-365 | [5 empty] | 2026-03-30T16:59:47.605+0500 | 2026-03-30T17:01:09.751+0500
DIGITALLOG | DIGITALLOG-366 | DIGITALLOG-366 | Story | Story |  | DDS | Resolved! | 2026-04-02 | 2026-04-02 |  |  | 8 | 8 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-366 | [5 empty] | 2026-03-31T14:38:27.523+0500 | 2026-04-29T14:08:46.195+0500
DIGITALLOG | DIGITALLOG-367 | DIGITALLOG-367 | Story | Story |  | QA Handover | Resolved! | 2026-04-09 | 2026-04-09 |  |  | 1 | 1 | Arsalan Zafar Khan | 1.5 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-367 | [5 empty] | 2026-03-31T14:38:54.302+0500 | 2026-04-10T11:43:12.958+0500
DIGITALLOG | DIGITALLOG-368 | DIGITALLOG-368 | Story | Story |  | QA Handover | Resolved! | 2026-04-23 | 2026-04-23 |  |  | 1 | 1 | Arsalan Zafar Khan | 1 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-368 | [5 empty] | 2026-03-31T14:41:34.554+0500 | 2026-04-23T15:26:25.371+0500
DIGITALLOG | DIGITALLOG-369 | DIGITALLOG-369 | Story | Story |  | DDS | Resolved! | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 12 | 12 | nadeem ahmed | 12 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-369 | [5 empty] | 2026-03-31T14:41:53.353+0500 | 2026-04-24T12:06:57.421+0500
DIGITALLOG | DIGITALLOG-37 | DIGITALLOG-37 | Story | Story |  | Custom Date Range in Checklist Stats | Resolved! | 2025-11-20 | 2025-11-21 |  |  | 48 | 48 | nadeem ahmed | 40 |  | DIGITALLOG-35 | DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-37 | [5 empty] | 2025-10-20T14:37:08.431+0500 | 2025-12-26T09:57:46.248+0500
DIGITALLOG | DIGITALLOG-370 | DIGITALLOG-370 | Story | Story |  | Bug Fixing | Resolved! | 2026-04-24 | 2026-04-27 |  |  | 3 | 3 | Arsalan Zafar Khan | 13.5 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-370 | [5 empty] | 2026-03-31T14:42:07.321+0500 | 2026-04-29T14:06:42.002+0500
DIGITALLOG | DIGITALLOG-371 | DIGITALLOG-371 | Story | Story |  | DDS | Resolved! | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-09 | 8 | 8 | nadeem ahmed | 8 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-371 | [5 empty] | 2026-03-31T14:42:28.572+0500 | 2026-04-24T11:26:32.070+0500
DIGITALLOG | DIGITALLOG-372 | DIGITALLOG-372 | Story | Story |  | Bug Fixing | Resolved! |  |  |  |  | 5 | 5 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-372 | [5 empty] | 2026-03-31T14:42:42.768+0500 | 2026-04-29T14:06:16.619+0500
DIGITALLOG | DIGITALLOG-373 | DIGITALLOG-373 | Story | Story |  | QA Handover | Resolved! | 2026-04-14 | 2026-04-14 |  |  | 1 | 1 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-373 | [5 empty] | 2026-03-31T14:42:57.057+0500 | 2026-04-23T15:33:57.544+0500
DIGITALLOG | DIGITALLOG-374 | DIGITALLOG-374 | Story | Story |  | QA Handover | To Do | 2026-04-17 | 2026-04-17 |  |  | 1 | 1 | Hassan Malik | 0 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-374 | [5 empty] | 2026-03-31T14:43:28.223+0500 | 2026-04-08T16:35:41.241+0500
DIGITALLOG | DIGITALLOG-375 | DIGITALLOG-375 | Story | Story |  | URS | Resolved! | 2026-04-01 | 2026-04-01 |  |  | 8 | 8 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-375 | [5 empty] | 2026-03-31T14:48:22.858+0500 | 2026-04-29T14:08:07.357+0500
DIGITALLOG | DIGITALLOG-376 | DIGITALLOG-376 | Story | Story |  | Bug Fixing | Resolved! |  |  |  |  | 3 | 3 | Arsalan Zafar Khan | 20 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | [5 empty] | 2026-03-31T14:49:43.612+0500 | 2026-04-29T14:04:12.356+0500
DIGITALLOG | DIGITALLOG-377 | DIGITALLOG-377 | Story | Story |  | URS | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 4 | 4 | nadeem ahmed | 4 |  | DIGITALLOG-223 | DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-377 | [5 empty] | 2026-03-31T15:01:03.573+0500 | 2026-04-22T09:56:42.643+0500
DIGITALLOG | DIGITALLOG-378 | DIGITALLOG-378 | Story | Story |  | General Training/Demo | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-218 | DIGITALLOG-218 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-218 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-378 | [5 empty] | 2026-04-01T09:34:58.687+0500 | 2026-04-01T09:34:59.643+0500
DIGITALLOG | DIGITALLOG-379 | DIGITALLOG-379 | Sub-task | Sub-task |  | Training Session ¦ Power of Mindset - AZ | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4 | 4 | Arsalan Zafar Khan | 4 |  | DIGITALLOG-378 | DIGITALLOG-378 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-378 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-379 | [5 empty] | 2026-04-01T09:35:34.812+0500 | 2026-04-01T09:39:22.454+0500
DIGITALLOG | DIGITALLOG-38 | DIGITALLOG-38 | Story | Story |  | SQA | Resolved! | 2025-12-22 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 120 | 120 | Zeeshan Sarwar | 112 |  | DIGITALLOG-35 | DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | [5 empty] | 2025-10-20T14:37:14.322+0500 | 2026-02-13T13:38:42.716+0500
DIGITALLOG | DIGITALLOG-380 | DIGITALLOG-380 | Sub-task | Sub-task |  | Allow Same Section Name With Different Department - Hot Fix Production Release and Post Production Verification. - AZ | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2 | 2 | Arsalan Zafar Khan | 2 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-380 | [5 empty] | 2026-04-01T09:42:53.372+0500 | 2026-04-01T09:43:48.457+0500
DIGITALLOG | DIGITALLOG-381 | DIGITALLOG-381 | Sub-task | Sub-task |  | Training Session ¦ Power of Mindset - MA | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4 | 4 | Muhammad Abdullah | 4 |  | DIGITALLOG-378 | DIGITALLOG-378 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-378 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-381 | [5 empty] | 2026-04-01T09:47:24.132+0500 | 2026-04-01T09:48:26.557+0500
DIGITALLOG | DIGITALLOG-382 | DIGITALLOG-382 | Sub-task | Sub-task |  | Allow Same Section Name With Different Department - Hot Fix Production Release and Post Production Verification. - MA | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4 | 4 | Muhammad Abdullah | 4 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-382 | [5 empty] | 2026-04-01T09:48:59.528+0500 | 2026-04-01T09:50:04.011+0500
DIGITALLOG | DIGITALLOG-383 | DIGITALLOG-383 | Story | Story |  | URS | Resolved! | 2026-04-13 | 2026-04-13 |  |  | 8 | 8 | Hassan Malik | 0 |  | DIGITALLOG-222 | DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-383 | [5 empty] | 2026-04-01T09:59:47.394+0500 | 2026-04-29T14:06:48.769+0500
DIGITALLOG | DIGITALLOG-384 | DIGITALLOG-384 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 15 | 15 | Muhammad Zeeshan Aslam | 0 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-384 | [5 empty] | 2026-04-01T11:06:39.971+0500 | 2026-04-01T11:10:06.274+0500
DIGITALLOG | DIGITALLOG-385 | DIGITALLOG-385 | Story | Story |  | URS | To Do | 2026-04-09 | 2026-04-09 |  |  | 4.8 | 4.8 | nadeem ahmed | 0 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-385 | [5 empty] | 2026-04-01T11:08:16.759+0500 | 2026-04-08T16:36:51.407+0500
DIGITALLOG | DIGITALLOG-386 | DIGITALLOG-386 | Story | Story |  | DDS | To Do | 2026-04-10 | 2026-04-13 |  |  | 8.8 | 8.8 | nadeem ahmed | 0 |  | DIGITALLOG-259 | DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-386 | [5 empty] | 2026-04-01T11:08:35.364+0500 | 2026-04-08T16:37:08.253+0500
DIGITALLOG | DIGITALLOG-387 | DIGITALLOG-387 | Sub-task | Sub-task |  | Design database schema changes to store return and re-approval parameter values along with comments history and traceability metadata. - AZ | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-387 | [5 empty] | 2026-04-01T14:18:23.648+0500 | 2026-04-02T10:07:39.138+0500
DIGITALLOG | DIGITALLOG-388 | DIGITALLOG-388 | Sub-task | Sub-task |  | Implement backend entities, DTOs, and repository layer to support storing and retrieving return and re-approval data. - AZ | Resolved! | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-388 | [5 empty] | 2026-04-01T14:18:34.511+0500 | 2026-04-03T15:52:53.765+0500
DIGITALLOG | DIGITALLOG-389 | DIGITALLOG-389 | Sub-task | Sub-task |  | Develop APIs to capture return actions with parameter values and user comments, including audit fields (user, timestamp). - AZ | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-389 | [5 empty] | 2026-04-01T14:18:43.594+0500 | 2026-04-06T10:35:14.873+0500
DIGITALLOG | DIGITALLOG-39 | DIGITALLOG-39 | Story | Story |  | Production Release | Resolved! | 2026-01-05 | 2026-01-06 | 2026-01-05 | 2026-01-06 | 48 | 48 | nadeem ahmed | 48 |  | DIGITALLOG-35 | DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-39 | [5 empty] | 2025-10-20T14:37:19.216+0500 | 2026-03-02T15:00:37.872+0500
DIGITALLOG | DIGITALLOG-390 | DIGITALLOG-390 | Sub-task | Sub-task |  | Implement APIs for re-approval workflow capturing updated parameter values and associated comments with version tracking. - AZ | Resolved! | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-390 | [5 empty] | 2026-04-01T14:18:52.237+0500 | 2026-04-07T10:06:14.330+0500
DIGITALLOG | DIGITALLOG-391 | DIGITALLOG-391 | Sub-task | Sub-task |  | Build service-layer logic to maintain full traceability history (who, when, what changes) for return and re-approval actions. - AZ | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-391 | [5 empty] | 2026-04-01T14:19:01.344+0500 | 2026-04-08T11:26:11.640+0500
DIGITALLOG | DIGITALLOG-392 | DIGITALLOG-392 | Sub-task | Sub-task |  | Perform developer testing to validate end-to-end traceability, data consistency, and audit history retrieval across return and re-approval scenarios. - AZ | Resolved! | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8 | 8 | Arsalan Zafar Khan | 6 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-392 | [5 empty] | 2026-04-01T14:19:10.530+0500 | 2026-04-09T09:10:01.435+0500
DIGITALLOG | DIGITALLOG-393 | DIGITALLOG-393 | Sub-task | Sub-task |  | Announcement Email Compilation | Resolved! | 2026-03-30 | 2026-03-30 | 2026-04-01 | 2026-04-01 | 1 | 1 | Hassan Malik | 1 |  | DIGITALLOG-242 | DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-242 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-393 | [5 empty] | 2026-04-02T09:55:29.482+0500 | 2026-04-02T09:57:03.330+0500
DIGITALLOG | DIGITALLOG-395 | DIGITALLOG-395 | Sub-task | Sub-task |  | Analyze UI requirements for Return/Re-Approval old vs new param value traceability across web and mobile applications. - MA | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-395 | [5 empty] | 2026-04-02T10:04:40.937+0500 | 2026-04-06T15:33:14.341+0500
DIGITALLOG | DIGITALLOG-396 | DIGITALLOG-396 | Sub-task | Sub-task |  | Identify Return/Re-Approval fields required for change comparison in web and mobile UI. - MA | Resolved! | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-396 | [5 empty] | 2026-04-02T10:06:11.777+0500 | 2026-04-06T15:58:57.240+0500
DIGITALLOG | DIGITALLOG-397 | DIGITALLOG-397 | Sub-task | Sub-task |  | Implement changed-field comparison logic for Return/Re-Approval params in web and mobile applications. - MA | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-397 | [5 empty] | 2026-04-02T10:07:11.936+0500 | 2026-04-06T15:59:41.765+0500
DIGITALLOG | DIGITALLOG-398 | DIGITALLOG-398 | Sub-task | Sub-task |  | Build traceability UI section to display old vs new parameter values in web and mobile applications. - MA | Resolved! | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-398 | [5 empty] | 2026-04-02T10:10:10.093+0500 | 2026-04-07T11:22:53.785+0500
DIGITALLOG | DIGITALLOG-399 | DIGITALLOG-399 | Sub-task | Sub-task |  | Render comments with corresponding Return/Re-Approval param changes in web and mobile UI. - MA | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-399 | [5 empty] | 2026-04-02T10:11:33.886+0500 | 2026-04-09T12:07:58.999+0500
DIGITALLOG | DIGITALLOG-4 | DIGITALLOG-4 | Story | Story |  | SQA | Resolved! | 2025-10-06 | 2025-10-09 |  |  | 32 | 32 | Zeeshan Sarwar | 22 |  | DIGITALLOG-1 | DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-4 | [5 empty] | 2025-10-06T14:08:43.043+0500 | 2026-02-26T14:58:00.797+0500
DIGITALLOG | DIGITALLOG-400 | DIGITALLOG-400 | Sub-task | Sub-task |  | Validate web and mobile UI rendering for Return/Re-Approval value comparison and comments traceability. - MA | Resolved! | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-247 | DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-247 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-400 | [5 empty] | 2026-04-02T10:12:32.468+0500 | 2026-04-09T12:08:35.898+0500
DIGITALLOG | DIGITALLOG-401 | DIGITALLOG-401 | Sub-task | Sub-task |  | Update the pie chart logic in logchat | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-401 | [5 empty] | 2026-04-02T11:48:19.390+0500 | 2026-04-02T11:51:29.278+0500
DIGITALLOG | DIGITALLOG-402 | DIGITALLOG-402 | Sub-task | Sub-task |  | Adding statistical analysis in logchat | Resolved! | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-27 | 24 | 24 | Muhammad Zeeshan Aslam | 24 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-402 | [5 empty] | 2026-04-02T11:49:04.456+0500 | 2026-04-02T11:53:31.404+0500
DIGITALLOG | DIGITALLOG-403 | DIGITALLOG-403 | Sub-task | Sub-task |  | Creating dataset (checklists) and testing on production | Resolved! | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 16 | 16 | Muhammad Zeeshan Aslam | 16 |  | DIGITALLOG-272 | DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-272 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-403 | [5 empty] | 2026-04-02T11:50:20.221+0500 | 2026-04-02T11:55:19.295+0500
DIGITALLOG | DIGITALLOG-404 | DIGITALLOG-404 | Sub-task | Sub-task |  | User Manual | Resolved! | 2026-03-25 | 2026-03-27 | 2026-04-02 | 2026-04-02 | 4 | 4 | Hassan Malik | 1 |  | DIGITALLOG-245 | DIGITALLOG-245 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-245 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-404 | [5 empty] | 2026-04-02T16:37:43.442+0500 | 2026-04-02T16:38:28.637+0500
DIGITALLOG | DIGITALLOG-405 | DIGITALLOG-405 | Sub-task | Sub-task |  | Design and implement backend data model and APIs to support digital signature requests, signer details, and document status tracking. | Resolved! | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-255 | DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-405 | [5 empty] | 2026-04-09T10:54:07.801+0500 | 2026-04-10T11:41:42.216+0500
DIGITALLOG | DIGITALLOG-406 | DIGITALLOG-406 | Sub-task | Sub-task |  | Update existing submit and approver endpoints to incorporate digital signature validation, capture signer details, and persist signature metadata with audit trail. | Resolved! | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-13 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-255 | DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-406 | [5 empty] | 2026-04-09T10:54:22.107+0500 | 2026-04-14T15:23:02.183+0500
DIGITALLOG | DIGITALLOG-407 | DIGITALLOG-407 | Sub-task | Sub-task |  | Perform developer testing and integrate digital signature workflow with checklist modules ensuring security, validation, and end-to-end traceability. | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-255 | DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-407 | [5 empty] | 2026-04-09T10:54:36.102+0500 | 2026-04-15T10:03:44.612+0500
DIGITALLOG | DIGITALLOG-408 | DIGITALLOG-408 | Sub-task | Sub-task |  | Handover to QA - AZ | Resolved! | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 0.5 | 0.5 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-373 | DIGITALLOG-373 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-373 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-408 | [5 empty] | 2026-04-10T11:40:07.625+0500 | 2026-04-23T15:34:18.272+0500
DIGITALLOG | DIGITALLOG-409 | DIGITALLOG-409 | Sub-task | Sub-task |  | Handover to QA - AZ | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5 | 0.5 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-367 | DIGITALLOG-367 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-367 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-409 | [5 empty] | 2026-04-10T11:43:22.084+0500 | 2026-04-10T11:43:59.679+0500
DIGITALLOG | DIGITALLOG-41 | DIGITALLOG-41 | Story | Story |  | User Activity Logs + Dashboards | Resolved! | 2025-11-24 | 2025-12-19 |  |  | 480 | 480 | nadeem ahmed | 341 |  | DIGITALLOG-35 | DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-41 | [5 empty] | 2025-10-20T14:37:59.098+0500 | 2026-01-16T16:06:42.706+0500
DIGITALLOG | DIGITALLOG-410 | DIGITALLOG-410 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-04-13 | 2026-04-29 | 2026-04-13 | 2026-04-29 | 40 | 40 | kamran khalid | 46 |  | DIGITALLOG-248 | DIGITALLOG-248 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-248 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-410 | [5 empty] | 2026-04-13T15:19:50.389+0500 | 2026-05-12T15:44:59.068+0500
DIGITALLOG | DIGITALLOG-413 | DIGITALLOG-413 | Task | Task |  | Change Texts on the Timestamp Labels and correct the Signature label Alignment | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1 | 1 | Muhammad Abdullah | 1 |  | DIGITALLOG-221 | DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-413 | [5 empty] | 2026-04-14T12:04:13.626+0500 | 2026-04-15T15:56:04.819+0500
DIGITALLOG | DIGITALLOG-414 | DIGITALLOG-414 | Sub-task | Sub-task |  | Handover session Digital Log | Resolved! |  |  | 2026-04-09 | 2026-04-09 | 1 | 1 | kamran khalid | 0.5 |  | DIGITALLOG-367 | DIGITALLOG-367 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-367 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-414 | [5 empty] | 2026-04-14T14:46:11.823+0500 | 2026-04-14T14:47:36.970+0500
DIGITALLOG | DIGITALLOG-416 | DIGITALLOG-416 | Sub-task | Sub-task |  | Design database schema and backend models to support user-defined checklist scheduling with configurable execution times and frequency - AZ | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-416 | [5 empty] | 2026-04-15T10:42:28.917+0500 | 2026-04-17T10:01:47.116+0500
DIGITALLOG | DIGITALLOG-417 | DIGITALLOG-417 | Sub-task | Sub-task |  | Implement APIs to create and update checklist schedules with user-specified time, timezone handling, and validation rules - AZ | Resolved! | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-417 | [5 empty] | 2026-04-15T10:45:22.860+0500 | 2026-04-17T10:15:54.934+0500
DIGITALLOG | DIGITALLOG-418 | DIGITALLOG-418 | Sub-task | Sub-task |  | Develop API to retrieve checklist schedules with filtering and organization-level configuration support - AZ | Resolved! | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-418 | [5 empty] | 2026-04-15T10:45:36.495+0500 | 2026-04-21T10:30:29.901+0500
DIGITALLOG | DIGITALLOG-419 | DIGITALLOG-419 | Sub-task | Sub-task |  | Enhance scheduler service to trigger checklists based on user-defined times and integrate with existing scheduling framework - AZ | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-419 | [5 empty] | 2026-04-15T10:45:45.557+0500 | 2026-04-22T12:28:01.089+0500
DIGITALLOG | DIGITALLOG-420 | DIGITALLOG-420 | Sub-task | Sub-task |  | Perform developer testing to validate scheduling accuracy, timezone consistency, and edge cases (missed triggers, overlaps, holiday conflicts) - AZ | Resolved! | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 8 | 8 | Arsalan Zafar Khan | 13.5 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-420 | [5 empty] | 2026-04-15T10:46:07.283+0500 | 2026-04-24T11:13:12.659+0500
DIGITALLOG | DIGITALLOG-421 | DIGITALLOG-421 | Sub-task | Sub-task |  | Implement e-signature enablement on Web including checklist builder toggle, list filters/badges, submission & review modals with signature capture, and signature display via API. - MA | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 8 | 8 | Muhammad Abdullah | 9.5 |  | DIGITALLOG-255 | DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-421 | [5 empty] | 2026-04-15T14:49:50.715+0500 | 2026-04-15T15:18:22.061+0500
DIGITALLOG | DIGITALLOG-422 | DIGITALLOG-422 | Sub-task | Sub-task |  | Implement e-signature functionality on Mobile (React Native) including checklist filters/badges, submission & review modals with signature capture, and signature display via API. - MA | Resolved! | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 8 | 8 | Muhammad Abdullah | 11 |  | DIGITALLOG-255 | DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-422 | [5 empty] | 2026-04-15T14:50:20.973+0500 | 2026-04-15T15:21:33.849+0500
DIGITALLOG | DIGITALLOG-423 | DIGITALLOG-423 | Sub-task | Sub-task |  | Integrate e-signature APIs across Web and Mobile, ensuring payload handling, signature retrieval, and visualization in checklist and data modules. - MA | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-255 | DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-255 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-423 | [5 empty] | 2026-04-15T14:51:00.813+0500 | 2026-04-15T15:23:26.642+0500
DIGITALLOG | DIGITALLOG-424 | DIGITALLOG-424 | Sub-task | Sub-task |  | Handover to QA - MA | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5 | 0.5 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-367 | DIGITALLOG-367 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-367 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-424 | [5 empty] | 2026-04-15T14:55:18.553+0500 | 2026-04-15T14:56:23.274+0500
DIGITALLOG | DIGITALLOG-425 | DIGITALLOG-425 | Sub-task | Sub-task |  | Code to fetch the Confluence File and store in vector store | Resolved! | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 24 | 24 | Muhammad Zeeshan Aslam | 24 |  | DIGITALLOG-260 | DIGITALLOG-260 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-260 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-425 | [5 empty] | 2026-04-16T10:59:22.381+0500 | 2026-04-17T09:38:59.690+0500
DIGITALLOG | DIGITALLOG-426 | DIGITALLOG-426 | Sub-task | Sub-task |  | Integrate User manual/confluence file vector store in the Log chat | Resolved! | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-07 | 16 | 16 | Muhammad Zeeshan Aslam | 16 |  | DIGITALLOG-260 | DIGITALLOG-260 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-260 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-426 | [5 empty] | 2026-04-16T11:01:28.838+0500 | 2026-04-17T09:42:11.968+0500
DIGITALLOG | DIGITALLOG-427 | DIGITALLOG-427 | Sub-task | Sub-task |  | Investigate and resolve SSL compatibility issues affecting backward compatibility on older Android mobile app versions. - AZ | Resolved! | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-427 | [5 empty] | 2026-04-21T10:32:34.612+0500 | 2026-04-21T10:33:21.789+0500
DIGITALLOG | DIGITALLOG-428 | DIGITALLOG-428 | Sub-task | Sub-task |  | Investigate and resolve SSL compatibility issues affecting backward compatibility on older Android mobile app versions. - MA | Resolved! | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-428 | [5 empty] | 2026-04-23T09:28:06.874+0500 | 2026-04-23T09:29:02.174+0500
DIGITALLOG | DIGITALLOG-429 | DIGITALLOG-429 | Sub-task | Sub-task |  | Refactor checklist builder UI by replacing Scheduled/Non-Scheduled checkboxes with a dropdown (Scheduled, Non-Scheduled, Time-based) and default to Non-Scheduled. - MA | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8 | 8 | Muhammad Abdullah | 7 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-429 | [5 empty] | 2026-04-23T09:40:10.514+0500 | 2026-04-23T09:41:26.637+0500
DIGITALLOG | DIGITALLOG-430 | DIGITALLOG-430 | Sub-task | Sub-task |  | Implement dynamic UI behavior to show/hide scheduling controls based on selected dropdown option, including new time-based inputs. - MA | Resolved! | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-430 | [5 empty] | 2026-04-23T09:42:02.405+0500 | 2026-04-23T09:43:05.814+0500
DIGITALLOG | DIGITALLOG-431 | DIGITALLOG-431 | Sub-task | Sub-task |  | Update scheduling API payload to support the new Time-based option and ensure proper data handling for all scheduling types. - MA | Resolved! | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-251 | DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-251 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-431 | [5 empty] | 2026-04-23T09:43:47.263+0500 | 2026-04-23T09:44:37.195+0500
DIGITALLOG | DIGITALLOG-432 | DIGITALLOG-432 | Bug Subtask | Bug Subtask |  | Checklist Name is appearing instead of Approver Name | Resolved |  |  | 2026-04-24 | 2026-04-24 | 0 | 0 | kamran khalid | 2 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-432 | [5 empty] | 2026-04-23T12:30:19.566+0500 | 2026-04-28T10:30:55.873+0500
DIGITALLOG | DIGITALLOG-433 | DIGITALLOG-433 | Bug Subtask | Bug Subtask |  | HEADER NOT RESPONSIVE | Bug Fixed | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 1.5 | 1.5 | Muhammad Abdullah | 1.5 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-433 | [5 empty] | 2026-04-23T12:33:02.096+0500 | 2026-04-24T15:43:43.884+0500
DIGITALLOG | DIGITALLOG-434 | DIGITALLOG-434 | Bug Subtask | Bug Subtask |  | Refresh button is not loading latest data into the list | Resolved | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2 | 2 | Muhammad Abdullah | 2 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-434 | [5 empty] | 2026-04-23T12:34:43.588+0500 | 2026-04-30T10:18:33.360+0500
DIGITALLOG | DIGITALLOG-435 | DIGITALLOG-435 | Bug Subtask | Bug Subtask |  | Permission issue for my user as i installed the new version of the mobile app | Bug Fixed | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2.67 | 2.67 | Muhammad Abdullah | 2.67 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-435 | [5 empty] | 2026-04-23T12:36:36.561+0500 | 2026-04-30T10:02:39.435+0500
DIGITALLOG | DIGITALLOG-437 | DIGITALLOG-437 | Sub-task | Sub-task |  | Handover to QA - AZ | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5 | 0.5 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-368 | DIGITALLOG-368 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-368 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-437 | [5 empty] | 2026-04-23T15:30:24.780+0500 | 2026-04-23T15:30:59.721+0500
DIGITALLOG | DIGITALLOG-438 | DIGITALLOG-438 | Sub-task | Sub-task |  | Newly created checklists do not appear at the top, and there is no filter available to sort by creation time. | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2 | 2 | Muhammad Abdullah | 2 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-438 | [5 empty] | 2026-04-24T16:33:32.624+0500 | 2026-04-30T10:16:39.740+0500
DIGITALLOG | DIGITALLOG-439 | DIGITALLOG-439 | Bug Subtask | Bug Subtask |  | Time-based scheduled checklist activation fails on the first attempt. However, after changing the checklist type from "Time Based" to "Scheduled", the activation succeeds, including validation through developer testing | Resolved | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 4 | 4 | Muhammad Abdullah | 4 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-439 | [5 empty] | 2026-04-24T17:10:34.161+0500 | 2026-04-30T10:10:30.661+0500
DIGITALLOG | DIGITALLOG-440 | DIGITALLOG-440 | Bug Subtask | Bug Subtask |  | Time-based checklist is not triggering according to the 24-hour format, even after multiple screen refresh attempts. | Development |  |  | 2026-04-27 | 2026-04-27 | 0 | 0 | Arsalan Zafar Khan | 0.5 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-440 | [5 empty] | 2026-04-24T17:16:49.627+0500 | 2026-04-28T10:29:46.386+0500
DIGITALLOG | DIGITALLOG-441 | DIGITALLOG-441 | Sub-task | Sub-task |  | E-Signature field should be Mandatory on web and mobile | Resolved! |  |  | 2026-04-27 | 2026-04-27 | 2.67 | 2.67 | Muhammad Abdullah | 2.67 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-441 | [5 empty] | 2026-04-27T12:22:40.708+0500 | 2026-04-30T10:01:22.010+0500
DIGITALLOG | DIGITALLOG-442 | DIGITALLOG-442 | Bug Subtask | Bug Subtask |  | Checklist gets activated when Start Time and End Time are identical (zero-duration window not validated) | Resolved | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2.67 | 2.67 | Muhammad Abdullah | 2.67 |  | DIGITALLOG-376 | DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-376 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-442 | [5 empty] | 2026-04-27T13:44:28.219+0500 | 2026-04-30T10:03:39.784+0500
DIGITALLOG | DIGITALLOG-443 | DIGITALLOG-443 | Epic | Epic |  | Enhance User Access Rights at granular level of Create, Read, Update, Delete like OmniConnect | To Do |  |  |  |  | 272 | 272 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-443 | [5 empty] | 2026-04-27T16:19:28.161+0500 | 2026-04-27T16:20:41.990+0500
DIGITALLOG | DIGITALLOG-444 | DIGITALLOG-444 | Epic | Epic |  | Email text formatting | To Do |  |  |  |  | 57.6 | 57.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-444 | [5 empty] | 2026-04-27T16:21:33.705+0500 | 2026-04-27T16:22:02.719+0500
DIGITALLOG | DIGITALLOG-445 | DIGITALLOG-445 | Epic | Epic |  | Notifications (desktop) at due, overdue checklist(s) | To Do |  |  |  |  | 222.4 | 222.4 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-445 | [5 empty] | 2026-04-27T16:22:42.638+0500 | 2026-04-27T16:23:11.075+0500
DIGITALLOG | DIGITALLOG-446 | DIGITALLOG-446 | Epic | Epic |  | Mobile App iOS | To Do |  |  |  |  | 46.4 | 46.4 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-446 | [5 empty] | 2026-04-27T16:25:23.868+0500 | 2026-04-27T16:37:10.529+0500
DIGITALLOG | DIGITALLOG-447 | DIGITALLOG-447 | Epic | Epic |  | DL Default Reports | To Do |  |  |  |  | 149.6 | 149.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-447 | [5 empty] | 2026-04-27T16:26:07.226+0500 | 2026-04-27T16:26:30.973+0500
DIGITALLOG | DIGITALLOG-448 | DIGITALLOG-448 | Epic | Epic |  | Journals for Mobile iOS | To Do |  |  |  |  | 100 | 100 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-448 | [5 empty] | 2026-04-27T16:27:01.743+0500 | 2026-04-27T16:37:58.813+0500
DIGITALLOG | DIGITALLOG-449 | DIGITALLOG-449 | Epic | Epic |  | Reports list is not available/viewable in tablet portrait mode | To Do |  |  |  |  | 23.2 | 23.2 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-449 | [5 empty] | 2026-04-27T16:27:19.254+0500 | 2026-04-27T16:27:36.435+0500
DIGITALLOG | DIGITALLOG-45 | DIGITALLOG-45 | Story | Story |  | abc | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-45 | [5 empty] | 2025-10-21T10:27:01.774+0500 | 2026-02-25T14:29:29.844+0500
DIGITALLOG | DIGITALLOG-450 | DIGITALLOG-450 | Epic | Epic |  | User Remarks Traceability | To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-450 | [5 empty] | 2026-04-27T16:28:00.092+0500 | 2026-04-27T16:28:00.285+0500
DIGITALLOG | DIGITALLOG-451 | DIGITALLOG-451 | Epic | Epic |  | DL Analytics (Dependent upon client need & Data) | To Do |  |  |  |  | 138.4 | 138.4 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-451 | [5 empty] | 2026-04-27T16:28:24.450+0500 | 2026-04-27T16:28:37.199+0500
DIGITALLOG | DIGITALLOG-452 | DIGITALLOG-452 | Epic | Epic |  | Calculated tags | To Do |  |  |  |  | 192 | 192 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-452 | [5 empty] | 2026-04-27T16:29:00.214+0500 | 2026-04-27T16:39:14.237+0500
DIGITALLOG | DIGITALLOG-453 | DIGITALLOG-453 | Epic | Epic |  | LogChat - Data Analysis | To Do |  |  |  |  | 126.4 | 126.4 | Muhammad Zeeshan Aslam | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-453 | [5 empty] | 2026-04-27T16:30:05.449+0500 | 2026-04-27T16:30:27.531+0500
DIGITALLOG | DIGITALLOG-454 | DIGITALLOG-454 | Epic | Epic |  | Attachments at remarks from approver1, approver2 | To Do |  |  |  |  | 76.8 | 76.8 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-454 | [5 empty] | 2026-04-27T16:30:11.134+0500 | 2026-04-27T16:39:33.302+0500
DIGITALLOG | DIGITALLOG-455 | DIGITALLOG-455 | Epic | Epic |  | DL Trial on WebSite | To Do |  |  |  |  | 241.6 | 241.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-455 | [5 empty] | 2026-04-27T16:31:24.481+0500 | 2026-04-27T16:31:39.441+0500
DIGITALLOG | DIGITALLOG-456 | DIGITALLOG-456 | Epic | Epic |  | Delete option to admin (to delete unclaimed checklists) Data Collector -> Inbox | To Do |  |  |  |  | 49.6 | 49.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-456 | [5 empty] | 2026-04-27T16:31:53.717+0500 | 2026-04-27T16:39:51.596+0500
DIGITALLOG | DIGITALLOG-457 | DIGITALLOG-457 | Epic | Epic |  | Triggering of checklist instance on some event (we have scheduled checklist feature & it is triggered on given frequency) | To Do |  |  |  |  | 126.4 | 126.4 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-457 | [5 empty] | 2026-04-27T16:32:25.667+0500 | 2026-04-27T16:32:35.782+0500
DIGITALLOG | DIGITALLOG-458 | DIGITALLOG-458 | Epic | Epic |  | Attachment pic with each Checklist (, audio, video, pdf, etc) | To Do |  |  |  |  | 64.8 | 64.8 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-458 | [5 empty] | 2026-04-27T16:32:47.202+0500 | 2026-04-27T16:40:10.836+0500
DIGITALLOG | DIGITALLOG-459 | DIGITALLOG-459 | Epic | Epic |  | Validation of Values to be within defined threshold | To Do |  |  |  |  | 57.6 | 57.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-459 | [5 empty] | 2026-04-27T16:33:41.614+0500 | 2026-04-27T16:40:26.692+0500
DIGITALLOG | DIGITALLOG-46 | DIGITALLOG-46 | Bug Subtask | Bug Subtask |  | Correct list of checklist are not displaying when they are returned in bulk through mobile app. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | DIGITALLOG-26 | DIGITALLOG-26 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-26 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-46 | [5 empty] | 2025-10-22T10:13:33.569+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-460 | DIGITALLOG-460 | Epic | Epic |  | Automated Triggered O&M Actions | To Do |  |  |  |  | 111.2 | 111.2 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-460 | [5 empty] | 2026-04-27T16:33:45.392+0500 | 2026-04-27T16:33:56.840+0500
DIGITALLOG | DIGITALLOG-461 | DIGITALLOG-461 | Epic | Epic |  | Import & export of assets hierarchy | To Do |  |  |  |  | 145.6 | 145.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-461 | [5 empty] | 2026-04-27T16:34:30.723+0500 | 2026-04-27T16:42:18.691+0500
DIGITALLOG | DIGITALLOG-462 | DIGITALLOG-462 | Epic | Epic |  | Bulk creation of parameters through importing CSV file(s) (User can develop a template of parameters and then can use for multiple areas/assets) | To Do |  |  |  |  | 126.4 | 126.4 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-462 | [5 empty] | 2026-04-27T16:35:25.410+0500 | 2026-04-27T16:35:42.536+0500
DIGITALLOG | DIGITALLOG-463 | DIGITALLOG-463 | Epic | Epic |  | Import & export of checklists | To Do |  |  |  |  | 145.6 | 145.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-463 | [5 empty] | 2026-04-27T16:35:55.888+0500 | 2026-04-27T16:42:37.102+0500
DIGITALLOG | DIGITALLOG-464 | DIGITALLOG-464 | Epic | Epic |  | Request for Digital Log Usage Dashboard Report | To Do |  |  |  |  | 195.2 | 195.2 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-464 | [5 empty] | 2026-04-28T09:40:52.208+0500 | 2026-04-28T09:41:21.788+0500
DIGITALLOG | DIGITALLOG-466 | DIGITALLOG-466 | Bug Subtask | Bug Subtask |  | Update checklist scheduling logic to ensure triggers occur only after the configured checklist start time, including validation and developer testing for edge cases - AZ | Bug Fixed | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 8 | 8 | Arsalan Zafar Khan | 7.5 |  | DIGITALLOG-370 | DIGITALLOG-370 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-370 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-466 | [5 empty] | 2026-04-28T10:35:57.615+0500 | 2026-04-28T10:40:48.959+0500
DIGITALLOG | DIGITALLOG-467 | DIGITALLOG-467 | Bug Subtask | Bug Subtask |  | Fix checklist scheduling logic to preserve original start time and prevent schedule shifts during checklist deactivation and reactivation, including validation through developer testing - AZ | Bug Fixed | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 6 | 6 | Arsalan Zafar Khan | 6 |  | DIGITALLOG-370 | DIGITALLOG-370 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-370 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-467 | [5 empty] | 2026-04-28T10:39:06.525+0500 | 2026-04-28T10:40:17.507+0500
DIGITALLOG | DIGITALLOG-468 | DIGITALLOG-468 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - AZ | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67 | 2.67 | Arsalan Zafar Khan | 2.67 |  | DIGITALLOG-250 | DIGITALLOG-250 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-250 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-468 | [5 empty] | 2026-04-29T14:03:11.489+0500 | 2026-04-29T14:10:25.324+0500
DIGITALLOG | DIGITALLOG-469 | DIGITALLOG-469 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - AZ | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67 | 2.67 | Arsalan Zafar Khan | 2.67 |  | DIGITALLOG-254 | DIGITALLOG-254 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-254 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-469 | [5 empty] | 2026-04-29T14:04:27.875+0500 | 2026-04-29T14:10:46.209+0500
DIGITALLOG | DIGITALLOG-47 | DIGITALLOG-47 | Bug Subtask | Bug Subtask |  | Date format parameter value is displaying in data visualizer with some random long integer value. | Resolved |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-32 | DIGITALLOG-32 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-32 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-47 | [5 empty] | 2025-11-03T11:21:01.449+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-470 | DIGITALLOG-470 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - AZ | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67 | 2.67 | Arsalan Zafar Khan | 2.67 |  | DIGITALLOG-258 | DIGITALLOG-258 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-258 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-470 | [5 empty] | 2026-04-29T14:05:21.820+0500 | 2026-04-29T14:11:08.608+0500
DIGITALLOG | DIGITALLOG-471 | DIGITALLOG-471 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - MA | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67 | 2.67 | Muhammad Abdullah | 2.67 |  | DIGITALLOG-258 | DIGITALLOG-258 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-258 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-471 | [5 empty] | 2026-04-30T09:38:42.822+0500 | 2026-04-30T09:40:34.986+0500
DIGITALLOG | DIGITALLOG-472 | DIGITALLOG-472 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - MA | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.67 | 2.67 | Muhammad Abdullah | 2.67 |  | DIGITALLOG-254 | DIGITALLOG-254 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-254 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-472 | [5 empty] | 2026-04-30T09:41:16.683+0500 | 2026-04-30T09:42:06.241+0500
DIGITALLOG | DIGITALLOG-473 | DIGITALLOG-473 | Sub-task | Sub-task |  | Production Deployment & Post-Deployment Verification. - MA | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2.5 | 2.5 | Muhammad Abdullah | 2.67 |  | DIGITALLOG-250 | DIGITALLOG-250 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-250 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-473 | [5 empty] | 2026-04-30T09:42:57.601+0500 | 2026-04-30T09:56:33.591+0500
DIGITALLOG | DIGITALLOG-474 | DIGITALLOG-474 | Sub-task | Sub-task |  | Handover to QA - MA | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5 | 0.5 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-368 | DIGITALLOG-368 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-368 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-474 | [5 empty] | 2026-04-30T10:20:33.377+0500 | 2026-04-30T10:22:46.021+0500
DIGITALLOG | DIGITALLOG-475 | DIGITALLOG-475 | Epic | Epic |  | Enhanced search functionality with dropdown-based filtering across the application | To Do |  |  |  |  | 64.8 | 64.8 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-475 | [5 empty] | 2026-04-30T11:48:22.667+0500 | 2026-04-30T11:48:47.410+0500
DIGITALLOG | DIGITALLOG-476 | DIGITALLOG-476 | Epic | Epic |  | Image integration in checklist PDF export for Review and Data Visualization screens. | To Do |  |  |  |  | 64.8 | 64.8 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-476 | [5 empty] | 2026-04-30T11:49:26.472+0500 | 2026-04-30T11:49:49.233+0500
DIGITALLOG | DIGITALLOG-477 | DIGITALLOG-477 | Epic | Epic |  | Configurable email notifications for checklist statuses (assigned, approved, returned, rejected, etc.). | To Do |  |  |  |  | 141.6 | 141.6 | Arsalan Zafar Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-477 | [5 empty] | 2026-04-30T11:50:26.283+0500 | 2026-04-30T11:50:48.927+0500
DIGITALLOG | DIGITALLOG-478 | DIGITALLOG-478 | Sub-task | Sub-task |  | Bug fixing, communication with clients/customers and meeting within team | To Do |  |  | 2026-05-05 | 2026-05-05 | 0 | 0 | nadeem ahmed | 8 |  | DIGITALLOG-237 | DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-237 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-478 | [5 empty] | 2026-05-05T16:55:10.784+0500 | 2026-05-05T16:55:43.643+0500
DIGITALLOG | DIGITALLOG-48 | DIGITALLOG-48 | Story | Story |  | User Manual | To Do | 2025-12-22 | 2026-01-02 |  |  | 16 | 16 | Hassan Malik | 0 |  | DIGITALLOG-35 | DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-35 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-48 | [5 empty] | 2025-12-11T09:36:30.611+0500 | 2026-02-20T09:46:21.220+0500
DIGITALLOG | DIGITALLOG-49 | DIGITALLOG-49 | Bug Subtask | Bug Subtask |  | Irrelevant information is displaying in tabs of count present on starting of activity stats page. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-49 | [5 empty] | 2025-12-24T14:55:11.708+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-5 | DIGITALLOG-5 | Story | Story |  | Production Release | Resolved! | 2025-10-10 | 2025-10-10 |  |  | 24 | 24 | nadeem ahmed | 16 |  | DIGITALLOG-1 | DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-5 | [5 empty] | 2025-10-06T14:08:47.824+0500 | 2026-02-26T14:58:31.702+0500
DIGITALLOG | DIGITALLOG-50 | DIGITALLOG-50 | Bug Subtask | Bug Subtask |  | Backend programming language is displaying against update activity of template structure. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 2 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-50 | [5 empty] | 2025-12-24T14:58:38.827+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-51 | DIGITALLOG-51 | Bug Subtask | Bug Subtask |  | Format of date and time in any activity update is not correct. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-51 | [5 empty] | 2025-12-24T15:03:27.306+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-52 | DIGITALLOG-52 | Bug Subtask | Bug Subtask |  | Module name that is created, updated or deleted should display first and then its entity should display in brackets while viewing its details. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-52 | [5 empty] | 2025-12-29T10:14:41.252+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-53 | DIGITALLOG-53 | Bug Subtask | Bug Subtask |  | Department name is not displaying correct after creating a section. | Resolved |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-53 | [5 empty] | 2025-12-29T10:24:32.486+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-54 | DIGITALLOG-54 | Bug Subtask | Bug Subtask |  | Checklist update activity is automatically triggered where as only group is updated. | Resolved |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-54 | [5 empty] | 2025-12-29T10:58:46.909+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-55 | DIGITALLOG-55 | Bug Subtask | Bug Subtask |  | Dept and section for data visualization checkbox is not selected when clicking on select all option while creating or updating role. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-55 | [5 empty] | 2025-12-29T11:23:55.462+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-56 | DIGITALLOG-56 | Bug Subtask | Bug Subtask |  | Role ID and other details are displaying while viewing user create activity. | Resolved |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-56 | [5 empty] | 2025-12-29T11:55:33.257+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-57 | DIGITALLOG-57 | Bug Subtask | Bug Subtask |  | Holiday declared in organizational management is not displaying with its date in activity stats screen. | Resolved |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-57 | [5 empty] | 2025-12-29T14:28:02.944+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-58 | DIGITALLOG-58 | Bug Subtask | Bug Subtask |  | Activity detail done in hierarchy builder is not displaying where as its count is displaying. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-58 | [5 empty] | 2025-12-30T10:25:36.018+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-59 | DIGITALLOG-59 | Bug Subtask | Bug Subtask |  | Activity of parameter creation in asset builder is displaying as creating it in template. | Resolved |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-59 | [5 empty] | 2025-12-30T11:50:37.244+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-6 | DIGITALLOG-6 | Story | Story |  | User Manual | Resolved! | 2025-10-06 | 2025-10-09 |  |  | 32 | 32 | Hassan Malik | 56 |  | DIGITALLOG-1 | DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-1 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-6 | [5 empty] | 2025-10-07T11:56:08.847+0500 | 2026-02-26T14:58:18.894+0500
DIGITALLOG | DIGITALLOG-60 | DIGITALLOG-60 | Bug Subtask | Bug Subtask |  | Required toggle activate/deactivate activity is with only type change description where as input type is not changed. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-60 | [5 empty] | 2025-12-30T12:12:23.306+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-61 | DIGITALLOG-61 | Bug Subtask | Bug Subtask |  | Location or asset is not displaying for selection again while configuring checklist after it is removed one time. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-61 | [5 empty] | 2025-12-31T10:52:10.481+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-62 | DIGITALLOG-62 | Bug Subtask | Bug Subtask |  | Start and end date as well as frequency changings are not displaying in checklist details on activity stats screen. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 1 |  | DIGITALLOG-38 | DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-38 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-62 | [5 empty] | 2025-12-31T12:05:16.880+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-65 | DIGITALLOG-65 | Epic | Epic |  | Digital Log Enhancements & Integration | Resolved! | 2026-01-07 | 2026-02-20 |  |  | 320 | 320 | Arsalan Zafar Khan | 16 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | [5 empty] | 2026-01-09T15:04:08.293+0500 | 2026-02-26T10:55:28.342+0500
DIGITALLOG | DIGITALLOG-66 | DIGITALLOG-66 | Story | Story |  | Development | Resolved! | 2026-01-07 | 2026-01-13 |  |  | 80 | 80 | Arsalan Zafar Khan | 120 |  | DIGITALLOG-192 | DIGITALLOG-192 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-192 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | [5 empty] | 2026-01-09T15:04:19.800+0500 | 2026-02-20T12:31:38.719+0500
DIGITALLOG | DIGITALLOG-67 | DIGITALLOG-67 | Story | Story |  | DEV: Default Reports (Research & Definition) | Resolved! | 2026-01-09 | 2026-01-13 | 2026-01-12 | 2026-01-13 | 24 | 24 | Arsalan Zafar Khan | 16 |  | DIGITALLOG-65 | DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-67 | [5 empty] | 2026-01-09T15:04:24.904+0500 | 2026-02-10T11:27:26.947+0500
DIGITALLOG | DIGITALLOG-68 | DIGITALLOG-68 | Story | Story |  | Development | Resolved! | 2026-01-14 | 2026-01-22 |  |  | 168 | 168 | Arsalan Zafar Khan | 168 |  | DIGITALLOG-146 | DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-146 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | [5 empty] | 2026-01-09T15:04:38.928+0500 | 2026-02-10T09:27:13.136+0500
DIGITALLOG | DIGITALLOG-69 | DIGITALLOG-69 | Story | Story |  | Development | Resolved! | 2026-01-23 | 2026-02-06 |  |  | 240 | 240 | Arsalan Zafar Khan | 208 |  | DIGITALLOG-150 | DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-150 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-69 | [5 empty] | 2026-01-09T15:12:28.774+0500 | 2026-02-13T15:48:35.623+0500
DIGITALLOG | DIGITALLOG-7 | DIGITALLOG-7 | Sub-task | Sub-task |  | Confluence Migration - Web App | Resolved! | 2025-10-01 | 2025-10-03 |  |  | 24 | 24 | Maria Sharafat | 44 |  | DIGITALLOG-6 | DIGITALLOG-6 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-6 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-7 | [5 empty] | 2025-10-07T16:06:03.172+0500 | 2025-12-11T10:07:39.730+0500
DIGITALLOG | DIGITALLOG-70 | DIGITALLOG-70 | Story | Story |  | Development | On Hold | 2026-02-09 | 2026-02-12 |  |  | 96 | 96 | Arsalan Zafar Khan | 118 |  | DIGITALLOG-154 | DIGITALLOG-154 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-154 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-70 | [5 empty] | 2026-01-09T15:12:33.683+0500 | 2026-02-20T12:30:37.002+0500
DIGITALLOG | DIGITALLOG-71 | DIGITALLOG-71 | Story | Story |  | SQA | In-Progress | 2026-02-13 | 2026-02-19 |  |  | 160 | 160 | Zeeshan Sarwar | 103.5 |  | DIGITALLOG-65 | DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-71 | [5 empty] | 2026-01-09T15:12:46.091+0500 | 2026-02-11T12:58:32.237+0500
DIGITALLOG | DIGITALLOG-72 | DIGITALLOG-72 | Story | Story |  | User Manual/Documentation | On Hold | 2026-02-13 | 2026-02-19 |  |  | 8 | 8 | Hassan Malik | 8 |  | DIGITALLOG-65 | DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-72 | [5 empty] | 2026-01-09T15:12:51.129+0500 | 2026-03-02T13:50:26.004+0500
DIGITALLOG | DIGITALLOG-73 | DIGITALLOG-73 | Story | Story |  | Production Release | To Do | 2026-02-20 | 2026-02-20 |  |  | 32 | 32 | Arsalan Zafar Khan | 0 |  | DIGITALLOG-65 | DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-65 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-73 | [5 empty] | 2026-01-09T15:12:54.655+0500 | 2026-01-13T15:32:21.331+0500
DIGITALLOG | DIGITALLOG-8 | DIGITALLOG-8 | Sub-task | Sub-task |  | Confluence - Mobile App | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 12 |  | DIGITALLOG-6 | DIGITALLOG-6 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-6 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-8 | [5 empty] | 2025-10-07T16:06:13.436+0500 | 2025-10-14T11:58:45.665+0500
DIGITALLOG | DIGITALLOG-82 | DIGITALLOG-82 | Sub-task | Sub-task |  | Get All Checklists API - Retrieves a complete list of checklists accessible to the authenticated user. - AZ | Resolved! | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-82 | [5 empty] | 2026-01-16T15:17:21.956+0500 | 2026-01-22T10:51:26.668+0500
DIGITALLOG | DIGITALLOG-83 | DIGITALLOG-83 | Sub-task | Sub-task |  | Get Tags for Multiple Checklists API - Fetches associated tags for one or more specified checklists in a single request. - AZ | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-83 | [5 empty] | 2026-01-16T15:17:29.864+0500 | 2026-01-22T10:50:50.055+0500
DIGITALLOG | DIGITALLOG-84 | DIGITALLOG-84 | Sub-task | Sub-task |  | Get Tag Data by Date Range API - Returns historical tag data within a specified start and end date range. - AZ | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-84 | [5 empty] | 2026-01-16T15:17:35.918+0500 | 2026-01-22T10:57:58.865+0500
DIGITALLOG | DIGITALLOG-85 | DIGITALLOG-85 | Sub-task | Sub-task |  | Get Tag Data by Date Range with Tags Filter API - Retrieves tag data for a defined date range filtered by selected tag(s). - AZ | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-85 | [5 empty] | 2026-01-16T15:17:41.188+0500 | 2026-01-22T10:53:20.173+0500
DIGITALLOG | DIGITALLOG-86 | DIGITALLOG-86 | Sub-task | Sub-task |  | User Authorization for Read API (Backend) - Implements backend-level authorization to control and validate user access to Read APIs. - AZ | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-86 | [5 empty] | 2026-01-16T15:17:46.076+0500 | 2026-01-22T10:54:27.855+0500
DIGITALLOG | DIGITALLOG-87 | DIGITALLOG-87 | Sub-task | Sub-task |  | User Authorization for Read API (Frontend) - Enforces frontend access control to expose Read API features based on user roles and permissions. - MA | Resolved! | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-87 | [5 empty] | 2026-01-16T15:17:55.458+0500 | 2026-01-22T10:34:23.227+0500
DIGITALLOG | DIGITALLOG-88 | DIGITALLOG-88 | Sub-task | Sub-task |  | UI Wrapper - Get All Checklists – Implement frontend wrapper/service to securely call and display data from the Get All Checklists API via public domain. - MA | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-88 | [5 empty] | 2026-01-16T15:21:26.441+0500 | 2026-01-22T10:35:09.694+0500
DIGITALLOG | DIGITALLOG-89 | DIGITALLOG-89 | Sub-task | Sub-task |  | UI Wrapper - Get Tags for Multiple Checklists – Develop frontend wrapper to invoke the API and present tags for selected multiple checklists. - MA | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-89 | [5 empty] | 2026-01-16T15:21:31.989+0500 | 2026-01-22T10:36:14.346+0500
DIGITALLOG | DIGITALLOG-9 | DIGITALLOG-9 | Bug Subtask | Bug Subtask |  | No option is selected by default when organizational management is selected in creating or editing a role. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0.5 |  | DIGITALLOG-2 | DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-2 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-9 | [5 empty] | 2025-10-07T12:20:47.349+0500 | 2026-02-11T12:26:26.161+0500
DIGITALLOG | DIGITALLOG-90 | DIGITALLOG-90 | Sub-task | Sub-task |  | UI Wrapper - Get Tag Data by Date Range – Create UI wrapper to fetch and visualize tag data based on user-selected date range. - MA | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-90 | [5 empty] | 2026-01-16T15:21:38.016+0500 | 2026-01-22T10:38:04.453+0500
DIGITALLOG | DIGITALLOG-91 | DIGITALLOG-91 | Sub-task | Sub-task |  | UI Wrapper - Get Tag Data by Date Range with Tags Filter – Implement frontend wrapper to call the API with date range and tag filters and render filtered results. - MA | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-91 | [5 empty] | 2026-01-16T15:21:46.413+0500 | 2026-01-22T10:39:01.799+0500
DIGITALLOG | DIGITALLOG-92 | DIGITALLOG-92 | Sub-task | Sub-task |  | Requirement Understanding & Analysis - AZ | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Arsalan Zafar Khan | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-92 | [5 empty] | 2026-01-16T15:39:29.799+0500 | 2026-02-10T11:28:46.069+0500
DIGITALLOG | DIGITALLOG-93 | DIGITALLOG-93 | Sub-task | Sub-task |  | UI/UX Design & Architecture - MA | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-93 | [5 empty] | 2026-01-16T15:39:47.549+0500 | 2026-01-22T10:49:29.068+0500
DIGITALLOG | DIGITALLOG-94 | DIGITALLOG-94 | Sub-task | Sub-task |  | Core UI Development - MA | Resolved! | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-94 | [5 empty] | 2026-01-16T15:40:05.907+0500 | 2026-01-22T10:49:33.805+0500
DIGITALLOG | DIGITALLOG-95 | DIGITALLOG-95 | Sub-task | Sub-task |  | Integration of Log Chat Apis - MA | Resolved! | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-95 | [5 empty] | 2026-01-16T15:40:15.829+0500 | 2026-01-22T10:49:37.883+0500
DIGITALLOG | DIGITALLOG-96 | DIGITALLOG-96 | Sub-task | Sub-task |  | Dev Testing - Verify all features function correctly and ensure statistical data aligns accurately with the Digital Log (DL) application - MA | Resolved! | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-96 | [5 empty] | 2026-01-16T15:40:37.648+0500 | 2026-01-22T10:22:47.692+0500
DIGITALLOG | DIGITALLOG-97 | DIGITALLOG-97 | Sub-task | Sub-task |  | Creation of read-only users to securely access client databases without modification privileges. - AZ | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2 | 2 | Arsalan Zafar Khan | 2 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-97 | [5 empty] | 2026-01-16T15:49:26.623+0500 | 2026-01-22T10:46:47.461+0500
DIGITALLOG | DIGITALLOG-98 | DIGITALLOG-98 | Sub-task | Sub-task |  | UI Wrapper - Get All Tags Hierarchy – Implement frontend wrapper/service to securely call and display data from the Get Hierarchy Tags API via public domain. - MA | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-68 | DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-68 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-98 | [5 empty] | 2026-01-21T13:42:31.700+0500 | 2026-01-22T10:40:57.792+0500
DIGITALLOG | DIGITALLOG-99 | DIGITALLOG-99 | Sub-task | Sub-task |  | Requirement Understanding & Analysis - MA | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Muhammad Abdullah | 8 |  | DIGITALLOG-66 | DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-66 | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-99 | [5 empty] | 2026-01-22T10:12:41.812+0500 | 2026-01-22T10:17:23.881+0500
FF | FF-1 | FF-1 | Epic | Epic |  | Fintech Fuel: Version 1 | To Do |  |  |  |  | 0 | 0 | awais akhter | 159 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-1 | [5 empty] | 2025-10-03T19:40:10.630+0500 | 2025-10-08T12:25:14.387+0500
FF | FF-10 | FF-10 | Story | Story |  | Sales Targets | Resolved! | 2025-09-26 | 2025-10-02 |  |  | 8 | 8 | Ameer Hamza Khan | 58 |  | FF-7 | FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-10 | [5 empty] | 2025-10-03T19:43:53.180+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-100 | FF-100 | Bug Subtask | Bug Subtask |  | The Filter on the Transaction page is not working correctly as i have applied filter the data for "PUMP_4" but its showing data of other pumps too | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-100 | [5 empty] | 2025-10-14T09:38:09.783+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-101 | FF-101 | Bug Subtask | Bug Subtask |  | ON the Nozzle usage page in the table the customer name is showing instead of site in the column "site name" | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.75 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-101 | [5 empty] | 2025-10-14T09:38:42.440+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-102 | FF-102 | Bug Subtask | Bug Subtask |  | The filter functionality is not consistent across pages. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-102 | [5 empty] | 2025-10-14T09:39:23.956+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-103 | FF-103 | Bug Subtask | Bug Subtask |  | The purpose of the filter on the Loss Gain Chart page is unclear, as it’s currently not functioning. The filter appears inactive, while the Loss Gain Chart itself is working correctly and displaying data. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-103 | [5 empty] | 2025-10-14T09:39:49.604+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-104 | FF-104 | Bug Subtask | Bug Subtask |  | 1. Remove datetime range control 2. Show respective tank name 3. Control to toggle view between tank / product wise display in Stock Level pages Pages | Request received |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-104 | [5 empty] | 2025-10-14T09:41:30.738+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-105 | FF-105 | Sub-task | Sub-task |  | Floating value display on column and show units as well like PKR, Ltr etc 1. Volume, 2. Money, and 3. PPU in Transaction page | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 1.33 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-105 | [5 empty] | 2025-10-14T09:42:44.827+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-106 | FF-106 | Sub-task | Sub-task |  | Icon needs to be replaced with appropriate icon in "per week target", "Daily average target" cards, | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 0.42 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-106 | [5 empty] | 2025-10-14T09:44:07.197+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-107 | FF-107 | Bug Subtask | Bug Subtask |  | Mock targets are being displayed | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-107 | [5 empty] | 2025-10-14T09:44:43.659+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-108 | FF-108 | Sub-task | Sub-task |  | FuelChat - DE API | To Do |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 296 |  | FF-97 | FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-108 | [5 empty] | 2025-10-14T09:56:56.267+0500 | 2026-01-01T16:47:54.672+0500
FF | FF-109 | FF-109 | Sub-task | Sub-task |  | Manual Tank Delivery Recon | In-Progress |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 40 |  | FF-17 | FF-17 | https://octopusdtlsupport.atlassian.net/browse/FF-17 | https://octopusdtlsupport.atlassian.net/browse/FF-109 | [5 empty] | 2025-10-14T14:48:52.926+0500 | 2026-02-11T12:32:16.755+0500
FF | FF-11 | FF-11 | Story | Story |  | Sudden Loss | Resolved! | 2025-09-26 | 2025-09-30 |  |  | 8 | 8 | Ameer Hamza Khan | 16 |  | FF-7 | FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-11 | [5 empty] | 2025-10-03T19:44:01.331+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-110 | FF-110 | Bug Subtask | Bug Subtask |  | On the Loss Gain Chart page the tank level filter is not working | Resolved | 2025-10-16 | 2025-10-17 |  |  | 8 | 8 | kamran khalid | 3.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-110 | [5 empty] | 2025-10-16T10:36:05.517+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-111 | FF-111 | Sub-task | Sub-task |  | User Manual | In-Progress |  |  |  |  | 0 | 0 | kamran khalid | 13 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-111 | [5 empty] | 2025-10-16T20:30:15.356+0500 | 2026-02-11T12:32:16.755+0500
FF | FF-118 | FF-118 | Story | Story |  | User Manual | Resolved! | 2025-10-29 | 2025-10-30 |  |  | 0 | 0 | Hassan Malik | 52 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-118 | [5 empty] | 2025-11-03T16:58:35.436+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-119 | FF-119 | Epic | Epic |  | Mobile App | On Hold | 2025-11-17 | 2026-02-12 |  |  | 560 | 560 | Sarmad Sabir | 191 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-119 | [5 empty] | 2025-12-01T15:51:16.238+0500 | 2026-02-20T10:39:04.457+0500
FF | FF-12 | FF-12 | Story | Story |  | Alarms | Resolved! | 2025-10-05 | 2025-10-08 |  |  | 32 | 32 | kamran khalid | 53 |  | FF-7 | FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-12 | [5 empty] | 2025-10-03T19:44:03.683+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-120 | FF-120 | Story | Story |  | Development | On Hold | 2025-11-24 | 2025-12-31 |  |  | 320 | 320 | Sarmad Sabir | 298 |  | FF-119 | FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | [5 empty] | 2025-12-01T15:51:30.894+0500 | 2026-02-11T16:02:12.627+0500
FF | FF-121 | FF-121 | Story | Story |  | SQA-Fintech Mobile App | In-Progress | 2026-01-08 | 2026-02-12 | 2026-01-07 | 2026-01-30 | 200 | 200 | Namra Zahid | 232.83 |  | FF-119 | FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | [5 empty] | 2025-12-01T15:51:33.510+0500 | 2026-03-04T10:10:01.123+0500
FF | FF-122 | FF-122 | Story | Story |  | User Manual | Resolved! | 2026-01-01 | 2026-01-15 | 2026-01-05 | 2026-01-06 | 32 | 32 | Hassan Malik | 16 |  | FF-119 | FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-122 | [5 empty] | 2025-12-01T15:51:38.926+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-123 | FF-123 | Story | Story |  | Production Release | To Do | 2026-01-16 | 2026-01-16 |  |  | 32 | 32 | Sarmad Sabir | 0 |  | FF-119 | FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-119 | https://octopusdtlsupport.atlassian.net/browse/FF-123 | [5 empty] | 2025-12-01T15:51:44.071+0500 | 2026-01-09T10:30:31.080+0500
FF | FF-124 | FF-124 | Task | Task |  | Fintech Portal Regression | To Do |  |  | 2026-01-01 | 2026-01-01 | 0 | 0 | Namra Zahid | 154 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-124 | [5 empty] | 2025-12-02T10:20:11.581+0500 | 2026-01-01T15:57:28.272+0500
FF | FF-125 | FF-125 | Task | Task |  | Fintech Dashboard Regression | In-Progress |  |  | 2026-01-01 | 2026-01-15 | 0 | 0 | Waqar Rasheed | 297.75 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-125 | [5 empty] | 2025-12-02T10:20:13.056+0500 | 2026-02-11T12:32:15.145+0500
FF | FF-127 | FF-127 | Bug Subtask | Bug Subtask |  | Dashboard> Hi Super and Excellium colors do not match between the tank display and the graph. | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-127 | [5 empty] | 2025-12-02T11:18:49.346+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-128 | FF-128 | Bug Subtask | Bug Subtask |  | Dashboard> No character limit is applied on Username/Email and Password fields across the application. | Resolved | 2025-12-02 | 2025-12-02 | 2026-01-16 | 2026-01-16 | 16 | 16 | Muhammad Usman Javed | 12 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-128 | [5 empty] | 2025-12-02T12:34:59.839+0500 | 2026-02-20T16:47:16.244+0500
FF | FF-129 | FF-129 | Bug Subtask | Bug Subtask |  | Expire time and Resend code button is not showing on OTP popup | Resolved | 2025-12-02 | 2025-12-03 | 2026-01-15 | 2026-01-15 | 0 | 0 | Muhammad Usman Javed | 12 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-129 | [5 empty] | 2025-12-02T12:43:15.495+0500 | 2026-02-12T11:06:42.955+0500
FF | FF-13 | FF-13 | Story | Story |  | SQA | Resolved! | 2025-10-09 | 2025-10-16 |  |  | 40 | 40 | kamran khalid | 166.33 |  | FF-7 | FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | [5 empty] | 2025-10-06T14:07:56.754+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-130 | FF-130 | Bug Subtask | Bug Subtask |  | OTP is not expired even after 3 minutes | Resolved | 2025-12-02 | 2025-12-03 | 2026-01-14 | 2026-01-14 | 16 | 16 | Muhammad Usman Javed | 12 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-130 | [5 empty] | 2025-12-02T14:07:35.067+0500 | 2026-02-20T16:42:38.534+0500
FF | FF-131 | FF-131 | Bug Subtask | Bug Subtask |  | Spelling mistake "Occurred" should be, instead of "Occured". | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 1.5 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-131 | [5 empty] | 2025-12-03T11:16:00.890+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-132 | FF-132 | Bug Subtask | Bug Subtask |  | Dashboard> Update password validation message and add view/hide icon on Reset Password screen wherever there are password fields | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-132 | [5 empty] | 2025-12-03T15:31:52.341+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-133 | FF-133 | Sub-task | Sub-task |  | Dashboard> Current Password field is missing on the Reset password screen | Resolved! | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-133 | [5 empty] | 2025-12-03T15:46:14.281+0500 | 2026-03-10T11:39:05.321+0500
FF | FF-134 | FF-134 | Sub-task | Sub-task |  | Portal Forgot Password: Current password is getting saved as in New Password and Confirm Password | To Do |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-134 | [5 empty] | 2025-12-03T15:54:16.617+0500 | 2025-12-11T11:27:14.212+0500
FF | FF-135 | FF-135 | Sub-task | Sub-task |  | User is redirected to Reset Password page after clicking the Activate Account button | On Hold |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-135 | [5 empty] | 2025-12-03T16:21:16.300+0500 | 2026-02-25T10:52:08.831+0500
FF | FF-136 | FF-136 | Bug Subtask | Bug Subtask |  | When a user access the forgot password feature of the portal,they are landed on a page where their password is changed for the dashboard.After logging in, the dashboard is accessible,but not the portal.“Signing up,also changing the password for both. | Not a Bug |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-136 | [5 empty] | 2025-12-04T10:59:16.315+0500 | 2025-12-05T09:56:13.316+0500
FF | FF-137 | FF-137 | Sub-task | Sub-task |  | Replace Site ID with Site Name across the application and add Product Name with Tank Name on the Alarms screen | Resolved! |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 2 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-137 | [5 empty] | 2025-12-04T14:10:34.894+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-138 | FF-138 | Sub-task | Sub-task |  | Remove "Resolved" option from Status dropdown on Alarms screen | Resolved! |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-138 | [5 empty] | 2025-12-04T14:11:26.114+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-139 | FF-139 | Bug Subtask | Bug Subtask |  | The staging dashboard is not loading correctly. | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-139 | [5 empty] | 2025-12-04T15:50:40.064+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-14 | FF-14 | Story | Story |  | Production Release | Resolved! | 2025-10-17 | 2025-10-17 |  |  | 8 | 8 | Ameer Hamza Khan | 3 |  | FF-7 | FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-14 | [5 empty] | 2025-10-06T14:08:00.748+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-140 | FF-140 | Bug Subtask | Bug Subtask |  | Unable to Configure a site Kindly check, Blocker for us | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-140 | [5 empty] | 2025-12-08T10:43:48.973+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-141 | FF-141 | Story | Story |  | Fintech PPT for management | Resolved! |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 24 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-141 | [5 empty] | 2025-12-08T11:56:04.604+0500 | 2026-02-13T12:21:41.173+0500
FF | FF-142 | FF-142 | Sub-task | Sub-task |  | PPT for management for Current usage of azure | To Do |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 24 |  | FF-141 | FF-141 | https://octopusdtlsupport.atlassian.net/browse/FF-141 | https://octopusdtlsupport.atlassian.net/browse/FF-142 | [5 empty] | 2025-12-08T11:56:54.415+0500 | 2025-12-08T11:58:32.849+0500
FF | FF-143 | FF-143 | Bug Subtask | Bug Subtask |  | Transactions: While selecting Pum_16 , Its allowing user to select Pump_1,2,3 with nozzle and so on. | QA Testing |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 2 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-143 | [5 empty] | 2025-12-09T12:13:22.248+0500 | 2026-02-11T12:32:07.287+0500
FF | FF-144 | FF-144 | Bug Subtask | Bug Subtask |  | User is Unable to change a Customer, after assigning a custom role, FOR EVERY SCREEN OF Dashboard. | Resolved | 2025-12-09 | 2025-12-11 |  |  | 0 | 0 | Muhammad Usman Javed | 3 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-144 | [5 empty] | 2025-12-09T14:38:16.590+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-145 | FF-145 | Bug Subtask | Bug Subtask |  | Non Existing Role : "Submit Portal" | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-145 | [5 empty] | 2025-12-09T14:55:16.445+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-146 | FF-146 | Bug Subtask | Bug Subtask |  | While View Permissions are off and Create Permission is on, It is displaying all menu options of dashboard. Same For All Edit Permissions as on view permissions | QA Testing | 2025-12-09 | 2025-12-11 |  |  | 0 | 0 | Muhammad Usman Javed | 2 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-146 | [5 empty] | 2025-12-09T14:56:57.851+0500 | 2026-02-11T12:32:07.287+0500
FF | FF-147 | FF-147 | Bug Subtask | Bug Subtask |  | Inactive Customer is being available or selected which we didn't assigned to this user. | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 3 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-147 | [5 empty] | 2025-12-10T10:33:53.554+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-148 | FF-148 | Bug Subtask | Bug Subtask |  | ‘Select Role’ Field Is Not Marked as Required on User Create/Update | Resolved | 2026-02-13 | 2026-02-13 | 2026-01-13 | 2026-01-13 | 16 | 16 | Muhammad Usman Javed | 10 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-148 | [5 empty] | 2025-12-11T11:38:06.792+0500 | 2026-02-20T16:42:02.871+0500
FF | FF-149 | FF-149 | Bug Subtask | Bug Subtask |  | Old Logo Is Displaying on System Emails (Account Activation, OTP Verification, Forgot Password) | Resolved | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 0.5 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-149 | [5 empty] | 2025-12-11T12:02:57.891+0500 | 2026-02-27T10:39:13.143+0500
FF | FF-15 | FF-15 | Sub-task | Sub-task |  | SP modification (Bug reported) | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 10 |  | FF-10 | FF-10 | https://octopusdtlsupport.atlassian.net/browse/FF-10 | https://octopusdtlsupport.atlassian.net/browse/FF-15 | [5 empty] | 2025-10-08T10:36:20.130+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-150 | FF-150 | Bug Subtask | Bug Subtask |  | Critical : Day End Sales Summary on Transactions. | QA Testing | 2025-12-11 |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-150 | [5 empty] | 2025-12-11T12:48:13.323+0500 | 2026-02-11T12:32:07.287+0500
FF | FF-151 | FF-151 | Sub-task | Sub-task |  | Configuration Portal Updates | In-Progress |  |  |  |  | 0 | 0 | Hassan Malik | 12 |  | FF-118 | FF-118 | https://octopusdtlsupport.atlassian.net/browse/FF-118 | https://octopusdtlsupport.atlassian.net/browse/FF-151 | [5 empty] | 2025-12-11T15:32:11.786+0500 | 2026-02-11T12:32:15.802+0500
FF | FF-152 | FF-152 | Sub-task | Sub-task |  | Error message is not displayed under the respective field while creating a user. | To Do |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-152 | [5 empty] | 2025-12-16T14:33:14.823+0500 | 2025-12-16T14:37:33.200+0500
FF | FF-153 | FF-153 | Sub-task | Sub-task |  | All cities should be shown under respective region while creating or editing a site | Resolved! |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 1 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-153 | [5 empty] | 2025-12-18T15:14:57.187+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-154 | FF-154 | Bug Subtask | Bug Subtask |  | For Adnan Chaudhary’s customer site Palace View FS, the products do not have any color set on the portal, but on the dashboard the products of Palace View FS are displayed with colors. | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 4 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-154 | [5 empty] | 2025-12-22T16:39:14.612+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-155 | FF-155 | Bug Subtask | Bug Subtask |  | For CALTEX_BE’s customer site Pine Avenue, the Diesel product color is blue on the portal, but it appears orange on the dashboard. The color should be consistent on both. | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 2 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-155 | [5 empty] | 2025-12-22T16:48:07.559+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-156 | FF-156 | Bug Subtask | Bug Subtask |  | The date on the X-axis gets hidden when the user hovers over the chart. This issue occurs on all charts across the dashboard. | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 2 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-156 | [5 empty] | 2025-12-23T10:09:22.937+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-157 | FF-157 | Story | Story |  | Fuelchat Enhancements | Resolved! | 2026-01-01 | 2026-01-30 |  |  | 160 | 160 | Hassan Saeed Wattoo | 116 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-157 | [5 empty] | 2025-12-29T12:43:25.550+0500 | 2026-02-19T11:27:49.765+0500
FF | FF-158 | FF-158 | Bug Subtask | Bug Subtask |  | While editing a pump and reconfigure its mapping, mapping gets removed after saving it. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-158 | [5 empty] | 2025-12-30T15:04:13.533+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-159 | FF-159 | Sub-task | Sub-task |  | Login Page | Resolved! | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 8 | 8 | Sarmad Sabir | 4 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-159 | [5 empty] | 2026-01-01T10:31:35.362+0500 | 2026-02-12T16:41:09.897+0500
FF | FF-16 | FF-16 | Epic | Epic |  | Fintech Fuel : Version 3 | To Do |  |  |  |  | 0 | 0 | awais akhter | 217 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-16 | [5 empty] | 2025-10-03T19:44:17.608+0500 | 2026-03-30T12:02:37.159+0500
FF | FF-160 | FF-160 | Sub-task | Sub-task |  | Forgot Password Screen | Resolved! | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-06 | 8 | 8 | Sarmad Sabir | 8 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-160 | [5 empty] | 2026-01-01T10:31:58.006+0500 | 2026-02-25T10:45:19.051+0500
FF | FF-161 | FF-161 | Sub-task | Sub-task |  | Dashboard Home Page | Resolved! | 2025-12-03 | 2025-12-04 |  |  | 0 | 0 | Sarmad Sabir | 24 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-161 | [5 empty] | 2026-01-01T10:43:33.524+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-162 | FF-162 | Sub-task | Sub-task |  | Alarms Page | Resolved! | 2025-12-08 | 2025-12-09 |  |  | 0 | 0 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-162 | [5 empty] | 2026-01-01T10:43:44.587+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-163 | FF-163 | Sub-task | Sub-task |  | Deliveries Page | Resolved! | 2025-12-10 | 2025-12-11 |  |  | 0 | 0 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-163 | [5 empty] | 2026-01-01T10:43:55.566+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-164 | FF-164 | Sub-task | Sub-task |  | Transactions Page | Resolved! | 2025-12-12 | 2025-12-15 |  |  | 0 | 0 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-164 | [5 empty] | 2026-01-01T10:44:04.407+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-165 | FF-165 | Sub-task | Sub-task |  | Reconciliation Report Page | Resolved! | 2025-12-18 | 2025-12-19 |  |  | 0 | 0 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-165 | [5 empty] | 2026-01-01T10:44:17.447+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-166 | FF-166 | Sub-task | Sub-task |  | Loss & Gain Charts Page | Resolved! | 2025-12-22 | 2025-12-23 |  |  | 0 | 0 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-166 | [5 empty] | 2026-01-01T10:44:32.142+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-167 | FF-167 | Sub-task | Sub-task |  | Sales Target Page | Resolved! | 2025-12-26 | 2025-12-29 |  |  | 0 | 0 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-167 | [5 empty] | 2026-01-01T10:44:48.077+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-168 | FF-168 | Sub-task | Sub-task |  | Stock Management Page | Resolved! | 2025-12-05 | 2025-12-05 |  |  | 0 | 0 | Sarmad Sabir | 8 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-168 | [5 empty] | 2026-01-01T10:44:59.776+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-169 | FF-169 | Sub-task | Sub-task |  | Nozzle Usage Page | Resolved! | 2025-12-16 | 2025-12-16 |  |  | 0 | 0 | Sarmad Sabir | 8 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-169 | [5 empty] | 2026-01-01T10:45:14.276+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-17 | FF-17 | Story | Story |  | Manual Entry Portal | Resolved! | 2025-10-21 | 2025-10-27 |  |  | 40 | 40 | Ameer Hamza Khan | 56 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-17 | [5 empty] | 2025-10-03T19:44:29.448+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-170 | FF-170 | Sub-task | Sub-task |  | FuelChat | Resolved! | 2025-12-24 | 2025-12-24 |  |  | 0 | 0 | Sarmad Sabir | 8 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-170 | [5 empty] | 2026-01-01T10:45:24.933+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-171 | FF-171 | Sub-task | Sub-task |  | Crash Fixes | Resolved! | 2025-12-30 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 16 | 16 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-171 | [5 empty] | 2026-01-01T10:45:38.832+0500 | 2026-03-04T13:05:34.082+0500
FF | FF-172 | FF-172 | Sub-task | Sub-task |  | Optimization for Responsiveness | Resolved! | 2025-12-31 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 16 | 16 | Sarmad Sabir | 12 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-172 | [5 empty] | 2026-01-01T10:45:58.648+0500 | 2026-03-04T13:05:05.112+0500
FF | FF-173 | FF-173 | Bug Subtask | Bug Subtask |  | For site Coco 5 LHR, the sales of products DI and PF are showing in the Sales Transaction tab of the Reconciliation Report, but in the Reconciliation Report tab, the sales for DI and PF are showing as 0 (zero). | Not a Bug |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-173 | [5 empty] | 2026-01-01T11:10:56.883+0500 | 2026-02-25T10:57:43.803+0500
FF | FF-174 | FF-174 | Bug Subtask | Bug Subtask |  | Multiple tenants access should not be allowed for (Dashboard user) while creating, editing. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-174 | [5 empty] | 2026-01-07T11:23:05.964+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-175 | FF-175 | Bug Subtask | Bug Subtask |  | UI Issues with Dropdown Colors and Date Visibility in Night Mode | Failed Testing | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 0.75 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-175 | [5 empty] | 2026-01-08T11:02:23.642+0500 | 2026-04-13T11:42:33.116+0500
FF | FF-176 | FF-176 | Bug Subtask | Bug Subtask |  | Side Navigation and Header Color Mismatch with Body Background in Night mode | Not a Bug |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-176 | [5 empty] | 2026-01-08T11:19:04.009+0500 | 2026-02-25T10:15:35.481+0500
FF | FF-177 | FF-177 | Bug Subtask | Bug Subtask |  | Tagline is Not same on Web And Mobile Application, Moreover it should be "Welcome To" Instead of "welcome Back" | Resolved | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-177 | [5 empty] | 2026-01-08T15:18:14.773+0500 | 2026-02-25T10:45:57.682+0500
FF | FF-178 | FF-178 | Bug Subtask | Bug Subtask |  | In Footer rights should be reserved for 2026 instead of 2025,The link to OctopusDigital should be included on the dashboard and throughout all other screens of the application. and the link should take users back to its original page | Resolved | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-178 | [5 empty] | 2026-01-08T15:28:01.366+0500 | 2026-02-25T10:46:26.124+0500
FF | FF-179 | FF-179 | Bug Subtask | Bug Subtask |  | Symmetry in icons and colors: Mentioned in the description | Resolved | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-179 | [5 empty] | 2026-01-08T15:43:28.475+0500 | 2026-03-02T13:27:13.523+0500
FF | FF-18 | FF-18 | Story | Story |  | Submit Data | Resolved! | 2025-10-20 | 2025-10-24 |  |  | 80 | 80 | kamran khalid | 68 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-18 | [5 empty] | 2025-10-03T19:44:34.008+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-180 | FF-180 | Bug Subtask | Bug Subtask |  | "Username" is missing from Placeholder, Need to add it. | Resolved | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-180 | [5 empty] | 2026-01-08T15:57:38.531+0500 | 2026-02-25T10:46:37.022+0500
FF | FF-181 | FF-181 | Bug Subtask | Bug Subtask |  | "Sign in With Microsoft" is missing from Fintech Fuel Mobile Application. | Not a Bug | 2026-01-08 | 2026-01-08 |  |  | 0.02 | 0.02 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-181 | [5 empty] | 2026-01-08T16:07:14.755+0500 | 2026-03-02T15:27:14.346+0500
FF | FF-182 | FF-182 | Bug Subtask | Bug Subtask |  | Unable to Reset the Password. | Resolved | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-182 | [5 empty] | 2026-01-08T16:26:06.308+0500 | 2026-02-25T10:47:21.395+0500
FF | FF-183 | FF-183 | Bug Subtask | Bug Subtask |  | “The eye icon should be updated to its inverse version.” on dashboard and Portal. | Resolved | 2026-01-09 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-183 | [5 empty] | 2026-01-09T15:19:58.046+0500 | 2026-03-02T13:27:58.736+0500
FF | FF-184 | FF-184 | Sub-task | Sub-task |  | Customer “Adnan Chaudhary” Disappeared from Customer List | Resolved! | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-184 | [5 empty] | 2026-01-09T15:46:20.250+0500 | 2026-02-23T13:10:10.923+0500
FF | FF-185 | FF-185 | Bug Subtask | Bug Subtask |  | “An expired OTP is being validated, allowing the user to log in and access the dashboard.” | Resolved | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-185 | [5 empty] | 2026-01-09T16:24:01.974+0500 | 2026-03-04T13:14:55.862+0500
FF | FF-186 | FF-186 | Bug Subtask | Bug Subtask |  | need to implement an error message on character limit | Resolved | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-186 | [5 empty] | 2026-01-12T10:30:23.554+0500 | 2026-03-04T13:14:41.573+0500
FF | FF-187 | FF-187 | Bug Subtask | Bug Subtask |  | Days and dates should be displayed as on dashboard, if both aren't manageable because of UI, Date must be displayed in Sales vs Target(Dashboard). | Resolved | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-187 | [5 empty] | 2026-01-12T12:07:49.002+0500 | 2026-03-04T13:14:30.774+0500
FF | FF-188 | FF-188 | Bug Subtask | Bug Subtask |  | Invalid OTP is being validated, allowing the user to log in and access the dashboard. | Resolved | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2.5 | 2.5 | Sarmad Sabir | 2.5 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-188 | [5 empty] | 2026-01-12T12:32:14.481+0500 | 2026-03-04T13:13:56.114+0500
FF | FF-189 | FF-189 | Bug Subtask | Bug Subtask |  | Need to Remove upper extra section, Moreover all the highlighted values need to be displayed same as its on web | Resolved | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-189 | [5 empty] | 2026-01-12T12:47:48.158+0500 | 2026-03-04T13:15:10.926+0500
FF | FF-19 | FF-19 | Story | Story |  | Support Portal | Resolved! | 2025-10-17 | 2025-10-20 |  |  | 16 | 16 | Ameer Hamza Khan | 16 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-19 | [5 empty] | 2025-10-03T19:44:38.194+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-190 | FF-190 | Bug Subtask | Bug Subtask |  | 1.Profile menu is not getting vanished while clicking anywhere on the dashboard screen, 2. Dashboard: Tagline need to be same | Resolved | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-190 | [5 empty] | 2026-01-12T14:33:46.254+0500 | 2026-03-04T13:14:17.008+0500
FF | FF-191 | FF-191 | Bug Subtask | Bug Subtask |  | Forgot Password: Check the description | Resolved | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-191 | [5 empty] | 2026-01-12T15:53:51.261+0500 | 2026-03-04T13:16:41.267+0500
FF | FF-192 | FF-192 | Bug Subtask | Bug Subtask |  | Week Fuel Trend is not Interactive Left Side Values are not same with web dashboard, Secondly Product colors are not same. | Request received | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-192 | [5 empty] | 2026-01-12T16:36:48.494+0500 | 2026-03-04T13:24:44.410+0500
FF | FF-193 | FF-193 | Bug Subtask | Bug Subtask |  | User Is Not Automatically Logged Out When Session Expires | Resolved | 2026-01-27 | 2026-01-30 | 2026-01-27 | 2026-02-25 | 16 | 16 | Muhammad Usman Javed | 4 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-193 | [5 empty] | 2026-01-12T16:40:14.243+0500 | 2026-02-26T12:50:08.527+0500
FF | FF-194 | FF-194 | Bug Subtask | Bug Subtask |  | Selected Customer's logo is not getting displayed in the top menu. | Resolved | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-194 | [5 empty] | 2026-01-13T11:14:59.853+0500 | 2026-03-04T13:16:30.814+0500
FF | FF-195 | FF-195 | Bug Subtask | Bug Subtask |  | Dashboard Left menu amendments in text and missing pages, including Sequence of left Menu. | Resolved | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-195 | [5 empty] | 2026-01-13T11:23:34.083+0500 | 2026-03-04T13:16:17.117+0500
FF | FF-196 | FF-196 | Bug Subtask | Bug Subtask |  | Remove Timestamp from Date-Time Filter on Recon Report and Loss/Gain Charts | Resolved | 2026-02-16 | 2026-02-17 |  |  | 24 | 24 | Muhammad Usman Javed | 0 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-196 | [5 empty] | 2026-01-13T12:47:54.639+0500 | 2026-02-25T15:29:39.775+0500
FF | FF-197 | FF-197 | Bug Subtask | Bug Subtask |  | Application doesn't blocks multiple failed login attempts | Not a Bug | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-197 | [5 empty] | 2026-01-13T14:52:15.968+0500 | 2026-03-04T13:24:57.025+0500
FF | FF-198 | FF-198 | Bug Subtask | Bug Subtask |  | Same web's error messages need to be displayed on mobile app, need to be fixed on all error messages. | Resolved | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-198 | [5 empty] | 2026-01-13T15:14:48.577+0500 | 2026-03-04T13:16:08.759+0500
FF | FF-199 | FF-199 | Sub-task | Sub-task |  | Play Store Deployment for Testers | Resolved! | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-20 | 16 | 16 | Sarmad Sabir | 16 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-199 | [5 empty] | 2026-01-13T16:15:40.553+0500 | 2026-02-25T10:47:46.592+0500
FF | FF-2 | FF-2 | Story | Story |  | Improved UI | Resolved! | 2025-08-19 | 2025-08-27 |  |  | 48 | 48 | Ameer Hamza Khan | 48 |  | FF-1 | FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-2 | [5 empty] | 2025-10-03T19:40:46.256+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-20 | FF-20 | Story | Story |  | SQA | Resolved! | 2025-10-29 | 2025-10-30 |  |  | 16 | 16 | kamran khalid | 151 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | [5 empty] | 2025-10-06T14:08:20.126+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-200 | FF-200 | Bug Subtask | Bug Subtask |  | Alarms Issues: | Resolved | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 4 | 4 | Sarmad Sabir | 4 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-200 | [5 empty] | 2026-01-13T16:45:29.227+0500 | 2026-03-04T13:15:55.411+0500
FF | FF-201 | FF-201 | Bug Subtask | Bug Subtask |  | Alarms and their Icons and colors need to be matched with web dashboard. | Resolved | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-201 | [5 empty] | 2026-01-13T16:49:54.756+0500 | 2026-03-04T13:17:59.792+0500
FF | FF-202 | FF-202 | Sub-task | Sub-task |  | Fuel Chat Testing | In-Progress |  |  | 2026-01-12 | 2026-01-13 | 40 | 40 | kamran khalid | 16 |  | FF-97 | FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-202 | [5 empty] | 2026-01-13T18:14:01.052+0500 | 2026-02-11T12:32:16.755+0500
FF | FF-203 | FF-203 | Bug Subtask | Bug Subtask |  | Search Placeholder is not visible completely, nor Icons and descriptions are same, alarm types Are missing also. | Resolved | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-203 | [5 empty] | 2026-01-14T11:00:02.789+0500 | 2026-03-04T13:17:50.465+0500
FF | FF-204 | FF-204 | Bug Subtask | Bug Subtask |  | User should Search/ Filter alarms on the basis of their: Title, Description, Severity | Resolved | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-204 | [5 empty] | 2026-01-14T11:34:01.476+0500 | 2026-03-04T13:19:02.157+0500
FF | FF-205 | FF-205 | Bug Subtask | Bug Subtask |  | While filtering multiple sites, or single site "Other" Alarm type is missing and its showing invalid count for that | Resolved | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-205 | [5 empty] | 2026-01-14T11:46:47.380+0500 | 2026-03-04T13:18:41.455+0500
FF | FF-206 | FF-206 | Bug Subtask | Bug Subtask |  | Severity Filter dropdown not implemented and functional. | Resolved | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-206 | [5 empty] | 2026-01-14T12:08:44.194+0500 | 2026-03-04T13:17:40.820+0500
FF | FF-207 | FF-207 | Bug Subtask | Bug Subtask |  | Selected Site/Customer name should be displayed. (on all screens) | Resolved | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 4 | 4 | Sarmad Sabir | 4 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-207 | [5 empty] | 2026-01-14T12:35:04.841+0500 | 2026-03-04T13:17:29.057+0500
FF | FF-208 | FF-208 | Bug Subtask | Bug Subtask |  | Date Range is limited to 2 weeks, Any 2 months for selection should be allowed to view data. It should be flexible that user can select data of 2 weeks or 1 month of any year, or 2 months or 1 day. | Resolved | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-208 | [5 empty] | 2026-01-14T14:58:57.169+0500 | 2026-03-04T13:19:43.577+0500
FF | FF-209 | FF-209 | Bug Subtask | Bug Subtask |  | The Application does not load data after login, Until we click the Refresh button. | Resolved | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-209 | [5 empty] | 2026-01-14T15:46:34.359+0500 | 2026-03-04T13:19:31.963+0500
FF | FF-21 | FF-21 | Story | Story |  | Production Release | Resolved! | 2025-11-03 | 2025-11-03 |  |  | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-21 | [5 empty] | 2025-10-06T14:08:23.855+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-210 | FF-210 | Sub-task | Sub-task |  | fuel chat testing | In-Progress |  |  | 2026-01-13 | 2026-01-15 | 0 | 0 | kamran khalid | 26 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-210 | [5 empty] | 2026-01-14T17:36:27.496+0500 | 2026-02-11T12:32:16.755+0500
FF | FF-211 | FF-211 | Bug Subtask | Bug Subtask |  | "Reconciliation Report" issues | Resolved | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-211 | [5 empty] | 2026-01-15T11:25:47.908+0500 | 2026-03-04T13:20:26.967+0500
FF | FF-212 | FF-212 | Bug Subtask | Bug Subtask |  | Missing Columns from Recon table: | Resolved | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-212 | [5 empty] | 2026-01-15T11:40:39.578+0500 | 2026-03-04T13:20:17.194+0500
FF | FF-213 | FF-213 | Bug Subtask | Bug Subtask |  | The Excel button for downloading the file is not implemented. | Not a Bug |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-213 | [5 empty] | 2026-01-15T12:01:04.754+0500 | 2026-02-04T10:59:27.685+0500
FF | FF-214 | FF-214 | Bug Subtask | Bug Subtask |  | Pagination needs to be implemented. on all the required pages as on web dashboard | Not a Bug |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-214 | [5 empty] | 2026-01-15T12:30:19.443+0500 | 2026-02-03T14:35:09.015+0500
FF | FF-215 | FF-215 | Bug Subtask | Bug Subtask |  | The Excel button for downloading the file is not implemented on Nozzle Usage, and description is not mentioned. | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-215 | [5 empty] | 2026-01-15T15:24:35.439+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-216 | FF-216 | Bug Subtask | Bug Subtask |  | All necessary columns must include IDs as well as inactive hours. | Resolved | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-216 | [5 empty] | 2026-01-15T15:49:04.149+0500 | 2026-03-04T13:19:55.854+0500
FF | FF-217 | FF-217 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-01-19 | 2026-01-23 | 2026-01-19 | 2026-01-23 | 40 | 40 | Muhammad Imran Aslam | 40 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-217 | [5 empty] | 2026-01-19T15:11:43.918+0500 | 2026-02-23T13:27:19.935+0500
FF | FF-218 | FF-218 | Sub-task | Sub-task |  | Low Stock Page | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Sarmad Sabir | 8 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-218 | [5 empty] | 2026-01-20T16:26:56.471+0500 | 2026-03-04T13:21:12.827+0500
FF | FF-219 | FF-219 | Bug Subtask | Bug Subtask |  | Select All functionality is missing, It should be implemented on all the filters as on web dashboard. | Resolved | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-219 | [5 empty] | 2026-01-21T11:20:02.817+0500 | 2026-03-04T13:22:07.326+0500
FF | FF-220 | FF-220 | Bug Subtask | Bug Subtask |  | Inactive hours should not be less than 0 | Resolved | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-220 | [5 empty] | 2026-01-21T11:54:48.739+0500 | 2026-03-04T13:21:54.897+0500
FF | FF-221 | FF-221 | Bug Subtask | Bug Subtask |  | Overall Active Hours of Last 7 days are not available on the nozzle usage screen. | Resolved | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-221 | [5 empty] | 2026-01-21T12:04:18.634+0500 | 2026-03-04T13:25:33.540+0500
FF | FF-222 | FF-222 | Bug Subtask | Bug Subtask |  | The values on the column should match against the Column names in the table | Request received | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2 | 2 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-222 | [5 empty] | 2026-01-21T12:09:53.311+0500 | 2026-03-04T13:25:10.739+0500
FF | FF-223 | FF-223 | Bug Subtask | Bug Subtask |  | Failed to load Nozzle Usage Data for 2 days | Not a Bug | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2 | 2 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-223 | [5 empty] | 2026-01-21T12:21:55.614+0500 | 2026-03-04T13:25:21.114+0500
FF | FF-224 | FF-224 | Bug Subtask | Bug Subtask |  | Stock Levels Issues | Resolved | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-224 | [5 empty] | 2026-01-21T15:05:17.495+0500 | 2026-03-04T13:23:09.501+0500
FF | FF-225 | FF-225 | Bug Subtask | Bug Subtask |  | All the Values must be same On Stock Levels. | Resolved | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-225 | [5 empty] | 2026-01-21T15:17:24.416+0500 | 2026-03-04T13:22:48.651+0500
FF | FF-226 | FF-226 | Sub-task | Sub-task |  | "Confirmed Quantity" and "Bill of Lading Reference" is missing from Deliveries Table, Moreover there must be some space in between Tank and Timestamp column. | On Hold | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-226 | [5 empty] | 2026-01-21T16:06:38.487+0500 | 2026-03-04T12:39:06.134+0500
FF | FF-227 | FF-227 | Bug Subtask | Bug Subtask |  | The Excel button for downloading the file is not implemented on Deliveries | Not a Bug |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-227 | [5 empty] | 2026-01-21T16:11:57.797+0500 | 2026-02-04T10:58:22.824+0500
FF | FF-228 | FF-228 | Task | Task |  | Remove only time part from Date and Time Filter on The Recon Report and Nozzle Usage Screen on Fintech Dashboard | Resolved! | 2026-01-26 | 2026-01-30 | 2026-01-27 | 2026-01-30 | 32 | 32 | Muhammad Usman Javed | 28 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-228 | [5 empty] | 2026-01-28T10:45:52.856+0500 | 2026-02-20T16:50:47.262+0500
FF | FF-229 | FF-229 | Story | Story |  | [Support Request] Support Request - Aramco | Resolved! |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 54 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-229 | [5 empty] | 2026-01-28T10:48:47.143+0500 | 2026-02-13T12:50:55.571+0500
FF | FF-230 | FF-230 | Sub-task | Sub-task |  | Aramco 7-7 Recon | Resolved! | 2026-01-23 | 2026-01-27 | 2026-01-23 | 2026-01-27 | 40 | 40 | Hassan Saeed Wattoo | 22 |  | FF-229 | FF-229 | https://octopusdtlsupport.atlassian.net/browse/FF-229 | https://octopusdtlsupport.atlassian.net/browse/FF-230 | [5 empty] | 2026-01-28T10:50:29.525+0500 | 2026-02-13T12:41:14.722+0500
FF | FF-231 | FF-231 | Sub-task | Sub-task |  | FuelChat - Summarized Version | To Do |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 0 |  | FF-157 | FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-231 | [5 empty] | 2026-01-28T10:52:12.385+0500 | 2026-01-28T10:54:38.573+0500
FF | FF-232 | FF-232 | Sub-task | Sub-task |  | POC on cost comparison (summarized vs. non-summarized versions) | Resolved! | 2026-01-15 | 2026-01-22 | 2026-01-14 | 2026-01-22 | 40 | 40 | Hassan Saeed Wattoo | 38 |  | FF-157 | FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-232 | [5 empty] | 2026-01-28T10:52:40.780+0500 | 2026-02-13T12:42:37.844+0500
FF | FF-233 | FF-233 | Sub-task | Sub-task |  | Presentation on All models comparison | Resolved! | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Hassan Saeed Wattoo | 6 |  | FF-157 | FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-233 | [5 empty] | 2026-01-28T10:54:36.189+0500 | 2026-02-13T12:49:46.215+0500
FF | FF-234 | FF-234 | Sub-task | Sub-task |  | POC on all models comparison | Resolved! | 2026-01-09 | 2026-01-14 | 2026-01-09 | 2026-01-13 | 24 | 24 | Hassan Saeed Wattoo | 24 |  | FF-157 | FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-234 | [5 empty] | 2026-01-28T10:55:19.970+0500 | 2026-02-13T12:49:57.787+0500
FF | FF-235 | FF-235 | Sub-task | Sub-task |  | Bug fixes | Resolved! | 2026-01-01 | 2026-01-05 | 2026-01-01 | 2026-01-06 | 24 | 24 | Hassan Saeed Wattoo | 24 |  | FF-157 | FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-235 | [5 empty] | 2026-01-28T10:59:45.279+0500 | 2026-02-13T12:50:10.047+0500
FF | FF-236 | FF-236 | Sub-task | Sub-task |  | Enhancement request from SQA | Resolved! | 2026-01-02 | 2026-01-08 | 2026-01-02 | 2026-01-08 | 48 | 48 | Hassan Saeed Wattoo | 24 |  | FF-157 | FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-157 | https://octopusdtlsupport.atlassian.net/browse/FF-236 | [5 empty] | 2026-01-28T11:00:47.172+0500 | 2026-02-23T13:05:06.291+0500
FF | FF-238 | FF-238 | Task | Task |  | Remove time part from filter and apply check based on customer that for Aramco it should select data from 07:00-07:00 and for rest of the customer it should be 08:00-08:00 | In-Progress |  |  | 2026-01-30 | 2026-01-30 | 0 | 0 | Muhammad Usman Javed | 2 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-238 | [5 empty] | 2026-01-28T11:20:32.466+0500 | 2026-02-20T16:35:47.459+0500
FF | FF-239 | FF-239 | Bug Subtask | Bug Subtask |  | Low Stocks Issues which need to be fixed: | QA Testing | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-239 | [5 empty] | 2026-01-28T11:45:45.807+0500 | 2026-03-04T13:26:42.034+0500
FF | FF-240 | FF-240 | Bug Subtask | Bug Subtask |  | Low Stocks: When choosing multiple sites, some values do not match, and Total Alerts should also be shown (for multiple sites/single sites). | Resolved | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-240 | [5 empty] | 2026-01-28T11:59:58.912+0500 | 2026-03-04T13:27:51.493+0500
FF | FF-241 | FF-241 | Bug Subtask | Bug Subtask |  | Low Stocks (Tank View ) : Alerts and Status column and Stock levels are missing | Resolved | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-241 | [5 empty] | 2026-01-28T12:16:51.046+0500 | 2026-03-04T13:27:43.871+0500
FF | FF-242 | FF-242 | Bug Subtask | Bug Subtask |  | Current Levels and Days Left should be same as implemented on Web Dashboard | Resolved | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-242 | [5 empty] | 2026-01-28T12:33:16.792+0500 | 2026-03-04T13:28:21.870+0500
FF | FF-243 | FF-243 | Bug Subtask | Bug Subtask |  | Grade View : | On Hold | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-243 | [5 empty] | 2026-01-28T12:53:31.224+0500 | 2026-03-04T13:27:28.111+0500
FF | FF-244 | FF-244 | Bug Subtask | Bug Subtask |  | Incorrect Stock Level Displayed for Product PF on Low Stock Screen (Coco 2 LHR) | Resolved | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-244 | [5 empty] | 2026-01-28T13:58:49.255+0500 | 2026-02-25T15:30:23.267+0500
FF | FF-245 | FF-245 | Sub-task | Sub-task |  | Site Level Alerts Page | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2 | 2 | Sarmad Sabir | 2 |  | FF-120 | FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-120 | https://octopusdtlsupport.atlassian.net/browse/FF-245 | [5 empty] | 2026-01-28T14:05:22.665+0500 | 2026-03-04T13:26:02.409+0500
FF | FF-246 | FF-246 | Bug Subtask | Bug Subtask |  | All values of Deliveries page and all other screen need to be same, and .00 should be removed as we don't have much space in the mobile app nor it is implemented on web dashboard. | Resolved | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-246 | [5 empty] | 2026-01-29T10:09:47.039+0500 | 2026-03-04T13:28:13.651+0500
FF | FF-247 | FF-247 | Bug Subtask | Bug Subtask |  | Contact Support button need to be implemented on Mobile application | Not a Bug |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-247 | [5 empty] | 2026-01-29T11:52:45.211+0500 | 2026-02-04T11:00:35.133+0500
FF | FF-248 | FF-248 | Bug Subtask | Bug Subtask |  | Sales Target is not same as on web, values sales trend analysis: line charts and bar charts Daily sales summary fields and values Performance Summary (need to remove Extra) | Resolved | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-248 | [5 empty] | 2026-01-29T14:45:30.128+0500 | 2026-03-04T12:25:58.777+0500
FF | FF-249 | FF-249 | Bug Subtask | Bug Subtask |  | Missing Alerts and invalid total alerts for single and multiple sites On both Tank view and Grade view of low stocks | Resolved | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-249 | [5 empty] | 2026-01-30T16:17:32.764+0500 | 2026-03-04T12:25:40.042+0500
FF | FF-250 | FF-250 | Bug Subtask | Bug Subtask |  | Grade view values are not same while selecting single or multiple sites | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-250 | [5 empty] | 2026-01-30T16:36:47.766+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-251 | FF-251 | Bug Subtask | Bug Subtask |  | Card view should be same as table view of transactions , (Day end Sales), ⁠Pump and Hose Filter dropdowns are missing from transaction page. | Resolved | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 3 | 3 | Sarmad Sabir | 3 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-251 | [5 empty] | 2026-02-02T10:37:39.285+0500 | 2026-03-04T12:25:12.480+0500
FF | FF-252 | FF-252 | Sub-task | Sub-task |  | Excel button should be available and functional to be downloaded for transaction screen (Day end Sales) | On Hold |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-252 | [5 empty] | 2026-02-02T10:45:51.094+0500 | 2026-02-11T12:32:16.125+0500
FF | FF-253 | FF-253 | Bug Subtask | Bug Subtask |  | (Day end sales Summary) title need to be correct and extra columns should be removed, | On Hold | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-253 | [5 empty] | 2026-02-02T11:12:46.513+0500 | 2026-03-04T12:39:18.965+0500
FF | FF-254 | FF-254 | Bug Subtask | Bug Subtask |  | Card view should be same as table view of transactions , ("Day End Sales Summary"). | On Hold | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-254 | [5 empty] | 2026-02-02T11:41:56.990+0500 | 2026-03-04T12:39:22.788+0500
FF | FF-255 | FF-255 | Bug Subtask | Bug Subtask |  | Excel button should be available and Functional for the types of reports of transaction | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-255 | [5 empty] | 2026-02-02T11:44:43.886+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-256 | FF-256 | Bug Subtask | Bug Subtask |  | Need to remove unstable pagination from Transactions level sales and wherever else it is implemented as we are using (Load more button previously) So Load more button should be implemented now on every screen | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-256 | [5 empty] | 2026-02-02T12:12:16.997+0500 | 2026-03-04T12:27:40.299+0500
FF | FF-257 | FF-257 | Bug Subtask | Bug Subtask |  | Transaction level sales : Title should complete. Padding must be added in between "Row Number" and "Site Name" | On Hold | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-257 | [5 empty] | 2026-02-02T12:53:16.515+0500 | 2026-03-04T12:39:12.729+0500
FF | FF-258 | FF-258 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-258 | [5 empty] | 2026-02-02T14:24:51.431+0500 | 2026-02-23T13:25:06.926+0500
FF | FF-259 | FF-259 | Bug Subtask | Bug Subtask |  | Loss & Gain Chart : dates are mismatched. and need discussion on other graph values | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-259 | [5 empty] | 2026-02-02T15:20:21.984+0500 | 2026-03-04T12:30:54.443+0500
FF | FF-260 | FF-260 | Bug Subtask | Bug Subtask |  | Invalid values for Daily Deliveries chart (Loss Gain Charts) | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-260 | [5 empty] | 2026-02-02T15:28:56.249+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-261 | FF-261 | Bug Subtask | Bug Subtask |  | Critical : Application is Crashing while changing the customer and transaction type, on Loss & Gain screen | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-261 | [5 empty] | 2026-02-02T16:25:34.360+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-262 | FF-262 | Bug Subtask | Bug Subtask |  | headings should be same while selecting any chart type on Loss Gain | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-262 | [5 empty] | 2026-02-03T10:49:50.745+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-263 | FF-263 | Bug Subtask | Bug Subtask |  | Selected date for filtration is from 26 but data is filtered from 25 (Sales target). | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2 | 2 | Sarmad Sabir | 2 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-263 | [5 empty] | 2026-02-03T11:07:11.638+0500 | 2026-03-04T12:30:40.942+0500
FF | FF-264 | FF-264 | Bug Subtask | Bug Subtask |  | Daily sales summary is getting displayed in weekly sales Summary | On Hold | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3 | 3 | Sarmad Sabir | 3 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-264 | [5 empty] | 2026-02-03T14:48:22.413+0500 | 2026-03-04T12:39:07.999+0500
FF | FF-265 | FF-265 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-265 | [5 empty] | 2026-02-03T15:21:59.997+0500 | 2026-02-23T13:24:44.171+0500
FF | FF-266 | FF-266 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-266 | [5 empty] | 2026-02-03T15:24:51.204+0500 | 2026-02-23T13:20:38.127+0500
FF | FF-267 | FF-267 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-267 | [5 empty] | 2026-02-03T15:28:21.540+0500 | 2026-02-26T13:56:46.195+0500
FF | FF-268 | FF-268 | Bug Subtask | Bug Subtask |  | While filtering the results for "92" which should be only 2 records its displaying 6 records, for card view of transactions | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-268 | [5 empty] | 2026-02-03T15:46:57.660+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-269 | FF-269 | Bug Subtask | Bug Subtask |  | those nozzles which are associated to the Pump2 should be filtered out, when user has specified the pump (Day end sales -Transactions ) instead of all the nozzles to be selected | On Hold |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-269 | [5 empty] | 2026-02-03T16:06:27.934+0500 | 2026-03-04T12:39:03.886+0500
FF | FF-270 | FF-270 | Story | Story |  | Fintech Dashboard Enchancements | In-Progress |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-270 | [5 empty] | 2026-02-03T16:41:34.050+0500 | 2026-02-11T12:32:18.988+0500
FF | FF-271 | FF-271 | Epic | Epic |  | Fintech Fuel Read API | On Hold | 2026-07-06 | 2026-07-24 |  |  | 208 | 208 | Muhammad Usman Javed | 0.5 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-271 | [5 empty] | 2026-02-04T11:12:03.898+0500 | 2026-04-16T10:59:09.400+0500
FF | FF-272 | FF-272 | Bug Subtask | Bug Subtask |  | Transaction , Recon Report Booked: minus sign with zero is being displayed in mobile app | On Hold | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1 | 1 | Sarmad Sabir | 1 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-272 | [5 empty] | 2026-02-04T12:18:22.021+0500 | 2026-03-04T12:38:29.276+0500
FF | FF-273 | FF-273 | Bug Subtask | Bug Subtask |  | Displaying Invalid Count while selecting multiple or all the sites of a customer (Low Stocks) | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-273 | [5 empty] | 2026-02-04T15:27:53.176+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-274 | FF-274 | Epic | Epic |  | Site Diagnostics Dashboard (System Health Monitoring) | On Hold | 2026-04-08 | 2026-05-06 |  |  | 336 | 336 | Hassan Saeed Wattoo | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-274 | [5 empty] | 2026-02-04T16:59:49.438+0500 | 2026-04-14T15:03:47.618+0500
FF | FF-275 | FF-275 | Story | Story |  | Development | In-Progress | 2026-02-02 | 2026-02-13 |  |  | 80 | 80 | Muhammad Usman Javed | 113.5 |  | FF-271 | FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | [5 empty] | 2026-02-04T17:00:19.099+0500 | 2026-04-23T15:47:56.018+0500
FF | FF-276 | FF-276 | Story | Story |  | Staging Handover | Resolved! | 2026-02-23 | 2026-02-23 |  |  | 8 | 8 | Muhammad Usman Javed | 2 |  | FF-271 | FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-276 | [5 empty] | 2026-02-04T17:01:25.131+0500 | 2026-03-12T11:27:28.823+0500
FF | FF-277 | FF-277 | Story | Story |  | Development | Resolved! | 2026-02-06 | 2026-02-17 |  |  | 56 | 56 | Muhammad Usman Javed | 103.5 |  | FF-274 | FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | [5 empty] | 2026-02-04T17:01:57.400+0500 | 2026-03-04T12:36:30.515+0500
FF | FF-278 | FF-278 | Story | Story |  | SQA | On Hold | 2026-02-18 | 2026-02-26 |  |  | 56 | 56 | kamran khalid | 39.5 |  | FF-274 | FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-278 | [5 empty] | 2026-02-04T17:02:06.864+0500 | 2026-04-08T16:16:25.885+0500
FF | FF-279 | FF-279 | Sub-task | Sub-task |  | Frontend Development | Resolved! |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-279 | [5 empty] | 2026-02-06T10:39:52.155+0500 | 2026-03-05T13:41:02.056+0500
FF | FF-280 | FF-280 | Sub-task | Sub-task |  | Backend API Development | Resolved! | 2026-02-19 | 2026-02-25 | 2026-02-09 | 2026-02-23 | 40 | 40 | Muhammad Usman Javed | 40 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-280 | [5 empty] | 2026-02-06T10:40:24.607+0500 | 2026-03-10T11:38:25.737+0500
FF | FF-281 | FF-281 | Sub-task | Sub-task |  | R&D | Resolved! | 2026-01-21 | 2026-01-23 | 2026-02-05 | 2026-02-05 | 24 | 24 | Muhammad Usman Javed | 16 |  | FF-275 | FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-281 | [5 empty] | 2026-02-06T10:42:32.835+0500 | 2026-02-23T12:40:24.030+0500
FF | FF-282 | FF-282 | Sub-task | Sub-task |  | Swagger API Development | Resolved! | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 32 | 32 | Muhammad Usman Javed | 32 |  | FF-275 | FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-282 | [5 empty] | 2026-02-06T10:42:48.134+0500 | 2026-03-10T11:34:28.403+0500
FF | FF-283 | FF-283 | Bug Subtask | Bug Subtask |  | Unable to Delete any chat from FuelCHat | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-283 | [5 empty] | 2026-02-06T10:59:45.836+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-284 | FF-284 | Bug Subtask | Bug Subtask |  | Unable to Edit any chat from FuelCHat | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-284 | [5 empty] | 2026-02-06T11:07:59.484+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-285 | FF-285 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-285 | [5 empty] | 2026-02-09T11:43:42.257+0500 | 2026-03-04T14:27:41.264+0500
FF | FF-286 | FF-286 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-286 | [5 empty] | 2026-02-09T11:47:21.675+0500 | 2026-03-12T12:36:00.855+0500
FF | FF-287 | FF-287 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-287 | [5 empty] | 2026-02-09T11:49:50.611+0500 | 2026-03-18T14:16:45.445+0500
FF | FF-288 | FF-288 | Sub-task | Sub-task |  | Fuel Chat Testing | Resolved! | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-20 | FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-20 | https://octopusdtlsupport.atlassian.net/browse/FF-288 | [5 empty] | 2026-02-09T11:52:46.144+0500 | 2026-03-25T15:14:52.298+0500
FF | FF-289 | FF-289 | Story | Story |  | SQA | Resolved! | 2026-06-17 | 2026-07-24 |  |  | 80 | 80 | kamran khalid | 49 |  | FF-271 | FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-289 | [5 empty] | 2026-02-10T09:39:49.078+0500 | 2026-04-23T15:41:49.970+0500
FF | FF-29 | FF-29 | Bug Subtask | Bug Subtask |  | After 10:43 AM utc time The Data for (PARCO GUNOVER) Gardenia Filling Station and (Adnan Chaudary) Palace View FS the Files are getting landed From the Un Processed Folder to the "Exceptional Folder". | Resolved | 2025-10-02 | 2025-10-02 |  |  | 0 | 0 | Muhammad Usman Javed | 4 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-29 | [5 empty] | 2025-10-08T14:06:57.941+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-290 | FF-290 | Story | Story |  | User Manual | To Do |  |  |  |  | 40 | 40 | Hassan Malik | 0 |  | FF-274 | FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-290 | [5 empty] | 2026-02-10T09:42:31.806+0500 | 2026-02-10T09:42:49.308+0500
FF | FF-291 | FF-291 | Story | Story |  | Bug Fixing | Resolved! |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 6 |  | FF-271 | FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | [5 empty] | 2026-02-10T09:44:48.113+0500 | 2026-04-23T15:41:54.845+0500
FF | FF-292 | FF-292 | Epic | Epic |  | ALSONs device data collection (read only) | In-Progress | 2026-02-09 | 2026-03-31 |  |  | 120 | 120 | yousha.agha | 104 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-292 | [5 empty] | 2026-02-10T09:45:45.725+0500 | 2026-03-16T10:48:46.297+0500
FF | FF-293 | FF-293 | Story | Story |  | Development | In-Progress | 2026-02-01 | 2026-03-31 | 2026-02-09 | 2026-02-27 | 120 | 120 | yousha.agha | 472 |  | FF-292 | FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | [5 empty] | 2026-02-10T09:46:06.034+0500 | 2026-03-31T11:16:06.852+0500
FF | FF-294 | FF-294 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | FF-292 | FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-294 | [5 empty] | 2026-02-10T09:46:15.775+0500 | 2026-02-23T13:00:23.703+0500
FF | FF-295 | FF-295 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-292 | FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-295 | [5 empty] | 2026-02-10T09:46:23.716+0500 | 2026-02-10T09:47:13.027+0500
FF | FF-296 | FF-296 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 0 |  | FF-292 | FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-292 | https://octopusdtlsupport.atlassian.net/browse/FF-296 | [5 empty] | 2026-02-10T09:46:33.290+0500 | 2026-03-18T10:21:07.504+0500
FF | FF-297 | FF-297 | Epic | Epic |  | Alsons Integration with FintechFuel | To Do | 2026-03-26 | 2026-05-06 |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-297 | [5 empty] | 2026-02-10T09:48:34.191+0500 | 2026-04-22T16:56:53.913+0500
FF | FF-298 | FF-298 | Story | Story |  | Development | In-Progress | 2026-03-30 | 2026-04-16 |  |  | 120 | 120 | Muhammad Usman Javed | 128 |  | FF-297 | FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-298 | [5 empty] | 2026-02-10T09:48:45.995+0500 | 2026-04-15T10:47:29.828+0500
FF | FF-299 | FF-299 | Story | Story |  | SQA | To Do | 2026-04-17 | 2026-05-06 |  |  | 120 | 120 | kamran khalid | 0 |  | FF-297 | FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-299 | [5 empty] | 2026-02-10T09:49:02.258+0500 | 2026-04-15T10:46:20.425+0500
FF | FF-3 | FF-3 | Story | Story |  | Dashboard | Resolved! | 2025-09-11 | 2025-09-15 |  |  | 24 | 24 | Ameer Hamza Khan | 17 |  | FF-1 | FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-3 | [5 empty] | 2025-10-03T19:40:52.014+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-30 | FF-30 | Bug Subtask | Bug Subtask |  | Again 2 files has been missed in the Processed folder for "Gardenia Filling Station" found in "Exception Folder". | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-30 | [5 empty] | 2025-10-08T14:12:32.093+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-300 | FF-300 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-297 | FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-300 | [5 empty] | 2026-02-10T09:49:09.203+0500 | 2026-02-10T09:49:09.319+0500
FF | FF-301 | FF-301 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-297 | FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-301 | [5 empty] | 2026-02-10T09:49:19.667+0500 | 2026-03-25T10:23:54.969+0500
FF | FF-302 | FF-302 | Epic | Epic |  | Fuel price write back | To Do | 2026-04-20 | 2026-05-11 |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-302 | [5 empty] | 2026-02-10T09:54:37.249+0500 | 2026-04-08T16:51:32.679+0500
FF | FF-303 | FF-303 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-302 | FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-303 | [5 empty] | 2026-02-10T09:54:48.953+0500 | 2026-02-10T09:54:49.056+0500
FF | FF-304 | FF-304 | Story | Story |  | SQA | To Do | 2026-05-01 | 2026-05-11 |  |  | 80 | 80 | kamran khalid | 0 |  | FF-302 | FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-304 | [5 empty] | 2026-02-10T09:54:52.075+0500 | 2026-04-08T16:21:30.911+0500
FF | FF-305 | FF-305 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-302 | FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-305 | [5 empty] | 2026-02-10T09:54:56.989+0500 | 2026-02-10T09:54:57.098+0500
FF | FF-306 | FF-306 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-302 | FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-302 | https://octopusdtlsupport.atlassian.net/browse/FF-306 | [5 empty] | 2026-02-10T09:55:01.090+0500 | 2026-02-10T09:55:01.239+0500
FF | FF-307 | FF-307 | Sub-task | Sub-task |  | Fuelchat Modification for 7-7 Recon | Resolved! | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 24 | 24 | Hassan Saeed Wattoo | 24 |  | FF-229 | FF-229 | https://octopusdtlsupport.atlassian.net/browse/FF-229 | https://octopusdtlsupport.atlassian.net/browse/FF-307 | [5 empty] | 2026-02-10T11:08:23.533+0500 | 2026-02-13T12:47:34.639+0500
FF | FF-308 | FF-308 | Sub-task | Sub-task |  | Unit Testing | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Hassan Saeed Wattoo | 8 |  | FF-229 | FF-229 | https://octopusdtlsupport.atlassian.net/browse/FF-229 | https://octopusdtlsupport.atlassian.net/browse/FF-308 | [5 empty] | 2026-02-10T11:11:42.658+0500 | 2026-03-13T11:00:15.654+0500
FF | FF-31 | FF-31 | Bug Subtask | Bug Subtask |  | The Forgot password screen is the old screen and is not responsive and does not align with the new layout. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.33 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-31 | [5 empty] | 2025-10-08T14:13:41.962+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-311 | FF-311 | Story | Story |  | Research | Resolved! | 2026-02-03 | 2026-02-10 |  |  | 48 | 48 | Ameer Hamza Khan | 48 |  | FF-274 | FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-311 | [5 empty] | 2026-02-10T11:29:19.450+0500 | 2026-04-09T16:39:17.565+0500
FF | FF-312 | FF-312 | Epic | Epic |  | FuelChat - Summarized Version | To Do | 2026-02-06 | 2026-02-23 |  |  | 0 | 0 | Hassan Saeed Wattoo | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-312 | [5 empty] | 2026-02-10T14:34:50.933+0500 | 2026-04-09T10:21:45.519+0500
FF | FF-314 | FF-314 | Epic | Epic |  | Configurable Alarms and Sites, Notifications | On Hold | 2026-02-06 | 2026-03-16 |  |  | 128 | 128 | Muhammad Usman Javed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-314 | [5 empty] | 2026-02-10T15:59:37.319+0500 | 2026-05-12T14:28:09.944+0500
FF | FF-315 | FF-315 | Story | Story |  | Development | Resolved! | 2026-02-06 | 2026-02-16 |  |  | 56 | 56 | Muhammad Usman Javed | 217.77 |  | FF-314 | FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | [5 empty] | 2026-02-10T16:02:12.234+0500 | 2026-03-04T12:39:21.057+0500
FF | FF-316 | FF-316 | Story | Story |  | SQA | Resolved! | 2026-02-18 | 2026-02-24 |  |  | 32 | 32 | kamran khalid | 58.5 |  | FF-314 | FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | [5 empty] | 2026-02-10T16:02:33.491+0500 | 2026-03-03T12:39:11.990+0500
FF | FF-317 | FF-317 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-314 | FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-317 | [5 empty] | 2026-02-10T16:02:37.970+0500 | 2026-02-10T16:02:38.442+0500
FF | FF-318 | FF-318 | Sub-task | Sub-task |  | Designing Database Schema | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-10 | 2026-02-10 | 8 | 8 | Muhammad Usman Javed | 8 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-318 | [5 empty] | 2026-02-10T16:11:13.747+0500 | 2026-02-20T10:41:16.450+0500
FF | FF-319 | FF-319 | Sub-task | Sub-task |  | Backend API Development | Resolved! | 2026-02-06 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 24 | 24 | Muhammad Usman Javed | 16 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-319 | [5 empty] | 2026-02-10T16:12:19.957+0500 | 2026-03-10T11:22:00.086+0500
FF | FF-32 | FF-32 | Bug Subtask | Bug Subtask |  | Kindly update the email validation check upon forgot password screen as we have currently encounter client emails such as "Nida.wasif@parcogunvor.com.pk" as currently its not accepting. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.67 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-32 | [5 empty] | 2025-10-08T14:19:09.697+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-320 | FF-320 | Bug Subtask | Bug Subtask |  | Need to modify finchat to "FuelChat" | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-320 | [5 empty] | 2026-02-11T10:26:13.109+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-321 | FF-321 | Bug Subtask | Bug Subtask |  | FuelChat is showing invalid results while we ask for sites of a tenant | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-321 | [5 empty] | 2026-02-11T10:45:44.790+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-322 | FF-322 | Bug Subtask | Bug Subtask |  | Site name, Cite and Province is missing from the table | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-322 | [5 empty] | 2026-02-11T10:54:12.504+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-323 | FF-323 | Bug Subtask | Bug Subtask |  | While we login with portal user, Customer is not changeable on mobile application | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-323 | [5 empty] | 2026-02-11T11:14:28.552+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-324 | FF-324 | Bug Subtask | Bug Subtask |  | When dashboard user is assigned only one customer, and asking question related to another customer which is not assigned to it, the system shows information related to the assigned customer without displaying any restriction message. | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-324 | [5 empty] | 2026-02-11T11:40:25.968+0500 | 2026-02-11T12:50:56.838+0500
FF | FF-326 | FF-326 | Bug Subtask | Bug Subtask |  | User can not Export chat in PDF by clicking on the "Export Chat" button. | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-326 | [5 empty] | 2026-02-11T12:59:34.550+0500 | 2026-02-11T13:18:13.571+0500
FF | FF-327 | FF-327 | Bug Subtask | Bug Subtask |  | Bar Charts, Line Charts, Pie Chart are not available in Fuel chat | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-327 | [5 empty] | 2026-02-11T14:28:28.400+0500 | 2026-02-11T14:47:13.831+0500
FF | FF-328 | FF-328 | Sub-task | Sub-task |  | Creating Notification Group Page | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 4 | 4 | Sarmad Sabir | 4 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-328 | [5 empty] | 2026-02-11T16:07:34.587+0500 | 2026-03-04T12:37:49.821+0500
FF | FF-329 | FF-329 | Sub-task | Sub-task |  | Creating Alarms Configurations Page | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 4 | 4 | Sarmad Sabir | 4 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-329 | [5 empty] | 2026-02-11T16:07:54.660+0500 | 2026-03-04T12:37:30.045+0500
FF | FF-33 | FF-33 | Bug Subtask | Bug Subtask |  | The links in the email for Forgot Password not working. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.33 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-33 | [5 empty] | 2025-10-08T14:21:26.247+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-330 | FF-330 | Sub-task | Sub-task |  | Integrating APIs (Notifications Group Page) | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Sarmad Sabir | 7 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-330 | [5 empty] | 2026-02-11T16:08:18.841+0500 | 2026-03-04T12:41:05.246+0500
FF | FF-331 | FF-331 | Sub-task | Sub-task |  | Integrating APIs (Alarm Configurations Page) | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8 | 8 | Sarmad Sabir | 7 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-331 | [5 empty] | 2026-02-11T16:08:30.812+0500 | 2026-03-04T12:41:46.241+0500
FF | FF-332 | FF-332 | Sub-task | Sub-task |  | Sanity and Bug Fixes | Resolved! | 2026-02-11 | 2026-02-16 | 2026-02-11 | 2026-02-16 | 24 | 24 | Sarmad Sabir | 23 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-332 | [5 empty] | 2026-02-11T16:10:08.849+0500 | 2026-03-04T12:43:21.255+0500
FF | FF-333 | FF-333 | Sub-task | Sub-task |  | Creation of Demo Customer for Demo Purpose - Clone of Aramco Customer | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Muhammad Usman Javed | 8 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-333 | [5 empty] | 2026-02-12T11:08:15.860+0500 | 2026-02-23T12:41:19.809+0500
FF | FF-334 | FF-334 | Sub-task | Sub-task |  | Duplication of Sale ID in fintech transaction table | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 16 | 16 | Muhammad Usman Javed | 8 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-334 | [5 empty] | 2026-02-12T11:10:15.324+0500 | 2026-02-20T16:47:50.826+0500
FF | FF-335 | FF-335 | Sub-task | Sub-task |  | Create a logic app for duplicate rows in Fintech raw tables | Resolved! | 2025-12-21 | 2026-01-22 | 2026-01-21 | 2026-01-23 | 24 | 24 | Muhammad Usman Javed | 24 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-335 | [5 empty] | 2026-02-12T11:12:31.692+0500 | 2026-02-20T16:48:30.760+0500
FF | FF-336 | FF-336 | Sub-task | Sub-task |  | Flushing of data for COCO 5 LHR site as per Affan's instructions | Resolved! | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Muhammad Usman Javed | 8 |  | FF-125 | FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-125 | https://octopusdtlsupport.atlassian.net/browse/FF-336 | [5 empty] | 2026-02-12T11:15:39.324+0500 | 2026-02-20T16:49:46.893+0500
FF | FF-337 | FF-337 | Story | Story |  | Production Release | To Do | 2026-02-27 | 2026-02-27 |  |  | 16 | 16 | Muhammad Usman Javed | 0 |  | FF-314 | FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-337 | [5 empty] | 2026-02-12T11:27:48.312+0500 | 2026-02-23T12:37:53.348+0500
FF | FF-338 | FF-338 | Sub-task | Sub-task |  | Integrating new APIs for Alarms page with Acknowledge functionality | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 4 | 4 | Sarmad Sabir | 4 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-338 | [5 empty] | 2026-02-12T16:27:05.409+0500 | 2026-03-04T12:43:38.070+0500
FF | FF-339 | FF-339 | Sub-task | Sub-task |  | Alarm Triggering Logic | Resolved! | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16 | 16 | Hassan Saeed Wattoo | 16 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-339 | [5 empty] | 2026-02-13T10:02:57.831+0500 | 2026-02-23T13:05:30.623+0500
FF | FF-34 | FF-34 | Bug Subtask | Bug Subtask |  | Login with Microsoft button not clickable | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.5 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-34 | [5 empty] | 2025-10-08T14:22:15.312+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-340 | FF-340 | Sub-task | Sub-task |  | SQL Triggers for Alarm Triggering | Resolved! | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 16 | 16 | Hassan Saeed Wattoo | 16 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-340 | [5 empty] | 2026-02-13T10:04:51.371+0500 | 2026-02-23T13:08:34.112+0500
FF | FF-341 | FF-341 | Sub-task | Sub-task |  | Logic App Development for Email Notifications | Resolved! | 2026-02-12 | 2026-02-16 | 2026-02-13 | 2026-02-13 | 8 | 8 | Muhammad Usman Javed | 8 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-341 | [5 empty] | 2026-02-13T12:26:12.037+0500 | 2026-03-10T11:21:09.413+0500
FF | FF-342 | FF-342 | Sub-task | Sub-task |  | Fintech Mobile App (Fuel Chat) | In-Progress | 2026-02-13 | 2026-02-18 | 2026-02-13 | 2026-02-17 | 32 | 32 | Namra Zahid | 12.83 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-342 | [5 empty] | 2026-02-13T15:21:07.363+0500 | 2026-03-05T10:32:37.600+0500
FF | FF-343 | FF-343 | Epic | Epic |  | Technical Support | In-Progress |  |  |  |  | 2920 | 2920 | Hassan Malik | 44 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-343 | [5 empty] | 2026-02-13T15:40:56.350+0500 | 2026-04-13T15:01:11.920+0500
FF | FF-344 | FF-344 | Sub-task | Sub-task |  | Requirement finalizing, unit testing, task management and staging release preparation | Resolved! | 2026-02-11 | 2026-02-18 | 2026-02-11 | 2026-02-18 | 48 | 48 | Ameer Hamza Khan | 48 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-344 | [5 empty] | 2026-02-16T10:50:05.046+0500 | 2026-03-12T14:01:00.141+0500
FF | FF-345 | FF-345 | Sub-task | Sub-task |  | Improvements in SQL Alarm Triggering Logic | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Hassan Saeed Wattoo | 8 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-345 | [5 empty] | 2026-02-16T11:42:43.749+0500 | 2026-02-17T15:40:17.155+0500
FF | FF-346 | FF-346 | Sub-task | Sub-task |  | Alarm triggering logic + Development | Resolved! | 2026-01-28 | 2026-01-30 | 2026-01-28 | 2026-01-30 | 24 | 24 | Hassan Saeed Wattoo | 24 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-346 | [5 empty] | 2026-02-16T12:04:32.300+0500 | 2026-02-26T10:56:22.554+0500
FF | FF-348 | FF-348 | Story | Story |  | Staging Release | Resolved! | 2026-02-16 | 2026-02-17 |  |  | 16 | 16 | Muhammad Usman Javed | 18.5 |  | FF-314 | FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-348 | [5 empty] | 2026-02-16T16:02:19.495+0500 | 2026-02-23T12:41:53.490+0500
FF | FF-349 | FF-349 | Sub-task | Sub-task |  | Deployment of Backend on Staging | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 8 | 8 | Muhammad Usman Javed | 6 |  | FF-348 | FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-349 | [5 empty] | 2026-02-16T16:05:38.514+0500 | 2026-02-23T12:42:14.043+0500
FF | FF-35 | FF-35 | Bug Subtask | Bug Subtask |  | Data does not align with the Fuel Transaction trend as selected in the filter applied | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-35 | [5 empty] | 2025-10-08T14:23:22.895+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-350 | FF-350 | Sub-task | Sub-task |  | Deployment of Frontend on Staging | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 8 | 8 | Sarmad Sabir | 8 |  | FF-348 | FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-350 | [5 empty] | 2026-02-16T16:06:05.608+0500 | 2026-03-04T12:45:29.284+0500
FF | FF-351 | FF-351 | Sub-task | Sub-task |  | QA Handover | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | Muhammad Usman Javed | 4 |  | FF-348 | FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-351 | [5 empty] | 2026-02-16T16:06:22.066+0500 | 2026-02-23T12:42:36.297+0500
FF | FF-352 | FF-352 | Sub-task | Sub-task |  | Unit Testing with web team | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Hassan Saeed Wattoo | 8 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-352 | [5 empty] | 2026-02-17T09:04:00.905+0500 | 2026-02-20T13:09:04.029+0500
FF | FF-353 | FF-353 | Bug Subtask | Bug Subtask |  | Dashboard and Portal users are not getting logged in on staging environment,Unable to change password through forgot password even , giving this Error. | Resolved | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-124 | FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-124 | https://octopusdtlsupport.atlassian.net/browse/FF-353 | [5 empty] | 2026-02-17T11:49:27.789+0500 | 2026-02-17T12:55:06.775+0500
FF | FF-354 | FF-354 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-02-18 | 2026-02-23 | 2026-02-18 | 2026-02-26 | 32 | 32 | kamran khalid | 39.5 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-354 | [5 empty] | 2026-02-17T12:16:15.029+0500 | 2026-03-03T12:38:33.937+0500
FF | FF-355 | FF-355 | Story | Story |  | QA-Handover | To Do | 2026-02-17 | 2026-02-17 |  |  | 5 | 5 | Muhammad Abbas | 2.75 |  | FF-314 | FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-314 | https://octopusdtlsupport.atlassian.net/browse/FF-355 | [5 empty] | 2026-02-17T15:07:21.996+0500 | 2026-02-17T15:08:04.893+0500
FF | FF-356 | FF-356 | Sub-task | Sub-task |  | Namra | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 0.67 | 0.67 | Namra Zahid | 0.67 |  | FF-355 | FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-356 | [5 empty] | 2026-02-17T15:08:14.262+0500 | 2026-03-09T12:50:45.089+0500
FF | FF-357 | FF-357 | Sub-task | Sub-task |  | M.Abbas | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | Muhammad Abbas | 0.58 |  | FF-355 | FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-357 | [5 empty] | 2026-02-17T15:08:23.268+0500 | 2026-02-17T15:22:51.024+0500
FF | FF-358 | FF-358 | Sub-task | Sub-task |  | Zeeshan | To Do |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | FF-355 | FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-358 | [5 empty] | 2026-02-17T15:08:41.371+0500 | 2026-02-17T15:10:08.463+0500
FF | FF-359 | FF-359 | Sub-task | Sub-task |  | Kamran | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | kamran khalid | 1 |  | FF-355 | FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-359 | [5 empty] | 2026-02-17T15:08:58.681+0500 | 2026-02-17T17:20:24.339+0500
FF | FF-36 | FF-36 | Bug Subtask | Bug Subtask |  | width of the selected option (selected Site) as the UI is disturbed in the filter modal | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.67 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-36 | [5 empty] | 2025-10-08T14:26:46.613+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-360 | FF-360 | Sub-task | Sub-task |  | Waqar | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 0.5 | 0.5 | Waqar Rasheed | 0.5 |  | FF-355 | FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-355 | https://octopusdtlsupport.atlassian.net/browse/FF-360 | [5 empty] | 2026-02-17T15:09:43.942+0500 | 2026-03-09T13:00:51.888+0500
FF | FF-361 | FF-361 | Sub-task | Sub-task |  | QA Handover | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | FF-348 | FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-348 | https://octopusdtlsupport.atlassian.net/browse/FF-361 | [5 empty] | 2026-02-17T15:25:00.408+0500 | 2026-03-04T12:46:38.686+0500
FF | FF-362 | FF-362 | Bug Subtask | Bug Subtask |  | User is able to create alarms with empty conditions | Resolved | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 16 | 16 | Muhammad Usman Javed | 3 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-362 | [5 empty] | 2026-02-18T15:02:44.324+0500 | 2026-02-26T11:26:01.277+0500
FF | FF-363 | FF-363 | Bug Subtask | Bug Subtask |  | Alarms permissions missing for Create, Edit and Delete | Resolved | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 16 | 16 | Muhammad Usman Javed | 3 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-363 | [5 empty] | 2026-02-18T15:04:14.653+0500 | 2026-02-26T11:28:19.396+0500
FF | FF-364 | FF-364 | Bug Subtask | Bug Subtask |  | Delivery Arrival time for alarms mismatch with the original deliveries landed in the prod env | Resolved | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 4 | 4 | Muhammad Usman Javed | 4 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-364 | [5 empty] | 2026-02-18T15:07:56.253+0500 | 2026-03-12T13:29:30.245+0500
FF | FF-365 | FF-365 | Sub-task | Sub-task |  | Add the Setpoints for Alarms triggered such as variance, Tanks Levels and others alarms too where suitable | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-19 | 6 | 6 | Muhammad Usman Javed | 5 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-365 | [5 empty] | 2026-02-18T15:30:33.536+0500 | 2026-03-10T11:22:50.134+0500
FF | FF-366 | FF-366 | Bug Subtask | Bug Subtask |  | While Configuring Condition based alarms if user selects a condition, no option is available to revert it i.e reverting back to single state | Resolved | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 16 | 16 | Muhammad Usman Javed | 1 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-366 | [5 empty] | 2026-02-18T16:50:56.566+0500 | 2026-02-26T11:43:50.219+0500
FF | FF-367 | FF-367 | Sub-task | Sub-task |  | Remove ID's along with entities on all pages | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-367 | [5 empty] | 2026-02-18T16:58:35.437+0500 | 2026-03-10T11:22:57.525+0500
FF | FF-368 | FF-368 | Bug Subtask | Bug Subtask |  | Inactive Customer still showing on staging | Resolved | 2026-02-19 | 2026-02-19 |  |  | 16 | 16 | Muhammad Usman Javed | 0 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-368 | [5 empty] | 2026-02-18T17:00:44.269+0500 | 2026-02-26T11:44:00.252+0500
FF | FF-369 | FF-369 | Bug Subtask | Bug Subtask |  | LOGIN with Microsoft not working | Bug Fixed | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 16 | 16 | Muhammad Usman Javed | 1 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-369 | [5 empty] | 2026-02-18T17:02:35.481+0500 | 2026-02-20T10:43:54.534+0500
FF | FF-37 | FF-37 | Bug Subtask | Bug Subtask |  | Multiple Customers are showing in the customer dropdown in the filter modal | Resolved | 2025-09-30 |  |  |  | 0 | 0 | Muhammad Usman Javed | 8.33 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-37 | [5 empty] | 2025-10-08T14:30:10.769+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-370 | FF-370 | Sub-task | Sub-task |  | Making fuelchat compatible | Resolved! | 2026-02-17 | 2026-02-20 | 2026-02-17 | 2026-02-19 | 24 | 24 | Hassan Saeed Wattoo | 19 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-370 | [5 empty] | 2026-02-19T09:56:30.407+0500 | 2026-03-16T11:45:22.357+0500
FF | FF-371 | FF-371 | Sub-task | Sub-task |  | "<=" amd ">=" conditions missing for Tank Level Alarms & Recon Alarms | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-371 | [5 empty] | 2026-02-19T10:02:18.426+0500 | 2026-03-10T11:23:05.554+0500
FF | FF-372 | FF-372 | Sub-task | Sub-task |  | Integration of backend and frontend | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | Hassan Saeed Wattoo | 6.5 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-372 | [5 empty] | 2026-02-20T16:33:35.028+0500 | 2026-03-12T13:30:40.341+0500
FF | FF-373 | FF-373 | Epic | Epic |  | Fintech Fuel - Regression | In-Progress | 2026-01-01 | 2026-12-31 |  |  | 0 | 0 | Muhammad Abbas | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-373 | [5 empty] | 2026-02-23T09:11:42.329+0500 | 2026-05-12T17:30:30.860+0500
FF | FF-374 | FF-374 | Task | Task |  | Fintech-Regression (2/23/26 - 2/27/26) | Resolved! | 2026-02-23 | 2026-02-27 |  |  | 64 | 64 | Muhammad Abbas | 23.25 |  | FF-373 | FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | [5 empty] | 2026-02-23T09:16:06.410+0500 | 2026-02-27T15:11:07.826+0500
FF | FF-375 | FF-375 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-02-27 | 32 | 32 | Namra Zahid | 36.78 |  | FF-427 | FF-427 | https://octopusdtlsupport.atlassian.net/browse/FF-427 | https://octopusdtlsupport.atlassian.net/browse/FF-375 | [5 empty] | 2026-02-23T09:16:38.459+0500 | 2026-03-03T16:25:00.170+0500
FF | FF-376 | FF-376 | Bug Subtask | Bug Subtask |  | Current Value For Delivery Arrival Alarm triggered is showing value in Percentages% | Resolved | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 16 | 16 | Muhammad Usman Javed | 0.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-376 | [5 empty] | 2026-02-23T09:37:59.335+0500 | 2026-02-26T12:11:08.324+0500
FF | FF-377 | FF-377 | Sub-task | Sub-task |  | Acknowledge Alarm should show the user name by which it is Acknowledge and the acknowledge time also | Resolved! | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-377 | [5 empty] | 2026-02-23T09:46:35.987+0500 | 2026-03-10T11:20:53.751+0500
FF | FF-378 | FF-378 | Bug Subtask | Bug Subtask |  | Variance Alarms Not Triggering Despite Condition Match | Resolved | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2 | 2 | Hassan Saeed Wattoo | 2 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-378 | [5 empty] | 2026-02-23T10:04:47.006+0500 | 2026-02-26T12:15:54.965+0500
FF | FF-379 | FF-379 | Bug Subtask | Bug Subtask |  | User type is not getting changed to AAD User, and showing the error while user tries to login with Microsoft. | Request received | 2026-02-23 | 2026-02-26 |  |  | 16 | 16 | Muhammad Usman Javed | 0 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-379 | [5 empty] | 2026-02-23T10:15:24.757+0500 | 2026-02-23T12:43:38.007+0500
FF | FF-38 | FF-38 | Bug Subtask | Bug Subtask |  | The Recon report which was working earlier just data not matched is now not working | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0.5 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-38 | [5 empty] | 2025-10-08T15:07:16.106+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-380 | FF-380 | Bug Subtask | Bug Subtask |  | Site Dropdown Inactive and doesn't show site name in Alarm Configuration When Single Site Selected in Main Filter | Resolved | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 16 | 16 | Muhammad Usman Javed | 0.25 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-380 | [5 empty] | 2026-02-23T10:20:13.413+0500 | 2026-02-26T14:58:45.504+0500
FF | FF-382 | FF-382 | Bug Subtask | Bug Subtask |  | Forgot Password Functionality if Failed with this error | Resolved | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 16 | 16 | Muhammad Usman Javed | 1 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-382 | [5 empty] | 2026-02-23T11:11:23.462+0500 | 2026-02-25T10:39:11.882+0500
FF | FF-383 | FF-383 | Bug Subtask | Bug Subtask |  | After turning on the OTP, Instead of letting the user to be logged in, its showing the Error | Resolved | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 16 | 16 | Muhammad Usman Javed | 1 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-383 | [5 empty] | 2026-02-23T12:59:00.872+0500 | 2026-02-25T14:58:52.801+0500
FF | FF-384 | FF-384 | Sub-task | Sub-task |  | login with Microsoft functionality should be implemented for dashboard user also. TASK | To Do |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-384 | [5 empty] | 2026-02-23T13:06:20.350+0500 | 2026-02-23T13:06:53.101+0500
FF | FF-385 | FF-385 | Bug Subtask | Bug Subtask |  | Unable to delete alarms | Bug Fixed | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 16 | 16 | Muhammad Usman Javed | 0.25 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-385 | [5 empty] | 2026-02-23T13:19:53.630+0500 | 2026-02-24T14:02:01.119+0500
FF | FF-386 | FF-386 | Bug Subtask | Bug Subtask |  | Inactive (Unacknowledged) Alarms Not Visible in Historical Tab as its showing inthe Data base | Not a Bug | 2026-02-24 | 2026-02-25 |  |  | 16 | 16 | Muhammad Usman Javed | 0 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-386 | [5 empty] | 2026-02-23T14:24:00.308+0500 | 2026-02-24T14:00:45.527+0500
FF | FF-387 | FF-387 | Sub-task | Sub-task |  | Pagination is not applied on alarms screen on configured alarms table | Resolved! | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 0.5 | 0.5 | Muhammad Usman Javed | 0.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-387 | [5 empty] | 2026-02-23T14:33:59.144+0500 | 2026-03-10T11:20:40.208+0500
FF | FF-388 | FF-388 | Bug Subtask | Bug Subtask |  | Application Not Redirecting to Login Page (MAIN URL) After Session Timeout on Refresh | Failed Testing | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 16 | 16 | Muhammad Usman Javed | 0.75 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-388 | [5 empty] | 2026-02-23T14:43:09.884+0500 | 2026-02-26T14:24:06.992+0500
FF | FF-389 | FF-389 | Bug Subtask | Bug Subtask |  | System Allows Creation of Duplicate Notification Groups | Resolved | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-24 | 16 | 16 | Muhammad Usman Javed | 0.25 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-389 | [5 empty] | 2026-02-23T15:03:30.061+0500 | 2026-02-26T11:52:12.677+0500
FF | FF-39 | FF-39 | Bug Subtask | Bug Subtask |  | For specific time filter Day End sales filter is showing data but on the same time duration Day End Sales Summary is not working. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 1 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-39 | [5 empty] | 2025-10-08T15:09:18.155+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-390 | FF-390 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-02-23 | 2026-02-26 | 2026-02-24 | 2026-02-27 | 32 | 32 | Waqar Rasheed | 25.5 |  | FF-427 | FF-427 | https://octopusdtlsupport.atlassian.net/browse/FF-427 | https://octopusdtlsupport.atlassian.net/browse/FF-390 | [5 empty] | 2026-02-24T09:56:24.658+0500 | 2026-03-03T16:26:22.267+0500
FF | FF-391 | FF-391 | Sub-task | Sub-task |  | Unit testing | Resolved! | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5 | 6.5 | Hassan Saeed Wattoo | 4.5 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-391 | [5 empty] | 2026-02-24T10:14:52.327+0500 | 2026-02-26T10:56:53.930+0500
FF | FF-392 | FF-392 | Bug Subtask | Bug Subtask |  | “Account Does Not Exist” Error on Staging and Forgot Password Failure | Resolved | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | 16 | 16 | Muhammad Usman Javed | 0.25 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-392 | [5 empty] | 2026-02-24T10:25:32.377+0500 | 2026-02-24T14:53:00.323+0500
FF | FF-393 | FF-393 | Bug Subtask | Bug Subtask |  | Selected Sites Not Displayed in Site Field (Deliveries Screen) — Implement Fix Across Application | Resolved |  |  | 2026-02-24 | 2026-02-24 | 0 | 0 | Muhammad Usman Javed | 2 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-393 | [5 empty] | 2026-02-24T10:54:51.252+0500 | 2026-02-24T14:52:53.866+0500
FF | FF-394 | FF-394 | Bug Subtask | Bug Subtask |  | Search Functionality Limited to Site Name and Article Columns on Deliveries Screen | Resolved |  |  | 2026-02-26 | 2026-02-26 | 0 | 0 | Muhammad Usman Javed | 0.5 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-394 | [5 empty] | 2026-02-24T11:11:36.357+0500 | 2026-02-27T10:31:08.816+0500
FF | FF-395 | FF-395 | Bug Subtask | Bug Subtask |  | Date Filter on Deliveries Screen Returns Data Outside Selected Date Range | Resolved | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 16 | 16 | Muhammad Usman Javed | 0.25 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-395 | [5 empty] | 2026-02-24T11:31:18.860+0500 | 2026-02-25T15:05:11.286+0500
FF | FF-396 | FF-396 | Bug Subtask | Bug Subtask |  | Validation Error Placement and Value Reset Issue When Entering Quantity Greater Than Capacity on Deliveries screen | Resolved | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 16 | 16 | Muhammad Usman Javed | 0.25 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-396 | [5 empty] | 2026-02-24T11:57:39.825+0500 | 2026-02-25T15:11:07.751+0500
FF | FF-397 | FF-397 | Bug Subtask | Bug Subtask |  | Updated Time Field Not Refreshing on Alarm Activation/Deactivation | QA Testing | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 16 | 16 | Muhammad Usman Javed | 1 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-397 | [5 empty] | 2026-02-24T12:07:06.336+0500 | 2026-02-26T14:27:38.218+0500
FF | FF-398 | FF-398 | Bug Subtask | Bug Subtask |  | “Submit Values” Button Enabled by Default on Deliveries Screen even when the Confirmed Quantity field and Bill of Lading Reference field is empty | Resolved | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 0.75 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-398 | [5 empty] | 2026-02-24T12:12:34.466+0500 | 2026-02-26T15:28:13.208+0500
FF | FF-399 | FF-399 | Bug Subtask | Bug Subtask |  | Warning Status Displayed for 3 Days Remaining on Low Stock Screen | Resolved | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 16 | 16 | Muhammad Usman Javed | 0.25 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-399 | [5 empty] | 2026-02-25T09:56:47.416+0500 | 2026-02-25T15:16:50.430+0500
FF | FF-4 | FF-4 | Story | Story |  | Transaction | Resolved! | 2025-09-11 | 2025-09-13 |  |  | 16 | 16 | kamran khalid | 9 |  | FF-1 | FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-4 | [5 empty] | 2025-10-03T19:40:57.067+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-40 | FF-40 | Sub-task | Sub-task |  | kindly remove the user profile image selecting option as its no longer required | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 0.83 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-40 | [5 empty] | 2025-10-08T15:10:10.456+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-400 | FF-400 | Sub-task | Sub-task |  | Improvements after unit testing | Resolved! | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-03-02 | 16 | 16 | Hassan Saeed Wattoo | 16.5 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-400 | [5 empty] | 2026-02-25T10:01:45.475+0500 | 2026-03-02T15:22:31.166+0500
FF | FF-401 | FF-401 | Bug Subtask | Bug Subtask |  | Support Icon Overlapping with “Next” Pagination Text on Low Stock Screen | Resolved | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 16 | 16 | Muhammad Usman Javed | 1 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-401 | [5 empty] | 2026-02-25T10:33:38.620+0500 | 2026-02-25T15:17:51.134+0500
FF | FF-402 | FF-402 | Sub-task | Sub-task |  | While Editing an existing alarm, the fields Customer, Sites, Alarm Type, and Sub Alarm Type should not be editable. | Resolved! | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-25 | 2 | 2 | Muhammad Usman Javed | 1 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-402 | [5 empty] | 2026-02-25T10:43:25.256+0500 | 2026-03-10T11:20:27.844+0500
FF | FF-403 | FF-403 | Bug Subtask | Bug Subtask |  | Search and Filter Functionality Not Working Correctly on Deliveries Screen | Resolved | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 0.5 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-403 | [5 empty] | 2026-02-25T13:35:30.137+0500 | 2026-02-27T10:28:36.444+0500
FF | FF-404 | FF-404 | Bug Subtask | Bug Subtask |  | Summary Metrics Not Updating According to Applied Search on Deliveries Screen | Resolved | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 0.5 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-404 | [5 empty] | 2026-02-25T13:53:09.818+0500 | 2026-02-27T10:26:59.015+0500
FF | FF-405 | FF-405 | Bug Subtask | Bug Subtask |  | Inconsistent Timestamp Format on Deliveries Screen | Resolved | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 0.5 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-405 | [5 empty] | 2026-02-25T15:06:55.056+0500 | 2026-03-02T15:41:49.351+0500
FF | FF-406 | FF-406 | Bug Subtask | Bug Subtask |  | Diagnostics Dashboard is loading data for sites other than the customer selected and this user has not access to Aramco sites | Resolved | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 3 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-406 | [5 empty] | 2026-02-25T15:30:08.178+0500 | 2026-03-02T15:49:54.231+0500
FF | FF-407 | FF-407 | Bug Subtask | Bug Subtask |  | Tooltip Color Mismatch on Loss/Gain Chart Screen | Resolved | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 16 | 16 | Muhammad Usman Javed | 1.5 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-407 | [5 empty] | 2026-02-26T11:30:17.621+0500 | 2026-02-27T10:22:57.757+0500
FF | FF-408 | FF-408 | Bug Subtask | Bug Subtask |  | Stock Volume Mismatch Between Loss/Gain Chart and Recon Report (Hi Super & Excellium) | Development |  |  | 2026-03-27 | 2026-03-27 | 0 | 0 | Hassan Saeed Wattoo | 4 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-408 | [5 empty] | 2026-02-26T11:58:26.960+0500 | 2026-04-02T10:07:38.257+0500
FF | FF-409 | FF-409 | Sub-task | Sub-task |  | ADD Scroll functionality for Notification Group Section | Resolved! | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.02 | 0.02 | Muhammad Usman Javed | 0.02 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-409 | [5 empty] | 2026-02-26T14:22:04.505+0500 | 2026-03-10T11:40:04.318+0500
FF | FF-41 | FF-41 | Sub-task | Sub-task |  | Kindly update the Update button name to generate report | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 0.67 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-41 | [5 empty] | 2025-10-08T15:21:33.563+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-410 | FF-410 | Sub-task | Sub-task |  | ADD pagination in the following screens 1. Recipients Groups 2. Diagnostic Configuration tabs in the Notifications group | Resolved! | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-26 | 0.5 | 0.5 | Muhammad Usman Javed | 0.25 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-410 | [5 empty] | 2026-02-26T14:40:31.887+0500 | 2026-03-10T11:19:47.876+0500
FF | FF-411 | FF-411 | Bug Subtask | Bug Subtask |  | Opening Level Field Not Editable for Non-Consecutive Days on Submit Data Screen | Bug Fixed | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-18 | 16 | 16 | Sarmad Sabir | 5 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-411 | [5 empty] | 2026-02-26T15:08:35.208+0500 | 2026-04-08T12:13:30.532+0500
FF | FF-412 | FF-412 | Bug Subtask | Bug Subtask |  | Side Menu “Submit Data” Tab Not Highlighted on Day Submission Screen | Resolved | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 16 | 16 | Muhammad Usman Javed | 1 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-412 | [5 empty] | 2026-02-26T15:16:40.634+0500 | 2026-04-13T11:24:24.465+0500
FF | FF-413 | FF-413 | Sub-task | Sub-task |  | Actual Closing Field Should Auto-Populate and Be Non-Editable on Submit Data Screen. Also add respective unit with each column | Resolved! | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 3 | 3 | Muhammad Usman Javed | 3 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-413 | [5 empty] | 2026-02-26T15:22:34.835+0500 | 2026-03-10T11:29:14.629+0500
FF | FF-414 | FF-414 | Story | Story |  | User Manual | Resolved! | 2026-03-11 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 8 | 8 | Hassan Malik | 0.5 |  | FF-271 | FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-414 | [5 empty] | 2026-02-27T10:08:16.765+0500 | 2026-04-01T10:02:26.783+0500
FF | FF-415 | FF-415 | Story | Story |  | Production Release | Resolved! |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-271 | FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-271 | https://octopusdtlsupport.atlassian.net/browse/FF-415 | [5 empty] | 2026-02-27T10:10:18.025+0500 | 2026-04-23T15:41:59.960+0500
FF | FF-416 | FF-416 | Story | Story |  | Production | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-274 | FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-416 | [5 empty] | 2026-02-27T10:12:28.783+0500 | 2026-02-27T10:12:53.902+0500
FF | FF-417 | FF-417 | Sub-task | Sub-task |  | Testing for fuelchat | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8 | 8 | Hassan Saeed Wattoo | 6.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-417 | [5 empty] | 2026-03-02T15:24:04.881+0500 | 2026-03-16T11:41:18.624+0500
FF | FF-418 | FF-418 | Bug Subtask | Bug Subtask |  | Pagination malfunction on Deliveries page | Bug Fixed | 2026-03-05 |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-374 | FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-374 | https://octopusdtlsupport.atlassian.net/browse/FF-418 | [5 empty] | 2026-03-02T15:31:01.720+0500 | 2026-04-08T12:13:33.329+0500
FF | FF-419 | FF-419 | Sub-task | Sub-task |  | Diagnostic Dashboard displaying timestamps in UTC instead of Local Time Zone | Resolved! | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 2 | 2 | Muhammad Usman Javed | 2 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-419 | [5 empty] | 2026-03-02T15:52:15.331+0500 | 2026-03-10T11:30:53.635+0500
FF | FF-42 | FF-42 | Bug Subtask | Bug Subtask |  | When user apply the filter for 6 days and calculate the recon the data is not fetched. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0.5 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-42 | [5 empty] | 2025-10-08T15:23:38.446+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-420 | FF-420 | Bug Subtask | Bug Subtask |  | Active and Inactive Site Status Count should not Dependent on Grid Pagination | QA Testing | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 8 | 8 | Muhammad Usman Javed | 2 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-420 | [5 empty] | 2026-03-03T11:07:27.966+0500 | 2026-03-18T07:36:05.900+0500
FF | FF-421 | FF-421 | Bug Subtask | Bug Subtask |  | “Per Site” Tab on Diagnostic Dashboard Displays Only Inactive Sites | Not a Bug | 2026-03-05 | 2026-03-09 |  |  | 2 | 2 | Muhammad Usman Javed | 0 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-421 | [5 empty] | 2026-03-03T11:11:13.811+0500 | 2026-03-05T13:14:55.888+0500
FF | FF-422 | FF-422 | Bug Subtask | Bug Subtask |  | Notification Groups Can Be Created Using Only Numbers or Special Characters | Bug Fixed | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 8 | 8 | Muhammad Usman Javed | 2 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-422 | [5 empty] | 2026-03-03T12:06:56.502+0500 | 2026-03-05T14:49:15.776+0500
FF | FF-423 | FF-423 | Bug Subtask | Bug Subtask |  | The Diagnostic Icon on the Top right bar shows notification number as "3" but in actual the customer has only one site and two activities in total | QA Testing | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-03-04 | 8 | 8 | Muhammad Usman Javed | 3 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-423 | [5 empty] | 2026-03-03T12:24:19.698+0500 | 2026-03-18T15:56:56.125+0500
FF | FF-424 | FF-424 | Sub-task | Sub-task |  | The SITE LEVEL ALARM (Connectivity / Disconnectivity) email should not contain Tank ID and Tank Capacity and Current Value | To Do |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-424 | [5 empty] | 2026-03-03T12:32:20.602+0500 | 2026-03-04T14:45:07.016+0500
FF | FF-425 | FF-425 | Sub-task | Sub-task |  | Integrate Additional Modules into Fuel Chat | Resolved! |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 0 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-425 | [5 empty] | 2026-03-03T14:57:35.920+0500 | 2026-03-30T11:08:09.655+0500
FF | FF-426 | FF-426 | Sub-task | Sub-task |  | Testing by Kamran | In-Progress |  |  | 2026-02-25 | 2026-03-05 | 40 | 40 | kamran khalid | 39.5 |  | FF-278 | FF-278 | https://octopusdtlsupport.atlassian.net/browse/FF-278 | https://octopusdtlsupport.atlassian.net/browse/FF-426 | [5 empty] | 2026-03-03T15:58:39.518+0500 | 2026-03-05T16:10:51.050+0500
FF | FF-427 | FF-427 | Story | Story |  | Fintech-Regression (2/23/26 - 2/27/26) | Resolved! | 2026-02-23 | 2026-02-27 |  |  | 64 | 64 | Muhammad Abbas | 62.28 |  | FF-373 | FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-427 | [5 empty] | 2026-03-03T16:22:03.657+0500 | 2026-03-10T10:01:46.472+0500
FF | FF-428 | FF-428 | Sub-task | Sub-task |  | Testing by Namra | In-Progress | 2026-01-08 | 2026-02-12 | 2026-02-02 | 2026-02-12 | 48 | 48 | Namra Zahid | 48 |  | FF-121 | FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-121 | https://octopusdtlsupport.atlassian.net/browse/FF-428 | [5 empty] | 2026-03-04T09:58:48.969+0500 | 2026-03-05T09:52:47.360+0500
FF | FF-429 | FF-429 | Bug Subtask | Bug Subtask |  | Connectivity Alarms Not Visible on Dashboard Despite Email Notifications | Not a Bug | 2026-03-05 | 2026-03-09 |  |  | 2 | 2 | Muhammad Usman Javed | 0 |  | FF-277 | FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-277 | https://octopusdtlsupport.atlassian.net/browse/FF-429 | [5 empty] | 2026-03-04T11:32:10.755+0500 | 2026-03-05T13:36:11.697+0500
FF | FF-43 | FF-43 | Bug Subtask | Bug Subtask |  | API Failure error when user tries to visit to Nozzle usage link while the Main Filter Modal is open. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.67 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-43 | [5 empty] | 2025-10-08T15:24:39.075+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-430 | FF-430 | Bug Subtask | Bug Subtask |  | Mismatch in Configured Alarms for ROSE MOUNT Between Dashboard and Fuel Chat | Bug Fixed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1 | 1 | Hassan Saeed Wattoo | 1 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-430 | [5 empty] | 2026-03-04T12:35:38.885+0500 | 2026-03-04T15:23:19.337+0500
FF | FF-431 | FF-431 | Bug Subtask | Bug Subtask |  | Created Date and Updated Date format is not correct in the CSV downloaded from FUEL chat for Configured Alarms | Bug Fixed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 0.5 | 0.5 | Hassan Saeed Wattoo | 0.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-431 | [5 empty] | 2026-03-04T12:40:29.716+0500 | 2026-03-04T15:22:23.739+0500
FF | FF-432 | FF-432 | Bug Subtask | Bug Subtask |  | Updated time is missing for some alarms on Fuel Chat | QA Testing | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 2 | 2 | Muhammad Usman Javed | 0.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-432 | [5 empty] | 2026-03-04T12:55:03.367+0500 | 2026-03-18T07:25:16.779+0500
FF | FF-433 | FF-433 | Bug Subtask | Bug Subtask |  | Some of Inactive Alarms Missing in Fuel Chat Despite Being Present on Dashboard | Bug Fixed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1 | 1 | Hassan Saeed Wattoo | 1 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-433 | [5 empty] | 2026-03-04T13:08:02.405+0500 | 2026-03-04T15:22:02.413+0500
FF | FF-434 | FF-434 | Bug Subtask | Bug Subtask |  | Fuel Chat Missed Disconnectivity Event Displayed on Dashboard | Bug Fixed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1 | 1 | Hassan Saeed Wattoo | 1 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-434 | [5 empty] | 2026-03-04T13:15:00.236+0500 | 2026-03-04T15:21:36.949+0500
FF | FF-435 | FF-435 | Bug Subtask | Bug Subtask |  | Fuel Chat Not Displaying Tank-Wise Delivery Alarms as Shown on Dashboard | Bug Fixed |  |  | 2026-03-04 | 2026-03-04 | 0 | 0 | Hassan Saeed Wattoo | 1 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-435 | [5 empty] | 2026-03-04T13:20:43.626+0500 | 2026-03-04T15:21:06.612+0500
FF | FF-436 | FF-436 | Bug Subtask | Bug Subtask |  | Fuel Chat Not Retrieving Alarm Trigger Conditions | Bug Fixed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2 | 2 | Hassan Saeed Wattoo | 1.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-436 | [5 empty] | 2026-03-04T13:27:01.378+0500 | 2026-03-05T12:45:15.450+0500
FF | FF-437 | FF-437 | Bug Subtask | Bug Subtask |  | Fuel Chat Not Displaying Only Active Notification Groups Used in Alarm Configuration | Not a Bug |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 0 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-437 | [5 empty] | 2026-03-04T13:40:41.198+0500 | 2026-03-04T15:20:46.226+0500
FF | FF-438 | FF-438 | Bug Subtask | Bug Subtask |  | Fuel Chat Session Does Not Expire After Inactivity | Failed Testing | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 | 8 | 8 | Muhammad Usman Javed | 0.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-438 | [5 empty] | 2026-03-04T14:31:46.642+0500 | 2026-03-18T07:27:14.499+0500
FF | FF-439 | FF-439 | Sub-task | Sub-task |  | Alson Device Integration R&D | Resolved! | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-03-04 | 16 | 16 | Muhammad Usman Javed | 3 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-439 | [5 empty] | 2026-03-04T14:44:38.667+0500 | 2026-03-12T11:38:12.124+0500
FF | FF-44 | FF-44 | Bug Subtask | Bug Subtask |  | The SMTP email issue, Emails not sending to users through both the “Forgot Password” and new user activation emails depend on it. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0.5 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-44 | [5 empty] | 2025-10-08T15:27:35.106+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-440 | FF-440 | Bug Subtask | Bug Subtask |  | Duplicates found in terms of Notification groups in Fuel Chat | Bug Fixed | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 0.5 | 0.5 | Hassan Saeed Wattoo | 0.5 |  | FF-315 | FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-315 | https://octopusdtlsupport.atlassian.net/browse/FF-440 | [5 empty] | 2026-03-04T14:46:57.476+0500 | 2026-03-04T15:23:54.653+0500
FF | FF-441 | FF-441 | Sub-task | Sub-task |  | R&D: ALSONS device data format & ingestion approach | Resolved! | 2026-02-01 |  | 2026-02-02 | 2026-03-03 | 24 | 24 | yousha.agha | 24 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-441 | [5 empty] | 2026-03-05T11:02:46.499+0500 | 2026-03-05T13:25:33.547+0500
FF | FF-442 | FF-442 | Sub-task | Sub-task |  | R&D on Tank Level Data and Delivery Detection Logic | Resolved! | 2026-03-03 | 2026-03-06 | 2026-03-03 | 2026-03-06 | 24 | 24 | Hassan Saeed Wattoo | 19.5 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-442 | [5 empty] | 2026-03-05T12:46:02.817+0500 | 2026-03-09T11:41:53.282+0500
FF | FF-443 | FF-443 | Sub-task | Sub-task |  | Design & Develop: Ingestion MQTT Broker service | Resolved! | 2026-02-05 | 2026-02-12 | 2026-02-05 | 2026-03-12 | 56 | 56 | yousha.agha | 56 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-443 | [5 empty] | 2026-03-05T13:17:03.607+0500 | 2026-03-05T13:25:30.215+0500
FF | FF-444 | FF-444 | Sub-task | Sub-task |  | Implement: Buffering & backpressure (MQTT-ETL) | Resolved! | 2026-02-16 | 2026-02-20 | 2026-02-16 | 2026-03-20 | 40 | 40 | yousha.agha | 41 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-444 | [5 empty] | 2026-03-05T13:22:49.027+0500 | 2026-03-12T14:08:12.470+0500
FF | FF-445 | FF-445 | Sub-task | Sub-task |  | Build: ETL flow to land raw data on SFTP | Resolved! | 2026-02-21 | 2026-02-28 | 2026-03-21 | 2026-03-26 | 56 | 56 | yousha.agha | 40 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-445 | [5 empty] | 2026-03-05T13:25:55.748+0500 | 2026-03-13T12:35:13.310+0500
FF | FF-446 | FF-446 | Epic | Epic |  | Audit trails (phase 1) - User-management | On Hold | 2026-05-18 | 2026-06-04 |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-446 | [5 empty] | 2026-03-05T13:54:33.894+0500 | 2026-04-09T16:20:48.044+0500
FF | FF-447 | FF-447 | Story | Story |  | Development | On Hold | 2026-02-13 | 2026-03-10 |  |  | 160 | 160 | Muhammad Usman Javed | 5 |  | FF-446 | FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-447 | [5 empty] | 2026-03-05T13:56:09.479+0500 | 2026-04-22T11:05:18.509+0500
FF | FF-448 | FF-448 | Sub-task | Sub-task |  | Database Schema Design | Resolved! | 2026-02-02 | 2026-02-03 | 2026-02-02 | 2026-02-02 | 8 | 8 | Muhammad Usman Javed | 2 |  | FF-447 | FF-447 | https://octopusdtlsupport.atlassian.net/browse/FF-447 | https://octopusdtlsupport.atlassian.net/browse/FF-448 | [5 empty] | 2026-03-05T13:57:38.666+0500 | 2026-03-10T11:24:40.817+0500
FF | FF-449 | FF-449 | Sub-task | Sub-task |  | Backend Development | Resolved! | 2026-02-09 | 2026-02-12 | 2026-02-10 | 2026-02-12 | 16 | 16 | Muhammad Usman Javed | 3 |  | FF-447 | FF-447 | https://octopusdtlsupport.atlassian.net/browse/FF-447 | https://octopusdtlsupport.atlassian.net/browse/FF-449 | [5 empty] | 2026-03-05T13:57:51.318+0500 | 2026-03-10T11:27:56.502+0500
FF | FF-45 | FF-45 | Bug Subtask | Bug Subtask |  | The issue is arising for Newly created users as the activation links redirects to 404 Error page | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0.5 |  | FF-5 | FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | https://octopusdtlsupport.atlassian.net/browse/FF-45 | [5 empty] | 2025-10-08T15:29:22.925+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-450 | FF-450 | Sub-task | Sub-task |  | SQA Handover | Resolved! | 2026-03-06 | 2026-03-06 |  |  | 8 | 8 | Muhammad Usman Javed | 0 |  | FF-447 | FF-447 | https://octopusdtlsupport.atlassian.net/browse/FF-447 | https://octopusdtlsupport.atlassian.net/browse/FF-450 | [5 empty] | 2026-03-05T14:01:41.961+0500 | 2026-04-09T16:21:49.151+0500
FF | FF-451 | FF-451 | Sub-task | Sub-task |  | Develop VM ETL to transform incoming files/data - PART B | Resolved! | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-06 | 32.5 | 32.5 | yousha.agha | 40 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-451 | [5 empty] | 2026-03-06T14:35:09.137+0500 | 2026-03-31T11:13:15.166+0500
FF | FF-452 | FF-452 | Sub-task | Sub-task |  | Implement and Test Logic on Dummy Delivery Table | Resolved! | 2026-03-10 | 2026-03-12 | 2026-03-10 | 2026-03-12 | 24 | 24 | Hassan Saeed Wattoo | 19.5 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-452 | [5 empty] | 2026-03-09T11:38:00.121+0500 | 2026-04-09T16:57:43.620+0500
FF | FF-453 | FF-453 | Sub-task | Sub-task |  | SP for Product-wise and Tank-wise Reconciliation | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 8 | 8 | Hassan Saeed Wattoo | 6.5 |  | FF-275 | FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-453 | [5 empty] | 2026-03-09T11:40:57.690+0500 | 2026-03-12T10:28:50.934+0500
FF | FF-454 | FF-454 | Sub-task | Sub-task |  | Integrate Logic with Logic App and Validate | Resolved! | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-16 | 16 | 16 | Hassan Saeed Wattoo | 13 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-454 | [5 empty] | 2026-03-09T11:42:19.324+0500 | 2026-04-09T16:57:47.382+0500
FF | FF-455 | FF-455 | Bug Subtask | Bug Subtask |  | Incorrect Side Navigation and Message Box Visibility Issue on Fuel Chat Screen | Resolved | 2026-03-18 | 2026-03-18 |  |  | 2 | 2 | Sarmad Sabir | 0 |  | FF-316 | FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-316 | https://octopusdtlsupport.atlassian.net/browse/FF-455 | [5 empty] | 2026-03-09T11:43:06.602+0500 | 2026-04-13T11:23:10.792+0500
FF | FF-456 | FF-456 | Story | Story |  | Fintech-Staging-Regression(3/10/2026 - 3/17/2026) | To Do | 2026-03-10 | 2026-03-17 |  |  | 80 | 80 | kamran khalid | 40 |  | FF-373 | FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-456 | [5 empty] | 2026-03-10T10:03:09.364+0500 | 2026-03-10T10:03:43.089+0500
FF | FF-457 | FF-457 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-03-10 | 2026-03-13 | 2026-03-10 | 2026-03-10 | 24 | 24 | kamran khalid | 8 |  | FF-456 | FF-456 | https://octopusdtlsupport.atlassian.net/browse/FF-456 | https://octopusdtlsupport.atlassian.net/browse/FF-457 | [5 empty] | 2026-03-10T10:03:54.836+0500 | 2026-05-12T15:36:31.713+0500
FF | FF-458 | FF-458 | Sub-task | Sub-task |  | API Development Architecture Rework | Resolved! | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-03-12 | 40 | 40 | Muhammad Usman Javed | 35 |  | FF-275 | FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-458 | [5 empty] | 2026-03-10T12:40:45.155+0500 | 2026-03-12T11:41:10.984+0500
FF | FF-459 | FF-459 | Sub-task | Sub-task |  | Testing By Kamran | In-Progress | 2026-03-11 |  | 2026-03-11 | 2026-03-25 | 40 | 40 | kamran khalid | 49 |  | FF-289 | FF-289 | https://octopusdtlsupport.atlassian.net/browse/FF-289 | https://octopusdtlsupport.atlassian.net/browse/FF-459 | [5 empty] | 2026-03-11T15:38:11.943+0500 | 2026-03-26T13:48:21.467+0500
FF | FF-460 | FF-460 | Sub-task | Sub-task |  | QA Handover | Resolved! | 2026-02-23 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 0 | 0 | Muhammad Usman Javed | 2 |  | FF-276 | FF-276 | https://octopusdtlsupport.atlassian.net/browse/FF-276 | https://octopusdtlsupport.atlassian.net/browse/FF-460 | [5 empty] | 2026-03-12T11:26:12.798+0500 | 2026-03-12T11:27:15.566+0500
FF | FF-461 | FF-461 | Sub-task | Sub-task |  | Create a Demo Web Application for PGL | Resolved! | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-17 | 24 | 24 | Muhammad Usman Javed | 20 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-461 | [5 empty] | 2026-03-12T11:38:52.769+0500 | 2026-03-17T13:57:18.542+0500
FF | FF-462 | FF-462 | Sub-task | Sub-task |  | Initial requirements gathering and finalizing | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-311 | FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-462 | [5 empty] | 2026-03-12T13:47:33.251+0500 | 2026-03-12T13:55:33.373+0500
FF | FF-463 | FF-463 | Sub-task | Sub-task |  | Screen Designing and UI/UX creation | Resolved! | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-05 | 16 | 16 | Ameer Hamza Khan | 16 |  | FF-311 | FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-463 | [5 empty] | 2026-03-12T13:48:15.063+0500 | 2026-03-12T13:56:17.945+0500
FF | FF-464 | FF-464 | Sub-task | Sub-task |  | Database schema designing | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-311 | FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-464 | [5 empty] | 2026-03-12T13:48:36.299+0500 | 2026-03-12T13:56:46.930+0500
FF | FF-465 | FF-465 | Sub-task | Sub-task |  | Finalizing development and unit testing with team | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-311 | FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-465 | [5 empty] | 2026-03-12T13:50:59.824+0500 | 2026-03-12T13:57:17.850+0500
FF | FF-466 | FF-466 | Sub-task | Sub-task |  | Preparing for staging release and handover | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-311 | FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-311 | https://octopusdtlsupport.atlassian.net/browse/FF-466 | [5 empty] | 2026-03-12T13:51:27.990+0500 | 2026-03-12T13:57:49.605+0500
FF | FF-467 | FF-467 | Sub-task | Sub-task |  | Develop VM ETL to transform incoming files/data - PART A | Resolved! | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-03-27 | 19.5 | 19.5 | yousha.agha | 24 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-467 | [5 empty] | 2026-03-12T14:13:31.332+0500 | 2026-03-31T11:11:41.580+0500
FF | FF-468 | FF-468 | Sub-task | Sub-task |  | Develop VM ETL to transform incoming files/data - PART C | Resolved! | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 32.5 | 32.5 | yousha.agha | 40 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-468 | [5 empty] | 2026-03-12T14:15:18.956+0500 | 2026-03-31T11:14:42.965+0500
FF | FF-469 | FF-469 | Sub-task | Sub-task |  | SQL Insertion Pipeline for PGL Demo | Resolved! | 2026-03-16 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 40 | 40 | yousha.agha | 8 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-469 | [5 empty] | 2026-03-13T12:34:42.237+0500 | 2026-04-09T10:20:04.161+0500
FF | FF-471 | FF-471 | Bug Subtask | Bug Subtask |  | Product Availability Percentage showing 0 despite Available Volume having value in API response | Resolved | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-291 | FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-471 | [5 empty] | 2026-03-17T13:38:58.226+0500 | 2026-03-26T10:49:55.731+0500
FF | FF-472 | FF-472 | Bug Subtask | Bug Subtask |  | Read API not returning all deliveries within the specified 'FromDate' and 'ToDate' range | Resolved | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2 | 2 | Muhammad Usman Javed | 1 |  | FF-291 | FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-472 | [5 empty] | 2026-03-17T13:40:59.176+0500 | 2026-03-26T10:50:54.727+0500
FF | FF-473 | FF-473 | Bug Subtask | Bug Subtask |  | Read API (Get Tank Levels) returning data for Customer and Site not assigned to the authenticated user | Resolved | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 3 | 3 | Muhammad Usman Javed | 3 |  | FF-291 | FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-473 | [5 empty] | 2026-03-17T13:43:22.900+0500 | 2026-03-26T10:51:10.780+0500
FF | FF-474 | FF-474 | Bug Subtask | Bug Subtask |  | The API accepts multiple parameters with the same name in the request but processes only the first parameter value while ignoring the remaining values without validation or error response. | Not a Bug | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1 | 1 | Muhammad Usman Javed | 1 |  | FF-291 | FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-474 | [5 empty] | 2026-03-17T13:45:18.247+0500 | 2026-03-26T10:51:28.132+0500
FF | FF-475 | FF-475 | Sub-task | Sub-task |  | Enhance Read API to support multiple site inputs for a single customer | On Hold |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-291 | FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-475 | [5 empty] | 2026-03-17T14:03:20.231+0500 | 2026-04-23T15:39:30.343+0500
FF | FF-476 | FF-476 | Story | Story |  | PGL - Fintech Fuel Functional and Architectural Document | In-Progress | 2026-03-13 | 2026-03-17 |  |  | 0 | 0 | Hassan Malik | 34 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-476 | [5 empty] | 2026-03-17T15:27:04.612+0500 | 2026-03-17T15:27:53.501+0500
FF | FF-477 | FF-477 | Sub-task | Sub-task |  | Documentation | Resolved! | 2026-03-16 | 2026-03-17 | 2026-03-16 | 2026-03-17 | 10.5 | 10.5 | Hassan Malik | 10 |  | FF-476 | FF-476 | https://octopusdtlsupport.atlassian.net/browse/FF-476 | https://octopusdtlsupport.atlassian.net/browse/FF-477 | [5 empty] | 2026-03-17T15:27:30.846+0500 | 2026-03-17T15:30:33.010+0500
FF | FF-478 | FF-478 | Sub-task | Sub-task |  | Kindly provide Formula to calculate Variance and Variance Percentage only in Tank Levels | On Hold |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-291 | FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-478 | [5 empty] | 2026-03-18T06:43:21.671+0500 | 2026-04-23T15:39:36.435+0500
FF | FF-479 | FF-479 | Sub-task | Sub-task |  | Alson data understanding to modify the SP accordingly | Resolved! | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-24 | 16 | 16 | Hassan Saeed Wattoo | 20 |  | FF-293 | FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-293 | https://octopusdtlsupport.atlassian.net/browse/FF-479 | [5 empty] | 2026-03-18T10:53:53.156+0500 | 2026-04-09T16:57:53.454+0500
FF | FF-48 | FF-48 | Bug Subtask | Bug Subtask |  | Update the unit From Dollars to PKR as highlighted in the screenshot | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-48 | [5 empty] | 2025-10-08T15:44:50.642+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-480 | FF-480 | Bug Subtask | Bug Subtask |  | The Get Transaction Summarized By Product API does not return aggregated (summarized) results for the provided date range. Instead of combining the data, the API response includes separate entries for each day within the range. | On Hold | 2026-03-25 | 2026-03-25 |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-291 | FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-291 | https://octopusdtlsupport.atlassian.net/browse/FF-480 | [5 empty] | 2026-03-18T16:28:32.157+0500 | 2026-04-23T15:39:45.604+0500
FF | FF-481 | FF-481 | Sub-task | Sub-task |  | Addressing client's queries, review and finalizing documentation | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-476 | FF-476 | https://octopusdtlsupport.atlassian.net/browse/FF-476 | https://octopusdtlsupport.atlassian.net/browse/FF-481 | [5 empty] | 2026-03-24T10:46:15.066+0500 | 2026-03-24T10:47:38.603+0500
FF | FF-482 | FF-482 | Sub-task | Sub-task |  | Internal data source backup and restoring(on local machine) practice | Resolved! | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2026-03-25 | 16 | 16 | Ameer Hamza Khan | 16 |  | FF-476 | FF-476 | https://octopusdtlsupport.atlassian.net/browse/FF-476 | https://octopusdtlsupport.atlassian.net/browse/FF-482 | [5 empty] | 2026-03-24T16:05:37.784+0500 | 2026-03-26T16:46:40.087+0500
FF | FF-483 | FF-483 | Story | Story |  | Research | Resolved! | 2026-03-26 | 2026-04-09 |  |  | 80 | 80 | Ameer Hamza Khan | 94 |  | FF-297 | FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-483 | [5 empty] | 2026-03-26T16:49:01.240+0500 | 2026-04-15T10:42:55.452+0500
FF | FF-484 | FF-484 | Sub-task | Sub-task |  | Requirements understanding and analyzing | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-483 | FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-484 | [5 empty] | 2026-03-26T16:53:44.889+0500 | 2026-03-26T16:58:02.133+0500
FF | FF-485 | FF-485 | Sub-task | Sub-task |  | Requirements gathering | Resolved! | 2026-03-26 | 2026-03-30 | 2026-03-26 | 2026-04-01 | 8 | 8 | Muhammad Usman Javed | 24 |  | FF-483 | FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-485 | [5 empty] | 2026-03-30T10:17:57.202+0500 | 2026-04-02T11:39:04.916+0500
FF | FF-486 | FF-486 | Sub-task | Sub-task |  | Database schema design planning | Resolved! | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | Muhammad Usman Javed | 8 |  | FF-483 | FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-486 | [5 empty] | 2026-03-30T10:18:18.447+0500 | 2026-03-30T10:23:05.983+0500
FF | FF-487 | FF-487 | Story | Story |  | SQA Fuel Chat | To Do | 2026-04-01 | 2026-04-30 |  |  | 32 | 32 | Muhammad Imran Aslam | 32 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-487 | [5 empty] | 2026-03-30T11:55:42.180+0500 | 2026-03-30T12:05:54.479+0500
FF | FF-488 | FF-488 | Sub-task | Sub-task |  | Fintech Fuel Chat Testing | Resolved! | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-487 | FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-488 | [5 empty] | 2026-03-30T12:14:35.630+0500 | 2026-04-20T11:28:13.353+0500
FF | FF-489 | FF-489 | Sub-task | Sub-task |  | Fintech Fuel Chat Testing | Resolved! | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-487 | FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-489 | [5 empty] | 2026-03-31T12:26:37.262+0500 | 2026-04-08T16:58:32.926+0500
FF | FF-49 | FF-49 | Bug Subtask | Bug Subtask |  | Generate button is containing string (DEBUG :FALSE) and its not working for Daily Stock chart for the same time period as selected for Daily sales chart | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-49 | [5 empty] | 2025-10-08T15:46:56.565+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-490 | FF-490 | Sub-task | Sub-task |  | Fintech Fuel Chat Testing | Resolved! | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-487 | FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-490 | [5 empty] | 2026-03-31T14:44:32.332+0500 | 2026-04-22T14:22:10.893+0500
FF | FF-491 | FF-491 | Sub-task | Sub-task |  | Fintech Fuel Chat Testing | Resolved! | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 8 | 8 | Muhammad Imran Aslam | 8 |  | FF-487 | FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-487 | https://octopusdtlsupport.atlassian.net/browse/FF-491 | [5 empty] | 2026-03-31T16:18:17.653+0500 | 2026-04-30T15:52:17.118+0500
FF | FF-492 | FF-492 | Sub-task | Sub-task |  | Alson requirements gathering | Resolved! | 2026-03-27 | 2026-04-10 | 2026-03-27 | 2026-04-07 | 32 | 32 | Hassan Saeed Wattoo | 38 |  | FF-483 | FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-492 | [5 empty] | 2026-04-02T10:12:42.755+0500 | 2026-04-09T17:08:31.710+0500
FF | FF-493 | FF-493 | Sub-task | Sub-task |  | Schema design validation and rectification | Resolved! | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 16 | 16 | Ameer Hamza Khan | 16 |  | FF-483 | FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-493 | [5 empty] | 2026-04-02T12:54:48.827+0500 | 2026-04-02T12:57:08.635+0500
FF | FF-495 | FF-495 | Story | Story |  | Addressing technical support tickets | In-Progress | 2026-04-02 |  |  |  | 0 | 0 | Ameer Hamza Khan | 1 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-495 | [5 empty] | 2026-04-02T13:22:11.905+0500 | 2026-04-02T13:22:55.113+0500
FF | FF-496 | FF-496 | Sub-task | Sub-task |  | Renaming site name, marking site inactive and verifying reactivation | Resolved! | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 1 | 1 | Ameer Hamza Khan | 1 |  | FF-495 | FF-495 | https://octopusdtlsupport.atlassian.net/browse/FF-495 | https://octopusdtlsupport.atlassian.net/browse/FF-496 | [5 empty] | 2026-04-02T13:24:10.336+0500 | 2026-04-02T13:25:02.143+0500
FF | FF-497 | FF-497 | Sub-task | Sub-task |  | Updated Site Configuration for Alson Devices | Resolved! | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-10 | 40 | 40 | Muhammad Usman Javed | 48 |  | FF-298 | FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-497 | [5 empty] | 2026-04-02T16:21:08.796+0500 | 2026-04-16T10:31:09.512+0500
FF | FF-498 | FF-498 | Epic | Epic |  | Multi Language Support | On Hold | 2026-04-08 | 2026-05-06 |  |  | 120 | 120 | Sarmad Sabir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-498 | [5 empty] | 2026-04-08T11:43:28.194+0500 | 2026-04-16T11:08:43.638+0500
FF | FF-499 | FF-499 | Story | Story |  | Research | Resolved! | 2026-04-08 | 2026-04-10 |  |  | 32 | 32 | Sarmad Sabir | 32 |  | FF-498 | FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-499 | [5 empty] | 2026-04-08T11:49:01.352+0500 | 2026-04-14T17:21:39.496+0500
FF | FF-5 | FF-5 | Story | Story |  | SQA | Resolved! | 2025-09-14 | 2025-09-17 |  |  | 40 | 40 | kamran khalid | 101 |  | FF-1 | FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-5 | [5 empty] | 2025-10-06T14:07:33.611+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-50 | FF-50 | Bug Subtask | Bug Subtask |  | when i change the option from "Daily Sales Chart" to "Daily Stock Chart", then the system generates error Timeout expired | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-50 | [5 empty] | 2025-10-08T15:47:06.701+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-500 | FF-500 | Story | Story |  | Development | In-Progress | 2026-04-13 | 2026-04-22 |  |  | 64 | 64 | Sarmad Sabir | 32 |  | FF-498 | FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | [5 empty] | 2026-04-08T11:51:18.264+0500 | 2026-05-04T10:38:13.265+0500
FF | FF-501 | FF-501 | Sub-task | Sub-task |  | Research on Multi Language Support | Resolved! | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 16 | 16 | Sarmad Sabir | 16 |  | FF-499 | FF-499 | https://octopusdtlsupport.atlassian.net/browse/FF-499 | https://octopusdtlsupport.atlassian.net/browse/FF-501 | [5 empty] | 2026-04-08T11:53:42.833+0500 | 2026-04-14T17:20:40.583+0500
FF | FF-502 | FF-502 | Sub-task | Sub-task |  | Research on Angular i18n for LS | Resolved! | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8 | 8 | Sarmad Sabir | 8 |  | FF-499 | FF-499 | https://octopusdtlsupport.atlassian.net/browse/FF-499 | https://octopusdtlsupport.atlassian.net/browse/FF-502 | [5 empty] | 2026-04-08T11:54:23.239+0500 | 2026-04-14T17:21:10.155+0500
FF | FF-503 | FF-503 | Story | Story |  | Fintech-Regression-Bug-Fixing (2/23/26 - 2/27/26) | Resolved! | 2026-02-23 | 2026-02-27 |  |  | 16 | 16 | Muhammad Usman Javed | 8 |  | FF-373 | FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-503 | [5 empty] | 2026-04-08T12:04:22.579+0500 | 2026-04-08T12:12:17.527+0500
FF | FF-504 | FF-504 | Sub-task | Sub-task |  | QA Reported UI Bugs | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8 | 8 | Sarmad Sabir | 8 |  | FF-503 | FF-503 | https://octopusdtlsupport.atlassian.net/browse/FF-503 | https://octopusdtlsupport.atlassian.net/browse/FF-504 | [5 empty] | 2026-04-08T12:08:15.003+0500 | 2026-04-08T12:10:36.517+0500
FF | FF-505 | FF-505 | Story | Story |  | SQA | To Do | 2026-05-12 | 2026-05-18 |  |  | 80 | 80 | kamran khalid | 0 |  | FF-312 | FF-312 | https://octopusdtlsupport.atlassian.net/browse/FF-312 | https://octopusdtlsupport.atlassian.net/browse/FF-505 | [5 empty] | 2026-04-08T16:23:14.381+0500 | 2026-04-08T16:23:57.732+0500
FF | FF-506 | FF-506 | Story | Story |  | SQA | To Do |  |  |  |  | 24 | 24 | kamran khalid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-506 | [5 empty] | 2026-04-08T16:24:56.172+0500 | 2026-04-08T16:25:13.298+0500
FF | FF-51 | FF-51 | Bug Subtask | Bug Subtask |  | While reviewing the Daily Sales chart for the one-month period, the report shows a total loss of 17.9k liters. This value appears incorrect and suggests an issue with the calculation or data representation. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 6 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-51 | [5 empty] | 2025-10-08T15:49:36.004+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-510 | FF-510 | Story | Story |  | SQA | To Do | 2026-05-04 | 2026-05-06 |  |  | 24 | 24 | kamran khalid | 0 |  | FF-498 | FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-510 | [5 empty] | 2026-04-08T16:32:39.815+0500 | 2026-04-08T16:33:41.092+0500
FF | FF-511 | FF-511 | Sub-task | Sub-task |  | ETL Modification for Alson | In-Progress | 2026-04-10 | 2026-04-16 | 2026-04-13 | 2026-04-15 | 40 | 40 | Muhammad Usman Javed | 24 |  | FF-298 | FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-511 | [5 empty] | 2026-04-09T15:41:36.609+0500 | 2026-04-16T10:31:58.734+0500
FF | FF-512 | FF-512 | Epic | Epic |  | Audit trails (phase 2) - Module Interaction | To Do | 2026-06-04 | 2026-06-23 |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-512 | [5 empty] | 2026-04-09T15:44:05.401+0500 | 2026-04-09T16:20:28.193+0500
FF | FF-513 | FF-513 | Story | Story |  | Development | To Do | 2026-06-08 | 2026-06-17 |  |  | 120 | 120 | Muhammad Usman Javed | 0 |  | FF-512 | FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-513 | [5 empty] | 2026-04-09T15:49:18.080+0500 | 2026-04-09T18:36:55.236+0500
FF | FF-514 | FF-514 | Story | Story |  | SQA | To Do | 2026-06-18 | 2026-06-22 |  |  | 40 | 40 | kamran khalid | 0 |  | FF-512 | FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-514 | [5 empty] | 2026-04-09T15:49:25.794+0500 | 2026-04-09T18:37:17.337+0500
FF | FF-515 | FF-515 | Story | Story |  | Research | To Do | 2026-06-04 | 2026-06-05 |  |  | 40 | 40 | Muhammad Usman Javed | 0 |  | FF-512 | FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-515 | [5 empty] | 2026-04-09T15:50:04.328+0500 | 2026-04-09T18:37:42.471+0500
FF | FF-516 | FF-516 | Story | Story |  | Production Release | To Do | 2026-06-22 | 2026-06-23 |  |  | 16 | 16 | Muhammad Usman Javed | 0 |  | FF-512 | FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-512 | https://octopusdtlsupport.atlassian.net/browse/FF-516 | [5 empty] | 2026-04-09T15:54:28.211+0500 | 2026-04-09T18:38:07.148+0500
FF | FF-517 | FF-517 | Epic | Epic |  | Audit trails (phase 3) - Activity Log | To Do | 2026-06-22 | 2026-07-06 |  |  | 216 | 216 | Muhammad Usman Javed | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-517 | [5 empty] | 2026-04-09T15:56:30.343+0500 | 2026-04-09T16:17:04.452+0500
FF | FF-518 | FF-518 | Story | Story |  | Development | To Do | 2026-06-24 | 2026-06-30 |  |  | 120 | 120 | Muhammad Usman Javed | 0 |  | FF-517 | FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-518 | [5 empty] | 2026-04-09T15:56:32.043+0500 | 2026-04-09T18:38:35.741+0500
FF | FF-519 | FF-519 | Story | Story |  | SQA | To Do | 2026-07-01 | 2026-07-03 |  |  | 40 | 40 | kamran khalid | 0 |  | FF-517 | FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-519 | [5 empty] | 2026-04-09T15:56:34.834+0500 | 2026-04-09T18:38:54.937+0500
FF | FF-52 | FF-52 | Bug Subtask | Bug Subtask |  | kindly change the Arrow position downwards as its reflecting LOSS not Gain | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-52 | [5 empty] | 2025-10-08T15:52:09.121+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-520 | FF-520 | Story | Story |  | Research | To Do | 2026-06-22 | 2026-06-23 |  |  | 40 | 40 | Muhammad Usman Javed | 0 |  | FF-517 | FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-520 | [5 empty] | 2026-04-09T15:56:37.571+0500 | 2026-04-09T18:39:14.622+0500
FF | FF-521 | FF-521 | Story | Story |  | Production Release | To Do | 2026-07-03 | 2026-07-06 |  |  | 16 | 16 | Muhammad Usman Javed | 0 |  | FF-517 | FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-517 | https://octopusdtlsupport.atlassian.net/browse/FF-521 | [5 empty] | 2026-04-09T15:56:40.688+0500 | 2026-04-09T18:39:37.921+0500
FF | FF-523 | FF-523 | Story | Story |  | SQA | To Do | 2026-06-01 | 2026-06-03 |  |  | 40 | 40 | kamran khalid | 0 |  | FF-446 | FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-523 | [5 empty] | 2026-04-09T16:23:13.635+0500 | 2026-04-09T18:34:12.172+0500
FF | FF-524 | FF-524 | Story | Story |  | Production Release | To Do | 2026-06-03 | 2026-06-04 |  |  | 16 | 16 | Muhammad Usman Javed | 0 |  | FF-446 | FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-524 | [5 empty] | 2026-04-09T16:23:27.603+0500 | 2026-04-09T18:34:46.385+0500
FF | FF-526 | FF-526 | Story | Story |  | Research | To Do | 2026-05-18 | 2026-05-19 |  |  | 40 | 40 | Muhammad Usman Javed | 0 |  | FF-446 | FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-446 | https://octopusdtlsupport.atlassian.net/browse/FF-526 | [5 empty] | 2026-04-09T16:23:27.705+0500 | 2026-04-09T18:35:48.684+0500
FF | FF-527 | FF-527 | Story | Story |  | Development (Enhancement) | To Do |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 29 |  | FF-274 | FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-274 | https://octopusdtlsupport.atlassian.net/browse/FF-527 | [5 empty] | 2026-04-09T16:38:37.050+0500 | 2026-04-09T16:41:58.222+0500
FF | FF-528 | FF-528 | Sub-task | Sub-task |  | Sp modification to insert Alson data into current TankDelivery | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-483 | FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-483 | https://octopusdtlsupport.atlassian.net/browse/FF-528 | [5 empty] | 2026-04-09T17:01:55.331+0500 | 2026-04-09T17:01:55.545+0500
FF | FF-529 | FF-529 | Sub-task | Sub-task |  | Current SP Modification + New SP for Tank Deliveries Calculation | Resolved! | 2026-04-08 | 2026-04-13 | 2026-04-08 | 2026-04-09 | 32 | 32 | Hassan Saeed Wattoo | 16 |  | FF-298 | FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-529 | [5 empty] | 2026-04-09T17:09:04.243+0500 | 2026-04-20T11:18:12.447+0500
FF | FF-53 | FF-53 | Bug Subtask | Bug Subtask |  | Upon Checking the Deliveries chart From Time Period 1 may to 30th may 2025 for Site COCO-Liberty as compared to the Data with the same Filter Applied on SM 360 Web Application. The Data Mismatch | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-53 | [5 empty] | 2025-10-08T15:52:56.993+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-530 | FF-530 | Sub-task | Sub-task |  | Testing By waqar | Resolved! | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 16 | 16 | Waqar Rasheed | 16 |  | FF-456 | FF-456 | https://octopusdtlsupport.atlassian.net/browse/FF-456 | https://octopusdtlsupport.atlassian.net/browse/FF-530 | [5 empty] | 2026-04-13T14:29:52.729+0500 | 2026-04-14T16:44:49.036+0500
FF | FF-531 | FF-531 | Task | Task |  | Support for Ticket FIN-112 COCO LHR-1 (Aramco) | Resolved! |  |  | 2026-03-19 | 2026-03-20 | 16 | 16 | kamran khalid | 14 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-531 | [5 empty] | 2026-04-13T14:37:15.786+0500 | 2026-04-13T14:39:03.764+0500
FF | FF-532 | FF-532 | Task | Task |  | Support for Ticket FIN-116 COCO-GUJRANWALA 2 (ARAMCO) | Resolved! |  |  | 2026-03-27 | 2026-04-13 | 16 | 16 | kamran khalid | 11 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-532 | [5 empty] | 2026-04-13T14:41:00.716+0500 | 2026-04-13T15:00:11.694+0500
FF | FF-533 | FF-533 | Task | Task |  | Support for Fin-116 COCO ISB 2 (ARAMCO) | In-Progress |  |  | 2026-04-13 | 2026-04-13 | 16 | 16 | kamran khalid | 6 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-533 | [5 empty] | 2026-04-13T17:18:26.554+0500 | 2026-04-13T17:19:09.594+0500
FF | FF-534 | FF-534 | Task | Task |  | Support for Fin-116 COCO ISB 2 (ARAMCO) | Resolved! | 2026-04-13 |  | 2026-04-13 | 2026-04-13 | 3 | 3 | Hassan Saeed Wattoo | 3 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-534 | [5 empty] | 2026-04-14T09:25:25.764+0500 | 2026-04-14T09:31:38.630+0500
FF | FF-535 | FF-535 | Sub-task | Sub-task |  | Dashboard POC Implementation | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8 | 8 | Sarmad Sabir | 8 |  | FF-499 | FF-499 | https://octopusdtlsupport.atlassian.net/browse/FF-499 | https://octopusdtlsupport.atlassian.net/browse/FF-535 | [5 empty] | 2026-04-14T17:21:59.591+0500 | 2026-04-14T17:22:35.436+0500
FF | FF-536 | FF-536 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-498 | FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-536 | [5 empty] | 2026-04-15T10:26:12.717+0500 | 2026-04-16T11:09:58.150+0500
FF | FF-537 | FF-537 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-498 | FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-537 | [5 empty] | 2026-04-15T10:30:06.302+0500 | 2026-04-16T11:11:13.976+0500
FF | FF-538 | FF-538 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-498 | FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-498 | https://octopusdtlsupport.atlassian.net/browse/FF-538 | [5 empty] | 2026-04-15T10:30:14.379+0500 | 2026-04-16T11:11:33.385+0500
FF | FF-539 | FF-539 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-297 | FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-539 | [5 empty] | 2026-04-15T10:44:53.780+0500 | 2026-04-15T10:49:30.817+0500
FF | FF-54 | FF-54 | Bug Subtask | Bug Subtask |  | Daily Stock Level Mismatch as of 1st May 2025 as compared to SM 360 for site COCO Liberty | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 2.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-54 | [5 empty] | 2025-10-08T15:54:48.065+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-540 | FF-540 | Story | Story |  | SQA Handover | To Do | 2026-04-17 | 2026-04-17 |  |  | 8 | 8 | kamran khalid | 0 |  | FF-297 | FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-297 | https://octopusdtlsupport.atlassian.net/browse/FF-540 | [5 empty] | 2026-04-15T10:45:35.239+0500 | 2026-04-15T10:48:50.768+0500
FF | FF-541 | FF-541 | Epic | Epic |  | User & role management | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-541 | [5 empty] | 2026-04-15T11:35:54.538+0500 | 2026-04-15T11:35:54.685+0500
FF | FF-542 | FF-542 | Epic | Epic |  | Calculate Tank delivery (Alsons device) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-542 | [5 empty] | 2026-04-15T11:36:46.497+0500 | 2026-04-21T15:48:42.114+0500
FF | FF-543 | FF-543 | Sub-task | Sub-task |  | Email and db structure modification | In-Progress | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-15 | 40 | 40 | Hassan Saeed Wattoo | 29 |  | FF-527 | FF-527 | https://octopusdtlsupport.atlassian.net/browse/FF-527 | https://octopusdtlsupport.atlassian.net/browse/FF-543 | [5 empty] | 2026-04-20T11:19:00.758+0500 | 2026-04-20T11:20:55.338+0500
FF | FF-544 | FF-544 | Sub-task | Sub-task |  | Testing the SP and integrating the logic into the current tank delivery table. | In-Progress | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-04-20 | 24 | 24 | Hassan Saeed Wattoo | 24 |  | FF-298 | FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-544 | [5 empty] | 2026-04-20T11:24:07.859+0500 | 2026-04-22T16:08:11.420+0500
FF | FF-545 | FF-545 | Sub-task | Sub-task |  | Pointer table changes and Integration with web team | In-Progress | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-22 | 16 | 16 | Hassan Malik | 16 |  | FF-298 | FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-298 | https://octopusdtlsupport.atlassian.net/browse/FF-545 | [5 empty] | 2026-04-22T16:08:40.863+0500 | 2026-04-22T16:09:16.873+0500
FF | FF-546 | FF-546 | Sub-task | Sub-task |  | Add Rate Limiting for ReadAPI | Resolved! | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 40 | 40 | Muhammad Usman Javed | 12 |  | FF-275 | FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-546 | [5 empty] | 2026-04-23T15:42:57.040+0500 | 2026-04-23T15:47:18.291+0500
FF | FF-547 | FF-547 | Sub-task | Sub-task |  | Add API Logs for ReadAPI | Resolved! | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 40 | 40 | Muhammad Usman Javed | 12 |  | FF-275 | FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-547 | [5 empty] | 2026-04-23T15:43:18.554+0500 | 2026-04-23T16:33:00.396+0500
FF | FF-548 | FF-548 | Sub-task | Sub-task |  | Add a new API User type | In-Progress |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | FF-275 | FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-275 | https://octopusdtlsupport.atlassian.net/browse/FF-548 | [5 empty] | 2026-04-23T15:43:36.635+0500 | 2026-04-23T15:48:05.155+0500
FF | FF-549 | FF-549 | Task | Task |  | Support for site validations fintech | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 4 | 4 | Waqar Rasheed | 4 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-549 | [5 empty] | 2026-04-23T16:31:03.630+0500 | 2026-04-24T11:49:07.022+0500
FF | FF-55 | FF-55 | Sub-task | Sub-task |  | Loader is missing on the Loss Gain Charts | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 1.08 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-55 | [5 empty] | 2025-10-08T15:57:35.953+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-550 | FF-550 | Task | Task |  | Support for Site Validations(COCO UET, COCO MULTAN and COCO Peshawar) | Resolved! |  |  | 2026-04-23 | 2026-04-23 | 6 | 6 | kamran khalid | 6 |  | FF-343 | FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-343 | https://octopusdtlsupport.atlassian.net/browse/FF-550 | [5 empty] | 2026-04-23T17:07:39.058+0500 | 2026-04-23T17:08:18.756+0500
FF | FF-551 | FF-551 | Sub-task | Sub-task |  | Integrating i18n + 8 Languages Support | Resolved! | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 8 | 8 | Sarmad Sabir | 8 |  | FF-500 | FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-551 | [5 empty] | 2026-05-04T10:32:02.407+0500 | 2026-05-04T10:38:21.219+0500
FF | FF-552 | FF-552 | Sub-task | Sub-task |  | Dashboard Language Change | Resolved! | 2026-05-28 | 2026-05-28 | 2026-04-28 | 2026-04-28 | 2 | 2 | Sarmad Sabir | 2 |  | FF-500 | FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-552 | [5 empty] | 2026-05-04T10:32:22.174+0500 | 2026-05-04T10:39:21.682+0500
FF | FF-553 | FF-553 | Sub-task | Sub-task |  | Alarms/Daily Deliveries/ Recon Page | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 6 | 6 | Sarmad Sabir | 6 |  | FF-500 | FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-553 | [5 empty] | 2026-05-04T10:33:51.906+0500 | 2026-05-04T10:40:04.843+0500
FF | FF-554 | FF-554 | Sub-task | Sub-task |  | Nozzle/Stock/ Low Stock Page | Resolved! | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 6 | 6 | Sarmad Sabir | 6 |  | FF-500 | FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-554 | [5 empty] | 2026-05-04T10:35:32.904+0500 | 2026-05-04T10:44:54.563+0500
FF | FF-555 | FF-555 | Sub-task | Sub-task |  | Transactions/ Sales Target/Target Setup Page | Resolved! | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-30 | 16 | 16 | Sarmad Sabir | 10 |  | FF-500 | FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-555 | [5 empty] | 2026-05-04T10:36:00.448+0500 | 2026-05-04T10:47:31.040+0500
FF | FF-556 | FF-556 | Sub-task | Sub-task |  | Submit Data/ Daily Sales/ Loss Gain Charts Page | To Do |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-500 | FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-556 | [5 empty] | 2026-05-04T10:36:23.152+0500 | 2026-05-04T10:36:54.383+0500
FF | FF-557 | FF-557 | Sub-task | Sub-task |  | My Profile/ Site Diag/ Notifications Group Page | To Do |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | FF-500 | FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-500 | https://octopusdtlsupport.atlassian.net/browse/FF-557 | [5 empty] | 2026-05-04T10:36:38.125+0500 | 2026-05-04T10:36:55.602+0500
FF | FF-56 | FF-56 | Bug Subtask | Bug Subtask |  | AS compared to SM 360 when user applies the Daily Sales filter the Fintech App showing values on the Loss Gain Chart in term of Money and on the other hand the SM 360 shows it in terms of Liters | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-56 | [5 empty] | 2025-10-08T15:58:31.214+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-569 | FF-569 | Sub-task | Sub-task |  | Testing By Kamran April | Resolved! | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | 16 | 16 | kamran khalid | 16 |  | FF-456 | FF-456 | https://octopusdtlsupport.atlassian.net/browse/FF-456 | https://octopusdtlsupport.atlassian.net/browse/FF-569 | [5 empty] | 2026-05-12T15:36:57.182+0500 | 2026-05-12T15:37:57.335+0500
FF | FF-57 | FF-57 | Sub-task | Sub-task |  | Kindly update the Date Time Filter as compared to SM 360 as currently it does not help the users | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-57 | [5 empty] | 2025-10-08T16:00:32.504+0500 | 2025-10-08T16:01:45.629+0500
FF | FF-570 | FF-570 | Task | Task |  | Regression Staging (12-05-2026 --20-05-2026) | To Do | 2026-05-13 | 2026-05-20 |  |  | 40 | 40 | kamran khalid | 0 |  | FF-373 | FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-373 | https://octopusdtlsupport.atlassian.net/browse/FF-570 | [5 empty] | 2026-05-12T17:31:32.507+0500 | 2026-05-12T17:37:25.469+0500
FF | FF-571 | FF-571 | Sub-task | Sub-task |  | Testing By kamran | To Do | 2026-05-13 | 2026-05-20 |  |  | 40 | 40 | kamran khalid | 0 |  | FF-570 | FF-570 | https://octopusdtlsupport.atlassian.net/browse/FF-570 | https://octopusdtlsupport.atlassian.net/browse/FF-571 | [5 empty] | 2026-05-12T17:32:16.942+0500 | 2026-05-12T17:37:12.658+0500
FF | FF-58 | FF-58 | Bug Subtask | Bug Subtask |  | The Tank filter should be dependent on Grade filter it should show only the tanks of the product selected. | Failed Testing |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-58 | [5 empty] | 2025-10-08T16:03:24.815+0500 | 2025-10-15T17:08:28.094+0500
FF | FF-59 | FF-59 | Bug Subtask | Bug Subtask |  | Dashboard data for Revenue does not match with the Production data for Same time period applied on both environments | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 4 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-59 | [5 empty] | 2025-10-08T16:07:50.254+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-6 | FF-6 | Story | Story |  | Production Release | Resolved! | 2025-09-18 | 2025-09-18 |  |  | 8 | 8 | Ameer Hamza Khan | 8 |  | FF-1 | FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-6 | [5 empty] | 2025-10-06T14:07:38.294+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-60 | FF-60 | Bug Subtask | Bug Subtask |  | In Recon Report every column should not be displayed in floating please verify it from Production as retail team has specified some column to be round off | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.33 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-60 | [5 empty] | 2025-10-08T16:15:31.750+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-61 | FF-61 | Bug Subtask | Bug Subtask |  | There is no such thing as Low Stock Alert Management as we do not manage any alerts regarding low stocks and secondly the columns mismatch as Capacity is missing Date column is missing threshold missing. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-61 | [5 empty] | 2025-10-08T16:23:08.738+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-62 | FF-62 | Bug Subtask | Bug Subtask |  | Sales data is not getting loaded against tank levels in Sales Target Module. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 3 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-62 | [5 empty] | 2025-10-08T16:25:08.683+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-63 | FF-63 | Bug Subtask | Bug Subtask |  | I have Applied Filter for Weekly Sales but the error is showing for Daily Sales | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-63 | [5 empty] | 2025-10-08T16:26:19.727+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-64 | FF-64 | Bug Subtask | Bug Subtask |  | I have set the Target for 10 days up to "500000" liters but the total target showing "5,150,000" Liters as in SM 360 the target is the total volume for the selected period not for a single day | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-64 | [5 empty] | 2025-10-08T16:27:22.861+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-65 | FF-65 | Bug Subtask | Bug Subtask |  | I Have set Target for Aramco Site but when i changed the filter to Total site the same targeted data is shown for Total as i have not set any targets for Total | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-65 | [5 empty] | 2025-10-08T16:28:20.324+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-66 | FF-66 | Bug Subtask | Bug Subtask |  | Success messages are not properly handled, please look into it | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.33 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-66 | [5 empty] | 2025-10-08T16:29:13.050+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-67 | FF-67 | Bug Subtask | Bug Subtask |  | Filter is not available for Recon Page and Nozzle Page | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.83 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-67 | [5 empty] | 2025-10-08T16:30:15.903+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-68 | FF-68 | Bug Subtask | Bug Subtask |  | Username Field on login page accepts spaces which is in correct, please restrict it as its restricted while creating user. | Failed Testing |  |  |  |  | 0 | 0 | kamran khalid | 0.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-68 | [5 empty] | 2025-10-08T16:32:09.862+0500 | 2025-10-15T17:15:28.591+0500
FF | FF-69 | FF-69 | Bug Subtask | Bug Subtask |  | Reset Password Validations are missing on Password and Confirm Password Fields, kindly apply validations | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-69 | [5 empty] | 2025-10-08T16:33:30.534+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-7 | FF-7 | Epic | Epic |  | Fintech Fuel : Version 2 | To Do |  |  |  |  | 0 | 0 | awais akhter | 300 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-7 | [5 empty] | 2025-10-03T19:43:22.055+0500 | 2025-10-08T12:28:12.524+0500
FF | FF-70 | FF-70 | Bug Subtask | Bug Subtask |  | new Sites for Total Parco got configured but some of the file of the sites landed in the exceptional folder, please look into it | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-70 | [5 empty] | 2025-10-08T16:34:36.702+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-71 | FF-71 | Sub-task | Sub-task |  | Increase the font size of the filter heading and dropdown text to ensure consistency with the other elements on the dashboard.” | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 0.67 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-71 | [5 empty] | 2025-10-08T16:35:51.964+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-72 | FF-72 | Bug Subtask | Bug Subtask |  | Never saw this column in Recon Report named "Variances" containing "Nan" values, please remove this and look into it why this appear | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-72 | [5 empty] | 2025-10-08T16:37:18.357+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-73 | FF-73 | Bug Subtask | Bug Subtask |  | Variance % and Cumulative Variances % column does not match with the Columns data for recon report with Production | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.67 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-73 | [5 empty] | 2025-10-08T16:42:40.671+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-74 | FF-74 | Bug Subtask | Bug Subtask |  | Spelling Mistake, please update cancel button spellings on the date Time Filter. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.42 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-74 | [5 empty] | 2025-10-08T16:45:19.963+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-75 | FF-75 | Bug Subtask | Bug Subtask |  | user is able to select the future Dates from the calendar in the filter, kindly restrict selecting future dates. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-75 | [5 empty] | 2025-10-08T16:45:58.709+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-76 | FF-76 | Bug Subtask | Bug Subtask |  | Export to excel is downloading empty file for Nozzle usage | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.83 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-76 | [5 empty] | 2025-10-08T16:46:56.955+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-77 | FF-77 | Bug Subtask | Bug Subtask |  | There are duplicate tanks named with "Site ID" With all the products in the stock level page | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.17 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-77 | [5 empty] | 2025-10-08T16:48:11.093+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-78 | FF-78 | Bug Subtask | Bug Subtask |  | When user Clicks on the Deliveries page the page loads with a filter error "Please select both From and to date/time | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1.33 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-78 | [5 empty] | 2025-10-08T16:49:58.521+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-79 | FF-79 | Sub-task | Sub-task |  | Kindly remove the Debug Info section from deliveries page. | Resolved! |  |  |  |  | 0 | 0 | kamran khalid | 0.5 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-79 | [5 empty] | 2025-10-08T16:51:15.092+0500 | 2026-02-11T12:32:17.045+0500
FF | FF-8 | FF-8 | Story | Story |  | Loss/Gain Charts | Resolved! | 2025-09-19 | 2025-09-24 |  |  | 24 | 24 | kamran khalid | 45 |  | FF-7 | FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-8 | [5 empty] | 2025-10-03T19:43:32.802+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-80 | FF-80 | Bug Subtask | Bug Subtask |  | kindly remove the floating datatype conversion from tanks column in the deliveries page. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 0.67 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-80 | [5 empty] | 2025-10-08T16:53:05.134+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-81 | FF-81 | Bug Subtask | Bug Subtask |  | Product names does not match with the Total Parco "gardenia filling station" Products in Low Stock Page. | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 1 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-81 | [5 empty] | 2025-10-08T16:54:15.228+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-82 | FF-82 | Bug Subtask | Bug Subtask |  | The Low Stock page is not displaying accurate predictions under the “Product Wise” filter. Please review this issue, and also update the label from “Grade View” to “Product View”, along with updating the product names accordingly. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-82 | [5 empty] | 2025-10-08T16:58:40.945+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-83 | FF-83 | Bug Subtask | Bug Subtask |  | Bug: Alarms for the Aramco site “COCO-Liberty” are not being displayed. Muhammad Usman Javed has already processed the Aramco site data on the Staging ETL. | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 2 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-83 | [5 empty] | 2025-10-08T16:59:53.733+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-84 | FF-84 | Bug Subtask | Bug Subtask |  | Kindly finalize which filter will be applicable on the Sales Target page — the first or the second — as discussed. One of the filters was supposed to be removed, but currently both are still visible. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-84 | [5 empty] | 2025-10-08T17:03:14.563+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-85 | FF-85 | Bug Subtask | Bug Subtask |  | The sales showing in the graph for "SALES and TARGET" GRAPH for the day "30 SEPT" is not matching with the sales data on the production | Resolved |  |  |  |  | 0 | 0 | kamran khalid | 8 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-85 | [5 empty] | 2025-10-08T17:12:55.331+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-86 | FF-86 | Bug Subtask | Bug Subtask |  | Day End Sale Summary and Recon again not working as new filter is added previously it was working | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-86 | [5 empty] | 2025-10-08T17:14:03.202+0500 | 2026-02-11T12:32:12.818+0500
FF | FF-87 | FF-87 | Bug Subtask | Bug Subtask |  | Tank Filter is not working for Loss Gain Charts as its showing total sum of deliveries of a single product | Resolved | 2025-10-16 | 2025-10-16 |  |  | 8 | 8 | kamran khalid | 2 |  | FF-13 | FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-13 | https://octopusdtlsupport.atlassian.net/browse/FF-87 | [5 empty] | 2025-10-08T17:15:24.725+0500 | 2026-02-11T12:32:07.614+0500
FF | FF-88 | FF-88 | Epic | Epic |  | ZDT on Fintech | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/FF-88 | [5 empty] | 2025-10-06T14:16:14.078+0500 | 2025-10-09T11:57:56.906+0500
FF | FF-89 | FF-89 | Story | Story |  | Research/URS | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-88 | FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-89 | [5 empty] | 2025-10-06T14:16:28.337+0500 | 2025-10-09T11:57:57.569+0500
FF | FF-9 | FF-9 | Story | Story |  | Low Stock Report | Resolved! | 2025-09-28 | 2025-10-05 |  |  | 8 | 8 | Ameer Hamza Khan | 42 |  | FF-7 | FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-7 | https://octopusdtlsupport.atlassian.net/browse/FF-9 | [5 empty] | 2025-10-03T19:43:44.472+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-90 | FF-90 | Story | Story |  | Research/DDS | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-88 | FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-90 | [5 empty] | 2025-10-06T14:16:29.016+0500 | 2025-10-09T11:57:58.966+0500
FF | FF-91 | FF-91 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-88 | FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-91 | [5 empty] | 2025-10-06T14:16:30.693+0500 | 2025-10-09T11:57:59.513+0500
FF | FF-92 | FF-92 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | kamran khalid | 0 |  | FF-88 | FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-92 | [5 empty] | 2025-10-06T14:16:32.469+0500 | 2026-02-13T13:40:56.089+0500
FF | FF-93 | FF-93 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | FF-88 | FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-93 | [5 empty] | 2025-10-06T14:16:34.750+0500 | 2025-10-09T11:58:00.458+0500
FF | FF-94 | FF-94 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | FF-88 | FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-88 | https://octopusdtlsupport.atlassian.net/browse/FF-94 | [5 empty] | 2025-10-06T14:16:39.686+0500 | 2025-10-09T11:58:00.919+0500
FF | FF-95 | FF-95 | Story | Story |  | User Manual / Guide | Resolved! | 2025-09-14 | 2025-09-17 |  |  | 40 | 40 | Hassan Malik | 4 |  | FF-1 | FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-1 | https://octopusdtlsupport.atlassian.net/browse/FF-95 | [5 empty] | 2025-10-09T15:33:17.646+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-96 | FF-96 | Sub-task | Sub-task |  | Features and Functionalities - Word/PDF Doc | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 4 |  | FF-95 | FF-95 | https://octopusdtlsupport.atlassian.net/browse/FF-95 | https://octopusdtlsupport.atlassian.net/browse/FF-96 | [5 empty] | 2025-10-09T15:34:20.275+0500 | 2025-10-09T15:34:47.062+0500
FF | FF-97 | FF-97 | Story | Story |  | Fuel Chat | Resolved! | 2025-10-23 | 2025-10-27 |  |  | 224 | 224 | Muhammad Ahmad Saleem | 508 |  | FF-16 | FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-16 | https://octopusdtlsupport.atlassian.net/browse/FF-97 | [5 empty] | 2025-10-10T15:38:56.392+0500 | 2026-02-11T12:32:19.345+0500
FF | FF-98 | FF-98 | Sub-task | Sub-task |  | FuelChat - Development( Frontend + Backend) | To Do |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 43 |  | FF-97 | FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-98 | [5 empty] | 2025-10-10T15:49:06.865+0500 | 2025-10-22T17:00:11.997+0500
FF | FF-99 | FF-99 | Sub-task | Sub-task |  | FuelChat - Visualization | To Do |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 137 |  | FF-97 | FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-97 | https://octopusdtlsupport.atlassian.net/browse/FF-99 | [5 empty] | 2025-10-13T17:37:10.153+0500 | 2025-12-09T10:51:50.615+0500
MN | MN-1 | MN-1 | Epic | Epic |  | Omni Chat Onboarding | Resolved! | 2025-12-17 | 2026-02-27 |  |  | 360 | 360 | Taimur Zahid | 104 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-1 | [5 empty] | 2025-12-29T17:31:31.586+0500 | 2026-03-17T11:50:53.866+0500
MN | MN-10 | MN-10 | Sub-task | Sub-task |  | Keeps loading if you click integrations and no option to stop | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-10 | [5 empty] | 2026-01-27T16:03:32.405+0500 | 2026-02-12T16:15:43.470+0500
MN | MN-100 | MN-100 | Story | Story |  | SQA | Resolved! | 2026-03-02 | 2026-04-10 |  |  | 480 | 480 | Muhammad Abbas | 16 |  | MN-94 | MN-94 | https://octopusdtlsupport.atlassian.net/browse/MN-94 | https://octopusdtlsupport.atlassian.net/browse/MN-100 | [5 empty] | 2026-02-25T12:29:32.208+0500 | 2026-04-14T17:03:32.701+0500
MN | MN-104 | MN-104 | Sub-task | Sub-task |  | LoginPage | Resolved! | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 16 | 16 | Muhammad Abbas | 16 |  | MN-100 | MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-104 | [5 empty] | 2026-02-25T13:04:37.879+0500 | 2026-02-26T16:00:36.685+0500
MN | MN-106 | MN-106 | Bug Subtask | Bug Subtask |  | Login with Microsoft is Not Working | Request received |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | MN-100 | MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-106 | [5 empty] | 2026-02-26T11:30:24.450+0500 | 2026-02-26T12:45:25.141+0500
MN | MN-107 | MN-107 | Bug Subtask | Bug Subtask |  | User Management Module is Not Working | Request received |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | MN-100 | MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-107 | [5 empty] | 2026-02-26T11:34:01.333+0500 | 2026-02-26T12:45:12.096+0500
MN | MN-108 | MN-108 | Bug Subtask | Bug Subtask |  | Forgot Password Module is Failing | Request received |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | MN-55 | MN-55 | https://octopusdtlsupport.atlassian.net/browse/MN-55 | https://octopusdtlsupport.atlassian.net/browse/MN-108 | [5 empty] | 2026-02-26T11:37:23.229+0500 | 2026-02-26T12:45:43.904+0500
MN | MN-109 | MN-109 | Sub-task | Sub-task |  | 2FA is Not Implemented for All Users in Omni Chat | To Do |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | MN-100 | MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-109 | [5 empty] | 2026-02-26T11:56:57.679+0500 | 2026-02-26T12:45:55.354+0500
MN | MN-11 | MN-11 | Sub-task | Sub-task |  | Explanations button not working in chat page | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1 | 1 | Aiza Hamid | 1 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-11 | [5 empty] | 2026-01-27T16:03:55.374+0500 | 2026-02-25T10:14:55.874+0500
MN | MN-110 | MN-110 | Story | Story |  | Understanding core OmniChat concepts | To Do | 2026-02-11 | 2026-02-13 |  |  | 24 | 24 | Hassan Malik | 24 |  | MN-1 | MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-110 | [5 empty] | 2026-02-26T11:58:25.557+0500 | 2026-03-10T16:33:45.594+0500
MN | MN-111 | MN-111 | Sub-task | Sub-task |  | Please change the Settings icon to a User Profile button and label it "User Profile. | To Do |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | MN-100 | MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-100 | https://octopusdtlsupport.atlassian.net/browse/MN-111 | [5 empty] | 2026-02-26T12:03:07.639+0500 | 2026-02-26T12:44:59.249+0500
MN | MN-112 | MN-112 | Sub-task | Sub-task |  | MCP server architecture | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Hamza Ali | 8 |  | MN-110 | MN-110 | https://octopusdtlsupport.atlassian.net/browse/MN-110 | https://octopusdtlsupport.atlassian.net/browse/MN-112 | [5 empty] | 2026-02-26T12:41:13.171+0500 | 2026-03-11T12:09:18.027+0500
MN | MN-113 | MN-113 | Sub-task | Sub-task |  | Import mechanisms. | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Hamza Ali | 8 |  | MN-110 | MN-110 | https://octopusdtlsupport.atlassian.net/browse/MN-110 | https://octopusdtlsupport.atlassian.net/browse/MN-113 | [5 empty] | 2026-02-26T12:41:29.308+0500 | 2026-03-11T12:09:07.592+0500
MN | MN-114 | MN-114 | Sub-task | Sub-task |  | Direct connection model | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Hamza Ali | 8 |  | MN-110 | MN-110 | https://octopusdtlsupport.atlassian.net/browse/MN-110 | https://octopusdtlsupport.atlassian.net/browse/MN-114 | [5 empty] | 2026-02-26T12:41:50.761+0500 | 2026-03-11T12:09:02.431+0500
MN | MN-116 | MN-116 | Epic | Epic |  | User Access Setting | To Do |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-116 | [5 empty] | 2026-03-03T11:48:31.865+0500 | 2026-03-03T11:50:17.475+0500
MN | MN-117 | MN-117 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 8 | 8 | Muhammad Abbas | 8 |  | MN-86 | MN-86 | https://octopusdtlsupport.atlassian.net/browse/MN-86 | https://octopusdtlsupport.atlassian.net/browse/MN-117 | [5 empty] | 2026-03-03T16:01:53.460+0500 | 2026-03-03T16:04:35.755+0500
MN | MN-118 | MN-118 | Sub-task | Sub-task |  | Text adjustment in chat input (Known Bug) | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8 | 8 | Aiza Hamid | 6.5 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-118 | [5 empty] | 2026-03-04T11:20:59.587+0500 | 2026-03-26T15:01:04.209+0500
MN | MN-119 | MN-119 | Sub-task | Sub-task |  | Keeps loading if you click integrations and no option to stop (Known Bug) | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 4 | 4 | Aiza Hamid | 2.5 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-119 | [5 empty] | 2026-03-04T11:21:19.151+0500 | 2026-03-26T15:02:23.921+0500
MN | MN-12 | MN-12 | Sub-task | Sub-task |  | Cant connect tables with spaces in Direct Connection | Resolved! | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-12 | [5 empty] | 2026-01-27T16:04:03.371+0500 | 2026-02-12T16:15:44.534+0500
MN | MN-120 | MN-120 | Sub-task | Sub-task |  | Cant connect tables with spaces in Direct Connection (Known Bug) | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 4 | 4 | Aiza Hamid | 4 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-120 | [5 empty] | 2026-03-04T11:22:07.802+0500 | 2026-03-04T11:24:58.280+0500
MN | MN-121 | MN-121 | Story | Story |  | Collaboration with Implementation Team | Resolved! | 2026-03-05 | 2026-03-05 |  |  | 8 | 8 | Taimur Zahid | 5 |  | MN-78 | MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-121 | [5 empty] | 2026-03-05T12:33:03.688+0500 | 2026-03-05T12:38:10.882+0500
MN | MN-122 | MN-122 | Sub-task | Sub-task |  | Meeting - March 5, 2026 | Resolved! |  |  | 2026-03-05 | 2026-03-05 | 2 | 2 | Taimur Zahid | 2 |  | MN-121 | MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-122 | [5 empty] | 2026-03-05T12:33:36.587+0500 | 2026-03-05T12:35:17.843+0500
MN | MN-123 | MN-123 | Sub-task | Sub-task |  | Meeting - March 5, 2026 | In-Progress | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2 | 2 | Aiza Hamid | 2 |  | MN-121 | MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-123 | [5 empty] | 2026-03-05T12:33:38.138+0500 | 2026-03-11T10:11:12.814+0500
MN | MN-124 | MN-124 | Sub-task | Sub-task |  | Meeting - March 5, 2026 | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | MN-121 | MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-124 | [5 empty] | 2026-03-05T12:33:38.672+0500 | 2026-03-05T12:34:06.591+0500
MN | MN-125 | MN-125 | Sub-task | Sub-task |  | Meeting - March 5, 2026 | To Do |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | MN-121 | MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-125 | [5 empty] | 2026-03-05T12:33:39.623+0500 | 2026-03-05T12:34:10.532+0500
MN | MN-126 | MN-126 | Sub-task | Sub-task |  | Meeting - March 5, 2026 | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 1 | 1 | Muhammad Abbas | 1 |  | MN-121 | MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-121 | https://octopusdtlsupport.atlassian.net/browse/MN-126 | [5 empty] | 2026-03-05T12:33:40.279+0500 | 2026-03-05T13:32:58.374+0500
MN | MN-127 | MN-127 | Sub-task | Sub-task |  | Staging Release | Resolved! |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | MN-95 | MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-127 | [5 empty] | 2026-03-10T16:12:53.366+0500 | 2026-03-10T16:13:13.672+0500
MN | MN-128 | MN-128 | Sub-task | Sub-task |  | Delete chats | Resolved! | 2026-02-16 | 2026-02-17 | 2026-02-16 | 2026-02-17 | 16 | 16 | Hamza Ali | 16 |  | MN-3 | MN-3 | https://octopusdtlsupport.atlassian.net/browse/MN-3 | https://octopusdtlsupport.atlassian.net/browse/MN-128 | [5 empty] | 2026-03-10T16:15:24.251+0500 | 2026-03-11T12:09:40.051+0500
MN | MN-129 | MN-129 | Sub-task | Sub-task |  | User testing | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Hamza Ali | 8 |  | MN-3 | MN-3 | https://octopusdtlsupport.atlassian.net/browse/MN-3 | https://octopusdtlsupport.atlassian.net/browse/MN-129 | [5 empty] | 2026-03-10T16:29:50.586+0500 | 2026-03-11T12:08:57.790+0500
MN | MN-13 | MN-13 | Sub-task | Sub-task |  | Background Image changed | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Aiza Hamid | 7 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-13 | [5 empty] | 2026-01-27T16:04:16.996+0500 | 2026-02-24T10:29:13.448+0500
MN | MN-130 | MN-130 | Sub-task | Sub-task |  | Missing Hierarchy Structure in UM | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | Hamza Ali | 8 |  | MN-5 | MN-5 | https://octopusdtlsupport.atlassian.net/browse/MN-5 | https://octopusdtlsupport.atlassian.net/browse/MN-130 | [5 empty] | 2026-03-10T16:45:00.454+0500 | 2026-03-11T12:09:32.624+0500
MN | MN-131 | MN-131 | Sub-task | Sub-task |  | Explanation button not working (Known bug) | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8 | 8 | Aiza Hamid | 6.5 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-131 | [5 empty] | 2026-03-11T10:05:58.097+0500 | 2026-03-26T15:02:33.232+0500
MN | MN-133 | MN-133 | Sub-task | Sub-task |  | Staging Release Unit Testing | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 6 | 6 | Aiza Hamid | 4.5 |  | MN-95 | MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-133 | [5 empty] | 2026-03-11T10:12:00.709+0500 | 2026-03-26T15:03:03.027+0500
MN | MN-137 | MN-137 | Epic | Epic |  | Chat Deletion Support | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-137 | [5 empty] | 2026-03-17T11:23:13.333+0500 | 2026-04-01T10:14:31.776+0500
MN | MN-138 | MN-138 | Sub-task | Sub-task |  | Yousaf's Onboarding | Resolved! | 2026-02-16 | 2026-02-27 | 2026-02-17 | 2026-02-20 | 64 | 64 | Syed Yousaf Qadri | 32 |  | MN-2 | MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-138 | [5 empty] | 2026-03-17T11:24:41.264+0500 | 2026-03-17T15:22:47.422+0500
MN | MN-139 | MN-139 | Epic | Epic |  | Missing Hierarchy Structure in UM | To Do |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-139 | [5 empty] | 2026-03-17T11:39:00.452+0500 | 2026-04-09T10:25:46.341+0500
MN | MN-14 | MN-14 | Sub-task | Sub-task |  | Chat and icons changed | Resolved! | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-14 | [5 empty] | 2026-01-27T16:04:45.940+0500 | 2026-02-12T16:15:45.440+0500
MN | MN-140 | MN-140 | Epic | Epic |  | Dataset Import Restrictions | In-Progress | 2026-03-30 | 2026-04-08 |  |  | 0 | 0 | Aiza Hamid | 32 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-140 | [5 empty] | 2026-03-30T16:35:15.283+0500 | 2026-04-02T10:53:53.162+0500
MN | MN-141 | MN-141 | Story | Story |  | Development | In-Progress | 2026-03-30 | 2026-04-08 | 2026-03-30 | 2026-04-02 | 72 | 72 | Aiza Hamid | 32 |  | MN-140 | MN-140 | https://octopusdtlsupport.atlassian.net/browse/MN-140 | https://octopusdtlsupport.atlassian.net/browse/MN-141 | [5 empty] | 2026-03-30T16:44:51.977+0500 | 2026-04-15T10:25:53.493+0500
MN | MN-142 | MN-142 | Epic | Epic |  | Data Transformations failure | Resolved! | 2026-03-10 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 56 | 56 | Aiza Hamid | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-142 | [5 empty] | 2026-04-02T10:55:11.485+0500 | 2026-04-06T10:43:20.660+0500
MN | MN-144 | MN-144 | Story | Story |  | Dev | Resolved! | 2026-03-10 | 2026-03-27 |  |  | 112 | 112 | Aiza Hamid | 53.5 |  | MN-142 | MN-142 | https://octopusdtlsupport.atlassian.net/browse/MN-142 | https://octopusdtlsupport.atlassian.net/browse/MN-144 | [5 empty] | 2026-04-02T10:57:42.044+0500 | 2026-04-20T12:33:11.160+0500
MN | MN-145 | MN-145 | Story | Story |  | SQA Handover | To Do | 2026-04-23 | 2026-04-23 |  |  | 8 | 8 | Aiza Hamid | 0 |  | MN-30 | MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-145 | [5 empty] | 2026-04-09T14:37:39.436+0500 | 2026-04-09T14:44:19.193+0500
MN | MN-146 | MN-146 | Story | Story |  | Regression SQA | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-30 | MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-146 | [5 empty] | 2026-04-09T14:39:49.665+0500 | 2026-04-09T14:39:49.902+0500
MN | MN-147 | MN-147 | Epic | Epic |  | Omni Chat Regression | In-Progress | 2026-01-01 | 2026-12-31 |  |  | 0 | 0 | Muhammad Abbas | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-147 | [5 empty] | 2026-04-14T11:48:33.427+0500 | 2026-04-14T11:49:46.361+0500
MN | MN-148 | MN-148 | Story | Story |  | Omni Chat Regression(4/15/2026) | In-Progress | 2026-04-14 | 2026-05-25 |  |  | 240 | 240 | Muhammad Abbas | 24 |  | MN-147 | MN-147 | https://octopusdtlsupport.atlassian.net/browse/MN-147 | https://octopusdtlsupport.atlassian.net/browse/MN-148 | [5 empty] | 2026-04-14T11:51:40.396+0500 | 2026-04-14T11:54:14.532+0500
MN | MN-149 | MN-149 | Sub-task | Sub-task |  | Forgot Password Module Regression | Resolved! | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-15 | 16 | 16 | Namra Zahid | 16 |  | MN-148 | MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-149 | [5 empty] | 2026-04-14T11:52:32.307+0500 | 2026-04-15T17:06:51.367+0500
MN | MN-15 | MN-15 | Sub-task | Sub-task |  | KT session for code | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-15 | [5 empty] | 2026-01-27T16:05:27.572+0500 | 2026-02-12T16:15:45.856+0500
MN | MN-150 | MN-150 | Sub-task | Sub-task |  | Login Module Regression | Resolved! | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 8 | 8 | Muhammad Abbas | 8 |  | MN-148 | MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-150 | [5 empty] | 2026-04-14T16:56:46.347+0500 | 2026-04-15T10:34:18.533+0500
MN | MN-151 | MN-151 | Bug Subtask | Bug Subtask |  | System accepts unregistered email and does not display proper error message | Request received | 2026-04-15 |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-148 | MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-151 | [5 empty] | 2026-04-15T10:55:23.542+0500 | 2026-04-15T11:07:51.902+0500
MN | MN-152 | MN-152 | Bug Subtask | Bug Subtask |  | Input field does not enforce min/max length constraints | Request received | 2026-04-15 |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-148 | MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-152 | [5 empty] | 2026-04-15T11:04:44.740+0500 | 2026-04-15T11:07:15.292+0500
MN | MN-153 | MN-153 | Epic | Epic |  | Text Overlap in Graphs (x-axis) | In-Progress | 2026-04-16 | 2026-04-22 |  |  | 40 | 40 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-153 | [5 empty] | 2026-04-15T12:03:06.648+0500 | 2026-04-29T12:03:18.451+0500
MN | MN-154 | MN-154 | Bug Subtask | Bug Subtask |  | Mismatch in reset link expiration time between application and email | Request received | 2026-04-15 |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-148 | MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-148 | https://octopusdtlsupport.atlassian.net/browse/MN-154 | [5 empty] | 2026-04-15T12:14:39.666+0500 | 2026-04-15T12:17:19.979+0500
MN | MN-155 | MN-155 | Sub-task | Sub-task |  | Development | Resolved! | 2026-03-10 | 2026-03-27 | 2026-03-10 | 2026-03-24 | 112 | 112 | Aiza Hamid | 53.5 |  | MN-144 | MN-144 | https://octopusdtlsupport.atlassian.net/browse/MN-144 | https://octopusdtlsupport.atlassian.net/browse/MN-155 | [5 empty] | 2026-04-20T12:27:30.176+0500 | 2026-04-20T12:33:27.227+0500
MN | MN-156 | MN-156 | Sub-task | Sub-task |  | Implementation of Forgot Password Module in Omni Chat Application | To Do |  |  | 2026-02-16 | 2026-02-16 | 0 | 0 | Aiza Hamid | 8 |  | MN-54 | MN-54 | https://octopusdtlsupport.atlassian.net/browse/MN-54 | https://octopusdtlsupport.atlassian.net/browse/MN-156 | [5 empty] | 2026-04-22T11:55:01.093+0500 | 2026-04-22T11:55:40.748+0500
MN | MN-157 | MN-157 | Story | Story |  | SQA Handover | To Do | 2026-06-30 | 2026-06-30 |  |  | 8 | 8 | Hamza Ali | 0 |  | MN-32 | MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-157 | [5 empty] | 2026-04-22T12:01:05.584+0500 | 2026-04-22T12:21:02.694+0500
MN | MN-158 | MN-158 | Story | Story |  | Development | In-Progress | 2026-04-16 | 2026-04-27 |  |  | 64 | 64 | Aiza Hamid | 16 |  | MN-153 | MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-158 | [5 empty] | 2026-04-22T12:04:22.077+0500 | 2026-04-27T14:45:39.141+0500
MN | MN-159 | MN-159 | Story | Story |  | SQA | To Do |  |  |  |  | 0.08 | 0.08 | Muhammad Abbas | 0 |  | MN-153 | MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-159 | [5 empty] | 2026-04-22T12:05:45.146+0500 | 2026-04-27T14:46:06.494+0500
MN | MN-16 | MN-16 | Sub-task | Sub-task |  | Understading of how the code works | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-16 | [5 empty] | 2026-01-27T16:05:40.691+0500 | 2026-02-12T16:15:46.307+0500
MN | MN-160 | MN-160 | Sub-task | Sub-task |  | Graph resizing | In-Progress | 2026-04-16 | 2026-04-22 | 2026-04-20 | 2026-04-21 | 40 | 40 | Aiza Hamid | 16 |  | MN-158 | MN-158 | https://octopusdtlsupport.atlassian.net/browse/MN-158 | https://octopusdtlsupport.atlassian.net/browse/MN-160 | [5 empty] | 2026-04-22T12:06:51.229+0500 | 2026-04-22T12:08:49.526+0500
MN | MN-161 | MN-161 | Story | Story |  | Development | To Do | 2026-04-21 | 2026-05-01 |  |  | 72 | 72 | Aiza Hamid | 0 |  | MN-75 | MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-161 | [5 empty] | 2026-04-22T12:07:59.887+0500 | 2026-04-22T13:02:24.119+0500
MN | MN-162 | MN-162 | Story | Story |  | SQA Handover | To Do | 2026-05-04 | 2026-05-04 |  |  | 8 | 8 | Aiza Hamid | 0 |  | MN-75 | MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-162 | [5 empty] | 2026-04-22T12:08:12.434+0500 | 2026-04-22T13:03:59.884+0500
MN | MN-163 | MN-163 | Story | Story |  | SQA | To Do | 2026-05-04 | 2026-05-12 |  |  | 0 | 0 | Muhammad Abbas | 0 |  | MN-75 | MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-163 | [5 empty] | 2026-04-22T12:08:23.956+0500 | 2026-04-22T13:04:39.389+0500
MN | MN-164 | MN-164 | Story | Story |  | Production Release | To Do | 2026-05-12 | 2026-05-12 |  |  | 8 | 8 | Aiza Hamid | 0 |  | MN-75 | MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-75 | https://octopusdtlsupport.atlassian.net/browse/MN-164 | [5 empty] | 2026-04-22T12:08:29.472+0500 | 2026-04-22T13:01:07.428+0500
MN | MN-165 | MN-165 | Story | Story |  | Production Release | To Do | 2026-08-26 | 2026-08-26 |  |  | 8 | 8 | Hamza Ali | 0 |  | MN-31 | MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-165 | [5 empty] | 2026-04-22T12:12:37.593+0500 | 2026-04-22T12:15:55.639+0500
MN | MN-166 | MN-166 | Story | Story |  | SQA Handover | To Do | 2026-08-17 | 2026-08-17 |  |  | 8 | 8 | Hamza Ali | 0 |  | MN-31 | MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-166 | [5 empty] | 2026-04-22T12:13:11.097+0500 | 2026-04-22T12:16:15.925+0500
MN | MN-167 | MN-167 | Story | Story |  | SQA Handover | To Do | 2026-04-20 | 2026-04-20 |  |  | 8 | 8 | Aiza Hamid | 0 |  | MN-153 | MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-167 | [5 empty] | 2026-04-22T12:26:02.880+0500 | 2026-04-22T12:29:19.182+0500
MN | MN-168 | MN-168 | Story | Story |  | Production Release | To Do | 2026-04-22 | 2026-04-22 |  |  | 8 | 8 | Aiza Hamid | 0 |  | MN-153 | MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-153 | https://octopusdtlsupport.atlassian.net/browse/MN-168 | [5 empty] | 2026-04-22T12:26:29.234+0500 | 2026-04-22T12:27:27.741+0500
MN | MN-169 | MN-169 | Story | Story |  | Development | To Do | 2026-05-04 | 2026-05-15 |  |  | 40 | 40 | Hamza Ali | 0 |  | MN-77 | MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-169 | [5 empty] | 2026-04-22T12:34:38.428+0500 | 2026-04-22T12:38:19.276+0500
MN | MN-17 | MN-17 | Sub-task | Sub-task |  | Flask and Jinja training | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-17 | [5 empty] | 2026-01-27T16:05:50.751+0500 | 2026-02-12T16:15:46.808+0500
MN | MN-170 | MN-170 | Story | Story |  | SQA Handover | To Do | 2026-05-18 | 2026-05-18 |  |  | 8 | 8 | Hamza Ali | 0 |  | MN-77 | MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-170 | [5 empty] | 2026-04-22T12:36:02.948+0500 | 2026-04-22T12:38:51.254+0500
MN | MN-171 | MN-171 | Story | Story |  | SQA | To Do | 2026-05-18 | 2026-05-22 |  |  | 40 | 40 | Muhammad Abbas | 0 |  | MN-77 | MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-171 | [5 empty] | 2026-04-22T12:36:17.533+0500 | 2026-04-22T12:53:50.056+0500
MN | MN-172 | MN-172 | Story | Story |  | Production Release | To Do | 2026-05-22 | 2026-05-22 |  |  | 8 | 8 | Hamza Ali | 0 |  | MN-77 | MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-77 | https://octopusdtlsupport.atlassian.net/browse/MN-172 | [5 empty] | 2026-04-22T12:36:33.656+0500 | 2026-04-22T12:39:41.829+0500
MN | MN-173 | MN-173 | Story | Story |  | Development | To Do | 2026-04-29 | 2026-05-06 |  |  | 40 | 40 | Aiza Hamid | 0 |  | MN-76 | MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-173 | [5 empty] | 2026-04-22T12:42:03.390+0500 | 2026-04-22T12:44:11.341+0500
MN | MN-174 | MN-174 | Story | Story |  | SQA Handover | To Do | 2026-05-07 | 2026-05-07 |  |  | 8 | 8 | Aiza Hamid | 0 |  | MN-76 | MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-174 | [5 empty] | 2026-04-22T12:42:12.408+0500 | 2026-04-22T12:57:55.878+0500
MN | MN-175 | MN-175 | Story | Story |  | SQA | To Do | 2026-05-07 |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | MN-76 | MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-175 | [5 empty] | 2026-04-22T12:42:30.289+0500 | 2026-04-22T12:58:27.667+0500
MN | MN-176 | MN-176 | Story | Story |  | Production Release | To Do | 2026-05-22 | 2026-05-22 |  |  | 8 | 8 | Aiza Hamid | 0 |  | MN-76 | MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-76 | https://octopusdtlsupport.atlassian.net/browse/MN-176 | [5 empty] | 2026-04-22T12:42:48.052+0500 | 2026-04-22T12:59:35.298+0500
MN | MN-177 | MN-177 | Story | Story |  | SQA Handover | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-53 | MN-53 | https://octopusdtlsupport.atlassian.net/browse/MN-53 | https://octopusdtlsupport.atlassian.net/browse/MN-177 | [5 empty] | 2026-04-22T12:55:05.247+0500 | 2026-04-22T12:55:05.453+0500
MN | MN-18 | MN-18 | Sub-task | Sub-task |  | Refactor code structure for improved readability and maintainability | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-18 | [5 empty] | 2026-01-28T10:54:08.639+0500 | 2026-02-12T16:15:47.264+0500
MN | MN-19 | MN-19 | Sub-task | Sub-task |  | update SweetAlert2 color scheme to use a green palette | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-19 | [5 empty] | 2026-01-28T10:54:32.827+0500 | 2026-02-12T16:15:47.692+0500
MN | MN-2 | MN-2 | Story | Story |  | Knowledge Transfer | Resolved! |  |  | 2026-01-19 | 2026-01-21 | 0 | 0 | awais akhter | 136 |  | MN-1 | MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-2 | [5 empty] | 2025-12-29T17:31:40.925+0500 | 2026-02-19T12:27:19.853+0500
MN | MN-20 | MN-20 | Sub-task | Sub-task |  | Update and add image assets in static directory | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-20 | [5 empty] | 2026-01-28T10:55:14.293+0500 | 2026-02-12T16:15:48.089+0500
MN | MN-21 | MN-21 | Sub-task | Sub-task |  | Handled navigation bar in Data and SOPs field for chat mode | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8 | 8 | Aiza Hamid | 4 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-21 | [5 empty] | 2026-01-29T12:53:21.937+0500 | 2026-02-12T16:15:48.473+0500
MN | MN-22 | MN-22 | Sub-task | Sub-task |  | Edited Feedback Report and Response Report | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 7 | 7 | Aiza Hamid | 7 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-22 | [5 empty] | 2026-01-30T14:00:16.114+0500 | 2026-02-25T10:18:30.867+0500
MN | MN-23 | MN-23 | Sub-task | Sub-task |  | Positive Feedback also gets saved to be presented in Feedback Report page | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-23 | [5 empty] | 2026-02-03T10:55:01.403+0500 | 2026-02-12T16:15:49.293+0500
MN | MN-24 | MN-24 | Sub-task | Sub-task |  | Dark mode and Light mode color changes | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-24 | [5 empty] | 2026-02-11T10:02:47.613+0500 | 2026-02-12T16:15:49.762+0500
MN | MN-25 | MN-25 | Sub-task | Sub-task |  | Separated navigation items for SOPs and Data | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 8 | 8 | Aiza Hamid | 6.5 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-25 | [5 empty] | 2026-02-11T14:43:49.981+0500 | 2026-03-25T10:37:38.982+0500
MN | MN-26 | MN-26 | Sub-task | Sub-task |  | Enhance UI elements and add keyboard shortcuts for improved user interaction | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 4 | 4 | Aiza Hamid | 4 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-26 | [5 empty] | 2026-02-11T14:44:20.049+0500 | 2026-02-12T16:15:50.690+0500
MN | MN-27 | MN-27 | Sub-task | Sub-task |  | Enhance styling for FAQs and VM Manager | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Aiza Hamid | 6 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-27 | [5 empty] | 2026-02-11T14:44:41.177+0500 | 2026-02-16T16:18:30.538+0500
MN | MN-28 | MN-28 | Sub-task | Sub-task |  | Enhanced file for Data Warehouse steps | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-28 | [5 empty] | 2026-02-11T16:15:34.959+0500 | 2026-02-20T11:09:30.592+0500
MN | MN-29 | MN-29 | Epic | Epic |  | Auto Dataset Selection | To Do | 2026-04-13 | 2026-05-01 |  |  | 144 | 144 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-29 | [5 empty] | 2026-02-13T11:50:32.530+0500 | 2026-04-22T11:56:21.785+0500
MN | MN-3 | MN-3 | Story | Story |  | Add the Support to Delete Chats | To Do | 2026-02-16 | 2026-02-18 |  |  | 24 | 24 | Hamza Ali | 24 |  | MN-137 | MN-137 | https://octopusdtlsupport.atlassian.net/browse/MN-137 | https://octopusdtlsupport.atlassian.net/browse/MN-3 | [5 empty] | 2026-01-26T11:59:32.697+0500 | 2026-03-17T11:23:35.013+0500
MN | MN-30 | MN-30 | Epic | Epic |  | Dashboard-level Filtering | To Do | 2026-04-10 | 2026-04-30 |  |  | 312 | 312 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-30 | [5 empty] | 2026-02-13T11:52:41.514+0500 | 2026-04-09T14:40:51.479+0500
MN | MN-31 | MN-31 | Epic | Epic |  | Team Collaborative Chat (Group Chat) | To Do | 2026-07-01 | 2026-08-26 |  |  | 352 | 352 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-31 | [5 empty] | 2026-02-13T11:55:52.422+0500 | 2026-04-22T12:16:27.309+0500
MN | MN-32 | MN-32 | Epic | Epic |  | Advanced Relationships for Multiple Datasets | To Do | 2026-05-19 | 2026-07-07 |  |  | 288 | 288 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-32 | [5 empty] | 2026-02-13T11:56:13.592+0500 | 2026-04-22T11:59:59.690+0500
MN | MN-33 | MN-33 | Epic | Epic |  | Enterprise Communication Channels Support | To Do |  |  |  |  | 400 | 400 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-33 | [5 empty] | 2026-02-13T11:56:58.640+0500 | 2026-03-27T16:09:05.240+0500
MN | MN-34 | MN-34 | Story | Story |  | Development | To Do | 2026-04-06 | 2026-04-24 |  |  | 104 | 104 | Hamza Ali | 0 |  | MN-29 | MN-29 | https://octopusdtlsupport.atlassian.net/browse/MN-29 | https://octopusdtlsupport.atlassian.net/browse/MN-34 | [5 empty] | 2026-02-13T12:01:19.398+0500 | 2026-02-16T15:19:14.826+0500
MN | MN-35 | MN-35 | Story | Story |  | Development | To Do | 2026-04-10 | 2026-04-22 |  |  | 32 | 32 | Aiza Hamid | 0 |  | MN-30 | MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-35 | [5 empty] | 2026-02-13T12:03:03.214+0500 | 2026-04-09T14:43:50.343+0500
MN | MN-36 | MN-36 | Story | Story |  | Development | To Do | 2026-07-01 | 2026-08-13 |  |  | 272 | 272 | Hamza Ali | 0 |  | MN-31 | MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-36 | [5 empty] | 2026-02-13T12:06:49.055+0500 | 2026-04-22T12:14:11.212+0500
MN | MN-37 | MN-37 | Story | Story |  | Development | To Do | 2026-05-19 | 2026-06-29 |  |  | 408 | 408 | Hamza Ali | 0 |  | MN-32 | MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-37 | [5 empty] | 2026-02-13T12:08:13.098+0500 | 2026-04-22T12:19:58.728+0500
MN | MN-38 | MN-38 | Story | Story |  | Development | To Do |  |  |  |  | 400 | 400 | Hamza Ali | 0 |  | MN-33 | MN-33 | https://octopusdtlsupport.atlassian.net/browse/MN-33 | https://octopusdtlsupport.atlassian.net/browse/MN-38 | [5 empty] | 2026-02-13T12:09:05.945+0500 | 2026-02-16T14:26:46.315+0500
MN | MN-4 | MN-4 | Story | Story |  | Chat Deletion Front-End Development | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-137 | MN-137 | https://octopusdtlsupport.atlassian.net/browse/MN-137 | https://octopusdtlsupport.atlassian.net/browse/MN-4 | [5 empty] | 2026-01-26T12:00:00.306+0500 | 2026-03-17T11:23:26.437+0500
MN | MN-42 | MN-42 | Epic | Epic |  | Technical Support | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-42 | [5 empty] | 2026-02-13T15:46:30.572+0500 | 2026-02-13T15:46:30.966+0500
MN | MN-43 | MN-43 | Story | Story |  | URS Handover and Work Breakdown Structure | Resolved! | 2026-02-12 | 2026-02-17 |  |  | 24 | 24 | Taimur Zahid | 21 |  | MN-1 | MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-43 | [5 empty] | 2026-02-13T16:17:46.175+0500 | 2026-03-05T15:38:26.613+0500
MN | MN-44 | MN-44 | Sub-task | Sub-task |  | Requirement Gathering from URS | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Taimur Zahid | 8 |  | MN-43 | MN-43 | https://octopusdtlsupport.atlassian.net/browse/MN-43 | https://octopusdtlsupport.atlassian.net/browse/MN-44 | [5 empty] | 2026-02-13T16:18:49.251+0500 | 2026-02-13T16:31:47.069+0500
MN | MN-46 | MN-46 | Story | Story |  | SQA Knowledge Transfer Recorded Sessions | To Do | 2026-02-13 | 2026-02-20 |  |  | 80 | 80 | Muhammad Abbas | 0 |  | MN-1 | MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-1 | https://octopusdtlsupport.atlassian.net/browse/MN-46 | [5 empty] | 2026-02-16T12:42:42.338+0500 | 2026-02-20T12:14:50.694+0500
MN | MN-47 | MN-47 | Sub-task | Sub-task |  | Front-end Changes | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-34 | MN-34 | https://octopusdtlsupport.atlassian.net/browse/MN-34 | https://octopusdtlsupport.atlassian.net/browse/MN-47 | [5 empty] | 2026-02-16T12:54:27.060+0500 | 2026-02-16T12:54:39.249+0500
MN | MN-48 | MN-48 | Sub-task | Sub-task |  | Function-App Changes | To Do |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | MN-34 | MN-34 | https://octopusdtlsupport.atlassian.net/browse/MN-34 | https://octopusdtlsupport.atlassian.net/browse/MN-48 | [5 empty] | 2026-02-16T12:55:06.139+0500 | 2026-02-16T12:55:13.237+0500
MN | MN-49 | MN-49 | Sub-task | Sub-task |  | Open AI Integration and Changes | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | MN-34 | MN-34 | https://octopusdtlsupport.atlassian.net/browse/MN-34 | https://octopusdtlsupport.atlassian.net/browse/MN-49 | [5 empty] | 2026-02-16T12:55:28.335+0500 | 2026-02-16T12:56:18.611+0500
MN | MN-5 | MN-5 | Story | Story |  | Missing Hierarchy Structure in UM | To Do | 2026-02-20 | 2026-02-20 |  |  | 8 | 8 | awais akhter | 8 |  | MN-139 | MN-139 | https://octopusdtlsupport.atlassian.net/browse/MN-139 | https://octopusdtlsupport.atlassian.net/browse/MN-5 | [5 empty] | 2026-01-28T11:51:34.789+0500 | 2026-03-17T11:39:36.056+0500
MN | MN-50 | MN-50 | Story | Story |  | SQA | To Do |  |  |  |  | 40 | 40 | Muhammad Abbas | 0 |  | MN-29 | MN-29 | https://octopusdtlsupport.atlassian.net/browse/MN-29 | https://octopusdtlsupport.atlassian.net/browse/MN-50 | [5 empty] | 2026-02-16T12:56:33.613+0500 | 2026-02-16T15:18:17.465+0500
MN | MN-51 | MN-51 | Story | Story |  | SQA | To Do |  |  |  |  | 8 | 8 | Muhammad Abbas | 0 |  | MN-30 | MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-51 | [5 empty] | 2026-02-16T14:08:44.323+0500 | 2026-04-09T14:44:45.615+0500
MN | MN-52 | MN-52 | Story | Story |  | User Manual | To Do |  |  |  |  | 24 | 24 | Hassan Malik | 0 |  | MN-30 | MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-30 | https://octopusdtlsupport.atlassian.net/browse/MN-52 | [5 empty] | 2026-02-16T14:10:10.080+0500 | 2026-02-19T14:26:00.589+0500
MN | MN-53 | MN-53 | Epic | Epic |  | Forgot Password Functionality | Resolved! | 2026-02-16 | 2026-03-04 |  |  | 104 | 104 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-53 | [5 empty] | 2026-02-16T14:19:50.831+0500 | 2026-04-22T12:00:13.399+0500
MN | MN-54 | MN-54 | Story | Story |  | Development | Resolved! | 2026-02-16 | 2026-03-03 |  |  | 40 | 40 | Aiza Hamid | 14.5 |  | MN-53 | MN-53 | https://octopusdtlsupport.atlassian.net/browse/MN-53 | https://octopusdtlsupport.atlassian.net/browse/MN-54 | [5 empty] | 2026-02-16T14:20:21.107+0500 | 2026-04-22T11:54:47.368+0500
MN | MN-55 | MN-55 | Story | Story |  | SQA | Resolved! | 2026-03-03 | 2026-03-04 |  |  | 1 | 1 | Muhammad Abbas | 1 |  | MN-53 | MN-53 | https://octopusdtlsupport.atlassian.net/browse/MN-53 | https://octopusdtlsupport.atlassian.net/browse/MN-55 | [5 empty] | 2026-02-16T14:20:35.709+0500 | 2026-03-25T10:47:25.104+0500
MN | MN-56 | MN-56 | Sub-task | Sub-task |  | Password Reset Functionality | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 8 | 8 | Aiza Hamid | 6.5 |  | MN-54 | MN-54 | https://octopusdtlsupport.atlassian.net/browse/MN-54 | https://octopusdtlsupport.atlassian.net/browse/MN-56 | [5 empty] | 2026-02-16T14:21:31.401+0500 | 2026-03-25T10:48:47.597+0500
MN | MN-57 | MN-57 | Sub-task | Sub-task |  | Unit Testing | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | MN-54 | MN-54 | https://octopusdtlsupport.atlassian.net/browse/MN-54 | https://octopusdtlsupport.atlassian.net/browse/MN-57 | [5 empty] | 2026-02-16T14:21:36.647+0500 | 2026-03-25T10:46:30.268+0500
MN | MN-58 | MN-58 | Story | Story |  | SQA | To Do |  |  |  |  | 80 | 80 | Muhammad Abbas | 0 |  | MN-33 | MN-33 | https://octopusdtlsupport.atlassian.net/browse/MN-33 | https://octopusdtlsupport.atlassian.net/browse/MN-58 | [5 empty] | 2026-02-16T14:26:58.729+0500 | 2026-02-16T14:27:30.159+0500
MN | MN-59 | MN-59 | Story | Story |  | Manual | To Do |  |  |  |  | 80 | 80 | Hassan Malik | 0 |  | MN-33 | MN-33 | https://octopusdtlsupport.atlassian.net/browse/MN-33 | https://octopusdtlsupport.atlassian.net/browse/MN-59 | [5 empty] | 2026-02-16T14:27:00.738+0500 | 2026-02-16T14:34:54.392+0500
MN | MN-6 | MN-6 | Story | Story |  | Frontend Changes | Resolved! | 2026-01-07 | 2026-02-24 |  |  | 296 | 296 | Aiza Hamid | 185.5 |  | MN-78 | MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | [5 empty] | 2026-01-22T15:26:17.936+0500 | 2026-02-25T11:47:41.502+0500
MN | MN-60 | MN-60 | Story | Story |  | SQA | To Do | 2026-06-30 | 2026-07-06 |  |  | 40 | 40 | Muhammad Abbas | 0 |  | MN-32 | MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-60 | [5 empty] | 2026-02-16T15:03:43.707+0500 | 2026-04-22T12:20:53.654+0500
MN | MN-61 | MN-61 | Story | Story |  | User Manual | To Do |  |  |  |  | 40 | 40 | Hassan Malik | 0 |  | MN-32 | MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-32 | https://octopusdtlsupport.atlassian.net/browse/MN-61 | [5 empty] | 2026-02-16T15:03:46.973+0500 | 2026-03-27T14:29:00.634+0500
MN | MN-62 | MN-62 | Story | Story |  | SQA | To Do | 2026-08-17 | 2026-08-26 |  |  | 40 | 40 | Muhammad Abbas | 0 |  | MN-31 | MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-62 | [5 empty] | 2026-02-16T15:06:22.401+0500 | 2026-04-22T12:14:56.316+0500
MN | MN-63 | MN-63 | Story | Story |  | User Manual | To Do | 2026-08-17 | 2026-08-26 |  |  | 40 | 40 | Hassan Malik | 0 |  | MN-31 | MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-31 | https://octopusdtlsupport.atlassian.net/browse/MN-63 | [5 empty] | 2026-02-16T15:06:33.999+0500 | 2026-04-22T12:15:33.410+0500
MN | MN-65 | MN-65 | Story | Story |  | DDS | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-65 | [5 empty] | 2026-02-16T16:08:55.138+0500 | 2026-02-16T16:21:36.200+0500
MN | MN-66 | MN-66 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-66 | [5 empty] | 2026-02-16T16:09:03.897+0500 | 2026-02-16T16:21:49.740+0500
MN | MN-67 | MN-67 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-67 | [5 empty] | 2026-02-16T16:10:26.606+0500 | 2026-02-16T16:21:56.416+0500
MN | MN-68 | MN-68 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-68 | [5 empty] | 2026-02-16T16:10:32.905+0500 | 2026-02-16T16:22:00.765+0500
MN | MN-7 | MN-7 | Sub-task | Sub-task |  | Main Logo changed | Resolved! | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-7 | [5 empty] | 2026-01-22T15:31:07.137+0500 | 2026-02-12T16:15:42.101+0500
MN | MN-70 | MN-70 | Sub-task | Sub-task |  | Password Reset through ACS functionality | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-70 | [5 empty] | 2026-02-18T10:20:45.303+0500 | 2026-02-18T10:21:35.088+0500
MN | MN-71 | MN-71 | Sub-task | Sub-task |  | Meetings and Requirements finalization | Resolved! | 2026-02-17 | 2026-02-18 | 2026-02-17 | 2026-02-18 | 16 | 16 | Taimur Zahid | 13 |  | MN-43 | MN-43 | https://octopusdtlsupport.atlassian.net/browse/MN-43 | https://octopusdtlsupport.atlassian.net/browse/MN-71 | [5 empty] | 2026-02-18T14:20:18.105+0500 | 2026-03-10T10:57:58.675+0500
MN | MN-72 | MN-72 | Sub-task | Sub-task |  | Ibhrahim's Onboarding | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | MN-2 | MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-72 | [5 empty] | 2026-02-19T12:20:17.958+0500 | 2026-02-19T12:28:59.595+0500
MN | MN-73 | MN-73 | Sub-task | Sub-task |  | Hamza's Onboarding | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | MN-2 | MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-73 | [5 empty] | 2026-02-19T12:20:26.096+0500 | 2026-02-19T12:20:26.238+0500
MN | MN-74 | MN-74 | Sub-task | Sub-task |  | Aiza's Onboarding | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | MN-2 | MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-2 | https://octopusdtlsupport.atlassian.net/browse/MN-74 | [5 empty] | 2026-02-19T12:20:32.034+0500 | 2026-02-19T12:20:32.181+0500
MN | MN-75 | MN-75 | Epic | Epic |  | Panel-level Filtering | To Do | 2026-04-21 | 2026-05-12 |  |  | 176 | 176 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-75 | [5 empty] | 2026-02-19T14:26:56.462+0500 | 2026-04-22T12:12:52.570+0500
MN | MN-76 | MN-76 | Epic | Epic |  | Panel Resizing | To Do | 2026-04-29 | 2026-05-22 |  |  | 104 | 104 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-76 | [5 empty] | 2026-02-19T14:27:20.852+0500 | 2026-04-22T12:43:38.346+0500
MN | MN-77 | MN-77 | Epic | Epic |  | Auto Dashboard Sharing | To Do | 2026-05-04 | 2026-05-22 |  |  | 120 | 120 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-77 | [5 empty] | 2026-02-19T14:27:53.513+0500 | 2026-04-22T12:37:26.924+0500
MN | MN-78 | MN-78 | Epic | Epic |  | OmniChat Bugs Fixing | Resolved! | 2026-01-07 | 2026-03-13 |  |  | 416 | 416 | Taimur Zahid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-78 | [5 empty] | 2026-02-20T11:58:25.661+0500 | 2026-04-02T12:22:48.832+0500
MN | MN-8 | MN-8 | Sub-task | Sub-task |  | LogIn page color scheme altered | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Aiza Hamid | 8 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-8 | [5 empty] | 2026-01-22T15:31:28.325+0500 | 2026-02-12T16:15:42.534+0500
MN | MN-86 | MN-86 | Story | Story |  | OmniChat Front-End Testing | Resolved! | 2026-03-03 | 2026-03-03 |  |  | 8 | 8 | Muhammad Abbas | 8 |  | MN-78 | MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-86 | [5 empty] | 2026-02-20T12:09:42.151+0500 | 2026-03-03T16:04:19.213+0500
MN | MN-89 | MN-89 | Sub-task | Sub-task |  | OmniAgent logo addition | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | Aiza Hamid | 6.5 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-89 | [5 empty] | 2026-02-20T14:38:07.392+0500 | 2026-03-25T10:38:24.790+0500
MN | MN-9 | MN-9 | Sub-task | Sub-task |  | Text adjustment in chat input | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8 | 8 | Aiza Hamid | 4 |  | MN-6 | MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-6 | https://octopusdtlsupport.atlassian.net/browse/MN-9 | [5 empty] | 2026-01-27T16:03:13.480+0500 | 2026-02-12T16:15:42.994+0500
MN | MN-90 | MN-90 | Epic | Epic |  | 2FA Alignment | To Do |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-90 | [5 empty] | 2026-02-24T10:12:23.990+0500 | 2026-03-13T12:16:36.068+0500
MN | MN-91 | MN-91 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | MN-90 | MN-90 | https://octopusdtlsupport.atlassian.net/browse/MN-90 | https://octopusdtlsupport.atlassian.net/browse/MN-91 | [5 empty] | 2026-02-24T10:12:43.553+0500 | 2026-02-25T08:45:55.084+0500
MN | MN-92 | MN-92 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | MN-90 | MN-90 | https://octopusdtlsupport.atlassian.net/browse/MN-90 | https://octopusdtlsupport.atlassian.net/browse/MN-92 | [5 empty] | 2026-02-24T10:12:48.231+0500 | 2026-02-24T10:13:17.142+0500
MN | MN-93 | MN-93 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-02-24 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1 | 1 | Muhammad Abbas | 1 |  | MN-55 | MN-55 | https://octopusdtlsupport.atlassian.net/browse/MN-55 | https://octopusdtlsupport.atlassian.net/browse/MN-93 | [5 empty] | 2026-02-24T11:02:04.672+0500 | 2026-03-25T10:47:05.094+0500
MN | MN-94 | MN-94 | Epic | Epic |  | OmniChat Regression | To Do | 2026-03-02 | 2026-04-10 |  |  | 480 | 480 | Muhammad Abbas | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/MN-94 | [5 empty] | 2026-02-24T11:05:07.933+0500 | 2026-02-25T13:03:04.430+0500
MN | MN-95 | MN-95 | Story | Story |  | Staging Release | Resolved! | 2026-02-24 | 2026-03-13 |  |  | 80 | 80 | Ibrahim Ahmed Qureshi | 25.5 |  | MN-78 | MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-78 | https://octopusdtlsupport.atlassian.net/browse/MN-95 | [5 empty] | 2026-02-24T14:31:38.415+0500 | 2026-04-02T12:23:01.755+0500
MN | MN-96 | MN-96 | Sub-task | Sub-task |  | Staging Release | Resolved! | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 12 | 12 | Ibrahim Ahmed Qureshi | 12 |  | MN-95 | MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-96 | [5 empty] | 2026-02-24T14:31:58.405+0500 | 2026-03-10T15:55:16.315+0500
MN | MN-97 | MN-97 | Sub-task | Sub-task |  | Staging Release | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 4 | 4 | Aiza Hamid | 2.5 |  | MN-95 | MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-97 | [5 empty] | 2026-02-24T14:32:12.189+0500 | 2026-03-25T10:45:10.070+0500
MN | MN-98 | MN-98 | Sub-task | Sub-task |  | Staging Release | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 6.5 | 6.5 | Taimur Zahid | 6.5 |  | MN-95 | MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-98 | [5 empty] | 2026-02-24T14:32:18.299+0500 | 2026-03-17T15:29:37.462+0500
MN | MN-99 | MN-99 | Sub-task | Sub-task |  | SQA Testing | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | MN-95 | MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-95 | https://octopusdtlsupport.atlassian.net/browse/MN-99 | [5 empty] | 2026-02-24T14:32:53.056+0500 | 2026-02-24T14:32:58.842+0500
O2 | O2-10 | O2-10 | Epic | Epic |  | Code Reusability in existing Batch/Bpm Jobs | To Do | 2026-02-27 | 2026-03-26 |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-10 | [5 empty] | 2025-10-02T14:00:47.248+0500 | 2026-04-20T11:50:18.762+0500
O2 | O2-100 | O2-100 | Story | Story |  | User Manual | Resolved! | 2025-10-06 | 2025-10-14 |  |  | 144 | 144 | Hassan Malik | 44 |  | O2-94 | O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-100 | [5 empty] | 2025-10-03T19:54:33.461+0500 | 2025-10-24T16:28:29.706+0500
O2 | O2-1000 | O2-1000 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-1000 | [5 empty] | 2026-01-22T11:30:05.082+0500 | 2026-01-22T11:30:05.214+0500
O2 | O2-1001 | O2-1001 | Story | Story |  | Add Training Material (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-1001 | [5 empty] | 2026-01-22T11:30:19.668+0500 | 2026-01-22T11:30:19.791+0500
O2 | O2-1002 | O2-1002 | Sub-task | Sub-task |  | Create Assets, Tags, simulator, assign alerts | Resolved! | 2026-01-05 | 2026-01-09 | 2026-01-05 | 2026-01-05 | 40 | 40 | Faiq Butt | 40 |  | O2-534 | O2-534 | https://octopusdtlsupport.atlassian.net/browse/O2-534 | https://octopusdtlsupport.atlassian.net/browse/O2-1002 | [5 empty] | 2026-01-22T11:44:57.018+0500 | 2026-01-22T12:20:59.506+0500
O2 | O2-1003 | O2-1003 | Sub-task | Sub-task |  | Make Training Material | Resolved! | 2026-01-22 | 2026-01-28 | 2026-01-26 | 2026-01-30 | 40 | 40 | Danish Rashid | 40 |  | O2-534 | O2-534 | https://octopusdtlsupport.atlassian.net/browse/O2-534 | https://octopusdtlsupport.atlassian.net/browse/O2-1003 | [5 empty] | 2026-01-22T11:45:18.832+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-1004 | O2-1004 | Bug Subtask | Bug Subtask |  | Latest Values Not Populating for Calculated Tag (Boolean Type) | Resolved |  |  |  |  | 8 | 8 | Mohsin Junaid | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1004 | [5 empty] | 2026-01-22T11:54:10.640+0500 | 2026-02-13T16:19:21.346+0500
O2 | O2-1005 | O2-1005 | Epic | Epic |  | Centrifugal Compressor What-If (Fixed / Variable Speed) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | [5 empty] | 2026-01-22T12:15:54.454+0500 | 2026-01-26T18:22:16.448+0500
O2 | O2-1006 | O2-1006 | Story | Story |  | Design What-If Model (P) | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1006 | [5 empty] | 2026-01-22T12:16:10.248+0500 | 2026-01-22T12:17:18.065+0500
O2 | O2-1007 | O2-1007 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1007 | [5 empty] | 2026-01-22T12:16:14.546+0500 | 2026-01-22T12:16:14.677+0500
O2 | O2-1008 | O2-1008 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1008 | [5 empty] | 2026-01-22T12:16:20.827+0500 | 2026-01-22T12:18:27.847+0500
O2 | O2-1009 | O2-1009 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1009 | [5 empty] | 2026-01-22T12:16:26.726+0500 | 2026-01-22T12:16:26.840+0500
O2 | O2-101 | O2-101 | Story | Story |  | Production Release | Resolved! | 2025-10-15 | 2025-10-15 |  |  | 16 | 16 | Faiza Nasir | 24 |  | O2-94 | O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-101 | [5 empty] | 2025-10-03T19:54:40.759+0500 | 2025-10-24T16:28:44.177+0500
O2 | O2-1010 | O2-1010 | Story | Story |  | OC Process testing (P) | Resolved! |  |  |  |  | 0 | 0 | Faiq Butt | 32 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1010 | [5 empty] | 2026-01-22T12:16:32.176+0500 | 2026-02-18T12:24:16.125+0500
O2 | O2-1011 | O2-1011 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1011 | [5 empty] | 2026-01-22T12:16:37.272+0500 | 2026-01-22T12:16:37.467+0500
O2 | O2-1012 | O2-1012 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1012 | [5 empty] | 2026-01-22T12:16:41.470+0500 | 2026-01-22T12:16:41.609+0500
O2 | O2-1013 | O2-1013 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1013 | [5 empty] | 2026-01-22T12:16:47.856+0500 | 2026-01-22T12:16:48.043+0500
O2 | O2-1014 | O2-1014 | Story | Story |  | Add Training Material (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1005 | O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1005 | https://octopusdtlsupport.atlassian.net/browse/O2-1014 | [5 empty] | 2026-01-22T12:16:53.331+0500 | 2026-01-22T12:16:53.448+0500
O2 | O2-1015 | O2-1015 | Story | Story |  | ADE utilisation on APX by OmniAgent Concept | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abdul Wasi | 64 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-1015 | [5 empty] | 2026-01-22T12:39:51.017+0500 | 2026-02-18T14:27:39.881+0500
O2 | O2-1016 | O2-1016 | Story | Story |  | APX Performance Module Training Material | Resolved! | 2025-12-11 | 2026-01-30 |  |  | 0 | 0 | Muhammad Abdul Wasi | 68 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-1016 | [5 empty] | 2026-01-22T12:50:13.355+0500 | 2026-02-18T14:46:45.393+0500
O2 | O2-1017 | O2-1017 | Sub-task | Sub-task |  | ADE / APXH Improvements Testing (P) | Resolved! | 2026-01-05 | 2026-01-30 | 2026-02-06 | 2026-02-10 | 24 | 24 | Muhammad Abdul Wasi | 24 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-1017 | [5 empty] | 2026-01-22T13:00:44.316+0500 | 2026-02-13T09:44:31.553+0500
O2 | O2-1018 | O2-1018 | Epic | Epic |  | Cooling Tower What-If | In-Progress |  |  |  |  | 0 | 0 | Muhammad Abdul Wasi | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | [5 empty] | 2026-01-22T13:12:02.484+0500 | 2026-03-26T09:16:27.038+0500
O2 | O2-1019 | O2-1019 | Story | Story |  | Design What-If Model (P) | Resolved! | 2025-11-03 | 2026-02-13 |  |  | 120 | 120 | Muhammad Abdul Wasi | 0 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1019 | [5 empty] | 2026-01-22T13:12:18.552+0500 | 2026-02-19T08:47:00.768+0500
O2 | O2-1020 | O2-1020 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1020 | [5 empty] | 2026-01-22T13:12:23.566+0500 | 2026-01-22T13:12:23.685+0500
O2 | O2-1021 | O2-1021 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abdul Wasi | 8 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1021 | [5 empty] | 2026-01-22T13:12:28.185+0500 | 2026-03-09T09:42:03.666+0500
O2 | O2-1022 | O2-1022 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1022 | [5 empty] | 2026-01-22T13:12:33.765+0500 | 2026-01-22T13:12:33.955+0500
O2 | O2-1023 | O2-1023 | Story | Story |  | OC Process testing (P) | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 38 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1023 | [5 empty] | 2026-01-22T13:12:39.287+0500 | 2026-02-18T15:04:02.562+0500
O2 | O2-1024 | O2-1024 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1024 | [5 empty] | 2026-01-22T13:12:44.862+0500 | 2026-01-22T13:12:44.981+0500
O2 | O2-1025 | O2-1025 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1025 | [5 empty] | 2026-01-22T13:12:50.680+0500 | 2026-01-22T13:12:50.960+0500
O2 | O2-1026 | O2-1026 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1026 | [5 empty] | 2026-01-22T13:12:55.265+0500 | 2026-01-22T13:12:55.387+0500
O2 | O2-1027 | O2-1027 | Story | Story |  | Add Training Material (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1018 | O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1018 | https://octopusdtlsupport.atlassian.net/browse/O2-1027 | [5 empty] | 2026-01-22T13:13:00.360+0500 | 2026-01-22T13:13:00.478+0500
O2 | O2-1028 | O2-1028 | Epic | Epic |  | Electric Motor - Health | To Do |  |  |  |  | 0 | 0 | awais akhter | 2 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | [5 empty] | 2026-01-22T14:26:35.768+0500 | 2026-02-18T12:44:20.135+0500
O2 | O2-1029 | O2-1029 | Story | Story |  | Module Design (P) | In-Progress |  |  | 2026-02-23 | 2026-02-23 | 0 | 0 | DANIYAL AHMAD | 149 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1029 | [5 empty] | 2026-01-22T14:26:50.373+0500 | 2026-02-24T13:25:54.889+0500
O2 | O2-1030 | O2-1030 | Story | Story |  | Template (P) | To Do | 2026-02-09 | 2026-02-20 |  |  | 16 | 16 | DANIYAL AHMAD | 37.5 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1030 | [5 empty] | 2026-01-22T14:26:55.253+0500 | 2026-01-22T14:34:01.469+0500
O2 | O2-1031 | O2-1031 | Story | Story |  | Asset type addition | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1031 | [5 empty] | 2026-01-22T14:27:01.656+0500 | 2026-01-22T14:27:01.774+0500
O2 | O2-1032 | O2-1032 | Story | Story |  | OC Process testing (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 83.5 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1032 | [5 empty] | 2026-01-22T14:27:07.456+0500 | 2026-01-22T14:27:07.579+0500
O2 | O2-1033 | O2-1033 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1033 | [5 empty] | 2026-01-22T14:27:13.334+0500 | 2026-01-22T14:27:13.512+0500
O2 | O2-1034 | O2-1034 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1034 | [5 empty] | 2026-01-22T14:27:19.831+0500 | 2026-01-22T14:27:19.960+0500
O2 | O2-1035 | O2-1035 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1035 | [5 empty] | 2026-01-22T14:27:25.523+0500 | 2026-01-22T14:27:25.634+0500
O2 | O2-1036 | O2-1036 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1028 | O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1028 | https://octopusdtlsupport.atlassian.net/browse/O2-1036 | [5 empty] | 2026-01-22T14:27:30.242+0500 | 2026-01-22T14:27:30.370+0500
O2 | O2-1037 | O2-1037 | Bug Subtask | Bug Subtask |  | All Countries Are Not Displayed in Country Dropdown While Creating or Editing Customer and Site | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1037 | [5 empty] | 2026-01-22T14:35:56.340+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1038 | O2-1038 | Bug Subtask | Bug Subtask |  | Tag Level Diagnostics Checkbox Missing in Notification Group | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1038 | [5 empty] | 2026-01-22T14:42:19.223+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1039 | O2-1039 | Bug Subtask | Bug Subtask |  | System Alarm Message Inconsistency Between Ashghal and Production Blue | Resolved |  |  | 2026-01-22 | 2026-01-22 | 0 | 0 | Faiza Nasir | 1 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1039 | [5 empty] | 2026-01-22T15:07:36.885+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-104 | O2-104 | Story | Story |  | Development | Resolved! | 2025-10-20 | 2025-10-24 |  |  | 96 | 96 | Hamza Ali | 102 |  | O2-95 | O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-104 | [5 empty] | 2025-10-03T19:54:54.091+0500 | 2025-10-30T09:46:12.573+0500
O2 | O2-1040 | O2-1040 | Bug Subtask | Bug Subtask |  | System Alarms Not Displayed for UserDefinedFunctions and UserDefinedTables | Resolved | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | Muhammad Usman Javed | 1 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1040 | [5 empty] | 2026-01-22T15:12:04.915+0500 | 2026-02-20T16:51:25.457+0500
O2 | O2-1041 | O2-1041 | Story | Story |  | Development | Resolved! | 2026-01-07 | 2026-01-19 |  |  | 192 | 192 | ahad omer | 256 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | [5 empty] | 2026-01-22T15:13:08.461+0500 | 2026-03-04T16:40:39.333+0500
O2 | O2-1042 | O2-1042 | Story | Story |  | User Manual | Resolved! |  |  | 2026-01-19 | 2026-01-21 | 48 | 48 | Hassan Malik | 16 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-1042 | [5 empty] | 2026-01-22T15:13:16.002+0500 | 2026-02-11T15:21:06.668+0500
O2 | O2-1043 | O2-1043 | Story | Story |  | Production Release | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-1043 | [5 empty] | 2026-01-22T15:13:19.134+0500 | 2026-02-19T14:17:06.303+0500
O2 | O2-1044 | O2-1044 | Epic | Epic |  | Centrifugal Compressor - Health (Fixed / Variable Speed) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | [5 empty] | 2026-01-22T15:13:48.005+0500 | 2026-01-26T18:22:42.699+0500
O2 | O2-1045 | O2-1045 | Story | Story |  | Module Design (P) | Resolved! | 2025-12-15 | 2026-02-10 |  |  | 80 | 80 | Danish Rashid | 109 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1045 | [5 empty] | 2026-01-22T15:13:57.664+0500 | 2026-02-18T13:02:52.799+0500
O2 | O2-1046 | O2-1046 | Story | Story |  | Template (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 8 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1046 | [5 empty] | 2026-01-22T15:14:01.405+0500 | 2026-01-22T15:14:01.527+0500
O2 | O2-1047 | O2-1047 | Story | Story |  | Asset type addition | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1047 | [5 empty] | 2026-01-22T15:14:07.395+0500 | 2026-01-22T15:14:07.515+0500
O2 | O2-1048 | O2-1048 | Story | Story |  | OC Process testing (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 37 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | [5 empty] | 2026-01-22T15:14:20.236+0500 | 2026-01-22T15:14:20.346+0500
O2 | O2-1049 | O2-1049 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1049 | [5 empty] | 2026-01-22T15:14:26.041+0500 | 2026-01-22T15:14:26.182+0500
O2 | O2-105 | O2-105 | Story | Story |  | SQA | Resolved! | 2025-10-27 | 2025-10-30 |  |  | 24 | 24 | Muhammad Abbas | 183 |  | O2-95 | O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | [5 empty] | 2025-10-03T19:54:55.463+0500 | 2026-02-11T09:38:57.299+0500
O2 | O2-1050 | O2-1050 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1050 | [5 empty] | 2026-01-22T15:14:31.013+0500 | 2026-01-22T15:14:31.131+0500
O2 | O2-1051 | O2-1051 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1051 | [5 empty] | 2026-01-22T15:14:35.410+0500 | 2026-01-22T15:14:35.590+0500
O2 | O2-1052 | O2-1052 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1044 | O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1044 | https://octopusdtlsupport.atlassian.net/browse/O2-1052 | [5 empty] | 2026-01-22T15:14:39.968+0500 | 2026-01-22T15:14:40.082+0500
O2 | O2-1053 | O2-1053 | Sub-task | Sub-task |  | UI Development | Resolved! | 2026-01-07 | 2026-01-09 | 2026-01-07 | 2026-01-09 | 24 | 24 | Arslan sohail | 24 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1053 | [5 empty] | 2026-01-22T15:19:05.193+0500 | 2026-03-04T16:07:22.369+0500
O2 | O2-1054 | O2-1054 | Sub-task | Sub-task |  | Frontend Development | Resolved! | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 0 | 0 | Arslan sohail | 24 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1054 | [5 empty] | 2026-01-22T15:19:14.851+0500 | 2026-03-04T16:08:22.120+0500
O2 | O2-1055 | O2-1055 | Sub-task | Sub-task |  | Backend Development | Resolved! | 2026-01-07 | 2026-01-19 | 2026-01-08 | 2026-01-19 | 136 | 136 | Syed Yousaf Qadri | 64 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1055 | [5 empty] | 2026-01-22T15:19:20.584+0500 | 2026-03-05T12:14:22.432+0500
O2 | O2-1056 | O2-1056 | Sub-task | Sub-task |  | End to end Testing | Resolved! | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1056 | [5 empty] | 2026-01-22T15:19:28.563+0500 | 2026-03-13T11:14:12.336+0500
O2 | O2-1057 | O2-1057 | Sub-task | Sub-task |  | Finalise Taglist | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1045 | O2-1045 | https://octopusdtlsupport.atlassian.net/browse/O2-1045 | https://octopusdtlsupport.atlassian.net/browse/O2-1057 | [5 empty] | 2026-01-22T15:25:58.049+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-1059 | O2-1059 | Bug Subtask | Bug Subtask |  | Latest Values Not Updating for Real-Time Tags Even After Publishing Changes | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1059 | [5 empty] | 2026-01-22T15:26:43.829+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-106 | O2-106 | Story | Story |  | User Manual | Resolved! | 2025-10-27 | 2025-10-30 |  |  | 24 | 24 | Hassan Malik | 29 |  | O2-95 | O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-106 | [5 empty] | 2025-10-03T19:55:01.926+0500 | 2025-11-04T15:45:08.028+0500
O2 | O2-1062 | O2-1062 | Bug Subtask | Bug Subtask |  | Unable to view associated assets against single area after coming back from folder view in asset hierarchy. | Resolved | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1062 | [5 empty] | 2026-01-22T15:32:10.986+0500 | 2026-02-20T16:54:59.252+0500
O2 | O2-1064 | O2-1064 | Bug Subtask | Bug Subtask |  | Write back is FAIL. | Resolved |  |  | 2026-01-26 | 2026-01-26 | 0 | 0 | Mohsin Junaid | 1 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1064 | [5 empty] | 2026-01-22T15:52:01.638+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1066 | O2-1066 | Story | Story |  | Process pre-sales support, Customer / Management Meetings | In-Progress |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 107 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | [5 empty] | 2026-01-22T16:07:16.628+0500 | 2026-02-27T09:26:40.432+0500
O2 | O2-1068 | O2-1068 | Bug Subtask | Bug Subtask |  | Source tags of MQTT device are not displaying. | Resolved |  |  | 2026-01-12 | 2026-01-30 | 40 | 40 | Muhammad Yousha Agha | 72 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1068 | [5 empty] | 2026-01-23T10:20:55.823+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1069 | O2-1069 | Task | Task |  | APX Engine VM Deployment Readiness | Resolved! |  |  | 2026-01-23 | 2026-01-23 | 16 | 16 | Arsalan Zafar Khan | 8 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1069 | [5 empty] | 2026-01-23T10:21:46.304+0500 | 2026-01-28T16:32:36.216+0500
O2 | O2-107 | O2-107 | Story | Story |  | Production Release | Resolved! | 2025-10-31 | 2025-10-31 |  |  | 16 | 16 | Ameer Hamza Khan | 40 |  | O2-95 | O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-95 | https://octopusdtlsupport.atlassian.net/browse/O2-107 | [5 empty] | 2025-10-03T19:55:07.915+0500 | 2026-02-11T09:38:57.299+0500
O2 | O2-1070 | O2-1070 | Epic | Epic |  | Process Eng. tasks: working, review and management | In-Progress |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1070 | [5 empty] | 2026-01-23T10:41:35.123+0500 | 2026-02-20T10:42:17.454+0500
O2 | O2-1071 | O2-1071 | Bug Subtask | Bug Subtask |  | User Defined Notifications are not getting received. | Resolved |  |  | 2026-01-26 | 2026-01-26 | 0 | 0 | Faiza Nasir | 2 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1071 | [5 empty] | 2026-01-23T10:41:58.459+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1072 | O2-1072 | Bug Subtask | Bug Subtask |  | Totalizer tag's values are not getting received | Resolved |  |  | 2026-01-26 | 2026-01-26 | 0 | 0 | Mohsin Junaid | 1 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1072 | [5 empty] | 2026-01-23T10:45:48.620+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1073 | O2-1073 | Bug Subtask | Bug Subtask |  | Unable to create timer and counter tags | Resolved |  |  | 2026-01-23 | 2026-01-23 | 0 | 0 | Mohsin Junaid | 1 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1073 | [5 empty] | 2026-01-23T10:47:29.624+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1074 | O2-1074 | Bug Subtask | Bug Subtask |  | Calculated tag latest values are not displaying. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1074 | [5 empty] | 2026-01-23T10:48:20.139+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1075 | O2-1075 | Bug Subtask | Bug Subtask |  | Latest Values Not Populating for Ingestion Format Devices | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1075 | [5 empty] | 2026-01-23T11:02:49.111+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1076 | O2-1076 | Bug Subtask | Bug Subtask |  | Diagnostics Alarm Emails Are Not Being Received | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1076 | [5 empty] | 2026-01-23T11:15:01.000+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1077 | O2-1077 | Bug Subtask | Bug Subtask |  | User Defined Function" and "UserDefined Table" is missing from roles and permissions of ASHGHAL | Resolved | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | Muhammad Usman Javed | 2 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1077 | [5 empty] | 2026-01-23T11:18:49.565+0500 | 2026-02-20T16:51:15.968+0500
O2 | O2-1078 | O2-1078 | Task | Task |  | Sanity Testing + Bug Fixes | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | Zain Munir | 8 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1078 | [5 empty] | 2026-01-23T11:37:04.325+0500 | 2026-01-28T14:06:49.995+0500
O2 | O2-1079 | O2-1079 | Bug Subtask | Bug Subtask |  | Permissions are not working according to the given access for all types of users. showing the actions to be performed while permissions were off for Create and Update, Delete Both Userdefined Function and Userdefined Table | Resolved |  |  | 2026-01-23 | 2026-01-26 | 0 | 0 | Arslan sohail | 2 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1079 | [5 empty] | 2026-01-23T12:18:58.406+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-108 | O2-108 | Epic | Epic |  | OC Faster | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 133.53 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-108 | [5 empty] | 2025-10-06T13:56:58.833+0500 | 2026-02-11T10:59:03.849+0500
O2 | O2-1080 | O2-1080 | Bug Subtask | Bug Subtask |  | AM/PM Missing from Date-Time Filter on Diagnostics Screen | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1080 | [5 empty] | 2026-01-23T12:35:20.951+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1081 | O2-1081 | Bug Subtask | Bug Subtask |  | Csv Bulk Import Success in blobs but no update in file status | Resolved |  |  | 2026-01-23 | 2026-01-23 | 0 | 0 | Hassan Saeed Wattoo | 2 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1081 | [5 empty] | 2026-01-23T12:52:22.383+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1084 | O2-1084 | Bug Subtask | Bug Subtask |  | Tag Count Shows Zero After Scheduling Scan on IoT Flatten and MQTT InHand Devices | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1084 | [5 empty] | 2026-01-26T10:40:10.435+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1085 | O2-1085 | Task | Task |  | Function Apps KeyVault Integration | Resolved! |  |  | 2026-01-22 | 2026-01-22 | 0 | 0 | Faiza Nasir | 2 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1085 | [5 empty] | 2026-01-26T10:55:53.377+0500 | 2026-01-28T15:19:03.580+0500
O2 | O2-1086 | O2-1086 | Task | Task |  | Function Apps Deployments | Resolved! |  |  | 2026-01-22 | 2026-02-10 | 0 | 0 | Faiza Nasir | 11 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1086 | [5 empty] | 2026-01-26T10:56:19.609+0500 | 2026-02-10T11:40:33.867+0500
O2 | O2-1087 | O2-1087 | Task | Task |  | Backfilling Data from production Ashghal Database | Resolved! |  |  | 2026-01-22 | 2026-01-22 | 0 | 0 | Faiza Nasir | 4 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1087 | [5 empty] | 2026-01-26T11:00:07.806+0500 | 2026-01-26T11:00:46.950+0500
O2 | O2-1088 | O2-1088 | Task | Task |  | Bug Fixing | Resolved! |  |  | 2026-01-23 | 2026-01-27 | 0 | 0 | Faiza Nasir | 12 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1088 | [5 empty] | 2026-01-26T11:01:24.255+0500 | 2026-02-09T10:56:57.395+0500
O2 | O2-1089 | O2-1089 | Bug Subtask | Bug Subtask |  | The "Single X,y-Axis Chart" is not available to be selected on Ashghal | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1089 | [5 empty] | 2026-01-26T11:03:11.651+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1090 | O2-1090 | Story | Story |  | Production Release Green | Resolved! | 2026-01-23 | 2026-01-26 |  |  | 48 | 48 | Faiza Nasir | 12 |  | O2-887 | O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-1090 | [5 empty] | 2026-01-26T11:07:50.279+0500 | 2026-02-13T12:17:32.653+0500
O2 | O2-1091 | O2-1091 | Sub-task | Sub-task |  | Production data mapping and bug fixing | Resolved! |  |  | 2026-01-23 | 2026-01-24 | 0 | 0 | Faiza Nasir | 5 |  | O2-1090 | O2-1090 | https://octopusdtlsupport.atlassian.net/browse/O2-1090 | https://octopusdtlsupport.atlassian.net/browse/O2-1091 | [5 empty] | 2026-01-26T11:23:57.720+0500 | 2026-01-26T21:54:48.926+0500
O2 | O2-1092 | O2-1092 | Story | Story |  | User Manual/Guide | Resolved! | 2026-01-26 | 2026-01-26 |  |  | 8 | 8 | Hassan Malik | 8 |  | O2-887 | O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-1092 | [5 empty] | 2026-01-26T11:25:45.278+0500 | 2026-03-03T12:32:39.463+0500
O2 | O2-1093 | O2-1093 | Story | Story |  | Production Deployment | Resolved! | 2026-01-23 | 2026-01-26 |  |  | 16 | 16 | Zain Munir | 13 |  | O2-887 | O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-1093 | [5 empty] | 2026-01-26T11:30:20.793+0500 | 2026-02-26T09:47:01.778+0500
O2 | O2-1094 | O2-1094 | Sub-task | Sub-task |  | OC Process Testing (staging & Production) | Resolved! | 2026-01-22 | 2026-01-26 | 2026-01-23 | 2026-01-26 | 4 | 4 | Mariam Zulfiqar | 4 |  | O2-1090 | O2-1090 | https://octopusdtlsupport.atlassian.net/browse/O2-1090 | https://octopusdtlsupport.atlassian.net/browse/O2-1094 | [5 empty] | 2026-01-26T11:37:01.627+0500 | 2026-01-30T11:17:04.022+0500
O2 | O2-1095 | O2-1095 | Story | Story |  | Development of VFD Dashboard | Resolved! | 2026-01-09 | 2026-01-23 |  |  | 200 | 200 | Muhammad Ahmad Saleem | 116 |  | O2-887 | O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | [5 empty] | 2026-01-26T11:39:09.524+0500 | 2026-02-26T09:44:28.210+0500
O2 | O2-1096 | O2-1096 | Sub-task | Sub-task |  | KT of VFD Dashboard | Resolved! | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1096 | [5 empty] | 2026-01-26T11:40:05.709+0500 | 2026-02-13T12:30:05.325+0500
O2 | O2-1097 | O2-1097 | Sub-task | Sub-task |  | Code Understanding(Research) | Resolved! | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1097 | [5 empty] | 2026-01-26T11:42:39.594+0500 | 2026-02-13T12:30:47.769+0500
O2 | O2-1098 | O2-1098 | Sub-task | Sub-task |  | Code Understanding+ Created New Component | Resolved! | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1098 | [5 empty] | 2026-01-26T11:45:24.006+0500 | 2026-02-13T12:39:56.251+0500
O2 | O2-1099 | O2-1099 | Sub-task | Sub-task |  | Code Understanding+ Started Integrated Dashboard | Resolved! | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1099 | [5 empty] | 2026-01-26T11:47:42.042+0500 | 2026-02-13T13:05:05.339+0500
O2 | O2-11 | O2-11 | Epic | Epic |  | Batch/BPM V6 (SQL) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-11 | [5 empty] | 2025-10-02T14:00:53.132+0500 | 2026-02-11T10:59:53.896+0500
O2 | O2-110 | O2-110 | Story | Story |  | Research/DDS | Resolved! | 2025-09-15 | 2025-09-19 |  |  | 40 | 40 | Mohsin Junaid | 8 |  | O2-108 | O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-110 | [5 empty] | 2025-10-06T13:57:08.182+0500 | 2025-11-24T14:32:01.762+0500
O2 | O2-1100 | O2-1100 | Sub-task | Sub-task |  | Integrated VFD Performance Dashboard | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1100 | [5 empty] | 2026-01-26T11:48:55.748+0500 | 2026-02-13T13:05:23.419+0500
O2 | O2-1101 | O2-1101 | Bug Subtask | Bug Subtask |  | Error is getting displayed with success message right after going to the "Data Selection" screen. only on VPC | Resolved |  |  | 2026-01-27 | 2026-01-27 | 0 | 0 | Ali Qumail | 9 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1101 | [5 empty] | 2026-01-26T11:50:27.643+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1102 | O2-1102 | Sub-task | Sub-task |  | Tested Complete VFD Dashboard + Fix Issues | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1102 | [5 empty] | 2026-01-26T11:51:06.680+0500 | 2026-02-13T11:46:23.898+0500
O2 | O2-1103 | O2-1103 | Sub-task | Sub-task |  | Testing + QA Handover + Fix Issues | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1103 | [5 empty] | 2026-01-26T11:58:13.553+0500 | 2026-02-13T13:05:51.821+0500
O2 | O2-1107 | O2-1107 | Sub-task | Sub-task |  | Support - Process team | Resolved! |  |  | 2026-01-26 | 2026-01-26 | 0 | 0 | Faiza Nasir | 3 |  | O2-1090 | O2-1090 | https://octopusdtlsupport.atlassian.net/browse/O2-1090 | https://octopusdtlsupport.atlassian.net/browse/O2-1107 | [5 empty] | 2026-01-26T21:54:31.066+0500 | 2026-02-03T14:45:12.106+0500
O2 | O2-1108 | O2-1108 | Bug Subtask | Bug Subtask |  | SQL Fail, just pipelines are getting created, No monitoring results are here to show no Data in SQL server. | Resolved |  |  | 2026-01-27 | 2026-01-27 | 0 | 0 | Syed Yousaf Qadri | 2 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1108 | [5 empty] | 2026-01-27T10:31:27.949+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1109 | O2-1109 | Epic | Epic |  | Azure Cost, Reservation, & Subscription Management | In-Progress | 2026-01-01 | 2026-04-30 |  |  | 152 | 152 | Usama Tariq | 14 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | [5 empty] | 2026-01-27T11:38:06.028+0500 | 2026-04-27T11:58:49.159+0500
O2 | O2-111 | O2-111 | Story | Story |  | Development | Resolved! | 2025-09-22 | 2025-10-13 |  |  | 960 | 960 | Muhammad Abbas | 216 |  | O2-108 | O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-111 | [5 empty] | 2025-10-06T13:57:11.244+0500 | 2025-11-24T12:58:59.507+0500
O2 | O2-1110 | O2-1110 | Story | Story |  | Ashghal Release Management / Deployment | Resolved! | 2026-01-27 | 2026-01-28 |  |  | 16 | 16 | Faiza Nasir | 8 |  | O2-887 | O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-1110 | [5 empty] | 2026-01-27T12:53:59.609+0500 | 2026-02-23T09:37:03.220+0500
O2 | O2-1111 | O2-1111 | Story | Story |  | APX: KPIE VM Reservation Exchange | Resolved! | 2026-01-27 | 2026-01-27 |  |  | 4 | 4 | Taimur Zahid | 4 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1111 | [5 empty] | 2026-01-27T12:55:48.289+0500 | 2026-02-16T16:50:05.428+0500
O2 | O2-1113 | O2-1113 | Story | Story |  | Research/URS | Resolved! | 2025-12-31 | 2026-01-06 |  |  | 80 | 80 | Syed Yousaf Qadri | 72 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-1113 | [5 empty] | 2026-01-27T13:02:48.432+0500 | 2026-03-05T12:48:06.315+0500
O2 | O2-1114 | O2-1114 | Bug Subtask | Bug Subtask |  | Invalid data is getting displayed in Site Hierarchy, against SQL pipelines | Resolved |  |  | 2026-01-27 | 2026-01-27 | 0 | 0 | Aiza Hamid | 1 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-1114 | [5 empty] | 2026-01-27T14:55:15.535+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1115 | O2-1115 | Story | Story |  | Staging and Production Database Cleanup | Resolved! | 2026-01-01 | 2026-02-06 |  |  | 80 | 80 | Taimur Zahid | 8 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1115 | [5 empty] | 2026-01-27T15:55:07.220+0500 | 2026-02-16T16:51:57.544+0500
O2 | O2-1116 | O2-1116 | Story | Story |  | VPC: KSA - RFQ Timing and Draft Specifications | Resolved! | 2026-01-27 | 2026-01-29 |  |  | 16 | 16 | Taimur Zahid | 4 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1116 | [5 empty] | 2026-01-27T15:55:13.911+0500 | 2026-02-16T16:55:04.479+0500
O2 | O2-112 | O2-112 | Story | Story |  | SQA | Resolved! | 2025-10-14 | 2025-11-04 |  |  | 152 | 152 | Muhammad Abbas | 338.53 |  | O2-108 | O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | [5 empty] | 2025-10-06T13:57:13.572+0500 | 2025-12-01T15:41:13.609+0500
O2 | O2-1125 | O2-1125 | Story | Story |  | OC-Regression 02/02/2026 | Resolved! | 2026-02-02 | 2026-02-05 |  |  | 32 | 32 | Muhammad Abbas | 133.5 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | [5 empty] | 2026-01-27T16:05:42.573+0500 | 2026-02-25T14:45:25.988+0500
O2 | O2-1127 | O2-1127 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-02-02 | 2026-02-05 | 2026-02-02 | 2026-02-04 | 32 | 32 | kamran khalid | 27 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1127 | [5 empty] | 2026-01-27T16:06:12.192+0500 | 2026-02-13T13:29:44.266+0500
O2 | O2-1128 | O2-1128 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 32 | 32 | Muhammad Abbas | 32 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1128 | [5 empty] | 2026-01-27T16:06:18.663+0500 | 2026-02-13T12:52:57.680+0500
O2 | O2-1129 | O2-1129 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 24 | 24 | Waqar Rasheed | 24 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1129 | [5 empty] | 2026-01-27T16:06:24.427+0500 | 2026-03-09T13:01:46.342+0500
O2 | O2-113 | O2-113 | Story | Story |  | User Manual | Resolved! | 2025-10-14 | 2025-11-04 |  |  | 16 | 16 | Hassan Malik | 40 |  | O2-108 | O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-113 | [5 empty] | 2025-10-06T13:57:21.270+0500 | 2025-11-21T16:22:59.548+0500
O2 | O2-1130 | O2-1130 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 32 | 32 | Zeeshan Sarwar | 32 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1130 | [5 empty] | 2026-01-27T16:06:29.586+0500 | 2026-02-13T13:18:01.606+0500
O2 | O2-1133 | O2-1133 | Story | Story |  | Development | Resolved! | 2026-01-01 | 2026-01-01 |  |  | 8 | 8 | Aiza Hamid | 8 |  | O2-1521 | O2-1521 | https://octopusdtlsupport.atlassian.net/browse/O2-1521 | https://octopusdtlsupport.atlassian.net/browse/O2-1133 | [5 empty] | 2026-01-28T10:43:29.969+0500 | 2026-02-24T09:55:53.481+0500
O2 | O2-1134 | O2-1134 | Story | Story |  | Dev | Resolved! | 2026-02-06 | 2026-02-06 |  |  | 8 | 8 | Aiza Hamid | 8 |  | O2-1523 | O2-1523 | https://octopusdtlsupport.atlassian.net/browse/O2-1523 | https://octopusdtlsupport.atlassian.net/browse/O2-1134 | [5 empty] | 2026-01-28T10:43:52.170+0500 | 2026-02-23T10:31:46.425+0500
O2 | O2-114 | O2-114 | Story | Story |  | Production Release | Resolved! | 2025-11-04 | 2025-11-07 |  |  | 16 | 16 | Mohsin Junaid | 8 |  | O2-108 | O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-108 | https://octopusdtlsupport.atlassian.net/browse/O2-114 | [5 empty] | 2025-10-06T13:58:47.854+0500 | 2025-12-01T15:41:28.815+0500
O2 | O2-1145 | O2-1145 | Story | Story |  | Code Cleanup | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-1145 | [5 empty] | 2026-01-28T10:52:35.577+0500 | 2026-01-28T11:08:30.077+0500
O2 | O2-1157 | O2-1157 | Sub-task | Sub-task |  | Working on pointer logic | Resolved! | 2026-01-05 | 2026-01-07 | 2026-01-05 | 2026-01-06 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-850 | O2-850 | https://octopusdtlsupport.atlassian.net/browse/O2-850 | https://octopusdtlsupport.atlassian.net/browse/O2-1157 | [5 empty] | 2026-01-28T11:09:09.382+0500 | 2026-02-10T11:31:55.554+0500
O2 | O2-1159 | O2-1159 | Sub-task | Sub-task |  | Deduplication | Resolved! |  |  | 2026-01-01 | 2026-01-05 | 0 | 0 | awais akhter | 24 |  | O2-850 | O2-850 | https://octopusdtlsupport.atlassian.net/browse/O2-850 | https://octopusdtlsupport.atlassian.net/browse/O2-1159 | [5 empty] | 2026-01-28T11:10:14.339+0500 | 2026-01-28T11:27:03.054+0500
O2 | O2-1160 | O2-1160 | Sub-task | Sub-task |  | Testing and Vaidation | Resolved! | 2026-01-06 | 2026-02-09 | 2026-01-06 | 2026-01-08 | 24 | 24 | kamran khalid | 32 |  | O2-850 | O2-850 | https://octopusdtlsupport.atlassian.net/browse/O2-850 | https://octopusdtlsupport.atlassian.net/browse/O2-1160 | [5 empty] | 2026-01-28T11:10:45.414+0500 | 2026-02-13T13:30:58.300+0500
O2 | O2-1161 | O2-1161 | Sub-task | Sub-task |  | Key Vaults and Deployments | To Do |  |  | 2026-01-21 | 2026-01-21 | 0 | 0 | Syed Yousaf Qadri | 8 |  | O2-945 | O2-945 | https://octopusdtlsupport.atlassian.net/browse/O2-945 | https://octopusdtlsupport.atlassian.net/browse/O2-1161 | [5 empty] | 2026-01-28T11:38:15.591+0500 | 2026-01-28T11:39:08.565+0500
O2 | O2-1162 | O2-1162 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-1162 | [5 empty] | 2026-01-28T11:39:12.691+0500 | 2026-01-28T11:39:12.816+0500
O2 | O2-1163 | O2-1163 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-02-27 | 2026-03-03 | 2026-01-28 | 2026-02-13 | 24 | 24 | kamran khalid | 34 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1163 | [5 empty] | 2026-01-28T11:41:41.365+0500 | 2026-02-24T10:03:10.606+0500
O2 | O2-1164 | O2-1164 | Task | Task |  | Quality Code Alarms, Trending In OC Deployments and Key Vaults | Resolved! |  |  | 2026-01-23 | 2026-01-23 | 0 | 0 | Syed Yousaf Qadri | 4 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1164 | [5 empty] | 2026-01-28T11:45:08.630+0500 | 2026-02-11T09:39:07.072+0500
O2 | O2-1165 | O2-1165 | Task | Task |  | Testing / Bug Fixing | To Do |  |  | 2026-01-23 | 2026-01-27 | 0 | 0 | Syed Yousaf Qadri | 16 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1165 | [5 empty] | 2026-01-28T11:47:15.276+0500 | 2026-01-28T11:52:51.900+0500
O2 | O2-1167 | O2-1167 | Bug Subtask | Bug Subtask |  | Data Points Not Displayed on Sites Screen While Creating a New Site Until Page Refresh | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1 | 1 | Zain Munir | 0.5 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1167 | [5 empty] | 2026-01-28T11:52:13.885+0500 | 2026-02-16T14:55:34.670+0500
O2 | O2-1168 | O2-1168 | Story | Story |  | Schedule Import OT wide support | Resolved! | 2026-02-02 | 2026-02-10 | 2026-01-28 | 2026-02-04 | 40 | 40 | Hamza Ali | 80 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-1168 | [5 empty] | 2026-01-28T11:53:54.963+0500 | 2026-03-11T12:46:45.047+0500
O2 | O2-1169 | O2-1169 | Sub-task | Sub-task |  | Scripting and Planning for Backward Compatibility | Resolved! |  |  | 2026-01-28 | 2026-02-02 | 24 | 24 | Syed Yousaf Qadri | 24 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1169 | [5 empty] | 2026-01-28T11:56:27.782+0500 | 2026-03-13T11:29:58.206+0500
O2 | O2-1170 | O2-1170 | Sub-task | Sub-task |  | Testing/ Bug Resolving | Resolved! |  |  | 2026-01-30 | 2026-02-06 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1170 | [5 empty] | 2026-01-28T12:02:53.560+0500 | 2026-03-13T11:30:21.128+0500
O2 | O2-1171 | O2-1171 | Story | Story |  | Optimizing Anomaly Results Data Insertion in ADX | Resolved! | 2026-01-19 | 2026-01-21 |  |  | 24 | 24 | Muhammad Zeeshan Aslam | 24 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | [5 empty] | 2026-01-28T12:50:51.266+0500 | 2026-03-04T10:55:33.591+0500
O2 | O2-1172 | O2-1172 | Sub-task | Sub-task |  | Stopped insertion in SQL database in all function apps | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | O2-1171 | O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1172 | [5 empty] | 2026-01-28T12:53:50.902+0500 | 2026-03-04T10:56:06.651+0500
O2 | O2-1173 | O2-1173 | Sub-task | Sub-task |  | Update Read API payload to fetch the data from ADX database tables | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | O2-1171 | O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1173 | [5 empty] | 2026-01-28T12:55:06.429+0500 | 2026-03-04T10:52:31.621+0500
O2 | O2-1174 | O2-1174 | Sub-task | Sub-task |  | Read APi integeration at omniconnect backend | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 4 | 4 | Muhammad Zeeshan Aslam | 4 |  | O2-1171 | O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1174 | [5 empty] | 2026-01-28T12:56:22.433+0500 | 2026-03-04T10:56:13.325+0500
O2 | O2-1175 | O2-1175 | Sub-task | Sub-task |  | Testing the Read API functionality from anomaly detection results module on omniconnect | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8 | 8 | Muhammad Zeeshan Aslam | 4 |  | O2-1171 | O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1171 | https://octopusdtlsupport.atlassian.net/browse/O2-1175 | [5 empty] | 2026-01-28T12:57:24.253+0500 | 2026-03-04T10:56:20.052+0500
O2 | O2-1176 | O2-1176 | Sub-task | Sub-task |  | Research/Discussion for Solution | Resolved! | 2026-01-26 | 2026-01-30 | 2026-01-26 | 2026-01-30 | 40 | 40 | Zain Munir | 29 |  | O2-514 | O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-1176 | [5 empty] | 2026-01-28T13:48:16.302+0500 | 2026-01-30T16:01:09.759+0500
O2 | O2-1177 | O2-1177 | Task | Task |  | Updating function app python stack | Resolved! | 2026-01-23 | 2026-01-27 | 2026-01-23 | 2026-01-27 | 24 | 24 | awais akhter | 24 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1177 | [5 empty] | 2026-01-28T14:36:29.992+0500 | 2026-03-04T10:59:06.159+0500
O2 | O2-1178 | O2-1178 | Bug Subtask | Bug Subtask |  | GPS Tag Live Values Are Not Populating | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1178 | [5 empty] | 2026-01-28T16:43:56.094+0500 | 2026-03-25T11:09:18.017+0500
O2 | O2-1179 | O2-1179 | Story | Story |  | SQA | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 4 |  | O2-887 | O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-887 | https://octopusdtlsupport.atlassian.net/browse/O2-1179 | [5 empty] | 2026-01-28T16:54:42.531+0500 | 2026-02-26T09:46:37.584+0500
O2 | O2-1180 | O2-1180 | Sub-task | Sub-task |  | APX Health Operating System not displaying appropriate values | Resolved! |  |  | 2026-01-28 | 2026-01-28 | 0 | 0 | Faiza Nasir | 4 |  | O2-1179 | O2-1179 | https://octopusdtlsupport.atlassian.net/browse/O2-1179 | https://octopusdtlsupport.atlassian.net/browse/O2-1180 | [5 empty] | 2026-01-28T16:55:30.025+0500 | 2026-01-28T16:58:41.030+0500
O2 | O2-1181 | O2-1181 | Task | Task |  | RMIs Project Management | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 3 |  | O2-798 | O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-1181 | [5 empty] | 2026-01-28T17:01:49.279+0500 | 2026-02-03T14:52:56.961+0500
O2 | O2-1182 | O2-1182 | Sub-task | Sub-task |  | Added details for IP Meeting , Coordination with Hassan Malik | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 3 | 3 | Faiza Nasir | 3 |  | O2-1181 | O2-1181 | https://octopusdtlsupport.atlassian.net/browse/O2-1181 | https://octopusdtlsupport.atlassian.net/browse/O2-1182 | [5 empty] | 2026-01-28T17:02:56.205+0500 | 2026-02-13T17:21:50.853+0500
O2 | O2-1183 | O2-1183 | Story | Story |  | Resource Cleanup and Deletion | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 4 | 4 | Taimur Zahid | 4 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1183 | [5 empty] | 2026-01-28T18:04:27.464+0500 | 2026-01-28T18:06:28.210+0500
O2 | O2-1184 | O2-1184 | Bug Subtask | Bug Subtask |  | Cloned batch job does not display the source (parent) job name after editing | Resolved |  |  | 2026-02-03 | 2026-02-03 | 0 | 0 | Arslan sohail | 2 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1184 | [5 empty] | 2026-01-29T10:15:16.868+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1185 | O2-1185 | Bug Subtask | Bug Subtask |  | CSV download generates an empty file in the Batch Compute module | Resolved |  |  | 2026-02-03 | 2026-02-03 | 0 | 0 | Arslan sohail | 3 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1185 | [5 empty] | 2026-01-29T10:20:06.717+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1186 | O2-1186 | Sub-task | Sub-task |  | QA + Fix Issues | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1186 | [5 empty] | 2026-01-29T10:21:59.369+0500 | 2026-02-13T13:06:11.116+0500
O2 | O2-1188 | O2-1188 | Bug Subtask | Bug Subtask |  | User-defined function appears in Batch Query window but not on User Defined Function page | Resolved | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8 | 8 | Arslan sohail | 8 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1188 | [5 empty] | 2026-01-29T11:07:35.701+0500 | 2026-03-04T16:39:49.672+0500
O2 | O2-1189 | O2-1189 | Bug Subtask | Bug Subtask |  | System does not restrict adding new entities to a user-defined table used by an active batch job | Resolved |  |  | 2026-02-03 | 2026-02-04 | 0 | 0 | Arslan sohail | 11 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1189 | [5 empty] | 2026-01-29T11:22:16.079+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1190 | O2-1190 | Bug Subtask | Bug Subtask |  | Live Values Not Populating for Real-Time Tags Created via Import Site Layout | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1190 | [5 empty] | 2026-01-29T11:25:12.354+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1192 | O2-1192 | Bug Subtask | Bug Subtask |  | In BATCH /BPM Activity output or Batch job result is not showing updated results according to the query after 1 day | Resolved |  |  | 2026-02-06 | 2026-02-06 | 0 | 0 | Arslan sohail | 8 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1192 | [5 empty] | 2026-01-30T09:57:16.234+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1193 | O2-1193 | Sub-task | Sub-task |  | Research on using different Dashboard | Resolved! | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-514 | O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-1193 | [5 empty] | 2026-01-30T10:16:29.359+0500 | 2026-02-13T12:29:21.467+0500
O2 | O2-1194 | O2-1194 | Sub-task | Sub-task |  | Discussion on All PPT Dashboard Files | Resolved! | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-514 | O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-1194 | [5 empty] | 2026-01-30T10:19:41.487+0500 | 2026-02-13T13:06:48.494+0500
O2 | O2-1195 | O2-1195 | Sub-task | Sub-task |  | OC Process Testing | Resolved! | 2026-01-26 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2 | 2 | Mariam Zulfiqar | 2 |  | O2-1110 | O2-1110 | https://octopusdtlsupport.atlassian.net/browse/O2-1110 | https://octopusdtlsupport.atlassian.net/browse/O2-1195 | [5 empty] | 2026-01-30T11:08:43.759+0500 | 2026-01-30T11:10:43.003+0500
O2 | O2-1196 | O2-1196 | Story | Story |  | APX (Perf, WIF, Health) implementation for 10 Ashghal VFP Pumps | Resolved! |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 97 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | [5 empty] | 2026-01-30T11:24:03.713+0500 | 2026-05-04T08:57:57.775+0500
O2 | O2-1197 | O2-1197 | Sub-task | Sub-task |  | APX implementation for 10 pumps | Resolved! | 2026-01-28 | 2026-02-03 | 2026-01-26 | 2026-02-04 | 40 | 40 | Mariam Zulfiqar | 35.5 |  | O2-1196 | O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1197 | [5 empty] | 2026-01-30T11:24:49.529+0500 | 2026-02-04T17:21:20.307+0500
O2 | O2-1198 | O2-1198 | Sub-task | Sub-task |  | Work-around for missing tags | Resolved! | 2026-01-28 | 2026-01-30 | 2026-01-28 | 2026-02-03 | 16 | 16 | Mariam Zulfiqar | 16 |  | O2-1196 | O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1198 | [5 empty] | 2026-01-30T11:25:14.472+0500 | 2026-02-04T17:24:14.026+0500
O2 | O2-1199 | O2-1199 | Epic | Epic |  | test | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1199 | [5 empty] | 2026-01-30T11:56:08.630+0500 | 2026-02-09T16:29:45.063+0500
O2 | O2-1200 | O2-1200 | Epic | Epic |  | 1 | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1200 | [5 empty] | 2026-01-30T11:56:11.351+0500 | 2026-01-30T11:56:11.431+0500
O2 | O2-1201 | O2-1201 | Story | Story |  | a | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1199 | O2-1199 | https://octopusdtlsupport.atlassian.net/browse/O2-1199 | https://octopusdtlsupport.atlassian.net/browse/O2-1201 | [5 empty] | 2026-01-30T11:56:23.459+0500 | 2026-01-30T11:56:23.638+0500
O2 | O2-1202 | O2-1202 | Bug Subtask | Bug Subtask |  | Totalizer Tag Values Not Updating While Calculated Tag Values Are Updating | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1202 | [5 empty] | 2026-01-30T12:09:05.788+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1203 | O2-1203 | Story | Story |  | Baladna Utilities Digitalization Documentation and Diagrams | Resolved! | 2026-01-29 | 2026-01-30 |  |  | 16 | 16 | Taimur Zahid | 16 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-1203 | [5 empty] | 2026-01-30T12:14:28.896+0500 | 2026-02-16T17:23:25.219+0500
O2 | O2-1204 | O2-1204 | Epic | Epic |  | Omni OEE | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1204 | [5 empty] | 2026-01-30T12:16:03.373+0500 | 2026-01-30T12:18:54.929+0500
O2 | O2-1205 | O2-1205 | Story | Story |  | URS | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1204 | O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1205 | [5 empty] | 2026-01-30T12:19:18.464+0500 | 2026-01-30T12:24:40.635+0500
O2 | O2-1206 | O2-1206 | Story | Story |  | DDS | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1204 | O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1206 | [5 empty] | 2026-01-30T12:19:32.793+0500 | 2026-01-30T12:24:47.525+0500
O2 | O2-1207 | O2-1207 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1204 | O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1207 | [5 empty] | 2026-01-30T12:19:42.208+0500 | 2026-01-30T12:24:49.877+0500
O2 | O2-1208 | O2-1208 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1204 | O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1208 | [5 empty] | 2026-01-30T12:19:50.562+0500 | 2026-01-30T12:24:52.389+0500
O2 | O2-1209 | O2-1209 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1204 | O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1209 | [5 empty] | 2026-01-30T12:20:01.429+0500 | 2026-01-30T12:24:56.048+0500
O2 | O2-1210 | O2-1210 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-1204 | O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1204 | https://octopusdtlsupport.atlassian.net/browse/O2-1210 | [5 empty] | 2026-01-30T12:20:08.114+0500 | 2026-01-30T12:24:58.774+0500
O2 | O2-1212 | O2-1212 | Story | Story |  | TLS Update and Data Backfill | Resolved! | 2026-01-29 | 2026-02-03 | 2026-01-28 | 2026-01-30 | 48 | 48 | Ayyan Babar | 25 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1212 | [5 empty] | 2026-01-30T14:18:18.085+0500 | 2026-02-11T09:38:57.299+0500
O2 | O2-1213 | O2-1213 | Story | Story |  | Qatar Central ADX Retention Policy Restoration | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8 | 8 | Mohsin Junaid | 2 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1213 | [5 empty] | 2026-01-30T14:18:45.753+0500 | 2026-01-30T14:21:23.548+0500
O2 | O2-1214 | O2-1214 | Story | Story |  | Demo OmniPetrol Reservation Renewel and Monitoring | Resolved! | 2026-01-30 | 2026-02-06 | 2026-01-30 | 2026-01-30 | 16 | 16 | Usama Tariq | 20 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1214 | [5 empty] | 2026-01-30T14:34:49.080+0500 | 2026-02-23T14:19:48.841+0500
O2 | O2-1219 | O2-1219 | Story | Story |  | Security Architecture and Documentation for Gunvor | Resolved! | 2026-02-02 | 2026-03-31 |  |  | 56 | 56 | Taimur Zahid | 42.5 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | [5 empty] | 2026-02-02T11:00:28.389+0500 | 2026-03-09T15:15:24.181+0500
O2 | O2-1220 | O2-1220 | Sub-task | Sub-task |  | apx demo data preparation using OmniConnect csv bulk import | Resolved! | 2026-01-29 | 2026-01-31 | 2026-01-29 | 2026-02-03 | 32 | 32 | Mohsin Junaid | 32 |  | O2-1196 | O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1220 | [5 empty] | 2026-02-02T11:06:35.728+0500 | 2026-03-13T10:44:33.387+0500
O2 | O2-1221 | O2-1221 | Sub-task | Sub-task |  | apx demo data preparation using OC batch compute and scheduled import | Resolved! |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1196 | O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1221 | [5 empty] | 2026-02-02T11:06:59.728+0500 | 2026-02-11T09:57:29.015+0500
O2 | O2-1222 | O2-1222 | Bug Subtask | Bug Subtask |  | Tag Values Not Updating for MQTT Devices and Not Populating for IoT Devices | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1222 | [5 empty] | 2026-02-02T11:30:54.866+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1223 | O2-1223 | Bug Subtask | Bug Subtask |  | Unknown error is occurring multiple times please look into this | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2 | 2 | Muhammad Ahmad Saleem | 2 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1223 | [5 empty] | 2026-02-02T11:48:16.316+0500 | 2026-02-20T16:53:09.565+0500
O2 | O2-1224 | O2-1224 | Bug Subtask | Bug Subtask |  | New Password Field Validation Message Mismatch on Reset Password Screen | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1 | 1 | Zain Munir | 0.5 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1224 | [5 empty] | 2026-02-02T12:32:30.711+0500 | 2026-02-16T10:02:28.132+0500
O2 | O2-1225 | O2-1225 | Bug Subtask | Bug Subtask |  | GPS Tag Latest Values Not Populating for Any Device on Staging Sub-Site | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1225 | [5 empty] | 2026-02-02T12:49:26.524+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1228 | O2-1228 | Bug Subtask | Bug Subtask |  | Publish Changes Functionality Is Not Working | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1228 | [5 empty] | 2026-02-02T15:24:22.525+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1229 | O2-1229 | Bug Subtask | Bug Subtask |  | Spaces Removed Automatically When Pasting Text into Calculated Tag Condition | Resolved | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2 | 2 | Muhammad Ahmad Saleem | 2 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1229 | [5 empty] | 2026-02-02T15:29:42.479+0500 | 2026-02-20T16:54:37.049+0500
O2 | O2-1230 | O2-1230 | Bug Subtask | Bug Subtask |  | Make Unit Field Optional for Calculated Tags Across the Application | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2 | 2 | Muhammad Ahmad Saleem | 2 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1230 | [5 empty] | 2026-02-02T16:14:53.593+0500 | 2026-02-20T16:52:56.605+0500
O2 | O2-1231 | O2-1231 | Bug Subtask | Bug Subtask |  | Timer Tag Alarms has not been triggered as values was populated | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1231 | [5 empty] | 2026-02-02T16:17:22.255+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-1232 | O2-1232 | Sub-task | Sub-task |  | Dashboard Template Builder UI & API | Resolved! | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 24 | 24 | Zain Munir | 14 |  | O2-515 | O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-1232 | [5 empty] | 2026-02-02T17:27:05.606+0500 | 2026-03-16T10:01:11.112+0500
O2 | O2-1233 | O2-1233 | Bug Subtask | Bug Subtask |  | Unknown API failure occurs when navigating back to Site Listing page from Site home page | Resolved | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2 | 2 | Muhammad Ahmad Saleem | 2 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1233 | [5 empty] | 2026-02-02T20:59:07.645+0500 | 2026-02-20T16:52:17.031+0500
O2 | O2-1234 | O2-1234 | Bug Subtask | Bug Subtask |  | Latest tag values are populated for newly replicated IoT device created via Bulk Device Replication without getting configured | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1234 | [5 empty] | 2026-02-02T21:41:56.762+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1235 | O2-1235 | Bug Subtask | Bug Subtask |  | Internal Server Error Occurs While Creating a Conditional Calculated Tag | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1235 | [5 empty] | 2026-02-03T10:36:57.726+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-1237 | O2-1237 | Bug Subtask | Bug Subtask |  | Write Back MQTT Simulator Is Not Working | Request received |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1237 | [5 empty] | 2026-02-03T10:58:01.258+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-1238 | O2-1238 | Bug Subtask | Bug Subtask |  | Latest Values Not Updating for Parameters on Write Back and Bulk Write Back Screens | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1238 | [5 empty] | 2026-02-03T11:06:40.335+0500 | 2026-04-13T11:24:42.427+0500
O2 | O2-1239 | O2-1239 | Bug Subtask | Bug Subtask |  | Complete list of mapped tags is not displaying against APX health asset as well as it is displaying some output cal tags against performance asset. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1239 | [5 empty] | 2026-02-03T11:10:37.899+0500 | 2026-02-26T10:48:54.828+0500
O2 | O2-1240 | O2-1240 | Bug Subtask | Bug Subtask |  | Unable to fetch data for a specific time period against health asset. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1240 | [5 empty] | 2026-02-03T11:22:03.710+0500 | 2026-02-26T10:52:00.481+0500
O2 | O2-1241 | O2-1241 | Bug Subtask | Bug Subtask |  | Real time tag values for both IOT, MQTT against flatten and inhand are not displaying. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1241 | [5 empty] | 2026-02-03T11:34:42.050+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1242 | O2-1242 | Bug Subtask | Bug Subtask |  | Device Diagnostics Functionality Is Not Working | Request received |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1242 | [5 empty] | 2026-02-03T11:53:35.133+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-1243 | O2-1243 | Bug Subtask | Bug Subtask |  | Anomaly results are not completely exported to excel file. | Resolved | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2 | 2 | Muhammad Ahmad Saleem | 2 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1243 | [5 empty] | 2026-02-03T14:35:40.854+0500 | 2026-02-20T16:54:09.644+0500
O2 | O2-1244 | O2-1244 | Sub-task | Sub-task |  | Need to display Is Global checkbox while editing a formula only in that SI where respective formula is created | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1244 | [5 empty] | 2026-02-03T15:32:11.146+0500 | 2026-02-03T15:54:52.569+0500
O2 | O2-1245 | O2-1245 | Sub-task | Sub-task |  | User created Asset type, Subtype and variable in formula library should be restricted only for specific SI except for global asset type, sub type and variable that are uneditable. | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1245 | [5 empty] | 2026-02-03T15:46:13.792+0500 | 2026-02-03T15:57:37.592+0500
O2 | O2-1246 | O2-1246 | Bug Subtask | Bug Subtask |  | Conditional Calculated Tag Cannot Be Deleted Due to Incorrect Dependency Validation | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1246 | [5 empty] | 2026-02-03T16:27:07.268+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-1247 | O2-1247 | Task | Task |  | Parco Gunvor Demo | Resolved! |  |  | 2026-02-02 | 2026-02-03 | 0 | 0 | Hassan Malik | 12 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-1247 | [5 empty] | 2026-02-03T17:04:50.807+0500 | 2026-02-03T17:05:43.093+0500
O2 | O2-1248 | O2-1248 | Bug Subtask | Bug Subtask |  | Certificate Expiry Notification Received but Email Not Delivered | Resolved | 2026-02-11 | 2026-02-12 | 2026-01-02 | 2026-01-02 | 16 | 16 | Muhammad Usman Javed | 8 |  | O2-1125 | O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1125 | https://octopusdtlsupport.atlassian.net/browse/O2-1248 | [5 empty] | 2026-02-04T11:02:07.418+0500 | 2026-02-23T12:44:01.793+0500
O2 | O2-1254 | O2-1254 | Story | Story |  | Process Eng. tasks: working, review and management | In-Progress |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 442.5 |  | O2-1070 | O2-1070 | https://octopusdtlsupport.atlassian.net/browse/O2-1070 | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | [5 empty] | 2026-02-04T16:14:17.876+0500 | 2026-02-20T11:03:53.888+0500
O2 | O2-1256 | O2-1256 | Sub-task | Sub-task |  | Process pre-sales support, Customer / Management Meetings | Resolved! | 2026-02-02 | 2026-02-27 | 2026-02-02 | 2026-02-27 | 32 | 32 | Mariam Zulfiqar | 31.5 |  | O2-1066 | O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1256 | [5 empty] | 2026-02-04T16:20:40.358+0500 | 2026-03-02T13:02:00.582+0500
O2 | O2-1260 | O2-1260 | Story | Story |  | OCM-Sanity-Testing-Green-09/02/2026 | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 68 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | [5 empty] | 2026-02-06T15:24:57.798+0500 | 2026-03-04T10:03:51.046+0500
O2 | O2-1261 | O2-1261 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 8 | 8 | kamran khalid | 16 |  | O2-1260 | O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1261 | [5 empty] | 2026-02-06T15:25:41.818+0500 | 2026-02-13T13:33:01.849+0500
O2 | O2-1262 | O2-1262 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 8 | 8 | Muhammad Abbas | 16 |  | O2-1260 | O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1262 | [5 empty] | 2026-02-06T15:25:48.207+0500 | 2026-02-13T12:53:25.706+0500
O2 | O2-1263 | O2-1263 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 8 | 8 | Zeeshan Sarwar | 16 |  | O2-1260 | O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1263 | [5 empty] | 2026-02-06T15:25:57.789+0500 | 2026-02-13T13:18:45.798+0500
O2 | O2-1264 | O2-1264 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 8 | 8 | Namra Zahid | 16 |  | O2-1260 | O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1264 | [5 empty] | 2026-02-06T15:26:05.107+0500 | 2026-03-04T10:03:04.241+0500
O2 | O2-1267 | O2-1267 | Sub-task | Sub-task |  | Backend API's Integration | Resolved! | 2026-01-28 | 2026-02-02 | 2026-01-28 | 2026-01-30 | 16 | 16 | Muhammad Ahmad Saleem | 16 |  | O2-514 | O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-1267 | [5 empty] | 2026-02-09T11:29:47.447+0500 | 2026-02-23T13:43:34.963+0500
O2 | O2-1268 | O2-1268 | Bug Subtask | Bug Subtask |  | Failed to Login with microsoft | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1260 | O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1268 | [5 empty] | 2026-02-09T15:40:31.532+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1270 | O2-1270 | Bug Subtask | Bug Subtask |  | MQTT flatten real time tag values are not displaying. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1260 | O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1270 | [5 empty] | 2026-02-10T10:16:29.553+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-1271 | O2-1271 | Bug Subtask | Bug Subtask |  | Models are not creating in user defined anomaly group where as data for specified time duration is displaying. | Resolved | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4 | 4 | Muhammad Zeeshan Aslam | 4 |  | O2-1260 | O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1260 | https://octopusdtlsupport.atlassian.net/browse/O2-1271 | [5 empty] | 2026-02-10T10:28:15.142+0500 | 2026-03-10T15:43:16.556+0500
O2 | O2-1272 | O2-1272 | Task | Task |  | Release management | Resolved! |  |  | 2026-01-05 | 2026-01-27 | 0 | 0 | Ameer Hamza Khan | 96 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1272 | [5 empty] | 2026-02-10T10:59:09.440+0500 | 2026-02-10T11:24:13.765+0500
O2 | O2-1273 | O2-1273 | Task | Task |  | Batch/Bpm/Connectors End to end Testing + Bug Fixes | To Do |  |  | 2026-01-20 | 2026-01-23 | 0 | 0 | ahad omer | 32 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1273 | [5 empty] | 2026-02-10T11:05:20.747+0500 | 2026-03-04T16:30:58.125+0500
O2 | O2-1274 | O2-1274 | Task | Task |  | Batch/BPM/Connectors Deployements | To Do |  |  | 2026-01-27 | 2026-01-27 | 0 | 0 | Arslan sohail | 16 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1274 | [5 empty] | 2026-02-10T11:08:31.148+0500 | 2026-02-10T12:58:04.218+0500
O2 | O2-1275 | O2-1275 | Sub-task | Sub-task |  | Requirement gathering and management | Resolved! | 2026-02-02 | 2026-02-02 | 2026-01-28 | 2026-02-02 | 40 | 40 | Ameer Hamza Khan | 32 |  | O2-514 | O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-1275 | [5 empty] | 2026-02-10T11:25:31.450+0500 | 2026-03-12T14:02:53.988+0500
O2 | O2-1276 | O2-1276 | Story | Story |  | Azure Cost and ASP Utilization Management | Resolved! | 2026-02-06 | 2026-02-13 |  |  | 40 | 40 | Taimur Zahid | 8 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1276 | [5 empty] | 2026-02-10T11:42:56.660+0500 | 2026-02-16T16:57:39.846+0500
O2 | O2-1277 | O2-1277 | Sub-task | Sub-task |  | SFTP OT wide support | Resolved! | 2026-02-02 | 2026-02-03 | 2026-02-02 | 2026-02-03 | 16 | 16 | Hamza Ali | 16 |  | O2-1168 | O2-1168 | https://octopusdtlsupport.atlassian.net/browse/O2-1168 | https://octopusdtlsupport.atlassian.net/browse/O2-1277 | [5 empty] | 2026-02-10T11:45:19.490+0500 | 2026-03-12T13:00:57.408+0500
O2 | O2-1278 | O2-1278 | Sub-task | Sub-task |  | RestApi OT wide support | Resolved! | 2026-02-04 | 2026-02-06 | 2026-02-04 | 2026-02-06 | 24 | 24 | Hamza Ali | 16 |  | O2-1168 | O2-1168 | https://octopusdtlsupport.atlassian.net/browse/O2-1168 | https://octopusdtlsupport.atlassian.net/browse/O2-1278 | [5 empty] | 2026-02-10T11:45:38.073+0500 | 2026-03-12T13:01:22.816+0500
O2 | O2-1279 | O2-1279 | Sub-task | Sub-task |  | SQL OT wide support | Resolved! | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16 | 16 | Hamza Ali | 16 |  | O2-1168 | O2-1168 | https://octopusdtlsupport.atlassian.net/browse/O2-1168 | https://octopusdtlsupport.atlassian.net/browse/O2-1279 | [5 empty] | 2026-02-10T11:45:52.652+0500 | 2026-03-12T13:01:33.758+0500
O2 | O2-1280 | O2-1280 | Sub-task | Sub-task |  | Bug Fixing, Improvements and Tasks | Resolved! | 2026-01-20 | 2026-01-26 | 2026-02-02 | 2026-02-10 | 40 | 40 | ahad omer | 40 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1280 | [5 empty] | 2026-02-10T12:22:54.424+0500 | 2026-03-04T16:44:24.715+0500
O2 | O2-1281 | O2-1281 | Sub-task | Sub-task |  | February Productivity Report - Planning and Feedback | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4 | 4 | Taimur Zahid | 4 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-1281 | [5 empty] | 2026-02-10T14:10:49.015+0500 | 2026-03-05T15:45:40.536+0500
O2 | O2-1283 | O2-1283 | Sub-task | Sub-task |  | Check PS32A values scaling loss issue | Resolved! | 2026-02-10 | 2026-02-12 | 2026-02-10 | 2026-02-12 | 8 | 8 | Mariam Zulfiqar | 8 |  | O2-1196 | O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1283 | [5 empty] | 2026-02-11T09:11:58.046+0500 | 2026-02-20T10:05:25.349+0500
O2 | O2-1284 | O2-1284 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-02-11 | 2026-02-17 | 2026-02-11 | 2026-02-17 | 32 | 32 | Muhammad Abbas | 32 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1284 | [5 empty] | 2026-02-11T09:17:08.692+0500 | 2026-03-09T13:08:53.342+0500
O2 | O2-1285 | O2-1285 | Story | Story |  | Add and implement RMI Planned Field | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-798 | O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-1285 | [5 empty] | 2026-02-11T09:33:09.336+0500 | 2026-02-11T10:53:14.368+0500
O2 | O2-1288 | O2-1288 | Task | Task |  | Add Support for Long-Format Response in Read API (Configurable via Flag) | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Aiza Hamid | 4 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-1288 | [5 empty] | 2026-02-11T14:39:58.467+0500 | 2026-02-11T14:56:41.649+0500
O2 | O2-1293 | O2-1293 | Story | Story |  | Jira Logging and Setup | In-Progress | 2026-02-10 | 2026-03-13 |  |  | 32 | 32 | Taimur Zahid | 43 |  | O2-798 | O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | [5 empty] | 2026-02-11T16:41:10.836+0500 | 2026-02-23T10:20:56.710+0500
O2 | O2-1294 | O2-1294 | Sub-task | Sub-task |  | API Update for Performance Dashboard | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Zain Munir | 5 |  | O2-515 | O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-1294 | [5 empty] | 2026-02-12T11:05:02.068+0500 | 2026-02-12T11:06:38.861+0500
O2 | O2-1295 | O2-1295 | Sub-task | Sub-task |  | Structure for Dashboard from Template Dev OC Frontend | Resolved! | 2026-02-09 | 2026-02-11 | 2026-02-09 | 2026-02-11 | 24 | 24 | Zain Munir | 18 |  | O2-515 | O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-1295 | [5 empty] | 2026-02-12T11:07:15.803+0500 | 2026-03-16T09:58:21.784+0500
O2 | O2-1296 | O2-1296 | Sub-task | Sub-task |  | Read API integration for historic data display on dashboard graphs | Resolved! | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-13 | 16 | 16 | Zain Munir | 12.5 |  | O2-515 | O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-1296 | [5 empty] | 2026-02-12T11:10:14.926+0500 | 2026-03-16T10:25:42.716+0500
O2 | O2-130 | O2-130 | Epic | Epic |  | Read API Enhancement | Resolved! | 2025-11-03 | 2025-12-31 |  |  | 800 | 800 | Aiza Hamid | 400 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-130 | [5 empty] | 2025-10-06T14:19:03.949+0500 | 2026-02-20T15:16:44.893+0500
O2 | O2-1302 | O2-1302 | Epic | Epic |  | OmniOEE (P) | In-Progress |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1302 | [5 empty] | 2026-02-13T09:43:46.340+0500 | 2026-03-12T10:41:30.618+0500
O2 | O2-1303 | O2-1303 | Epic | Epic |  | Heat Exchangers What-If | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | [5 empty] | 2026-02-13T09:51:15.600+0500 | 2026-02-13T11:43:35.421+0500
O2 | O2-1304 | O2-1304 | Story | Story |  | Design What-If Model (P) | Resolved! |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1304 | [5 empty] | 2026-02-13T09:52:27.560+0500 | 2026-02-13T09:54:52.684+0500
O2 | O2-1305 | O2-1305 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1305 | [5 empty] | 2026-02-13T09:52:43.240+0500 | 2026-02-13T09:52:43.350+0500
O2 | O2-1306 | O2-1306 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! | 2026-02-12 | 2026-02-12 |  |  | 16 | 16 | Mariam Zulfiqar | 16 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1306 | [5 empty] | 2026-02-13T09:52:59.212+0500 | 2026-02-18T13:03:36.957+0500
O2 | O2-1307 | O2-1307 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1307 | [5 empty] | 2026-02-13T09:53:26.582+0500 | 2026-02-13T09:53:26.793+0500
O2 | O2-1308 | O2-1308 | Story | Story |  | OC Process Testing (P) | In-Progress |  |  |  |  | 0 | 0 | Faiq Butt | 39 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1308 | [5 empty] | 2026-02-13T09:53:41.804+0500 | 2026-02-23T09:31:17.824+0500
O2 | O2-1309 | O2-1309 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1309 | [5 empty] | 2026-02-13T09:53:46.335+0500 | 2026-02-13T09:53:46.485+0500
O2 | O2-131 | O2-131 | Story | Story |  | Smart Limit Optimizations | Resolved! | 2025-09-29 | 2025-10-01 |  |  | 48 | 48 | Ibrahim Ahmed Qureshi | 16 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-131 | [5 empty] | 2025-10-06T14:24:01.991+0500 | 2025-10-24T16:35:20.180+0500
O2 | O2-1310 | O2-1310 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1310 | [5 empty] | 2026-02-13T09:53:53.507+0500 | 2026-02-13T09:53:53.630+0500
O2 | O2-1311 | O2-1311 | Story | Story |  | Add Training Material (P) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1303 | O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1303 | https://octopusdtlsupport.atlassian.net/browse/O2-1311 | [5 empty] | 2026-02-13T09:54:04.704+0500 | 2026-02-13T09:54:04.807+0500
O2 | O2-1313 | O2-1313 | Bug Subtask | Bug Subtask |  | Model is not getting created for anomaly "User train" group, its showing error. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1313 | [5 empty] | 2026-02-13T11:57:08.640+0500 | 2026-02-13T11:57:46.402+0500
O2 | O2-1314 | O2-1314 | Sub-task | Sub-task |  | real streaming - urs - streaming RnD feasibility on ADX cluster | Resolved! | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-07 | 16 | 16 | Mohsin Junaid | 16 |  | O2-788 | O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-1314 | [5 empty] | 2026-02-13T12:23:02.017+0500 | 2026-02-13T15:46:27.172+0500
O2 | O2-1315 | O2-1315 | Sub-task | Sub-task |  | real streaming - urs - RnD of Function Apps working on streaming | Resolved! | 2026-01-01 | 2026-01-05 | 2026-01-01 | 2026-01-05 | 24 | 24 | Mohsin Junaid | 24 |  | O2-788 | O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-1315 | [5 empty] | 2026-02-13T12:24:59.484+0500 | 2026-02-20T11:08:35.608+0500
O2 | O2-1316 | O2-1316 | Sub-task | Sub-task |  | real streaming - urs - Rnd of Azure Eventhubs related to streaming | Resolved! | 2026-01-08 | 2026-01-09 | 2026-01-08 | 2026-01-09 | 16 | 16 | Mohsin Junaid | 16 |  | O2-788 | O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-1316 | [5 empty] | 2026-02-13T12:25:46.903+0500 | 2026-02-13T15:54:28.671+0500
O2 | O2-1317 | O2-1317 | Sub-task | Sub-task |  | real streaming - urs - Communication between Azure Eventhub - Functions Apps- ADX database | Resolved! | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 24 | 24 | Mohsin Junaid | 24 |  | O2-788 | O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-1317 | [5 empty] | 2026-02-13T12:27:00.861+0500 | 2026-02-13T15:56:01.079+0500
O2 | O2-1318 | O2-1318 | Epic | Epic |  | OmniOEE | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1318 | [5 empty] | 2026-02-13T15:05:04.054+0500 | 2026-02-13T15:08:49.734+0500
O2 | O2-132 | O2-132 | Story | Story |  | Custom Tables JSON Schema Retrieval | Resolved! | 2025-09-22 | 2025-09-26 |  |  | 80 | 80 | Aiza Hamid | 28 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-132 | [5 empty] | 2025-10-06T14:24:09.581+0500 | 2025-10-24T16:35:05.460+0500
O2 | O2-1320 | O2-1320 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-1318 | O2-1318 | https://octopusdtlsupport.atlassian.net/browse/O2-1318 | https://octopusdtlsupport.atlassian.net/browse/O2-1320 | [5 empty] | 2026-02-13T15:05:17.833+0500 | 2026-02-13T15:09:07.950+0500
O2 | O2-1321 | O2-1321 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-1318 | O2-1318 | https://octopusdtlsupport.atlassian.net/browse/O2-1318 | https://octopusdtlsupport.atlassian.net/browse/O2-1321 | [5 empty] | 2026-02-13T15:05:21.468+0500 | 2026-02-13T15:09:26.120+0500
O2 | O2-1322 | O2-1322 | Sub-task | Sub-task |  | cal tags no code - dev - Calculated tags unconditional | In-Progress |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-700 | O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-1322 | [5 empty] | 2026-02-13T15:14:53.521+0500 | 2026-02-17T10:28:29.928+0500
O2 | O2-1323 | O2-1323 | Sub-task | Sub-task |  | cal tags no code - dev - Calculated tags conditional | In-Progress |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-700 | O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-1323 | [5 empty] | 2026-02-13T15:15:25.669+0500 | 2026-02-17T10:28:32.353+0500
O2 | O2-1324 | O2-1324 | Sub-task | Sub-task |  | cal tags no code - dev - Timer Tags | In-Progress |  |  | 2026-02-19 | 2026-02-19 | 0 | 0 | Mohsin Junaid | 8 |  | O2-700 | O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-1324 | [5 empty] | 2026-02-13T15:16:00.237+0500 | 2026-03-12T13:11:32.002+0500
O2 | O2-1325 | O2-1325 | Sub-task | Sub-task |  | cal tags no code - dev - Counter Tags | In-Progress |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-700 | O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-1325 | [5 empty] | 2026-02-13T15:16:46.712+0500 | 2026-02-17T10:28:37.404+0500
O2 | O2-1326 | O2-1326 | Sub-task | Sub-task |  | cal tags no code - dev - Totalizer Tags Real | To Do |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-700 | O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-1326 | [5 empty] | 2026-02-13T15:25:44.799+0500 | 2026-02-13T15:27:18.932+0500
O2 | O2-1327 | O2-1327 | Sub-task | Sub-task |  | cal tags no code - dev - Totalizer Tags Calc | To Do | 2026-02-16 | 2026-02-20 | 2026-02-16 | 2026-02-16 | 8 | 8 | Mohsin Junaid | 8 |  | O2-700 | O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-1327 | [5 empty] | 2026-02-13T15:27:12.500+0500 | 2026-03-12T10:32:49.042+0500
O2 | O2-1328 | O2-1328 | Sub-task | Sub-task |  | real streaming - dev - function app just code testing with reals | Resolved! | 2026-02-04 | 2026-02-06 | 2026-02-04 | 2026-02-24 | 24 | 24 | Mohsin Junaid | 22.5 |  | O2-789 | O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-1328 | [5 empty] | 2026-02-13T15:28:49.021+0500 | 2026-03-18T11:24:55.717+0500
O2 | O2-1329 | O2-1329 | Sub-task | Sub-task |  | real streaming - dev - function app python code optimization of data outgoing | Resolved! | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16 | 16 | Mohsin Junaid | 16 |  | O2-789 | O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-1329 | [5 empty] | 2026-02-13T15:29:56.277+0500 | 2026-02-13T16:31:10.655+0500
O2 | O2-133 | O2-133 | Epic | Epic |  | OC Security - Enhancement and Documentations | Resolved! | 2025-10-06 | 2026-04-03 |  |  | 800 | 800 | Taimur Zahid | 4 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-133 | [5 empty] | 2025-10-06T16:43:33.301+0500 | 2026-02-19T11:40:55.463+0500
O2 | O2-1330 | O2-1330 | Sub-task | Sub-task |  | real streaming - dev - function app just polars implementaion in real tags | Resolved! | 2026-02-11 | 2026-02-13 | 2026-02-11 | 2026-02-23 | 24 | 24 | Mohsin Junaid | 22.5 |  | O2-789 | O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-1330 | [5 empty] | 2026-02-13T15:30:16.065+0500 | 2026-03-18T11:24:36.984+0500
O2 | O2-1331 | O2-1331 | Sub-task | Sub-task |  | real streaming - dev - function app OPC,IOT,MQTT device compatibility of real | Resolved! |  |  | 2026-02-13 | 2026-02-27 | 0 | 0 | Ayyan Babar | 83.5 |  | O2-789 | O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-1331 | [5 empty] | 2026-02-13T15:30:55.382+0500 | 2026-03-25T10:56:18.796+0500
O2 | O2-1332 | O2-1332 | Sub-task | Sub-task |  | real streaming - dev - function app handling datatypes of real tags | Resolved! |  |  | 2026-03-03 | 2026-03-13 | 0 | 0 | Mohsin Junaid | 58.5 |  | O2-789 | O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-1332 | [5 empty] | 2026-02-13T15:31:07.846+0500 | 2026-03-25T10:44:37.246+0500
O2 | O2-1333 | O2-1333 | Sub-task | Sub-task |  | real streaming - dev - real tag implementation automation | Resolved! | 2026-02-02 | 2026-03-11 |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-789 | O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-1333 | [5 empty] | 2026-02-13T15:31:56.765+0500 | 2026-03-25T11:39:47.234+0500
O2 | O2-1334 | O2-1334 | Sub-task | Sub-task |  | real streaming - urs - multiInstance scaling in function apps | Resolved! | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-16 | 16 | 16 | Mohsin Junaid | 16 |  | O2-788 | O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-788 | https://octopusdtlsupport.atlassian.net/browse/O2-1334 | [5 empty] | 2026-02-13T16:00:21.979+0500 | 2026-02-13T16:02:06.949+0500
O2 | O2-1335 | O2-1335 | Story | Story |  | OCM-Sanity-Testing-Blue-02/16/2026 | Resolved! | 2026-02-16 | 2026-02-16 |  |  | 32 | 32 | kamran khalid | 49 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | [5 empty] | 2026-02-13T16:43:18.013+0500 | 2026-02-25T14:45:32.596+0500
O2 | O2-1336 | O2-1336 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 8 | 8 | kamran khalid | 17 |  | O2-1335 | O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1336 | [5 empty] | 2026-02-13T16:44:11.046+0500 | 2026-02-17T17:21:34.103+0500
O2 | O2-1337 | O2-1337 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Waqar Rasheed | 8 |  | O2-1335 | O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1337 | [5 empty] | 2026-02-13T16:44:23.851+0500 | 2026-02-16T16:38:12.654+0500
O2 | O2-1338 | O2-1338 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Zeeshan Sarwar | 8 |  | O2-1335 | O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1338 | [5 empty] | 2026-02-13T16:44:35.182+0500 | 2026-02-16T17:24:50.751+0500
O2 | O2-1339 | O2-1339 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Namra Zahid | 8 |  | O2-1335 | O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1339 | [5 empty] | 2026-02-13T16:44:50.018+0500 | 2026-02-17T11:44:29.586+0500
O2 | O2-134 | O2-134 | Story | Story |  | Key Vault Integration | Resolved! | 2025-10-06 | 2025-11-14 |  |  | 880 | 880 | Taimur Zahid | 308 |  | O2-1460 | O2-1460 | https://octopusdtlsupport.atlassian.net/browse/O2-1460 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | [5 empty] | 2025-10-06T16:43:44.245+0500 | 2026-02-19T11:35:00.813+0500
O2 | O2-1340 | O2-1340 | Epic | Epic |  | OmniAgent - Multi-agent system | Resolved! | 2026-02-02 | 2026-02-28 |  |  | 128 | 128 | Ibrahim Ahmed Qureshi | 44 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | [5 empty] | 2026-02-13T16:59:40.579+0500 | 2026-04-17T10:06:34.803+0500
O2 | O2-1341 | O2-1341 | Story | Story |  | Production Release | Resolved! |  |  |  |  | 8 | 8 | Ibrahim Ahmed Qureshi | 0 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1341 | [5 empty] | 2026-02-13T17:03:56.679+0500 | 2026-04-17T10:06:11.360+0500
O2 | O2-1342 | O2-1342 | Story | Story |  | Development | Resolved! |  |  |  |  | 40 | 40 | Ibrahim Ahmed Qureshi | 162 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | [5 empty] | 2026-02-13T17:04:11.249+0500 | 2026-03-24T14:54:42.352+0500
O2 | O2-1343 | O2-1343 | Story | Story |  | SQA | In-Progress | 2026-03-18 | 2026-03-30 |  |  | 80 | 80 | Muhammad Abbas | 150.5 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | [5 empty] | 2026-02-13T17:04:38.852+0500 | 2026-03-27T11:03:50.911+0500
O2 | O2-1344 | O2-1344 | Story | Story |  | Research | Resolved! | 2026-02-02 | 2026-02-06 |  |  | 40 | 40 | Ibrahim Ahmed Qureshi | 32 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1344 | [5 empty] | 2026-02-13T17:04:48.895+0500 | 2026-02-18T16:30:45.860+0500
O2 | O2-1345 | O2-1345 | Story | Story |  | User Manual | To Do |  |  |  |  | 40 | 40 | Hassan Malik | 0 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1345 | [5 empty] | 2026-02-13T17:05:18.300+0500 | 2026-02-18T16:30:25.635+0500
O2 | O2-1346 | O2-1346 | Sub-task | Sub-task |  | Site Configuration Manager API: Tag Catalog | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Ibrahim Ahmed Qureshi | 8 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1346 | [5 empty] | 2026-02-13T17:06:19.100+0500 | 2026-02-13T17:31:04.563+0500
O2 | O2-1347 | O2-1347 | Sub-task | Sub-task |  | Researching against OpenAI practices | Resolved! | 2026-02-02 | 2026-02-04 | 2026-02-02 | 2026-02-04 | 24 | 24 | Ibrahim Ahmed Qureshi | 24 |  | O2-1344 | O2-1344 | https://octopusdtlsupport.atlassian.net/browse/O2-1344 | https://octopusdtlsupport.atlassian.net/browse/O2-1347 | [5 empty] | 2026-02-13T17:12:03.257+0500 | 2026-02-13T17:17:37.840+0500
O2 | O2-1348 | O2-1348 | Sub-task | Sub-task |  | Researching Documentation | Resolved! | 2026-02-05 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Ibrahim Ahmed Qureshi | 8 |  | O2-1344 | O2-1344 | https://octopusdtlsupport.atlassian.net/browse/O2-1344 | https://octopusdtlsupport.atlassian.net/browse/O2-1348 | [5 empty] | 2026-02-13T17:13:33.957+0500 | 2026-03-10T15:46:42.981+0500
O2 | O2-1349 | O2-1349 | Sub-task | Sub-task |  | Site Configuration Manager API: Custom Table Catalog | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 4 | 4 | Ibrahim Ahmed Qureshi | 4 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1349 | [5 empty] | 2026-02-13T17:23:58.800+0500 | 2026-03-10T15:57:10.545+0500
O2 | O2-135 | O2-135 | Story | Story |  | Defender for Cloud | Resolved! | 2026-02-02 | 2026-02-27 |  |  | 40 | 40 | Taimur Zahid | 32 |  | O2-1459 | O2-1459 | https://octopusdtlsupport.atlassian.net/browse/O2-1459 | https://octopusdtlsupport.atlassian.net/browse/O2-135 | [5 empty] | 2025-10-06T16:43:52.952+0500 | 2026-02-19T15:11:26.330+0500
O2 | O2-1350 | O2-1350 | Sub-task | Sub-task |  | Site Configuration Manager API: Anomaly Catalog | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Ibrahim Ahmed Qureshi | 8 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1350 | [5 empty] | 2026-02-13T17:24:57.035+0500 | 2026-02-13T17:33:24.492+0500
O2 | O2-1352 | O2-1352 | Sub-task | Sub-task |  | Tag Data Agent | Resolved! | 2026-02-10 | 2026-02-12 | 2026-02-10 | 2026-02-10 | 24 | 24 | Ibrahim Ahmed Qureshi | 8 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1352 | [5 empty] | 2026-02-13T17:27:49.952+0500 | 2026-02-13T17:34:15.755+0500
O2 | O2-1353 | O2-1353 | Sub-task | Sub-task |  | Custom Table Agent | Resolved! | 2026-02-10 | 2026-02-12 | 2026-02-11 | 2026-02-11 | 8 | 8 | Ibrahim Ahmed Qureshi | 8 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1353 | [5 empty] | 2026-02-13T17:28:00.118+0500 | 2026-03-10T15:56:32.177+0500
O2 | O2-1354 | O2-1354 | Sub-task | Sub-task |  | Security Documentation | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8 | 8 | Taimur Zahid | 8 |  | O2-1219 | O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1354 | [5 empty] | 2026-02-13T17:32:24.151+0500 | 2026-02-13T17:33:31.258+0500
O2 | O2-1355 | O2-1355 | Sub-task | Sub-task |  | Security Documentation Review and Feedback | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8 | 8 | Taimur Zahid | 8 |  | O2-1219 | O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1355 | [5 empty] | 2026-02-13T17:32:34.553+0500 | 2026-02-13T17:34:29.143+0500
O2 | O2-1356 | O2-1356 | Sub-task | Sub-task |  | Security Architecture | Resolved! | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-05 | 16 | 16 | Taimur Zahid | 16 |  | O2-1219 | O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1356 | [5 empty] | 2026-02-13T17:32:40.719+0500 | 2026-03-03T14:14:21.871+0500
O2 | O2-1357 | O2-1357 | Sub-task | Sub-task |  | Security Architecture Review and Feedback | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 4 | 4 | Taimur Zahid | 4 |  | O2-1219 | O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1357 | [5 empty] | 2026-02-13T17:32:48.130+0500 | 2026-03-05T15:47:22.438+0500
O2 | O2-136 | O2-136 | Story | Story |  | Defender for IoT | To Do | 2026-02-23 | 2026-03-06 |  |  | 80 | 80 | Taimur Zahid | 0 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-136 | [5 empty] | 2025-10-06T16:44:07.060+0500 | 2026-02-20T15:15:29.942+0500
O2 | O2-1362 | O2-1362 | Story | Story |  | Development Web | To Do | 2026-05-04 | 2026-05-08 |  |  | 40 | 40 | Muhammad Ahmad Saleem | 14.5 |  | O2-697 | O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-1362 | [5 empty] | 2026-02-13T17:57:28.320+0500 | 2026-04-08T16:12:30.279+0500
O2 | O2-1363 | O2-1363 | Sub-task | Sub-task |  | cal tags no code - dev web - Dependency Matrix nested calculations | In-Progress |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1362 | O2-1362 | https://octopusdtlsupport.atlassian.net/browse/O2-1362 | https://octopusdtlsupport.atlassian.net/browse/O2-1363 | [5 empty] | 2026-02-13T18:00:10.613+0500 | 2026-02-16T16:09:30.155+0500
O2 | O2-1364 | O2-1364 | Sub-task | Sub-task |  | cal tags no code - dev - counter tag 2nd condition and reset condition | In-Progress |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1362 | O2-1362 | https://octopusdtlsupport.atlassian.net/browse/O2-1362 | https://octopusdtlsupport.atlassian.net/browse/O2-1364 | [5 empty] | 2026-02-13T18:02:49.931+0500 | 2026-02-16T16:09:34.672+0500
O2 | O2-1365 | O2-1365 | Sub-task | Sub-task |  | Counter Tag | To Do | 2026-05-22 | 2026-05-26 |  |  | 24 | 24 | Waqar Rasheed | 0 |  | O2-698 | O2-698 | https://octopusdtlsupport.atlassian.net/browse/O2-698 | https://octopusdtlsupport.atlassian.net/browse/O2-1365 | [5 empty] | 2026-02-13T18:19:35.772+0500 | 2026-04-08T15:21:39.480+0500
O2 | O2-1366 | O2-1366 | Sub-task | Sub-task |  | Timer Tag | To Do | 2026-05-27 | 2026-05-29 |  |  | 24 | 24 | Waqar Rasheed | 0 |  | O2-698 | O2-698 | https://octopusdtlsupport.atlassian.net/browse/O2-698 | https://octopusdtlsupport.atlassian.net/browse/O2-1366 | [5 empty] | 2026-02-13T18:19:43.728+0500 | 2026-04-08T15:25:53.487+0500
O2 | O2-1367 | O2-1367 | Sub-task | Sub-task |  | Calculated Tag | To Do | 2026-05-22 | 2026-05-29 |  |  | 40 | 40 | Muhammad Abbas | 0 |  | O2-698 | O2-698 | https://octopusdtlsupport.atlassian.net/browse/O2-698 | https://octopusdtlsupport.atlassian.net/browse/O2-1367 | [5 empty] | 2026-02-13T18:19:57.660+0500 | 2026-04-08T15:24:01.015+0500
O2 | O2-1368 | O2-1368 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-03-02 | 40 | 40 | Zeeshan Sarwar | 37.5 |  | O2-517 | O2-517 | https://octopusdtlsupport.atlassian.net/browse/O2-517 | https://octopusdtlsupport.atlassian.net/browse/O2-1368 | [5 empty] | 2026-02-13T18:26:45.457+0500 | 2026-03-02T15:29:28.958+0500
O2 | O2-137 | O2-137 | Sub-task | Sub-task |  | Regression testing | Resolved! | 2025-10-07 | 2025-10-14 |  |  | 200 | 200 | Zeeshan Sarwar | 190 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-137 | [5 empty] | 2025-10-07T10:53:46.325+0500 | 2025-10-21T16:14:27.022+0500
O2 | O2-1375 | O2-1375 | Story | Story |  | OmniOEE Pre-URS working (P) | Resolved! | 2026-02-11 | 2026-03-11 |  |  | 80 | 80 | Muhammad Abdul Wasi | 96.5 |  | O2-1302 | O2-1302 | https://octopusdtlsupport.atlassian.net/browse/O2-1302 | https://octopusdtlsupport.atlassian.net/browse/O2-1375 | [5 empty] | 2026-02-16T09:58:30.356+0500 | 2026-03-17T13:17:46.126+0500
O2 | O2-1376 | O2-1376 | Sub-task | Sub-task |  | Optimizing the chart rendering logic in html template | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Zain Munir | 8 |  | O2-515 | O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-1376 | [5 empty] | 2026-02-16T14:32:28.826+0500 | 2026-02-16T15:08:26.279+0500
O2 | O2-1378 | O2-1378 | Story | Story |  | Research | To Do | 2026-01-28 | 2026-01-30 |  |  | 48 | 48 | ahad omer | 48 |  | O2-1318 | O2-1318 | https://octopusdtlsupport.atlassian.net/browse/O2-1318 | https://octopusdtlsupport.atlassian.net/browse/O2-1378 | [5 empty] | 2026-02-16T16:02:50.628+0500 | 2026-03-04T16:36:56.868+0500
O2 | O2-1379 | O2-1379 | Sub-task | Sub-task |  | cal tags no code - dev - prepare data locally for nested tags | To Do | 2026-02-10 | 2026-02-20 | 2026-02-17 | 2026-02-20 | 16 | 16 | Mohsin Junaid | 14.5 |  | O2-1362 | O2-1362 | https://octopusdtlsupport.atlassian.net/browse/O2-1362 | https://octopusdtlsupport.atlassian.net/browse/O2-1379 | [5 empty] | 2026-02-16T16:12:46.255+0500 | 2026-03-18T11:24:14.571+0500
O2 | O2-138 | O2-138 | Sub-task | Sub-task |  | Sanity testing | Resolved! | 2025-10-17 | 2025-10-20 |  |  | 80 | 80 | Muhammad Abbas | 79 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-138 | [5 empty] | 2025-10-07T10:53:49.450+0500 | 2025-10-21T09:44:44.912+0500
O2 | O2-1381 | O2-1381 | Story | Story |  | Research | Resolved! | 2026-02-11 | 2026-02-13 |  |  | 56 | 56 | ahad omer | 72 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | [5 empty] | 2026-02-16T16:17:39.015+0500 | 2026-03-04T15:45:47.231+0500
O2 | O2-1382 | O2-1382 | Task | Task |  | Added Asset Dependency count in Tag Deletion | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 7 | 7 | Muhammad Ahmad Saleem | 7 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-1382 | [5 empty] | 2026-02-16T16:25:15.281+0500 | 2026-02-16T16:27:50.359+0500
O2 | O2-1383 | O2-1383 | Bug Subtask | Bug Subtask |  | Area Count Mismatch for “Subs_Sanity_BL W” Site in OmniAgent Data Analysis | Bug Fixed |  |  | 2026-03-09 | 2026-03-09 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-1335 | O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1335 | https://octopusdtlsupport.atlassian.net/browse/O2-1383 | [5 empty] | 2026-02-16T16:27:00.541+0500 | 2026-04-22T16:01:50.586+0500
O2 | O2-1385 | O2-1385 | Sub-task | Sub-task |  | Reservation Activity | Resolved! | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 8 | 8 | Taimur Zahid | 4 |  | O2-1111 | O2-1111 | https://octopusdtlsupport.atlassian.net/browse/O2-1111 | https://octopusdtlsupport.atlassian.net/browse/O2-1385 | [5 empty] | 2026-02-16T16:46:56.567+0500 | 2026-02-16T16:47:48.058+0500
O2 | O2-1386 | O2-1386 | Sub-task | Sub-task |  | Kick-off Meeting | Resolved! | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Taimur Zahid | 8 |  | O2-1115 | O2-1115 | https://octopusdtlsupport.atlassian.net/browse/O2-1115 | https://octopusdtlsupport.atlassian.net/browse/O2-1386 | [5 empty] | 2026-02-16T16:50:38.987+0500 | 2026-02-16T16:51:48.823+0500
O2 | O2-1387 | O2-1387 | Sub-task | Sub-task |  | Documentation | Resolved! | 2026-01-27 | 2026-01-30 | 2026-01-27 | 2026-01-27 | 16 | 16 | Taimur Zahid | 4 |  | O2-1116 | O2-1116 | https://octopusdtlsupport.atlassian.net/browse/O2-1116 | https://octopusdtlsupport.atlassian.net/browse/O2-1387 | [5 empty] | 2026-02-16T16:53:43.811+0500 | 2026-02-16T16:54:48.655+0500
O2 | O2-1388 | O2-1388 | Sub-task | Sub-task |  | Utilization Management | Resolved! | 2026-02-06 | 2026-02-13 | 2026-02-06 | 2026-02-06 | 8 | 8 | Taimur Zahid | 8 |  | O2-1276 | O2-1276 | https://octopusdtlsupport.atlassian.net/browse/O2-1276 | https://octopusdtlsupport.atlassian.net/browse/O2-1388 | [5 empty] | 2026-02-16T16:56:05.774+0500 | 2026-03-05T15:42:48.838+0500
O2 | O2-1389 | O2-1389 | Sub-task | Sub-task |  | Key Vault Setup and Integration | Resolved! | 2025-10-01 | 2025-11-28 |  |  | 120 | 120 | Taimur Zahid | 88 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-1389 | [5 empty] | 2026-02-16T17:14:38.479+0500 | 2026-02-20T15:15:23.031+0500
O2 | O2-1390 | O2-1390 | Sub-task | Sub-task |  | Documentation | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 8 | 8 | Taimur Zahid | 8 |  | O2-1203 | O2-1203 | https://octopusdtlsupport.atlassian.net/browse/O2-1203 | https://octopusdtlsupport.atlassian.net/browse/O2-1390 | [5 empty] | 2026-02-16T17:21:03.337+0500 | 2026-02-16T17:22:22.587+0500
O2 | O2-1391 | O2-1391 | Sub-task | Sub-task |  | Diagram | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8 | 8 | Taimur Zahid | 8 |  | O2-1203 | O2-1203 | https://octopusdtlsupport.atlassian.net/browse/O2-1203 | https://octopusdtlsupport.atlassian.net/browse/O2-1391 | [5 empty] | 2026-02-16T17:21:04.452+0500 | 2026-02-16T17:23:16.511+0500
O2 | O2-1393 | O2-1393 | Sub-task | Sub-task |  | February 16, 2026 | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Taimur Zahid | 8 |  | O2-1293 | O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1393 | [5 empty] | 2026-02-16T17:30:51.599+0500 | 2026-03-05T15:47:39.338+0500
O2 | O2-1394 | O2-1394 | Sub-task | Sub-task |  | December EPR | Resolved! | 2025-12-01 | 2025-12-31 |  |  | 160 | 160 | Taimur Zahid | 160 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-1394 | [5 empty] | 2026-02-16T17:33:10.100+0500 | 2026-02-16T18:22:35.415+0500
O2 | O2-1395 | O2-1395 | Epic | Epic |  | OC Regression 2026 | In-Progress | 2026-01-01 | 2026-12-31 |  |  | 0 | 0 | Muhammad Abbas | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | [5 empty] | 2026-02-17T10:34:03.001+0500 | 2026-04-09T10:30:10.424+0500
O2 | O2-1396 | O2-1396 | Story | Story |  | Feb-2026 Release | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1396 | [5 empty] | 2026-02-17T10:34:42.418+0500 | 2026-04-30T18:21:48.721+0500
O2 | O2-1397 | O2-1397 | Story | Story |  | QA-Handover | Resolved! | 2026-02-17 | 2026-02-17 |  |  | 5 | 5 | Muhammad Abbas | 5 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | [5 empty] | 2026-02-17T11:02:14.613+0500 | 2026-02-18T12:01:47.471+0500
O2 | O2-1398 | O2-1398 | Sub-task | Sub-task |  | Kamran | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | kamran khalid | 1 |  | O2-1397 | O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1398 | [5 empty] | 2026-02-17T11:04:13.933+0500 | 2026-02-18T11:58:52.632+0500
O2 | O2-1399 | O2-1399 | Sub-task | Sub-task |  | Zeeshan | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | Zeeshan Sarwar | 1 |  | O2-1397 | O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1399 | [5 empty] | 2026-02-17T11:04:37.427+0500 | 2026-02-17T11:32:51.826+0500
O2 | O2-1400 | O2-1400 | Sub-task | Sub-task |  | Abbas | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | Muhammad Abbas | 1 |  | O2-1397 | O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1400 | [5 empty] | 2026-02-17T11:04:54.355+0500 | 2026-02-17T11:30:12.645+0500
O2 | O2-1401 | O2-1401 | Sub-task | Sub-task |  | Namra | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | Namra Zahid | 1 |  | O2-1397 | O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1401 | [5 empty] | 2026-02-17T11:05:09.646+0500 | 2026-02-17T11:31:53.266+0500
O2 | O2-1402 | O2-1402 | Sub-task | Sub-task |  | waqar | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1 | 1 | Waqar Rasheed | 1 |  | O2-1397 | O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1397 | https://octopusdtlsupport.atlassian.net/browse/O2-1402 | [5 empty] | 2026-02-17T11:05:19.323+0500 | 2026-02-17T12:19:11.210+0500
O2 | O2-1404 | O2-1404 | Task | Task |  | Fintech Fuel Demonstration | Resolved! |  |  |  |  | 8 | 8 | Sarmad Sabir | 12.5 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | [5 empty] | 2026-02-17T12:09:42.353+0500 | 2026-03-25T10:29:21.370+0500
O2 | O2-1405 | O2-1405 | Task | Task |  | Digital Log Demonstration | Resolved! |  |  |  |  | 0 | 0 | Sarmad Sabir | 1.5 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-1405 | [5 empty] | 2026-02-17T12:09:56.835+0500 | 2026-03-04T12:56:56.746+0500
O2 | O2-1406 | O2-1406 | Bug Subtask | Bug Subtask |  | Live Values Not Populating on Streaming for IoT and MQTT InHand Devices | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1406 | [5 empty] | 2026-02-17T12:24:12.515+0500 | 2026-03-25T11:09:09.924+0500
O2 | O2-1407 | O2-1407 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-20 | 16 | 16 | Muhammad Abbas | 24 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1407 | [5 empty] | 2026-02-17T12:40:31.257+0500 | 2026-02-24T10:02:24.245+0500
O2 | O2-1408 | O2-1408 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-20 | 16 | 16 | Zeeshan Sarwar | 14.5 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1408 | [5 empty] | 2026-02-17T12:41:16.318+0500 | 2026-02-24T10:02:27.839+0500
O2 | O2-1409 | O2-1409 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-23 | 16 | 16 | Waqar Rasheed | 27.5 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1409 | [5 empty] | 2026-02-17T12:41:25.018+0500 | 2026-02-27T15:13:37.872+0500
O2 | O2-1410 | O2-1410 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-20 | 16 | 16 | Namra Zahid | 24 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1410 | [5 empty] | 2026-02-17T12:41:35.580+0500 | 2026-02-23T09:21:49.267+0500
O2 | O2-1411 | O2-1411 | Bug Subtask | Bug Subtask |  | Get latest values for both IOT and MQTT devices in write back module is not working | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1411 | [5 empty] | 2026-02-17T16:23:04.001+0500 | 2026-03-25T11:09:53.380+0500
O2 | O2-1412 | O2-1412 | Sub-task | Sub-task |  | Code Merging, Staging Deployment & Handover Session | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4 | 4 | Zain Munir | 4 |  | O2-515 | O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-1412 | [5 empty] | 2026-02-18T10:09:17.714+0500 | 2026-03-11T10:46:24.778+0500
O2 | O2-1414 | O2-1414 | Sub-task | Sub-task |  | OC Process Testing (P) | To Do |  |  | 2026-02-11 | 2026-02-20 | 40 | 40 | Faiq Butt | 39 |  | O2-1308 | O2-1308 | https://octopusdtlsupport.atlassian.net/browse/O2-1308 | https://octopusdtlsupport.atlassian.net/browse/O2-1414 | [5 empty] | 2026-02-18T11:52:09.757+0500 | 2026-02-23T09:37:23.762+0500
O2 | O2-1415 | O2-1415 | Sub-task | Sub-task |  | Make Training Material (P) | Resolved! | 2026-01-01 | 2026-01-30 | 2026-01-05 | 2026-01-14 | 80 | 80 | DANIYAL AHMAD | 64 |  | O2-502 | O2-502 | https://octopusdtlsupport.atlassian.net/browse/O2-502 | https://octopusdtlsupport.atlassian.net/browse/O2-1415 | [5 empty] | 2026-02-18T11:54:06.137+0500 | 2026-02-18T13:14:35.828+0500
O2 | O2-1416 | O2-1416 | Sub-task | Sub-task |  | OC Process testing (P) | To Do | 2026-02-06 | 2026-02-10 | 2026-02-06 | 2026-02-10 | 24 | 24 | Faiq Butt | 24 |  | O2-997 | O2-997 | https://octopusdtlsupport.atlassian.net/browse/O2-997 | https://octopusdtlsupport.atlassian.net/browse/O2-1416 | [5 empty] | 2026-02-18T12:09:34.226+0500 | 2026-02-18T12:11:35.919+0500
O2 | O2-1417 | O2-1417 | Sub-task | Sub-task |  | OC Process testing (P) | To Do | 2026-01-19 | 2026-01-21 | 2026-01-21 | 2026-01-23 | 24 | 24 | Danish Rashid | 24 |  | O2-446 | O2-446 | https://octopusdtlsupport.atlassian.net/browse/O2-446 | https://octopusdtlsupport.atlassian.net/browse/O2-1417 | [5 empty] | 2026-02-18T12:14:19.497+0500 | 2026-02-18T12:17:01.972+0500
O2 | O2-1418 | O2-1418 | Sub-task | Sub-task |  | OC Process Testing (P) | To Do | 2026-01-30 | 2026-02-04 | 2026-01-30 | 2026-02-04 | 32 | 32 | Faiq Butt | 32 |  | O2-1010 | O2-1010 | https://octopusdtlsupport.atlassian.net/browse/O2-1010 | https://octopusdtlsupport.atlassian.net/browse/O2-1418 | [5 empty] | 2026-02-18T12:20:52.554+0500 | 2026-02-18T12:22:12.083+0500
O2 | O2-1419 | O2-1419 | Sub-task | Sub-task |  | Tags, Groups, FMEA, Alerts Update | To Do | 2025-12-26 | 2026-01-07 | 2026-01-01 | 2026-01-09 | 64 | 64 | Danish Rashid | 64 |  | O2-529 | O2-529 | https://octopusdtlsupport.atlassian.net/browse/O2-529 | https://octopusdtlsupport.atlassian.net/browse/O2-1419 | [5 empty] | 2026-02-18T12:21:17.186+0500 | 2026-02-18T12:27:07.832+0500
O2 | O2-142 | O2-142 | Sub-task | Sub-task |  | Schedule Pull from Rest API | Resolved! | 2025-10-08 | 2025-10-15 |  |  | 40 | 40 | Muhammad Abbas | 52.55 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-142 | [5 empty] | 2025-10-07T12:06:32.555+0500 | 2026-02-13T12:56:11.721+0500
O2 | O2-1420 | O2-1420 | Sub-task | Sub-task |  | Module Design Induction (P) | Resolved! | 2026-01-15 | 2026-02-28 | 2026-01-15 | 2026-02-26 | 96 | 96 | DANIYAL AHMAD | 94 |  | O2-1029 | O2-1029 | https://octopusdtlsupport.atlassian.net/browse/O2-1029 | https://octopusdtlsupport.atlassian.net/browse/O2-1420 | [5 empty] | 2026-02-18T12:24:10.686+0500 | 2026-03-25T14:41:18.092+0500
O2 | O2-1421 | O2-1421 | Sub-task | Sub-task |  | ADE utilisation on APX by OmniAgent Concept | Resolved! | 2026-01-05 | 2026-01-29 | 2026-01-05 | 2026-01-16 | 64 | 64 | Muhammad Abdul Wasi | 64 |  | O2-1015 | O2-1015 | https://octopusdtlsupport.atlassian.net/browse/O2-1015 | https://octopusdtlsupport.atlassian.net/browse/O2-1421 | [5 empty] | 2026-02-18T12:29:58.276+0500 | 2026-02-18T14:27:52.973+0500
O2 | O2-1422 | O2-1422 | Sub-task | Sub-task |  | Module Design (P) | To Do | 2025-12-15 | 2026-02-10 | 2026-02-02 | 2026-02-11 | 80 | 80 | Danish Rashid | 96 |  | O2-1045 | O2-1045 | https://octopusdtlsupport.atlassian.net/browse/O2-1045 | https://octopusdtlsupport.atlassian.net/browse/O2-1422 | [5 empty] | 2026-02-18T12:30:14.060+0500 | 2026-02-18T13:14:49.653+0500
O2 | O2-1423 | O2-1423 | Sub-task | Sub-task |  | OC Process Testing (P) | Resolved! | 2026-01-27 | 2026-01-29 | 2026-01-27 | 2026-01-29 | 24 | 24 | Faiq Butt | 24 |  | O2-478 | O2-478 | https://octopusdtlsupport.atlassian.net/browse/O2-478 | https://octopusdtlsupport.atlassian.net/browse/O2-1423 | [5 empty] | 2026-02-18T12:35:49.397+0500 | 2026-02-18T12:49:22.843+0500
O2 | O2-1424 | O2-1424 | Sub-task | Sub-task |  | Template Update | To Do | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-03-02 | 16 | 16 | Danish Rashid | 31 |  | O2-530 | O2-530 | https://octopusdtlsupport.atlassian.net/browse/O2-530 | https://octopusdtlsupport.atlassian.net/browse/O2-1424 | [5 empty] | 2026-02-18T12:42:16.296+0500 | 2026-03-05T11:13:47.593+0500
O2 | O2-1425 | O2-1425 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | Resolved! | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-02-12 | 16 | 16 | DANIYAL AHMAD | 16 |  | O2-1306 | O2-1306 | https://octopusdtlsupport.atlassian.net/browse/O2-1306 | https://octopusdtlsupport.atlassian.net/browse/O2-1425 | [5 empty] | 2026-02-18T12:48:23.547+0500 | 2026-03-02T13:08:16.061+0500
O2 | O2-1426 | O2-1426 | Sub-task | Sub-task |  | OC Process testing (P) | To Do | 2026-01-21 | 2026-01-26 | 2026-01-21 | 2026-01-26 | 32 | 32 | Faiq Butt | 32 |  | O2-413 | O2-413 | https://octopusdtlsupport.atlassian.net/browse/O2-413 | https://octopusdtlsupport.atlassian.net/browse/O2-1426 | [5 empty] | 2026-02-18T12:56:15.217+0500 | 2026-02-18T13:08:46.724+0500
O2 | O2-1427 | O2-1427 | Sub-task | Sub-task |  | OC Process testing (P) | To Do | 2026-01-15 | 2026-01-20 | 2026-01-15 | 2026-01-20 | 32 | 32 | Faiq Butt | 32 |  | O2-403 | O2-403 | https://octopusdtlsupport.atlassian.net/browse/O2-403 | https://octopusdtlsupport.atlassian.net/browse/O2-1427 | [5 empty] | 2026-02-18T13:11:51.850+0500 | 2026-02-18T13:15:11.851+0500
O2 | O2-1428 | O2-1428 | Sub-task | Sub-task |  | Asset Design, HB and Expected models (P) | To Do |  |  | 2026-01-01 | 2026-01-02 | 16 | 16 | Faiq Butt | 16 |  | O2-474 | O2-474 | https://octopusdtlsupport.atlassian.net/browse/O2-474 | https://octopusdtlsupport.atlassian.net/browse/O2-1428 | [5 empty] | 2026-02-18T13:29:19.708+0500 | 2026-02-18T13:30:27.292+0500
O2 | O2-1429 | O2-1429 | Bug Subtask | Bug Subtask |  | Data Lake and Enterprise Connector in site status is not getting ready. | Bug Fixed |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1429 | [5 empty] | 2026-02-18T14:24:55.543+0500 | 2026-03-11T14:52:13.249+0500
O2 | O2-1430 | O2-1430 | Sub-task | Sub-task |  | APX Performance Module Training Material | Resolved! | 2025-12-11 | 2026-01-30 | 2026-01-12 | 2026-02-13 | 40 | 40 | Muhammad Abdul Wasi | 56 |  | O2-1016 | O2-1016 | https://octopusdtlsupport.atlassian.net/browse/O2-1016 | https://octopusdtlsupport.atlassian.net/browse/O2-1430 | [5 empty] | 2026-02-18T14:32:52.346+0500 | 2026-02-18T14:47:18.198+0500
O2 | O2-1431 | O2-1431 | Sub-task | Sub-task |  | OC Process testing (P) | Resolved! | 2026-01-19 | 2026-01-23 | 2026-01-19 | 2026-01-23 | 40 | 40 | Muhammad Abdul Wasi | 40 |  | O2-469 | O2-469 | https://octopusdtlsupport.atlassian.net/browse/O2-469 | https://octopusdtlsupport.atlassian.net/browse/O2-1431 | [5 empty] | 2026-02-18T14:50:31.138+0500 | 2026-02-18T14:54:48.498+0500
O2 | O2-1432 | O2-1432 | Sub-task | Sub-task |  | OC Process testing (P) | Resolved! | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-04 | 22 | 22 | Muhammad Abdul Wasi | 22 |  | O2-1023 | O2-1023 | https://octopusdtlsupport.atlassian.net/browse/O2-1023 | https://octopusdtlsupport.atlassian.net/browse/O2-1432 | [5 empty] | 2026-02-18T14:56:34.453+0500 | 2026-03-11T10:46:03.383+0500
O2 | O2-1434 | O2-1434 | Sub-task | Sub-task |  | Green Environment resource creation | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Mohsin Junaid | 8 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1434 | [5 empty] | 2026-02-18T15:06:31.386+0500 | 2026-02-18T15:07:12.458+0500
O2 | O2-1436 | O2-1436 | Sub-task | Sub-task |  | OmniOEE Pre-URS working (P) | Resolved! | 2026-02-11 | 2026-02-23 | 2026-02-11 | 2026-02-19 | 39 | 39 | Muhammad Abdul Wasi | 38.5 |  | O2-1375 | O2-1375 | https://octopusdtlsupport.atlassian.net/browse/O2-1375 | https://octopusdtlsupport.atlassian.net/browse/O2-1436 | [5 empty] | 2026-02-18T15:09:05.102+0500 | 2026-03-12T10:42:28.959+0500
O2 | O2-1437 | O2-1437 | Story | Story |  | Development | Resolved! | 2026-02-16 | 2026-03-04 |  |  | 272 | 272 | Arslan sohail | 210 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | [5 empty] | 2026-02-18T15:46:57.440+0500 | 2026-03-17T14:05:56.183+0500
O2 | O2-1438 | O2-1438 | Story | Story |  | SQA | Resolved! | 2026-03-17 | 2026-04-02 |  |  | 80 | 80 | Muhammad Abbas | 83 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | [5 empty] | 2026-02-18T15:47:06.809+0500 | 2026-04-07T08:46:34.879+0500
O2 | O2-1439 | O2-1439 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1439 | [5 empty] | 2026-02-18T15:47:25.340+0500 | 2026-02-18T15:47:25.472+0500
O2 | O2-1440 | O2-1440 | Story | Story |  | Production Release | Resolved! |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 22.17 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | [5 empty] | 2026-02-18T15:48:07.250+0500 | 2026-04-16T11:27:27.039+0500
O2 | O2-1442 | O2-1442 | Bug Subtask | Bug Subtask |  | SMS Opt-in: Number registration fails with a 403 Forbidden error. | Resolved | 2026-02-18 | 2026-02-19 | 2026-02-19 | 2026-02-20 | 16 | 16 | Ameer Hamza Khan | 16 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1442 | [5 empty] | 2026-02-18T15:50:57.468+0500 | 2026-03-12T14:11:14.202+0500
O2 | O2-1443 | O2-1443 | Bug Subtask | Bug Subtask |  | Real-Time Tag Latest Values Not Showing | Resolved |  |  |  |  | 8 | 8 | Mohsin Junaid | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1443 | [5 empty] | 2026-02-18T15:51:01.004+0500 | 2026-02-20T12:07:06.947+0500
O2 | O2-1445 | O2-1445 | Sub-task | Sub-task |  | real tag streaming - production release - backward compatible (connecting IOThubs with evenhub and function app) so that original flow is not altered and monitor function apps | In-Progress | 2026-01-12 | 2026-01-15 | 2026-03-16 | 2026-03-26 | 16 | 16 | Mohsin Junaid | 43.5 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1445 | [5 empty] | 2026-02-18T16:33:26.146+0500 | 2026-03-30T16:49:08.840+0500
O2 | O2-1446 | O2-1446 | Sub-task | Sub-task |  | February 11, 2026 | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Taimur Zahid | 8 |  | O2-1293 | O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1446 | [5 empty] | 2026-02-18T16:40:41.843+0500 | 2026-02-18T16:41:18.285+0500
O2 | O2-1448 | O2-1448 | Sub-task | Sub-task |  | Green Enviroment Deployment Preparation | To Do | 2026-03-10 | 2026-03-12 |  |  | 16 | 16 | Mohsin Junaid | 0 |  | O2-701 | O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-1448 | [5 empty] | 2026-02-19T09:32:06.014+0500 | 2026-02-19T09:36:33.443+0500
O2 | O2-1449 | O2-1449 | Sub-task | Sub-task |  | test production sites before backward compatibility | To Do | 2026-03-12 | 2026-03-16 |  |  | 16 | 16 | Mohsin Junaid | 0 |  | O2-701 | O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-1449 | [5 empty] | 2026-02-19T09:32:42.383+0500 | 2026-03-03T09:34:36.041+0500
O2 | O2-1450 | O2-1450 | Sub-task | Sub-task |  | making sites backward compatible | To Do | 2026-03-16 | 2026-03-17 |  |  | 16 | 16 | Mohsin Junaid | 0 |  | O2-701 | O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-1450 | [5 empty] | 2026-02-19T09:32:57.839+0500 | 2026-02-19T09:40:03.613+0500
O2 | O2-1451 | O2-1451 | Sub-task | Sub-task |  | deployment on blue | To Do | 2026-03-11 | 2026-03-13 |  |  | 16 | 16 | Mohsin Junaid | 0 |  | O2-701 | O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-701 | https://octopusdtlsupport.atlassian.net/browse/O2-1451 | [5 empty] | 2026-02-19T09:35:04.925+0500 | 2026-03-02T14:14:14.620+0500
O2 | O2-1452 | O2-1452 | Bug Subtask | Bug Subtask |  | Write Back Is FAIL, Values are not getting updated | Resolved | 2026-02-19 | 2026-02-19 | 2026-02-27 | 2026-02-27 | 8 | 8 | Mohsin Junaid | 6.5 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1452 | [5 empty] | 2026-02-19T10:06:14.281+0500 | 2026-03-18T11:25:34.661+0500
O2 | O2-1453 | O2-1453 | Epic | Epic |  | Read API - Handling Deleted Sites | Resolved! | 2026-02-17 | 2026-02-24 |  |  | 56 | 56 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1453 | [5 empty] | 2026-02-19T10:52:33.236+0500 | 2026-03-25T10:39:38.750+0500
O2 | O2-1454 | O2-1454 | Sub-task | Sub-task |  | Impact Analysis | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | ahad omer | 8 |  | O2-1381 | O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1454 | [5 empty] | 2026-02-19T11:13:42.930+0500 | 2026-03-03T19:42:37.150+0500
O2 | O2-1455 | O2-1455 | Sub-task | Sub-task |  | POC Template Variables | Resolved! | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 16 | 16 | ahad omer | 16 |  | O2-1381 | O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1455 | [5 empty] | 2026-02-19T11:14:54.947+0500 | 2026-03-03T19:43:47.557+0500
O2 | O2-1456 | O2-1456 | Sub-task | Sub-task |  | POC Template Variable Mapping | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Arslan sohail | 8 |  | O2-1381 | O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1456 | [5 empty] | 2026-02-19T11:15:56.707+0500 | 2026-03-03T19:45:40.710+0500
O2 | O2-1457 | O2-1457 | Bug Subtask | Bug Subtask |  | Calculated Tag Latest Values Not Populating | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1457 | [5 empty] | 2026-02-19T11:17:32.958+0500 | 2026-02-20T10:21:52.689+0500
O2 | O2-1458 | O2-1458 | Sub-task | Sub-task |  | Impact Analysis | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Arslan sohail | 8 |  | O2-1381 | O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1458 | [5 empty] | 2026-02-19T11:21:31.068+0500 | 2026-03-03T19:46:46.951+0500
O2 | O2-1459 | O2-1459 | Epic | Epic |  | OC Security - Defender for Cloud | To Do |  |  |  |  | 40 | 40 | Taimur Zahid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1459 | [5 empty] | 2026-02-19T11:22:12.724+0500 | 2026-02-19T15:26:15.356+0500
O2 | O2-1460 | O2-1460 | Epic | Epic |  | OC Security - Azure Key Vault Integration | To Do |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1460 | [5 empty] | 2026-02-19T11:26:59.777+0500 | 2026-02-19T11:26:59.863+0500
O2 | O2-1461 | O2-1461 | Epic | Epic |  | OmniChat Integration with OmniAgent | In-Progress | 2026-02-23 | 2026-05-08 |  |  | 208 | 208 | Hamza Ali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | [5 empty] | 2026-02-19T11:45:58.632+0500 | 2026-04-09T14:18:56.213+0500
O2 | O2-1462 | O2-1462 | Story | Story |  | DDS | Resolved! | 2026-02-23 | 2026-02-26 |  |  | 32 | 32 | Hamza Ali | 42 |  | O2-1461 | O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1462 | [5 empty] | 2026-02-19T11:46:35.592+0500 | 2026-04-07T14:39:13.673+0500
O2 | O2-1469 | O2-1469 | Story | Story |  | SQA | In-Progress | 2026-03-17 | 2026-03-24 |  |  | 40 | 40 | Muhammad Abbas | 8 |  | O2-1461 | O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1469 | [5 empty] | 2026-02-19T11:55:45.276+0500 | 2026-05-11T09:47:55.339+0500
O2 | O2-147 | O2-147 | Sub-task | Sub-task |  | Modify Existing API For Connectors | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-147 | [5 empty] | 2025-10-07T13:09:11.433+0500 | 2025-10-08T10:03:22.791+0500
O2 | O2-1470 | O2-1470 | Story | Story |  | User Manual | To Do | 2026-03-17 | 2026-03-24 |  |  | 24 | 24 | Hassan Malik | 0 |  | O2-1461 | O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1470 | [5 empty] | 2026-02-19T11:55:59.625+0500 | 2026-02-20T11:31:00.944+0500
O2 | O2-1471 | O2-1471 | Bug Subtask | Bug Subtask |  | OPC Device Real-Time Tag Latest Values Not Updated but Diagnostics Alarms Auto-Resolved | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1471 | [5 empty] | 2026-02-19T12:28:32.570+0500 | 2026-02-20T10:21:11.794+0500
O2 | O2-1472 | O2-1472 | Story | Story |  | Development | In-Progress | 2026-02-26 | 2026-04-17 |  |  | 264 | 264 | Hamza Ali | 302.5 |  | O2-1461 | O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | [5 empty] | 2026-02-19T12:29:30.162+0500 | 2026-04-09T14:20:42.207+0500
O2 | O2-1473 | O2-1473 | Sub-task | Sub-task |  | RBAC for OmniChat (aligned with OmniConnect/ReadAPI) | To Do | 2026-03-12 | 2026-03-16 |  |  | 24 | 24 | Aiza Hamid | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1473 | [5 empty] | 2026-02-19T12:29:51.890+0500 | 2026-02-20T11:36:34.283+0500
O2 | O2-1474 | O2-1474 | Sub-task | Sub-task |  | OmniChat Database Changes to save OmniAgent Conversation | To Do | 2026-03-09 | 2026-03-12 |  |  | 32 | 32 | Hamza Ali | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1474 | [5 empty] | 2026-02-19T12:34:50.159+0500 | 2026-02-19T12:35:32.669+0500
O2 | O2-1475 | O2-1475 | Sub-task | Sub-task |  | OmniAgent Payload Support for Clean Response - Part B | To Do | 2026-03-12 | 2026-03-13 |  |  | 16 | 16 | Ibrahim Ahmed Qureshi | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1475 | [5 empty] | 2026-02-19T12:53:10.987+0500 | 2026-03-10T15:50:50.372+0500
O2 | O2-1476 | O2-1476 | Sub-task | Sub-task |  | OmniAgent Payload Support for Clean Response - Part A | To Do | 2026-03-02 | 2026-03-04 |  |  | 24 | 24 | Ibrahim Ahmed Qureshi | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1476 | [5 empty] | 2026-02-19T12:53:24.009+0500 | 2026-03-10T15:50:09.495+0500
O2 | O2-1477 | O2-1477 | Bug Subtask | Bug Subtask |  | GPS Tag Latest Values Not Populating | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1477 | [5 empty] | 2026-02-19T12:58:26.634+0500 | 2026-02-20T15:53:20.334+0500
O2 | O2-1478 | O2-1478 | Sub-task | Sub-task |  | OmniAgent Database Changes to save OmniChat Conversations | To Do | 2026-03-05 | 2026-03-10 |  |  | 32 | 32 | Ibrahim Ahmed Qureshi | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1478 | [5 empty] | 2026-02-19T13:02:36.684+0500 | 2026-02-19T13:03:27.074+0500
O2 | O2-1479 | O2-1479 | Sub-task | Sub-task |  | Front-end Development - Chat window modifications | To Do | 2026-02-26 | 2026-02-27 |  |  | 16 | 16 | Aiza Hamid | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1479 | [5 empty] | 2026-02-19T13:11:33.656+0500 | 2026-02-20T12:23:35.145+0500
O2 | O2-148 | O2-148 | Sub-task | Sub-task |  | Modify Existing API For Pipelines | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-148 | [5 empty] | 2025-10-07T13:09:43.295+0500 | 2025-10-08T10:00:37.493+0500
O2 | O2-1480 | O2-1480 | Sub-task | Sub-task |  | Front-end Development - OmniAgent Button | To Do | 2026-03-02 | 2026-03-10 |  |  | 64 | 64 | Aiza Hamid | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1480 | [5 empty] | 2026-02-19T13:11:42.617+0500 | 2026-02-20T12:24:04.113+0500
O2 | O2-1481 | O2-1481 | Sub-task | Sub-task |  | Back-end Integration - Part A | Resolved! | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 16 | 16 | Hamza Ali | 8 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1481 | [5 empty] | 2026-02-19T13:13:30.971+0500 | 2026-03-11T12:22:16.800+0500
O2 | O2-1482 | O2-1482 | Sub-task | Sub-task |  | Back-end Integration - Part B | In-Progress | 2026-03-16 | 2026-03-31 | 2026-03-16 | 2026-03-31 | 72 | 72 | Hamza Ali | 59.5 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1482 | [5 empty] | 2026-02-19T13:13:34.572+0500 | 2026-03-31T15:57:44.969+0500
O2 | O2-1483 | O2-1483 | Bug Subtask | Bug Subtask |  | Loader Keeps Running After Clicking “Execute All and Save Output” and User Cannot Proceed | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1483 | [5 empty] | 2026-02-19T14:22:39.763+0500 | 2026-02-20T12:10:29.971+0500
O2 | O2-1484 | O2-1484 | Bug Subtask | Bug Subtask |  | MQTT values are not getting Updated | Bug Fixed | 2026-02-19 | 2026-02-19 |  |  | 8 | 8 | Ayyan Babar | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1484 | [5 empty] | 2026-02-19T14:43:08.678+0500 | 2026-03-25T10:58:50.404+0500
O2 | O2-1485 | O2-1485 | Sub-task | Sub-task |  | Dev Work | To Do |  |  |  |  | 40 | 40 | Taimur Zahid | 40 |  | O2-577 | O2-577 | https://octopusdtlsupport.atlassian.net/browse/O2-577 | https://octopusdtlsupport.atlassian.net/browse/O2-1485 | [5 empty] | 2026-02-19T15:18:21.866+0500 | 2026-02-19T15:22:05.899+0500
O2 | O2-1486 | O2-1486 | Sub-task | Sub-task |  | Cost Estimation | Resolved! |  |  |  |  | 8 | 8 | Taimur Zahid | 8 |  | O2-254 | O2-254 | https://octopusdtlsupport.atlassian.net/browse/O2-254 | https://octopusdtlsupport.atlassian.net/browse/O2-1486 | [5 empty] | 2026-02-19T15:23:36.007+0500 | 2026-02-19T15:24:27.575+0500
O2 | O2-1487 | O2-1487 | Sub-task | Sub-task |  | Estimation | Resolved! |  |  |  |  | 8 | 8 | Hassan Malik | 8 |  | O2-253 | O2-253 | https://octopusdtlsupport.atlassian.net/browse/O2-253 | https://octopusdtlsupport.atlassian.net/browse/O2-1487 | [5 empty] | 2026-02-19T15:35:15.383+0500 | 2026-02-19T15:35:52.048+0500
O2 | O2-1488 | O2-1488 | Sub-task | Sub-task |  | Authentication and Authorization Tasks | To Do |  |  |  |  | 24 | 24 | Taimur Zahid | 24 |  | O2-165 | O2-165 | https://octopusdtlsupport.atlassian.net/browse/O2-165 | https://octopusdtlsupport.atlassian.net/browse/O2-1488 | [5 empty] | 2026-02-19T15:38:42.272+0500 | 2026-02-19T15:40:04.522+0500
O2 | O2-149 | O2-149 | Sub-task | Sub-task |  | Modify Existing API For Triggers | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-149 | [5 empty] | 2025-10-07T13:09:52.869+0500 | 2025-10-10T10:11:18.374+0500
O2 | O2-1491 | O2-1491 | Sub-task | Sub-task |  | check PS32A invalid tags issue | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 3 | 3 | Mariam Zulfiqar | 3 |  | O2-1196 | O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1491 | [5 empty] | 2026-02-20T10:01:51.595+0500 | 2026-02-20T10:04:28.523+0500
O2 | O2-1492 | O2-1492 | Sub-task | Sub-task |  | Process pre-sales support, Customer / Management Meetings | Resolved! | 2026-01-01 | 2026-01-30 | 2026-01-07 | 2026-01-30 | 32 | 32 | Mariam Zulfiqar | 26 |  | O2-1066 | O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1492 | [5 empty] | 2026-02-20T10:19:53.004+0500 | 2026-02-27T09:26:59.930+0500
O2 | O2-1497 | O2-1497 | Sub-task | Sub-task |  | Production Release | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | Taimur Zahid | 8 |  | O2-982 | O2-982 | https://octopusdtlsupport.atlassian.net/browse/O2-982 | https://octopusdtlsupport.atlassian.net/browse/O2-1497 | [5 empty] | 2026-02-20T11:04:25.868+0500 | 2026-02-20T11:04:58.356+0500
O2 | O2-1498 | O2-1498 | Sub-task | Sub-task |  | Process Eng. tasks: working, review and management | Resolved! | 2026-01-01 | 2026-01-30 | 2026-01-01 | 2026-01-30 | 135 | 135 | Mariam Zulfiqar | 131 |  | O2-1254 | O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1498 | [5 empty] | 2026-02-20T11:05:39.421+0500 | 2026-02-20T11:12:25.593+0500
O2 | O2-1499 | O2-1499 | Sub-task | Sub-task |  | Process Eng. tasks: working, review and management | Resolved! | 2026-02-02 | 2026-02-27 | 2026-02-02 | 2026-02-27 | 114 | 114 | Mariam Zulfiqar | 77 |  | O2-1254 | O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1499 | [5 empty] | 2026-02-20T11:12:49.824+0500 | 2026-03-02T13:05:51.375+0500
O2 | O2-15 | O2-15 | Story | Story |  | Development | Resolved! | 2025-10-06 | 2025-10-17 |  |  | 32 | 32 | ahad omer | 136 |  | O2-9 | O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-15 | [5 empty] | 2025-10-02T14:04:08.701+0500 | 2025-10-29T10:33:05.369+0500
O2 | O2-150 | O2-150 | Sub-task | Sub-task |  | Modify Current SQL Schema | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-150 | [5 empty] | 2025-10-07T13:10:21.772+0500 | 2025-10-10T10:11:33.697+0500
O2 | O2-1500 | O2-1500 | Story | Story |  | Development | Resolved! | 2026-02-17 | 2026-02-23 |  |  | 24 | 24 | Aiza Hamid | 29 |  | O2-1453 | O2-1453 | https://octopusdtlsupport.atlassian.net/browse/O2-1453 | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | [5 empty] | 2026-02-20T11:20:40.453+0500 | 2026-02-24T14:13:22.087+0500
O2 | O2-1501 | O2-1501 | Story | Story |  | SQA | Resolved! | 2026-02-23 | 2026-02-25 |  |  | 16 | 16 | Muhammad Abbas | 16 |  | O2-1453 | O2-1453 | https://octopusdtlsupport.atlassian.net/browse/O2-1453 | https://octopusdtlsupport.atlassian.net/browse/O2-1501 | [5 empty] | 2026-02-20T11:20:49.211+0500 | 2026-02-24T15:06:48.506+0500
O2 | O2-1502 | O2-1502 | Bug Subtask | Bug Subtask |  | Longitude's value is missing whish is mandatory and being used in GPS, Kindly fix completely | Resolved | 2026-02-20 | 2026-02-20 |  |  | 1 | 1 | Mohsin Junaid | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1502 | [5 empty] | 2026-02-20T11:23:56.977+0500 | 2026-03-12T10:28:57.072+0500
O2 | O2-1503 | O2-1503 | Sub-task | Sub-task |  | OmniChat Integration with OmniAgent DDS - Hamza Ali | Resolved! | 2026-02-23 | 2026-02-26 | 2026-02-23 | 2026-02-26 | 16 | 16 | Hamza Ali | 32 |  | O2-1462 | O2-1462 | https://octopusdtlsupport.atlassian.net/browse/O2-1462 | https://octopusdtlsupport.atlassian.net/browse/O2-1503 | [5 empty] | 2026-02-20T11:38:20.569+0500 | 2026-03-11T12:11:41.875+0500
O2 | O2-1504 | O2-1504 | Sub-task | Sub-task |  | OmniChat Integration with OmniAgent DDS - Aiza Hamid | Resolved! | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 16 | 16 | Aiza Hamid | 10 |  | O2-1462 | O2-1462 | https://octopusdtlsupport.atlassian.net/browse/O2-1462 | https://octopusdtlsupport.atlassian.net/browse/O2-1504 | [5 empty] | 2026-02-20T11:38:23.052+0500 | 2026-03-26T15:01:27.148+0500
O2 | O2-1506 | O2-1506 | Story | Story |  | Production Release | To Do | 2026-04-30 | 2026-05-01 |  |  | 32 | 32 | Hamza Ali | 0 |  | O2-1461 | O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | [5 empty] | 2026-02-20T11:51:14.686+0500 | 2026-04-22T00:30:44.713+0500
O2 | O2-1507 | O2-1507 | Sub-task | Sub-task |  | Production Release - Hamza Ali | To Do | 2026-03-25 | 2026-03-26 |  |  | 16 | 16 | Hamza Ali | 0 |  | O2-1506 | O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1507 | [5 empty] | 2026-02-20T11:52:33.192+0500 | 2026-02-20T12:00:35.237+0500
O2 | O2-1508 | O2-1508 | Sub-task | Sub-task |  | Production Release - Aiza Hamid | To Do | 2026-03-25 | 2026-03-26 |  |  | 16 | 16 | Aiza Hamid | 0 |  | O2-1506 | O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1508 | [5 empty] | 2026-02-20T11:52:36.856+0500 | 2026-02-20T15:18:51.754+0500
O2 | O2-1509 | O2-1509 | Sub-task | Sub-task |  | Production Release - Ibrahim A. Qureshi | To Do | 2026-03-25 | 2026-03-26 |  |  | 16 | 16 | Ibrahim Ahmed Qureshi | 0 |  | O2-1506 | O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1509 | [5 empty] | 2026-02-20T11:52:45.194+0500 | 2026-02-20T15:17:02.947+0500
O2 | O2-151 | O2-151 | Epic | Epic |  | OmniAgent Phase 2.0 | Resolved! |  |  | 2026-01-01 | 2026-01-30 | 0 | 0 | awais akhter | 136 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-151 | [5 empty] | 2025-10-07T13:34:05.538+0500 | 2026-02-11T10:58:20.938+0500
O2 | O2-1510 | O2-1510 | Sub-task | Sub-task |  | SQA | In-Progress | 2026-03-17 | 2026-03-23 | 2026-05-11 | 2026-05-11 | 40 | 40 | Namra Zahid | 8 |  | O2-1469 | O2-1469 | https://octopusdtlsupport.atlassian.net/browse/O2-1469 | https://octopusdtlsupport.atlassian.net/browse/O2-1510 | [5 empty] | 2026-02-20T11:53:16.485+0500 | 2026-05-12T14:21:48.035+0500
O2 | O2-1511 | O2-1511 | Sub-task | Sub-task |  | Documentation Task | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1470 | O2-1470 | https://octopusdtlsupport.atlassian.net/browse/O2-1470 | https://octopusdtlsupport.atlassian.net/browse/O2-1511 | [5 empty] | 2026-02-20T11:54:33.660+0500 | 2026-02-20T11:54:33.796+0500
O2 | O2-1512 | O2-1512 | Sub-task | Sub-task |  | Production Release Testing - Abbas | To Do | 2026-03-24 | 2026-03-26 |  |  | 24 | 24 | Muhammad Abbas | 0 |  | O2-1506 | O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1512 | [5 empty] | 2026-02-20T11:55:46.280+0500 | 2026-02-20T15:17:39.777+0500
O2 | O2-1513 | O2-1513 | Sub-task | Sub-task |  | Production Release - Taimur | To Do |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | O2-1506 | O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1513 | [5 empty] | 2026-02-20T12:01:07.451+0500 | 2026-02-20T12:01:34.746+0500
O2 | O2-1514 | O2-1514 | Sub-task | Sub-task |  | Production Release Testing - Kamran | To Do |  |  |  |  | 0 | 0 | kamran khalid | 0 |  | O2-1506 | O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1506 | https://octopusdtlsupport.atlassian.net/browse/O2-1514 | [5 empty] | 2026-02-20T12:01:32.933+0500 | 2026-02-20T12:01:38.475+0500
O2 | O2-1515 | O2-1515 | Bug Subtask | Bug Subtask |  | Unable to create ODBC pipeline system showing error "database not found" | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1515 | [5 empty] | 2026-02-20T12:09:26.997+0500 | 2026-02-20T12:11:42.462+0500
O2 | O2-1516 | O2-1516 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-20 | 8 | 8 | kamran khalid | 7 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1516 | [5 empty] | 2026-02-20T12:10:03.641+0500 | 2026-02-24T10:02:34.874+0500
O2 | O2-1517 | O2-1517 | Sub-task | Sub-task |  | Schema Changes | Resolved! | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1381 | O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1517 | [5 empty] | 2026-02-20T14:28:48.767+0500 | 2026-03-06T11:51:30.071+0500
O2 | O2-1518 | O2-1518 | Sub-task | Sub-task |  | Bpm Batch Engine Impact | Resolved! | 2026-02-13 | 2026-02-16 | 2026-02-13 | 2026-02-16 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1381 | O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1381 | https://octopusdtlsupport.atlassian.net/browse/O2-1518 | [5 empty] | 2026-02-20T14:35:22.770+0500 | 2026-03-06T11:54:22.218+0500
O2 | O2-1519 | O2-1519 | Bug Subtask | Bug Subtask |  | Latest Values not populating for tags created from import site layout | Bug Fixed |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1519 | [5 empty] | 2026-02-20T15:17:45.023+0500 | 2026-03-25T10:58:46.776+0500
O2 | O2-152 | O2-152 | Story | Story |  | Development | Resolved! | 2025-09-22 | 2025-10-03 |  |  | 160 | 160 | Ameer Hamza Khan | 0 |  | O2-151 | O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-152 | [5 empty] | 2025-10-07T13:37:14.492+0500 | 2026-02-11T09:38:57.299+0500
O2 | O2-1521 | O2-1521 | Epic | Epic |  | Read API - Nanosecond Support | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1521 | [5 empty] | 2026-02-20T15:20:44.953+0500 | 2026-02-24T09:55:56.458+0500
O2 | O2-1522 | O2-1522 | Story | Story |  | SQA | Resolved! | 2026-01-15 | 2026-01-15 |  |  | 1 | 1 | Muhammad Abbas | 1 |  | O2-1521 | O2-1521 | https://octopusdtlsupport.atlassian.net/browse/O2-1521 | https://octopusdtlsupport.atlassian.net/browse/O2-1522 | [5 empty] | 2026-02-20T15:22:05.419+0500 | 2026-02-23T12:10:16.626+0500
O2 | O2-1523 | O2-1523 | Epic | Epic |  | Read API - Support for Long and Wide Response Layouts | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1523 | [5 empty] | 2026-02-20T15:23:19.915+0500 | 2026-02-24T10:33:39.103+0500
O2 | O2-1524 | O2-1524 | Story | Story |  | SQA | Resolved! | 2026-02-04 | 2026-02-04 |  |  | 2 | 2 | Muhammad Abbas | 2 |  | O2-1523 | O2-1523 | https://octopusdtlsupport.atlassian.net/browse/O2-1523 | https://octopusdtlsupport.atlassian.net/browse/O2-1524 | [5 empty] | 2026-02-20T15:25:13.649+0500 | 2026-02-23T12:18:30.405+0500
O2 | O2-1525 | O2-1525 | Epic | Epic |  | Read API - Query Optimisation | Resolved! | 2026-01-02 | 2026-01-23 |  |  | 0.17 | 0.17 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1525 | [5 empty] | 2026-02-20T15:25:26.927+0500 | 2026-02-24T10:01:04.933+0500
O2 | O2-1527 | O2-1527 | Sub-task | Sub-task |  | Database Migration and Dashboard Mapping | Resolved! | 2026-01-23 | 2026-01-26 | 2026-01-23 | 2026-01-26 | 16 | 16 | Zain Munir | 13 |  | O2-1093 | O2-1093 | https://octopusdtlsupport.atlassian.net/browse/O2-1093 | https://octopusdtlsupport.atlassian.net/browse/O2-1527 | [5 empty] | 2026-02-20T16:35:39.380+0500 | 2026-02-20T16:38:31.653+0500
O2 | O2-153 | O2-153 | Story | Story |  | SQA | Resolved! | 2025-10-06 | 2025-10-16 |  |  | 72 | 72 | awais akhter | 0 |  | O2-151 | O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-153 | [5 empty] | 2025-10-07T13:37:37.429+0500 | 2025-10-23T10:12:01.518+0500
O2 | O2-1530 | O2-1530 | Sub-task | Sub-task |  | Asghal Deployment /Release Management | Resolved! | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-01-27 | 6 | 6 | Faiza Nasir | 6 |  | O2-1110 | O2-1110 | https://octopusdtlsupport.atlassian.net/browse/O2-1110 | https://octopusdtlsupport.atlassian.net/browse/O2-1530 | [5 empty] | 2026-02-23T09:35:56.938+0500 | 2026-02-23T13:58:52.081+0500
O2 | O2-1532 | O2-1532 | Story | Story |  | Development | Resolved! | 2026-01-02 | 2026-01-16 |  |  | 38 | 38 | Aiza Hamid | 40 |  | O2-1525 | O2-1525 | https://octopusdtlsupport.atlassian.net/browse/O2-1525 | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | [5 empty] | 2026-02-23T10:16:46.514+0500 | 2026-02-24T10:00:54.833+0500
O2 | O2-1533 | O2-1533 | Sub-task | Sub-task |  | Optimized queries for Read API | Resolved! | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8 | 8 | Aiza Hamid | 8 |  | O2-1532 | O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1533 | [5 empty] | 2026-02-23T10:17:39.595+0500 | 2026-02-23T10:22:41.352+0500
O2 | O2-1534 | O2-1534 | Sub-task | Sub-task |  | Updated stored procedure for hierarchies | Resolved! | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8 | 8 | Aiza Hamid | 8 |  | O2-1532 | O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1534 | [5 empty] | 2026-02-23T10:17:50.062+0500 | 2026-02-23T10:23:05.017+0500
O2 | O2-1535 | O2-1535 | Sub-task | Sub-task |  | February 19, 2026 | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 8 | 8 | Taimur Zahid | 6.5 |  | O2-1293 | O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1535 | [5 empty] | 2026-02-23T10:18:04.497+0500 | 2026-03-10T10:58:20.456+0500
O2 | O2-1536 | O2-1536 | Sub-task | Sub-task |  | Updated custom table schemas query to add description | Resolved! | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8 | 8 | Aiza Hamid | 8 |  | O2-1532 | O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1536 | [5 empty] | 2026-02-23T10:18:07.095+0500 | 2026-02-23T10:22:49.573+0500
O2 | O2-1537 | O2-1537 | Sub-task | Sub-task |  | February 20, 2026 | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | Taimur Zahid | 6.5 |  | O2-1293 | O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1537 | [5 empty] | 2026-02-23T10:18:59.330+0500 | 2026-03-10T10:58:34.722+0500
O2 | O2-1538 | O2-1538 | Sub-task | Sub-task |  | February 23, 2026 | Resolved! | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 8 | 8 | Taimur Zahid | 6.5 |  | O2-1293 | O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1538 | [5 empty] | 2026-02-23T10:19:14.184+0500 | 2026-03-10T10:58:49.105+0500
O2 | O2-1539 | O2-1539 | Sub-task | Sub-task |  | Read API ADX Query Optimization | Resolved! | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8 | 8 | Aiza Hamid | 8 |  | O2-1532 | O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1539 | [5 empty] | 2026-02-23T10:19:31.074+0500 | 2026-02-23T10:22:05.209+0500
O2 | O2-154 | O2-154 | Story | Story |  | User Manual | Resolved! | 2025-10-06 | 2025-10-16 |  |  | 176 | 176 | Hassan Malik | 24 |  | O2-151 | O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-154 | [5 empty] | 2025-10-07T13:37:41.341+0500 | 2025-10-24T16:30:15.339+0500
O2 | O2-1540 | O2-1540 | Story | Story |  | SQA | Resolved! | 2026-01-19 | 2026-01-19 |  |  | 1 | 1 | Muhammad Abbas | 1 |  | O2-1525 | O2-1525 | https://octopusdtlsupport.atlassian.net/browse/O2-1525 | https://octopusdtlsupport.atlassian.net/browse/O2-1540 | [5 empty] | 2026-02-23T10:28:10.891+0500 | 2026-02-23T12:15:03.955+0500
O2 | O2-1541 | O2-1541 | Sub-task | Sub-task |  | Added support for wide and long response layouts | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Aiza Hamid | 8 |  | O2-1134 | O2-1134 | https://octopusdtlsupport.atlassian.net/browse/O2-1134 | https://octopusdtlsupport.atlassian.net/browse/O2-1541 | [5 empty] | 2026-02-23T10:30:10.318+0500 | 2026-02-23T10:30:52.535+0500
O2 | O2-1542 | O2-1542 | Sub-task | Sub-task |  | Added support for nanoseconds and micro seconds in timestamps (start and end timestamps) | Resolved! | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8 | 8 | Aiza Hamid | 8 |  | O2-1133 | O2-1133 | https://octopusdtlsupport.atlassian.net/browse/O2-1133 | https://octopusdtlsupport.atlassian.net/browse/O2-1542 | [5 empty] | 2026-02-23T10:32:37.550+0500 | 2026-02-23T10:33:40.981+0500
O2 | O2-1544 | O2-1544 | Sub-task | Sub-task |  | Handling API Calls for Deleted Sites | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Aiza Hamid | 8 |  | O2-1500 | O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1544 | [5 empty] | 2026-02-23T10:36:56.242+0500 | 2026-02-23T10:37:48.906+0500
O2 | O2-1545 | O2-1545 | Epic | Epic |  | APX Health multiple asset configuration | Resolved! | 2026-02-23 | 2026-02-24 |  |  | 16 | 16 | Muhammad Zeeshan Aslam | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1545 | [5 empty] | 2026-02-23T11:18:29.040+0500 | 2026-04-17T10:40:09.262+0500
O2 | O2-1546 | O2-1546 | Task | Task |  | APX Health multiple asset configuration | Resolved! | 2026-02-23 | 2026-02-24 |  |  | 16 | 16 | Muhammad Zeeshan Aslam | 26 |  | O2-1545 | O2-1545 | https://octopusdtlsupport.atlassian.net/browse/O2-1545 | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | [5 empty] | 2026-02-23T11:20:37.295+0500 | 2026-04-17T10:33:27.086+0500
O2 | O2-1547 | O2-1547 | Sub-task | Sub-task |  | APX Health multiple asset configuration (ADE) | Resolved! | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 13 | 13 | Muhammad Zeeshan Aslam | 13 |  | O2-1546 | O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1547 | [5 empty] | 2026-02-23T11:22:29.148+0500 | 2026-03-10T15:46:19.253+0500
O2 | O2-1548 | O2-1548 | Sub-task | Sub-task |  | APX Health multiple asset configuration (APXE) | Resolved! | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 16 | 16 | Arsalan Zafar Khan | 13 |  | O2-1546 | O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1548 | [5 empty] | 2026-02-23T11:22:42.253+0500 | 2026-03-02T09:14:51.342+0500
O2 | O2-155 | O2-155 | Story | Story |  | Production Release | Resolved! | 2025-10-17 | 2025-10-17 |  |  | 8 | 8 | Ameer Hamza Khan | 8 |  | O2-151 | O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-155 | [5 empty] | 2025-10-07T13:37:44.958+0500 | 2025-10-22T11:26:07.465+0500
O2 | O2-1551 | O2-1551 | Sub-task | Sub-task |  | Process Testing (P) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1546 | O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1551 | [5 empty] | 2026-02-23T11:31:57.808+0500 | 2026-02-23T11:31:57.992+0500
O2 | O2-1552 | O2-1552 | Sub-task | Sub-task |  | Process Testing (P) | To Do | 2026-02-23 | 2026-02-25 |  |  | 16 | 16 | Danish Rashid | 0 |  | O2-1546 | O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1546 | https://octopusdtlsupport.atlassian.net/browse/O2-1552 | [5 empty] | 2026-02-23T11:32:23.404+0500 | 2026-02-23T11:45:55.099+0500
O2 | O2-1553 | O2-1553 | Story | Story |  | Read API Support | Resolved! | 2026-01-12 | 2026-02-23 |  |  | 24 | 24 | Aiza Hamid | 16.5 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-1553 | [5 empty] | 2026-02-23T11:50:50.176+0500 | 2026-02-23T14:40:18.571+0500
O2 | O2-1554 | O2-1554 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-24 | 16 | 16 | Muhammad Abbas | 16 |  | O2-1501 | O2-1501 | https://octopusdtlsupport.atlassian.net/browse/O2-1501 | https://octopusdtlsupport.atlassian.net/browse/O2-1554 | [5 empty] | 2026-02-23T11:58:55.690+0500 | 2026-02-24T15:06:37.406+0500
O2 | O2-1555 | O2-1555 | Sub-task | Sub-task |  | Filtering Response for Anomaly Predictors Values | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Aiza Hamid | 2 |  | O2-1553 | O2-1553 | https://octopusdtlsupport.atlassian.net/browse/O2-1553 | https://octopusdtlsupport.atlassian.net/browse/O2-1555 | [5 empty] | 2026-02-23T12:05:17.436+0500 | 2026-02-23T12:06:58.619+0500
O2 | O2-1556 | O2-1556 | Sub-task | Sub-task |  | Updated Correlation Matrix for Anomaly Configuration | Resolved! | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Aiza Hamid | 8 |  | O2-1553 | O2-1553 | https://octopusdtlsupport.atlassian.net/browse/O2-1553 | https://octopusdtlsupport.atlassian.net/browse/O2-1556 | [5 empty] | 2026-02-23T12:05:40.405+0500 | 2026-02-23T12:12:33.755+0500
O2 | O2-1557 | O2-1557 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1 | 1 | Muhammad Abbas | 1 |  | O2-1522 | O2-1522 | https://octopusdtlsupport.atlassian.net/browse/O2-1522 | https://octopusdtlsupport.atlassian.net/browse/O2-1557 | [5 empty] | 2026-02-23T12:08:15.810+0500 | 2026-02-23T12:10:05.256+0500
O2 | O2-1558 | O2-1558 | Sub-task | Sub-task |  | Testing By Abbas | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 1 | 1 | Muhammad Abbas | 1 |  | O2-1540 | O2-1540 | https://octopusdtlsupport.atlassian.net/browse/O2-1540 | https://octopusdtlsupport.atlassian.net/browse/O2-1558 | [5 empty] | 2026-02-23T12:13:37.509+0500 | 2026-02-23T12:14:50.776+0500
O2 | O2-1559 | O2-1559 | Sub-task | Sub-task |  | Testing By Abbas | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2 | 2 | Muhammad Abbas | 2 |  | O2-1524 | O2-1524 | https://octopusdtlsupport.atlassian.net/browse/O2-1524 | https://octopusdtlsupport.atlassian.net/browse/O2-1559 | [5 empty] | 2026-02-23T12:17:06.303+0500 | 2026-02-23T12:18:27.641+0500
O2 | O2-1560 | O2-1560 | Story | Story |  | Production Release | Resolved! | 2026-02-25 | 2026-02-25 |  |  | 8 | 8 | Aiza Hamid | 3 |  | O2-1453 | O2-1453 | https://octopusdtlsupport.atlassian.net/browse/O2-1453 | https://octopusdtlsupport.atlassian.net/browse/O2-1560 | [5 empty] | 2026-02-23T12:19:05.278+0500 | 2026-02-25T12:26:07.124+0500
O2 | O2-1561 | O2-1561 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1 | 1 | Muhammad Abbas | 1 |  | O2-1560 | O2-1560 | https://octopusdtlsupport.atlassian.net/browse/O2-1560 | https://octopusdtlsupport.atlassian.net/browse/O2-1561 | [5 empty] | 2026-02-23T12:19:43.684+0500 | 2026-02-25T12:25:18.581+0500
O2 | O2-1562 | O2-1562 | Story | Story |  | Read API Support | Resolved! | 2026-01-09 | 2026-01-09 |  |  | 8 | 8 | Aiza Hamid | 8 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1562 | [5 empty] | 2026-02-23T12:20:35.305+0500 | 2026-02-23T12:26:00.874+0500
O2 | O2-1563 | O2-1563 | Sub-task | Sub-task |  | Added host in ReadAPI and response format for all tags | Resolved! | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8 | 8 | Aiza Hamid | 8 |  | O2-1562 | O2-1562 | https://octopusdtlsupport.atlassian.net/browse/O2-1562 | https://octopusdtlsupport.atlassian.net/browse/O2-1563 | [5 empty] | 2026-02-23T12:23:47.447+0500 | 2026-02-23T12:25:40.175+0500
O2 | O2-1564 | O2-1564 | Bug Subtask | Bug Subtask |  | Read API is Returning internal server error after latest deployment | Resolved | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 1 | 1 | Aiza Hamid | 1 |  | O2-1500 | O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1564 | [5 empty] | 2026-02-23T12:28:00.374+0500 | 2026-02-24T09:56:59.401+0500
O2 | O2-1565 | O2-1565 | Sub-task | Sub-task |  | Code Refactoring | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Aiza Hamid | 8 |  | O2-1532 | O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1532 | https://octopusdtlsupport.atlassian.net/browse/O2-1565 | [5 empty] | 2026-02-23T12:39:58.772+0500 | 2026-02-24T10:32:00.888+0500
O2 | O2-1566 | O2-1566 | Story | Story |  | Production Release | Resolved! | 2026-01-19 | 2026-01-19 |  |  | 8 | 8 | Aiza Hamid | 1 |  | O2-1525 | O2-1525 | https://octopusdtlsupport.atlassian.net/browse/O2-1525 | https://octopusdtlsupport.atlassian.net/browse/O2-1566 | [5 empty] | 2026-02-23T12:41:36.395+0500 | 2026-02-24T10:09:17.871+0500
O2 | O2-1567 | O2-1567 | Sub-task | Sub-task |  | Dev | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 1 | 1 | Aiza Hamid | 1 |  | O2-1566 | O2-1566 | https://octopusdtlsupport.atlassian.net/browse/O2-1566 | https://octopusdtlsupport.atlassian.net/browse/O2-1567 | [5 empty] | 2026-02-23T12:42:05.293+0500 | 2026-02-24T10:30:33.980+0500
O2 | O2-1568 | O2-1568 | Sub-task | Sub-task |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-1566 | O2-1566 | https://octopusdtlsupport.atlassian.net/browse/O2-1566 | https://octopusdtlsupport.atlassian.net/browse/O2-1568 | [5 empty] | 2026-02-23T12:42:12.483+0500 | 2026-02-23T12:42:21.427+0500
O2 | O2-1569 | O2-1569 | Sub-task | Sub-task |  | Integrated the new required changes | Resolved! | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-848 | O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-1569 | [5 empty] | 2026-02-23T13:22:11.038+0500 | 2026-02-23T13:23:33.272+0500
O2 | O2-1570 | O2-1570 | Sub-task | Sub-task |  | Requirement gathering + Meetings | Resolved! | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-848 | O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-1570 | [5 empty] | 2026-02-23T13:24:58.045+0500 | 2026-02-23T13:25:48.475+0500
O2 | O2-1572 | O2-1572 | Sub-task | Sub-task |  | Testing of API's | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 5 | 5 | Muhammad Ahmad Saleem | 5 |  | O2-514 | O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-514 | https://octopusdtlsupport.atlassian.net/browse/O2-1572 | [5 empty] | 2026-02-23T13:43:59.348+0500 | 2026-02-23T13:45:11.776+0500
O2 | O2-1573 | O2-1573 | Task | Task |  | JIRA Logging Issues Discussion | Resolved! | 2026-02-20 | 2026-02-20 |  |  | 1.67 | 1.67 | Faiza Nasir | 1.67 |  | O2-798 | O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-1573 | [5 empty] | 2026-02-23T13:54:10.157+0500 | 2026-03-13T16:34:55.571+0500
O2 | O2-1574 | O2-1574 | Bug Subtask | Bug Subtask |  | Incase of Real-Stat Read API is returning R-Mapped name instead of user-friendly name even user-friendly parameter is set to true | Resolved |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | O2-1500 | O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1574 | [5 empty] | 2026-02-23T13:55:35.518+0500 | 2026-02-24T14:12:26.929+0500
O2 | O2-1577 | O2-1577 | Bug Subtask | Bug Subtask |  | latest values are not being populated for MQTT (default format) and OPC devices. Real-time and GPS tags on the newly created site | Bug Fixed |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1577 | [5 empty] | 2026-02-23T14:13:15.923+0500 | 2026-03-25T10:58:44.410+0500
O2 | O2-1578 | O2-1578 | Bug Subtask | Bug Subtask |  | IOT,MQTT inhand latest values are not populating | Bug Fixed |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1578 | [5 empty] | 2026-02-23T14:14:27.275+0500 | 2026-03-25T10:58:42.321+0500
O2 | O2-1579 | O2-1579 | Sub-task | Sub-task |  | Reservation task | Resolved! |  |  | 2026-01-30 | 2026-02-10 | 16 | 16 | Usama Tariq | 16 |  | O2-1214 | O2-1214 | https://octopusdtlsupport.atlassian.net/browse/O2-1214 | https://octopusdtlsupport.atlassian.net/browse/O2-1579 | [5 empty] | 2026-02-23T14:17:42.860+0500 | 2026-02-23T14:20:10.981+0500
O2 | O2-158 | O2-158 | Story | Story |  | Edge Metrics Data Retrieval | Resolved! | 2025-09-29 | 2025-10-01 |  |  | 24 | 24 | Aiza Hamid | 40 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-158 | [5 empty] | 2025-10-07T14:45:36.485+0500 | 2025-10-14T11:14:48.763+0500
O2 | O2-1580 | O2-1580 | Sub-task | Sub-task |  | Rservation Renewel | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8 | 8 | Taimur Zahid | 2 |  | O2-1214 | O2-1214 | https://octopusdtlsupport.atlassian.net/browse/O2-1214 | https://octopusdtlsupport.atlassian.net/browse/O2-1580 | [5 empty] | 2026-02-23T14:19:06.116+0500 | 2026-02-23T14:20:05.036+0500
O2 | O2-1581 | O2-1581 | Sub-task | Sub-task |  | Filtering Response for Anomaly Predicted Values | Resolved! | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 8 | 8 | Aiza Hamid | 6.5 |  | O2-1553 | O2-1553 | https://octopusdtlsupport.atlassian.net/browse/O2-1553 | https://octopusdtlsupport.atlassian.net/browse/O2-1581 | [5 empty] | 2026-02-23T14:29:03.744+0500 | 2026-03-25T10:42:41.089+0500
O2 | O2-1582 | O2-1582 | Bug Subtask | Bug Subtask |  | Unauthorized Tag Data Accessible via Read API | Bug Fixed | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 4 | 4 | Aiza Hamid | 4 |  | O2-1500 | O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1582 | [5 empty] | 2026-02-23T15:04:01.445+0500 | 2026-02-24T14:35:05.417+0500
O2 | O2-1583 | O2-1583 | Sub-task | Sub-task |  | Site Configuration Manager: Alarm Catalog | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 4 | 4 | Ibrahim Ahmed Qureshi | 4 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1583 | [5 empty] | 2026-02-23T15:14:56.972+0500 | 2026-03-10T15:55:40.772+0500
O2 | O2-1584 | O2-1584 | Sub-task | Sub-task |  | Anomaly Data Agent | Resolved! | 2026-02-16 | 2026-02-20 | 2026-02-19 | 2026-02-25 | 16 | 16 | Ibrahim Ahmed Qureshi | 12 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1584 | [5 empty] | 2026-02-23T15:15:38.766+0500 | 2026-02-25T15:40:17.928+0500
O2 | O2-1585 | O2-1585 | Sub-task | Sub-task |  | OmniConnect_Revamp_(UI/UX)_ Variation_01 | Resolved! | 2026-01-15 | 2026-01-24 | 2026-01-15 | 2026-01-23 | 56 | 56 | Hassan Wali | 56 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1585 | [5 empty] | 2026-02-23T15:20:15.375+0500 | 2026-03-12T14:01:18.686+0500
O2 | O2-1586 | O2-1586 | Sub-task | Sub-task |  | OmniConnect_ Revamp_(UI/UX)_ Variation_ 02_ Part A | Resolved! | 2026-01-26 | 2026-01-30 | 2026-01-26 | 2026-01-30 | 40 | 40 | Hassan Wali | 40 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1586 | [5 empty] | 2026-02-23T15:20:31.870+0500 | 2026-03-12T13:53:02.496+0500
O2 | O2-1587 | O2-1587 | Sub-task | Sub-task |  | OmniConnect_Revamp_(UI/UX)_ Changes | Resolved! | 2026-02-09 | 2026-02-16 | 2026-02-09 | 2026-02-13 | 40 | 40 | Hassan Wali | 40 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1587 | [5 empty] | 2026-02-23T15:29:51.016+0500 | 2026-03-12T13:50:00.397+0500
O2 | O2-1589 | O2-1589 | Sub-task | Sub-task |  | OmniConnect- Dashboard Design + 4 layers Design (UX/UI) | Resolved! | 2026-02-19 | 2026-02-25 | 2026-02-19 | 2026-02-25 | 32.5 | 32.5 | Hassan Wali | 32.5 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1589 | [5 empty] | 2026-02-24T10:41:25.340+0500 | 2026-03-12T13:52:26.712+0500
O2 | O2-159 | O2-159 | Story | Story |  | Site Hierarchy Retrieval | Resolved! | 2025-09-22 | 2025-09-26 |  |  | 120 | 120 | Aiza Hamid | 28 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-159 | [5 empty] | 2025-10-07T14:46:21.561+0500 | 2025-10-24T16:35:13.578+0500
O2 | O2-1590 | O2-1590 | Sub-task | Sub-task |  | OC template (P) | To Do | 2026-02-23 | 2026-02-26 | 2026-02-23 | 2026-02-25 | 12 | 12 | DANIYAL AHMAD | 12 |  | O2-427 | O2-427 | https://octopusdtlsupport.atlassian.net/browse/O2-427 | https://octopusdtlsupport.atlassian.net/browse/O2-1590 | [5 empty] | 2026-02-24T13:16:03.525+0500 | 2026-03-16T15:00:34.212+0500
O2 | O2-1591 | O2-1591 | Sub-task | Sub-task |  | Process Testing (P) | To Do | 2026-02-25 | 2026-03-03 | 2026-02-25 | 2026-02-27 | 3 | 3 | DANIYAL AHMAD | 6.5 |  | O2-427 | O2-427 | https://octopusdtlsupport.atlassian.net/browse/O2-427 | https://octopusdtlsupport.atlassian.net/browse/O2-1591 | [5 empty] | 2026-02-24T13:16:28.590+0500 | 2026-03-02T14:21:49.350+0500
O2 | O2-1592 | O2-1592 | Sub-task | Sub-task |  | Deleted Sites' Record | Resolved! | 2026-02-17 | 2026-02-18 | 2026-02-17 | 2026-02-18 | 16 | 16 | Ibrahim Ahmed Qureshi | 16 |  | O2-1500 | O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1500 | https://octopusdtlsupport.atlassian.net/browse/O2-1592 | [5 empty] | 2026-02-24T14:09:42.535+0500 | 2026-02-24T14:14:44.018+0500
O2 | O2-1595 | O2-1595 | Epic | Epic |  | Process Team Sales / marketing Tasks | In-Progress |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1595 | [5 empty] | 2026-02-25T10:25:22.226+0500 | 2026-02-25T10:37:06.043+0500
O2 | O2-1596 | O2-1596 | Task | Task |  | Process Team Sales / marketing Tasks | Resolved! | 2026-01-01 | 2026-01-30 |  |  | 16 | 16 | Mariam Zulfiqar | 16 |  | O2-1595 | O2-1595 | https://octopusdtlsupport.atlassian.net/browse/O2-1595 | https://octopusdtlsupport.atlassian.net/browse/O2-1596 | [5 empty] | 2026-02-25T10:25:46.184+0500 | 2026-03-02T13:09:36.142+0500
O2 | O2-1597 | O2-1597 | Sub-task | Sub-task |  | Ashghal demo support | Resolved! | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | 16 | 16 | Danish Rashid | 16 |  | O2-1596 | O2-1596 | https://octopusdtlsupport.atlassian.net/browse/O2-1596 | https://octopusdtlsupport.atlassian.net/browse/O2-1597 | [5 empty] | 2026-02-25T10:27:20.549+0500 | 2026-02-25T10:58:20.327+0500
O2 | O2-1598 | O2-1598 | Task | Task |  | Process Team Sales / marketing Tasks | Resolved! | 2026-02-02 | 2026-02-27 |  |  | 28 | 28 | Mariam Zulfiqar | 28 |  | O2-1595 | O2-1595 | https://octopusdtlsupport.atlassian.net/browse/O2-1595 | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | [5 empty] | 2026-02-25T10:29:13.792+0500 | 2026-03-03T12:42:05.857+0500
O2 | O2-1599 | O2-1599 | Sub-task | Sub-task |  | Marketing team support for APX | Resolved! | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-04 | 8 | 8 | Danish Rashid | 8 |  | O2-1598 | O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1599 | [5 empty] | 2026-02-25T10:30:01.670+0500 | 2026-02-25T10:59:37.621+0500
O2 | O2-16 | O2-16 | Story | Story |  | SQA | Resolved! | 2025-10-20 | 2025-10-23 |  |  | 0 | 0 | Waqar Rasheed | 149 |  | O2-9 | O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | [5 empty] | 2025-10-02T14:08:00.852+0500 | 2025-10-29T11:03:52.620+0500
O2 | O2-1600 | O2-1600 | Sub-task | Sub-task |  | Health module marketing video update | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Danish Rashid | 8 |  | O2-1598 | O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1600 | [5 empty] | 2026-02-25T10:31:02.254+0500 | 2026-02-25T11:00:09.990+0500
O2 | O2-1601 | O2-1601 | Sub-task | Sub-task |  | MPCL ADE demo support | Resolved! | 2026-02-05 | 2026-02-27 | 2026-02-06 | 2026-02-19 | 10 | 10 | DANIYAL AHMAD | 10 |  | O2-1598 | O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1601 | [5 empty] | 2026-02-25T10:32:12.204+0500 | 2026-03-03T12:41:19.847+0500
O2 | O2-1602 | O2-1602 | Sub-task | Sub-task |  | MPCL data review for demo | Resolved! | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-04 | 2 | 2 | Muhammad Abdul Wasi | 2 |  | O2-1598 | O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1598 | https://octopusdtlsupport.atlassian.net/browse/O2-1602 | [5 empty] | 2026-02-25T10:33:47.254+0500 | 2026-02-25T11:11:29.843+0500
O2 | O2-1605 | O2-1605 | Sub-task | Sub-task |  | OC template (P) | Resolved! | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-24 | 8 | 8 | Muhammad Abdul Wasi | 8 |  | O2-473 | O2-473 | https://octopusdtlsupport.atlassian.net/browse/O2-473 | https://octopusdtlsupport.atlassian.net/browse/O2-1605 | [5 empty] | 2026-02-25T11:47:20.993+0500 | 2026-03-11T11:08:24.143+0500
O2 | O2-1606 | O2-1606 | Sub-task | Sub-task |  | Process Testing (P) | Resolved! | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-27 | 2 | 2 | Muhammad Abdul Wasi | 5 |  | O2-473 | O2-473 | https://octopusdtlsupport.atlassian.net/browse/O2-473 | https://octopusdtlsupport.atlassian.net/browse/O2-1606 | [5 empty] | 2026-02-25T11:47:38.140+0500 | 2026-03-11T11:12:15.608+0500
O2 | O2-1607 | O2-1607 | Sub-task | Sub-task |  | February 25,2026 | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1 | 1 | Aiza Hamid | 1 |  | O2-1293 | O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1607 | [5 empty] | 2026-02-25T11:52:34.180+0500 | 2026-02-26T10:40:24.372+0500
O2 | O2-1608 | O2-1608 | Sub-task | Sub-task |  | real-streaming-dev-UnitTesting | In-Progress | 2026-02-25 | 2026-02-28 | 2026-02-25 | 2026-03-13 | 40 | 40 | Mohsin Junaid | 71.5 |  | O2-789 | O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | https://octopusdtlsupport.atlassian.net/browse/O2-1608 | [5 empty] | 2026-02-25T12:24:31.548+0500 | 2026-03-18T11:27:36.056+0500
O2 | O2-1609 | O2-1609 | Sub-task | Sub-task |  | Deployment to Production and Unit Testing | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2 | 2 | Aiza Hamid | 2 |  | O2-1560 | O2-1560 | https://octopusdtlsupport.atlassian.net/browse/O2-1560 | https://octopusdtlsupport.atlassian.net/browse/O2-1609 | [5 empty] | 2026-02-25T12:24:54.142+0500 | 2026-02-26T10:40:55.419+0500
O2 | O2-161 | O2-161 | Story | Story |  | Azure Front Door | To Do | 2026-03-16 | 2026-03-27 |  |  | 80 | 80 | Taimur Zahid | 0 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-161 | [5 empty] | 2025-10-07T14:48:25.159+0500 | 2026-02-20T15:15:08.570+0500
O2 | O2-1610 | O2-1610 | Sub-task | Sub-task |  | Alarm Data Agent | Resolved! | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-03-04 | 16 | 16 | Ibrahim Ahmed Qureshi | 36 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1610 | [5 empty] | 2026-02-25T15:31:43.097+0500 | 2026-03-18T12:29:21.405+0500
O2 | O2-1611 | O2-1611 | Sub-task | Sub-task |  | OC Template (P) | To Do |  |  | 2026-02-24 | 2026-02-25 | 8 | 8 | Faiq Butt | 8 |  | O2-407 | O2-407 | https://octopusdtlsupport.atlassian.net/browse/O2-407 | https://octopusdtlsupport.atlassian.net/browse/O2-1611 | [5 empty] | 2026-02-26T09:09:09.402+0500 | 2026-02-26T10:46:15.336+0500
O2 | O2-1612 | O2-1612 | Sub-task | Sub-task |  | Process testing (P) | To Do |  |  | 2026-02-24 | 2026-02-25 | 2 | 2 | Faiq Butt | 2 |  | O2-407 | O2-407 | https://octopusdtlsupport.atlassian.net/browse/O2-407 | https://octopusdtlsupport.atlassian.net/browse/O2-1612 | [5 empty] | 2026-02-26T09:36:52.811+0500 | 2026-02-26T10:48:03.577+0500
O2 | O2-1615 | O2-1615 | Sub-task | Sub-task |  | OC Template (P)- Faiq | To Do |  |  | 2026-02-25 | 2026-02-26 | 4 | 4 | Faiq Butt | 8 |  | O2-417 | O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-1615 | [5 empty] | 2026-02-26T10:32:57.552+0500 | 2026-03-17T09:54:28.288+0500
O2 | O2-1616 | O2-1616 | Sub-task | Sub-task |  | OC Template (P)- Wasi | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 4 | 4 | Muhammad Abdul Wasi | 4 |  | O2-417 | O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-1616 | [5 empty] | 2026-02-26T10:33:17.405+0500 | 2026-03-16T15:17:31.240+0500
O2 | O2-1617 | O2-1617 | Sub-task | Sub-task |  | Process testing (P)- Faiq | To Do |  |  | 2026-02-26 | 2026-02-27 | 1 | 1 | Faiq Butt | 7 |  | O2-417 | O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-1617 | [5 empty] | 2026-02-26T10:33:50.025+0500 | 2026-03-24T14:58:32.765+0500
O2 | O2-1618 | O2-1618 | Sub-task | Sub-task |  | Process testing (P)- Wasi | Resolved! | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-25 | 1 | 1 | Hassan Malik | 1 |  | O2-417 | O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-417 | https://octopusdtlsupport.atlassian.net/browse/O2-1618 | [5 empty] | 2026-02-26T10:34:02.113+0500 | 2026-03-11T11:10:47.898+0500
O2 | O2-162 | O2-162 | Story | Story |  | Azure Web Application Firewall | To Do | 2026-03-02 | 2026-03-13 |  |  | 80 | 80 | Taimur Zahid | 0 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-162 | [5 empty] | 2025-10-07T14:48:33.447+0500 | 2026-02-20T15:14:56.938+0500
O2 | O2-1621 | O2-1621 | Epic | Epic |  | OmniEMS pre-URS working (P) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1621 | [5 empty] | 2026-02-26T12:47:31.865+0500 | 2026-02-26T12:47:31.968+0500
O2 | O2-1622 | O2-1622 | Story | Story |  | OmniEMS pre-URS working (P) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 24.5 |  | O2-1621 | O2-1621 | https://octopusdtlsupport.atlassian.net/browse/O2-1621 | https://octopusdtlsupport.atlassian.net/browse/O2-1622 | [5 empty] | 2026-02-26T12:47:51.540+0500 | 2026-02-26T12:47:51.689+0500
O2 | O2-1623 | O2-1623 | Sub-task | Sub-task |  | OmniEMS pre-URS working (P) | To Do |  |  | 2026-03-13 | 2026-03-18 | 0 | 0 | Faiq Butt | 24.5 |  | O2-1622 | O2-1622 | https://octopusdtlsupport.atlassian.net/browse/O2-1622 | https://octopusdtlsupport.atlassian.net/browse/O2-1623 | [5 empty] | 2026-02-26T12:48:06.229+0500 | 2026-03-24T14:40:11.301+0500
O2 | O2-1625 | O2-1625 | Epic | Epic |  | Ingestion Time-based Data Alarms | To Do |  |  |  |  | 200 | 200 | Taimur Zahid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1625 | [5 empty] | 2026-02-26T14:25:43.329+0500 | 2026-04-14T14:53:08.675+0500
O2 | O2-1626 | O2-1626 | Story | Story |  | Dev | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-1625 | O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1626 | [5 empty] | 2026-02-26T14:26:26.899+0500 | 2026-02-26T15:28:55.174+0500
O2 | O2-1627 | O2-1627 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-1625 | O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1627 | [5 empty] | 2026-02-26T14:26:35.148+0500 | 2026-02-26T15:28:47.902+0500
O2 | O2-1628 | O2-1628 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1625 | O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1628 | [5 empty] | 2026-02-26T14:26:41.589+0500 | 2026-02-26T14:26:41.817+0500
O2 | O2-163 | O2-163 | Story | Story |  | API Management for DDOS Protection | To Do | 2026-03-02 | 2026-03-13 |  |  | 80 | 80 | Taimur Zahid | 0 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-163 | [5 empty] | 2025-10-07T14:48:42.946+0500 | 2026-02-20T12:25:21.042+0500
O2 | O2-1633 | O2-1633 | Story | Story |  | Read API Support | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | O2-1625 | O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1625 | https://octopusdtlsupport.atlassian.net/browse/O2-1633 | [5 empty] | 2026-02-26T15:28:38.566+0500 | 2026-02-26T15:28:44.206+0500
O2 | O2-1635 | O2-1635 | Sub-task | Sub-task |  | Check OC and APX issues | Resolved! | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 2.5 | 2.5 | Mariam Zulfiqar | 2.5 |  | O2-1196 | O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1196 | https://octopusdtlsupport.atlassian.net/browse/O2-1635 | [5 empty] | 2026-02-27T09:47:11.377+0500 | 2026-02-27T09:51:45.688+0500
O2 | O2-164 | O2-164 | Epic | Epic |  | Trigger API | Resolved! | 2025-09-19 | 2025-10-17 |  |  | 200 | 200 | Taimur Zahid | 28 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-164 | [5 empty] | 2025-10-07T15:03:34.865+0500 | 2026-02-18T16:14:09.246+0500
O2 | O2-1648 | O2-1648 | Sub-task | Sub-task |  | OC Template - Coal (P) | To Do |  |  | 2026-02-23 | 2026-02-24 | 4 | 4 | Danish Rashid | 5 |  | O2-482 | O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-1648 | [5 empty] | 2026-03-02T10:28:07.355+0500 | 2026-03-05T09:46:05.030+0500
O2 | O2-1649 | O2-1649 | Sub-task | Sub-task |  | OC Template - NG (P) | To Do |  |  | 2026-02-23 | 2026-02-23 | 4 | 4 | Danish Rashid | 4 |  | O2-482 | O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-1649 | [5 empty] | 2026-03-02T10:30:23.019+0500 | 2026-03-02T10:30:54.225+0500
O2 | O2-165 | O2-165 | Story | Story |  | Authentication and Authorization | Resolved! | 2025-09-22 | 2025-09-26 |  |  | 40 | 40 | Taimur Zahid | 24 |  | O2-164 | O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-165 | [5 empty] | 2025-10-07T15:03:49.479+0500 | 2026-02-19T15:41:06.229+0500
O2 | O2-1650 | O2-1650 | Sub-task | Sub-task |  | Process Testing - NG (P) | To Do |  |  | 2026-02-26 | 2026-02-27 | 1 | 1 | Danish Rashid | 4 |  | O2-482 | O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-1650 | [5 empty] | 2026-03-02T10:32:28.040+0500 | 2026-03-05T09:46:59.863+0500
O2 | O2-1651 | O2-1651 | Sub-task | Sub-task |  | Process Testing - Coal (P) | To Do |  |  | 2026-02-26 | 2026-02-27 | 1 | 1 | Danish Rashid | 4 |  | O2-482 | O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-482 | https://octopusdtlsupport.atlassian.net/browse/O2-1651 | [5 empty] | 2026-03-02T10:37:09.801+0500 | 2026-03-05T09:47:21.598+0500
O2 | O2-1652 | O2-1652 | Sub-task | Sub-task |  | OC Template (P) | To Do |  |  | 2026-02-25 | 2026-02-25 | 4 | 4 | Danish Rashid | 4 |  | O2-450 | O2-450 | https://octopusdtlsupport.atlassian.net/browse/O2-450 | https://octopusdtlsupport.atlassian.net/browse/O2-1652 | [5 empty] | 2026-03-02T10:40:16.815+0500 | 2026-03-02T10:41:31.591+0500
O2 | O2-1653 | O2-1653 | Sub-task | Sub-task |  | Process Testing (P) | To Do |  |  | 2026-02-26 | 2026-02-27 | 1 | 1 | Danish Rashid | 5 |  | O2-450 | O2-450 | https://octopusdtlsupport.atlassian.net/browse/O2-450 | https://octopusdtlsupport.atlassian.net/browse/O2-1653 | [5 empty] | 2026-03-02T10:40:30.644+0500 | 2026-03-05T09:52:02.436+0500
O2 | O2-1654 | O2-1654 | Epic | Epic |  | Steam Surface Condenser What-If | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 24 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | [5 empty] | 2026-03-02T10:47:23.421+0500 | 2026-03-02T10:47:23.515+0500
O2 | O2-1656 | O2-1656 | Story | Story |  | Design What-If Model (P) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1656 | [5 empty] | 2026-03-02T10:50:53.037+0500 | 2026-03-02T10:50:53.184+0500
O2 | O2-1657 | O2-1657 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1657 | [5 empty] | 2026-03-02T11:02:38.933+0500 | 2026-03-02T11:02:39.215+0500
O2 | O2-1658 | O2-1658 | Story | Story |  | Template, wizards and dashboard design (P) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1658 | [5 empty] | 2026-03-02T11:02:46.250+0500 | 2026-03-02T11:02:46.447+0500
O2 | O2-1659 | O2-1659 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1659 | [5 empty] | 2026-03-02T11:02:59.676+0500 | 2026-03-02T11:02:59.851+0500
O2 | O2-166 | O2-166 | Story | Story |  | Pipeline Scheduling | Resolved! | 2025-09-29 | 2025-10-06 |  |  | 48 | 48 | Aiza Hamid | 16 |  | O2-164 | O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-166 | [5 empty] | 2025-10-07T15:05:23.741+0500 | 2026-02-11T11:40:10.455+0500
O2 | O2-1660 | O2-1660 | Story | Story |  | OC Process testing (P) | To Do |  |  | 2026-02-16 | 2026-02-18 | 24 | 24 | Danish Rashid | 24 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1660 | [5 empty] | 2026-03-02T11:03:06.281+0500 | 2026-03-02T11:05:15.866+0500
O2 | O2-1661 | O2-1661 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1661 | [5 empty] | 2026-03-02T11:03:12.650+0500 | 2026-03-02T11:03:12.824+0500
O2 | O2-1662 | O2-1662 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1662 | [5 empty] | 2026-03-02T11:03:19.873+0500 | 2026-03-02T11:03:20.014+0500
O2 | O2-1663 | O2-1663 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1663 | [5 empty] | 2026-03-02T11:03:26.898+0500 | 2026-03-02T11:03:27.094+0500
O2 | O2-1664 | O2-1664 | Story | Story |  | Add Training Material (P) | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1654 | O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1654 | https://octopusdtlsupport.atlassian.net/browse/O2-1664 | [5 empty] | 2026-03-02T11:03:33.458+0500 | 2026-03-02T11:03:33.626+0500
O2 | O2-167 | O2-167 | Story | Story |  | Pipeline Status | Resolved! | 2025-09-29 | 2025-10-06 |  |  | 48 | 48 | Aiza Hamid | 16 |  | O2-164 | O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-167 | [5 empty] | 2025-10-07T15:05:30.315+0500 | 2026-02-11T11:40:10.556+0500
O2 | O2-1672 | O2-1672 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | Resolved! | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-26 | 8 | 8 | Muhammad Abdul Wasi | 8 |  | O2-1021 | O2-1021 | https://octopusdtlsupport.atlassian.net/browse/O2-1021 | https://octopusdtlsupport.atlassian.net/browse/O2-1672 | [5 empty] | 2026-03-02T13:33:44.833+0500 | 2026-03-11T11:11:20.963+0500
O2 | O2-1673 | O2-1673 | Sub-task | Sub-task |  | Template (P) | Resolved! | 2026-02-25 | 2026-02-28 | 2026-02-26 | 2026-02-27 | 7 | 7 | DANIYAL AHMAD | 7 |  | O2-1030 | O2-1030 | https://octopusdtlsupport.atlassian.net/browse/O2-1030 | https://octopusdtlsupport.atlassian.net/browse/O2-1673 | [5 empty] | 2026-03-02T14:16:06.633+0500 | 2026-03-11T11:06:40.979+0500
O2 | O2-1675 | O2-1675 | Sub-task | Sub-task |  | Process Eng. tasks: working, review and management | Resolved! | 2026-03-02 | 2026-03-31 | 2026-03-02 | 2026-03-31 | 103 | 103 | Mariam Zulfiqar | 103 |  | O2-1254 | O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1675 | [5 empty] | 2026-03-03T08:54:04.386+0500 | 2026-04-02T12:54:10.891+0500
O2 | O2-1676 | O2-1676 | Sub-task | Sub-task |  | Process pre-sales support, Customer / Management Meetings | Resolved! | 2026-03-02 | 2026-03-31 | 2026-03-02 | 2026-03-26 | 17 | 17 | Mariam Zulfiqar | 16.5 |  | O2-1066 | O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1676 | [5 empty] | 2026-03-03T08:55:53.813+0500 | 2026-04-02T13:05:48.474+0500
O2 | O2-1677 | O2-1677 | Sub-task | Sub-task |  | Support | Resolved! | 2026-03-03 | 2026-03-05 | 2026-03-03 | 2026-03-04 | 16 | 16 | Zeeshan Sarwar | 13 |  | O2-517 | O2-517 | https://octopusdtlsupport.atlassian.net/browse/O2-517 | https://octopusdtlsupport.atlassian.net/browse/O2-1677 | [5 empty] | 2026-03-03T10:14:37.842+0500 | 2026-03-04T15:19:10.441+0500
O2 | O2-168 | O2-168 | Story | Story |  | SQA | Resolved! | 2025-10-07 | 2025-10-07 |  |  | 16 | 16 | Muhammad Abbas | 4 |  | O2-164 | O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-168 | [5 empty] | 2025-10-07T15:19:12.516+0500 | 2026-02-11T11:40:10.367+0500
O2 | O2-1684 | O2-1684 | Story | Story |  | Tapal ETL Redesign by Implementation Team: Monitoring and Reporting | Resolved! | 2026-02-25 | 2026-03-31 |  |  | 56 | 56 | Taimur Zahid | 37 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1684 | [5 empty] | 2026-03-03T10:38:28.134+0500 | 2026-03-25T15:29:05.681+0500
O2 | O2-1688 | O2-1688 | Sub-task | Sub-task |  | Monitoring and Reporting - February 2026 | Resolved! | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 19.5 | 19.5 | Taimur Zahid | 19.5 |  | O2-1684 | O2-1684 | https://octopusdtlsupport.atlassian.net/browse/O2-1684 | https://octopusdtlsupport.atlassian.net/browse/O2-1688 | [5 empty] | 2026-03-03T10:47:52.679+0500 | 2026-03-10T11:28:00.330+0500
O2 | O2-1689 | O2-1689 | Sub-task | Sub-task |  | Testing By M.Abbas Rework | In-Progress | 2026-03-03 | 2026-03-05 | 2026-03-04 | 2026-03-10 | 24 | 24 | Muhammad Abbas | 30 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1689 | [5 empty] | 2026-03-03T11:00:14.569+0500 | 2026-03-10T15:51:59.452+0500
O2 | O2-169 | O2-169 | Story | Story |  | Production Release | Resolved! | 2025-10-08 | 2025-10-08 |  |  | 8 | 8 | Taimur Zahid | 0 |  | O2-164 | O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-169 | [5 empty] | 2025-10-07T15:19:16.711+0500 | 2026-02-11T11:40:10.681+0500
O2 | O2-1693 | O2-1693 | Sub-task | Sub-task |  | Documentation | To Do | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Hassan Malik | 8 |  | O2-1092 | O2-1092 | https://octopusdtlsupport.atlassian.net/browse/O2-1092 | https://octopusdtlsupport.atlassian.net/browse/O2-1693 | [5 empty] | 2026-03-03T12:32:25.631+0500 | 2026-03-03T12:33:34.232+0500
O2 | O2-1699 | O2-1699 | Sub-task | Sub-task |  | UI Changes Batch RunOnDemand | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Arslan sohail | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1699 | [5 empty] | 2026-03-03T19:51:49.821+0500 | 2026-04-07T14:30:16.010+0500
O2 | O2-17 | O2-17 | Story | Story |  | Production Release | Resolved! | 2025-10-24 | 2025-10-24 |  |  | 16 | 16 | Ameer Hamza Khan | 8 |  | O2-9 | O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-17 | [5 empty] | 2025-10-02T14:08:09.169+0500 | 2025-10-29T11:18:33.909+0500
O2 | O2-170 | O2-170 | Story | Story |  | SQA | Resolved! | 2025-10-02 | 2025-10-02 |  |  | 16 | 16 | Muhammad Abbas | 4 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-170 | [5 empty] | 2025-10-07T15:20:07.201+0500 | 2025-10-24T16:36:15.524+0500
O2 | O2-1700 | O2-1700 | Sub-task | Sub-task |  | New UI BPM RunOnDemand | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | Arslan sohail | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1700 | [5 empty] | 2026-03-03T19:52:26.738+0500 | 2026-04-07T14:32:29.627+0500
O2 | O2-1701 | O2-1701 | Sub-task | Sub-task |  | UI Changes Templates Variables Batch | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 8 | 8 | Arslan sohail | 4 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1701 | [5 empty] | 2026-03-03T19:53:36.526+0500 | 2026-04-07T14:42:29.957+0500
O2 | O2-1702 | O2-1702 | Sub-task | Sub-task |  | UI Changes Template Variable BPM | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Arslan sohail | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1702 | [5 empty] | 2026-03-03T19:54:04.825+0500 | 2026-04-07T14:34:18.575+0500
O2 | O2-1703 | O2-1703 | Sub-task | Sub-task |  | Database Tables and Changes for Batch | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | ahad omer | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1703 | [5 empty] | 2026-03-03T19:54:21.507+0500 | 2026-04-07T16:47:57.906+0500
O2 | O2-1704 | O2-1704 | Sub-task | Sub-task |  | Database Tables and ¦Changes BPM | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | ahad omer | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1704 | [5 empty] | 2026-03-03T19:54:40.596+0500 | 2026-04-07T16:47:39.578+0500
O2 | O2-1705 | O2-1705 | Sub-task | Sub-task |  | Backend API Changes Batch Template | Resolved! | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-19 | 16 | 16 | ahad omer | 16 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1705 | [5 empty] | 2026-03-03T19:55:14.702+0500 | 2026-04-07T17:00:01.870+0500
O2 | O2-1706 | O2-1706 | Sub-task | Sub-task |  | Backend API Changes BPM Template | Resolved! | 2026-02-19 | 2026-02-25 | 2026-02-20 | 2026-02-25 | 24 | 24 | ahad omer | 24 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1706 | [5 empty] | 2026-03-03T19:55:20.079+0500 | 2026-04-07T16:53:37.627+0500
O2 | O2-1707 | O2-1707 | Sub-task | Sub-task |  | Unit Testing frontend | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 8 | 8 | Arslan sohail | 4 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1707 | [5 empty] | 2026-03-03T19:57:03.301+0500 | 2026-04-07T14:41:17.084+0500
O2 | O2-1709 | O2-1709 | Sub-task | Sub-task |  | UI Changes Integration with API | Resolved! | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 16 | 16 | Arslan sohail | 16 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1709 | [5 empty] | 2026-03-03T19:59:12.838+0500 | 2026-04-07T14:37:27.234+0500
O2 | O2-171 | O2-171 | Story | Story |  | Production Release | Resolved! | 2025-10-03 | 2025-10-03 |  |  | 8 | 8 | Aiza Hamid | 0 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-171 | [5 empty] | 2025-10-07T15:20:18.763+0500 | 2025-10-14T11:14:57.549+0500
O2 | O2-1711 | O2-1711 | Sub-task | Sub-task |  | Backend Api Run on Demand in BPM | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 8 | 8 | Arslan sohail | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1711 | [5 empty] | 2026-03-04T10:28:10.056+0500 | 2026-04-07T14:34:54.945+0500
O2 | O2-1713 | O2-1713 | Sub-task | Sub-task |  | updated the APIs | Resolved! |  |  |  |  | 40 | 40 | Muhammad Zeeshan Aslam | 0 |  | O2-848 | O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-1713 | [5 empty] | 2026-03-04T10:37:31.984+0500 | 2026-03-04T10:38:50.190+0500
O2 | O2-1714 | O2-1714 | Sub-task | Sub-task |  | Backend Api Run on Demand in Batch | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 8 | 8 | Arslan sohail | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1714 | [5 empty] | 2026-03-04T10:37:41.648+0500 | 2026-04-07T14:35:38.860+0500
O2 | O2-1715 | O2-1715 | Sub-task | Sub-task |  | Unit Testing Backend | Resolved! | 2026-03-04 | 2026-03-04 | 2026-02-26 | 2026-02-26 | 8 | 8 | Arslan sohail | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1715 | [5 empty] | 2026-03-04T10:41:05.025+0500 | 2026-04-07T14:39:36.497+0500
O2 | O2-1716 | O2-1716 | Sub-task | Sub-task |  | Backend Improvements and Bug fixing | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 8 | 8 | ahad omer | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1716 | [5 empty] | 2026-03-04T11:00:30.305+0500 | 2026-04-07T16:54:29.441+0500
O2 | O2-172 | O2-172 | Sub-task | Sub-task |  | Research/DDS | Resolved! |  |  |  |  | 24 | 24 | Muhammad Zeeshan Aslam | 24 |  | O2-67 | O2-67 | https://octopusdtlsupport.atlassian.net/browse/O2-67 | https://octopusdtlsupport.atlassian.net/browse/O2-172 | [5 empty] | 2025-10-07T15:44:13.645+0500 | 2026-03-12T13:25:05.791+0500
O2 | O2-1721 | O2-1721 | Sub-task | Sub-task |  | OmniConnect Demo Prep 17th Feb | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2 | 2 | Sarmad Sabir | 2 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1721 | [5 empty] | 2026-03-04T12:47:48.948+0500 | 2026-03-04T12:49:06.243+0500
O2 | O2-1722 | O2-1722 | Sub-task | Sub-task |  | OmniConnect Demo Day 18th Feb | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Sarmad Sabir | 8 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1722 | [5 empty] | 2026-03-04T12:48:05.658+0500 | 2026-03-04T12:49:32.835+0500
O2 | O2-1723 | O2-1723 | Sub-task | Sub-task |  | Mihir Demo on OmniConnect | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5 | 6.5 | Sarmad Sabir | 6.5 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1723 | [5 empty] | 2026-03-04T12:48:22.682+0500 | 2026-03-04T12:50:01.234+0500
O2 | O2-1724 | O2-1724 | Sub-task | Sub-task |  | DL Demo Prep 17th Feb | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1.5 | 1.5 | Sarmad Sabir | 1.5 |  | O2-1405 | O2-1405 | https://octopusdtlsupport.atlassian.net/browse/O2-1405 | https://octopusdtlsupport.atlassian.net/browse/O2-1724 | [5 empty] | 2026-03-04T12:50:39.681+0500 | 2026-03-04T12:51:23.507+0500
O2 | O2-1725 | O2-1725 | Sub-task | Sub-task |  | Fintech Fuel Demo Prep 17th Feb | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 1.5 | 1.5 | Sarmad Sabir | 1.5 |  | O2-1404 | O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1725 | [5 empty] | 2026-03-04T12:51:46.196+0500 | 2026-03-04T12:52:21.387+0500
O2 | O2-1726 | O2-1726 | Sub-task | Sub-task |  | MPC Demo on OmniConnect | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 4 | 4 | Sarmad Sabir | 4 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1726 | [5 empty] | 2026-03-04T12:57:54.575+0500 | 2026-03-04T12:58:36.578+0500
O2 | O2-1729 | O2-1729 | Sub-task | Sub-task |  | OmniConnect Demo prep 7th Jan | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Sarmad Sabir | 8 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1729 | [5 empty] | 2026-03-04T13:09:40.884+0500 | 2026-03-04T13:11:56.308+0500
O2 | O2-173 | O2-173 | Sub-task | Sub-task |  | User Manual | Resolved! |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-70 | O2-70 | https://octopusdtlsupport.atlassian.net/browse/O2-70 | https://octopusdtlsupport.atlassian.net/browse/O2-173 | [5 empty] | 2025-10-07T15:45:22.232+0500 | 2025-11-13T19:06:17.344+0500
O2 | O2-1730 | O2-1730 | Sub-task | Sub-task |  | OmniConnect Demo prep 8th Jan | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8 | 8 | Sarmad Sabir | 8 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1730 | [5 empty] | 2026-03-04T13:09:42.725+0500 | 2026-03-04T13:12:20.077+0500
O2 | O2-1731 | O2-1731 | Sub-task | Sub-task |  | OmniConnect Demo 28th Jan | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 4 | 4 | Sarmad Sabir | 4 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1731 | [5 empty] | 2026-03-04T13:10:06.931+0500 | 2026-03-04T13:11:31.518+0500
O2 | O2-1732 | O2-1732 | Sub-task | Sub-task |  | OmniConnect Demo 30th Jan | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8 | 8 | Sarmad Sabir | 8 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1732 | [5 empty] | 2026-03-04T13:10:15.897+0500 | 2026-03-04T13:12:38.016+0500
O2 | O2-1744 | O2-1744 | Sub-task | Sub-task |  | Impact Analysis | Resolved! | 2025-12-31 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 32 | 32 | Arslan sohail | 32 |  | O2-1113 | O2-1113 | https://octopusdtlsupport.atlassian.net/browse/O2-1113 | https://octopusdtlsupport.atlassian.net/browse/O2-1744 | [5 empty] | 2026-03-04T15:58:50.083+0500 | 2026-03-04T16:15:05.015+0500
O2 | O2-1745 | O2-1745 | Sub-task | Sub-task |  | Impact Analysis | Resolved! | 2025-12-31 | 2026-01-06 | 2026-01-01 | 2026-01-06 | 40 | 40 | ahad omer | 40 |  | O2-1113 | O2-1113 | https://octopusdtlsupport.atlassian.net/browse/O2-1113 | https://octopusdtlsupport.atlassian.net/browse/O2-1745 | [5 empty] | 2026-03-04T15:58:59.855+0500 | 2026-03-04T16:05:38.067+0500
O2 | O2-1747 | O2-1747 | Sub-task | Sub-task |  | Add New Column BPM API Changes | Resolved! | 2026-01-07 | 2026-01-13 | 2026-01-07 | 2026-01-13 | 32 | 32 | ahad omer | 32 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1747 | [5 empty] | 2026-03-04T16:17:30.468+0500 | 2026-03-04T16:22:14.976+0500
O2 | O2-1748 | O2-1748 | Sub-task | Sub-task |  | Add New Column Batch API Changes | Resolved! | 2026-01-14 | 2026-01-19 | 2026-01-14 | 2026-01-19 | 32 | 32 | ahad omer | 32 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1748 | [5 empty] | 2026-03-04T16:17:38.437+0500 | 2026-03-04T16:39:40.209+0500
O2 | O2-1749 | O2-1749 | Sub-task | Sub-task |  | Add New Column in Custom Functions | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Arslan sohail | 8 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1749 | [5 empty] | 2026-03-04T16:20:24.498+0500 | 2026-03-04T16:22:06.425+0500
O2 | O2-1750 | O2-1750 | Sub-task | Sub-task |  | Frontend End to End Testing | Resolved! | 2026-01-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | 16 | 16 | Arslan sohail | 16 |  | O2-1041 | O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1041 | https://octopusdtlsupport.atlassian.net/browse/O2-1750 | [5 empty] | 2026-03-04T16:23:37.587+0500 | 2026-03-04T16:40:12.865+0500
O2 | O2-1751 | O2-1751 | Task | Task |  | Batch/Bpm/Connectors End to end Testing + Bug Fixes | To Do | 2026-01-20 | 2026-01-27 | 2026-01-20 | 2026-01-27 | 0 | 0 | Arslan sohail | 40 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-1751 | [5 empty] | 2026-03-04T16:30:50.475+0500 | 2026-03-04T16:33:55.178+0500
O2 | O2-1752 | O2-1752 | Sub-task | Sub-task |  | Initial Research OEE NO CODE | Resolved! | 2026-01-28 | 2026-01-30 | 2026-01-28 | 2026-01-30 | 24 | 24 | ahad omer | 24 |  | O2-1378 | O2-1378 | https://octopusdtlsupport.atlassian.net/browse/O2-1378 | https://octopusdtlsupport.atlassian.net/browse/O2-1752 | [5 empty] | 2026-03-04T16:36:12.025+0500 | 2026-03-04T16:38:17.615+0500
O2 | O2-1753 | O2-1753 | Sub-task | Sub-task |  | Initial Research OEE NO CODE | Resolved! | 2026-01-28 |  | 2026-01-28 | 2026-01-30 | 0 | 0 | Arslan sohail | 24 |  | O2-1378 | O2-1378 | https://octopusdtlsupport.atlassian.net/browse/O2-1378 | https://octopusdtlsupport.atlassian.net/browse/O2-1753 | [5 empty] | 2026-03-04T16:36:32.218+0500 | 2026-03-04T16:37:58.274+0500
O2 | O2-1754 | O2-1754 | Sub-task | Sub-task |  | Bug Fixing, Improvements and Tasks | Resolved! | 2026-02-09 | 2026-02-11 | 2026-02-09 | 2026-02-11 | 0 | 0 | Arslan sohail | 24 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1754 | [5 empty] | 2026-03-04T16:41:48.893+0500 | 2026-03-04T16:44:13.560+0500
O2 | O2-1755 | O2-1755 | Epic | Epic |  | SQA | To Do | 2026-01-01 | 2026-12-31 |  |  | 384 | 384 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1755 | [5 empty] | 2026-02-02T15:33:48.159+0500 | 2026-03-30T11:44:08.686+0500
O2 | O2-1756 | O2-1756 | Sub-task | Sub-task |  | Create Training data set | Resolved! |  |  | 2026-03-03 | 2026-03-03 | 4 | 4 | Muhammad Abdul Wasi | 4 |  | O2-1048 | O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-1756 | [5 empty] | 2026-03-05T09:29:14.829+0500 | 2026-03-26T09:17:43.421+0500
O2 | O2-1757 | O2-1757 | Sub-task | Sub-task |  | OmniConnect_Revamp_(UI/UX)_Main Dashboard (P) | To Do |  |  | 2026-02-20 | 2026-04-01 | 0 | 0 | Danish Rashid | 83 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1757 | [5 empty] | 2026-03-05T10:32:19.228+0500 | 2026-04-07T10:10:38.256+0500
O2 | O2-1758 | O2-1758 | Sub-task | Sub-task |  | Testing By Zeeshan Rework | Resolved! | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-10 | 24 | 24 | Zeeshan Sarwar | 13 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1758 | [5 empty] | 2026-03-05T10:34:24.108+0500 | 2026-03-11T11:15:36.110+0500
O2 | O2-176 | O2-176 | Sub-task | Sub-task |  | How to | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 16 |  | O2-154 | O2-154 | https://octopusdtlsupport.atlassian.net/browse/O2-154 | https://octopusdtlsupport.atlassian.net/browse/O2-176 | [5 empty] | 2025-10-07T16:19:28.916+0500 | 2025-10-14T11:01:23.387+0500
O2 | O2-1760 | O2-1760 | Sub-task | Sub-task |  | OC Process testing (P) | To Do | 2026-03-02 | 2026-03-28 | 2026-03-02 | 2026-03-02 | 4 | 4 | DANIYAL AHMAD | 3.5 |  | O2-423 | O2-423 | https://octopusdtlsupport.atlassian.net/browse/O2-423 | https://octopusdtlsupport.atlassian.net/browse/O2-1760 | [5 empty] | 2026-03-05T11:36:31.717+0500 | 2026-03-24T14:54:37.690+0500
O2 | O2-1761 | O2-1761 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | To Do | 2026-03-02 | 2026-03-28 | 2026-03-02 | 2026-03-02 | 4 | 4 | DANIYAL AHMAD | 3 |  | O2-421 | O2-421 | https://octopusdtlsupport.atlassian.net/browse/O2-421 | https://octopusdtlsupport.atlassian.net/browse/O2-1761 | [5 empty] | 2026-03-05T11:37:56.157+0500 | 2026-03-05T11:39:40.254+0500
O2 | O2-1762 | O2-1762 | Sub-task | Sub-task |  | Data Prep. & Offline testing | To Do | 2026-03-02 | 2026-03-31 | 2026-03-03 | 2026-03-12 | 40 | 40 | DANIYAL AHMAD | 40 |  | O2-1032 | O2-1032 | https://octopusdtlsupport.atlassian.net/browse/O2-1032 | https://octopusdtlsupport.atlassian.net/browse/O2-1762 | [5 empty] | 2026-03-05T11:42:11.863+0500 | 2026-03-25T14:33:58.584+0500
O2 | O2-1763 | O2-1763 | Sub-task | Sub-task |  | Bug Fixing, Improvements and Tasks | Resolved! | 2026-01-20 | 2026-01-26 | 2026-01-20 | 2026-01-20 | 48 | 48 | Syed Yousaf Qadri | 8 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-1763 | [5 empty] | 2026-03-05T12:16:58.317+0500 | 2026-03-05T12:27:36.302+0500
O2 | O2-1765 | O2-1765 | Sub-task | Sub-task |  | Schema Changes | Resolved! | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-24 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1765 | [5 empty] | 2026-03-05T12:22:41.117+0500 | 2026-03-05T12:33:19.704+0500
O2 | O2-1766 | O2-1766 | Sub-task | Sub-task |  | BPM Backend Development | Resolved! | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | 24 | 24 | Syed Yousaf Qadri | 24 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1766 | [5 empty] | 2026-03-05T12:22:51.872+0500 | 2026-03-05T12:35:22.565+0500
O2 | O2-1768 | O2-1768 | Sub-task | Sub-task |  | Monitoring and Reporting - March 2026 | Resolved! | 2026-03-02 | 2026-03-30 | 2026-03-03 | 2026-03-05 | 19.5 | 19.5 | Taimur Zahid | 17.5 |  | O2-1684 | O2-1684 | https://octopusdtlsupport.atlassian.net/browse/O2-1684 | https://octopusdtlsupport.atlassian.net/browse/O2-1768 | [5 empty] | 2026-03-05T12:58:40.960+0500 | 2026-03-17T14:27:43.796+0500
O2 | O2-177 | O2-177 | Sub-task | Sub-task |  | Fields | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 0 |  | O2-154 | O2-154 | https://octopusdtlsupport.atlassian.net/browse/O2-154 | https://octopusdtlsupport.atlassian.net/browse/O2-177 | [5 empty] | 2025-10-07T16:19:46.482+0500 | 2025-10-13T22:31:58.143+0500
O2 | O2-1778 | O2-1778 | Story | Story |  | Technical support for Roshan Packages data extraction pipeline | Resolved! |  |  | 2026-03-04 | 2026-03-05 | 16 | 16 | yousha.agha | 32 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-1778 | [5 empty] | 2026-03-06T14:46:46.650+0500 | 2026-03-12T14:05:29.383+0500
O2 | O2-178 | O2-178 | Story | Story |  | User Manual | Resolved! | 2025-10-07 | 2025-10-07 |  |  | 16 | 16 | Hassan Malik | 16 |  | O2-164 | O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-164 | https://octopusdtlsupport.atlassian.net/browse/O2-178 | [5 empty] | 2025-10-07T16:23:59.434+0500 | 2026-02-11T11:40:10.415+0500
O2 | O2-1783 | O2-1783 | Epic | Epic |  | OmniConnect SaaS Cost Optimization: Azure Functions | On Hold | 2026-03-09 | 2026-04-10 |  |  | 360 | 360 | Mohsin Junaid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1783 | [5 empty] | 2026-03-09T10:52:01.843+0500 | 2026-04-24T10:03:17.907+0500
O2 | O2-1784 | O2-1784 | Story | Story |  | Read/Write API Bearer Token Client Secret Renewel | Resolved! | 2026-03-07 | 2026-03-09 |  |  | 32 | 32 | Taimur Zahid | 29.5 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | [5 empty] | 2026-03-09T10:56:41.997+0500 | 2026-03-09T15:11:38.042+0500
O2 | O2-1785 | O2-1785 | Sub-task | Sub-task |  | Read API Client Secrete Bearer Token Regeneration | Resolved! | 2026-03-07 | 2026-03-08 | 2026-03-07 | 2026-03-07 | 4 | 4 | Taimur Zahid | 2 |  | O2-1784 | O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1785 | [5 empty] | 2026-03-09T10:57:36.310+0500 | 2026-03-09T14:59:41.010+0500
O2 | O2-1786 | O2-1786 | Sub-task | Sub-task |  | Write API Client Secrete Bearer Token Regeneration | Resolved! | 2026-03-07 | 2026-03-08 | 2026-03-07 | 2026-03-07 | 4 | 4 | Taimur Zahid | 2 |  | O2-1784 | O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1786 | [5 empty] | 2026-03-09T10:57:43.386+0500 | 2026-03-09T15:07:43.809+0500
O2 | O2-1787 | O2-1787 | Sub-task | Sub-task |  | SQA Testing | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-1784 | O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1787 | [5 empty] | 2026-03-09T10:57:57.901+0500 | 2026-03-09T10:58:43.414+0500
O2 | O2-1788 | O2-1788 | Sub-task | Sub-task |  | Read API Validation and Monitoring | Resolved! | 2026-03-07 | 2026-03-08 | 2026-03-07 | 2026-03-07 | 6 | 6 | Aiza Hamid | 4 |  | O2-1784 | O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1788 | [5 empty] | 2026-03-09T10:58:09.530+0500 | 2026-03-11T10:16:08.421+0500
O2 | O2-1789 | O2-1789 | Sub-task | Sub-task |  | Write API Validation and Monitoring | Resolved! |  |  | 2026-03-07 | 2026-03-07 | 2 | 2 | Hassan Saeed Wattoo | 2 |  | O2-1784 | O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1789 | [5 empty] | 2026-03-09T10:58:14.684+0500 | 2026-03-16T12:42:57.041+0500
O2 | O2-179 | O2-179 | Sub-task | Sub-task |  | API Documentation | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 16 |  | O2-178 | O2-178 | https://octopusdtlsupport.atlassian.net/browse/O2-178 | https://octopusdtlsupport.atlassian.net/browse/O2-179 | [5 empty] | 2025-10-07T16:26:50.376+0500 | 2025-10-07T16:31:27.127+0500
O2 | O2-1791 | O2-1791 | Sub-task | Sub-task |  | Key Vault Integration and Updates | Resolved! | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 19.5 | 19.5 | Taimur Zahid | 19.5 |  | O2-1784 | O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1784 | https://octopusdtlsupport.atlassian.net/browse/O2-1791 | [5 empty] | 2026-03-09T15:11:26.892+0500 | 2026-03-17T13:59:27.553+0500
O2 | O2-1792 | O2-1792 | Sub-task | Sub-task |  | Fintech Fuel For PGL Leadership - Documentation and Diagram | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5 | 6.5 | Taimur Zahid | 6.5 |  | O2-1219 | O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1219 | https://octopusdtlsupport.atlassian.net/browse/O2-1792 | [5 empty] | 2026-03-09T15:17:19.472+0500 | 2026-03-17T14:13:14.673+0500
O2 | O2-180 | O2-180 | Sub-task | Sub-task |  | UI/UX | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 24 |  | O2-15 | O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-180 | [5 empty] | 2025-10-07T16:51:58.190+0500 | 2025-10-29T16:09:54.264+0500
O2 | O2-1800 | O2-1800 | Bug Subtask | Bug Subtask |  | Output Cal tag latest values for APX performance asset are not displaying. | Bug Fixed |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1800 | [5 empty] | 2026-03-10T11:43:00.380+0500 | 2026-03-25T10:58:39.569+0500
O2 | O2-1807 | O2-1807 | Bug Subtask | Bug Subtask |  | Alarms are not triggering after the recent release of Real-Time Tag Streaming | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1807 | [5 empty] | 2026-03-10T13:12:57.332+0500 | 2026-03-10T13:14:43.929+0500
O2 | O2-1809 | O2-1809 | Bug Subtask | Bug Subtask |  | Batch jobs are failing on the staging environment and failure logs are not generated | Request received |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1809 | [5 empty] | 2026-03-10T13:17:41.106+0500 | 2026-03-10T13:18:18.616+0500
O2 | O2-181 | O2-181 | Sub-task | Sub-task |  | Frontend | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 32 |  | O2-15 | O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-181 | [5 empty] | 2025-10-07T16:53:58.246+0500 | 2025-10-29T16:09:58.078+0500
O2 | O2-1810 | O2-1810 | Bug Subtask | Bug Subtask |  | BPM jobs are not executing | Request received |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-1810 | [5 empty] | 2026-03-10T13:19:35.474+0500 | 2026-03-10T13:20:17.285+0500
O2 | O2-182 | O2-182 | Sub-task | Sub-task |  | API Development | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 64 |  | O2-15 | O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-182 | [5 empty] | 2025-10-07T16:54:13.199+0500 | 2025-10-29T16:10:01.232+0500
O2 | O2-183 | O2-183 | Sub-task | Sub-task |  | Unit Testing Backend | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 8 |  | O2-15 | O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-183 | [5 empty] | 2025-10-07T16:54:44.680+0500 | 2025-10-29T16:10:03.378+0500
O2 | O2-1832 | O2-1832 | Sub-task | Sub-task |  | OmniOEE Pre-URS working (P) | Resolved! | 2026-03-02 | 2026-03-11 | 2026-03-02 | 2026-03-11 | 47 | 47 | Muhammad Abdul Wasi | 47 |  | O2-1375 | O2-1375 | https://octopusdtlsupport.atlassian.net/browse/O2-1375 | https://octopusdtlsupport.atlassian.net/browse/O2-1832 | [5 empty] | 2026-03-11T10:04:51.574+0500 | 2026-03-12T12:24:49.329+0500
O2 | O2-1833 | O2-1833 | Sub-task | Sub-task |  | OmniOEE Pre-URS working (P) | Resolved! | 2026-02-18 | 2026-02-27 | 2026-02-20 | 2026-02-27 | 11 | 11 | Muhammad Abdul Wasi | 11 |  | O2-1375 | O2-1375 | https://octopusdtlsupport.atlassian.net/browse/O2-1375 | https://octopusdtlsupport.atlassian.net/browse/O2-1833 | [5 empty] | 2026-03-11T10:25:20.604+0500 | 2026-03-12T10:42:55.999+0500
O2 | O2-1834 | O2-1834 | Sub-task | Sub-task |  | User Management for Omni Connect through Omni Agent | Resolved! | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-03-09 | 16 | 16 | Aiza Hamid | 13 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1834 | [5 empty] | 2026-03-11T10:33:14.155+0500 | 2026-03-26T15:03:27.061+0500
O2 | O2-1835 | O2-1835 | Sub-task | Sub-task |  | OC Process testing (P) | Resolved! | 2026-01-29 | 2026-01-30 | 2026-01-29 | 2026-01-30 | 16 | 16 | Muhammad Abdul Wasi | 16 |  | O2-1023 | O2-1023 | https://octopusdtlsupport.atlassian.net/browse/O2-1023 | https://octopusdtlsupport.atlassian.net/browse/O2-1835 | [5 empty] | 2026-03-11T10:41:21.845+0500 | 2026-03-11T10:43:02.435+0500
O2 | O2-1839 | O2-1839 | Sub-task | Sub-task |  | Template (P) | Resolved! | 2026-03-09 | 2026-03-25 | 2026-03-09 | 2026-03-13 | 15 | 15 | DANIYAL AHMAD | 14.5 |  | O2-1030 | O2-1030 | https://octopusdtlsupport.atlassian.net/browse/O2-1030 | https://octopusdtlsupport.atlassian.net/browse/O2-1839 | [5 empty] | 2026-03-11T11:07:01.954+0500 | 2026-04-29T16:07:46.786+0500
O2 | O2-184 | O2-184 | Sub-task | Sub-task |  | Unit Testing frontend | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 8 |  | O2-15 | O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-15 | https://octopusdtlsupport.atlassian.net/browse/O2-184 | [5 empty] | 2025-10-07T16:56:10.160+0500 | 2025-10-29T16:10:06.808+0500
O2 | O2-1842 | O2-1842 | Sub-task | Sub-task |  | OmniConnect_ Revamp_(UI/UX)_ Variation_ 02_ Part B | Resolved! | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-06 | 40 | 40 | Hassan Wali | 40 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1842 | [5 empty] | 2026-03-11T12:00:42.827+0500 | 2026-03-12T13:53:53.138+0500
O2 | O2-1844 | O2-1844 | Sub-task | Sub-task |  | Testing By Kamran Prod Rework(Green) | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 8 | 8 | kamran khalid | 6.5 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1844 | [5 empty] | 2026-03-11T12:50:43.325+0500 | 2026-03-12T16:15:53.610+0500
O2 | O2-1846 | O2-1846 | Sub-task | Sub-task |  | Testing By Namra Prod Rework(Greeen) | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 16 | 16 | Namra Zahid | 10.5 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1846 | [5 empty] | 2026-03-11T12:54:45.826+0500 | 2026-03-12T16:15:57.840+0500
O2 | O2-1847 | O2-1847 | Sub-task | Sub-task |  | Testing By Waqar Prod Rework(Greeen) | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 16 | 16 | Waqar Rasheed | 9 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1847 | [5 empty] | 2026-03-11T12:55:47.942+0500 | 2026-03-12T15:19:47.185+0500
O2 | O2-1848 | O2-1848 | Sub-task | Sub-task |  | Testing By Zeeshan Prod Rework(Greeen) | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 16 | 16 | Zeeshan Sarwar | 9 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1848 | [5 empty] | 2026-03-11T12:56:27.912+0500 | 2026-03-12T15:34:58.952+0500
O2 | O2-1849 | O2-1849 | Sub-task | Sub-task |  | Testing By M.Abbas Prod Rework(Greeen) | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 16 | 16 | Muhammad Abbas | 16 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1849 | [5 empty] | 2026-03-11T12:57:44.510+0500 | 2026-03-12T16:15:17.772+0500
O2 | O2-185 | O2-185 | Sub-task | Sub-task |  | Production Release | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 0 |  | O2-114 | O2-114 | https://octopusdtlsupport.atlassian.net/browse/O2-114 | https://octopusdtlsupport.atlassian.net/browse/O2-185 | [5 empty] | 2025-10-08T09:51:49.414+0500 | 2025-11-13T18:51:29.531+0500
O2 | O2-1854 | O2-1854 | Sub-task | Sub-task |  | Changed Data Analysis API Format | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1854 | [5 empty] | 2026-03-12T09:37:57.232+0500 | 2026-03-12T09:40:16.365+0500
O2 | O2-1855 | O2-1855 | Task | Task |  | OmniOEE URS (P) | In-Progress |  |  |  |  | 0 | 0 | Muhammad Abdul Wasi | 54 |  | O2-1302 | O2-1302 | https://octopusdtlsupport.atlassian.net/browse/O2-1302 | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | [5 empty] | 2026-03-12T10:42:00.281+0500 | 2026-03-18T09:22:10.549+0500
O2 | O2-1857 | O2-1857 | Bug Subtask | Bug Subtask |  | Monitoring Page Shows Error Even Though Table Schema and Query Schema Match | Resolved |  |  |  |  | 6.5 | 6.5 | Arslan sohail | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1857 | [5 empty] | 2026-03-12T12:26:00.051+0500 | 2026-04-07T14:45:00.619+0500
O2 | O2-1858 | O2-1858 | Sub-task | Sub-task |  | OmniConnect- Revamp- Site Dashboard and OmniAgent- UX/UI | Resolved! | 2026-02-26 | 2026-03-04 | 2026-02-26 | 2026-03-04 | 32.5 | 32.5 | Hassan Wali | 32.5 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1858 | [5 empty] | 2026-03-12T13:30:26.250+0500 | 2026-03-12T14:00:45.030+0500
O2 | O2-186 | O2-186 | Sub-task | Sub-task |  | Discussion for Solution | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 16 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-186 | [5 empty] | 2025-10-08T09:52:30.640+0500 | 2025-11-25T09:41:48.673+0500
O2 | O2-1860 | O2-1860 | Sub-task | Sub-task |  | OmniConnect-Revamp- (UI/UX) | Resolved! |  |  | 2026-02-16 | 2026-03-18 | 22.5 | 22.5 | Hassan Wali | 22.5 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-1860 | [5 empty] | 2026-03-12T13:55:38.856+0500 | 2026-03-12T13:58:13.804+0500
O2 | O2-1862 | O2-1862 | Sub-task | Sub-task |  | Inhand Live | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8 | 8 | yousha.agha | 8 |  | O2-1778 | O2-1778 | https://octopusdtlsupport.atlassian.net/browse/O2-1778 | https://octopusdtlsupport.atlassian.net/browse/O2-1862 | [5 empty] | 2026-03-12T14:16:24.124+0500 | 2026-03-12T14:25:56.884+0500
O2 | O2-1863 | O2-1863 | Sub-task | Sub-task |  | Cloud Connectivity | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8 | 8 | yousha.agha | 8 |  | O2-1778 | O2-1778 | https://octopusdtlsupport.atlassian.net/browse/O2-1778 | https://octopusdtlsupport.atlassian.net/browse/O2-1863 | [5 empty] | 2026-03-12T14:16:50.385+0500 | 2026-03-12T14:25:54.904+0500
O2 | O2-1867 | O2-1867 | Sub-task | Sub-task |  | SAP HANA Connector – Tables Not Auto-Fetched During Pipeline Creation | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1867 | [5 empty] | 2026-03-12T16:22:42.364+0500 | 2026-03-13T11:39:57.296+0500
O2 | O2-1868 | O2-1868 | Bug Subtask | Bug Subtask |  | Unable to Create ODBC connector | Request received |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1868 | [5 empty] | 2026-03-12T16:27:01.924+0500 | 2026-03-12T16:56:31.336+0500
O2 | O2-1869 | O2-1869 | Sub-task | Sub-task |  | Testing the data analysis flow | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1869 | [5 empty] | 2026-03-13T10:04:02.036+0500 | 2026-03-13T10:05:18.157+0500
O2 | O2-187 | O2-187 | Sub-task | Sub-task |  | REST API Dev OC Frontend | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 88 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-187 | [5 empty] | 2025-10-08T09:53:41.511+0500 | 2025-10-10T10:38:24.929+0500
O2 | O2-1871 | O2-1871 | Sub-task | Sub-task |  | OmniOEE URS (P) | Resolved! | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-16 | 24 | 24 | Muhammad Abdul Wasi | 18.5 |  | O2-1855 | O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-1871 | [5 empty] | 2026-03-13T11:16:33.956+0500 | 2026-03-17T09:55:16.889+0500
O2 | O2-1878 | O2-1878 | Sub-task | Sub-task |  | Preping OmniConnect Product Review to Arsalan Avanceon | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 3 | 3 | Sarmad Sabir | 3 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1878 | [5 empty] | 2026-03-13T13:46:54.284+0500 | 2026-03-13T13:52:43.835+0500
O2 | O2-1879 | O2-1879 | Sub-task | Sub-task |  | Preping APX Review to Arsalan Avanceon | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 4 | 4 | Sarmad Sabir | 4 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1879 | [5 empty] | 2026-03-13T13:47:21.322+0500 | 2026-03-13T13:52:05.354+0500
O2 | O2-188 | O2-188 | Sub-task | Sub-task |  | Code Review and Feedback | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 8 |  | O2-132 | O2-132 | https://octopusdtlsupport.atlassian.net/browse/O2-132 | https://octopusdtlsupport.atlassian.net/browse/O2-188 | [5 empty] | 2025-10-08T09:55:55.828+0500 | 2025-10-08T09:58:32.294+0500
O2 | O2-1880 | O2-1880 | Sub-task | Sub-task |  | OmniConnect + APX Review to Arsalan Avanceon | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1 | 1 | Sarmad Sabir | 1 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-1880 | [5 empty] | 2026-03-13T13:47:44.275+0500 | 2026-03-13T13:49:12.815+0500
O2 | O2-1881 | O2-1881 | Sub-task | Sub-task |  | Preping FintechFuel Product Review to Arsalan Avanceon | Resolved! | 2026-03-11 | 2026-03-12 | 2026-03-11 | 2026-03-12 | 2.5 | 2.5 | Sarmad Sabir | 2.5 |  | O2-1404 | O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1881 | [5 empty] | 2026-03-13T13:49:37.687+0500 | 2026-03-13T13:53:13.984+0500
O2 | O2-1882 | O2-1882 | Sub-task | Sub-task |  | FintechFuel Product Review to Arsalan Avanceon | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | O2-1404 | O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1882 | [5 empty] | 2026-03-13T13:49:47.779+0500 | 2026-03-13T13:50:52.169+0500
O2 | O2-189 | O2-189 | Sub-task | Sub-task |  | Code Review and Feedback | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 8 |  | O2-159 | O2-159 | https://octopusdtlsupport.atlassian.net/browse/O2-159 | https://octopusdtlsupport.atlassian.net/browse/O2-189 | [5 empty] | 2025-10-08T09:58:58.168+0500 | 2025-10-08T09:59:42.317+0500
O2 | O2-1891 | O2-1891 | Sub-task | Sub-task |  | Testing By M.Abbas Prod Rework(Blue) | Resolved! | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-16 | 16 | 16 | Muhammad Abbas | 16 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1891 | [5 empty] | 2026-03-13T16:19:30.497+0500 | 2026-03-16T15:38:11.816+0500
O2 | O2-1892 | O2-1892 | Sub-task | Sub-task |  | Testing By Zeeshan Prod Rework(Blue) | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 8 | 8 | Zeeshan Sarwar | 6.5 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1892 | [5 empty] | 2026-03-13T16:21:10.818+0500 | 2026-03-16T15:18:38.393+0500
O2 | O2-1893 | O2-1893 | Sub-task | Sub-task |  | JIRA Logging Discussion | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 1.67 | 1.67 | Faiza Nasir | 1.67 |  | O2-1573 | O2-1573 | https://octopusdtlsupport.atlassian.net/browse/O2-1573 | https://octopusdtlsupport.atlassian.net/browse/O2-1893 | [5 empty] | 2026-03-13T16:33:02.293+0500 | 2026-03-13T16:34:34.183+0500
O2 | O2-1897 | O2-1897 | Sub-task | Sub-task |  | Module Design - Fixed Speed (P) | To Do |  |  | 2026-03-12 | 2026-03-13 | 0 | 0 | Unassigned | 13 |  | O2-1045 | O2-1045 | https://octopusdtlsupport.atlassian.net/browse/O2-1045 | https://octopusdtlsupport.atlassian.net/browse/O2-1897 | [5 empty] | 2026-03-16T10:26:21.963+0500 | 2026-03-16T10:42:46.423+0500
O2 | O2-19 | O2-19 | Story | Story |  | Research/DDS | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 24 |  | O2-10 | O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-19 | [5 empty] | 2025-10-02T14:09:44.972+0500 | 2026-04-20T16:17:32.147+0500
O2 | O2-190 | O2-190 | Sub-task | Sub-task |  | Code Review and Feedback | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 16 |  | O2-131 | O2-131 | https://octopusdtlsupport.atlassian.net/browse/O2-131 | https://octopusdtlsupport.atlassian.net/browse/O2-190 | [5 empty] | 2025-10-08T10:00:19.116+0500 | 2025-10-08T10:15:31.103+0500
O2 | O2-191 | O2-191 | Sub-task | Sub-task |  | Discussion and Review | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 16 |  | O2-158 | O2-158 | https://octopusdtlsupport.atlassian.net/browse/O2-158 | https://octopusdtlsupport.atlassian.net/browse/O2-191 | [5 empty] | 2025-10-08T10:03:45.189+0500 | 2025-10-08T10:04:50.410+0500
O2 | O2-1913 | O2-1913 | Sub-task | Sub-task |  | OmniOEE Method Selection & Formulae Setup (P) | Resolved! | 2026-03-17 | 2026-03-31 | 2026-03-17 | 2026-03-18 | 16 | 16 | Muhammad Abdul Wasi | 8.5 |  | O2-1855 | O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-1913 | [5 empty] | 2026-03-17T09:54:42.995+0500 | 2026-04-06T09:30:21.427+0500
O2 | O2-1918 | O2-1918 | Story | Story |  | Handover | Resolved! | 2026-03-17 | 2026-03-18 |  |  | 5 | 5 | Arslan sohail | 1.63 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1918 | [5 empty] | 2026-03-17T13:41:03.723+0500 | 2026-03-17T13:44:05.954+0500
O2 | O2-1919 | O2-1919 | Sub-task | Sub-task |  | Handover - Hassan Malik | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1 | 1 | Hassan Malik | 0.63 |  | O2-1918 | O2-1918 | https://octopusdtlsupport.atlassian.net/browse/O2-1918 | https://octopusdtlsupport.atlassian.net/browse/O2-1919 | [5 empty] | 2026-03-17T13:42:04.769+0500 | 2026-03-17T13:43:52.447+0500
O2 | O2-192 | O2-192 | Sub-task | Sub-task |  | Modify Existing API For Connectors CRUD | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 16 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-192 | [5 empty] | 2025-10-08T10:04:14.959+0500 | 2025-10-10T10:10:34.855+0500
O2 | O2-1920 | O2-1920 | Story | Story |  | Bug Fixing | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 16 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1920 | [5 empty] | 2026-03-17T14:06:28.813+0500 | 2026-04-20T16:07:21.852+0500
O2 | O2-1921 | O2-1921 | Story | Story |  | QA Handover | Resolved! | 2026-03-17 | 2026-03-17 |  |  | 0.5 | 0.5 | Muhammad Abbas | 0.5 |  | O2-818 | O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-818 | https://octopusdtlsupport.atlassian.net/browse/O2-1921 | [5 empty] | 2026-03-17T14:06:57.212+0500 | 2026-04-15T10:42:50.351+0500
O2 | O2-1922 | O2-1922 | Sub-task | Sub-task |  | Handover | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 0 | 0 | Arslan sohail | 1 |  | O2-1918 | O2-1918 | https://octopusdtlsupport.atlassian.net/browse/O2-1918 | https://octopusdtlsupport.atlassian.net/browse/O2-1922 | [5 empty] | 2026-03-17T14:07:12.850+0500 | 2026-03-17T15:02:59.616+0500
O2 | O2-1923 | O2-1923 | Sub-task | Sub-task |  | Handover By Abbas | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 0.5 | 0.5 | Muhammad Abbas | 0.5 |  | O2-1921 | O2-1921 | https://octopusdtlsupport.atlassian.net/browse/O2-1921 | https://octopusdtlsupport.atlassian.net/browse/O2-1923 | [5 empty] | 2026-03-17T14:07:33.047+0500 | 2026-03-17T14:09:08.853+0500
O2 | O2-1924 | O2-1924 | Sub-task | Sub-task |  | Batch Run on demand | Resolved! | 2026-03-17 | 2026-03-25 | 2026-03-17 | 2026-03-26 | 32 | 32 | Muhammad Abbas | 32 |  | O2-1438 | O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-1924 | [5 empty] | 2026-03-17T14:11:33.201+0500 | 2026-03-26T10:29:47.351+0500
O2 | O2-1925 | O2-1925 | Sub-task | Sub-task |  | Testing by Zeeshan | Resolved! | 2026-03-17 | 2026-03-19 | 2026-03-17 | 2026-03-30 | 24 | 24 | Zeeshan Sarwar | 25 |  | O2-520 | O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-1925 | [5 empty] | 2026-03-17T14:13:42.616+0500 | 2026-03-30T16:52:09.315+0500
O2 | O2-1926 | O2-1926 | Sub-task | Sub-task |  | Deployment + Unit Testing + DB Changes/Migrations | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 3.5 | 3.5 | Zain Munir | 3.5 |  | O2-520 | O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-1926 | [5 empty] | 2026-03-17T14:52:07.776+0500 | 2026-03-17T14:52:54.280+0500
O2 | O2-1927 | O2-1927 | Sub-task | Sub-task |  | Production Green Deployment | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 3 | 3 | Faiza Nasir | 3 |  | O2-520 | O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-1927 | [5 empty] | 2026-03-17T15:19:46.975+0500 | 2026-03-17T15:20:36.517+0500
O2 | O2-193 | O2-193 | Sub-task | Sub-task |  | New Table and Database changes for Rest API | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-193 | [5 empty] | 2025-10-08T10:04:32.339+0500 | 2025-10-10T10:10:38.453+0500
O2 | O2-1932 | O2-1932 | Sub-task | Sub-task |  | Meetings and Discussions | Resolved! | 2026-03-11 | 2026-03-13 | 2026-03-12 | 2026-03-13 | 13 | 13 | Taimur Zahid | 13 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1932 | [5 empty] | 2026-03-17T15:27:27.985+0500 | 2026-03-17T15:28:53.497+0500
O2 | O2-1933 | O2-1933 | Sub-task | Sub-task |  | Code Merge + Testing + Deployement to staging | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1933 | [5 empty] | 2026-03-17T15:32:46.147+0500 | 2026-03-17T15:33:47.548+0500
O2 | O2-1934 | O2-1934 | Sub-task | Sub-task |  | March 17, 2026 | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5 | 6.5 | Taimur Zahid | 6.5 |  | O2-1293 | O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1293 | https://octopusdtlsupport.atlassian.net/browse/O2-1934 | [5 empty] | 2026-03-17T15:36:33.321+0500 | 2026-03-17T15:37:11.401+0500
O2 | O2-1935 | O2-1935 | Epic | Epic |  | Disaster Recovery | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1935 | [5 empty] | 2026-03-17T15:55:39.964+0500 | 2026-03-17T15:55:40.106+0500
O2 | O2-1937 | O2-1937 | Story | Story |  | Handover | Resolved! | 2026-03-18 | 2026-03-18 |  |  | 1 | 1 | Ibrahim Ahmed Qureshi | 5 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | [5 empty] | 2026-03-18T11:09:31.956+0500 | 2026-04-17T10:06:23.094+0500
O2 | O2-1938 | O2-1938 | Sub-task | Sub-task |  | Handover By Namra | In-Progress | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 1 | 1 | Namra Zahid | 1 |  | O2-1937 | O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1938 | [5 empty] | 2026-03-18T11:11:09.932+0500 | 2026-03-18T12:09:07.825+0500
O2 | O2-1939 | O2-1939 | Sub-task | Sub-task |  | Handover By Waqar | Resolved! |  |  | 2026-03-18 | 2026-03-18 | 1 | 1 | Waqar Rasheed | 1 |  | O2-1937 | O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1939 | [5 empty] | 2026-03-18T11:11:23.888+0500 | 2026-03-18T12:24:35.536+0500
O2 | O2-194 | O2-194 | Sub-task | Sub-task |  | Modify Existing API For Triggers CRUD | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 16 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-194 | [5 empty] | 2025-10-08T10:05:17.663+0500 | 2025-10-10T10:10:44.134+0500
O2 | O2-1940 | O2-1940 | Sub-task | Sub-task |  | Handover By Zeeshan | Resolved! |  |  | 2026-03-18 | 2026-03-18 | 1 | 1 | Zeeshan Sarwar | 1 |  | O2-1937 | O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1940 | [5 empty] | 2026-03-18T11:11:38.283+0500 | 2026-03-18T11:54:50.777+0500
O2 | O2-1941 | O2-1941 | Sub-task | Sub-task |  | Handover By Abbas | To Do |  |  |  |  | 1 | 1 | Muhammad Abbas | 0 |  | O2-1937 | O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1941 | [5 empty] | 2026-03-18T11:11:53.310+0500 | 2026-03-18T11:53:56.412+0500
O2 | O2-1942 | O2-1942 | Sub-task | Sub-task |  | Testing By Namra march | Resolved! | 2026-03-18 | 2026-03-30 | 2026-03-18 | 2026-03-31 | 40 | 40 | Namra Zahid | 15.5 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1942 | [5 empty] | 2026-03-18T11:34:58.530+0500 | 2026-05-12T15:38:52.404+0500
O2 | O2-1944 | O2-1944 | Sub-task | Sub-task |  | Handover - Hassan Saeed Wattoo | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 1 | 1 | Hassan Saeed Wattoo | 1 |  | O2-1937 | O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1944 | [5 empty] | 2026-03-18T11:56:38.850+0500 | 2026-03-24T11:01:44.536+0500
O2 | O2-1945 | O2-1945 | Story | Story |  | Export To SQL Pointer Lookback Window | In-Progress |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 13 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-1945 | [5 empty] | 2026-03-18T11:59:36.003+0500 | 2026-03-18T13:29:24.545+0500
O2 | O2-1946 | O2-1946 | Sub-task | Sub-task |  | BPM Run on demand | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 8 | 8 | Waqar Rasheed | 5.5 |  | O2-1438 | O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-1946 | [5 empty] | 2026-03-18T12:04:03.269+0500 | 2026-03-26T10:31:07.280+0500
O2 | O2-1947 | O2-1947 | Sub-task | Sub-task |  | Implementing Lookback for Pointer | Resolved! | 2026-03-06 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 19.5 | 19.5 | Syed Yousaf Qadri | 13 |  | O2-1945 | O2-1945 | https://octopusdtlsupport.atlassian.net/browse/O2-1945 | https://octopusdtlsupport.atlassian.net/browse/O2-1947 | [5 empty] | 2026-03-18T12:04:34.066+0500 | 2026-04-07T14:37:24.410+0500
O2 | O2-1949 | O2-1949 | Sub-task | Sub-task |  | Orchestrator Agent | Resolved! | 2026-03-04 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 16 | 16 | Ibrahim Ahmed Qureshi | 13 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1949 | [5 empty] | 2026-03-18T12:29:35.853+0500 | 2026-03-18T12:31:09.665+0500
O2 | O2-195 | O2-195 | Sub-task | Sub-task |  | Modify Existing API For Pipelines CRUD | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 32 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-195 | [5 empty] | 2025-10-08T10:05:40.445+0500 | 2025-10-10T10:10:49.957+0500
O2 | O2-1950 | O2-1950 | Sub-task | Sub-task |  | Handover - Hassan Malik | Resolved! |  |  | 2026-03-18 | 2026-03-18 | 1 | 1 | Hassan Malik | 1 |  | O2-1937 | O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1937 | https://octopusdtlsupport.atlassian.net/browse/O2-1950 | [5 empty] | 2026-03-18T12:30:13.790+0500 | 2026-03-18T12:30:56.306+0500
O2 | O2-1953 | O2-1953 | Epic | Epic |  | Trigger API Integration with Batch/BPM | In-Progress | 2026-03-17 | 2026-04-21 |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | [5 empty] | 2026-03-18T15:21:43.510+0500 | 2026-04-29T17:07:37.030+0500
O2 | O2-1954 | O2-1954 | Task | Task |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1954 | [5 empty] | 2026-03-18T15:24:53.515+0500 | 2026-03-18T15:26:06.439+0500
O2 | O2-1955 | O2-1955 | Task | Task |  | Development | To Do |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 224 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | [5 empty] | 2026-03-18T15:25:06.841+0500 | 2026-03-18T15:26:13.584+0500
O2 | O2-1957 | O2-1957 | Task | Task |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1957 | [5 empty] | 2026-03-18T15:25:18.189+0500 | 2026-03-18T15:26:21.041+0500
O2 | O2-196 | O2-196 | Sub-task | Sub-task |  | Development OC Frontend | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 40 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-196 | [5 empty] | 2025-10-08T10:07:15.766+0500 | 2025-10-22T09:37:45.587+0500
O2 | O2-1962 | O2-1962 | Sub-task | Sub-task |  | SQL/Databse Layers including SPs | Resolved! | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-06 | 32.5 | 32.5 | Hamza Ali | 32.5 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1962 | [5 empty] | 2026-03-24T01:15:16.334+0500 | 2026-03-24T01:21:48.980+0500
O2 | O2-1963 | O2-1963 | Sub-task | Sub-task |  | Backend Endpoints OmniChat | Resolved! | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 32.5 | 32.5 | Hamza Ali | 32.5 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1963 | [5 empty] | 2026-03-24T01:15:56.229+0500 | 2026-03-24T01:24:36.988+0500
O2 | O2-1964 | O2-1964 | Sub-task | Sub-task |  | Metadata Linkage for Integration | To Do |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1964 | [5 empty] | 2026-03-24T01:16:33.344+0500 | 2026-03-24T01:17:55.417+0500
O2 | O2-1965 | O2-1965 | Sub-task | Sub-task |  | Module Design (P) Review | To Do |  |  | 2026-03-16 | 2026-03-17 | 0 | 0 | Unassigned | 13 |  | O2-1029 | O2-1029 | https://octopusdtlsupport.atlassian.net/browse/O2-1029 | https://octopusdtlsupport.atlassian.net/browse/O2-1965 | [5 empty] | 2026-03-24T14:40:18.962+0500 | 2026-03-24T14:41:03.614+0500
O2 | O2-1966 | O2-1966 | Sub-task | Sub-task |  | OC Process testing (P) - Faiq | To Do |  |  | 2026-02-23 | 2026-02-23 | 0 | 0 | Faiq Butt | 6 |  | O2-423 | O2-423 | https://octopusdtlsupport.atlassian.net/browse/O2-423 | https://octopusdtlsupport.atlassian.net/browse/O2-1966 | [5 empty] | 2026-03-24T14:55:30.045+0500 | 2026-03-24T14:55:58.032+0500
O2 | O2-1967 | O2-1967 | Story | Story |  | SQA OmniConnect | To Do | 2026-02-02 | 2026-04-30 |  |  | 72 | 72 | Muhammad Imran Aslam | 82 |  | O2-1755 | O2-1755 | https://octopusdtlsupport.atlassian.net/browse/O2-1755 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | [5 empty] | 2026-03-24T15:29:33.048+0500 | 2026-04-09T09:34:16.116+0500
O2 | O2-1968 | O2-1968 | Sub-task | Sub-task |  | Automation Learning Coding | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Muhammad Imran Aslam | 8 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1968 | [5 empty] | 2026-03-24T15:35:06.462+0500 | 2026-03-24T15:37:59.019+0500
O2 | O2-1969 | O2-1969 | Sub-task | Sub-task |  | Automation Learning Coding | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Muhammad Imran Aslam | 8 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1969 | [5 empty] | 2026-03-24T15:52:19.000+0500 | 2026-03-24T15:54:00.594+0500
O2 | O2-197 | O2-197 | Sub-task | Sub-task |  | Code Review and Feedback | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 4 |  | O2-166 | O2-166 | https://octopusdtlsupport.atlassian.net/browse/O2-166 | https://octopusdtlsupport.atlassian.net/browse/O2-197 | [5 empty] | 2025-10-08T10:09:29.062+0500 | 2026-01-23T15:42:49.482+0500
O2 | O2-1970 | O2-1970 | Sub-task | Sub-task |  | Automation Learning Coding | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1970 | [5 empty] | 2026-03-24T15:54:51.706+0500 | 2026-03-24T15:56:43.950+0500
O2 | O2-1971 | O2-1971 | Sub-task | Sub-task |  | Automation Learning Coding | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1971 | [5 empty] | 2026-03-24T15:57:41.295+0500 | 2026-03-24T15:59:44.638+0500
O2 | O2-1972 | O2-1972 | Sub-task | Sub-task |  | Automation Learning Coding | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1972 | [5 empty] | 2026-03-24T16:01:00.663+0500 | 2026-03-24T16:02:29.760+0500
O2 | O2-1973 | O2-1973 | Sub-task | Sub-task |  | Automation Learning Coding | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1973 | [5 empty] | 2026-03-24T16:03:25.737+0500 | 2026-03-24T16:09:48.889+0500
O2 | O2-1974 | O2-1974 | Sub-task | Sub-task |  | Automation Learning Coding | Resolved! | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | Muhammad Imran Aslam | 8 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1974 | [5 empty] | 2026-03-24T16:06:08.388+0500 | 2026-03-30T10:12:35.547+0500
O2 | O2-1975 | O2-1975 | Sub-task | Sub-task |  | QA Testing (P) | Resolved! | 2026-03-18 | 2026-03-31 | 2026-03-18 | 2026-03-31 | 40 | 40 | Muhammad Abdul Wasi | 40 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1975 | [5 empty] | 2026-03-25T10:09:01.375+0500 | 2026-04-01T10:17:18.260+0500
O2 | O2-1976 | O2-1976 | Epic | Epic |  | OmniConnect Export to SQL Enhancement | In-Progress | 2026-03-17 | 2026-04-16 |  |  | 145.6 | 145.6 | Sarmad Sabir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | [5 empty] | 2026-03-25T10:23:03.290+0500 | 2026-04-16T11:12:09.787+0500
O2 | O2-1977 | O2-1977 | Story | Story |  | Development | In-Progress | 2026-03-17 | 2026-04-03 |  |  | 20 | 20 | Sarmad Sabir | 152 |  | O2-1976 | O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | [5 empty] | 2026-03-25T10:24:06.250+0500 | 2026-04-16T11:12:14.755+0500
O2 | O2-1978 | O2-1978 | Sub-task | Sub-task |  | Fintech Fuel Demo to Mihir and Deepak | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Sarmad Sabir | 8 |  | O2-1404 | O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1404 | https://octopusdtlsupport.atlassian.net/browse/O2-1978 | [5 empty] | 2026-03-25T10:29:40.798+0500 | 2026-03-25T10:30:19.784+0500
O2 | O2-1979 | O2-1979 | Sub-task | Sub-task |  | Backword Compatability | Resolved! | 2026-01-12 | 2026-01-15 | 2026-03-16 | 2026-03-17 | 0 | 0 | Ayyan Babar | 13 |  | O2-792 | O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | https://octopusdtlsupport.atlassian.net/browse/O2-1979 | [5 empty] | 2026-03-25T10:32:45.944+0500 | 2026-04-08T11:19:47.950+0500
O2 | O2-198 | O2-198 | Sub-task | Sub-task |  | Code Review and Feedback | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 4 |  | O2-167 | O2-167 | https://octopusdtlsupport.atlassian.net/browse/O2-167 | https://octopusdtlsupport.atlassian.net/browse/O2-198 | [5 empty] | 2025-10-08T10:11:21.992+0500 | 2025-10-08T10:11:55.979+0500
O2 | O2-1980 | O2-1980 | Sub-task | Sub-task |  | Code Setup + Understanding of the repo | Resolved! | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-18 | 16 | 16 | Sarmad Sabir | 9 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1980 | [5 empty] | 2026-03-25T10:38:53.902+0500 | 2026-03-25T10:41:12.710+0500
O2 | O2-1981 | O2-1981 | Epic | Epic |  | HVAC-APX (P) | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1981 | [5 empty] | 2026-03-25T14:06:12.887+0500 | 2026-04-22T14:54:47.076+0500
O2 | O2-1982 | O2-1982 | Story | Story |  | Kick-off meetings | To Do |  |  |  |  | 0 | 0 | Unassigned | 35.5 |  | O2-1981 | O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | [5 empty] | 2026-03-25T14:06:57.640+0500 | 2026-03-25T14:06:57.815+0500
O2 | O2-1983 | O2-1983 | Sub-task | Sub-task |  | Kick-off meetings (DR) | In-Progress |  |  | 2026-03-24 | 2026-03-27 | 0 | 0 | Danish Rashid | 16 |  | O2-1982 | O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1983 | [5 empty] | 2026-03-25T14:11:22.458+0500 | 2026-03-27T14:20:16.994+0500
O2 | O2-1984 | O2-1984 | Sub-task | Sub-task |  | Kick-off meetings (MAW) | Resolved! | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-03-25 | 10 | 10 | Muhammad Abdul Wasi | 8.5 |  | O2-1982 | O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1984 | [5 empty] | 2026-03-25T14:11:41.646+0500 | 2026-04-06T10:24:54.240+0500
O2 | O2-1985 | O2-1985 | Sub-task | Sub-task |  | Kick-off meetings (DA) | In-Progress | 2026-03-24 |  | 2026-03-24 | 2026-03-24 | 0 | 0 | DANIYAL AHMAD | 2 |  | O2-1982 | O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1985 | [5 empty] | 2026-03-25T14:12:03.134+0500 | 2026-03-25T15:05:20.967+0500
O2 | O2-1986 | O2-1986 | Sub-task | Sub-task |  | Module Design Synchronous (P) | To Do |  |  | 2026-03-10 | 2026-04-29 | 40 | 40 | DANIYAL AHMAD | 40 |  | O2-1029 | O2-1029 | https://octopusdtlsupport.atlassian.net/browse/O2-1029 | https://octopusdtlsupport.atlassian.net/browse/O2-1986 | [5 empty] | 2026-03-25T14:41:56.952+0500 | 2026-04-29T16:08:28.910+0500
O2 | O2-1987 | O2-1987 | Sub-task | Sub-task |  | Enhance Monitoring Logs for Batch/BPM Module to Include Variable Values | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-1920 | O2-1920 | https://octopusdtlsupport.atlassian.net/browse/O2-1920 | https://octopusdtlsupport.atlassian.net/browse/O2-1987 | [5 empty] | 2026-03-25T14:44:34.582+0500 | 2026-03-25T14:45:45.619+0500
O2 | O2-1989 | O2-1989 | Sub-task | Sub-task |  | Create Scheduled Trigger API -With AI | Resolved! | 2026-03-18 | 2026-03-26 | 2026-03-18 | 2026-03-18 | 4 | 4 | Faiza Nasir | 3.5 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1989 | [5 empty] | 2026-03-25T15:20:55.077+0500 | 2026-03-26T17:05:19.419+0500
O2 | O2-199 | O2-199 | Epic | Epic |  | Technical Support | In-Progress | 2026-01-01 | 2026-12-31 |  |  | 48 | 48 | Hassan Malik | 368 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-199 | [5 empty] | 2025-10-08T10:15:45.952+0500 | 2026-04-10T09:25:53.414+0500
O2 | O2-1990 | O2-1990 | Story | Story |  | Costs review and optimizations | Resolved! | 2026-03-16 | 2026-03-27 |  |  | 40 | 40 | Taimur Zahid | 14.5 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1990 | [5 empty] | 2026-03-25T15:28:59.045+0500 | 2026-04-27T12:04:40.219+0500
O2 | O2-1991 | O2-1991 | Epic | Epic |  | WhatIf Visual Screens (Pump, Comp,Cond,Hex, Boiler) II | In-Progress | 2026-04-06 | 2026-04-29 |  |  | 180 | 180 | Zain Munir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | [5 empty] | 2026-03-25T15:53:52.635+0500 | 2026-05-08T09:39:18.800+0500
O2 | O2-1992 | O2-1992 | Story | Story |  | Research | Resolved! | 2026-04-06 | 2026-04-10 |  |  | 21 | 21 | Zain Munir | 21 |  | O2-1991 | O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1992 | [5 empty] | 2026-03-25T15:55:06.776+0500 | 2026-04-13T09:45:50.233+0500
O2 | O2-1993 | O2-1993 | Story | Story |  | Development | Resolved! | 2026-04-13 | 2026-04-23 |  |  | 81.6 | 81.6 | Zain Munir | 64 |  | O2-1991 | O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | [5 empty] | 2026-03-25T15:55:45.594+0500 | 2026-04-27T12:37:25.076+0500
O2 | O2-1994 | O2-1994 | Story | Story |  | Handover Session | Resolved! | 2026-04-24 | 2026-04-24 |  |  | 0 | 0 | Zain Munir | 0 |  | O2-1991 | O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1994 | [5 empty] | 2026-03-25T15:56:26.447+0500 | 2026-05-08T09:39:52.393+0500
O2 | O2-1995 | O2-1995 | Story | Story |  | SQA | In-Progress | 2026-04-24 | 2026-04-28 |  |  | 24.8 | 24.8 | Muhammad Abbas | 8 |  | O2-1991 | O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1995 | [5 empty] | 2026-03-25T15:56:53.946+0500 | 2026-05-08T09:39:44.502+0500
O2 | O2-1996 | O2-1996 | Story | Story |  | Bugs Fixing | To Do |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-1991 | O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1996 | [5 empty] | 2026-03-25T15:57:24.291+0500 | 2026-03-25T15:57:24.428+0500
O2 | O2-1997 | O2-1997 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-1991 | O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1997 | [5 empty] | 2026-03-25T15:57:47.500+0500 | 2026-03-25T15:57:47.691+0500
O2 | O2-1998 | O2-1998 | Story | Story |  | Production Release | To Do | 2026-04-29 | 2026-04-29 |  |  | 24 | 24 | Ameer Hamza Khan | 0 |  | O2-1991 | O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | https://octopusdtlsupport.atlassian.net/browse/O2-1998 | [5 empty] | 2026-03-25T15:58:20.578+0500 | 2026-04-09T15:37:53.637+0500
O2 | O2-1999 | O2-1999 | Sub-task | Sub-task |  | Batch On Demand Integration | Resolved! | 2026-03-31 | 2026-04-02 | 2026-03-31 | 2026-04-02 | 24 | 24 | Syed Yousaf Qadri | 24 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1999 | [5 empty] | 2026-03-25T16:34:46.357+0500 | 2026-04-22T16:40:06.174+0500
O2 | O2-2 | O2-2 | Epic | Epic |  | Batch/BPM V4 – GitHub Integration | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 72 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2 | [5 empty] | 2025-10-02T13:16:47.442+0500 | 2026-02-19T11:08:33.161+0500
O2 | O2-20 | O2-20 | Story | Story |  | Development | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 228 |  | O2-10 | O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | [5 empty] | 2025-10-02T14:10:16.644+0500 | 2026-04-20T16:17:23.901+0500
O2 | O2-200 | O2-200 | Story | Story |  | Collaboration with Implementation team on Tapal Project | In-Progress |  |  |  |  | 0 | 0 | yousha.agha | 128 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-200 | [5 empty] | 2025-10-08T10:16:10.536+0500 | 2026-02-11T10:23:20.009+0500
O2 | O2-2000 | O2-2000 | Sub-task | Sub-task |  | Batch/BPM Trigger | Resolved! | 2026-03-26 | 2026-03-31 | 2026-03-26 | 2026-03-31 | 32 | 32 | Muhammad Abbas | 29.5 |  | O2-1438 | O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-2000 | [5 empty] | 2026-03-26T10:31:42.205+0500 | 2026-05-12T15:44:03.251+0500
O2 | O2-2001 | O2-2001 | Epic | Epic |  | OmniAgent - Charting | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | [5 empty] | 2026-03-26T12:24:02.299+0500 | 2026-04-15T10:32:01.337+0500
O2 | O2-2002 | O2-2002 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-2001 | O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2002 | [5 empty] | 2026-03-26T12:25:39.109+0500 | 2026-03-26T12:37:28.449+0500
O2 | O2-2003 | O2-2003 | Story | Story |  | Development | In-Progress |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 144.5 |  | O2-2001 | O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | [5 empty] | 2026-03-26T12:26:10.217+0500 | 2026-04-22T16:13:44.333+0500
O2 | O2-2004 | O2-2004 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-2001 | O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2004 | [5 empty] | 2026-03-26T12:26:28.612+0500 | 2026-03-26T12:36:58.784+0500
O2 | O2-2005 | O2-2005 | Epic | Epic |  | Read API - Analysis for SQL | Resolved! | 2026-03-25 | 2026-03-26 |  |  | 16 | 16 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2005 | [5 empty] | 2026-03-26T12:31:44.024+0500 | 2026-03-27T12:31:29.554+0500
O2 | O2-2006 | O2-2006 | Story | Story |  | Analysis | Resolved! | 2026-03-25 | 2026-03-26 |  |  | 16 | 16 | Aiza Hamid | 16 |  | O2-2005 | O2-2005 | https://octopusdtlsupport.atlassian.net/browse/O2-2005 | https://octopusdtlsupport.atlassian.net/browse/O2-2006 | [5 empty] | 2026-03-26T12:32:59.446+0500 | 2026-03-27T12:30:42.581+0500
O2 | O2-2007 | O2-2007 | Sub-task | Sub-task |  | Analysis for APX hits | Resolved! | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8 | 8 | Aiza Hamid | 8 |  | O2-2006 | O2-2006 | https://octopusdtlsupport.atlassian.net/browse/O2-2006 | https://octopusdtlsupport.atlassian.net/browse/O2-2007 | [5 empty] | 2026-03-26T12:33:19.338+0500 | 2026-03-26T12:37:34.360+0500
O2 | O2-2008 | O2-2008 | Sub-task | Sub-task |  | Analysis for Customer Hits | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8 | 8 | Aiza Hamid | 8 |  | O2-2006 | O2-2006 | https://octopusdtlsupport.atlassian.net/browse/O2-2006 | https://octopusdtlsupport.atlassian.net/browse/O2-2008 | [5 empty] | 2026-03-26T12:33:34.886+0500 | 2026-03-27T12:30:32.475+0500
O2 | O2-2009 | O2-2009 | Story | Story |  | Research | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-2001 | O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2009 | [5 empty] | 2026-03-26T12:35:37.228+0500 | 2026-03-26T12:37:04.750+0500
O2 | O2-201 | O2-201 | Bug Subtask | Bug Subtask |  | Blocker: IOT HUB status is still in Progress. | Resolved |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-201 | [5 empty] | 2025-10-08T10:21:42.181+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2010 | O2-2010 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-2001 | O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2010 | [5 empty] | 2026-03-26T12:36:01.096+0500 | 2026-03-26T12:37:09.810+0500
O2 | O2-2011 | O2-2011 | Story | Story |  | Read API Support | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | O2-2001 | O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2011 | [5 empty] | 2026-03-26T12:36:26.489+0500 | 2026-03-26T12:37:15.715+0500
O2 | O2-2012 | O2-2012 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-2001 | O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2001 | https://octopusdtlsupport.atlassian.net/browse/O2-2012 | [5 empty] | 2026-03-26T12:36:40.061+0500 | 2026-03-26T12:37:23.317+0500
O2 | O2-2013 | O2-2013 | Sub-task | Sub-task |  | Re-Develop Create Trigger API | Resolved! | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 8 | 8 | Faiza Nasir | 7 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2013 | [5 empty] | 2026-03-26T12:41:03.375+0500 | 2026-03-30T10:26:48.020+0500
O2 | O2-2014 | O2-2014 | Sub-task | Sub-task |  | Modify Create Apis | Resolved! | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 5 | 5 | Faiza Nasir | 4 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2014 | [5 empty] | 2026-03-26T12:42:11.310+0500 | 2026-03-31T12:37:48.781+0500
O2 | O2-2016 | O2-2016 | Story | Story |  | Research | In-Progress | 2026-03-30 | 2026-03-30 |  |  | 240 | 240 | Mohsin Junaid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2016 | [5 empty] | 2026-03-26T12:46:17.526+0500 | 2026-03-26T12:48:54.281+0500
O2 | O2-2017 | O2-2017 | Sub-task | Sub-task |  | Create hello world function app and app service on seperate ASPs and analyze utilization of asp | Resolved! | 2026-03-30 | 2026-03-31 |  |  | 8 | 8 | Ayyan Babar | 0 |  | O2-2016 | O2-2016 | https://octopusdtlsupport.atlassian.net/browse/O2-2016 | https://octopusdtlsupport.atlassian.net/browse/O2-2017 | [5 empty] | 2026-03-26T12:47:13.062+0500 | 2026-04-08T11:19:55.749+0500
O2 | O2-2019 | O2-2019 | Sub-task | Sub-task |  | Code Understanding | Resolved! | 2026-03-18 | 2026-03-25 | 2026-03-18 | 2026-03-24 | 6 | 6 | Faiza Nasir | 6 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2019 | [5 empty] | 2026-03-26T16:51:37.394+0500 | 2026-04-06T10:56:29.723+0500
O2 | O2-202 | O2-202 | Bug Subtask | Bug Subtask |  | Un-necessary space is showing on Create and Edit Customer modal | Resolved | 2025-10-08 | 2025-10-08 |  |  | 0 | 0 | Ali Qumail | 2 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-202 | [5 empty] | 2025-10-08T10:28:20.596+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2020 | O2-2020 | Story | Story |  | Research | In-Progress | 2026-03-09 | 2026-03-10 |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-1783 | O2-1783 | https://octopusdtlsupport.atlassian.net/browse/O2-1783 | https://octopusdtlsupport.atlassian.net/browse/O2-2020 | [5 empty] | 2026-03-27T11:01:52.709+0500 | 2026-03-27T11:04:33.156+0500
O2 | O2-2021 | O2-2021 | Sub-task | Sub-task |  | hello world of function apps and app service on azure app service plan | Resolved! | 2026-03-30 |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2020 | O2-2020 | https://octopusdtlsupport.atlassian.net/browse/O2-2020 | https://octopusdtlsupport.atlassian.net/browse/O2-2021 | [5 empty] | 2026-03-27T11:03:21.250+0500 | 2026-04-08T11:20:01.452+0500
O2 | O2-2022 | O2-2022 | Story | Story |  | Bug Fixing | Resolved! |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 35 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | [5 empty] | 2026-03-27T11:04:59.464+0500 | 2026-04-17T10:06:31.021+0500
O2 | O2-2023 | O2-2023 | Sub-task | Sub-task |  | Started Backend + Research on Code | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 5.5 | 5.5 | Muhammad Ahmad Saleem | 5.5 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2023 | [5 empty] | 2026-03-27T11:46:38.530+0500 | 2026-03-27T11:48:22.481+0500
O2 | O2-2024 | O2-2024 | Sub-task | Sub-task |  | Completed Backend(Responses + Request) Model | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2024 | [5 empty] | 2026-03-27T11:56:36.734+0500 | 2026-03-27T11:57:45.535+0500
O2 | O2-2025 | O2-2025 | Story | Story |  | SAP Testing (Ticket created by implementation team) | Resolved! | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 8 | 8 | kamran khalid | 24 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2025 | [5 empty] | 2026-03-27T15:12:59.233+0500 | 2026-04-08T12:23:45.089+0500
O2 | O2-2026 | O2-2026 | Sub-task | Sub-task |  | Testing By Kamran | In-Progress | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 16 | 16 | kamran khalid | 16 |  | O2-2025 | O2-2025 | https://octopusdtlsupport.atlassian.net/browse/O2-2025 | https://octopusdtlsupport.atlassian.net/browse/O2-2026 | [5 empty] | 2026-03-27T15:13:44.199+0500 | 2026-03-27T16:33:56.375+0500
O2 | O2-2028 | O2-2028 | Sub-task | Sub-task |  | Get all triggers API | Resolved! | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 6 | 6 | Faiza Nasir | 6 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2028 | [5 empty] | 2026-03-30T10:21:05.298+0500 | 2026-04-06T10:55:13.758+0500
O2 | O2-2029 | O2-2029 | Sub-task | Sub-task |  | Fixes, while API integrations | Resolved! | 2026-03-27 | 2026-03-31 | 2026-03-27 | 2026-03-27 | 2 | 2 | Faiza Nasir | 2 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2029 | [5 empty] | 2026-03-30T10:29:35.556+0500 | 2026-03-31T12:38:10.670+0500
O2 | O2-203 | O2-203 | Sub-task | Sub-task |  | Understanding The URS | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 12 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-203 | [5 empty] | 2025-10-08T10:29:08.832+0500 | 2025-10-13T10:31:30.603+0500
O2 | O2-2031 | O2-2031 | Bug Subtask | Bug Subtask |  | Cloned BPM Jobs Showing “Pending” Status on Monitoring Page | Bug Fixed | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | Arslan sohail | 8 |  | O2-1920 | O2-1920 | https://octopusdtlsupport.atlassian.net/browse/O2-1920 | https://octopusdtlsupport.atlassian.net/browse/O2-2031 | [5 empty] | 2026-03-30T14:16:09.930+0500 | 2026-04-20T16:09:18.202+0500
O2 | O2-2032 | O2-2032 | Sub-task | Sub-task |  | Integrated Chart logic Frontend | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2032 | [5 empty] | 2026-03-30T15:30:47.537+0500 | 2026-03-30T15:33:22.598+0500
O2 | O2-2033 | O2-2033 | Sub-task | Sub-task |  | UI Changes + Completed Integration of Charts logic | Resolved! | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2033 | [5 empty] | 2026-03-30T15:33:59.427+0500 | 2026-03-30T15:35:08.569+0500
O2 | O2-2034 | O2-2034 | Epic | Epic |  | SUPPORT-tapal edge trouble shooting | To Do | 2026-03-23 | 2026-04-27 |  |  | 80 | 80 | Mohsin Junaid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2034 | [5 empty] | 2026-03-30T16:52:52.988+0500 | 2026-03-30T16:55:48.983+0500
O2 | O2-2035 | O2-2035 | Story | Story |  | Bug Fixing | In-Progress | 2026-03-23 | 2026-04-27 |  |  | 80 | 80 | Mohsin Junaid | 48 |  | O2-2034 | O2-2034 | https://octopusdtlsupport.atlassian.net/browse/O2-2034 | https://octopusdtlsupport.atlassian.net/browse/O2-2035 | [5 empty] | 2026-03-30T16:55:12.448+0500 | 2026-03-30T16:56:59.866+0500
O2 | O2-2036 | O2-2036 | Sub-task | Sub-task |  | support table edge trouble shooting - bug fixing - trouble shooting | In-Progress | 2026-03-30 | 2026-04-02 | 2026-03-27 | 2026-04-03 | 40 | 40 | Mohsin Junaid | 48 |  | O2-2035 | O2-2035 | https://octopusdtlsupport.atlassian.net/browse/O2-2035 | https://octopusdtlsupport.atlassian.net/browse/O2-2036 | [5 empty] | 2026-03-30T16:56:10.399+0500 | 2026-04-06T10:42:44.098+0500
O2 | O2-2037 | O2-2037 | Sub-task | Sub-task |  | troubleshoot edge | To Do |  |  |  |  | 0 | 0 | Usama Tariq | 0 |  | O2-2035 | O2-2035 | https://octopusdtlsupport.atlassian.net/browse/O2-2035 | https://octopusdtlsupport.atlassian.net/browse/O2-2037 | [5 empty] | 2026-03-30T16:56:37.687+0500 | 2026-03-30T16:56:54.774+0500
O2 | O2-2038 | O2-2038 | Story | Story |  | OC_Training To Avanceon | Resolved! | 2026-03-30 | 2026-04-03 |  |  | 7 | 7 | Muhammad Abbas | 3 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2038 | [5 empty] | 2026-03-30T17:26:19.470+0500 | 2026-04-08T12:23:39.702+0500
O2 | O2-2039 | O2-2039 | Sub-task | Sub-task |  | Training By Abbas | Resolved! | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 3 | 3 | Muhammad Abbas | 3 |  | O2-2038 | O2-2038 | https://octopusdtlsupport.atlassian.net/browse/O2-2038 | https://octopusdtlsupport.atlassian.net/browse/O2-2039 | [5 empty] | 2026-03-30T17:27:18.873+0500 | 2026-05-12T15:51:49.319+0500
O2 | O2-204 | O2-204 | Bug Subtask | Bug Subtask |  | When user click on edit icon of Subscription/Demo site, then Publish Changes button is showing in side navigation bar | Resolved | 2025-10-15 | 2025-10-15 |  |  | 2 | 2 | Ali Qumail | 2 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-204 | [5 empty] | 2025-10-08T10:33:27.331+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2040 | O2-2040 | Bug Subtask | Bug Subtask |  | End Date is not working on when specified on Trigger while creating a trigger as it does not stopped on the date specified | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2025 | O2-2025 | https://octopusdtlsupport.atlassian.net/browse/O2-2025 | https://octopusdtlsupport.atlassian.net/browse/O2-2040 | [5 empty] | 2026-03-30T18:10:19.057+0500 | 2026-03-30T18:12:06.338+0500
O2 | O2-2041 | O2-2041 | Bug Subtask | Bug Subtask |  | validation update in Validate button on entering Complex Query while creating sap HANA and ODBC Connector | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2025 | O2-2025 | https://octopusdtlsupport.atlassian.net/browse/O2-2025 | https://octopusdtlsupport.atlassian.net/browse/O2-2041 | [5 empty] | 2026-03-30T18:14:55.694+0500 | 2026-03-30T18:15:57.117+0500
O2 | O2-2042 | O2-2042 | Sub-task | Sub-task |  | OmniConnect Testing Automation Learning Coding | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8 | 8 | Muhammad Imran Aslam | 8 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-2042 | [5 empty] | 2026-03-31T12:31:02.398+0500 | 2026-04-09T16:48:01.109+0500
O2 | O2-2043 | O2-2043 | Sub-task | Sub-task |  | Production Blue Environment | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3 | 3 | Faiza Nasir | 3 |  | O2-520 | O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-520 | https://octopusdtlsupport.atlassian.net/browse/O2-2043 | [5 empty] | 2026-03-31T12:35:56.392+0500 | 2026-04-07T14:20:10.882+0500
O2 | O2-2044 | O2-2044 | Sub-task | Sub-task |  | OmniConnect Testing Automation Learning Coding | Resolved! | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8 | 8 | Muhammad Imran Aslam | 8 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-2044 | [5 empty] | 2026-03-31T14:32:25.457+0500 | 2026-04-16T12:06:50.128+0500
O2 | O2-2045 | O2-2045 | Bug Subtask | Bug Subtask |  | When querying “how many total areas/assets are in this site (with names)”, the OmniAgent Data Analysis module returns only one area/asset and does not display the complete list or count. | Bug Fixed | 2026-03-31 |  | 2026-04-06 | 2026-04-06 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2045 | [5 empty] | 2026-03-31T14:35:46.305+0500 | 2026-04-22T15:43:48.675+0500
O2 | O2-2046 | O2-2046 | Sub-task | Sub-task |  | OmniConnect Testing Automation Learning Coding | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 8 | 8 | Muhammad Imran Aslam | 8 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-2046 | [5 empty] | 2026-03-31T14:48:36.747+0500 | 2026-04-23T11:24:15.579+0500
O2 | O2-2047 | O2-2047 | Bug Subtask | Bug Subtask |  | Omni Agent fail to answer this question Which machine experienced the most downtime and how long did it last? | Bug Fixed |  |  | 2026-03-31 | 2026-03-31 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2047 | [5 empty] | 2026-03-31T14:56:30.391+0500 | 2026-04-22T15:38:36.622+0500
O2 | O2-2048 | O2-2048 | Bug Subtask | Bug Subtask |  | Bug: Instead of devices name omni agent is returning asset names | On Hold | 2026-03-31 |  | 2026-03-31 | 2026-03-31 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2048 | [5 empty] | 2026-03-31T15:12:37.526+0500 | 2026-04-22T15:37:28.767+0500
O2 | O2-2049 | O2-2049 | Bug Subtask | Bug Subtask |  | Bug: Omni Agent showing zero tag incase deadband and persistence | Bug Fixed |  |  | 2026-03-31 | 2026-04-02 | 0 | 0 | Hassan Saeed Wattoo | 8 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2049 | [5 empty] | 2026-03-31T15:22:52.407+0500 | 2026-04-06T16:53:21.102+0500
O2 | O2-2050 | O2-2050 | Bug Subtask | Bug Subtask |  | Bug: Omni Agent is not fetching only acknowledge alarm | Development |  |  | 2026-03-31 | 2026-03-31 | 0 | 0 | Hassan Saeed Wattoo | 3 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2050 | [5 empty] | 2026-03-31T15:27:06.552+0500 | 2026-04-02T10:08:20.743+0500
O2 | O2-2051 | O2-2051 | Bug Subtask | Bug Subtask |  | Bug: Omni Agent fail to fetch suppress alarms name, and Omni Agent fail to fetch suppress time duration of tag alarm | Bug Fixed | 2026-03-31 |  | 2026-03-31 | 2026-04-07 | 0 | 0 | Hassan Saeed Wattoo | 5 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2051 | [5 empty] | 2026-03-31T15:32:59.757+0500 | 2026-04-08T10:24:57.459+0500
O2 | O2-2053 | O2-2053 | Bug Subtask | Bug Subtask |  | Incorrect asset types displayed in OmniAgent query response | Bug Fixed | 2026-03-31 |  | 2026-04-06 | 2026-04-06 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2053 | [5 empty] | 2026-03-31T15:49:42.065+0500 | 2026-04-22T15:36:36.419+0500
O2 | O2-2054 | O2-2054 | Sub-task | Sub-task |  | OmniConnect Testing Automation Learning Coding | Resolved! | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 8 | 8 | Muhammad Imran Aslam | 8 |  | O2-1967 | O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-1967 | https://octopusdtlsupport.atlassian.net/browse/O2-2054 | [5 empty] | 2026-03-31T16:20:30.700+0500 | 2026-04-30T15:54:06.436+0500
O2 | O2-2055 | O2-2055 | Sub-task | Sub-task |  | Fixed issues on Frontend and backend | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2055 | [5 empty] | 2026-04-01T09:14:29.170+0500 | 2026-04-01T09:15:52.687+0500
O2 | O2-2056 | O2-2056 | Sub-task | Sub-task |  | Integrated OmniAgent Charts and Refresh Site API | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2056 | [5 empty] | 2026-04-01T09:16:40.861+0500 | 2026-04-01T09:17:50.964+0500
O2 | O2-2057 | O2-2057 | Story | Story |  | Initial Research | To Do |  |  |  |  | 0 | 0 | Unassigned | 48 |  | O2-1981 | O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-2057 | [5 empty] | 2026-04-01T09:40:28.166+0500 | 2026-04-14T11:23:44.919+0500
O2 | O2-2058 | O2-2058 | Sub-task | Sub-task |  | Initial Research (DR) | To Do |  |  | 2026-03-30 | 2026-04-07 | 0 | 0 | Unassigned | 24 |  | O2-2057 | O2-2057 | https://octopusdtlsupport.atlassian.net/browse/O2-2057 | https://octopusdtlsupport.atlassian.net/browse/O2-2058 | [5 empty] | 2026-04-01T09:40:52.332+0500 | 2026-04-14T11:23:27.684+0500
O2 | O2-2059 | O2-2059 | Sub-task | Sub-task |  | Removing trigger fields from Export to SQL | Resolved! | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 4 | 4 | Sarmad Sabir | 4 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2059 | [5 empty] | 2026-04-01T09:50:25.945+0500 | 2026-04-01T09:56:27.528+0500
O2 | O2-206 | O2-206 | Sub-task | Sub-task |  | Moving Read API Configurations to Environment Variables | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 40 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-206 | [5 empty] | 2025-10-08T11:02:35.902+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-2060 | O2-2060 | Sub-task | Sub-task |  | Creating a new triggers page for Export to SQL | Resolved! | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 16 | 16 | Sarmad Sabir | 12 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2060 | [5 empty] | 2026-04-01T09:50:49.701+0500 | 2026-04-01T09:57:12.984+0500
O2 | O2-2061 | O2-2061 | Sub-task | Sub-task |  | Integrating NEW APIs for Triggers page | Resolved! | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 16 | 16 | Sarmad Sabir | 8 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2061 | [5 empty] | 2026-04-01T09:54:41.408+0500 | 2026-04-06T10:00:34.744+0500
O2 | O2-2062 | O2-2062 | Sub-task | Sub-task |  | Template Optimizations | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4 | 4 | Muhammad Abdul Wasi | 4 |  | O2-467 | O2-467 | https://octopusdtlsupport.atlassian.net/browse/O2-467 | https://octopusdtlsupport.atlassian.net/browse/O2-2062 | [5 empty] | 2026-04-01T10:14:16.094+0500 | 2026-04-01T10:16:29.050+0500
O2 | O2-2063 | O2-2063 | Bug Subtask | Bug Subtask |  | Deleted chats reappear after navigation or logout in OmniAgent | Bug Fixed | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2 | 2 | Muhammad Ahmad Saleem | 2 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2063 | [5 empty] | 2026-04-01T10:54:59.662+0500 | 2026-04-14T12:04:34.672+0500
O2 | O2-2064 | O2-2064 | Bug Subtask | Bug Subtask |  | Timer tag value not retrieved; schema error shown instead of value and timestamp | Bug Fixed | 2026-04-01 |  | 2026-04-03 | 2026-04-03 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2064 | [5 empty] | 2026-04-01T14:15:50.073+0500 | 2026-04-22T15:35:47.336+0500
O2 | O2-2065 | O2-2065 | Bug Subtask | Bug Subtask |  | Duplicate information displayed in OmniAgent response (text + scrollable error) | Bug Fixed | 2026-04-01 |  | 2026-04-03 | 2026-04-03 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2065 | [5 empty] | 2026-04-01T15:03:16.685+0500 | 2026-04-22T15:34:52.578+0500
O2 | O2-2066 | O2-2066 | Bug Subtask | Bug Subtask |  | Not showing complete data for all tags and incorrect missing tags list on re-query | Bug Fixed | 2026-04-01 |  | 2026-04-01 | 2026-04-01 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2066 | [5 empty] | 2026-04-01T15:44:33.221+0500 | 2026-04-22T15:33:55.149+0500
O2 | O2-2067 | O2-2067 | Sub-task | Sub-task |  | Template Optimizations | Resolved! | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-01 | 8 | 8 | Muhammad Abdul Wasi | 8 |  | O2-467 | O2-467 | https://octopusdtlsupport.atlassian.net/browse/O2-467 | https://octopusdtlsupport.atlassian.net/browse/O2-2067 | [5 empty] | 2026-04-02T09:59:05.201+0500 | 2026-04-02T10:00:26.249+0500
O2 | O2-2068 | O2-2068 | Story | Story |  | Development | Resolved! | 2026-03-30 | 2026-04-07 |  |  | 40 | 40 | Faiza Nasir | 32.5 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | [5 empty] | 2026-04-02T11:26:08.218+0500 | 2026-04-28T09:59:13.281+0500
O2 | O2-2069 | O2-2069 | Bug Subtask | Bug Subtask |  | Publish Changes version is not getting updated | Resolved | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2 | 2 | Ameer Hamza Khan | 2 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2069 | [5 empty] | 2026-04-02T11:49:02.524+0500 | 2026-04-02T14:57:51.052+0500
O2 | O2-207 | O2-207 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | Resolved! |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-207 | [5 empty] | 2025-10-08T11:02:52.382+0500 | 2026-02-26T10:21:05.463+0500
O2 | O2-2070 | O2-2070 | Sub-task | Sub-task |  | OC Process testing (P) - DA | To Do |  |  | 2026-03-26 | 2026-03-27 | 12 | 12 | DANIYAL AHMAD | 10 |  | O2-423 | O2-423 | https://octopusdtlsupport.atlassian.net/browse/O2-423 | https://octopusdtlsupport.atlassian.net/browse/O2-2070 | [5 empty] | 2026-04-02T11:52:32.109+0500 | 2026-04-02T11:53:52.802+0500
O2 | O2-2071 | O2-2071 | Sub-task | Sub-task |  | Data Prep. & Offline testing - Sync Motor | To Do | 2026-03-27 | 2026-04-30 | 2026-03-27 | 2026-04-30 | 40 | 40 | DANIYAL AHMAD | 35.5 |  | O2-1032 | O2-1032 | https://octopusdtlsupport.atlassian.net/browse/O2-1032 | https://octopusdtlsupport.atlassian.net/browse/O2-2071 | [5 empty] | 2026-04-02T11:55:38.794+0500 | 2026-05-04T16:51:47.054+0500
O2 | O2-2072 | O2-2072 | Sub-task | Sub-task |  | ADE Enhancement rev 3.0 - March | Resolved! | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 12 | 12 | DANIYAL AHMAD | 12 |  | O2-497 | O2-497 | https://octopusdtlsupport.atlassian.net/browse/O2-497 | https://octopusdtlsupport.atlassian.net/browse/O2-2072 | [5 empty] | 2026-04-02T11:58:56.723+0500 | 2026-04-02T12:00:48.795+0500
O2 | O2-2073 | O2-2073 | Sub-task | Sub-task |  | ADE Enhancement rev 3.0 - April | In-Progress | 2026-04-01 | 2026-04-10 | 2026-04-01 | 2026-04-06 | 32 | 32 | DANIYAL AHMAD | 28 |  | O2-497 | O2-497 | https://octopusdtlsupport.atlassian.net/browse/O2-497 | https://octopusdtlsupport.atlassian.net/browse/O2-2073 | [5 empty] | 2026-04-02T11:59:08.964+0500 | 2026-04-08T09:38:03.011+0500
O2 | O2-2074 | O2-2074 | Sub-task | Sub-task |  | Kick-off working | Resolved! |  |  | 2026-03-24 | 2026-03-26 | 10 | 10 | Mariam Zulfiqar | 9 |  | O2-1982 | O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-2074 | [5 empty] | 2026-04-02T12:05:53.816+0500 | 2026-04-02T12:38:58.309+0500
O2 | O2-2075 | O2-2075 | Bug Subtask | Bug Subtask |  | Duplicate tags created on single tag creation and reflected in Latest Values screen | Not a Bug | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 1 | 1 | Ameer Hamza Khan | 1 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2075 | [5 empty] | 2026-04-02T12:34:43.770+0500 | 2026-04-02T13:19:24.887+0500
O2 | O2-2076 | O2-2076 | Sub-task | Sub-task |  | Set up Start And End Pull time for each trigger | Resolved! | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-02 | 6 | 6 | Faiza Nasir | 6 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2076 | [5 empty] | 2026-04-02T12:42:27.635+0500 | 2026-04-02T15:20:32.433+0500
O2 | O2-2077 | O2-2077 | Sub-task | Sub-task |  | Requirements gathering and finalizing | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Ameer Hamza Khan | 8 |  | O2-60 | O2-60 | https://octopusdtlsupport.atlassian.net/browse/O2-60 | https://octopusdtlsupport.atlassian.net/browse/O2-2077 | [5 empty] | 2026-04-02T13:02:43.026+0500 | 2026-04-09T11:13:39.296+0500
O2 | O2-2078 | O2-2078 | Sub-task | Sub-task |  | Update Health Activation API | Resolved! | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 7 | 7 | Faiza Nasir | 7 |  | O2-2068 | O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2078 | [5 empty] | 2026-04-02T13:11:00.992+0500 | 2026-04-02T13:13:18.157+0500
O2 | O2-2079 | O2-2079 | Sub-task | Sub-task |  | Update all Status Check APIs | Resolved! | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-01 | 8 | 8 | Faiza Nasir | 8 |  | O2-2068 | O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2079 | [5 empty] | 2026-04-02T13:11:31.694+0500 | 2026-04-08T12:13:11.298+0500
O2 | O2-208 | O2-208 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | Resolved! |  |  |  |  | 0 | 0 | Hamza Ali | 8 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-208 | [5 empty] | 2025-10-08T11:03:06.829+0500 | 2025-11-13T19:05:52.687+0500
O2 | O2-2080 | O2-2080 | Sub-task | Sub-task |  | Update Health Model Creation Request API | Resolved! | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 0 | 0 | Faiza Nasir | 6 |  | O2-2068 | O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2080 | [5 empty] | 2026-04-02T13:12:04.127+0500 | 2026-04-08T10:27:26.081+0500
O2 | O2-2081 | O2-2081 | Bug Subtask | Bug Subtask |  | OmniAgent fails to detect configured and fired Statistical Alarms | Bug Fixed | 2026-04-02 |  | 2026-04-02 | 2026-04-02 | 0 | 0 | Unassigned | 6 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2081 | [5 empty] | 2026-04-02T14:48:15.685+0500 | 2026-04-06T17:41:49.463+0500
O2 | O2-2082 | O2-2082 | Bug Subtask | Bug Subtask |  | OmniAgent gets stuck on “Please wait for response” after network interruption and does not recover | Bug Fixed | 2026-04-02 |  | 2026-04-02 | 2026-04-02 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-2022 | O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2022 | https://octopusdtlsupport.atlassian.net/browse/O2-2082 | [5 empty] | 2026-04-02T15:20:09.757+0500 | 2026-04-22T15:32:45.703+0500
O2 | O2-2083 | O2-2083 | Sub-task | Sub-task |  | Fixed Refresh Site issue + UI issue | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2083 | [5 empty] | 2026-04-02T16:38:25.217+0500 | 2026-04-02T16:39:47.546+0500
O2 | O2-2084 | O2-2084 | Story | Story |  | Sanity_Testing_4/3/26(Staging) | Resolved! | 2026-04-03 | 2026-04-03 |  |  | 32 | 32 | Muhammad Abbas | 70 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | [5 empty] | 2026-04-03T10:36:56.264+0500 | 2026-04-07T08:38:26.606+0500
O2 | O2-2085 | O2-2085 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-06 | 8 | 8 | kamran khalid | 18 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2085 | [5 empty] | 2026-04-03T10:37:40.863+0500 | 2026-05-12T14:56:56.297+0500
O2 | O2-2086 | O2-2086 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-06 | 8 | 8 | Waqar Rasheed | 16 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2086 | [5 empty] | 2026-04-03T10:37:49.768+0500 | 2026-04-06T16:50:42.681+0500
O2 | O2-2087 | O2-2087 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-04-03 | 2026-04-06 | 2026-04-03 | 2026-04-06 | 16 | 16 | Namra Zahid | 16 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2087 | [5 empty] | 2026-04-03T10:37:58.064+0500 | 2026-05-12T15:57:59.554+0500
O2 | O2-2088 | O2-2088 | Sub-task | Sub-task |  | Testing By Abbas | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-06 | 8 | 8 | Muhammad Abbas | 16 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2088 | [5 empty] | 2026-04-03T10:38:12.597+0500 | 2026-04-07T08:38:18.520+0500
O2 | O2-209 | O2-209 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 16 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-209 | [5 empty] | 2025-10-08T11:03:18.743+0500 | 2025-12-01T10:13:58.613+0500
O2 | O2-2090 | O2-2090 | Bug Subtask | Bug Subtask |  | Latest Values are not populating for real tags on Staging. | Resolved | 2026-04-03 |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2090 | [5 empty] | 2026-04-03T10:55:33.079+0500 | 2026-04-06T16:39:49.012+0500
O2 | O2-2092 | O2-2092 | Sub-task | Sub-task |  | Update Create trigger api, Check for unique names only | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 1 | 1 | Faiza Nasir | 1 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2092 | [5 empty] | 2026-04-03T11:56:15.235+0500 | 2026-04-03T11:59:25.842+0500
O2 | O2-2093 | O2-2093 | Sub-task | Sub-task |  | modify get trigger api, bring trigger name and is enabled | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 3 | 3 | Faiza Nasir | 3 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2093 | [5 empty] | 2026-04-03T11:56:37.223+0500 | 2026-04-08T12:15:08.434+0500
O2 | O2-2094 | O2-2094 | Bug Subtask | Bug Subtask |  | Version is not getting updated again. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2094 | [5 empty] | 2026-04-03T15:52:32.529+0500 | 2026-04-03T15:52:56.308+0500
O2 | O2-2095 | O2-2095 | Sub-task | Sub-task |  | Testing Module + Deployed to staging | Resolved! | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2095 | [5 empty] | 2026-04-03T16:59:58.564+0500 | 2026-04-03T17:01:02.676+0500
O2 | O2-2096 | O2-2096 | Sub-task | Sub-task |  | Initial Research (FB) | To Do |  |  | 2026-04-01 | 2026-04-03 | 0 | 0 | Faiq Butt | 24 |  | O2-2057 | O2-2057 | https://octopusdtlsupport.atlassian.net/browse/O2-2057 | https://octopusdtlsupport.atlassian.net/browse/O2-2096 | [5 empty] | 2026-04-06T09:15:05.775+0500 | 2026-04-06T09:15:59.508+0500
O2 | O2-2097 | O2-2097 | Sub-task | Sub-task |  | Kick-off meetings (FB) | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-1982 | O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-1982 | https://octopusdtlsupport.atlassian.net/browse/O2-2097 | [5 empty] | 2026-04-06T09:21:43.988+0500 | 2026-04-06T09:21:44.202+0500
O2 | O2-2098 | O2-2098 | Sub-task | Sub-task |  | OmniOEE Method Selection & Formulae Setup (P) | Resolved! | 2026-04-06 | 2026-04-30 | 2026-04-17 | 2026-04-28 | 24 | 24 | Muhammad Abdul Wasi | 24 |  | O2-1855 | O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-2098 | [5 empty] | 2026-04-06T09:30:45.459+0500 | 2026-05-05T10:55:03.574+0500
O2 | O2-2099 | O2-2099 | Sub-task | Sub-task |  | QA Testing (P) | Resolved! | 2026-04-02 | 2026-04-17 | 2026-04-02 | 2026-04-08 | 40 | 40 | Muhammad Abdul Wasi | 39 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2099 | [5 empty] | 2026-04-06T09:37:49.722+0500 | 2026-04-17T10:43:13.369+0500
O2 | O2-21 | O2-21 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-10 | O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-21 | [5 empty] | 2025-10-02T14:10:28.698+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-210 | O2-210 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | Resolved! |  |  |  |  | 0 | 0 | Ayyan Babar | 8 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-210 | [5 empty] | 2025-10-08T11:03:33.248+0500 | 2025-11-13T19:05:53.116+0500
O2 | O2-2100 | O2-2100 | Sub-task | Sub-task |  | API Changes for Triggers | Resolved! | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | 16 | 16 | Sarmad Sabir | 12 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2100 | [5 empty] | 2026-04-06T10:01:11.234+0500 | 2026-04-06T10:02:58.993+0500
O2 | O2-2101 | O2-2101 | Sub-task | Sub-task |  | Bug Fixes Dev Side | Resolved! | 2026-04-03 | 2026-04-06 | 2026-04-02 | 2026-04-06 | 24 | 24 | Sarmad Sabir | 20 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2101 | [5 empty] | 2026-04-06T10:01:38.498+0500 | 2026-04-08T12:10:00.447+0500
O2 | O2-2102 | O2-2102 | Sub-task | Sub-task |  | Research on Adding the Image Support to HTML Template | Resolved! | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-07 | 13 | 13 | Zain Munir | 13 |  | O2-1992 | O2-1992 | https://octopusdtlsupport.atlassian.net/browse/O2-1992 | https://octopusdtlsupport.atlassian.net/browse/O2-2102 | [5 empty] | 2026-04-06T10:18:18.177+0500 | 2026-04-10T10:55:25.946+0500
O2 | O2-2103 | O2-2103 | Bug Subtask | Bug Subtask |  | Anomaly Group Model is not getting created. | Resolved | 2026-04-06 |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2103 | [5 empty] | 2026-04-06T10:23:44.691+0500 | 2026-04-13T10:11:52.550+0500
O2 | O2-2104 | O2-2104 | Sub-task | Sub-task |  | fixing issues | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2104 | [5 empty] | 2026-04-06T10:40:46.056+0500 | 2026-04-06T10:41:38.697+0500
O2 | O2-2105 | O2-2105 | Epic | Epic |  | Read API - Rounding off the value | In-Progress | 2026-04-03 | 2026-04-07 |  |  | 24 | 24 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2105 | [5 empty] | 2026-04-06T10:46:46.401+0500 | 2026-04-22T13:36:20.760+0500
O2 | O2-2107 | O2-2107 | Sub-task | Sub-task |  | Overview code to incorporate requirements | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3 | 3 | Faiza Nasir | 3 |  | O2-2068 | O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2107 | [5 empty] | 2026-04-06T10:51:50.875+0500 | 2026-04-06T10:53:33.860+0500
O2 | O2-211 | O2-211 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | To Do |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 8 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-211 | [5 empty] | 2025-10-08T11:03:43.446+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-2111 | O2-2111 | Story | Story |  | Development | Resolved! | 2026-04-03 | 2026-04-07 |  |  | 24 | 24 | Aiza Hamid | 12 |  | O2-2105 | O2-2105 | https://octopusdtlsupport.atlassian.net/browse/O2-2105 | https://octopusdtlsupport.atlassian.net/browse/O2-2111 | [5 empty] | 2026-04-06T10:56:56.561+0500 | 2026-04-20T12:44:33.583+0500
O2 | O2-2112 | O2-2112 | Story | Story |  | SQA | Resolved! | 2026-04-16 | 2026-04-16 |  |  | 8 | 8 | Muhammad Abbas | 8 |  | O2-2105 | O2-2105 | https://octopusdtlsupport.atlassian.net/browse/O2-2105 | https://octopusdtlsupport.atlassian.net/browse/O2-2112 | [5 empty] | 2026-04-06T10:57:36.708+0500 | 2026-04-20T15:13:57.909+0500
O2 | O2-2113 | O2-2113 | Story | Story |  | Production | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | O2-2105 | O2-2105 | https://octopusdtlsupport.atlassian.net/browse/O2-2105 | https://octopusdtlsupport.atlassian.net/browse/O2-2113 | [5 empty] | 2026-04-06T10:58:54.297+0500 | 2026-04-06T10:59:21.431+0500
O2 | O2-2114 | O2-2114 | Sub-task | Sub-task |  | Dev | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | O2-2113 | O2-2113 | https://octopusdtlsupport.atlassian.net/browse/O2-2113 | https://octopusdtlsupport.atlassian.net/browse/O2-2114 | [5 empty] | 2026-04-06T11:00:14.851+0500 | 2026-04-06T11:00:39.293+0500
O2 | O2-2115 | O2-2115 | Sub-task | Sub-task |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-2113 | O2-2113 | https://octopusdtlsupport.atlassian.net/browse/O2-2113 | https://octopusdtlsupport.atlassian.net/browse/O2-2115 | [5 empty] | 2026-04-06T11:00:41.272+0500 | 2026-04-06T11:00:48.877+0500
O2 | O2-2116 | O2-2116 | Sub-task | Sub-task |  | Added feature to round off the value in Read API | Resolved! | 2026-04-03 | 2026-04-07 | 2026-04-03 | 2026-04-07 | 16 | 16 | Aiza Hamid | 12 |  | O2-2111 | O2-2111 | https://octopusdtlsupport.atlassian.net/browse/O2-2111 | https://octopusdtlsupport.atlassian.net/browse/O2-2116 | [5 empty] | 2026-04-06T11:01:24.129+0500 | 2026-04-20T15:13:56.901+0500
O2 | O2-2117 | O2-2117 | Bug Subtask | Bug Subtask |  | “Get Latest Values” Not Working for Single and Bulk Write Back | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2117 | [5 empty] | 2026-04-06T12:28:02.751+0500 | 2026-04-06T16:01:39.453+0500
O2 | O2-2118 | O2-2118 | Bug Subtask | Bug Subtask |  | Unable to create SAP HANA and ODBC Connector | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2118 | [5 empty] | 2026-04-06T12:32:56.733+0500 | 2026-04-06T12:35:59.251+0500
O2 | O2-2119 | O2-2119 | Bug Subtask | Bug Subtask |  | Diagnostics Email Alerts Are Not Being Received | Request received |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2119 | [5 empty] | 2026-04-06T12:44:28.435+0500 | 2026-04-06T14:32:15.660+0500
O2 | O2-212 | O2-212 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | To Do |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 8 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-212 | [5 empty] | 2025-10-08T11:03:55.090+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-2120 | O2-2120 | Bug Subtask | Bug Subtask |  | Data center Specified module failed on staging | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2120 | [5 empty] | 2026-04-06T12:46:04.824+0500 | 2026-04-06T12:46:14.049+0500
O2 | O2-2121 | O2-2121 | Bug Subtask | Bug Subtask |  | Asset and Real , Manual and Cal tags are getting duplicated, while we create Asset Built In, and double click on the save button | Request received | 2026-04-06 |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2121 | [5 empty] | 2026-04-06T12:54:35.694+0500 | 2026-04-06T14:20:37.597+0500
O2 | O2-2124 | O2-2124 | Story | Story |  | Research/DDS | On Hold | 2026-04-06 |  |  |  | 0 | 0 | Ameer Hamza Khan | 57.5 |  | O2-460 | O2-460 | https://octopusdtlsupport.atlassian.net/browse/O2-460 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | [5 empty] | 2026-04-06T14:13:38.565+0500 | 2026-04-09T09:30:14.936+0500
O2 | O2-2125 | O2-2125 | Sub-task | Sub-task |  | Walk-through session with process team | Resolved! | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8 | 8 | Ameer Hamza Khan | 8 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2125 | [5 empty] | 2026-04-06T14:19:46.876+0500 | 2026-04-06T14:20:49.407+0500
O2 | O2-2127 | O2-2127 | Bug Subtask | Bug Subtask |  | Anomaly Group results are not getting displayed | Resolved | 2026-04-06 |  | 2026-04-06 | 2026-04-06 | 0 | 0 | Muhammad Zeeshan Aslam | 4 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2127 | [5 empty] | 2026-04-06T14:22:01.705+0500 | 2026-04-17T09:48:31.646+0500
O2 | O2-2128 | O2-2128 | Sub-task | Sub-task |  | Omni Alla Walkthrough | Resolved! | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2.5 | 2.5 | Faiza Nasir | 2.5 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2128 | [5 empty] | 2026-04-06T14:24:54.950+0500 | 2026-04-08T10:38:03.128+0500
O2 | O2-213 | O2-213 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | Resolved! |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 48 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-213 | [5 empty] | 2025-10-08T11:04:06.073+0500 | 2026-02-09T14:47:18.204+0500
O2 | O2-2132 | O2-2132 | Bug Subtask | Bug Subtask |  | Unable to verify phone number using SMS OPT-IN feature | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2132 | [5 empty] | 2026-04-06T15:19:36.262+0500 | 2026-04-06T15:20:36.430+0500
O2 | O2-2133 | O2-2133 | Bug Subtask | Bug Subtask |  | MQTT Default Simulator for Ingestion Transfection is getting closed with this error , right after running it. | Request received |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2133 | [5 empty] | 2026-04-06T15:21:08.038+0500 | 2026-04-06T15:32:18.609+0500
O2 | O2-2134 | O2-2134 | Bug Subtask | Bug Subtask |  | EMAIL Alerts for alarms notifications are not triggering | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2084 | O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2084 | https://octopusdtlsupport.atlassian.net/browse/O2-2134 | [5 empty] | 2026-04-06T15:44:49.032+0500 | 2026-04-06T15:45:03.912+0500
O2 | O2-2136 | O2-2136 | Sub-task | Sub-task |  | Walk-through session with process team | Resolved! |  |  | 2026-04-06 | 2026-04-06 | 2 | 2 | Zain Munir | 2 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2136 | [5 empty] | 2026-04-06T17:08:03.190+0500 | 2026-04-08T10:32:33.381+0500
O2 | O2-2137 | O2-2137 | Story | Story |  | Sanity_Testing_4/7/26(Prod Green) | Resolved! | 2026-04-07 | 2026-04-07 |  |  | 32 | 32 | Muhammad Abbas | 97.17 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | [5 empty] | 2026-04-07T08:39:26.179+0500 | 2026-04-09T10:16:11.601+0500
O2 | O2-2138 | O2-2138 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 8 | 8 | kamran khalid | 16 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2138 | [5 empty] | 2026-04-07T08:40:43.537+0500 | 2026-05-12T15:12:40.245+0500
O2 | O2-2139 | O2-2139 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 8 | 8 | Waqar Rasheed | 15 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2139 | [5 empty] | 2026-04-07T08:40:50.013+0500 | 2026-04-09T12:55:16.794+0500
O2 | O2-214 | O2-214 | Sub-task | Sub-task |  | Moving Configurations to Environment Variables | To Do |  |  |  |  | 0 | 0 | Usama Tariq | 8 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-214 | [5 empty] | 2025-10-08T11:04:24.187+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-2140 | O2-2140 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 8 | 8 | Namra Zahid | 16 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2140 | [5 empty] | 2026-04-07T08:40:57.742+0500 | 2026-05-12T14:49:10.682+0500
O2 | O2-2141 | O2-2141 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 6 | 6 | Muhammad Abbas | 14 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2141 | [5 empty] | 2026-04-07T08:41:15.450+0500 | 2026-05-12T14:32:27.805+0500
O2 | O2-2142 | O2-2142 | Sub-task | Sub-task |  | Batch/BPM Testing | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2 | 2 | Muhammad Abbas | 2 |  | O2-1440 | O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-2142 | [5 empty] | 2026-04-07T08:45:04.373+0500 | 2026-04-09T10:22:02.006+0500
O2 | O2-2143 | O2-2143 | Sub-task | Sub-task |  | OmniConnect_Revamp_(UI/UX)_URS (P) | To Do |  |  | 2026-04-01 | 2026-04-17 | 0 | 0 | Unassigned | 32 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-2143 | [5 empty] | 2026-04-07T10:03:22.446+0500 | 2026-04-21T09:50:35.665+0500
O2 | O2-2144 | O2-2144 | Epic | Epic |  | Alarms in ReadAPI - OC Optimization | To Do | 2026-04-09 | 2026-04-15 |  |  | 40 | 40 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2144 | [5 empty] | 2026-04-07T13:34:24.326+0500 | 2026-04-07T13:35:33.435+0500
O2 | O2-2145 | O2-2145 | Sub-task | Sub-task |  | Changes in BPM Engine | Resolved! | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | 24 | 24 | Syed Yousaf Qadri | 19.5 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2145 | [5 empty] | 2026-04-07T14:16:14.982+0500 | 2026-04-07T14:56:02.709+0500
O2 | O2-2146 | O2-2146 | Sub-task | Sub-task |  | Changes in Batch Engine | Resolved! | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-03-12 | 24 | 24 | Syed Yousaf Qadri | 19.5 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2146 | [5 empty] | 2026-04-07T14:16:38.633+0500 | 2026-04-07T14:57:01.668+0500
O2 | O2-2147 | O2-2147 | Sub-task | Sub-task |  | End To End testing | Resolved! | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-16 | 13 | 13 | Syed Yousaf Qadri | 13 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2147 | [5 empty] | 2026-04-07T14:17:05.017+0500 | 2026-04-07T14:50:23.698+0500
O2 | O2-2148 | O2-2148 | Story | Story |  | Configure Manual DB/Table Mapping for SAP HANA Source | Resolved! | 2026-03-04 | 2026-03-06 |  |  | 24 | 24 | Arslan sohail | 24 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-2148 | [5 empty] | 2026-04-07T14:50:28.417+0500 | 2026-04-07T15:58:19.053+0500
O2 | O2-2149 | O2-2149 | Sub-task | Sub-task |  | Implement manual DB/Table to bypass SAP HANA Connector | Resolved! |  |  | 2026-03-04 | 2026-03-07 | 0 | 0 | Arslan sohail | 24 |  | O2-2148 | O2-2148 | https://octopusdtlsupport.atlassian.net/browse/O2-2148 | https://octopusdtlsupport.atlassian.net/browse/O2-2149 | [5 empty] | 2026-04-07T14:54:08.664+0500 | 2026-04-07T15:31:40.542+0500
O2 | O2-215 | O2-215 | Sub-task | Sub-task |  | usamaMoving Configurations to Environment Variables | Resolved! |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-215 | [5 empty] | 2025-10-08T11:04:48.591+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-2150 | O2-2150 | Bug Subtask | Bug Subtask |  | Latest Values are not getting populated (Green Production) | Resolved | 2026-04-07 |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2150 | [5 empty] | 2026-04-07T15:04:36.725+0500 | 2026-04-08T11:37:13.248+0500
O2 | O2-2151 | O2-2151 | Sub-task | Sub-task |  | UI Changes Batch Trigger | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 8 | 8 | Arslan sohail | 8 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2151 | [5 empty] | 2026-04-07T15:08:58.164+0500 | 2026-04-07T15:19:09.206+0500
O2 | O2-2152 | O2-2152 | Sub-task | Sub-task |  | UI Changes BPM Trigger | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 8 | 8 | Arslan sohail | 8 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2152 | [5 empty] | 2026-04-07T15:09:12.658+0500 | 2026-04-07T15:20:03.982+0500
O2 | O2-2153 | O2-2153 | Sub-task | Sub-task |  | Batch Variable Mapping | Resolved! | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-09 | 16 | 16 | Arslan sohail | 16 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2153 | [5 empty] | 2026-04-07T15:09:21.893+0500 | 2026-04-07T15:21:33.135+0500
O2 | O2-2154 | O2-2154 | Sub-task | Sub-task |  | BPM Variable Mapping | Resolved! | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-11 | 16 | 16 | Arslan sohail | 16 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2154 | [5 empty] | 2026-04-07T15:09:30.623+0500 | 2026-04-07T15:22:50.192+0500
O2 | O2-2155 | O2-2155 | Sub-task | Sub-task |  | Design and implement SQL tables for BPM/Batch variable mapping | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 8 | 8 | Arslan sohail | 8 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2155 | [5 empty] | 2026-04-07T15:13:38.376+0500 | 2026-04-07T15:23:35.676+0500
O2 | O2-2156 | O2-2156 | Sub-task | Sub-task |  | Unit Testing Frontend | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Arslan sohail | 8 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2156 | [5 empty] | 2026-04-07T15:14:24.105+0500 | 2026-04-07T16:37:58.370+0500
O2 | O2-2157 | O2-2157 | Sub-task | Sub-task |  | Unit Testing Backend | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8 | 8 | Arslan sohail | 8 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2157 | [5 empty] | 2026-04-07T15:14:29.605+0500 | 2026-04-07T16:37:29.437+0500
O2 | O2-2158 | O2-2158 | Sub-task | Sub-task |  | UI Integrate With API | Resolved! | 2026-03-13 | 2026-03-18 | 2026-03-13 | 2026-03-18 | 32 | 32 | Arslan sohail | 32 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2158 | [5 empty] | 2026-04-07T15:15:28.067+0500 | 2026-04-07T16:29:41.317+0500
O2 | O2-2159 | O2-2159 | Bug Subtask | Bug Subtask |  | Data center module fail on prod green env | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2159 | [5 empty] | 2026-04-07T16:09:31.800+0500 | 2026-04-07T16:35:01.244+0500
O2 | O2-216 | O2-216 | Sub-task | Sub-task |  | Trigger API | Resolved! |  |  |  |  | 0 | 0 | Taimur Zahid | 16 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-216 | [5 empty] | 2025-10-08T11:05:27.216+0500 | 2025-12-18T16:36:40.745+0500
O2 | O2-2160 | O2-2160 | Bug Subtask | Bug Subtask |  | Unable to create Enterprise Connectors on Production (Green). The issue was recently fixed on the staging environment but the fix has not yet been deployed to production. | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2160 | [5 empty] | 2026-04-07T16:11:34.183+0500 | 2026-04-07T16:12:06.215+0500
O2 | O2-2161 | O2-2161 | Bug Subtask | Bug Subtask |  | Request A Format For Ingestion Transformation is not getting created, Showing this error. | Resolved | 2026-04-07 |  | 2026-04-08 | 2026-04-08 | 8 | 8 | Ameer Hamza Khan | 8 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2161 | [5 empty] | 2026-04-07T16:35:26.560+0500 | 2026-04-08T14:35:45.472+0500
O2 | O2-2162 | O2-2162 | Sub-task | Sub-task |  | Initial POC | Resolved! | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-03-03 | 24 | 24 | ahad omer | 24 |  | O2-19 | O2-19 | https://octopusdtlsupport.atlassian.net/browse/O2-19 | https://octopusdtlsupport.atlassian.net/browse/O2-2162 | [5 empty] | 2026-04-07T16:57:53.501+0500 | 2026-04-07T17:06:33.423+0500
O2 | O2-2163 | O2-2163 | Sub-task | Sub-task |  | BATCH and BPM Trigger Design Changes | Resolved! | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-16 | 40 | 40 | ahad omer | 40 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2163 | [5 empty] | 2026-04-07T17:14:47.055+0500 | 2026-04-07T17:18:19.209+0500
O2 | O2-2164 | O2-2164 | Sub-task | Sub-task |  | Instance api Development Changes | Resolved! |  |  | 2026-03-17 | 2026-03-18 | 16 | 16 | ahad omer | 16 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2164 | [5 empty] | 2026-04-07T17:19:50.792+0500 | 2026-04-07T17:21:30.849+0500
O2 | O2-2165 | O2-2165 | Sub-task | Sub-task |  | Unit Testing | Resolved! | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 16 | 16 | ahad omer | 16 |  | O2-20 | O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-20 | https://octopusdtlsupport.atlassian.net/browse/O2-2165 | [5 empty] | 2026-04-07T17:22:39.386+0500 | 2026-04-07T17:25:05.779+0500
O2 | O2-2166 | O2-2166 | Task | Task |  | ADE Stress Testing Support | To Do |  |  |  |  | 0 | 0 | Muhammad Abdul Wasi | 1 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-2166 | [5 empty] | 2026-04-08T09:29:52.927+0500 | 2026-04-08T09:32:11.263+0500
O2 | O2-2167 | O2-2167 | Sub-task | Sub-task |  | ADE Stress Testing Support | Resolved! | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 1 | 1 | Muhammad Abdul Wasi | 1 |  | O2-2166 | O2-2166 | https://octopusdtlsupport.atlassian.net/browse/O2-2166 | https://octopusdtlsupport.atlassian.net/browse/O2-2167 | [5 empty] | 2026-04-08T09:33:04.579+0500 | 2026-04-08T09:34:29.416+0500
O2 | O2-2168 | O2-2168 | Sub-task | Sub-task |  | Data Prep for Demo (P) | To Do |  |  | 2026-04-06 | 2026-04-07 | 16 | 16 | DANIYAL AHMAD | 12 |  | O2-427 | O2-427 | https://octopusdtlsupport.atlassian.net/browse/O2-427 | https://octopusdtlsupport.atlassian.net/browse/O2-2168 | [5 empty] | 2026-04-08T09:40:02.218+0500 | 2026-04-08T09:41:13.454+0500
O2 | O2-2169 | O2-2169 | Bug Subtask | Bug Subtask |  | “Get Latest Values” Not Working for Single and Bulk Write Back | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2169 | [5 empty] | 2026-04-08T11:53:56.499+0500 | 2026-04-08T14:36:11.890+0500
O2 | O2-2170 | O2-2170 | Bug Subtask | Bug Subtask |  | Site Changes Refresh button is not working. as its not showing newly created Real tag even after clicking on refresh button. Prod green | Bug Fixed | 2026-04-08 |  | 2026-04-09 | 2026-04-09 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2170 | [5 empty] | 2026-04-08T11:54:07.793+0500 | 2026-04-22T15:31:45.807+0500
O2 | O2-2171 | O2-2171 | Sub-task | Sub-task |  | Green production release | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8 | 8 | Ameer Hamza Khan | 8 |  | O2-1440 | O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-2171 | [5 empty] | 2026-04-08T12:09:50.119+0500 | 2026-04-08T12:11:02.421+0500
O2 | O2-2172 | O2-2172 | Sub-task | Sub-task |  | Production Green Release / Release Management | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 8 | 8 | Faiza Nasir | 8 |  | O2-1440 | O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-2172 | [5 empty] | 2026-04-08T12:10:07.187+0500 | 2026-04-09T12:49:28.375+0500
O2 | O2-2173 | O2-2173 | Sub-task | Sub-task |  | Update Digital twin APIs | Resolved! | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-06 | 5.5 | 5.5 | Faiza Nasir | 5.5 |  | O2-2068 | O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2173 | [5 empty] | 2026-04-08T12:14:12.550+0500 | 2026-04-16T10:43:40.764+0500
O2 | O2-2174 | O2-2174 | Bug Subtask | Bug Subtask |  | Schedule Scanning not Woking for Digital LOG Device | Request received | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 4 | 4 | Arsalan Zafar Khan | 8 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2174 | [5 empty] | 2026-04-08T12:17:35.437+0500 | 2026-04-16T10:23:47.045+0500
O2 | O2-2175 | O2-2175 | Bug Subtask | Bug Subtask |  | Publish Changes version is not getting updated Again (Production Green) | Resolved | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8 | 8 | Ameer Hamza Khan | 8 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2175 | [5 empty] | 2026-04-08T12:21:03.626+0500 | 2026-04-09T11:52:33.040+0500
O2 | O2-2176 | O2-2176 | Bug Subtask | Bug Subtask |  | Application is getting logout While we Create model for Anomaly group. | Request received | 2026-04-08 |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2176 | [5 empty] | 2026-04-08T12:28:10.487+0500 | 2026-04-08T12:30:52.907+0500
O2 | O2-2177 | O2-2177 | Story | Story |  | URS | To Do | 2026-03-17 |  |  |  | 3.2 | 3.2 | Unassigned | 0 |  | O2-1976 | O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-2177 | [5 empty] | 2026-04-08T14:08:56.421+0500 | 2026-04-08T15:08:24.864+0500
O2 | O2-2178 | O2-2178 | Story | Story |  | DDS | To Do |  |  |  |  | 10 | 10 | Unassigned | 0 |  | O2-1976 | O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-2178 | [5 empty] | 2026-04-08T14:10:05.551+0500 | 2026-04-08T16:03:23.524+0500
O2 | O2-2179 | O2-2179 | Story | Story |  | SQA | In-Progress | 2026-04-16 | 2026-04-22 |  |  | 40 | 40 | Muhammad Abbas | 80 |  | O2-1976 | O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-2179 | [5 empty] | 2026-04-08T14:10:29.140+0500 | 2026-04-20T23:41:20.624+0500
O2 | O2-2180 | O2-2180 | Bug Subtask | Bug Subtask |  | Data Alarms and Stats Alarms are configured and getting fired, but OmniAgent is not Showing records. | Bug Fixed |  |  | 2026-04-08 | 2026-04-08 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2180 | [5 empty] | 2026-04-08T14:35:58.048+0500 | 2026-04-22T15:30:58.930+0500
O2 | O2-2181 | O2-2181 | Bug Subtask | Bug Subtask |  | Real Time tags are getting Duplicated while we create from Wizard | Not a Bug |  |  | 2026-04-08 | 2026-04-08 | 0.17 | 0.17 | Ameer Hamza Khan | 0.17 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2181 | [5 empty] | 2026-04-08T14:41:51.071+0500 | 2026-04-08T14:50:34.244+0500
O2 | O2-2182 | O2-2182 | Sub-task | Sub-task |  | OmniAla Walkthrough Session + Discussion | Resolved! | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 5 | 5 | Muhammad Ahmad Saleem | 5 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2182 | [5 empty] | 2026-04-08T14:44:07.131+0500 | 2026-04-08T14:48:48.803+0500
O2 | O2-2183 | O2-2183 | Sub-task | Sub-task |  | Fixed OmniAgent issue | Resolved! | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 3 | 3 | Muhammad Ahmad Saleem | 3 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2183 | [5 empty] | 2026-04-08T14:46:44.653+0500 | 2026-04-08T14:48:22.350+0500
O2 | O2-2184 | O2-2184 | Sub-task | Sub-task |  | DDS Discussion + prepared OmniAla ERD | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2184 | [5 empty] | 2026-04-08T14:55:01.793+0500 | 2026-04-08T14:56:19.465+0500
O2 | O2-2185 | O2-2185 | Sub-task | Sub-task |  | DDS(Added Content + Prepared Flowchart) | Resolved! | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2185 | [5 empty] | 2026-04-08T14:57:02.275+0500 | 2026-04-09T09:30:03.846+0500
O2 | O2-2186 | O2-2186 | Epic | Epic |  | Tempate Tool Enhancement for WhatIf and Health | To Do | 2026-04-06 | 2026-04-27 |  |  | 180 | 180 | Faiza Nasir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2186 | [5 empty] | 2026-04-08T15:11:57.875+0500 | 2026-04-22T10:34:28.646+0500
O2 | O2-2187 | O2-2187 | Story | Story |  | Development | In-Progress | 2026-04-09 | 2026-04-16 |  |  | 52 | 52 | Faiza Nasir | 41.5 |  | O2-2186 | O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | [5 empty] | 2026-04-08T15:13:52.245+0500 | 2026-04-15T10:22:37.391+0500
O2 | O2-2188 | O2-2188 | Epic | Epic |  | Support for Wide tables from SQL Source | In-Progress | 2026-05-08 | 2026-05-19 |  |  | 96 | 96 | Muhammad Ahmad Saleem | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | [5 empty] | 2026-04-08T15:20:21.348+0500 | 2026-05-12T14:24:33.055+0500
O2 | O2-2189 | O2-2189 | Epic | Epic |  | Support for Wide tables from API Source | To Do | 2026-06-01 | 2026-06-05 |  |  | 96 | 96 | Muhammad Ahmad Saleem | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | [5 empty] | 2026-04-08T15:20:34.263+0500 | 2026-04-10T12:08:46.516+0500
O2 | O2-2190 | O2-2190 | Epic | Epic |  | Support for Wide tables from SFTP Source | To Do | 2026-06-03 | 2026-06-12 |  |  | 96 | 96 | Muhammad Ahmad Saleem | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | [5 empty] | 2026-04-08T15:20:50.176+0500 | 2026-04-09T17:25:46.083+0500
O2 | O2-2191 | O2-2191 | Story | Story |  | Research/URS | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2188 | O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2191 | [5 empty] | 2026-04-08T15:21:51.564+0500 | 2026-04-08T15:21:51.742+0500
O2 | O2-2192 | O2-2192 | Story | Story |  | Research/DDS | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2188 | O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2192 | [5 empty] | 2026-04-08T15:22:10.811+0500 | 2026-04-08T15:22:11.001+0500
O2 | O2-2193 | O2-2193 | Story | Story |  | Development | In-Progress | 2026-05-08 | 2026-05-14 |  |  | 34.4 | 34.4 | Muhammad Ahmad Saleem | 20 |  | O2-2188 | O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | [5 empty] | 2026-04-08T15:22:24.782+0500 | 2026-05-07T12:14:10.411+0500
O2 | O2-2195 | O2-2195 | Story | Story |  | Handover | To Do | 2026-04-17 | 2026-04-17 |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-2186 | O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2195 | [5 empty] | 2026-04-08T15:23:36.526+0500 | 2026-04-08T15:38:18.919+0500
O2 | O2-2196 | O2-2196 | Story | Story |  | QA Handover | To Do | 2026-05-15 | 2026-05-15 |  |  | 9 | 9 | Muhammad Ahmad Saleem | 0 |  | O2-2188 | O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2196 | [5 empty] | 2026-04-08T15:24:42.041+0500 | 2026-04-09T16:51:09.504+0500
O2 | O2-2198 | O2-2198 | Story | Story |  | SQA | To Do | 2026-04-17 | 2026-04-24 |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-2186 | O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2198 | [5 empty] | 2026-04-08T15:26:52.332+0500 | 2026-04-16T10:15:38.266+0500
O2 | O2-2199 | O2-2199 | Story | Story |  | Production Release | To Do | 2026-05-19 | 2026-05-20 |  |  | 72 | 72 | Muhammad Ahmad Saleem | 0 |  | O2-2188 | O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2199 | [5 empty] | 2026-04-08T15:26:57.081+0500 | 2026-04-09T16:51:46.337+0500
O2 | O2-22 | O2-22 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-10 | O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-22 | [5 empty] | 2025-10-02T14:10:34.661+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-2200 | O2-2200 | Story | Story |  | Research/URS | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2189 | O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2200 | [5 empty] | 2026-04-08T15:27:35.372+0500 | 2026-04-08T15:27:35.596+0500
O2 | O2-2201 | O2-2201 | Story | Story |  | Research/DDS | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2189 | O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2201 | [5 empty] | 2026-04-08T15:27:49.440+0500 | 2026-04-08T15:27:49.698+0500
O2 | O2-2202 | O2-2202 | Story | Story |  | Production Release | To Do | 2026-04-27 | 2026-04-28 |  |  | 24 | 24 | Faiza Nasir | 0 |  | O2-2186 | O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2202 | [5 empty] | 2026-04-08T15:28:57.355+0500 | 2026-04-08T16:12:43.936+0500
O2 | O2-2203 | O2-2203 | Story | Story |  | Development | In-Progress | 2026-05-22 | 2026-05-28 |  |  | 34.4 | 34.4 | Muhammad Ahmad Saleem | 20 |  | O2-2189 | O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | [5 empty] | 2026-04-08T15:29:11.220+0500 | 2026-05-07T12:15:48.176+0500
O2 | O2-2204 | O2-2204 | Story | Story |  | QA Handover | To Do | 2026-05-29 | 2026-05-29 |  |  | 9 | 9 | Muhammad Ahmad Saleem | 0 |  | O2-2189 | O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2204 | [5 empty] | 2026-04-08T15:29:24.226+0500 | 2026-04-09T17:09:05.169+0500
O2 | O2-2205 | O2-2205 | Story | Story |  | Production Release | To Do | 2026-06-02 | 2026-06-03 |  |  | 72 | 72 | Muhammad Ahmad Saleem | 0 |  | O2-2189 | O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2205 | [5 empty] | 2026-04-08T15:29:37.863+0500 | 2026-04-09T17:08:45.825+0500
O2 | O2-2206 | O2-2206 | Story | Story |  | Research/URS | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2190 | O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2206 | [5 empty] | 2026-04-08T15:30:05.092+0500 | 2026-04-08T15:30:05.279+0500
O2 | O2-2207 | O2-2207 | Story | Story |  | Research/DDS | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2190 | O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2207 | [5 empty] | 2026-04-08T15:30:19.002+0500 | 2026-04-08T15:30:19.225+0500
O2 | O2-2208 | O2-2208 | Story | Story |  | Development | To Do | 2026-06-03 | 2026-06-09 |  |  | 34.4 | 34.4 | Muhammad Ahmad Saleem | 0 |  | O2-2190 | O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2208 | [5 empty] | 2026-04-08T15:30:32.842+0500 | 2026-04-09T17:20:53.857+0500
O2 | O2-2209 | O2-2209 | Story | Story |  | QA Handover | To Do | 2026-06-10 | 2026-06-10 |  |  | 9 | 9 | Muhammad Ahmad Saleem | 0 |  | O2-2190 | O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2209 | [5 empty] | 2026-04-08T15:30:48.194+0500 | 2026-04-09T17:22:16.891+0500
O2 | O2-221 | O2-221 | Epic | Epic |  | ( Demo / Presentation) Assignments | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 351.6 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-221 | [5 empty] | 2025-10-08T12:39:52.326+0500 | 2026-03-25T10:28:03.345+0500
O2 | O2-2210 | O2-2210 | Story | Story |  | Production Release | To Do | 2026-06-12 | 2026-06-15 |  |  | 72 | 72 | Muhammad Ahmad Saleem | 0 |  | O2-2190 | O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2210 | [5 empty] | 2026-04-08T15:31:02.292+0500 | 2026-04-09T17:24:39.368+0500
O2 | O2-2211 | O2-2211 | Story | Story |  | QA Handover | To Do | 2026-05-22 | 2026-05-22 |  |  | 8 | 8 | Muhammad Ahmad Saleem | 0 |  | O2-697 | O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-2211 | [5 empty] | 2026-04-08T15:57:26.718+0500 | 2026-04-08T16:37:02.723+0500
O2 | O2-2212 | O2-2212 | Bug Subtask | Bug Subtask |  | APX Asset Creation – Next Button Creates Tag but Does Not Navigate, Causes Duplication Error on Re-click | Request received |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-2137 | O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2137 | https://octopusdtlsupport.atlassian.net/browse/O2-2212 | [5 empty] | 2026-04-08T16:09:35.789+0500 | 2026-04-08T17:09:25.657+0500
O2 | O2-2213 | O2-2213 | Story | Story |  | SQA | To Do | 2026-05-15 | 2026-05-21 |  |  | 32 | 32 | kamran khalid | 24 |  | O2-2188 | O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | https://octopusdtlsupport.atlassian.net/browse/O2-2213 | [5 empty] | 2026-04-08T16:09:45.775+0500 | 2026-05-07T14:11:19.275+0500
O2 | O2-2214 | O2-2214 | Story | Story |  | SQA | In-Progress | 2026-06-03 | 2026-06-08 |  |  | 32 | 32 | Waqar Rasheed | 8 |  | O2-2189 | O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | https://octopusdtlsupport.atlassian.net/browse/O2-2214 | [5 empty] | 2026-04-08T16:11:05.322+0500 | 2026-05-08T15:17:42.629+0500
O2 | O2-2215 | O2-2215 | Story | Story |  | SQA | To Do | 2026-06-11 | 2026-06-16 |  |  | 32 | 32 | Unassigned | 0 |  | O2-2190 | O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | https://octopusdtlsupport.atlassian.net/browse/O2-2215 | [5 empty] | 2026-04-08T16:13:47.347+0500 | 2026-04-08T16:15:09.565+0500
O2 | O2-2216 | O2-2216 | Story | Story |  | Bug Fixing | To Do | 2026-04-17 | 2026-04-24 |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-2186 | O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2186 | https://octopusdtlsupport.atlassian.net/browse/O2-2216 | [5 empty] | 2026-04-08T16:14:22.283+0500 | 2026-04-08T16:14:58.036+0500
O2 | O2-2217 | O2-2217 | Story | Story |  | Sanity_Testing_4/9/26(Prod Blue) | Resolved! | 2026-04-09 | 2026-04-09 |  |  | 32 | 32 | Muhammad Abbas | 61 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | [5 empty] | 2026-04-09T10:17:28.334+0500 | 2026-04-10T17:14:30.706+0500
O2 | O2-2218 | O2-2218 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 8 | 8 | kamran khalid | 17 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2218 | [5 empty] | 2026-04-09T10:18:09.960+0500 | 2026-04-10T16:11:46.996+0500
O2 | O2-222 | O2-222 | Bug Subtask | Bug Subtask |  | Same OTP is received and not getting expired after using. This issue occur sometime and sometime it is working fine. | Resolved |  |  |  |  | 0 | 0 | Faiza Nasir | 1 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-222 | [5 empty] | 2025-10-08T12:48:31.142+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2220 | O2-2220 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 8 | 8 | Namra Zahid | 16 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2220 | [5 empty] | 2026-04-09T10:18:24.397+0500 | 2026-04-10T17:13:30.421+0500
O2 | O2-2221 | O2-2221 | Sub-task | Sub-task |  | Testing By Abbas | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 8 | 8 | Muhammad Abbas | 16 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2221 | [5 empty] | 2026-04-09T10:18:49.011+0500 | 2026-04-10T17:14:15.923+0500
O2 | O2-2222 | O2-2222 | Sub-task | Sub-task |  | Bug Fixing | Resolved! | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 3 | 3 | Faiza Nasir | 2.17 |  | O2-1440 | O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-2222 | [5 empty] | 2026-04-09T12:50:23.599+0500 | 2026-04-09T12:51:00.684+0500
O2 | O2-2223 | O2-2223 | Sub-task | Sub-task |  | Production Blue Deployment / Release Management | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2 | 2 | Faiza Nasir | 2 |  | O2-1440 | O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-1440 | https://octopusdtlsupport.atlassian.net/browse/O2-2223 | [5 empty] | 2026-04-09T12:51:21.880+0500 | 2026-04-14T10:50:48.866+0500
O2 | O2-2224 | O2-2224 | Story | Story |  | SQA Handover | To Do | 2026-04-20 | 2026-04-20 |  |  | 2 | 2 | Hamza Ali | 0 |  | O2-1461 | O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-2224 | [5 empty] | 2026-04-09T14:24:05.716+0500 | 2026-04-22T00:27:53.232+0500
O2 | O2-2225 | O2-2225 | Story | Story |  | Regression SQA | To Do |  |  |  |  | 24 | 24 | Muhammad Abbas | 0 |  | O2-1461 | O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | https://octopusdtlsupport.atlassian.net/browse/O2-2225 | [5 empty] | 2026-04-09T14:26:01.538+0500 | 2026-04-09T14:30:21.653+0500
O2 | O2-2226 | O2-2226 | Bug Subtask | Bug Subtask |  | Values are not populating for newly created sites, Second time In a day, and we will be creating all the site third time now | Resolved | 2026-04-09 |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2226 | [5 empty] | 2026-04-09T14:40:05.964+0500 | 2026-04-09T16:12:22.486+0500
O2 | O2-2227 | O2-2227 | Bug Subtask | Bug Subtask |  | Unable to Create connectors | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2227 | [5 empty] | 2026-04-09T14:49:17.710+0500 | 2026-04-09T14:50:02.726+0500
O2 | O2-223 | O2-223 | Story | Story |  | IP Meeting Preparation | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 16 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-223 | [5 empty] | 2025-10-08T12:51:23.277+0500 | 2025-10-08T12:59:08.242+0500
O2 | O2-2231 | O2-2231 | Bug Subtask | Bug Subtask |  | “Get Latest Values” Not Working for Single and Bulk Write Back | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2231 | [5 empty] | 2026-04-09T16:04:36.552+0500 | 2026-04-10T15:17:51.875+0500
O2 | O2-2232 | O2-2232 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 8 | 8 | Waqar Rasheed | 8 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2232 | [5 empty] | 2026-04-09T16:08:57.217+0500 | 2026-04-10T16:38:49.331+0500
O2 | O2-2233 | O2-2233 | Bug Subtask | Bug Subtask |  | Anomaly Group Results are not getting displayed | Resolved | 2026-04-09 |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2233 | [5 empty] | 2026-04-09T16:12:47.768+0500 | 2026-04-13T16:16:30.458+0500
O2 | O2-2234 | O2-2234 | Sub-task | Sub-task |  | Process Eng. tasks: working, review and management | Resolved! | 2026-04-01 | 2026-04-30 | 2026-04-02 | 2026-04-30 | 120 | 120 | Mariam Zulfiqar | 119.5 |  | O2-1254 | O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-2234 | [5 empty] | 2026-04-09T16:45:59.367+0500 | 2026-05-04T11:33:48.368+0500
O2 | O2-2235 | O2-2235 | Sub-task | Sub-task |  | Process pre-sales support, Customer / Management Meetings | Resolved! | 2026-04-01 | 2026-04-30 | 2026-04-03 | 2026-04-29 | 32 | 32 | Mariam Zulfiqar | 31 |  | O2-1066 | O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-2235 | [5 empty] | 2026-04-09T16:47:42.339+0500 | 2026-05-04T11:34:28.300+0500
O2 | O2-2236 | O2-2236 | Bug Subtask | Bug Subtask |  | Failed to refresh with button and we cant proceed with OmniAgent Testing Prod Blue | Bug Fixed |  |  | 2026-04-10 | 2026-04-10 | 0 | 0 | Ibrahim Ahmed Qureshi | 4 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2236 | [5 empty] | 2026-04-10T10:06:00.867+0500 | 2026-04-22T15:30:06.474+0500
O2 | O2-2237 | O2-2237 | Sub-task | Sub-task |  | Research for Slider, Radio Buttons, Inputs Support to HTML Template | Resolved! | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8 | 8 | Zain Munir | 8 |  | O2-1992 | O2-1992 | https://octopusdtlsupport.atlassian.net/browse/O2-1992 | https://octopusdtlsupport.atlassian.net/browse/O2-2237 | [5 empty] | 2026-04-10T10:36:13.539+0500 | 2026-04-13T09:45:39.488+0500
O2 | O2-2238 | O2-2238 | Bug Subtask | Bug Subtask |  | State Duplication in Data Alarms for Totalizer Tags | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2217 | O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2217 | https://octopusdtlsupport.atlassian.net/browse/O2-2238 | [5 empty] | 2026-04-10T14:44:59.341+0500 | 2026-04-10T14:45:53.793+0500
O2 | O2-2239 | O2-2239 | Sub-task | Sub-task |  | Image, Radio Button, Slider Incorporation in the HTML Template | Resolved! | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-15 | 24 | 24 | Zain Munir | 24 |  | O2-1993 | O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-2239 | [5 empty] | 2026-04-13T09:48:40.815+0500 | 2026-04-16T10:14:51.626+0500
O2 | O2-224 | O2-224 | Sub-task | Sub-task |  | Event-based Real-Time Tags | Resolved! | 2025-09-15 | 2025-10-07 |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-111 | O2-111 | https://octopusdtlsupport.atlassian.net/browse/O2-111 | https://octopusdtlsupport.atlassian.net/browse/O2-224 | [5 empty] | 2025-10-08T13:55:01.032+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-2240 | O2-2240 | Sub-task | Sub-task |  | OmniConnect- Site Dashboard UI + Plus Navigation | Resolved! | 2026-03-05 | 2026-03-11 | 2026-03-05 | 2026-03-11 | 32.5 | 32.5 | Hassan Wali | 32.5 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-2240 | [5 empty] | 2026-04-13T11:13:48.734+0500 | 2026-04-13T11:19:13.314+0500
O2 | O2-2241 | O2-2241 | Sub-task | Sub-task |  | OmniConnect_ Feedback Incorporation | Resolved! | 2026-03-12 | 2026-03-18 | 2026-03-12 | 2026-03-18 | 32.5 | 32.5 | Hassan Wali | 32.5 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-2241 | [5 empty] | 2026-04-13T11:19:38.578+0500 | 2026-04-13T11:27:07.962+0500
O2 | O2-2242 | O2-2242 | Sub-task | Sub-task |  | OmniConnect_ Organization Dashboard + Navigation changes | Resolved! | 2026-03-24 | 2026-03-30 | 2026-03-24 | 2026-03-30 | 40 | 40 | Hassan Wali | 40 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-2242 | [5 empty] | 2026-04-13T11:27:01.450+0500 | 2026-04-13T12:20:25.363+0500
O2 | O2-2243 | O2-2243 | Sub-task | Sub-task |  | OmniConnect_ OmniAgent Revamp + Site Connectivity | Resolved! | 2026-03-31 | 2026-04-06 | 2026-03-31 | 2026-04-06 | 40 | 40 | Hassan Wali | 40 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-2243 | [5 empty] | 2026-04-13T11:30:21.110+0500 | 2026-04-13T12:23:03.911+0500
O2 | O2-2244 | O2-2244 | Sub-task | Sub-task |  | OmniConnect_ Revamp Overall Feedback Incorportion | Resolved! | 2026-04-07 | 2026-04-13 | 2026-04-07 | 2026-04-13 | 40 | 40 | Hassan Wali | 40 |  | O2-894 | O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | https://octopusdtlsupport.atlassian.net/browse/O2-2244 | [5 empty] | 2026-04-13T12:24:16.938+0500 | 2026-04-13T12:29:36.890+0500
O2 | O2-2245 | O2-2245 | Story | Story |  | APX Chiller Performance | To Do |  |  |  |  | 0 | 0 | Unassigned | 212 |  | O2-1981 | O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | [5 empty] | 2026-04-14T11:16:29.835+0500 | 2026-04-14T11:16:30.113+0500
O2 | O2-2246 | O2-2246 | Story | Story |  | APX AHU Performance | To Do |  |  |  |  | 0 | 0 | Unassigned | 187 |  | O2-1981 | O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | [5 empty] | 2026-04-14T11:17:20.411+0500 | 2026-04-14T11:18:24.221+0500
O2 | O2-2247 | O2-2247 | Sub-task | Sub-task |  | Asset Design, HB and Expected models (P) | Resolved! | 2026-04-09 | 2026-04-30 | 2026-04-09 | 2026-04-24 | 80 | 80 | Danish Rashid | 48 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2247 | [5 empty] | 2026-04-14T11:18:04.812+0500 | 2026-05-11T09:41:02.699+0500
O2 | O2-2248 | O2-2248 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | Resolved! |  |  | 2026-04-17 | 2026-04-22 | 40 | 40 | Unassigned | 28 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2248 | [5 empty] | 2026-04-14T11:18:20.758+0500 | 2026-05-11T09:46:23.506+0500
O2 | O2-2249 | O2-2249 | Sub-task | Sub-task |  | Initial Research | Resolved! |  |  | 2026-04-06 | 2026-04-07 | 12 | 12 | Faiq Butt | 12 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2249 | [5 empty] | 2026-04-14T11:18:58.478+0500 | 2026-04-27T11:51:11.509+0500
O2 | O2-225 | O2-225 | Sub-task | Sub-task |  | Timer-based Processed Tags | Resolved! | 2025-09-15 | 2025-10-07 |  |  | 0 | 0 | Mohsin Junaid | 160 |  | O2-111 | O2-111 | https://octopusdtlsupport.atlassian.net/browse/O2-111 | https://octopusdtlsupport.atlassian.net/browse/O2-225 | [5 empty] | 2025-10-08T13:56:41.929+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-2250 | O2-2250 | Sub-task | Sub-task |  | Walk-through session with process team (P) | Resolved! |  |  | 2026-04-06 | 2026-04-06 | 4 | 4 | Faiq Butt | 4 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2250 | [5 empty] | 2026-04-14T11:29:21.632+0500 | 2026-04-14T11:30:46.871+0500
O2 | O2-2251 | O2-2251 | Sub-task | Sub-task |  | AHU Presentation | Resolved! |  |  | 2026-04-08 | 2026-04-08 | 8 | 8 | Faiq Butt | 8 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2251 | [5 empty] | 2026-04-14T11:33:53.768+0500 | 2026-04-27T11:51:02.910+0500
O2 | O2-2252 | O2-2252 | Sub-task | Sub-task |  | Asset Design, HB and Expected models (P) | In-Progress |  |  | 2026-04-09 | 2026-04-23 | 80 | 80 | Faiq Butt | 84 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2252 | [5 empty] | 2026-04-14T11:35:48.105+0500 | 2026-05-07T09:10:00.211+0500
O2 | O2-2253 | O2-2253 | Story | Story |  | APX AHU Health | To Do |  |  |  |  | 0 | 0 | Unassigned | 16 |  | O2-1981 | O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-1981 | https://octopusdtlsupport.atlassian.net/browse/O2-2253 | [5 empty] | 2026-04-14T16:58:51.950+0500 | 2026-04-14T16:58:52.253+0500
O2 | O2-2254 | O2-2254 | Sub-task | Sub-task |  | Module Design (P) | To Do |  |  | 2026-04-13 | 2026-04-17 | 40 | 40 | Unassigned | 16 |  | O2-2253 | O2-2253 | https://octopusdtlsupport.atlassian.net/browse/O2-2253 | https://octopusdtlsupport.atlassian.net/browse/O2-2254 | [5 empty] | 2026-04-14T16:59:16.301+0500 | 2026-04-21T09:43:16.372+0500
O2 | O2-2255 | O2-2255 | Sub-task | Sub-task |  | Curves Digitalization | Resolved! |  |  | 2026-04-08 | 2026-04-20 | 40 | 40 | DANIYAL AHMAD | 40 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2255 | [5 empty] | 2026-04-14T16:59:47.760+0500 | 2026-04-29T16:16:07.408+0500
O2 | O2-2256 | O2-2256 | Sub-task | Sub-task |  | Setup additional Property for health | Resolved! | 2026-04-10 | 2026-04-14 | 2026-04-10 | 2026-04-10 | 5.5 | 5.5 | Faiza Nasir | 5.5 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2256 | [5 empty] | 2026-04-14T17:09:12.433+0500 | 2026-04-16T10:49:09.284+0500
O2 | O2-2257 | O2-2257 | Sub-task | Sub-task |  | Code review to incorporate changes | Resolved! | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 5 | 5 | Faiza Nasir | 6 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2257 | [5 empty] | 2026-04-14T17:09:27.529+0500 | 2026-04-16T10:33:41.327+0500
O2 | O2-2258 | O2-2258 | Sub-task | Sub-task |  | Product Demo 14th April | Resolved! | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 16 | 16 | Sarmad Sabir | 11 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-2258 | [5 empty] | 2026-04-14T17:23:29.574+0500 | 2026-04-14T17:24:16.297+0500
O2 | O2-2259 | O2-2259 | Sub-task | Sub-task |  | Add steps for health additional property | Resolved! | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | 3.5 | 3.5 | Faiza Nasir | 3.5 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2259 | [5 empty] | 2026-04-15T10:10:53.284+0500 | 2026-04-16T11:01:23.776+0500
O2 | O2-2260 | O2-2260 | Sub-task | Sub-task |  | modify steps api to incorporate health additional properties | Resolved! | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2.5 | 2.5 | Faiza Nasir | 2.5 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2260 | [5 empty] | 2026-04-15T10:13:03.326+0500 | 2026-04-16T11:03:09.637+0500
O2 | O2-2261 | O2-2261 | Sub-task | Sub-task |  | Modify the template code to incorporate changes | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 3 | 3 | Faiza Nasir | 3 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2261 | [5 empty] | 2026-04-15T10:14:29.441+0500 | 2026-04-16T11:04:35.867+0500
O2 | O2-2262 | O2-2262 | Sub-task | Sub-task |  | Modify health get steps api to call additional property template | Resolved! | 2026-04-15 | 2026-04-16 |  |  | 2 | 2 | Faiza Nasir | 0 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2262 | [5 empty] | 2026-04-15T10:15:07.522+0500 | 2026-04-16T11:05:55.598+0500
O2 | O2-2263 | O2-2263 | Sub-task | Sub-task |  | Export To Sql (April16, 17) | Resolved! | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-17 | 16 | 16 | Namra Zahid | 16 |  | O2-2179 | O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2263 | [5 empty] | 2026-04-15T10:37:23.305+0500 | 2026-05-12T16:01:19.146+0500
O2 | O2-2265 | O2-2265 | Story | Story |  | QA Handover | Resolved! | 2026-04-15 | 2026-04-16 |  |  | 6 | 6 | Muhammad Abbas | 4.5 |  | O2-1976 | O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | [5 empty] | 2026-04-15T10:39:36.982+0500 | 2026-04-17T10:44:24.057+0500
O2 | O2-2266 | O2-2266 | Sub-task | Sub-task |  | Handover By Abbas | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1 | 1 | Muhammad Abbas | 1 |  | O2-2265 | O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2266 | [5 empty] | 2026-04-15T10:55:00.098+0500 | 2026-04-15T11:52:54.649+0500
O2 | O2-2267 | O2-2267 | Sub-task | Sub-task |  | Handover Taken By Kamran | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1 | 1 | kamran khalid | 1 |  | O2-2265 | O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2267 | [5 empty] | 2026-04-15T10:55:11.924+0500 | 2026-04-15T11:53:17.037+0500
O2 | O2-2268 | O2-2268 | Sub-task | Sub-task |  | Handover By Namra | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1 | 1 | Namra Zahid | 1 |  | O2-2265 | O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2268 | [5 empty] | 2026-04-15T10:55:25.769+0500 | 2026-04-15T14:16:55.795+0500
O2 | O2-2269 | O2-2269 | Epic | Epic |  | OmniEdge Diagnostics Metrics Collection | To Do |  |  |  |  | 0 | 0 | yousha.agha | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | [5 empty] | 2026-04-15T11:55:36.422+0500 | 2026-04-29T12:29:20.112+0500
O2 | O2-227 | O2-227 | Bug Subtask | Bug Subtask |  | When user selects the Notification group in the edit site and re-saves the configuration then the datapoints column for the respective site is getting empty | Resolved | 2025-10-15 | 2025-10-15 |  |  | 2 | 2 | Ali Qumail | 2 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-227 | [5 empty] | 2025-10-08T14:31:34.715+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2270 | O2-2270 | Story | Story |  | URS | To Do |  |  |  |  | 0 | 0 | yousha.agha | 0 |  | O2-2269 | O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2270 | [5 empty] | 2026-04-15T11:56:07.661+0500 | 2026-04-15T11:56:07.805+0500
O2 | O2-2271 | O2-2271 | Story | Story |  | DDS | To Do |  |  |  |  | 0 | 0 | yousha.agha | 0 |  | O2-2269 | O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2271 | [5 empty] | 2026-04-15T11:56:45.039+0500 | 2026-04-15T11:56:45.220+0500
O2 | O2-2272 | O2-2272 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | yousha.agha | 0 |  | O2-2269 | O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2272 | [5 empty] | 2026-04-15T11:57:31.909+0500 | 2026-04-29T12:28:50.810+0500
O2 | O2-2273 | O2-2273 | Story | Story |  | SQA Handover | Resolved! |  |  |  |  | 0 | 0 | yousha.agha | 1 |  | O2-2269 | O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2273 | [5 empty] | 2026-04-15T11:57:55.648+0500 | 2026-04-23T11:03:16.093+0500
O2 | O2-2274 | O2-2274 | Story | Story |  | SQA | In-Progress |  |  |  |  | 24 | 24 | Muhammad Abbas | 24 |  | O2-2269 | O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2274 | [5 empty] | 2026-04-15T11:59:10.958+0500 | 2026-04-23T11:04:03.126+0500
O2 | O2-2275 | O2-2275 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | yousha.agha | 0 |  | O2-2269 | O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | https://octopusdtlsupport.atlassian.net/browse/O2-2275 | [5 empty] | 2026-04-15T11:59:30.096+0500 | 2026-04-15T11:59:30.339+0500
O2 | O2-2276 | O2-2276 | Story | Story |  | Bug Fixing | In-Progress |  |  |  |  | 0 | 0 | Faiza Nasir | 136.17 |  | O2-1976 | O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | [5 empty] | 2026-04-15T12:41:10.820+0500 | 2026-04-20T10:23:29.648+0500
O2 | O2-2277 | O2-2277 | Epic | Epic |  | Alarms for Batch IT Data | To Do | 2026-04-16 |  |  |  | 304 | 304 | Syed Yousaf Qadri | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | [5 empty] | 2026-04-15T14:29:19.380+0500 | 2026-04-16T11:54:00.230+0500
O2 | O2-2278 | O2-2278 | Epic | Epic |  | Alarms for BPM IT Data | To Do |  |  |  |  | 352 | 352 | Arslan sohail | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | [5 empty] | 2026-04-15T14:32:42.464+0500 | 2026-04-15T15:44:44.010+0500
O2 | O2-2279 | O2-2279 | Epic | Epic |  | Alarms for Enterprise Connectors IT Data SQL | To Do |  |  |  |  | 224 | 224 | Arslan sohail | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | [5 empty] | 2026-04-15T14:33:48.481+0500 | 2026-04-15T16:28:46.342+0500
O2 | O2-228 | O2-228 | Bug Subtask | Bug Subtask |  | Data is not being ingested into ADX for any site and device. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-228 | [5 empty] | 2025-10-08T15:33:38.624+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2280 | O2-2280 | Epic | Epic |  | Alarms for Enterprise Connectors IT Data SAP | To Do |  |  |  |  | 224 | 224 | Arslan sohail | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | [5 empty] | 2026-04-15T14:34:50.429+0500 | 2026-04-15T16:38:27.057+0500
O2 | O2-2281 | O2-2281 | Story | Story |  | Research | To Do |  |  |  |  | 24 | 24 | ahad omer | 8 |  | O2-2277 | O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2281 | [5 empty] | 2026-04-15T14:38:45.437+0500 | 2026-04-15T15:40:53.773+0500
O2 | O2-2282 | O2-2282 | Story | Story |  | Development | To Do |  |  |  |  | 192 | 192 | Syed Yousaf Qadri | 24 |  | O2-2277 | O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2282 | [5 empty] | 2026-04-15T14:39:00.932+0500 | 2026-04-16T11:54:24.882+0500
O2 | O2-2283 | O2-2283 | Story | Story |  | SQA | To Do | 2026-04-15 | 2026-04-16 |  |  | 16 | 16 | Muhammad Abbas | 0 |  | O2-2277 | O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2283 | [5 empty] | 2026-04-15T14:39:11.213+0500 | 2026-04-15T14:41:55.778+0500
O2 | O2-2284 | O2-2284 | Story | Story |  | User Manual | To Do |  |  |  |  | 8 | 8 | Hassan Malik | 0 |  | O2-2277 | O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2284 | [5 empty] | 2026-04-15T14:39:23.431+0500 | 2026-04-15T15:42:30.839+0500
O2 | O2-2285 | O2-2285 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2277 | O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2285 | [5 empty] | 2026-04-15T14:39:36.861+0500 | 2026-04-15T14:41:22.310+0500
O2 | O2-2287 | O2-2287 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2277 | O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2287 | [5 empty] | 2026-04-15T15:36:56.046+0500 | 2026-04-15T15:36:56.200+0500
O2 | O2-2288 | O2-2288 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2277 | O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | https://octopusdtlsupport.atlassian.net/browse/O2-2288 | [5 empty] | 2026-04-15T15:37:12.389+0500 | 2026-04-15T15:37:12.553+0500
O2 | O2-2289 | O2-2289 | Story | Story |  | Research | To Do |  |  |  |  | 48 | 48 | Unassigned | 0 |  | O2-2278 | O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2289 | [5 empty] | 2026-04-15T15:37:29.521+0500 | 2026-04-15T15:43:29.470+0500
O2 | O2-229 | O2-229 | Bug Subtask | Bug Subtask |  | Un-necessary space is showing on Create and Edit GPS modal | Resolved | 2025-10-08 | 2025-10-08 |  |  | 0 | 0 | Ali Qumail | 2 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-229 | [5 empty] | 2025-10-08T16:20:22.749+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2290 | O2-2290 | Story | Story |  | Development | To Do |  |  |  |  | 216 | 216 | Unassigned | 0 |  | O2-2278 | O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2290 | [5 empty] | 2026-04-15T15:37:58.488+0500 | 2026-04-15T15:43:42.778+0500
O2 | O2-2291 | O2-2291 | Story | Story |  | SQA | To Do |  |  |  |  | 40 | 40 | Unassigned | 0 |  | O2-2278 | O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2291 | [5 empty] | 2026-04-15T15:38:12.265+0500 | 2026-04-15T15:43:57.696+0500
O2 | O2-2292 | O2-2292 | Story | Story |  | User Manual | To Do |  |  |  |  | 8 | 8 | Unassigned | 0 |  | O2-2278 | O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2292 | [5 empty] | 2026-04-15T15:38:20.231+0500 | 2026-04-15T15:44:09.233+0500
O2 | O2-2293 | O2-2293 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2278 | O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2293 | [5 empty] | 2026-04-15T15:38:29.824+0500 | 2026-04-15T15:38:30.020+0500
O2 | O2-2294 | O2-2294 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2278 | O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2294 | [5 empty] | 2026-04-15T15:38:45.021+0500 | 2026-04-15T15:38:45.244+0500
O2 | O2-2295 | O2-2295 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2278 | O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | https://octopusdtlsupport.atlassian.net/browse/O2-2295 | [5 empty] | 2026-04-15T15:38:56.833+0500 | 2026-04-15T15:38:57.013+0500
O2 | O2-2296 | O2-2296 | Epic | Epic |  | Alarms for Enterprise Connectors IT Data SFTP | To Do |  |  |  |  | 0.47 | 0.47 | Arslan sohail | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | [5 empty] | 2026-04-15T16:23:31.857+0500 | 2026-04-15T16:38:24.298+0500
O2 | O2-2297 | O2-2297 | Epic | Epic |  | Alarms for Enterprise Connectors IT Data Rest API | To Do |  |  |  |  | 224 | 224 | Arslan sohail | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | [5 empty] | 2026-04-15T16:23:44.675+0500 | 2026-04-15T16:37:29.763+0500
O2 | O2-2298 | O2-2298 | Story | Story |  | Research | To Do |  |  |  |  | 24 | 24 | ahad omer | 0 |  | O2-2279 | O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2298 | [5 empty] | 2026-04-15T16:25:55.342+0500 | 2026-04-15T16:28:19.125+0500
O2 | O2-2299 | O2-2299 | Story | Story |  | Development | To Do |  |  |  |  | 120 | 120 | Arslan sohail | 0 |  | O2-2279 | O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2299 | [5 empty] | 2026-04-15T16:26:13.587+0500 | 2026-04-15T16:28:21.119+0500
O2 | O2-23 | O2-23 | Story | Story |  | Research/URS | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-11 | O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-23 | [5 empty] | 2025-10-02T14:10:46.730+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-2300 | O2-2300 | Story | Story |  | SQA | To Do |  |  |  |  | 40 | 40 | Muhammad Abbas | 0 |  | O2-2279 | O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2300 | [5 empty] | 2026-04-15T16:26:24.615+0500 | 2026-04-15T16:28:24.134+0500
O2 | O2-2301 | O2-2301 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-2279 | O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2301 | [5 empty] | 2026-04-15T16:26:34.672+0500 | 2026-04-15T16:28:29.741+0500
O2 | O2-2302 | O2-2302 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2279 | O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2302 | [5 empty] | 2026-04-15T16:26:47.467+0500 | 2026-04-15T16:28:33.934+0500
O2 | O2-2303 | O2-2303 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2279 | O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2303 | [5 empty] | 2026-04-15T16:26:57.881+0500 | 2026-04-15T16:28:37.155+0500
O2 | O2-2304 | O2-2304 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2279 | O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | https://octopusdtlsupport.atlassian.net/browse/O2-2304 | [5 empty] | 2026-04-15T16:27:11.306+0500 | 2026-04-15T16:28:40.832+0500
O2 | O2-2305 | O2-2305 | Story | Story |  | Research | To Do |  |  |  |  | 24 | 24 | Unassigned | 0 |  | O2-2280 | O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2305 | [5 empty] | 2026-04-15T16:29:28.524+0500 | 2026-04-15T16:30:59.267+0500
O2 | O2-2306 | O2-2306 | Story | Story |  | Development | To Do |  |  |  |  | 120 | 120 | Unassigned | 0 |  | O2-2280 | O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2306 | [5 empty] | 2026-04-15T16:29:39.340+0500 | 2026-04-15T16:31:09.388+0500
O2 | O2-2307 | O2-2307 | Story | Story |  | SQA | To Do |  |  |  |  | 40 | 40 | Unassigned | 0 |  | O2-2280 | O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2307 | [5 empty] | 2026-04-15T16:29:53.628+0500 | 2026-04-15T16:31:19.822+0500
O2 | O2-2308 | O2-2308 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2280 | O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2308 | [5 empty] | 2026-04-15T16:30:04.855+0500 | 2026-04-15T16:30:05.001+0500
O2 | O2-2309 | O2-2309 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2280 | O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2309 | [5 empty] | 2026-04-15T16:30:15.030+0500 | 2026-04-15T16:30:15.244+0500
O2 | O2-231 | O2-231 | Sub-task | Sub-task |  | IT Data Connector table not visible on Batch BPM Query page despite successful ingestion | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-231 | [5 empty] | 2025-10-08T16:55:22.691+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-2310 | O2-2310 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2280 | O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2310 | [5 empty] | 2026-04-15T16:30:30.809+0500 | 2026-04-15T16:30:30.949+0500
O2 | O2-2311 | O2-2311 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2280 | O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | https://octopusdtlsupport.atlassian.net/browse/O2-2311 | [5 empty] | 2026-04-15T16:30:42.379+0500 | 2026-04-15T16:30:42.551+0500
O2 | O2-2312 | O2-2312 | Story | Story |  | Research | To Do |  |  |  |  | 24 | 24 | ahad omer | 0 |  | O2-2296 | O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2312 | [5 empty] | 2026-04-15T16:32:27.228+0500 | 2026-04-15T16:34:31.481+0500
O2 | O2-2313 | O2-2313 | Story | Story |  | Development | To Do |  |  |  |  | 120 | 120 | Arslan sohail | 0 |  | O2-2296 | O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2313 | [5 empty] | 2026-04-15T16:32:41.133+0500 | 2026-04-15T16:34:48.704+0500
O2 | O2-2314 | O2-2314 | Story | Story |  | SQA | To Do |  |  |  |  | 40 | 40 | Muhammad Abbas | 0 |  | O2-2296 | O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2314 | [5 empty] | 2026-04-15T16:32:50.673+0500 | 2026-04-15T16:34:56.759+0500
O2 | O2-2315 | O2-2315 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-2296 | O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2315 | [5 empty] | 2026-04-15T16:33:01.558+0500 | 2026-04-15T16:34:00.838+0500
O2 | O2-2316 | O2-2316 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2296 | O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2316 | [5 empty] | 2026-04-15T16:33:11.854+0500 | 2026-04-15T16:34:04.241+0500
O2 | O2-2317 | O2-2317 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2296 | O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2317 | [5 empty] | 2026-04-15T16:33:27.179+0500 | 2026-04-15T16:34:07.711+0500
O2 | O2-2318 | O2-2318 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2296 | O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | https://octopusdtlsupport.atlassian.net/browse/O2-2318 | [5 empty] | 2026-04-15T16:33:41.126+0500 | 2026-04-15T16:34:09.747+0500
O2 | O2-2319 | O2-2319 | Story | Story |  | Research | To Do |  |  |  |  | 24 | 24 | ahad omer | 0 |  | O2-2297 | O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2319 | [5 empty] | 2026-04-15T16:35:36.202+0500 | 2026-04-15T16:37:44.622+0500
O2 | O2-232 | O2-232 | Bug Subtask | Bug Subtask |  | Duplicate table creation shows success in UI but only one table exists in ADX. | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-232 | [5 empty] | 2025-10-08T20:51:43.015+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2320 | O2-2320 | Story | Story |  | Development | To Do |  |  |  |  | 120 | 120 | Arslan sohail | 0 |  | O2-2297 | O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2320 | [5 empty] | 2026-04-15T16:35:51.216+0500 | 2026-04-15T16:38:01.935+0500
O2 | O2-2321 | O2-2321 | Story | Story |  | SQA | To Do |  |  |  |  | 40 | 40 | Muhammad Abbas | 0 |  | O2-2297 | O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2321 | [5 empty] | 2026-04-15T16:36:00.102+0500 | 2026-04-15T16:38:14.835+0500
O2 | O2-2322 | O2-2322 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-2297 | O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2322 | [5 empty] | 2026-04-15T16:36:14.298+0500 | 2026-04-15T16:37:13.211+0500
O2 | O2-2323 | O2-2323 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2297 | O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2323 | [5 empty] | 2026-04-15T16:36:24.706+0500 | 2026-04-15T16:37:16.382+0500
O2 | O2-2324 | O2-2324 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2297 | O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2324 | [5 empty] | 2026-04-15T16:36:40.872+0500 | 2026-04-15T16:37:18.428+0500
O2 | O2-2325 | O2-2325 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2297 | O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2297 | https://octopusdtlsupport.atlassian.net/browse/O2-2325 | [5 empty] | 2026-04-15T16:36:50.584+0500 | 2026-04-15T16:37:19.559+0500
O2 | O2-2326 | O2-2326 | Story | Story |  | SQA | In-Progress | 2026-04-16 | 2026-04-22 |  |  | 40 | 40 | Muhammad Abbas | 40 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-2326 | [5 empty] | 2026-04-15T17:14:16.007+0500 | 2026-04-28T19:29:14.371+0500
O2 | O2-2327 | O2-2327 | Sub-task | Sub-task |  | Incorporate Additional propertty while configuring asset's Health | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 3 | Faiza Nasir | 3 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2327 | [5 empty] | 2026-04-16T10:26:14.989+0500 | 2026-04-30T09:24:56.100+0500
O2 | O2-2328 | O2-2328 | Sub-task | Sub-task |  | Incorporate additional property in VM calls for digital twin creation and Activation | Resolved! | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 5 | 5 | Faiza Nasir | 5 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2328 | [5 empty] | 2026-04-16T10:26:55.663+0500 | 2026-04-28T10:04:31.393+0500
O2 | O2-2329 | O2-2329 | Sub-task | Sub-task |  | User End dynamic HTML Rendering and id mappings | Resolved! | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-17 | 16 | 16 | Zain Munir | 16 |  | O2-1993 | O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-2329 | [5 empty] | 2026-04-16T10:34:09.421+0500 | 2026-04-17T12:43:37.591+0500
O2 | O2-233 | O2-233 | Bug Subtask | Bug Subtask |  | Pipeline creation fails on GET method despite Read API supporting both GET and POST. | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-233 | [5 empty] | 2025-10-08T21:12:18.191+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2330 | O2-2330 | Sub-task | Sub-task |  | Testing for VM calls with Process Team Coordination | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 3 | 3 | Faiza Nasir | 3 |  | O2-2068 | O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2068 | https://octopusdtlsupport.atlassian.net/browse/O2-2330 | [5 empty] | 2026-04-16T10:36:03.622+0500 | 2026-04-16T10:39:12.977+0500
O2 | O2-2331 | O2-2331 | Story | Story |  | Handover to QA | Resolved! | 2026-04-15 | 2026-04-15 |  |  | 0.5 | 0.5 | kamran khalid | 0 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-2331 | [5 empty] | 2026-04-16T10:41:22.358+0500 | 2026-04-16T10:41:58.348+0500
O2 | O2-2332 | O2-2332 | Story | Story |  | Production Release | To Do |  |  |  |  | 16 | 16 | Faiza Nasir | 0 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-2332 | [5 empty] | 2026-04-16T10:42:28.092+0500 | 2026-04-16T10:43:00.008+0500
O2 | O2-2333 | O2-2333 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-2333 | [5 empty] | 2026-04-16T10:53:16.447+0500 | 2026-04-16T10:53:22.968+0500
O2 | O2-2334 | O2-2334 | Sub-task | Sub-task |  | BPM On Demand Integration | Resolved! | 2026-04-03 | 2026-04-07 | 2026-04-03 | 2026-04-07 | 24 | 24 | Syed Yousaf Qadri | 24 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2334 | [5 empty] | 2026-04-16T10:56:20.921+0500 | 2026-04-22T16:41:45.549+0500
O2 | O2-2335 | O2-2335 | Story | Story |  | Login failing on Production Environment | Resolved! | 2026-04-14 | 2026-04-14 |  |  | 2 | 2 | Faiza Nasir | 2 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-2335 | [5 empty] | 2026-04-16T10:56:25.279+0500 | 2026-04-16T10:57:57.087+0500
O2 | O2-2336 | O2-2336 | Sub-task | Sub-task |  | BPM Job Tracking Integration | Resolved! | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2336 | [5 empty] | 2026-04-16T10:56:55.240+0500 | 2026-04-22T16:44:02.751+0500
O2 | O2-2337 | O2-2337 | Sub-task | Sub-task |  | Batch Job Tracking Integration | Resolved! | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-13 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2337 | [5 empty] | 2026-04-16T10:57:16.610+0500 | 2026-04-22T16:45:32.420+0500
O2 | O2-2338 | O2-2338 | Sub-task | Sub-task |  | Authorization Implementation for BPM/Batch | Resolved! | 2026-04-14 | 2026-04-16 | 2026-04-14 | 2026-04-16 | 24 | 24 | Syed Yousaf Qadri | 24 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2338 | [5 empty] | 2026-04-16T10:58:23.779+0500 | 2026-04-22T16:47:52.728+0500
O2 | O2-2339 | O2-2339 | Sub-task | Sub-task |  | Database connection failing - Due to VNET deletion | Resolved! | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2 | 2 | Faiza Nasir | 2 |  | O2-2335 | O2-2335 | https://octopusdtlsupport.atlassian.net/browse/O2-2335 | https://octopusdtlsupport.atlassian.net/browse/O2-2339 | [5 empty] | 2026-04-16T10:58:36.431+0500 | 2026-04-16T10:59:31.158+0500
O2 | O2-234 | O2-234 | Bug Subtask | Bug Subtask |  | Run on Demand is not working for IT Data pipelines. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-234 | [5 empty] | 2025-10-08T21:26:33.275+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2340 | O2-2340 | Epic | Epic |  | DOE Engro: Simulated Tags Experiment on Sandbox | Resolved! | 2026-04-03 | 2026-04-13 |  |  | 192 | 192 | Taimur Zahid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2340 | [5 empty] | 2026-04-16T11:05:54.119+0500 | 2026-04-27T11:56:17.337+0500
O2 | O2-2341 | O2-2341 | Story | Story |  | SQA | To Do | 2026-04-15 |  |  |  | 0 | 0 | kamran khalid | 0 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-2341 | [5 empty] | 2026-04-16T11:06:45.992+0500 | 2026-04-16T11:07:07.850+0500
O2 | O2-2342 | O2-2342 | Story | Story |  | Anomaly Detection Engine: Cost per Tag Simulation | Resolved! | 2026-04-03 | 2026-04-13 |  |  | 56 | 56 | Muhammad Zeeshan Aslam | 24 |  | O2-2340 | O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2342 | [5 empty] | 2026-04-16T11:08:36.472+0500 | 2026-04-16T11:30:48.804+0500
O2 | O2-2343 | O2-2343 | Sub-task | Sub-task |  | Handover to QA | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | O2-2265 | O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2343 | [5 empty] | 2026-04-16T11:08:46.327+0500 | 2026-04-16T11:09:18.176+0500
O2 | O2-2344 | O2-2344 | Story | Story |  | Calculated Tags Creation and Simulation | Resolved! | 2026-04-03 | 2026-04-13 |  |  | 56 | 56 | Muhammad Abbas | 6 |  | O2-2340 | O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2344 | [5 empty] | 2026-04-16T11:10:09.926+0500 | 2026-05-12T14:35:59.872+0500
O2 | O2-2345 | O2-2345 | Sub-task | Sub-task |  | Delete Trigger API Creation | Resolved! | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 1.5 | 1.5 | Faiza Nasir | 1.5 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2345 | [5 empty] | 2026-04-16T11:10:37.568+0500 | 2026-04-16T11:15:42.664+0500
O2 | O2-2346 | O2-2346 | Sub-task | Sub-task |  | Post Handover feedback Incorporated | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1 | 1 | Faiza Nasir | 1 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2346 | [5 empty] | 2026-04-16T11:10:58.899+0500 | 2026-04-16T11:17:12.768+0500
O2 | O2-2347 | O2-2347 | Story | Story |  | Alarm Tags Creation and Simulation | Resolved! | 2026-04-03 | 2026-04-13 |  |  | 56 | 56 | Ameer Hamza Khan | 24 |  | O2-2340 | O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2347 | [5 empty] | 2026-04-16T11:11:11.709+0500 | 2026-04-16T11:30:48.715+0500
O2 | O2-2348 | O2-2348 | Sub-task | Sub-task |  | Resolve Update Pipeline API Issues | Resolved! | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-16 | 5 | 5 | Faiza Nasir | 5 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2348 | [5 empty] | 2026-04-16T11:11:28.641+0500 | 2026-04-16T16:46:45.303+0500
O2 | O2-2349 | O2-2349 | Story | Story |  | Real Tags Creation and Simulation | Resolved! | 2026-04-03 | 2026-04-13 |  |  | 40 | 40 | yousha.agha | 0 |  | O2-2340 | O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2349 | [5 empty] | 2026-04-16T11:11:54.001+0500 | 2026-04-16T11:30:48.734+0500
O2 | O2-235 | O2-235 | Bug Subtask | Bug Subtask |  | Duplicate Manual and Cal tags are being created. | Request received |  |  |  |  | 0 | 0 | Muhammad Abbas | 1 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-235 | [5 empty] | 2025-10-08T21:34:51.772+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-2350 | O2-2350 | Story | Story |  | Read API Logic App Creation and Tags Retrieval | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 36 |  | O2-2340 | O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2350 | [5 empty] | 2026-04-16T11:12:36.133+0500 | 2026-04-16T11:30:48.734+0500
O2 | O2-2351 | O2-2351 | Story | Story |  | Monitoring, Report Creation, and Cost Per Tag Estimation | Resolved! | 2026-04-03 | 2026-04-13 |  |  | 72 | 72 | Taimur Zahid | 44 |  | O2-2340 | O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2340 | https://octopusdtlsupport.atlassian.net/browse/O2-2351 | [5 empty] | 2026-04-16T11:13:36.286+0500 | 2026-04-16T11:30:58.784+0500
O2 | O2-2352 | O2-2352 | Sub-task | Sub-task |  | Anomaly Detection ASP Experimentation Costing | Resolved! | 2026-04-03 | 2026-04-13 | 2026-04-03 | 2026-04-07 | 24 | 24 | Taimur Zahid | 8 |  | O2-2351 | O2-2351 | https://octopusdtlsupport.atlassian.net/browse/O2-2351 | https://octopusdtlsupport.atlassian.net/browse/O2-2352 | [5 empty] | 2026-04-16T11:21:01.434+0500 | 2026-04-16T12:08:32.652+0500
O2 | O2-2354 | O2-2354 | Sub-task | Sub-task |  | Proposal and Azure Costs Estimations for 12000 Sites | Resolved! | 2026-04-03 | 2026-04-13 | 2026-04-07 | 2026-04-14 | 56 | 56 | Taimur Zahid | 36 |  | O2-2351 | O2-2351 | https://octopusdtlsupport.atlassian.net/browse/O2-2351 | https://octopusdtlsupport.atlassian.net/browse/O2-2354 | [5 empty] | 2026-04-16T11:21:26.963+0500 | 2026-04-16T12:17:26.594+0500
O2 | O2-2356 | O2-2356 | Sub-task | Sub-task |  | Source Tag Creation and Setup | To Do |  |  |  |  | 0 | 0 | yousha.agha | 0 |  | O2-2349 | O2-2349 | https://octopusdtlsupport.atlassian.net/browse/O2-2349 | https://octopusdtlsupport.atlassian.net/browse/O2-2356 | [5 empty] | 2026-04-16T11:24:42.914+0500 | 2026-04-16T11:25:03.140+0500
O2 | O2-2357 | O2-2357 | Sub-task | Sub-task |  | Real-time Tags Creation and Simulation | To Do |  |  |  |  | 0 | 0 | yousha.agha | 0 |  | O2-2349 | O2-2349 | https://octopusdtlsupport.atlassian.net/browse/O2-2349 | https://octopusdtlsupport.atlassian.net/browse/O2-2357 | [5 empty] | 2026-04-16T11:24:55.739+0500 | 2026-04-16T11:25:06.558+0500
O2 | O2-2358 | O2-2358 | Sub-task | Sub-task |  | Tag Groups Creation and Simulation | Resolved! | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 16 | 16 | Muhammad Zeeshan Aslam | 16 |  | O2-2342 | O2-2342 | https://octopusdtlsupport.atlassian.net/browse/O2-2342 | https://octopusdtlsupport.atlassian.net/browse/O2-2358 | [5 empty] | 2026-04-16T11:25:25.507+0500 | 2026-04-17T09:45:45.606+0500
O2 | O2-2359 | O2-2359 | Sub-task | Sub-task |  | Cost per Tag Reporting | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | O2-2342 | O2-2342 | https://octopusdtlsupport.atlassian.net/browse/O2-2342 | https://octopusdtlsupport.atlassian.net/browse/O2-2359 | [5 empty] | 2026-04-16T11:25:29.324+0500 | 2026-04-17T09:46:53.772+0500
O2 | O2-236 | O2-236 | Sub-task | Sub-task |  | Perform API validations on Create Connector screen to improve user experience. | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-236 | [5 empty] | 2025-10-08T21:57:27.813+0500 | 2025-10-13T14:21:52.483+0500
O2 | O2-2360 | O2-2360 | Sub-task | Sub-task |  | Logic App Creation and Simulation | Resolved! | 2026-04-03 | 2026-04-07 | 2026-04-03 | 2026-04-06 | 24 | 24 | Aiza Hamid | 24 |  | O2-2350 | O2-2350 | https://octopusdtlsupport.atlassian.net/browse/O2-2350 | https://octopusdtlsupport.atlassian.net/browse/O2-2360 | [5 empty] | 2026-04-16T11:26:27.615+0500 | 2026-04-20T12:47:51.297+0500
O2 | O2-2361 | O2-2361 | Sub-task | Sub-task |  | Database Logs and Monitoring | To Do |  |  | 2026-04-10 | 2026-04-13 | 0 | 0 | Ibrahim Ahmed Qureshi | 12 |  | O2-2350 | O2-2350 | https://octopusdtlsupport.atlassian.net/browse/O2-2350 | https://octopusdtlsupport.atlassian.net/browse/O2-2361 | [5 empty] | 2026-04-16T11:26:49.906+0500 | 2026-04-22T16:05:04.559+0500
O2 | O2-2362 | O2-2362 | Sub-task | Sub-task |  | DDS(Added Sequence Diagram +ERD) | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2362 | [5 empty] | 2026-04-16T11:50:01.638+0500 | 2026-04-16T11:51:12.633+0500
O2 | O2-2363 | O2-2363 | Bug Subtask | Bug Subtask |  | Values are not getting displayed (Staging) | Resolved | 2026-04-16 |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2363 | [5 empty] | 2026-04-16T15:45:18.809+0500 | 2026-04-16T16:39:38.569+0500
O2 | O2-2364 | O2-2364 | Sub-task | Sub-task |  | Add Quality Codes in Export pipeline table , update all crud operations | Resolved! | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2 | 2 | Faiza Nasir | 2 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2364 | [5 empty] | 2026-04-16T16:45:28.827+0500 | 2026-04-16T16:45:57.820+0500
O2 | O2-2365 | O2-2365 | Story | Story |  | Bug-Fixing | To Do |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-2365 | [5 empty] | 2026-04-16T23:14:37.115+0500 | 2026-04-16T23:14:49.016+0500
O2 | O2-2367 | O2-2367 | Bug Subtask | Bug Subtask |  | Trigger AP returns “Variable 'StartTime' not found” error despite variable being configured | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2365 | O2-2365 | https://octopusdtlsupport.atlassian.net/browse/O2-2365 | https://octopusdtlsupport.atlassian.net/browse/O2-2367 | [5 empty] | 2026-04-16T23:20:06.032+0500 | 2026-04-16T23:21:25.344+0500
O2 | O2-2368 | O2-2368 | Story | Story |  | Process Team Sales / marketing Tasks | In-Progress |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 30 |  | O2-1595 | O2-1595 | https://octopusdtlsupport.atlassian.net/browse/O2-1595 | https://octopusdtlsupport.atlassian.net/browse/O2-2368 | [5 empty] | 2026-04-17T10:06:22.512+0500 | 2026-04-17T10:09:40.714+0500
O2 | O2-2369 | O2-2369 | Sub-task | Sub-task |  | PPX marketing presentation for gas processing plant | Resolved! | 2026-04-15 | 2026-04-23 | 2026-04-15 | 2026-04-23 | 30 | 30 | Muhammad Abdul Wasi | 30 |  | O2-2368 | O2-2368 | https://octopusdtlsupport.atlassian.net/browse/O2-2368 | https://octopusdtlsupport.atlassian.net/browse/O2-2369 | [5 empty] | 2026-04-17T10:07:31.914+0500 | 2026-05-05T10:49:45.552+0500
O2 | O2-2370 | O2-2370 | Epic | Epic |  | ADE–OmniAgent AutoRCA URS (P) | To Do |  |  |  |  | 0 | 0 | Muhammad Abdul Wasi | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2370 | [5 empty] | 2026-04-17T10:29:03.360+0500 | 2026-04-17T10:29:44.282+0500
O2 | O2-2371 | O2-2371 | Story | Story |  | ADE–OmniAgent AutoRCA URS (P) | To Do |  |  |  |  | 0 | 0 | Muhammad Abdul Wasi | 36 |  | O2-2370 | O2-2370 | https://octopusdtlsupport.atlassian.net/browse/O2-2370 | https://octopusdtlsupport.atlassian.net/browse/O2-2371 | [5 empty] | 2026-04-17T10:31:06.825+0500 | 2026-04-17T10:31:32.156+0500
O2 | O2-2372 | O2-2372 | Sub-task | Sub-task |  | ADE–OmniAgent AutoRCA URS (P) | Resolved! | 2026-04-08 | 2026-04-30 | 2026-04-09 | 2026-04-21 | 60 | 60 | Muhammad Abdul Wasi | 36 |  | O2-2371 | O2-2371 | https://octopusdtlsupport.atlassian.net/browse/O2-2371 | https://octopusdtlsupport.atlassian.net/browse/O2-2372 | [5 empty] | 2026-04-17T10:31:28.902+0500 | 2026-05-05T10:55:34.071+0500
O2 | O2-2373 | O2-2373 | Story | Story |  | SQA Handover | In-Progress |  |  |  |  | 0 | 0 | Syeda Rubab | 1 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-2373 | [5 empty] | 2026-04-17T10:47:22.858+0500 | 2026-04-17T11:06:25.547+0500
O2 | O2-2374 | O2-2374 | Sub-task | Sub-task |  | Handover By Abbas | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1 | 1 | Muhammad Abbas | 1 |  | O2-2373 | O2-2373 | https://octopusdtlsupport.atlassian.net/browse/O2-2373 | https://octopusdtlsupport.atlassian.net/browse/O2-2374 | [5 empty] | 2026-04-17T10:47:56.965+0500 | 2026-04-17T10:49:20.660+0500
O2 | O2-2375 | O2-2375 | Bug Subtask | Bug Subtask |  | SQL Manual pipeline is not getting started and Showing An ERROR | Resolved | 2026-04-17 |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2375 | [5 empty] | 2026-04-17T11:02:47.576+0500 | 2026-04-21T11:53:01.393+0500
O2 | O2-2376 | O2-2376 | Sub-task | Sub-task |  | Manual and Scheduled Export to SQL are not aligned in terms of data export. Please align both manual and scheduled export types for SQL export. | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2376 | [5 empty] | 2026-04-17T12:11:06.375+0500 | 2026-04-17T12:12:09.693+0500
O2 | O2-2377 | O2-2377 | Bug Subtask | Bug Subtask |  | On all types of SQL(Scheduled, Manual) This Error is getting displayed while we Stop or Start the Pipelie | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2377 | [5 empty] | 2026-04-17T12:27:48.983+0500 | 2026-04-22T10:30:40.817+0500
O2 | O2-2378 | O2-2378 | Bug Subtask | Bug Subtask |  | Trigger Name Minimum Length Validation Not Implemented | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2378 | [5 empty] | 2026-04-17T15:44:46.940+0500 | 2026-04-21T14:19:54.676+0500
O2 | O2-2379 | O2-2379 | Sub-task | Sub-task |  | Trigger-API-Testing | Resolved! | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-04-29 | 40 | 40 | Muhammad Abbas | 40 |  | O2-2326 | O2-2326 | https://octopusdtlsupport.atlassian.net/browse/O2-2326 | https://octopusdtlsupport.atlassian.net/browse/O2-2379 | [5 empty] | 2026-04-17T16:17:24.623+0500 | 2026-05-12T14:43:05.362+0500
O2 | O2-2380 | O2-2380 | Sub-task | Sub-task |  | Non-Ebs Exp Calculations | Resolved! |  |  | 2026-04-15 | 2026-04-24 | 8 | 8 | Faiq Butt | 8 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2380 | [5 empty] | 2026-04-20T09:27:24.493+0500 | 2026-05-07T09:11:57.921+0500
O2 | O2-2381 | O2-2381 | Sub-task | Sub-task |  | What-If call using dynamic controls | Resolved! | 2026-04-20 | 2026-04-23 | 2026-04-20 | 2026-04-23 | 16 | 16 | Zain Munir | 16 |  | O2-1993 | O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-2381 | [5 empty] | 2026-04-20T10:04:23.585+0500 | 2026-04-23T16:24:20.499+0500
O2 | O2-2382 | O2-2382 | Sub-task | Sub-task |  | Bug fixing | Resolved! | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-04-20 | 0 | 0 | Faiza Nasir | 12 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2382 | [5 empty] | 2026-04-20T10:25:02.174+0500 | 2026-04-22T16:12:01.494+0500
O2 | O2-2384 | O2-2384 | Story | Story |  | Development | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2384 | [5 empty] | 2026-04-20T10:35:13.658+0500 | 2026-04-20T10:44:22.344+0500
O2 | O2-2385 | O2-2385 | Story | Story |  | SQA | In-Progress | 2026-04-15 | 2026-04-15 |  |  | 8 | 8 | Muhammad Abbas | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2385 | [5 empty] | 2026-04-20T10:35:48.502+0500 | 2026-04-20T14:57:17.876+0500
O2 | O2-2386 | O2-2386 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2386 | [5 empty] | 2026-04-20T10:36:32.878+0500 | 2026-04-20T10:38:24.881+0500
O2 | O2-239 | O2-239 | Bug Subtask | Bug Subtask |  | Latest values of GPS tag are not landing | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-239 | [5 empty] | 2025-10-09T10:22:36.445+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2390 | O2-2390 | Bug Subtask | Bug Subtask |  | Pagination, footer, and grid UI get disturbed after creating multiple triggers | Resolved | 2026-04-20 | 2026-04-23 | 2026-04-21 | 2026-04-22 | 2 | 2 | Faiza Nasir | 2 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2390 | [5 empty] | 2026-04-20T11:18:55.189+0500 | 2026-04-23T15:52:50.932+0500
O2 | O2-2391 | O2-2391 | Sub-task | Sub-task |  | Batch Job On Demand API | Resolved! | 2026-04-02 | 2026-04-06 | 2026-04-02 | 2026-04-06 | 24 | 24 | Arslan sohail | 24 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2391 | [5 empty] | 2026-04-20T11:36:24.284+0500 | 2026-04-20T16:40:45.987+0500
O2 | O2-2392 | O2-2392 | Sub-task | Sub-task |  | BPM Job On Demand API | Resolved! | 2026-04-07 | 2026-04-09 | 2026-04-07 | 2026-04-09 | 24 | 24 | Arslan sohail | 24 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2392 | [5 empty] | 2026-04-20T11:36:42.309+0500 | 2026-04-20T16:41:33.429+0500
O2 | O2-2393 | O2-2393 | Sub-task | Sub-task |  | Variables Mapping | Resolved! | 2026-04-10 | 2026-04-14 | 2026-04-10 | 2026-04-14 | 24 | 24 | Arslan sohail | 24 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2393 | [5 empty] | 2026-04-20T11:37:00.935+0500 | 2026-04-20T16:43:16.065+0500
O2 | O2-2394 | O2-2394 | Sub-task | Sub-task |  | End to End Testing | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8 | 8 | Arslan sohail | 8 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2394 | [5 empty] | 2026-04-20T11:37:16.851+0500 | 2026-04-20T16:43:40.051+0500
O2 | O2-2395 | O2-2395 | Bug Subtask | Bug Subtask |  | Trigger is not getting deleted and an error is displayed | Resolved | 2026-04-20 |  | 2026-04-20 | 2026-04-20 | 0 | 0 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2395 | [5 empty] | 2026-04-20T12:27:13.441+0500 | 2026-04-21T14:20:30.337+0500
O2 | O2-2396 | O2-2396 | Epic | Epic |  | Support - Totalizer Calculation Pipeline Re-do (EMF) | To Do | 2026-04-01 | 2026-05-08 |  |  | 0 | 0 | Mohsin Junaid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | [5 empty] | 2026-04-20T14:25:35.510+0500 | 2026-04-20T14:28:28.909+0500
O2 | O2-2397 | O2-2397 | Story | Story |  | Documentation and Meetings | To Do |  |  |  |  | 0 | 0 | Taimur Zahid | 116 |  | O2-2396 | O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2397 | [5 empty] | 2026-04-20T14:28:17.324+0500 | 2026-04-20T14:28:17.538+0500
O2 | O2-2398 | O2-2398 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Mohsin Junaid | 56 |  | O2-2396 | O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2398 | [5 empty] | 2026-04-20T14:29:02.279+0500 | 2026-04-20T14:29:02.492+0500
O2 | O2-2399 | O2-2399 | Story | Story |  | Read API Experiments and Updates | To Do |  |  |  |  | 0 | 0 | Aiza Hamid | 40 |  | O2-2396 | O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | [5 empty] | 2026-04-20T14:29:55.152+0500 | 2026-04-20T15:18:03.525+0500
O2 | O2-24 | O2-24 | Story | Story |  | Research/DDS | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-11 | O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-24 | [5 empty] | 2025-10-02T14:10:51.996+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-240 | O2-240 | Sub-task | Sub-task |  | Anomaly Detection V3 OCM Development | Resolved! |  | 2025-10-17 |  |  | 0 | 0 | Ali Qumail | 36 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-240 | [5 empty] | 2025-10-09T11:39:12.268+0500 | 2025-10-20T11:46:47.024+0500
O2 | O2-2400 | O2-2400 | Story | Story |  | Data Mart and ADX Comparisons | To Do |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-2396 | O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2400 | [5 empty] | 2026-04-20T14:30:29.030+0500 | 2026-04-20T14:30:29.234+0500
O2 | O2-2401 | O2-2401 | Story | Story |  | Unit Testing | To Do |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-2396 | O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2401 | [5 empty] | 2026-04-20T14:30:53.574+0500 | 2026-04-20T14:30:53.811+0500
O2 | O2-2402 | O2-2402 | Story | Story |  | SQA Handover | To Do |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-2396 | O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2402 | [5 empty] | 2026-04-20T14:31:19.414+0500 | 2026-04-20T14:31:19.669+0500
O2 | O2-2403 | O2-2403 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-2396 | O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2396 | https://octopusdtlsupport.atlassian.net/browse/O2-2403 | [5 empty] | 2026-04-20T14:31:47.977+0500 | 2026-04-20T14:31:48.175+0500
O2 | O2-2404 | O2-2404 | Sub-task | Sub-task |  | Support - Totalizer Calculation Pipeline Re-do (EMF)-Documentation and Meetings-subtask | Resolved! |  |  | 2026-04-06 | 2026-04-20 | 0 | 0 | Mohsin Junaid | 88 |  | O2-2397 | O2-2397 | https://octopusdtlsupport.atlassian.net/browse/O2-2397 | https://octopusdtlsupport.atlassian.net/browse/O2-2404 | [5 empty] | 2026-04-20T14:34:20.459+0500 | 2026-04-30T10:19:46.533+0500
O2 | O2-2405 | O2-2405 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8 | 8 | Muhammad Abbas | 8 |  | O2-2385 | O2-2385 | https://octopusdtlsupport.atlassian.net/browse/O2-2385 | https://octopusdtlsupport.atlassian.net/browse/O2-2405 | [5 empty] | 2026-04-20T14:56:38.981+0500 | 2026-04-20T14:57:56.466+0500
O2 | O2-2406 | O2-2406 | Bug Subtask | Bug Subtask |  | Create Trigger API fails on decimal Recurrence input and shows multiple errors instead of a single validation message. | Resolved | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-20 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2406 | [5 empty] | 2026-04-20T15:07:55.437+0500 | 2026-04-22T16:26:39.008+0500
O2 | O2-2407 | O2-2407 | Sub-task | Sub-task |  | Support- Read API Null and Missing Values Discussion | In-Progress | 2026-04-07 | 2026-04-17 | 2026-04-07 | 2026-04-10 | 0 | 0 | Aiza Hamid | 28 |  | O2-2397 | O2-2397 | https://octopusdtlsupport.atlassian.net/browse/O2-2397 | https://octopusdtlsupport.atlassian.net/browse/O2-2407 | [5 empty] | 2026-04-20T15:11:22.059+0500 | 2026-04-20T15:14:30.908+0500
O2 | O2-2408 | O2-2408 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | 8 | 8 | Muhammad Abbas | 8 |  | O2-2112 | O2-2112 | https://octopusdtlsupport.atlassian.net/browse/O2-2112 | https://octopusdtlsupport.atlassian.net/browse/O2-2408 | [5 empty] | 2026-04-20T15:12:42.752+0500 | 2026-04-20T15:13:38.651+0500
O2 | O2-2409 | O2-2409 | Sub-task | Sub-task |  | Experimentation to replicate the same issue | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8 | 8 | Aiza Hamid | 5 |  | O2-2399 | O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2409 | [5 empty] | 2026-04-20T15:15:25.652+0500 | 2026-04-20T15:24:57.691+0500
O2 | O2-241 | O2-241 | Bug Subtask | Bug Subtask |  | After the recent release, the system is unable to create any type of connector — all API calls are failing. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-241 | [5 empty] | 2025-10-09T14:48:27.620+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2410 | O2-2410 | Sub-task | Sub-task |  | Totalizer tag added percentage | In-Progress | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-04-16 | 32 | 32 | Aiza Hamid | 24 |  | O2-2399 | O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2410 | [5 empty] | 2026-04-20T15:15:43.531+0500 | 2026-04-20T15:21:55.380+0500
O2 | O2-2411 | O2-2411 | Sub-task | Sub-task |  | Logging for totalizer tags in SQL and in blob | In-Progress | 2026-04-17 | 2026-04-20 | 2026-04-17 | 2026-04-17 | 8 | 8 | Aiza Hamid | 8 |  | O2-2399 | O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2411 | [5 empty] | 2026-04-20T15:15:56.062+0500 | 2026-04-20T15:24:12.075+0500
O2 | O2-2412 | O2-2412 | Sub-task | Sub-task |  | SQL optimization and redo of tasks | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8 | 8 | Aiza Hamid | 3 |  | O2-2399 | O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2399 | https://octopusdtlsupport.atlassian.net/browse/O2-2412 | [5 empty] | 2026-04-20T15:16:43.737+0500 | 2026-04-20T15:26:00.468+0500
O2 | O2-2413 | O2-2413 | Bug Subtask | Bug Subtask |  | 🚫Blocker: Trigger creation fails in UTC and data export fails in Local time due to incorrect time validation handling | Resolved | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-04-23 | 1.33 | 1.33 | Faiza Nasir | 1.33 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2413 | [5 empty] | 2026-04-20T15:29:18.349+0500 | 2026-04-23T15:58:36.204+0500
O2 | O2-2414 | O2-2414 | Sub-task | Sub-task |  | Implement info icon for time fields indicating all times should be in UTC | Resolved! | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2 | 2 | Faiza Nasir | 2 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2414 | [5 empty] | 2026-04-20T15:40:05.232+0500 | 2026-04-23T15:51:15.247+0500
O2 | O2-2415 | O2-2415 | Sub-task | Sub-task |  | BPM RunOnDemand Bug Fix | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8 | 8 | Arslan sohail | 8 |  | O2-1920 | O2-1920 | https://octopusdtlsupport.atlassian.net/browse/O2-1920 | https://octopusdtlsupport.atlassian.net/browse/O2-2415 | [5 empty] | 2026-04-20T16:11:06.554+0500 | 2026-04-20T16:44:56.723+0500
O2 | O2-2416 | O2-2416 | Story | Story |  | Bug Fixing | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 16 |  | O2-10 | O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-2416 | [5 empty] | 2026-04-20T16:17:02.439+0500 | 2026-04-20T16:17:16.447+0500
O2 | O2-2417 | O2-2417 | Sub-task | Sub-task |  | Republish Job With Updated variable value | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8 | 8 | Arslan sohail | 8 |  | O2-2416 | O2-2416 | https://octopusdtlsupport.atlassian.net/browse/O2-2416 | https://octopusdtlsupport.atlassian.net/browse/O2-2417 | [5 empty] | 2026-04-20T16:19:21.067+0500 | 2026-04-20T16:45:45.166+0500
O2 | O2-2418 | O2-2418 | Sub-task | Sub-task |  | Bug Fixing Batch/Bpm Schedule | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Arslan sohail | 8 |  | O2-2416 | O2-2416 | https://octopusdtlsupport.atlassian.net/browse/O2-2416 | https://octopusdtlsupport.atlassian.net/browse/O2-2418 | [5 empty] | 2026-04-20T16:21:22.522+0500 | 2026-04-20T16:46:02.990+0500
O2 | O2-2419 | O2-2419 | Sub-task | Sub-task |  | Design Review and Discussion | Resolved! | 2026-04-06 | 2026-04-16 | 2026-04-06 | 2026-04-13 | 24 | 24 | ahad omer | 24 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2419 | [5 empty] | 2026-04-20T16:36:57.965+0500 | 2026-04-20T16:46:15.113+0500
O2 | O2-242 | O2-242 | Sub-task | Sub-task |  | How To | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 40 |  | O2-113 | O2-113 | https://octopusdtlsupport.atlassian.net/browse/O2-113 | https://octopusdtlsupport.atlassian.net/browse/O2-242 | [5 empty] | 2025-10-09T15:27:37.952+0500 | 2025-11-13T18:51:26.382+0500
O2 | O2-2420 | O2-2420 | Bug Subtask | Bug Subtask |  | Trigger cannot be restarted after being stopped before first execution (of time. | Resolved | 2026-04-20 |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2420 | [5 empty] | 2026-04-20T16:40:41.525+0500 | 2026-04-23T14:23:29.841+0500
O2 | O2-2421 | O2-2421 | Sub-task | Sub-task |  | Batch/BPM Code Improvements and testing | Resolved! | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 16 | 16 | ahad omer | 16 |  | O2-1955 | O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-1955 | https://octopusdtlsupport.atlassian.net/browse/O2-2421 | [5 empty] | 2026-04-20T16:44:36.404+0500 | 2026-04-20T16:46:02.428+0500
O2 | O2-2422 | O2-2422 | Bug Subtask | Bug Subtask |  | Bug: I created an IT data pipeline, but when I edit the same pipeline, the pipeline type is shown as OT instead of IT. | Resolved | 2026-04-20 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 2 | 2 | Faiza Nasir | 2 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2422 | [5 empty] | 2026-04-21T11:53:13.179+0500 | 2026-04-22T16:15:20.127+0500
O2 | O2-2423 | O2-2423 | Bug Subtask | Bug Subtask |  | Bug: IT data is successfully exported to SQL, but the logs are not appearing on the Monitoring page. | Request received |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2423 | [5 empty] | 2026-04-21T11:54:51.201+0500 | 2026-04-22T16:00:44.931+0500
O2 | O2-2424 | O2-2424 | Bug Subtask | Bug Subtask |  | Bug: Trigger delete System Alarm is not available | Resolved | 2026-04-21 | 2026-04-23 | 2026-04-21 | 2026-04-23 | 1.33 | 1.33 | Faiza Nasir | 1.33 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2424 | [5 empty] | 2026-04-21T11:57:52.358+0500 | 2026-04-23T16:00:15.174+0500
O2 | O2-2425 | O2-2425 | Bug Subtask | Bug Subtask |  | Critical Bug: When the pipeline is stopped and restarted, it does not export data. | Resolved | 2026-04-21 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2425 | [5 empty] | 2026-04-21T12:03:10.342+0500 | 2026-04-24T11:58:47.112+0500
O2 | O2-2426 | O2-2426 | Bug Subtask | Bug Subtask |  | Bug: While associating tags from the wizard, the asset list is not being displayed. | Resolved | 2026-04-20 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2426 | [5 empty] | 2026-04-21T12:07:16.408+0500 | 2026-04-22T16:01:28.627+0500
O2 | O2-2427 | O2-2427 | Bug Subtask | Bug Subtask |  | Bug: After stopping and restarting the trigger, system alarms are not being triggered. | Resolved | 2026-04-20 | 2026-04-23 | 2026-04-22 | 2026-04-23 | 1.83 | 1.83 | Faiza Nasir | 1.83 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2427 | [5 empty] | 2026-04-21T12:10:34.127+0500 | 2026-04-24T11:37:40.393+0500
O2 | O2-2428 | O2-2428 | Bug Subtask | Bug Subtask |  | Bug: Permissions for Trigger Start/Stop, Create, Update, Delete, and Read are not available in the Roles and Permissions module. | Resolved | 2026-04-20 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 4 | 4 | Muhammad Usman Javed | 4 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2428 | [5 empty] | 2026-04-21T12:13:12.831+0500 | 2026-04-23T14:27:12.071+0500
O2 | O2-2429 | O2-2429 | Sub-task | Sub-task |  | Task: Error message should be only Pipeline name is duplicated or A Pipeline with this name already exist | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2429 | [5 empty] | 2026-04-21T12:26:52.202+0500 | 2026-04-22T16:24:55.641+0500
O2 | O2-243 | O2-243 | Sub-task | Sub-task |  | Restructure Enterprise Connectors to reflect latest updates + AI Friendly | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 20 |  | O2-100 | O2-100 | https://octopusdtlsupport.atlassian.net/browse/O2-100 | https://octopusdtlsupport.atlassian.net/browse/O2-243 | [5 empty] | 2025-10-09T15:31:04.781+0500 | 2025-10-13T22:29:19.841+0500
O2 | O2-2430 | O2-2430 | Bug Subtask | Bug Subtask |  | Read the title below | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2430 | [5 empty] | 2026-04-21T12:31:44.140+0500 | 2026-04-24T12:15:43.461+0500
O2 | O2-2431 | O2-2431 | Bug Subtask | Bug Subtask |  | Bug: The pipeline can still be edited while its associated trigger is turned on. The system should restrict users from editing a pipeline if any associated trigger is in the running state. | Resolved | 2026-04-20 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2431 | [5 empty] | 2026-04-21T12:34:23.193+0500 | 2026-04-24T12:09:57.600+0500
O2 | O2-2432 | O2-2432 | Bug Subtask | Bug Subtask |  | Bug: Trigger names should not be allowed to consist of only numbers. | Resolved | 2026-04-21 | 2026-04-21 | 2026-04-22 | 2026-04-22 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2432 | [5 empty] | 2026-04-21T12:36:01.791+0500 | 2026-04-23T16:11:35.118+0500
O2 | O2-2433 | O2-2433 | Bug Subtask | Bug Subtask |  | Bug: In the case of minute-based recurrence, the minimum allowed limit should be 5 minutes, as it was implemented in this module before this enhancement. | Resolved | 2026-04-20 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2433 | [5 empty] | 2026-04-21T12:37:04.387+0500 | 2026-04-24T12:17:26.542+0500
O2 | O2-2434 | O2-2434 | Bug Subtask | Bug Subtask |  | Bug: Trigger should not create with only underscore in the name | Resolved | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2434 | [5 empty] | 2026-04-21T12:38:36.606+0500 | 2026-04-24T12:19:49.480+0500
O2 | O2-2435 | O2-2435 | Bug Subtask | Bug Subtask |  | An undefined/empty space is displayed at the bottom of the Trigger list page. Scrollbar is not properly implemented on the Trigger list page, resulting in a large empty space at the bottom. | On Hold |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2435 | [5 empty] | 2026-04-21T12:40:00.566+0500 | 2026-04-30T09:59:25.099+0500
O2 | O2-2436 | O2-2436 | Bug Subtask | Bug Subtask |  | Bug (Security Concern): Password field can be exposed via DOM manipulation Issue: | On Hold |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2436 | [5 empty] | 2026-04-21T12:42:12.183+0500 | 2026-04-30T09:59:43.659+0500
O2 | O2-2437 | O2-2437 | Bug Subtask | Bug Subtask |  | Bug: Trigger name is not visible on the Monitoring page, which is necessary because multiple triggers can be associated with a single pipeline. | Resolved | 2026-04-22 | 2026-04-24 | 2026-04-22 | 2026-04-23 | 4 | 4 | Faiza Nasir | 4 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2437 | [5 empty] | 2026-04-21T12:45:30.576+0500 | 2026-04-24T12:25:02.719+0500
O2 | O2-2438 | O2-2438 | Sub-task | Sub-task |  | Task: This should be Site name | Resolved! | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-04-21 | 0.17 | 0.17 | Faiza Nasir | 0.17 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2438 | [5 empty] | 2026-04-21T12:46:53.324+0500 | 2026-04-22T16:06:51.593+0500
O2 | O2-2439 | O2-2439 | Bug Subtask | Bug Subtask |  | Bug: Unable to export Site Hierarchy | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2439 | [5 empty] | 2026-04-21T12:48:04.188+0500 | 2026-04-24T12:26:15.050+0500
O2 | O2-244 | O2-244 | Sub-task | Sub-task |  | REST API Fields and How Tos | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 16 |  | O2-100 | O2-100 | https://octopusdtlsupport.atlassian.net/browse/O2-100 | https://octopusdtlsupport.atlassian.net/browse/O2-244 | [5 empty] | 2025-10-09T15:31:36.149+0500 | 2025-10-22T11:30:56.051+0500
O2 | O2-2440 | O2-2440 | Bug Subtask | Bug Subtask |  | Bug: In the case of Data, Stat, and Quality Code alarms, the following options should not be displayed: Resolution Value Data Quality Filter Aggregate | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2440 | [5 empty] | 2026-04-21T12:49:02.536+0500 | 2026-04-24T12:27:31.179+0500
O2 | O2-2441 | O2-2441 | Bug Subtask | Bug Subtask |  | Bug: Unable to export alarms | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2441 | [5 empty] | 2026-04-21T12:50:08.727+0500 | 2026-04-24T12:31:36.914+0500
O2 | O2-2442 | O2-2442 | Bug Subtask | Bug Subtask |  | Site Hierarchy trigger created successfully but data is not exported to SQL | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2442 | [5 empty] | 2026-04-21T14:43:48.789+0500 | 2026-04-24T12:33:14.651+0500
O2 | O2-2443 | O2-2443 | Sub-task | Sub-task |  | QA Reported Bugs | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 3 | 3 | Zain Munir | 3 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2443 | [5 empty] | 2026-04-21T15:08:38.586+0500 | 2026-04-21T15:09:15.944+0500
O2 | O2-2444 | O2-2444 | Sub-task | Sub-task |  | Tags creation | Resolved! | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8 | 8 | Ameer Hamza Khan | 8 |  | O2-2347 | O2-2347 | https://octopusdtlsupport.atlassian.net/browse/O2-2347 | https://octopusdtlsupport.atlassian.net/browse/O2-2444 | [5 empty] | 2026-04-21T16:19:31.005+0500 | 2026-04-21T16:20:46.497+0500
O2 | O2-2445 | O2-2445 | Sub-task | Sub-task |  | Alarms configuration | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 8 | 8 | Ameer Hamza Khan | 16 |  | O2-2347 | O2-2347 | https://octopusdtlsupport.atlassian.net/browse/O2-2347 | https://octopusdtlsupport.atlassian.net/browse/O2-2445 | [5 empty] | 2026-04-21T16:19:42.864+0500 | 2026-04-28T10:25:19.440+0500
O2 | O2-2446 | O2-2446 | Bug Subtask | Bug Subtask |  | Changings are not getting saved and Showing Error after deleting few tags from SQL pipeline | Resolved | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-22 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2446 | [5 empty] | 2026-04-22T11:20:37.089+0500 | 2026-04-24T12:34:26.322+0500
O2 | O2-2447 | O2-2447 | Bug Subtask | Bug Subtask |  | Mapped name of tags are not getting displayed | Resolved | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2447 | [5 empty] | 2026-04-22T11:30:31.132+0500 | 2026-04-24T12:36:53.631+0500
O2 | O2-2448 | O2-2448 | Story | Story |  | Sanity_Testing_4/21/26(Staging) | Resolved! | 2026-04-21 | 2026-04-22 |  |  | 24 | 24 | Waqar Rasheed | 106.25 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | [5 empty] | 2026-04-22T11:31:44.761+0500 | 2026-04-30T09:52:12.072+0500
O2 | O2-2449 | O2-2449 | Sub-task | Sub-task |  | Testing by kamran | Resolved! | 2026-04-21 | 2026-04-23 | 2026-04-21 | 2026-04-23 | 24 | 24 | kamran khalid | 19 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2449 | [5 empty] | 2026-04-22T11:32:41.667+0500 | 2026-05-12T15:43:12.235+0500
O2 | O2-245 | O2-245 | Bug Subtask | Bug Subtask |  | Latest values for some real time tags are not updating also other tag values are updating with 5 mins interval | Resolved |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-245 | [5 empty] | 2025-10-09T15:37:38.464+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2450 | O2-2450 | Sub-task | Sub-task |  | Testing by Waqar | Resolved! | 2026-04-22 | 2026-04-24 | 2026-04-22 | 2026-04-29 | 26.5 | 26.5 | Waqar Rasheed | 26.25 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2450 | [5 empty] | 2026-04-22T11:32:53.587+0500 | 2026-04-29T15:10:50.197+0500
O2 | O2-2451 | O2-2451 | Bug Subtask | Bug Subtask |  | Diagnostics Alarm Not Triggered Despite No Latest Values Since 10:55 | Resolved | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-22 | 8 | 8 | Mohsin Junaid | 8 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2451 | [5 empty] | 2026-04-22T11:35:56.343+0500 | 2026-04-22T12:30:18.171+0500
O2 | O2-2452 | O2-2452 | Bug Subtask | Bug Subtask |  | Data center Specified module failed on staging | Resolved |  |  | 2026-04-22 | 2026-04-22 | 1 | 1 | Faiza Nasir | 1 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2452 | [5 empty] | 2026-04-22T11:50:44.431+0500 | 2026-04-22T12:07:35.408+0500
O2 | O2-2455 | O2-2455 | Bug Subtask | Bug Subtask |  | “Get Latest Values” Not Working for Single and Bulk Write Back | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2455 | [5 empty] | 2026-04-22T12:07:51.163+0500 | 2026-04-22T12:44:46.475+0500
O2 | O2-2456 | O2-2456 | Bug Subtask | Bug Subtask |  | IT table and Time stamp column name is getting removed , While editing IT pipelines. | Resolved | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2456 | [5 empty] | 2026-04-22T12:16:52.182+0500 | 2026-04-24T12:38:15.007+0500
O2 | O2-2457 | O2-2457 | Bug Subtask | Bug Subtask |  | State duplication occurred in Totalizer tags Alarms | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2457 | [5 empty] | 2026-04-22T12:19:47.685+0500 | 2026-04-22T12:20:17.381+0500
O2 | O2-2458 | O2-2458 | Bug Subtask | Bug Subtask |  | Unable to Verify Phone number for SMS alerts | Development |  |  |  |  | 2 | 2 | Muhammad Usman Javed | 0 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2458 | [5 empty] | 2026-04-22T12:26:11.384+0500 | 2026-04-22T15:35:23.488+0500
O2 | O2-2459 | O2-2459 | Bug Subtask | Bug Subtask |  | Diagnostics Email Alerts Are Not Being Received | Development |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2459 | [5 empty] | 2026-04-22T12:26:48.565+0500 | 2026-04-22T12:30:16.979+0500
O2 | O2-2460 | O2-2460 | Bug Subtask | Bug Subtask |  | Scheduled scanning is unable to retrieve new parameters in the case of Digital Log. Additionally, on multiple scan triggers, it is duplicating the newly added parameters. | Development |  |  | 2026-04-22 | 2026-04-22 | 4 | 4 | Muhammad Usman Javed | 4 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2460 | [5 empty] | 2026-04-22T13:21:15.582+0500 | 2026-04-22T15:29:02.017+0500
O2 | O2-2461 | O2-2461 | Sub-task | Sub-task |  | Implement and integrate hyperbolic functions (sinh, cosh, tanh, etc.) in both offline and online calculation flows, ensuring consistency and validating results through developer testing + Backfilling of missing data on Prod - AZ | Resolved! | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 7.5 | 7.5 | Arsalan Zafar Khan | 7 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2461 | [5 empty] | 2026-04-22T15:05:35.877+0500 | 2026-04-23T15:34:57.644+0500
O2 | O2-2462 | O2-2462 | Sub-task | Sub-task |  | Research and fix SOLVER formula calculation to return expected values | Resolved! | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2 | 2 | Arsalan Zafar Khan | 2 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2462 | [5 empty] | 2026-04-22T15:14:57.626+0500 | 2026-04-22T15:16:33.368+0500
O2 | O2-2463 | O2-2463 | Sub-task | Sub-task |  | Batch Backend Development | Resolved! | 2026-03-17 | 2026-03-25 | 2026-03-17 | 2026-03-25 | 32 | 32 | Syed Yousaf Qadri | 26 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-2463 | [5 empty] | 2026-04-22T15:50:00.342+0500 | 2026-04-22T15:55:18.233+0500
O2 | O2-2464 | O2-2464 | Sub-task | Sub-task |  | Unit Testing | Resolved! | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-26 | 8 | 8 | Syed Yousaf Qadri | 8 |  | O2-1437 | O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-1437 | https://octopusdtlsupport.atlassian.net/browse/O2-2464 | [5 empty] | 2026-04-22T15:55:32.392+0500 | 2026-04-22T15:57:00.035+0500
O2 | O2-2465 | O2-2465 | Sub-task | Sub-task |  | Omni-ALA Walk through Sessions + Discussion | Resolved! | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | 12 | 12 | Muhammad Zeeshan Aslam | 12 |  | O2-2124 | O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2124 | https://octopusdtlsupport.atlassian.net/browse/O2-2465 | [5 empty] | 2026-04-22T16:08:45.741+0500 | 2026-04-22T16:10:34.324+0500
O2 | O2-2466 | O2-2466 | Story | Story |  | Demo & Presentation | In-Progress |  |  | 2026-04-07 | 2026-04-22 | 0 | 0 | Ibrahim Ahmed Qureshi | 44 |  | O2-1340 | O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-1340 | https://octopusdtlsupport.atlassian.net/browse/O2-2466 | [5 empty] | 2026-04-22T16:10:23.595+0500 | 2026-04-22T16:25:03.306+0500
O2 | O2-2467 | O2-2467 | Sub-task | Sub-task |  | Add charting to Output Schemas | Resolved! |  |  | 2026-03-25 | 2026-03-27 | 0 | 0 | Ibrahim Ahmed Qureshi | 24 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2467 | [5 empty] | 2026-04-22T16:14:18.434+0500 | 2026-04-22T16:17:09.909+0500
O2 | O2-2468 | O2-2468 | Sub-task | Sub-task |  | Add Bar to charting | Resolved! |  |  | 2026-03-23 | 2026-03-23 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2468 | [5 empty] | 2026-04-22T16:14:28.415+0500 | 2026-04-22T16:17:56.310+0500
O2 | O2-2469 | O2-2469 | Sub-task | Sub-task |  | Add line to charting | Resolved! |  |  | 2026-03-24 | 2026-03-24 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2469 | [5 empty] | 2026-04-22T16:14:38.239+0500 | 2026-04-22T16:18:21.413+0500
O2 | O2-247 | O2-247 | Bug Subtask | Bug Subtask |  | Real time totalizer tag values are not updated in latest values screen, where as cal tag totalizer values are updated. | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-247 | [5 empty] | 2025-10-09T16:12:23.400+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2470 | O2-2470 | Sub-task | Sub-task |  | Add column to charting | Resolved! |  |  | 2026-03-30 | 2026-03-30 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2470 | [5 empty] | 2026-04-22T16:15:05.328+0500 | 2026-04-22T16:18:41.091+0500
O2 | O2-2471 | O2-2471 | Sub-task | Sub-task |  | Collapse Resolver to Orchestrator | Resolved! |  |  | 2026-04-15 | 2026-04-17 | 0 | 0 | Ibrahim Ahmed Qureshi | 16 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2471 | [5 empty] | 2026-04-22T16:15:33.013+0500 | 2026-04-22T16:23:38.568+0500
O2 | O2-2472 | O2-2472 | Sub-task | Sub-task |  | Integration Testing | To Do |  |  | 2026-03-10 | 2026-03-18 | 0 | 0 | Ibrahim Ahmed Qureshi | 40.5 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-2472 | [5 empty] | 2026-04-22T16:19:24.147+0500 | 2026-04-22T16:22:48.650+0500
O2 | O2-2473 | O2-2473 | Sub-task | Sub-task |  | Agent Improvements | To Do |  |  | 2026-03-16 | 2026-03-16 | 0 | 0 | Unassigned | 6.5 |  | O2-1342 | O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-1342 | https://octopusdtlsupport.atlassian.net/browse/O2-2473 | [5 empty] | 2026-04-22T16:21:54.887+0500 | 2026-04-22T16:22:18.011+0500
O2 | O2-2474 | O2-2474 | Sub-task | Sub-task |  | Improve Instructions for each agent | Resolved! |  |  | 2026-04-20 | 2026-04-20 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-2003 | O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2003 | https://octopusdtlsupport.atlassian.net/browse/O2-2474 | [5 empty] | 2026-04-22T16:24:13.601+0500 | 2026-04-22T16:24:46.650+0500
O2 | O2-2475 | O2-2475 | Story | Story |  | KT | To Do | 2026-03-27 | 2026-03-30 |  |  | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-2475 | [5 empty] | 2026-04-22T16:29:57.011+0500 | 2026-04-22T16:33:05.665+0500
O2 | O2-2476 | O2-2476 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-2476 | [5 empty] | 2026-04-22T16:30:41.001+0500 | 2026-04-22T16:31:15.467+0500
O2 | O2-2477 | O2-2477 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-1953 | O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-1953 | https://octopusdtlsupport.atlassian.net/browse/O2-2477 | [5 empty] | 2026-04-22T16:31:07.998+0500 | 2026-04-22T16:31:17.727+0500
O2 | O2-2478 | O2-2478 | Bug Subtask | Bug Subtask |  | No data is getting exported to SQL nor Monitoring logs are getting displayed | Request received |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2478 | [5 empty] | 2026-04-22T16:32:28.748+0500 | 2026-04-22T16:52:18.999+0500
O2 | O2-2479 | O2-2479 | Sub-task | Sub-task |  | Code Review | To Do | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 16 | 16 | Syed Yousaf Qadri | 16 |  | O2-2475 | O2-2475 | https://octopusdtlsupport.atlassian.net/browse/O2-2475 | https://octopusdtlsupport.atlassian.net/browse/O2-2479 | [5 empty] | 2026-04-22T16:33:25.249+0500 | 2026-04-22T16:34:52.761+0500
O2 | O2-248 | O2-248 | Sub-task | Sub-task |  | The development team needs to add support for REST APIs without time parameters. | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-248 | [5 empty] | 2025-10-09T17:27:31.357+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-2480 | O2-2480 | Sub-task | Sub-task |  | Architecture Design | Resolved! | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8 | 8 | Syed Yousaf Qadri | 8 |  | O2-2281 | O2-2281 | https://octopusdtlsupport.atlassian.net/browse/O2-2281 | https://octopusdtlsupport.atlassian.net/browse/O2-2480 | [5 empty] | 2026-04-22T16:49:03.975+0500 | 2026-04-22T16:49:59.783+0500
O2 | O2-2481 | O2-2481 | Sub-task | Sub-task |  | Batch Alarm Engine POC | To Do | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-22 | 24 | 24 | Syed Yousaf Qadri | 24 |  | O2-2282 | O2-2282 | https://octopusdtlsupport.atlassian.net/browse/O2-2282 | https://octopusdtlsupport.atlassian.net/browse/O2-2481 | [5 empty] | 2026-04-22T16:51:12.818+0500 | 2026-04-22T16:52:51.869+0500
O2 | O2-2482 | O2-2482 | Sub-task | Sub-task |  | Batch Alarm Engine Design | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2282 | O2-2282 | https://octopusdtlsupport.atlassian.net/browse/O2-2282 | https://octopusdtlsupport.atlassian.net/browse/O2-2482 | [5 empty] | 2026-04-22T16:51:40.084+0500 | 2026-04-22T16:51:40.355+0500
O2 | O2-2483 | O2-2483 | Sub-task | Sub-task |  | Handover session - kamran | Resolved! |  |  | 2026-04-16 | 2026-04-16 | 1 | 1 | Unassigned | 1 |  | O2-2273 | O2-2273 | https://octopusdtlsupport.atlassian.net/browse/O2-2273 | https://octopusdtlsupport.atlassian.net/browse/O2-2483 | [5 empty] | 2026-04-23T11:02:05.467+0500 | 2026-04-23T11:03:00.298+0500
O2 | O2-2484 | O2-2484 | Sub-task | Sub-task |  | Testing BY Kamran | Resolved! |  |  | 2026-04-16 | 2026-04-20 | 24 | 24 | Unassigned | 24 |  | O2-2274 | O2-2274 | https://octopusdtlsupport.atlassian.net/browse/O2-2274 | https://octopusdtlsupport.atlassian.net/browse/O2-2484 | [5 empty] | 2026-04-23T11:03:49.378+0500 | 2026-04-23T11:05:21.585+0500
O2 | O2-2485 | O2-2485 | Sub-task | Sub-task |  | Handover to QA | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 1 | 1 | Sarmad Sabir | 1 |  | O2-2265 | O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2265 | https://octopusdtlsupport.atlassian.net/browse/O2-2485 | [5 empty] | 2026-04-23T14:47:55.892+0500 | 2026-04-23T14:48:30.252+0500
O2 | O2-2486 | O2-2486 | Sub-task | Sub-task |  | Requirements Change / Rework | Resolved! | 2026-04-15 | 2026-04-24 | 2026-04-15 | 2026-04-23 | 40 | 40 | Sarmad Sabir | 39 |  | O2-1977 | O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-1977 | https://octopusdtlsupport.atlassian.net/browse/O2-2486 | [5 empty] | 2026-04-23T14:49:00.221+0500 | 2026-04-27T12:07:06.661+0500
O2 | O2-2487 | O2-2487 | Bug Subtask | Bug Subtask |  | Need to remove the extra stats alarms related to Schedule SQL start and stop | Resolved | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-23 | 1 | 1 | Faiza Nasir | 1 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2487 | [5 empty] | 2026-04-23T15:27:42.752+0500 | 2026-04-24T12:43:52.389+0500
O2 | O2-2488 | O2-2488 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-24 | 16 | 16 | Muhammad Abbas | 16 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2488 | [5 empty] | 2026-04-24T10:41:48.166+0500 | 2026-05-12T14:42:01.693+0500
O2 | O2-2489 | O2-2489 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-29 | 8 | 8 | Zeeshan Sarwar | 32 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2489 | [5 empty] | 2026-04-24T10:41:58.937+0500 | 2026-04-29T17:02:54.530+0500
O2 | O2-249 | O2-249 | Sub-task | Sub-task |  | Enhance the system to support custom date-time formats while creating connectors. | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-249 | [5 empty] | 2025-10-09T17:33:08.190+0500 | 2025-10-16T10:02:48.873+0500
O2 | O2-2490 | O2-2490 | Sub-task | Sub-task |  | Unit Testing & Fixes | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 8 | 8 | Zain Munir | 8 |  | O2-1993 | O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-1993 | https://octopusdtlsupport.atlassian.net/browse/O2-2490 | [5 empty] | 2026-04-24T11:51:54.855+0500 | 2026-04-24T11:52:31.902+0500
O2 | O2-2491 | O2-2491 | Bug Subtask | Bug Subtask |  | Weekly Scheduled export to SQL FAILED, NO monitoring no export | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2491 | [5 empty] | 2026-04-24T15:49:16.292+0500 | 2026-04-30T10:16:23.377+0500
O2 | O2-2492 | O2-2492 | Bug Subtask | Bug Subtask |  | Schedule Type as Monthly Export is also Failed with Data Alarm | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2492 | [5 empty] | 2026-04-24T15:52:53.449+0500 | 2026-04-30T10:04:29.699+0500
O2 | O2-2493 | O2-2493 | Sub-task | Sub-task |  | Bugs Fixing and management | In-Progress | 2026-04-15 | 2026-04-29 | 2026-04-15 | 2026-04-29 | 64 | 64 | Ameer Hamza Khan | 64 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2493 | [5 empty] | 2026-04-27T08:57:34.982+0500 | 2026-04-29T09:53:04.358+0500
O2 | O2-2494 | O2-2494 | Sub-task | Sub-task |  | Task | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2494 | [5 empty] | 2026-04-27T09:45:46.010+0500 | 2026-04-27T09:47:03.386+0500
O2 | O2-2495 | O2-2495 | Sub-task | Sub-task |  | Bug Fixing and Discussions | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 8 | 8 | Faiza Nasir | 8 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2495 | [5 empty] | 2026-04-27T10:22:49.657+0500 | 2026-04-27T10:24:42.463+0500
O2 | O2-2496 | O2-2496 | Epic | Epic |  | Streaming Pub/Sub Architecture | To Do | 2026-04-20 | 2026-05-29 |  |  | 232 | 232 | Ayyan Babar | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2496 | [5 empty] | 2026-04-27T11:18:22.898+0500 | 2026-04-28T08:55:35.431+0500
O2 | O2-2497 | O2-2497 | Story | Story |  | URS/DDS | To Do | 2026-05-04 | 2026-05-06 |  |  | 16 | 16 | Ayyan Babar | 0 |  | O2-2496 | O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2497 | [5 empty] | 2026-04-27T11:23:36.885+0500 | 2026-04-27T14:23:18.157+0500
O2 | O2-2498 | O2-2498 | Story | Story |  | Development | To Do | 2026-05-07 | 2026-05-25 |  |  | 112 | 112 | Ayyan Babar | 0 |  | O2-2496 | O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2498 | [5 empty] | 2026-04-27T11:23:51.433+0500 | 2026-04-27T14:23:44.695+0500
O2 | O2-2499 | O2-2499 | Story | Story |  | QA Handover | To Do | 2026-05-26 | 2026-05-26 |  |  | 8 | 8 | Ayyan Babar | 0 |  | O2-2496 | O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2499 | [5 empty] | 2026-04-27T11:24:02.993+0500 | 2026-04-27T14:25:10.384+0500
O2 | O2-25 | O2-25 | Story | Story |  | Dev | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-11 | O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-25 | [5 empty] | 2025-10-02T14:11:04.245+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-250 | O2-250 | Sub-task | Sub-task |  | Trigger execution functionality should be separated from data fetching logic. | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-250 | [5 empty] | 2025-10-09T17:41:41.311+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-2500 | O2-2500 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-2496 | O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2500 | [5 empty] | 2026-04-27T11:24:25.876+0500 | 2026-04-27T11:24:58.415+0500
O2 | O2-2501 | O2-2501 | Story | Story |  | Production Release | To Do | 2026-05-28 | 2026-05-29 |  |  | 16 | 16 | Ayyan Babar | 0 |  | O2-2496 | O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2496 | https://octopusdtlsupport.atlassian.net/browse/O2-2501 | [5 empty] | 2026-04-27T11:24:41.842+0500 | 2026-04-27T14:25:26.761+0500
O2 | O2-2502 | O2-2502 | Sub-task | Sub-task |  | Process Testing (P) | To Do |  |  |  |  | 24 | 24 | Faiq Butt | 0 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2502 | [5 empty] | 2026-04-27T11:49:41.539+0500 | 2026-04-27T11:50:12.077+0500
O2 | O2-2503 | O2-2503 | Sub-task | Sub-task |  | Non-Ebs Advisory Calculations | Resolved! | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-30 | 32 | 32 | Faiq Butt | 32 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2503 | [5 empty] | 2026-04-27T11:56:58.874+0500 | 2026-05-07T09:04:27.007+0500
O2 | O2-2504 | O2-2504 | Sub-task | Sub-task |  | Dispatch Advisory Methodology (P) | In-Progress | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-30 | 32 | 32 | Danish Rashid | 32 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2504 | [5 empty] | 2026-04-27T12:00:39.806+0500 | 2026-05-05T09:42:53.451+0500
O2 | O2-2505 | O2-2505 | Sub-task | Sub-task |  | Cost Review and Optimizations | Resolved! | 2026-03-16 | 2026-03-31 | 2026-03-18 | 2026-03-25 | 40 | 40 | Taimur Zahid | 14.5 |  | O2-1990 | O2-1990 | https://octopusdtlsupport.atlassian.net/browse/O2-1990 | https://octopusdtlsupport.atlassian.net/browse/O2-2505 | [5 empty] | 2026-04-27T12:01:34.444+0500 | 2026-04-27T12:04:29.847+0500
O2 | O2-2506 | O2-2506 | Sub-task | Sub-task |  | Process Testing (P) | To Do | 2026-05-13 | 2026-05-31 |  |  | 40 | 40 | Danish Rashid | 0 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2506 | [5 empty] | 2026-04-27T12:01:41.877+0500 | 2026-05-11T09:49:51.194+0500
O2 | O2-2507 | O2-2507 | Story | Story |  | Azure Region Availability | Resolved! | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 16 | 16 | Taimur Zahid | 8 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-2507 | [5 empty] | 2026-04-27T12:06:09.843+0500 | 2026-04-27T12:07:37.558+0500
O2 | O2-2508 | O2-2508 | Sub-task | Sub-task |  | Product Demo to Kwang 24/04/26 | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 12 | 12 | Sarmad Sabir | 12 |  | O2-705 | O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | https://octopusdtlsupport.atlassian.net/browse/O2-2508 | [5 empty] | 2026-04-27T12:08:02.833+0500 | 2026-04-27T12:09:16.301+0500
O2 | O2-2509 | O2-2509 | Story | Story |  | Key Vault Integration - March | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8 | 8 | Taimur Zahid | 4 |  | O2-1109 | O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-1109 | https://octopusdtlsupport.atlassian.net/browse/O2-2509 | [5 empty] | 2026-04-27T12:08:22.600+0500 | 2026-04-27T12:10:46.325+0500
O2 | O2-251 | O2-251 | Bug Subtask | Bug Subtask |  | Latest values not updating since yesterday but Diagnostics alarm not fired yet | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-251 | [5 empty] | 2025-10-10T09:50:12.612+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2510 | O2-2510 | Epic | Epic |  | GitHub Administration | To Do | 2026-04-01 | 2026-04-30 |  |  | 8 | 8 | Taimur Zahid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2510 | [5 empty] | 2026-04-27T12:11:41.675+0500 | 2026-04-27T12:13:18.412+0500
O2 | O2-2511 | O2-2511 | Story | Story |  | GitHub Copilot Access and Administration | Resolved! | 2026-04-01 | 2026-04-30 |  |  | 8 | 8 | Taimur Zahid | 4 |  | O2-2510 | O2-2510 | https://octopusdtlsupport.atlassian.net/browse/O2-2510 | https://octopusdtlsupport.atlassian.net/browse/O2-2511 | [5 empty] | 2026-04-27T12:14:07.093+0500 | 2026-04-27T12:18:21.649+0500
O2 | O2-2512 | O2-2512 | Sub-task | Sub-task |  | Copilot Access and Administration | Resolved! | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-01 | 8 | 8 | Taimur Zahid | 4 |  | O2-2511 | O2-2511 | https://octopusdtlsupport.atlassian.net/browse/O2-2511 | https://octopusdtlsupport.atlassian.net/browse/O2-2512 | [5 empty] | 2026-04-27T12:14:41.975+0500 | 2026-04-27T12:16:05.497+0500
O2 | O2-2513 | O2-2513 | Story | Story |  | Audit Report | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 4 | 4 | Taimur Zahid | 4 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-2513 | [5 empty] | 2026-04-27T12:25:39.335+0500 | 2026-04-27T12:31:14.122+0500
O2 | O2-2514 | O2-2514 | Story | Story |  | Support - Device Diagnostics Enhancement | Resolved! | 2026-04-14 | 2026-04-17 |  |  | 30 | 30 | Muhammad Ahmad Saleem | 30 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | [5 empty] | 2026-04-27T12:31:34.386+0500 | 2026-04-27T13:04:25.274+0500
O2 | O2-2515 | O2-2515 | Sub-task | Sub-task |  | Code Research + Understanding | Resolved! | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 6 | 6 | Muhammad Ahmad Saleem | 6 |  | O2-2514 | O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2515 | [5 empty] | 2026-04-27T12:32:28.556+0500 | 2026-04-27T12:33:39.677+0500
O2 | O2-2516 | O2-2516 | Sub-task | Sub-task |  | Integration of graph and new tab(OPC Server) | Resolved! | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2514 | O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2516 | [5 empty] | 2026-04-27T12:55:26.623+0500 | 2026-04-27T12:56:44.134+0500
O2 | O2-2517 | O2-2517 | Sub-task | Sub-task |  | Deployment to staging + Bug Fixing | Resolved! | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2514 | O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2517 | [5 empty] | 2026-04-27T13:01:13.960+0500 | 2026-04-27T13:01:57.068+0500
O2 | O2-2518 | O2-2518 | Sub-task | Sub-task |  | Bug Fixing | Resolved! | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-2514 | O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2514 | https://octopusdtlsupport.atlassian.net/browse/O2-2518 | [5 empty] | 2026-04-27T13:02:27.719+0500 | 2026-04-27T13:03:14.816+0500
O2 | O2-2519 | O2-2519 | Sub-task | Sub-task |  | Meeting + Code Understanding | Resolved! | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2193 | O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2519 | [5 empty] | 2026-04-27T13:45:40.745+0500 | 2026-04-27T13:47:35.193+0500
O2 | O2-252 | O2-252 | Sub-task | Sub-task |  | Design Document template creation using AI | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 15 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-252 | [5 empty] | 2025-10-10T10:13:49.040+0500 | 2025-10-13T17:59:08.706+0500
O2 | O2-2520 | O2-2520 | Sub-task | Sub-task |  | Meeting + Code Understanding | Resolved! | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2203 | O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2520 | [5 empty] | 2026-04-27T13:46:40.989+0500 | 2026-04-27T13:48:13.287+0500
O2 | O2-2521 | O2-2521 | Epic | Epic |  | Integrate Monaco Editor For SQL Support | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | [5 empty] | 2026-04-27T16:13:20.021+0500 | 2026-04-27T16:13:20.175+0500
O2 | O2-2522 | O2-2522 | Epic | Epic |  | Support for SQL Language in Batch(Features Supported by adx) | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | [5 empty] | 2026-04-27T16:13:43.627+0500 | 2026-04-27T16:13:43.768+0500
O2 | O2-2523 | O2-2523 | Epic | Epic |  | Support for SQL Language in BPM(Features Supported by adx) | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | [5 empty] | 2026-04-27T16:14:02.206+0500 | 2026-04-27T16:14:02.315+0500
O2 | O2-2524 | O2-2524 | Story | Story |  | Research | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2521 | O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2524 | [5 empty] | 2026-04-27T16:14:51.019+0500 | 2026-04-27T16:14:51.207+0500
O2 | O2-2525 | O2-2525 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2521 | O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2525 | [5 empty] | 2026-04-27T16:15:15.155+0500 | 2026-04-27T16:15:15.375+0500
O2 | O2-2526 | O2-2526 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2521 | O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2526 | [5 empty] | 2026-04-27T16:15:26.171+0500 | 2026-04-27T16:15:26.378+0500
O2 | O2-2527 | O2-2527 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2521 | O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2527 | [5 empty] | 2026-04-27T16:15:38.695+0500 | 2026-04-27T16:15:38.877+0500
O2 | O2-2528 | O2-2528 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2521 | O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2528 | [5 empty] | 2026-04-27T16:15:51.141+0500 | 2026-04-27T16:15:51.323+0500
O2 | O2-2529 | O2-2529 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2521 | O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2529 | [5 empty] | 2026-04-27T16:16:01.419+0500 | 2026-04-27T16:16:01.586+0500
O2 | O2-253 | O2-253 | Story | Story |  | Cost Estimation - Key Vault | Resolved! | 2025-10-13 | 2025-10-17 |  |  | 8 | 8 | Taimur Zahid | 8 |  | O2-1460 | O2-1460 | https://octopusdtlsupport.atlassian.net/browse/O2-1460 | https://octopusdtlsupport.atlassian.net/browse/O2-253 | [5 empty] | 2025-10-10T10:27:55.625+0500 | 2026-02-19T15:35:30.141+0500
O2 | O2-2530 | O2-2530 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2521 | O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2521 | https://octopusdtlsupport.atlassian.net/browse/O2-2530 | [5 empty] | 2026-04-27T16:16:09.212+0500 | 2026-04-27T16:16:09.440+0500
O2 | O2-2531 | O2-2531 | Story | Story |  | Research | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2522 | O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2531 | [5 empty] | 2026-04-27T16:17:16.263+0500 | 2026-04-27T16:17:16.458+0500
O2 | O2-2532 | O2-2532 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2522 | O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2532 | [5 empty] | 2026-04-27T16:17:25.253+0500 | 2026-04-27T16:17:25.440+0500
O2 | O2-2533 | O2-2533 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2522 | O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2533 | [5 empty] | 2026-04-27T16:17:36.675+0500 | 2026-04-27T16:17:36.824+0500
O2 | O2-2534 | O2-2534 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2522 | O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2534 | [5 empty] | 2026-04-27T16:17:44.910+0500 | 2026-04-27T16:17:45.103+0500
O2 | O2-2535 | O2-2535 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2522 | O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2535 | [5 empty] | 2026-04-27T16:18:00.037+0500 | 2026-04-27T16:18:00.257+0500
O2 | O2-2536 | O2-2536 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2522 | O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2536 | [5 empty] | 2026-04-27T16:18:10.282+0500 | 2026-04-27T16:18:10.479+0500
O2 | O2-2537 | O2-2537 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2522 | O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2522 | https://octopusdtlsupport.atlassian.net/browse/O2-2537 | [5 empty] | 2026-04-27T16:18:22.249+0500 | 2026-04-27T16:18:22.477+0500
O2 | O2-2538 | O2-2538 | Story | Story |  | Research | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2523 | O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2538 | [5 empty] | 2026-04-27T16:18:49.836+0500 | 2026-04-27T16:18:50.218+0500
O2 | O2-2539 | O2-2539 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2523 | O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2539 | [5 empty] | 2026-04-27T16:19:09.096+0500 | 2026-04-27T16:19:09.278+0500
O2 | O2-254 | O2-254 | Story | Story |  | Cost Estimation - Defender for Cloud/IOT | Resolved! |  | 2025-10-17 |  |  | 16 | 16 | Taimur Zahid | 8 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-254 | [5 empty] | 2025-10-10T10:28:31.171+0500 | 2026-02-20T15:14:23.526+0500
O2 | O2-2540 | O2-2540 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2523 | O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2540 | [5 empty] | 2026-04-27T16:19:20.389+0500 | 2026-04-27T16:19:20.542+0500
O2 | O2-2541 | O2-2541 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2523 | O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2541 | [5 empty] | 2026-04-27T16:19:33.763+0500 | 2026-04-27T16:19:33.994+0500
O2 | O2-2542 | O2-2542 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2523 | O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2542 | [5 empty] | 2026-04-27T16:19:48.303+0500 | 2026-04-27T16:19:48.462+0500
O2 | O2-2543 | O2-2543 | Story | Story |  | Handover | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2523 | O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2543 | [5 empty] | 2026-04-27T16:19:58.612+0500 | 2026-04-27T16:19:58.832+0500
O2 | O2-2544 | O2-2544 | Story | Story |  | Bug Fixing | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2523 | O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2523 | https://octopusdtlsupport.atlassian.net/browse/O2-2544 | [5 empty] | 2026-04-27T16:20:08.047+0500 | 2026-04-27T16:20:08.322+0500
O2 | O2-2545 | O2-2545 | Sub-task | Sub-task |  | Identify issues and fix during the testing flow in template | Resolved! | 2026-04-28 | 2026-04-30 | 2026-04-28 | 2026-04-28 | 5 | 5 | Faiza Nasir | 5 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2545 | [5 empty] | 2026-04-28T10:05:55.459+0500 | 2026-04-30T09:27:18.923+0500
O2 | O2-2546 | O2-2546 | Sub-task | Sub-task |  | Thorough flow walk through and fixes additional property creation to asset activation | Resolved! | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | 3 | 3 | Faiza Nasir | 3 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2546 | [5 empty] | 2026-04-28T10:09:40.783+0500 | 2026-04-30T09:28:28.799+0500
O2 | O2-2547 | O2-2547 | Epic | Epic |  | ML-Based Tier 2 Diagnostics (Landing Pattern-based Alerts) | To Do | 2026-06-01 | 2026-07-10 |  |  | 240 | 240 | Mohsin Junaid | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2547 | [5 empty] | 2026-04-28T14:42:51.534+0500 | 2026-04-29T11:07:24.548+0500
O2 | O2-2548 | O2-2548 | Bug Subtask | Bug Subtask |  | Real-time tag latest values are not populating for any device type on the newly created site. | Request received |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-2448 | O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2448 | https://octopusdtlsupport.atlassian.net/browse/O2-2548 | [5 empty] | 2026-04-28T14:44:33.029+0500 | 2026-04-28T14:45:59.813+0500
O2 | O2-2549 | O2-2549 | Epic | Epic |  | OmniConnect Revamped UI | On Hold |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | [5 empty] | 2026-04-28T14:58:38.738+0500 | 2026-05-04T09:59:20.544+0500
O2 | O2-255 | O2-255 | Story | Story |  | Change Password for Production SQL | Resolved! | 2025-12-01 | 2025-12-05 |  |  | 95 | 95 | Ameer Hamza Khan | 0 |  | O2-1460 | O2-1460 | https://octopusdtlsupport.atlassian.net/browse/O2-1460 | https://octopusdtlsupport.atlassian.net/browse/O2-255 | [5 empty] | 2025-10-10T10:29:22.645+0500 | 2026-02-19T11:35:27.480+0500
O2 | O2-2550 | O2-2550 | Story | Story |  | Research | On Hold |  |  |  |  | 0 | 0 | Zain Munir | 32 |  | O2-2549 | O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2550 | [5 empty] | 2026-04-28T14:59:47.371+0500 | 2026-05-04T09:59:18.244+0500
O2 | O2-2551 | O2-2551 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2549 | O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2551 | [5 empty] | 2026-04-28T15:00:23.927+0500 | 2026-04-28T15:01:42.573+0500
O2 | O2-2552 | O2-2552 | Story | Story |  | Handover Session | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2549 | O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2552 | [5 empty] | 2026-04-28T15:00:51.476+0500 | 2026-04-28T15:01:48.612+0500
O2 | O2-2553 | O2-2553 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-2549 | O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2553 | [5 empty] | 2026-04-28T15:02:20.073+0500 | 2026-04-28T15:02:20.243+0500
O2 | O2-2554 | O2-2554 | Story | Story |  | Bugs Fixing | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2549 | O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2554 | [5 empty] | 2026-04-28T15:03:05.158+0500 | 2026-04-28T15:03:05.367+0500
O2 | O2-2555 | O2-2555 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-2549 | O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2555 | [5 empty] | 2026-04-28T15:03:50.980+0500 | 2026-04-28T15:03:51.348+0500
O2 | O2-2556 | O2-2556 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2549 | O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2549 | https://octopusdtlsupport.atlassian.net/browse/O2-2556 | [5 empty] | 2026-04-28T15:04:23.237+0500 | 2026-04-28T15:04:23.409+0500
O2 | O2-2557 | O2-2557 | Sub-task | Sub-task |  | Project Structure, Redux, Internationalization | Resolved! | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-30 | 32 | 32 | Zain Munir | 32 |  | O2-2550 | O2-2550 | https://octopusdtlsupport.atlassian.net/browse/O2-2550 | https://octopusdtlsupport.atlassian.net/browse/O2-2557 | [5 empty] | 2026-04-28T15:05:23.501+0500 | 2026-04-30T10:40:40.639+0500
O2 | O2-2558 | O2-2558 | Bug Subtask | Bug Subtask |  | Invalid error message persists and blocks trigger creation | Resolved | 2026-04-28 |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2558 | [5 empty] | 2026-04-28T16:27:28.229+0500 | 2026-04-30T10:02:57.076+0500
O2 | O2-2559 | O2-2559 | Bug Subtask | Bug Subtask |  | Weekly and Monthly triggers are still FAILED for SQL Pipelines | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2559 | [5 empty] | 2026-04-29T10:15:48.051+0500 | 2026-04-29T16:59:30.567+0500
O2 | O2-256 | O2-256 | Bug Subtask | Bug Subtask |  | Latest value of calculated tag is not updating. | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-256 | [5 empty] | 2025-10-10T10:33:56.451+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2560 | O2-2560 | Story | Story |  | Research/URS | To Do | 2026-06-01 | 2026-06-12 |  |  | 80 | 80 | Mohsin Junaid | 0 |  | O2-2547 | O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2560 | [5 empty] | 2026-04-29T10:57:54.420+0500 | 2026-04-29T11:03:17.238+0500
O2 | O2-2561 | O2-2561 | Story | Story |  | Development | To Do | 2026-06-15 | 2026-06-26 |  |  | 80 | 80 | Mohsin Junaid | 0 |  | O2-2547 | O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2561 | [5 empty] | 2026-04-29T10:58:20.704+0500 | 2026-04-29T11:03:48.665+0500
O2 | O2-2562 | O2-2562 | Story | Story |  | SQA | To Do | 2026-06-29 | 2026-07-03 |  |  | 40 | 40 | Muhammad Abbas | 0 |  | O2-2547 | O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2562 | [5 empty] | 2026-04-29T10:58:29.175+0500 | 2026-04-29T11:04:58.549+0500
O2 | O2-2563 | O2-2563 | Story | Story |  | Production Release | To Do | 2026-07-06 | 2026-07-10 |  |  | 40 | 40 | Mohsin Junaid | 0 |  | O2-2547 | O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2547 | https://octopusdtlsupport.atlassian.net/browse/O2-2563 | [5 empty] | 2026-04-29T10:58:45.019+0500 | 2026-04-29T11:04:48.566+0500
O2 | O2-2564 | O2-2564 | Sub-task | Sub-task |  | Support for Omniagent Charting (AMcharts) | To Do | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-04-27 | 48 | 48 | Hamza Ali | 48 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-2564 | [5 empty] | 2026-04-29T11:49:42.044+0500 | 2026-04-29T12:13:59.602+0500
O2 | O2-2565 | O2-2565 | Sub-task | Sub-task |  | Sync Site configuration Button and API integration | Resolved! | 2026-04-13 | 2026-04-17 | 2026-04-13 | 2026-04-17 | 40 | 40 | Hamza Ali | 40 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-2565 | [5 empty] | 2026-04-29T11:50:03.682+0500 | 2026-04-29T12:07:51.431+0500
O2 | O2-2566 | O2-2566 | Sub-task | Sub-task |  | Back-end Integration- Part C | Resolved! | 2026-04-01 | 2026-04-10 | 2026-04-01 | 2026-04-10 | 80 | 80 | Hamza Ali | 56 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-2566 | [5 empty] | 2026-04-29T11:51:12.546+0500 | 2026-04-29T12:15:34.414+0500
O2 | O2-2567 | O2-2567 | Sub-task | Sub-task |  | Code Merge (OmniAgent Feature and Prod) | To Do |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-1472 | O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-1472 | https://octopusdtlsupport.atlassian.net/browse/O2-2567 | [5 empty] | 2026-04-29T11:51:39.233+0500 | 2026-04-29T11:51:46.180+0500
O2 | O2-2568 | O2-2568 | Bug Subtask | Bug Subtask |  | Schedule SQL is Failed when Granularity =Day, Job Start Time = Day | On Hold |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2568 | [5 empty] | 2026-04-29T15:36:18.358+0500 | 2026-04-29T16:25:45.450+0500
O2 | O2-2569 | O2-2569 | Sub-task | Sub-task |  | Template issues and configuration | To Do | 2026-04-22 | 2026-04-30 | 2026-04-23 | 2026-04-24 | 16 | 16 | DANIYAL AHMAD | 16 |  | O2-1030 | O2-1030 | https://octopusdtlsupport.atlassian.net/browse/O2-1030 | https://octopusdtlsupport.atlassian.net/browse/O2-2569 | [5 empty] | 2026-04-29T16:09:11.392+0500 | 2026-04-29T16:10:04.748+0500
O2 | O2-257 | O2-257 | Bug Subtask | Bug Subtask |  | Conditional cal tag latest values are not displaying. | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-257 | [5 empty] | 2025-10-10T10:36:19.349+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2570 | O2-2570 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | Resolved! | 2026-04-14 | 2026-04-30 | 2026-04-21 | 2026-04-22 | 16 | 16 | DANIYAL AHMAD | 16 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2570 | [5 empty] | 2026-04-29T16:16:33.327+0500 | 2026-05-11T09:54:10.835+0500
O2 | O2-2571 | O2-2571 | Sub-task | Sub-task |  | API Modification for Digital Twin Models | Resolved! | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-04-29 | 8 | 8 | Faiza Nasir | 5 |  | O2-2187 | O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2187 | https://octopusdtlsupport.atlassian.net/browse/O2-2571 | [5 empty] | 2026-04-30T09:22:49.880+0500 | 2026-04-30T09:26:11.612+0500
O2 | O2-2572 | O2-2572 | Sub-task | Sub-task |  | Bug Fixing | Resolved! | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-27 | 3 | 3 | Faiza Nasir | 3 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2572 | [5 empty] | 2026-04-30T09:23:32.134+0500 | 2026-04-30T09:29:11.133+0500
O2 | O2-2573 | O2-2573 | Story | Story |  | Production Release | In-Progress |  |  |  |  | 0 | 0 | Faiza Nasir | 14 |  | O2-1976 | O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | https://octopusdtlsupport.atlassian.net/browse/O2-2573 | [5 empty] | 2026-04-30T09:41:11.333+0500 | 2026-04-30T09:41:32.250+0500
O2 | O2-2574 | O2-2574 | Story | Story |  | Sanity_Testing_4/30/26(Prod Green) | Resolved! | 2026-04-30 | 2026-05-04 |  |  | 40 | 40 | Muhammad Abbas | 133 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | [5 empty] | 2026-04-30T09:53:10.758+0500 | 2026-05-06T10:05:25.236+0500
O2 | O2-2575 | O2-2575 | Sub-task | Sub-task |  | Testing By Namra ( April 30 ) | Resolved! | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 12 | 12 | Namra Zahid | 8 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2575 | [5 empty] | 2026-04-30T09:54:08.636+0500 | 2026-05-12T15:56:08.980+0500
O2 | O2-2576 | O2-2576 | Sub-task | Sub-task |  | Testing By Kamran April | Resolved! | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 8 | 8 | kamran khalid | 8 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2576 | [5 empty] | 2026-04-30T09:54:17.823+0500 | 2026-05-12T15:16:34.508+0500
O2 | O2-2577 | O2-2577 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-05 | 12 | 12 | Zeeshan Sarwar | 25.5 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2577 | [5 empty] | 2026-04-30T09:54:28.980+0500 | 2026-05-05T17:34:06.063+0500
O2 | O2-2578 | O2-2578 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-05 | 12 | 12 | Waqar Rasheed | 24 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2578 | [5 empty] | 2026-04-30T09:54:37.025+0500 | 2026-05-05T17:34:03.348+0500
O2 | O2-2579 | O2-2579 | Sub-task | Sub-task |  | Testing By M.Abbas Apirl | Resolved! | 2026-04-30 | 2026-05-30 | 2026-04-30 | 2026-04-30 | 12 | 12 | Muhammad Abbas | 8 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2579 | [5 empty] | 2026-04-30T09:55:19.175+0500 | 2026-05-12T15:12:27.128+0500
O2 | O2-258 | O2-258 | Sub-task | Sub-task |  | Bugs Fixing, Tasks, Improvements | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 40 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-258 | [5 empty] | 2025-10-10T10:39:50.313+0500 | 2025-10-16T10:35:38.467+0500
O2 | O2-2580 | O2-2580 | Sub-task | Sub-task |  | development of landing pattern fix on totalizers | In-Progress | 2026-04-20 | 2026-05-10 | 2026-04-21 | 2026-04-30 | 48 | 48 | Unassigned | 56 |  | O2-2398 | O2-2398 | https://octopusdtlsupport.atlassian.net/browse/O2-2398 | https://octopusdtlsupport.atlassian.net/browse/O2-2580 | [5 empty] | 2026-04-30T10:18:32.284+0500 | 2026-04-30T10:22:27.082+0500
O2 | O2-2581 | O2-2581 | Sub-task | Sub-task |  | Production Green Release Management / Deployment | Resolved! | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 8 | 8 | Faiza Nasir | 8 |  | O2-2573 | O2-2573 | https://octopusdtlsupport.atlassian.net/browse/O2-2573 | https://octopusdtlsupport.atlassian.net/browse/O2-2581 | [5 empty] | 2026-04-30T11:48:07.407+0500 | 2026-04-30T17:05:56.817+0500
O2 | O2-2582 | O2-2582 | Bug Subtask | Bug Subtask |  | Live values of real/ cal tags are not getting populated. | Resolved | 2026-04-30 | 2026-05-01 | 2026-04-30 | 2026-04-30 | 8 | 8 | Ayyan Babar | 8 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2582 | [5 empty] | 2026-04-30T13:09:22.348+0500 | 2026-05-04T10:21:38.731+0500
O2 | O2-2583 | O2-2583 | Bug Subtask | Bug Subtask |  | “Get Latest Values” Not Working for Single and Bulk Write Back | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2583 | [5 empty] | 2026-04-30T14:31:30.396+0500 | 2026-04-30T15:16:12.286+0500
O2 | O2-2584 | O2-2584 | Bug Subtask | Bug Subtask |  | Model is not getting created for Anomaly Group | Resolved | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2 | 2 | Muhammad Zeeshan Aslam | 2 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2584 | [5 empty] | 2026-04-30T14:34:38.602+0500 | 2026-05-04T14:49:24.897+0500
O2 | O2-2585 | O2-2585 | Bug Subtask | Bug Subtask |  | Unable to verify number for SMS_OPT_IN | Bug Fixed |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2585 | [5 empty] | 2026-04-30T14:53:54.426+0500 | 2026-04-30T15:03:16.378+0500
O2 | O2-2586 | O2-2586 | Bug Subtask | Bug Subtask |  | SQL pipelines are getting displayed with triggers in monitoring logs | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2586 | [5 empty] | 2026-04-30T15:40:04.532+0500 | 2026-05-04T14:49:00.942+0500
O2 | O2-2587 | O2-2587 | Bug Subtask | Bug Subtask |  | Invalid Critical Errors are getting displayed of un-authorization and Read API Issue of Customer and site not found, In logs. | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2587 | [5 empty] | 2026-04-30T15:42:40.236+0500 | 2026-05-04T14:50:01.708+0500
O2 | O2-2588 | O2-2588 | Sub-task | Sub-task |  | UI + API Changes | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2203 | O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2588 | [5 empty] | 2026-04-30T16:18:12.776+0500 | 2026-04-30T16:22:27.690+0500
O2 | O2-2589 | O2-2589 | Sub-task | Sub-task |  | UI + API Changes | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2193 | O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2589 | [5 empty] | 2026-04-30T16:18:25.341+0500 | 2026-04-30T16:20:20.435+0500
O2 | O2-259 | O2-259 | Bug Subtask | Bug Subtask |  | Latest values for MQTT device are not updating while Live Telemetry show latest values | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-259 | [5 empty] | 2025-10-10T10:54:52.954+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2590 | O2-2590 | Sub-task | Sub-task |  | Integration of Wide Format(FrontEnd) | Resolved! | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2193 | O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2590 | [5 empty] | 2026-04-30T16:22:09.858+0500 | 2026-04-30T16:32:30.153+0500
O2 | O2-2591 | O2-2591 | Sub-task | Sub-task |  | Integration of Wide Format(FrontEnd) | Resolved! | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2203 | O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2591 | [5 empty] | 2026-04-30T16:22:40.667+0500 | 2026-04-30T16:33:37.383+0500
O2 | O2-2592 | O2-2592 | Sub-task | Sub-task |  | Testing+ Fixed Issues | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2193 | O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2592 | [5 empty] | 2026-04-30T17:04:30.597+0500 | 2026-04-30T17:25:44.790+0500
O2 | O2-2593 | O2-2593 | Sub-task | Sub-task |  | Testing + Fixed Issues | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2203 | O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2593 | [5 empty] | 2026-04-30T17:04:47.682+0500 | 2026-04-30T17:26:21.209+0500
O2 | O2-2594 | O2-2594 | Sub-task | Sub-task |  | Meeting with DE team + New Changes | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2193 | O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2193 | https://octopusdtlsupport.atlassian.net/browse/O2-2594 | [5 empty] | 2026-04-30T17:29:03.245+0500 | 2026-04-30T17:31:18.261+0500
O2 | O2-2595 | O2-2595 | Sub-task | Sub-task |  | Meeting with DE team + New Changes | Resolved! | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 4 | 4 | Muhammad Ahmad Saleem | 4 |  | O2-2203 | O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2203 | https://octopusdtlsupport.atlassian.net/browse/O2-2595 | [5 empty] | 2026-04-30T17:29:25.934+0500 | 2026-04-30T17:31:32.491+0500
O2 | O2-2596 | O2-2596 | Bug Subtask | Bug Subtask |  | NO Values for these tags Calculated, Timer, Counter, Totalizer Real, Totalizer Cal. With New Site. Only Real and GPS values are here. | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2596 | [5 empty] | 2026-05-04T10:23:40.284+0500 | 2026-05-06T09:49:51.482+0500
O2 | O2-2597 | O2-2597 | Story | Story |  | OEE Productisation Approach | In-Progress |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 6 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-2597 | [5 empty] | 2026-05-04T10:23:56.360+0500 | 2026-05-04T10:36:16.865+0500
O2 | O2-2598 | O2-2598 | Sub-task | Sub-task |  | Identify Productisable entities from implementation working | Resolved! | 2026-04-28 | 2026-04-30 | 2026-04-28 | 2026-04-30 | 5 | 5 | Mariam Zulfiqar | 5 |  | O2-2597 | O2-2597 | https://octopusdtlsupport.atlassian.net/browse/O2-2597 | https://octopusdtlsupport.atlassian.net/browse/O2-2598 | [5 empty] | 2026-05-04T10:28:37.863+0500 | 2026-05-04T10:42:43.033+0500
O2 | O2-2599 | O2-2599 | Sub-task | Sub-task |  | Develop Produstisation approach / areas | To Do | 2026-05-04 |  | 2026-05-05 | 2026-05-05 | 0 | 0 | Mariam Zulfiqar | 1 |  | O2-2597 | O2-2597 | https://octopusdtlsupport.atlassian.net/browse/O2-2597 | https://octopusdtlsupport.atlassian.net/browse/O2-2599 | [5 empty] | 2026-05-04T10:36:52.989+0500 | 2026-05-06T13:14:51.692+0500
O2 | O2-26 | O2-26 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-11 | O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-26 | [5 empty] | 2025-10-02T14:11:11.045+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-260 | O2-260 | Bug Subtask | Bug Subtask |  | Values are not showing on Write back screen after clicking on Get latest values button | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-260 | [5 empty] | 2025-10-10T11:37:40.137+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2600 | O2-2600 | Bug Subtask | Bug Subtask |  | The System Alarms need to be updated in the green environment to align with the staging environment. | Resolved |  |  | 2026-05-04 | 2026-05-04 | 1.5 | 1.5 | Ameer Hamza Khan | 1.5 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2600 | [5 empty] | 2026-05-04T10:39:39.290+0500 | 2026-05-04T14:53:05.102+0500
O2 | O2-2601 | O2-2601 | Bug Subtask | Bug Subtask |  | The SQL has failed again. No data is being displayed in the logs or in the SQL database tables. Please investigate and resolve the issue. | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2601 | [5 empty] | 2026-05-04T11:07:20.574+0500 | 2026-05-04T14:48:38.751+0500
O2 | O2-2602 | O2-2602 | Bug Subtask | Bug Subtask |  | An issue has been observed where state duplication occurs along with multiple states being triggered at the same timestamp for a single tag. This results in conflicting state entries and inconsistent system behavior | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2602 | [5 empty] | 2026-05-04T11:23:16.372+0500 | 2026-05-04T11:35:05.181+0500
O2 | O2-2603 | O2-2603 | Bug Subtask | Bug Subtask |  | The Watchdog module is missing in the Docker deployment on Green Production. Due to this, critical metrics including Upload Speed, Download Speed, and OPC Server metrics are not being populated in the system. | Request received |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2603 | [5 empty] | 2026-05-04T11:35:34.971+0500 | 2026-05-04T11:36:16.376+0500
O2 | O2-2604 | O2-2604 | Sub-task | Sub-task |  | Process pre-sales support, Customer / Management Meetings | In-Progress | 2026-05-01 |  | 2026-05-05 | 2026-05-05 | 0 | 0 | Mariam Zulfiqar | 2 |  | O2-1066 | O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-1066 | https://octopusdtlsupport.atlassian.net/browse/O2-2604 | [5 empty] | 2026-05-04T11:36:47.039+0500 | 2026-05-06T13:12:53.731+0500
O2 | O2-2605 | O2-2605 | Sub-task | Sub-task |  | Process Eng. tasks: working, review and management | To Do | 2026-05-01 | 2026-05-29 | 2026-05-04 | 2026-05-05 | 0 | 0 | Mariam Zulfiqar | 12 |  | O2-1254 | O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-1254 | https://octopusdtlsupport.atlassian.net/browse/O2-2605 | [5 empty] | 2026-05-04T11:38:30.825+0500 | 2026-05-06T13:16:19.950+0500
O2 | O2-2606 | O2-2606 | Bug Subtask | Bug Subtask |  | Email Notifications are not getting received as alarms are triggering | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2606 | [5 empty] | 2026-05-04T15:14:54.119+0500 | 2026-05-04T15:15:24.174+0500
O2 | O2-2607 | O2-2607 | Epic | Epic |  | APX Chiller (ChilloWatt) | In-Progress |  |  |  |  | 0 | 0 | Zain Munir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-2607 | [5 empty] | 2026-05-04T15:19:43.039+0500 | 2026-05-04T15:20:46.066+0500
O2 | O2-2608 | O2-2608 | Story | Story |  | Development | In-Progress | 2026-05-05 |  |  |  | 0 | 0 | Zain Munir | 42 |  | O2-2607 | O2-2607 | https://octopusdtlsupport.atlassian.net/browse/O2-2607 | https://octopusdtlsupport.atlassian.net/browse/O2-2608 | [5 empty] | 2026-05-04T15:20:26.464+0500 | 2026-05-06T16:03:18.853+0500
O2 | O2-2609 | O2-2609 | Sub-task | Sub-task |  | Displaying Dynamic Headers for each KPI Step | Resolved! | 2026-05-04 | 2026-05-08 | 2026-05-05 | 2026-05-08 | 26 | 26 | Zain Munir | 26 |  | O2-2608 | O2-2608 | https://octopusdtlsupport.atlassian.net/browse/O2-2608 | https://octopusdtlsupport.atlassian.net/browse/O2-2609 | [5 empty] | 2026-05-04T15:22:34.435+0500 | 2026-05-11T09:55:05.147+0500
O2 | O2-261 | O2-261 | Bug Subtask | Bug Subtask |  | Account activation link should valid for 24 hours and if user send new link after 24 hours from web front-end then old link should expire | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-261 | [5 empty] | 2025-10-10T11:46:49.313+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2610 | O2-2610 | Bug Subtask | Bug Subtask |  | The Run On Demand popup for Batch and BPM jobs is behaving incorrectly across environments | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2610 | [5 empty] | 2026-05-04T15:23:06.359+0500 | 2026-05-04T15:24:25.895+0500
O2 | O2-2611 | O2-2611 | Sub-task | Sub-task |  | Release Support | Resolved! | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 6 | 6 | Zain Munir | 6 |  | O2-2573 | O2-2573 | https://octopusdtlsupport.atlassian.net/browse/O2-2573 | https://octopusdtlsupport.atlassian.net/browse/O2-2611 | [5 empty] | 2026-05-04T15:26:09.077+0500 | 2026-05-04T15:26:48.434+0500
O2 | O2-2612 | O2-2612 | Bug Subtask | Bug Subtask |  | Duplicated real tags Bug Reproduced again, Kindly Check | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2612 | [5 empty] | 2026-05-04T15:52:47.111+0500 | 2026-05-04T15:53:18.725+0500
O2 | O2-2613 | O2-2613 | Sub-task | Sub-task |  | Variable Speed Compressor Template (P) | Resolved! | 2026-04-01 | 2026-04-30 | 2026-04-28 | 2026-04-29 | 8 | 8 | Muhammad Abdul Wasi | 8 |  | O2-1046 | O2-1046 | https://octopusdtlsupport.atlassian.net/browse/O2-1046 | https://octopusdtlsupport.atlassian.net/browse/O2-2613 | [5 empty] | 2026-05-04T16:05:12.163+0500 | 2026-05-05T09:20:21.227+0500
O2 | O2-2614 | O2-2614 | Bug Subtask | Bug Subtask |  | Omni Agent Invalid response: Show my Assets with asset type and asset names | Request received |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2614 | [5 empty] | 2026-05-04T16:45:06.708+0500 | 2026-05-04T16:49:12.349+0500
O2 | O2-2615 | O2-2615 | Bug Subtask | Bug Subtask |  | Tooltip Spacing Issue on Green Prod Compared to Prod Blue | Request received |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2615 | [5 empty] | 2026-05-04T16:46:19.671+0500 | 2026-05-07T10:04:17.337+0500
O2 | O2-2616 | O2-2616 | Sub-task | Sub-task |  | OC Process Testing RCA | To Do | 2026-05-04 | 2026-05-20 | 2026-05-04 | 2026-05-06 | 40 | 40 | DANIYAL AHMAD | 20 |  | O2-1048 | O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-2616 | [5 empty] | 2026-05-04T16:47:20.091+0500 | 2026-05-07T09:23:22.427+0500
O2 | O2-2617 | O2-2617 | Sub-task | Sub-task |  | Data Prep. & Offline testing - Sync Motor | To Do | 2026-05-01 | 2026-05-22 | 2026-05-04 | 2026-05-07 | 24 | 24 | DANIYAL AHMAD | 8 |  | O2-1032 | O2-1032 | https://octopusdtlsupport.atlassian.net/browse/O2-1032 | https://octopusdtlsupport.atlassian.net/browse/O2-2617 | [5 empty] | 2026-05-04T16:51:16.549+0500 | 2026-05-11T09:49:36.249+0500
O2 | O2-2618 | O2-2618 | Sub-task | Sub-task |  | OC process Testing RCA | Resolved! | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2 | 2 | DANIYAL AHMAD | 2 |  | O2-1048 | O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-2618 | [5 empty] | 2026-05-04T16:53:43.433+0500 | 2026-05-04T16:54:28.330+0500
O2 | O2-2619 | O2-2619 | Sub-task | Sub-task |  | OC Process Testing (P) | Resolved! | 2026-04-28 | 2026-04-30 | 2026-04-29 | 2026-04-30 | 16 | 16 | Muhammad Abdul Wasi | 11 |  | O2-1048 | O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-1048 | https://octopusdtlsupport.atlassian.net/browse/O2-2619 | [5 empty] | 2026-05-05T09:22:26.414+0500 | 2026-05-05T09:25:45.745+0500
O2 | O2-262 | O2-262 | Bug Subtask | Bug Subtask |  | Development Tools permission are not working | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 4 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-262 | [5 empty] | 2025-10-10T11:53:49.235+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2620 | O2-2620 | Sub-task | Sub-task |  | APX WIF Training Material | Resolved! | 2026-04-27 | 2026-04-30 | 2026-04-24 | 2026-04-27 | 16 | 16 | Muhammad Abdul Wasi | 12 |  | O2-1016 | O2-1016 | https://octopusdtlsupport.atlassian.net/browse/O2-1016 | https://octopusdtlsupport.atlassian.net/browse/O2-2620 | [5 empty] | 2026-05-05T09:46:47.193+0500 | 2026-05-05T09:50:39.163+0500
O2 | O2-2621 | O2-2621 | Sub-task | Sub-task |  | OmniOEE Handover Session | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 3 | Muhammad Abdul Wasi | 3 |  | O2-1855 | O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-1855 | https://octopusdtlsupport.atlassian.net/browse/O2-2621 | [5 empty] | 2026-05-05T09:52:46.689+0500 | 2026-05-05T09:54:47.438+0500
O2 | O2-2622 | O2-2622 | Story | Story |  | Research | In-Progress | 2026-05-04 | 2026-05-06 |  |  | 16 | 16 | Ameer Hamza Khan | 16 |  | O2-2607 | O2-2607 | https://octopusdtlsupport.atlassian.net/browse/O2-2607 | https://octopusdtlsupport.atlassian.net/browse/O2-2622 | [5 empty] | 2026-05-05T11:48:17.407+0500 | 2026-05-05T11:50:10.132+0500
O2 | O2-2623 | O2-2623 | Sub-task | Sub-task |  | Research and evaluate approaches for integrating Excel-based calculations into C# (Interop vs alternative libraries) for ChilloWatt. | Resolved! | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 8 | 8 | Arsalan Zafar Khan | 8 |  | O2-2622 | O2-2622 | https://octopusdtlsupport.atlassian.net/browse/O2-2622 | https://octopusdtlsupport.atlassian.net/browse/O2-2623 | [5 empty] | 2026-05-05T11:51:57.237+0500 | 2026-05-05T11:53:44.546+0500
O2 | O2-2624 | O2-2624 | Sub-task | Sub-task |  | Research on Logic + Joint Discussion | Resolved! |  |  | 2026-05-04 | 2026-05-05 | 8 | 8 | Zain Munir | 8 |  | O2-2622 | O2-2622 | https://octopusdtlsupport.atlassian.net/browse/O2-2622 | https://octopusdtlsupport.atlassian.net/browse/O2-2624 | [5 empty] | 2026-05-05T14:59:48.027+0500 | 2026-05-05T15:00:41.840+0500
O2 | O2-2625 | O2-2625 | Sub-task | Sub-task |  | Release bugs fixing, and release management | Resolved! | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 16 | 16 | Ameer Hamza Khan | 16 |  | O2-2276 | O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2276 | https://octopusdtlsupport.atlassian.net/browse/O2-2625 | [5 empty] | 2026-05-06T09:27:06.735+0500 | 2026-05-06T09:28:25.136+0500
O2 | O2-2626 | O2-2626 | Sub-task | Sub-task |  | API for Chillowat incorporation and APX configurational module enhancements | In-Progress | 2026-05-06 |  | 2026-05-06 | 2026-05-07 | 0 | 0 | Ameer Hamza Khan | 16 |  | O2-2608 | O2-2608 | https://octopusdtlsupport.atlassian.net/browse/O2-2608 | https://octopusdtlsupport.atlassian.net/browse/O2-2626 | [5 empty] | 2026-05-06T09:29:23.957+0500 | 2026-05-07T09:49:42.056+0500
O2 | O2-2627 | O2-2627 | Story | Story |  | Sanity_Testing_5/5/26(Prod Blue) | Resolved! | 2026-05-06 | 2026-05-06 |  |  | 40 | 40 | Muhammad Abbas | 72 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | [5 empty] | 2026-05-06T10:03:40.753+0500 | 2026-05-06T18:27:28.900+0500
O2 | O2-2628 | O2-2628 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 8 | 8 | kamran khalid | 8 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2628 | [5 empty] | 2026-05-06T10:04:03.303+0500 | 2026-05-06T17:53:13.044+0500
O2 | O2-2629 | O2-2629 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 8 | 8 | Waqar Rasheed | 16 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2629 | [5 empty] | 2026-05-06T10:04:10.429+0500 | 2026-05-07T16:48:14.553+0500
O2 | O2-263 | O2-263 | Bug Subtask | Bug Subtask |  | OT Pipeline is not executing — showing 404 error, even though Test API and Create Pipeline show success | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-263 | [5 empty] | 2025-10-10T17:28:46.070+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2630 | O2-2630 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 8 | 8 | Zeeshan Sarwar | 16 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2630 | [5 empty] | 2026-05-06T10:04:18.300+0500 | 2026-05-07T15:54:16.305+0500
O2 | O2-2631 | O2-2631 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-08 | 8 | 8 | Namra Zahid | 24 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2631 | [5 empty] | 2026-05-06T10:04:34.013+0500 | 2026-05-12T15:00:35.126+0500
O2 | O2-2632 | O2-2632 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 8 | 8 | Muhammad Abbas | 8 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2632 | [5 empty] | 2026-05-06T10:04:44.773+0500 | 2026-05-06T18:26:17.471+0500
O2 | O2-2633 | O2-2633 | Bug Subtask | Bug Subtask |  | CRITICAL: False alarms triggered for Boolean tag — TRUE-configured alarm firing on FALSE state and condition set by default & not editable | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2633 | [5 empty] | 2026-05-06T11:03:49.900+0500 | 2026-05-06T11:13:06.864+0500
O2 | O2-2634 | O2-2634 | Bug Subtask | Bug Subtask |  | Read API fail to fetch False Alarm against Boolean tag | Request received |  |  |  |  | 0 | 0 | Aiza Hamid | 0 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2634 | [5 empty] | 2026-05-06T12:57:22.411+0500 | 2026-05-06T13:15:34.054+0500
O2 | O2-2635 | O2-2635 | Bug Subtask | Bug Subtask |  | Different Alarm states are triggering for a single totalizer Tag on same timestamp | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2635 | [5 empty] | 2026-05-06T14:10:24.739+0500 | 2026-05-06T14:12:03.422+0500
O2 | O2-2636 | O2-2636 | Bug Subtask | Bug Subtask |  | Anomaly Group Results screen is displaying Error | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2636 | [5 empty] | 2026-05-06T14:46:50.945+0500 | 2026-05-07T10:02:06.960+0500
O2 | O2-2637 | O2-2637 | Bug Subtask | Bug Subtask |  | Omni Agent displays False results in response. | Request received |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2637 | [5 empty] | 2026-05-06T16:40:47.377+0500 | 2026-05-06T16:42:50.734+0500
O2 | O2-2638 | O2-2638 | Bug Subtask | Bug Subtask |  | Invalid response for assets types again | Request received |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-2627 | O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2627 | https://octopusdtlsupport.atlassian.net/browse/O2-2638 | [5 empty] | 2026-05-06T16:46:16.000+0500 | 2026-05-07T10:03:47.802+0500
O2 | O2-2639 | O2-2639 | Story | Story |  | OC_Known_Issues | In-Progress |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | [5 empty] | 2026-05-07T09:49:21.389+0500 | 2026-05-07T10:04:17.478+0500
O2 | O2-264 | O2-264 | Bug Subtask | Bug Subtask |  | Unable to start OT Data Pipeline when running manually | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-264 | [5 empty] | 2025-10-10T17:33:15.601+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2640 | O2-2640 | Bug Subtask | Bug Subtask |  | Extra Space Displayed Between Tooltip Icon and Tooltip Popup | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2639 | O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2640 | [5 empty] | 2026-05-07T10:28:10.867+0500 | 2026-05-07T10:43:54.459+0500
O2 | O2-2641 | O2-2641 | Bug Subtask | Bug Subtask |  | Different Alarm states are triggering for a single totalizer Tag on same timestamp | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2639 | O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2641 | [5 empty] | 2026-05-07T11:19:31.036+0500 | 2026-05-07T11:20:28.028+0500
O2 | O2-2642 | O2-2642 | Bug Subtask | Bug Subtask |  | An issue has been observed where state duplication occurs along with multiple states being triggered at the same timestamp for a single tag. This results in conflicting state entries and inconsistent system behavior | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2639 | O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2642 | [5 empty] | 2026-05-07T11:26:49.875+0500 | 2026-05-07T11:27:25.088+0500
O2 | O2-2643 | O2-2643 | Bug Subtask | Bug Subtask |  | Email Notifications are not getting received as alarms are triggering from "alerts@octopusdtl.com" account | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-2639 | O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2643 | [5 empty] | 2026-05-07T11:28:38.830+0500 | 2026-05-07T11:29:20.332+0500
O2 | O2-2644 | O2-2644 | Bug Subtask | Bug Subtask |  | The Watchdog module is missing in the Docker deployment on Green Production. Due to this, critical metrics including Upload Speed, Download Speed, and OPC Server metrics are not being populated in the system. | Request received |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 0 |  | O2-2639 | O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2644 | [5 empty] | 2026-05-07T11:30:25.628+0500 | 2026-05-07T11:31:03.097+0500
O2 | O2-2645 | O2-2645 | Bug Subtask | Bug Subtask |  | Table Conflict Detected popup appears when user tries to publish a BPM job in a new site. | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2639 | O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2645 | [5 empty] | 2026-05-07T11:35:04.884+0500 | 2026-05-07T11:36:39.716+0500
O2 | O2-2646 | O2-2646 | Bug Subtask | Bug Subtask |  | when user selects an existing table while creating a BPM job an error occurs that "NO publish Columns Found in the request" | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-2639 | O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2639 | https://octopusdtlsupport.atlassian.net/browse/O2-2646 | [5 empty] | 2026-05-07T11:38:34.322+0500 | 2026-05-07T11:38:56.621+0500
O2 | O2-2647 | O2-2647 | Sub-task | Sub-task |  | Testing By Kamran | In-Progress | 2026-05-07 | 2026-05-13 | 2026-05-07 | 2026-05-11 | 32 | 32 | kamran khalid | 24 |  | O2-2213 | O2-2213 | https://octopusdtlsupport.atlassian.net/browse/O2-2213 | https://octopusdtlsupport.atlassian.net/browse/O2-2647 | [5 empty] | 2026-05-07T14:11:39.543+0500 | 2026-05-11T17:10:31.907+0500
O2 | O2-2648 | O2-2648 | Story | Story |  | Totalizer_Landing_Pattern_Testing | In-Progress | 2026-05-07 | 2026-05-11 |  |  | 40 | 40 | Muhammad Abbas | 32 |  | O2-1395 | O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-1395 | https://octopusdtlsupport.atlassian.net/browse/O2-2648 | [5 empty] | 2026-05-07T15:53:19.909+0500 | 2026-05-12T17:22:25.767+0500
O2 | O2-2649 | O2-2649 | Sub-task | Sub-task |  | Testing By M.Abbas | In-Progress | 2026-05-07 | 2026-05-11 | 2026-05-07 | 2026-05-12 | 40 | 40 | Muhammad Abbas | 32 |  | O2-2648 | O2-2648 | https://octopusdtlsupport.atlassian.net/browse/O2-2648 | https://octopusdtlsupport.atlassian.net/browse/O2-2649 | [5 empty] | 2026-05-07T15:54:05.598+0500 | 2026-05-12T17:22:50.713+0500
O2 | O2-265 | O2-265 | Bug Subtask | Bug Subtask |  | IT Data Pipeline stuck in “In Progress” state when run manually | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-265 | [5 empty] | 2025-10-10T17:37:07.518+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2650 | O2-2650 | Sub-task | Sub-task |  | Testing By Waqar | In-Progress | 2026-05-08 | 2026-05-13 | 2026-05-08 | 2026-05-08 | 32 | 32 | Waqar Rasheed | 8 |  | O2-2214 | O2-2214 | https://octopusdtlsupport.atlassian.net/browse/O2-2214 | https://octopusdtlsupport.atlassian.net/browse/O2-2650 | [5 empty] | 2026-05-07T16:52:37.788+0500 | 2026-05-08T16:37:51.294+0500
O2 | O2-2651 | O2-2651 | Sub-task | Sub-task |  | Testing by Zeeshan | In-Progress |  |  | 2026-05-08 | 2026-05-08 | 0 | 0 | Zeeshan Sarwar | 8 |  | O2-1995 | O2-1995 | https://octopusdtlsupport.atlassian.net/browse/O2-1995 | https://octopusdtlsupport.atlassian.net/browse/O2-2651 | [5 empty] | 2026-05-08T09:42:55.295+0500 | 2026-05-08T16:42:31.254+0500
O2 | O2-2652 | O2-2652 | Sub-task | Sub-task |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2652 | [5 empty] | 2026-05-11T09:37:01.973+0500 | 2026-05-11T09:37:02.303+0500
O2 | O2-2653 | O2-2653 | Sub-task | Sub-task |  | Asset Design, HB and Expected models (P) | To Do | 2026-05-01 | 2026-05-08 | 2026-05-04 | 2026-05-08 | 0 | 0 | Danish Rashid | 40 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2653 | [5 empty] | 2026-05-11T09:41:11.308+0500 | 2026-05-11T09:43:16.778+0500
O2 | O2-2654 | O2-2654 | Sub-task | Sub-task |  | APX Engine per Development (P) | Resolved! | 2026-05-04 | 2026-05-08 | 2026-05-04 | 2026-05-07 | 0 | 0 | Faiq Butt | 24 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2654 | [5 empty] | 2026-05-11T09:45:11.399+0500 | 2026-05-11T09:48:36.456+0500
O2 | O2-2655 | O2-2655 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | To Do | 2026-05-11 | 2026-05-15 |  |  | 16 | 16 | Danish Rashid | 0 |  | O2-2245 | O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2245 | https://octopusdtlsupport.atlassian.net/browse/O2-2655 | [5 empty] | 2026-05-11T09:47:28.406+0500 | 2026-05-11T09:48:59.296+0500
O2 | O2-2656 | O2-2656 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | To Do | 2026-05-05 | 2026-05-22 | 2026-05-07 | 2026-05-08 | 24 | 24 | DANIYAL AHMAD | 10 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2656 | [5 empty] | 2026-05-11T09:51:54.891+0500 | 2026-05-11T09:54:21.427+0500
O2 | O2-2657 | O2-2657 | Sub-task | Sub-task |  | Template, wizards and dashboard design (P) | To Do |  |  | 2026-05-08 | 2026-05-08 | 8 | 8 | Faiq Butt | 8 |  | O2-2246 | O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2246 | https://octopusdtlsupport.atlassian.net/browse/O2-2657 | [5 empty] | 2026-05-11T09:54:35.172+0500 | 2026-05-11T09:55:03.555+0500
O2 | O2-266 | O2-266 | Sub-task | Sub-task |  | Test API validation for Start Time, End Time, and Time Format missing — system allows Connector creation without proper validation. | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-266 | [5 empty] | 2025-10-10T17:51:58.931+0500 | 2025-10-15T16:27:28.529+0500
O2 | O2-267 | O2-267 | Bug Subtask | Bug Subtask |  | Full log file is not showing for failed scheduled and manual triggers. The system should display and provide the failed JSON response file in a downloadable format for both IT and OT pipelines. | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-267 | [5 empty] | 2025-10-10T18:11:22.866+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2679 | O2-2679 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-04-11 | 2026-04-12 | 2026-04-11 | 2026-04-12 | 6 | 6 | Muhammad Abbas | 6 |  | O2-2344 | O2-2344 | https://octopusdtlsupport.atlassian.net/browse/O2-2344 | https://octopusdtlsupport.atlassian.net/browse/O2-2679 | [5 empty] | 2026-05-12T14:34:32.576+0500 | 2026-05-12T14:35:42.641+0500
O2 | O2-268 | O2-268 | Sub-task | Sub-task |  | Content Generation for DDS Design Overview Using AI | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-268 | [5 empty] | 2025-10-13T10:32:18.293+0500 | 2025-10-22T11:56:45.432+0500
O2 | O2-2680 | O2-2680 | Sub-task | Sub-task |  | Testing By Namra- May ( 4, 5 ) | To Do | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 16 | 16 | Muhammad Abbas | 16 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2680 | [5 empty] | 2026-05-12T15:08:39.697+0500 | 2026-05-12T16:24:48.790+0500
O2 | O2-2681 | O2-2681 | Sub-task | Sub-task |  | Testing By M.Abbas May | Resolved! | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 16 | 16 | Muhammad Abbas | 16 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2681 | [5 empty] | 2026-05-12T15:12:46.007+0500 | 2026-05-12T15:13:48.488+0500
O2 | O2-2682 | O2-2682 | Sub-task | Sub-task |  | Testing by Namra April | Resolved! | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | 16 | 16 | Namra Zahid | 16 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2682 | [5 empty] | 2026-05-12T15:14:51.829+0500 | 2026-05-12T15:56:59.007+0500
O2 | O2-2684 | O2-2684 | Sub-task | Sub-task |  | Testing By Kamran May | Resolved! | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 16 | 16 | kamran khalid | 16 |  | O2-2574 | O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2574 | https://octopusdtlsupport.atlassian.net/browse/O2-2684 | [5 empty] | 2026-05-12T15:17:56.126+0500 | 2026-05-12T15:19:43.950+0500
O2 | O2-2686 | O2-2686 | Sub-task | Sub-task |  | Testing by Namra April (2 ) | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8 | 8 | Namra Zahid | 8 |  | O2-1343 | O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-1343 | https://octopusdtlsupport.atlassian.net/browse/O2-2686 | [5 empty] | 2026-05-12T15:25:42.294+0500 | 2026-05-12T16:01:49.308+0500
O2 | O2-2688 | O2-2688 | Sub-task | Sub-task |  | Export To Sql (April 20, 21, 22 ) | Resolved! | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-22 | 24 | 24 | Namra Zahid | 24 |  | O2-2179 | O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2688 | [5 empty] | 2026-05-12T15:42:32.927+0500 | 2026-05-12T15:48:58.662+0500
O2 | O2-2689 | O2-2689 | Sub-task | Sub-task |  | Export To Sql (April 23, 24 ) | Resolved! | 2026-04-23 | 2026-04-24 | 2026-04-23 | 2026-04-24 | 16 | 16 | Namra Zahid | 16 |  | O2-2179 | O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2689 | [5 empty] | 2026-05-12T15:44:28.530+0500 | 2026-05-12T15:48:37.614+0500
O2 | O2-269 | O2-269 | Bug Subtask | Bug Subtask |  | Notification group selection drop down is displaying on import site layout screen as well as on login screen. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-269 | [5 empty] | 2025-10-13T10:38:51.248+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-2690 | O2-2690 | Sub-task | Sub-task |  | Batch/BPM Apirl Testing | Resolved! | 2026-04-01 | 2026-04-02 | 2026-04-01 | 2026-04-02 | 16 | 16 | Muhammad Abbas | 16 |  | O2-1438 | O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-1438 | https://octopusdtlsupport.atlassian.net/browse/O2-2690 | [5 empty] | 2026-05-12T15:44:43.724+0500 | 2026-05-12T15:47:32.940+0500
O2 | O2-2691 | O2-2691 | Sub-task | Sub-task |  | Export To Sql (April 27, 28, 29 ) | Resolved! | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 24 | 24 | Namra Zahid | 24 |  | O2-2179 | O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2179 | https://octopusdtlsupport.atlassian.net/browse/O2-2691 | [5 empty] | 2026-05-12T15:45:59.630+0500 | 2026-05-12T15:48:29.434+0500
O2 | O2-27 | O2-27 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-11 | O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-27 | [5 empty] | 2025-10-02T14:11:16.975+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-270 | O2-270 | Bug Subtask | Bug Subtask |  | Wrong error message is displaying when I tried to create 3 areas through import site layout. All records are added but empty records are displaying in fault file. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 4 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-270 | [5 empty] | 2025-10-13T11:56:40.206+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-271 | O2-271 | Bug Subtask | Bug Subtask |  | Notification group is inactive error displaying in fault file where as data alarms notifications are enabled in site. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-271 | [5 empty] | 2025-10-13T11:58:52.360+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-272 | O2-272 | Bug Subtask | Bug Subtask |  | Tags having notification groups added in import site layout file are not adding when only data alarms notification configurations are enabled in respective site but they are adding when both data alarms and APX notification configurations are enabled. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-272 | [5 empty] | 2025-10-13T12:00:14.705+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-273 | O2-273 | Bug Subtask | Bug Subtask |  | Statistical alarms notification group configured through import site layout are not displaying in configurations of real time and calculated tags against 24 hour duration on front end. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-273 | [5 empty] | 2025-10-13T12:01:40.781+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-274 | O2-274 | Bug Subtask | Bug Subtask |  | No character limit is applied while creating area from import site layout where as maximum 15 character limit is applied on front end, also wrong error message is displaying when character limit is reached on front end. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 2 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-274 | [5 empty] | 2025-10-13T12:05:20.664+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-275 | O2-275 | Bug Subtask | Bug Subtask |  | Conditional cal tags in which simple cal tags are used, they are displaying in counter and timer tags listing while viewing dependencies of simple calculated tag. | Resolved | 2025-10-15 |  |  |  | 0 | 0 | Ali Qumail | 2 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-275 | [5 empty] | 2025-10-13T12:53:19.253+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-276 | O2-276 | Bug Subtask | Bug Subtask |  | All tag's values are not getting landing for IOT, Kindly look into it | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 1 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-276 | [5 empty] | 2025-10-13T13:48:27.803+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-277 | O2-277 | Bug Subtask | Bug Subtask |  | REST API OT Connector is failing during execution. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-277 | [5 empty] | 2025-10-13T13:57:56.094+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-278 | O2-278 | Bug Subtask | Bug Subtask |  | String and Datetime tag data not displaying on Latest Value page after successful OT REST API data ingestion. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 4 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-278 | [5 empty] | 2025-10-13T16:38:50.427+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-279 | O2-279 | Bug Subtask | Bug Subtask |  | OMNI Agent fails to return all tables with schema, whereas the Read API supports this functionality. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-279 | [5 empty] | 2025-10-13T17:05:03.296+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-280 | O2-280 | Sub-task | Sub-task |  | Generated Content Integration in the Document with Formatting | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 14 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-280 | [5 empty] | 2025-10-13T17:59:41.409+0500 | 2025-10-23T10:11:02.294+0500
O2 | O2-283 | O2-283 | Bug Subtask | Bug Subtask |  | Creation modal closes when user enters a duplicate name for Workflow or Trigger instead of remaining open after showing error | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 4 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-283 | [5 empty] | 2025-10-14T10:49:14.138+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-284 | O2-284 | Bug Subtask | Bug Subtask |  | if final table name is not defined then BPM should not be published and if name is defined but schema is not defined incase of new table then system should throw error on both | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 8 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-284 | [5 empty] | 2025-10-14T10:59:02.053+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-285 | O2-285 | Bug Subtask | Bug Subtask |  | Wrong fault records quantity is displaying in imports site layout screen after uploading a file. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 6 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-285 | [5 empty] | 2025-10-14T11:01:06.187+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-286 | O2-286 | Bug Subtask | Bug Subtask |  | BPM validation job fails showing "The BPM Validation Job Failed" message, but the Activity Status does not display any corresponding error | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 8 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-286 | [5 empty] | 2025-10-14T11:02:39.526+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-287 | O2-287 | Bug Subtask | Bug Subtask |  | When user uses activity name as table name inside other activity then upon validation the result shows but when user runs triggers it shows error | Resolved |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-287 | [5 empty] | 2025-10-14T11:13:41.369+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-288 | O2-288 | Bug Subtask | Bug Subtask |  | APX real time and calculated tag latest values are not displaying. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-288 | [5 empty] | 2025-10-14T11:45:48.952+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-289 | O2-289 | Bug Subtask | Bug Subtask |  | Latest values of tags created through import site layout are not displaying. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-289 | [5 empty] | 2025-10-14T11:48:18.904+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-290 | O2-290 | Bug Subtask | Bug Subtask |  | Real time tag latest values created using MQTT device are not displaying. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-290 | [5 empty] | 2025-10-14T11:50:47.720+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-291 | O2-291 | Bug Subtask | Bug Subtask |  | Timer Tag's values are not getting landed in OmniConnect. | Resolved |  |  |  |  | 0 | 0 | Namra Zahid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-291 | [5 empty] | 2025-10-14T12:27:44.056+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-292 | O2-292 | Bug Subtask | Bug Subtask |  | Azure SQL (IT) connector is not getting created on sites where SAP HANA or ODBC connectors are already created. | Resolved |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-292 | [5 empty] | 2025-10-14T12:39:23.184+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-293 | O2-293 | Bug Subtask | Bug Subtask |  | The user has created multiple tags from the IoT device using the same source tag. However, the live value is populating for only one tag, while the others are not updating. | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-293 | [5 empty] | 2025-10-14T12:40:53.891+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-294 | O2-294 | Bug Subtask | Bug Subtask |  | Data alarm not triggering for the IOT tag alarm as its value is populating | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-294 | [5 empty] | 2025-10-14T12:52:18.406+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-295 | O2-295 | Bug Subtask | Bug Subtask |  | Value is not displaying on the Query Validation screen in the Batch BPM module, whereas the same value appears correctly when the user downloads the CSV file. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-295 | [5 empty] | 2025-10-14T12:59:08.509+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-296 | O2-296 | Bug Subtask | Bug Subtask |  | Integer type of tags have no values,IOT | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 1 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-296 | [5 empty] | 2025-10-14T14:22:20.725+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-297 | O2-297 | Task | Task |  | Alarm Configuration Enhancement DDS | In-Progress | 2025-10-13 |  |  |  | 0 | 0 | Ali Qumail | 14 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-297 | [5 empty] | 2025-10-14T14:56:20.606+0500 | 2026-02-11T10:23:24.571+0500
O2 | O2-298 | O2-298 | Bug Subtask | Bug Subtask |  | Tag values imported through CSV bulk import are not displaying accordingly in export to excel when resolution time is 30 days. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-298 | [5 empty] | 2025-10-14T14:57:53.762+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-299 | O2-299 | Bug Subtask | Bug Subtask |  | In Batch BPM, query with semicolon (;) at the end shows data in preview but fails on execution | Resolved |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-299 | [5 empty] | 2025-10-14T17:47:52.642+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-3 | O2-3 | Story | Story |  | Research/URS | Resolved! | 2025-10-27 | 2025-10-31 |  |  | 64 | 64 | ahad omer | 64 |  | O2-2 | O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-3 | [5 empty] | 2025-10-02T13:54:15.963+0500 | 2025-11-20T18:11:57.604+0500
O2 | O2-300 | O2-300 | Sub-task | Sub-task |  | Logic App Integration | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-300 | [5 empty] | 2025-10-14T17:54:49.699+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-301 | O2-301 | Sub-task | Sub-task |  | Data Factory Integration | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-301 | [5 empty] | 2025-10-14T17:54:58.291+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-302 | O2-302 | Sub-task | Sub-task |  | IoT Hub Integration | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-302 | [5 empty] | 2025-10-14T17:55:04.587+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-303 | O2-303 | Bug Subtask | Bug Subtask |  | CORS error occurs while calling REST API Connector using Bearer Token authentication | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-303 | [5 empty] | 2025-10-15T10:41:28.382+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-304 | O2-304 | Sub-task | Sub-task |  | iothub data is stored from iothub as is | Resolved! |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-111 | O2-111 | https://octopusdtlsupport.atlassian.net/browse/O2-111 | https://octopusdtlsupport.atlassian.net/browse/O2-304 | [5 empty] | 2025-10-15T10:46:05.488+0500 | 2025-11-13T18:51:24.240+0500
O2 | O2-305 | O2-305 | Bug Subtask | Bug Subtask |  | Latest value of date time against DL tag is displaying in UTC where as DL organization as well as OC site is set to local time. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-305 | [5 empty] | 2025-10-15T12:07:03.133+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-306 | O2-306 | Bug Subtask | Bug Subtask |  | Temp table is showing in Activity Query modal and when user select any temp table then it is showing error | Resolved |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-306 | [5 empty] | 2025-10-15T15:36:29.153+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-307 | O2-307 | Bug Subtask | Bug Subtask |  | Validate button in the query modal is showing Green tick "Query is successfully validated" on the same time the system is showing error | Resolved |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-307 | [5 empty] | 2025-10-15T15:45:06.826+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-308 | O2-308 | Bug Subtask | Bug Subtask |  | Query with validation errors is still being saved upon clicking the Validate button when user closes the query modal and reopen it | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-308 | [5 empty] | 2025-10-15T16:22:19.061+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-316 | O2-316 | Story | Story |  | Enhancements for anomaly detection | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 56 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-316 | [5 empty] | 2025-10-16T09:23:03.062+0500 | 2025-12-30T10:22:35.477+0500
O2 | O2-317 | O2-317 | Task | Task |  | Import Site Layout Exception Handling | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 6 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-317 | [5 empty] | 2025-10-16T10:29:11.839+0500 | 2025-10-23T10:11:48.949+0500
O2 | O2-318 | O2-318 | Bug Subtask | Bug Subtask |  | AI Chat fails to retrieve the latest record from the table in OMNI Data Analysis | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-318 | [5 empty] | 2025-10-16T10:30:34.504+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-319 | O2-319 | Sub-task | Sub-task |  | New Asset Sub types setup for Template for process team | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 2 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-319 | [5 empty] | 2025-10-16T10:37:02.355+0500 | 2025-10-17T19:47:42.441+0500
O2 | O2-320 | O2-320 | Sub-task | Sub-task |  | Creating Scanner For RestAPI Pulls | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 24 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-320 | [5 empty] | 2025-10-16T10:47:35.889+0500 | 2025-10-16T10:49:47.281+0500
O2 | O2-321 | O2-321 | Sub-task | Sub-task |  | Creating Generic API Caller | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 80 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-321 | [5 empty] | 2025-10-16T10:49:33.420+0500 | 2025-10-16T10:52:56.444+0500
O2 | O2-322 | O2-322 | Sub-task | Sub-task |  | OT Data Formatting and Ingestion to ADX | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 40 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-322 | [5 empty] | 2025-10-16T10:52:44.804+0500 | 2026-02-13T12:58:05.780+0500
O2 | O2-323 | O2-323 | Bug Subtask | Bug Subtask |  | AI Chat fails to answer the query “Can you show me the edge metrics details of device ID 7950” | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-323 | [5 empty] | 2025-10-16T10:57:35.887+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-324 | O2-324 | Bug Subtask | Bug Subtask |  | Downloaded result CSV does not show full timestamp — only minutes and seconds are displayed | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-324 | [5 empty] | 2025-10-16T12:24:16.005+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-325 | O2-325 | Sub-task | Sub-task |  | Downloaded JOSN Txt file should only contain data and exclude return description, asset info, and other metadata | Resolved! |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-325 | [5 empty] | 2025-10-16T12:31:59.485+0500 | 2026-02-13T12:58:55.066+0500
O2 | O2-326 | O2-326 | Bug Subtask | Bug Subtask |  | Agent returns associated tag list with distorted UI in AI Chat | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 1 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-326 | [5 empty] | 2025-10-16T12:39:41.917+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-33 | O2-33 | Epic | Epic |  | APX Template Enhancement | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 85 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-33 | [5 empty] | 2025-10-02T14:12:41.489+0500 | 2026-02-11T09:39:00.318+0500
O2 | O2-332 | O2-332 | Bug Subtask | Bug Subtask |  | AI Chat returns an error when analyzing tag hourly maximums and averages | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-332 | [5 empty] | 2025-10-16T12:50:55.524+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-334 | O2-334 | Sub-task | Sub-task |  | zee 127 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-334 | [5 empty] | 2025-10-16T12:55:22.706+0500 | 2025-10-16T16:00:40.695+0500
O2 | O2-335 | O2-335 | Bug Subtask | Bug Subtask |  | test | Resolved |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-317 | O2-317 | https://octopusdtlsupport.atlassian.net/browse/O2-317 | https://octopusdtlsupport.atlassian.net/browse/O2-335 | [5 empty] | 2025-10-16T13:00:46.678+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-337 | O2-337 | Bug Subtask | Bug Subtask |  | 1 | Resolved |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-223 | O2-223 | https://octopusdtlsupport.atlassian.net/browse/O2-223 | https://octopusdtlsupport.atlassian.net/browse/O2-337 | [5 empty] | 2025-10-16T13:24:27.357+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-339 | O2-339 | Bug Subtask | Bug Subtask |  | AI Chat returns invalid data when comparing timestamps for two tags with expected values | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-339 | [5 empty] | 2025-10-16T14:40:04.026+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-34 | O2-34 | Epic | Epic |  | Scheduled Pulls from Data Source (SQL OT) | Resolved! |  |  |  |  | 0 | 0 | Hamza Ali | 100 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-34 | [5 empty] | 2025-10-02T14:13:22.590+0500 | 2026-02-18T16:17:22.376+0500
O2 | O2-340 | O2-340 | Sub-task | Sub-task |  | OCM Frontend Integration Anomaly | Resolved! | 2025-10-01 | 2025-10-17 |  |  | 0 | 0 | Ali Qumail | 16 |  | O2-68 | O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-340 | [5 empty] | 2025-10-16T15:32:07.995+0500 | 2025-10-20T11:46:42.095+0500
O2 | O2-343 | O2-343 | Sub-task | Sub-task |  | Frontend Development + Unit Testing | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 38 |  | O2-104 | O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-343 | [5 empty] | 2025-10-17T10:00:43.159+0500 | 2025-10-27T16:38:51.472+0500
O2 | O2-346 | O2-346 | Bug Subtask | Bug Subtask |  | SQL Scheduled logs UI is Disturbed, Issue was fixed on staging | Resolved | 2025-10-20 | 2025-10-20 |  |  | 0 | 0 | Namra Zahid | 5 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-346 | [5 empty] | 2025-10-17T14:45:14.844+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-349 | O2-349 | Bug Subtask | Bug Subtask |  | Stats Alarm Schedule SQL: Showing failure in logs but data is displayed in SQL | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-349 | [5 empty] | 2025-10-17T16:23:38.826+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-35 | O2-35 | Epic | Epic |  | OmniAgent Phase 2.1 ( APX Perf, What-if, Health ) | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 298 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-35 | [5 empty] | 2025-10-02T14:13:32.409+0500 | 2026-02-11T10:59:11.322+0500
O2 | O2-354 | O2-354 | Bug Subtask | Bug Subtask |  | Industry "Transportation" is Duplicated in Site Creation and update | Resolved |  |  |  |  | 0 | 0 | Namra Zahid | 1.83 |  | O2-99 | O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | https://octopusdtlsupport.atlassian.net/browse/O2-354 | [5 empty] | 2025-10-20T11:48:04.314+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-355 | O2-355 | Sub-task | Sub-task |  | Productin Release Blue Env | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-101 | O2-101 | https://octopusdtlsupport.atlassian.net/browse/O2-101 | https://octopusdtlsupport.atlassian.net/browse/O2-355 | [5 empty] | 2025-10-21T09:56:52.584+0500 | 2025-10-22T12:03:27.801+0500
O2 | O2-356 | O2-356 | Story | Story |  | Documentation | Resolved! | 2025-09-01 | 2025-11-21 |  |  | 0 | 0 | Hassan Malik | 104 |  | O2-133 | O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-133 | https://octopusdtlsupport.atlassian.net/browse/O2-356 | [5 empty] | 2025-10-21T10:40:02.170+0500 | 2026-01-14T10:04:58.953+0500
O2 | O2-357 | O2-357 | Sub-task | Sub-task |  | OCM-Regression | Resolved! | 2025-10-21 | 2025-11-11 |  |  | 200 | 200 | Muhammad Abbas | 194.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-357 | [5 empty] | 2025-10-21T11:05:18.234+0500 | 2026-02-13T13:00:00.468+0500
O2 | O2-358 | O2-358 | Sub-task | Sub-task |  | Umair Iftikhar - Quick Security Questions | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 16 |  | O2-356 | O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-358 | [5 empty] | 2025-10-21T11:38:35.889+0500 | 2025-10-21T11:40:29.953+0500
O2 | O2-359 | O2-359 | Sub-task | Sub-task |  | How To - Batch | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 16 |  | O2-47 | O2-47 | https://octopusdtlsupport.atlassian.net/browse/O2-47 | https://octopusdtlsupport.atlassian.net/browse/O2-359 | [5 empty] | 2025-10-21T11:42:15.390+0500 | 2025-10-27T09:19:27.331+0500
O2 | O2-36 | O2-36 | Epic | Epic |  | Unified Notification Engine | To Do | 2026-04-13 | 2026-05-06 |  |  | 152 | 152 | Ameer Hamza Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-36 | [5 empty] | 2025-10-02T14:13:39.974+0500 | 2026-04-15T10:39:58.658+0500
O2 | O2-360 | O2-360 | Sub-task | Sub-task |  | How to - BPM | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 16 |  | O2-47 | O2-47 | https://octopusdtlsupport.atlassian.net/browse/O2-47 | https://octopusdtlsupport.atlassian.net/browse/O2-360 | [5 empty] | 2025-10-21T11:42:28.421+0500 | 2025-10-29T11:51:30.963+0500
O2 | O2-362 | O2-362 | Sub-task | Sub-task |  | Fields - BPM | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 8 |  | O2-47 | O2-47 | https://octopusdtlsupport.atlassian.net/browse/O2-47 | https://octopusdtlsupport.atlassian.net/browse/O2-362 | [5 empty] | 2025-10-21T11:42:42.553+0500 | 2025-10-29T11:52:31.232+0500
O2 | O2-363 | O2-363 | Sub-task | Sub-task |  | Bug Fixing, Improvements and Tasks | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 32 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-363 | [5 empty] | 2025-10-21T15:48:56.596+0500 | 2025-10-29T16:37:14.113+0500
O2 | O2-364 | O2-364 | Sub-task | Sub-task |  | Bug Fixing, Improvements and Tasks | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 31.5 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-364 | [5 empty] | 2025-10-21T15:50:12.629+0500 | 2025-10-29T16:37:10.124+0500
O2 | O2-365 | O2-365 | Sub-task | Sub-task |  | How to - Anomaly Detection Updates | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 16 |  | O2-70 | O2-70 | https://octopusdtlsupport.atlassian.net/browse/O2-70 | https://octopusdtlsupport.atlassian.net/browse/O2-365 | [5 empty] | 2025-10-21T16:13:52.855+0500 | 2025-11-13T19:06:17.597+0500
O2 | O2-366 | O2-366 | Sub-task | Sub-task |  | Fields - Anomaly Detection Updates | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 8 |  | O2-70 | O2-70 | https://octopusdtlsupport.atlassian.net/browse/O2-70 | https://octopusdtlsupport.atlassian.net/browse/O2-366 | [5 empty] | 2025-10-21T16:14:38.240+0500 | 2025-11-13T19:06:17.857+0500
O2 | O2-367 | O2-367 | Sub-task | Sub-task |  | Backend Connectors and Trigger APIs modifications | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 10 |  | O2-104 | O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-367 | [5 empty] | 2025-10-22T10:17:46.536+0500 | 2025-10-29T09:39:37.315+0500
O2 | O2-368 | O2-368 | Sub-task | Sub-task |  | New Schema changes for Pipeline | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 1 |  | O2-104 | O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-368 | [5 empty] | 2025-10-22T10:18:22.649+0500 | 2025-10-29T09:39:26.763+0500
O2 | O2-369 | O2-369 | Sub-task | Sub-task |  | SFTP Pipeline APIs development | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 3 |  | O2-104 | O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-369 | [5 empty] | 2025-10-22T10:18:50.790+0500 | 2025-10-29T09:39:05.368+0500
O2 | O2-37 | O2-37 | Epic | Epic |  | Anomaly Detection Engine Enrichment | Resolved! |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 452.5 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-37 | [5 empty] | 2025-10-02T14:13:45.782+0500 | 2026-02-11T09:38:59.510+0500
O2 | O2-370 | O2-370 | Sub-task | Sub-task |  | Handover to QA | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 4 |  | O2-68 | O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-370 | [5 empty] | 2025-10-22T10:20:23.314+0500 | 2025-10-22T16:50:12.485+0500
O2 | O2-371 | O2-371 | Sub-task | Sub-task |  | Generate DDS Sequence diagram through AI | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 1.67 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-371 | [5 empty] | 2025-10-22T11:58:33.656+0500 | 2025-11-03T14:03:18.180+0500
O2 | O2-374 | O2-374 | Sub-task | Sub-task |  | OCM Anomaly V3 Internal Bugs/Improvements | Resolved! | 2025-10-21 | 2025-10-30 |  |  | 0 | 0 | Ali Qumail | 32 |  | O2-68 | O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-374 | [5 empty] | 2025-10-23T09:49:55.787+0500 | 2025-11-05T10:06:09.844+0500
O2 | O2-375 | O2-375 | Sub-task | Sub-task |  | SFTP Development for JSON and CSV formats | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 32 |  | O2-104 | O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-375 | [5 empty] | 2025-10-23T10:07:05.867+0500 | 2025-10-30T09:46:32.389+0500
O2 | O2-376 | O2-376 | Sub-task | Sub-task |  | Read AI Update for Device Diagnostics | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 8 |  | O2-154 | O2-154 | https://octopusdtlsupport.atlassian.net/browse/O2-154 | https://octopusdtlsupport.atlassian.net/browse/O2-376 | [5 empty] | 2025-10-23T10:17:26.257+0500 | 2025-10-29T11:19:36.273+0500
O2 | O2-377 | O2-377 | Story | Story |  | API Enrichment | Resolved! | 2025-10-23 | 2025-11-17 |  |  | 48 | 48 | Taimur Zahid | 124 |  | O2-35 | O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-377 | [5 empty] | 2025-10-23T10:33:04.696+0500 | 2025-12-08T12:06:06.988+0500
O2 | O2-378 | O2-378 | Bug Subtask | Bug Subtask |  | Deleted Cal Tag Duplicating While we access the dependencies of any type of tag which is used in this cal tag | Resolved |  |  |  |  | 0 | 0 | Namra Zahid | 2.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-378 | [5 empty] | 2025-10-23T11:39:07.783+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-379 | O2-379 | Bug Subtask | Bug Subtask |  | Ingestion Format unusual behavior | Resolved |  |  |  |  | 0 | 0 | Waqar Rasheed | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-379 | [5 empty] | 2025-10-23T11:57:07.314+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-38 | O2-38 | Story | Story |  | Research/URS (P) | Resolved! | 2025-09-15 | 2025-09-19 |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-33 | O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-38 | [5 empty] | 2025-10-02T14:16:27.469+0500 | 2025-11-04T11:17:19.191+0500
O2 | O2-380 | O2-380 | Bug Subtask | Bug Subtask |  | When user tries to set datapoints using floating values the validation is missing i.e (only numeric values ) | Resolved |  |  |  |  | 0 | 0 | Waqar Rasheed | 2 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-380 | [5 empty] | 2025-10-23T12:00:10.688+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-381 | O2-381 | Bug Subtask | Bug Subtask |  | User unable to create same name notification group in different SIs. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 2 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-381 | [5 empty] | 2025-10-23T12:01:10.734+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-382 | O2-382 | Bug Subtask | Bug Subtask |  | Resource creation ticket for data center specificity is not getting created when the site is created in a data center other than Southeast Asia. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-382 | [5 empty] | 2025-10-23T12:07:24.936+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-383 | O2-383 | Bug Subtask | Bug Subtask |  | Omni Agent Chat responds to queries from other sites even when the user has selected a different site. | Resolved |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-383 | [5 empty] | 2025-10-23T12:19:46.189+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-384 | O2-384 | Bug Subtask | Bug Subtask |  | Agent returns data when user shares a Read API payload — which is not a valid implementation. | Bug Fixed |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-384 | [5 empty] | 2025-10-23T12:30:09.101+0500 | 2026-02-26T10:22:05.928+0500
O2 | O2-387 | O2-387 | Bug Subtask | Bug Subtask |  | User has created multiple tags from the IoT device using the same source tag. However, the live value is populating for only one tag, while the others are not updating.# | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-387 | [5 empty] | 2025-10-23T14:19:41.158+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-388 | O2-388 | Bug Subtask | Bug Subtask |  | While updating the Data Points of a specific site, all other sites are getting system alarms of it. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-388 | [5 empty] | 2025-10-23T14:32:05.214+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-389 | O2-389 | Bug Subtask | Bug Subtask |  | Counter tag latest values are not updating. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-389 | [5 empty] | 2025-10-23T15:48:28.672+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-39 | O2-39 | Story | Story |  | Research/DDS | Resolved! | 2025-10-08 | 2025-11-19 |  |  | 144 | 144 | Faiza Nasir | 119.67 |  | O2-33 | O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | [5 empty] | 2025-10-02T14:16:38.172+0500 | 2025-12-02T12:01:17.180+0500
O2 | O2-390 | O2-390 | Bug Subtask | Bug Subtask |  | Timer Tag latest values are not showing | Resolved |  |  |  |  | 0 | 0 | Waqar Rasheed | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-390 | [5 empty] | 2025-10-23T15:50:47.957+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-391 | O2-391 | Bug Subtask | Bug Subtask |  | Latest values for AHU and variable pump speed performance APX asset are not updating. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-391 | [5 empty] | 2025-10-23T16:02:05.870+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-392 | O2-392 | Bug Subtask | Bug Subtask |  | Once a user validates an activity with error, the system incorrectly sets the validation status to true and displays the “Save Output” button and upon clicking on “Save Output,” the system throws error “Failed to publish activity | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-392 | [5 empty] | 2025-10-23T16:03:11.182+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-393 | O2-393 | Bug Subtask | Bug Subtask |  | The GPS tag is not displaying the Longitude and Latitude values — only the Altitude value is being shown. | Resolved |  |  |  |  | 0 | 0 | Namra Zahid | 2.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-393 | [5 empty] | 2025-10-23T16:04:47.045+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-394 | O2-394 | Bug Subtask | Bug Subtask |  | when user uses a temp table of another BPM Workflow activity it shows error | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-394 | [5 empty] | 2025-10-23T16:19:15.050+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-395 | O2-395 | Sub-task | Sub-task |  | APx And BPM Discussion | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 4 |  | O2-377 | O2-377 | https://octopusdtlsupport.atlassian.net/browse/O2-377 | https://octopusdtlsupport.atlassian.net/browse/O2-395 | [5 empty] | 2025-10-23T16:50:10.253+0500 | 2025-11-19T11:30:01.876+0500
O2 | O2-396 | O2-396 | Bug Subtask | Bug Subtask |  | when user using existing functionality uses a batch job with OT function and while validating its not showing the "Status Code" and "ID" column empty | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-396 | [5 empty] | 2025-10-23T16:51:02.759+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-397 | O2-397 | Sub-task | Sub-task |  | Bug Fixing / Deployments | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 3 |  | O2-98 | O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | https://octopusdtlsupport.atlassian.net/browse/O2-397 | [5 empty] | 2025-10-23T16:52:29.352+0500 | 2025-10-30T09:48:16.128+0500
O2 | O2-398 | O2-398 | Epic | Epic |  | Centrifugal Compressor (Fixed Speed) | To Do | 2025-06-30 | 2025-07-13 |  |  | 0 | 0 | awais akhter | 80 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-398 | [5 empty] | 2025-10-23T16:55:14.166+0500 | 2026-01-26T18:18:50.115+0500
O2 | O2-399 | O2-399 | Story | Story |  | Asset Design, HB and Expected models (P) | Resolved! | 2025-06-30 | 2025-07-06 |  |  | 0 | 0 | Mariam Zulfiqar | 40 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-399 | [5 empty] | 2025-10-23T16:55:26.179+0500 | 2025-11-04T12:13:45.829+0500
O2 | O2-40 | O2-40 | Story | Story |  | Development | Resolved! | 2025-11-20 | 2026-01-02 |  |  | 720 | 720 | Faiza Nasir | 451 |  | O2-33 | O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | [5 empty] | 2025-10-02T14:16:43.973+0500 | 2026-01-12T12:15:50.358+0500
O2 | O2-400 | O2-400 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-400 | [5 empty] | 2025-10-23T16:56:41.278+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-401 | O2-401 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! | 2025-07-07 | 2025-07-13 |  |  | 0 | 0 | Mariam Zulfiqar | 40 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-401 | [5 empty] | 2025-10-23T16:57:03.120+0500 | 2025-11-04T12:15:11.536+0500
O2 | O2-402 | O2-402 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-402 | [5 empty] | 2025-10-23T16:57:13.881+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-403 | O2-403 | Story | Story |  | OC Process testing (P) | Resolved! | 2026-01-15 | 2026-01-20 |  |  | 0 | 0 | Faiq Butt | 32 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-403 | [5 empty] | 2025-10-23T16:57:27.010+0500 | 2026-02-18T13:16:19.396+0500
O2 | O2-404 | O2-404 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-404 | [5 empty] | 2025-10-23T16:57:36.047+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-405 | O2-405 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-405 | [5 empty] | 2025-10-23T16:57:43.892+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-406 | O2-406 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-406 | [5 empty] | 2025-10-23T16:57:48.473+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-407 | O2-407 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 10 |  | O2-398 | O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-398 | https://octopusdtlsupport.atlassian.net/browse/O2-407 | [5 empty] | 2025-10-23T16:57:53.278+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-408 | O2-408 | Epic | Epic |  | Centrifugal Compressor (Multi Speed) | To Do | 2025-07-28 | 2025-08-10 |  |  | 0 | 0 | awais akhter | 80 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-408 | [5 empty] | 2025-10-23T17:05:37.119+0500 | 2026-01-26T18:19:06.294+0500
O2 | O2-409 | O2-409 | Story | Story |  | Asset Design, HB and Expected models (P) | Resolved! | 2025-07-28 | 2025-08-03 |  |  | 0 | 0 | Mariam Zulfiqar | 40 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-409 | [5 empty] | 2025-10-23T17:06:11.576+0500 | 2025-11-04T12:25:35.904+0500
O2 | O2-41 | O2-41 | Story | Story |  | SQA | Resolved! | 2026-01-05 | 2026-01-15 | 2026-01-08 | 2026-01-15 | 360 | 360 | Zeeshan Sarwar | 159 |  | O2-33 | O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | [5 empty] | 2025-10-02T14:16:51.940+0500 | 2026-02-09T11:13:35.158+0500
O2 | O2-410 | O2-410 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-410 | [5 empty] | 2025-10-23T17:06:18.511+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-411 | O2-411 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! | 2025-08-04 | 2025-08-10 |  |  | 0 | 0 | Mariam Zulfiqar | 40 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-411 | [5 empty] | 2025-10-23T17:06:27.568+0500 | 2025-11-04T12:31:57.340+0500
O2 | O2-412 | O2-412 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-412 | [5 empty] | 2025-10-23T17:06:32.279+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-413 | O2-413 | Story | Story |  | OC Process testing (P) | Resolved! |  |  |  |  | 0 | 0 | Faiq Butt | 32 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-413 | [5 empty] | 2025-10-23T17:06:39.039+0500 | 2026-02-18T13:10:18.761+0500
O2 | O2-414 | O2-414 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-414 | [5 empty] | 2025-10-23T17:06:44.263+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-415 | O2-415 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-415 | [5 empty] | 2025-10-23T17:06:48.345+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-416 | O2-416 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-416 | [5 empty] | 2025-10-23T17:06:52.407+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-417 | O2-417 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 20 |  | O2-408 | O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-408 | https://octopusdtlsupport.atlassian.net/browse/O2-417 | [5 empty] | 2025-10-23T17:06:59.823+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-418 | O2-418 | Epic | Epic |  | Simple Heat Exchangers | To Do |  | 2025-10-12 |  |  | 0 | 0 | awais akhter | 48 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-418 | [5 empty] | 2025-10-23T17:07:24.662+0500 | 2026-01-26T18:19:17.822+0500
O2 | O2-419 | O2-419 | Story | Story |  | Asset Design, HB and Expected models (P) | Resolved! | 2025-09-15 | 2025-10-12 |  |  | 0 | 0 | Mariam Zulfiqar | 8 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-419 | [5 empty] | 2025-10-23T17:07:35.778+0500 | 2025-11-26T15:48:22.300+0500
O2 | O2-420 | O2-420 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-420 | [5 empty] | 2025-10-23T17:07:48.398+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-421 | O2-421 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! | 2025-09-29 | 2025-10-06 |  |  | 0 | 0 | Mariam Zulfiqar | 3 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-421 | [5 empty] | 2025-10-23T17:07:56.234+0500 | 2025-10-29T15:58:46.222+0500
O2 | O2-422 | O2-422 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-422 | [5 empty] | 2025-10-23T17:08:00.581+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-423 | O2-423 | Story | Story |  | OC Process testing (P) | Resolved! | 2026-01-19 | 2026-01-23 | 2026-01-19 | 2026-01-23 | 40 | 40 | DANIYAL AHMAD | 59.5 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-423 | [5 empty] | 2025-10-23T17:08:28.314+0500 | 2026-01-26T18:31:17.489+0500
O2 | O2-424 | O2-424 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-424 | [5 empty] | 2025-10-23T17:08:33.058+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-425 | O2-425 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-425 | [5 empty] | 2025-10-23T17:08:37.470+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-426 | O2-426 | Story | Story |  | User Manual | To Do | 2025-10-02 | 2025-10-03 |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-426 | [5 empty] | 2025-10-23T17:08:41.856+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-427 | O2-427 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 30.5 |  | O2-418 | O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-418 | https://octopusdtlsupport.atlassian.net/browse/O2-427 | [5 empty] | 2025-10-23T17:08:47.905+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-428 | O2-428 | Task | Task |  | FuelAgent - value prop - ppt | Resolved! | 2025-10-21 | 2025-10-24 |  |  | 0 | 0 | Hassan Malik | 24 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-428 | [5 empty] | 2025-10-23T22:07:42.040+0500 | 2025-10-28T09:08:04.544+0500
O2 | O2-429 | O2-429 | Bug Subtask | Bug Subtask |  | Cal tags values are not getting updated | Resolved | 2025-10-24 |  |  |  | 0 | 0 | Namra Zahid | 2 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-429 | [5 empty] | 2025-10-24T10:28:40.374+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-43 | O2-43 | Story | Story |  | Production Release | Resolved! | 2026-01-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | 40 | 40 | Faiza Nasir | 12 |  | O2-33 | O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-43 | [5 empty] | 2025-10-02T14:17:27.934+0500 | 2026-02-13T12:59:36.496+0500
O2 | O2-430 | O2-430 | Sub-task | Sub-task |  | Backend APIs for Pipeline & Triggers | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 18 |  | O2-104 | O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-104 | https://octopusdtlsupport.atlassian.net/browse/O2-430 | [5 empty] | 2025-10-24T11:03:16.842+0500 | 2025-10-27T16:38:58.945+0500
O2 | O2-431 | O2-431 | Bug Subtask | Bug Subtask |  | Update option is not showing when user open saved trending graph and click on Save as button | Resolved | 2025-10-27 | 2025-10-29 |  |  | 0 | 0 | Ali Qumail | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-431 | [5 empty] | 2025-10-24T12:22:39.924+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-432 | O2-432 | Bug Subtask | Bug Subtask |  | Invalid modeled tags count is getting displayed for user Trained anomaly group, Kindly look into it. | Resolved | 2025-10-24 |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 1.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-432 | [5 empty] | 2025-10-24T15:35:08.856+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-433 | O2-433 | Task | Task |  | APX Template Support | Resolved! | 2025-10-23 | 2025-10-24 |  |  | 0 | 0 | Ali Qumail | 12 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-433 | [5 empty] | 2025-10-24T17:21:16.414+0500 | 2025-10-24T17:23:05.669+0500
O2 | O2-434 | O2-434 | Sub-task | Sub-task |  | Smoke-Production | Resolved! | 2025-10-27 | 2025-10-28 |  |  | 80 | 80 | Muhammad Abbas | 58 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-434 | [5 empty] | 2025-10-27T09:28:55.723+0500 | 2026-02-13T13:00:37.895+0500
O2 | O2-435 | O2-435 | Sub-task | Sub-task |  | Production Green Deployment | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-17 | O2-17 | https://octopusdtlsupport.atlassian.net/browse/O2-17 | https://octopusdtlsupport.atlassian.net/browse/O2-435 | [5 empty] | 2025-10-27T10:32:08.630+0500 | 2025-10-27T13:02:29.360+0500
O2 | O2-436 | O2-436 | Bug Subtask | Bug Subtask |  | Internal Server error is showing while creating conditional cal tag | Resolved |  |  |  |  | 0 | 0 | Waqar Rasheed | 1 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-436 | [5 empty] | 2025-10-27T11:13:03.278+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-437 | O2-437 | Bug Subtask | Bug Subtask |  | Internal Server error is showing while creating Timer Tag | Resolved |  |  |  |  | 0 | 0 | Waqar Rasheed | 1 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-437 | [5 empty] | 2025-10-27T11:33:24.630+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-438 | O2-438 | Bug Subtask | Bug Subtask |  | Totalizer Calculated tag live values are not showing | Resolved |  |  |  |  | 0 | 0 | Waqar Rasheed | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-438 | [5 empty] | 2025-10-27T11:37:12.114+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-439 | O2-439 | Bug Subtask | Bug Subtask |  | Drop down options are not displaying in model relaxation factor of anomaly creation | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-439 | [5 empty] | 2025-10-27T13:03:45.086+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-440 | O2-440 | Sub-task | Sub-task |  | Analyzing KeyVault integration in OC | Resolved! | 2025-10-27 |  |  |  | 0 | 0 | Faiza Nasir | 14 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-440 | [5 empty] | 2025-10-27T13:07:05.860+0500 | 2025-12-17T12:49:39.792+0500
O2 | O2-441 | O2-441 | Epic | Epic |  | Water Cooled Steam Condenser | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-441 | [5 empty] | 2025-10-27T14:20:30.501+0500 | 2026-01-26T18:19:28.413+0500
O2 | O2-442 | O2-442 | Story | Story |  | Asset Design, HB and Expected models (P) | Resolved! | 2025-09-15 | 2025-09-26 |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-442 | [5 empty] | 2025-10-27T14:20:42.461+0500 | 2025-10-29T16:00:34.830+0500
O2 | O2-443 | O2-443 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-443 | [5 empty] | 2025-10-27T14:20:52.700+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-444 | O2-444 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! | 2025-09-29 | 2025-10-06 |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-444 | [5 empty] | 2025-10-27T14:21:00.745+0500 | 2025-10-29T16:00:53.609+0500
O2 | O2-445 | O2-445 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-445 | [5 empty] | 2025-10-27T14:21:06.840+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-446 | O2-446 | Story | Story |  | OC Process testing (P) | Resolved! | 2026-01-19 | 2026-01-21 |  |  | 24 | 24 | Danish Rashid | 24 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-446 | [5 empty] | 2025-10-27T14:21:12.728+0500 | 2026-02-18T13:01:28.480+0500
O2 | O2-447 | O2-447 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-447 | [5 empty] | 2025-10-27T14:21:18.131+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-448 | O2-448 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-448 | [5 empty] | 2025-10-27T14:21:23.267+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-449 | O2-449 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-449 | [5 empty] | 2025-10-27T14:21:39.220+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-45 | O2-45 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-11 | O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-11 | https://octopusdtlsupport.atlassian.net/browse/O2-45 | [5 empty] | 2025-10-02T14:18:08.552+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-450 | O2-450 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 9 |  | O2-441 | O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-441 | https://octopusdtlsupport.atlassian.net/browse/O2-450 | [5 empty] | 2025-10-27T14:21:44.303+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-451 | O2-451 | Bug Subtask | Bug Subtask |  | Import site layout failed. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-451 | [5 empty] | 2025-10-27T14:37:04.149+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-452 | O2-452 | Epic | Epic |  | Cooling Tower | To Do |  |  |  |  | 0 | 0 | awais akhter | 7 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-452 | [5 empty] | 2025-10-27T14:48:31.478+0500 | 2026-01-26T18:19:38.903+0500
O2 | O2-453 | O2-453 | Epic | Epic |  | Boiler | To Do |  | 2025-10-16 |  |  | 0 | 0 | awais akhter | 120 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-453 | [5 empty] | 2025-10-27T14:48:42.089+0500 | 2026-01-26T18:19:50.340+0500
O2 | O2-456 | O2-456 | Epic | Epic |  | OC Trending V2 | To Do | 2026-05-04 | 2026-06-10 |  |  | 256 | 256 | Zain Munir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-456 | [5 empty] | 2025-10-27T14:49:02.341+0500 | 2026-04-14T16:29:50.187+0500
O2 | O2-457 | O2-457 | Epic | Epic |  | APX Visualisations Enhancements | Resolved! | 2026-01-26 | 2026-03-03 |  |  | 440 | 440 | Zain Munir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-457 | [5 empty] | 2025-10-27T14:49:06.300+0500 | 2026-03-31T13:05:21.017+0500
O2 | O2-458 | O2-458 | Epic | Epic |  | APX Performance Module Enhancements | To Do |  |  |  |  | 0 | 0 | awais akhter | 20 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-458 | [5 empty] | 2025-10-27T14:49:11.076+0500 | 2026-01-26T18:20:20.543+0500
O2 | O2-459 | O2-459 | Epic | Epic |  | Centrifugal Pump Health Module Update (P) | Resolved! | 2025-10-27 | 2026-05-10 |  |  | 0 | 0 | Faiza Nasir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-459 | [5 empty] | 2025-10-27T14:49:16.038+0500 | 2026-04-28T10:02:26.979+0500
O2 | O2-46 | O2-46 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-10 | O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-10 | https://octopusdtlsupport.atlassian.net/browse/O2-46 | [5 empty] | 2025-10-02T14:18:23.574+0500 | 2026-02-11T10:59:41.498+0500
O2 | O2-460 | O2-460 | Epic | Epic |  | Auxiliary Load Advisor (OmniALA) | To Do | 2025-10-30 | 2025-11-07 |  |  | 0 | 0 | awais akhter | 110 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-460 | [5 empty] | 2025-10-27T14:49:22.057+0500 | 2026-04-08T10:29:18.696+0500
O2 | O2-461 | O2-461 | Epic | Epic |  | Cooling Tower Advisor | To Do |  |  |  |  | 0 | 0 | awais akhter | 16 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-461 | [5 empty] | 2025-10-27T14:49:27.047+0500 | 2026-01-26T18:21:06.849+0500
O2 | O2-462 | O2-462 | Epic | Epic |  | Pumps Operating OC Advisor (like DEWA) | To Do | 2025-03-20 | 2025-04-10 |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-462 | [5 empty] | 2025-10-27T14:49:30.813+0500 | 2026-03-31T15:47:09.031+0500
O2 | O2-463 | O2-463 | Story | Story |  | Pre-URS Engineering | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-462 | O2-462 | https://octopusdtlsupport.atlassian.net/browse/O2-462 | https://octopusdtlsupport.atlassian.net/browse/O2-463 | [5 empty] | 2025-10-27T14:53:44.054+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-464 | O2-464 | Story | Story |  | User Requirement Specifications | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-462 | O2-462 | https://octopusdtlsupport.atlassian.net/browse/O2-462 | https://octopusdtlsupport.atlassian.net/browse/O2-464 | [5 empty] | 2025-10-27T14:53:54.155+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-465 | O2-465 | Story | Story |  | Asset Design, HB and Expected models (P) | Resolved! | 2025-09-15 | 2025-09-26 |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-465 | [5 empty] | 2025-10-27T16:47:18.682+0500 | 2025-10-29T16:01:40.296+0500
O2 | O2-466 | O2-466 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-466 | [5 empty] | 2025-10-27T16:47:25.773+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-467 | O2-467 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! | 2025-09-29 | 2025-10-06 |  |  | 0 | 0 | Mariam Zulfiqar | 12 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-467 | [5 empty] | 2025-10-27T16:47:30.903+0500 | 2025-10-29T16:01:51.417+0500
O2 | O2-468 | O2-468 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-468 | [5 empty] | 2025-10-27T16:47:35.059+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-469 | O2-469 | Story | Story |  | OC Process testing (P) | Resolved! | 2026-01-19 | 2026-01-23 |  |  | 0 | 0 | Muhammad Abdul Wasi | 40 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-469 | [5 empty] | 2025-10-27T16:47:39.479+0500 | 2026-02-18T14:54:32.720+0500
O2 | O2-47 | O2-47 | Story | Story |  | User Manual | Resolved! | 2025-10-20 | 2025-10-23 |  |  | 48 | 48 | awais akhter | 40 |  | O2-9 | O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-9 | https://octopusdtlsupport.atlassian.net/browse/O2-47 | [5 empty] | 2025-10-02T14:18:38.334+0500 | 2025-10-29T11:44:13.875+0500
O2 | O2-470 | O2-470 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-470 | [5 empty] | 2025-10-27T16:47:44.092+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-471 | O2-471 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-471 | [5 empty] | 2025-10-27T16:47:48.297+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-472 | O2-472 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-472 | [5 empty] | 2025-10-27T16:47:52.525+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-473 | O2-473 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 13 |  | O2-452 | O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-452 | https://octopusdtlsupport.atlassian.net/browse/O2-473 | [5 empty] | 2025-10-27T16:47:56.128+0500 | 2026-03-10T16:17:34.881+0500
O2 | O2-474 | O2-474 | Story | Story |  | Asset Design, HB and Expected models (P) | Resolved! | 2025-09-23 | 2025-10-12 |  |  | 88 | 88 | Mariam Zulfiqar | 104 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-474 | [5 empty] | 2025-10-27T16:49:13.557+0500 | 2026-02-18T13:30:49.956+0500
O2 | O2-475 | O2-475 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-475 | [5 empty] | 2025-10-27T16:49:19.998+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-476 | O2-476 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! | 2025-10-13 | 2025-10-16 |  |  | 0 | 0 | Mariam Zulfiqar | 32 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-476 | [5 empty] | 2025-10-27T16:49:27.009+0500 | 2026-01-22T12:09:16.001+0500
O2 | O2-477 | O2-477 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-477 | [5 empty] | 2025-10-27T16:49:31.396+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-478 | O2-478 | Story | Story |  | OC Process testing (P) | Resolved! |  |  |  |  | 0 | 0 | Faiq Butt | 24 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-478 | [5 empty] | 2025-10-27T16:49:35.839+0500 | 2026-02-18T12:54:51.823+0500
O2 | O2-479 | O2-479 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-479 | [5 empty] | 2025-10-27T16:49:40.499+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-48 | O2-48 | Story | Story |  | Research/URS | Resolved! | 2025-09-15 | 2025-09-15 |  |  | 8 | 8 | Hamza Ali | 8 |  | O2-34 | O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-48 | [5 empty] | 2025-10-02T14:19:03.847+0500 | 2025-10-23T09:46:16.901+0500
O2 | O2-480 | O2-480 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-480 | [5 empty] | 2025-10-27T16:49:44.910+0500 | 2026-01-22T11:29:18.418+0500
O2 | O2-481 | O2-481 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-481 | [5 empty] | 2025-10-27T16:49:48.844+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-482 | O2-482 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 17 |  | O2-453 | O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-453 | https://octopusdtlsupport.atlassian.net/browse/O2-482 | [5 empty] | 2025-10-27T16:49:53.793+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-483 | O2-483 | Task | Task |  | Fintech fuel with AI - value propt - ppt - GoAIHub.io | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 17 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-483 | [5 empty] | 2025-10-28T09:08:28.024+0500 | 2025-11-10T16:58:12.761+0500
O2 | O2-484 | O2-484 | Task | Task |  | FuelAgent - Competitive Landscape - Research PPT | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 16 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-484 | [5 empty] | 2025-10-28T09:09:07.305+0500 | 2025-11-06T10:04:20.435+0500
O2 | O2-485 | O2-485 | Story | Story |  | Pre-URS Engineering | To Do | 2025-09-01 |  |  |  | 40 | 40 | Mariam Zulfiqar | 16 |  | O2-461 | O2-461 | https://octopusdtlsupport.atlassian.net/browse/O2-461 | https://octopusdtlsupport.atlassian.net/browse/O2-485 | [5 empty] | 2025-10-28T11:29:38.575+0500 | 2026-02-12T09:32:35.419+0500
O2 | O2-486 | O2-486 | Story | Story |  | User Requirement Specifications | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-461 | O2-461 | https://octopusdtlsupport.atlassian.net/browse/O2-461 | https://octopusdtlsupport.atlassian.net/browse/O2-486 | [5 empty] | 2025-10-28T11:29:45.695+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-487 | O2-487 | Story | Story |  | User Requirement Specifications | Resolved! | 2025-10-30 | 2025-12-31 | 2026-02-13 | 2026-02-13 | 80 | 80 | Faiq Butt | 86 |  | O2-460 | O2-460 | https://octopusdtlsupport.atlassian.net/browse/O2-460 | https://octopusdtlsupport.atlassian.net/browse/O2-487 | [5 empty] | 2025-10-28T11:30:39.356+0500 | 2026-02-13T17:08:10.340+0500
O2 | O2-488 | O2-488 | Story | Story |  | Pre-URS Engineering | Resolved! | 2025-09-08 | 2025-09-30 |  |  | 24 | 24 | Mariam Zulfiqar | 24 |  | O2-460 | O2-460 | https://octopusdtlsupport.atlassian.net/browse/O2-460 | https://octopusdtlsupport.atlassian.net/browse/O2-488 | [5 empty] | 2025-10-28T11:30:44.424+0500 | 2026-01-23T11:01:29.905+0500
O2 | O2-49 | O2-49 | Story | Story |  | Research/DDS | Resolved! | 2025-09-16 | 2025-09-16 |  |  | 8 | 8 | Hamza Ali | 8 |  | O2-34 | O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-49 | [5 empty] | 2025-10-02T14:19:15.695+0500 | 2025-10-17T16:46:22.749+0500
O2 | O2-497 | O2-497 | Story | Story |  | Research/URS (P) | Resolved! | 2025-09-15 | 2025-09-22 |  |  | 0 | 0 | Mariam Zulfiqar | 40 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-497 | [5 empty] | 2025-10-28T11:32:57.855+0500 | 2025-11-04T11:11:05.286+0500
O2 | O2-5 | O2-5 | Story | Story |  | Development | Resolved! | 2025-11-03 | 2025-11-17 |  |  | 160 | 160 | ahad omer | 152 |  | O2-2 | O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-5 | [5 empty] | 2025-10-02T13:56:09.761+0500 | 2025-12-01T15:40:41.013+0500
O2 | O2-50 | O2-50 | Story | Story |  | Development | Resolved! | 2025-09-17 | 2025-09-26 |  |  | 320 | 320 | Hamza Ali | 164 |  | O2-34 | O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | [5 empty] | 2025-10-02T14:19:23.930+0500 | 2025-10-24T16:24:40.440+0500
O2 | O2-502 | O2-502 | Story | Story |  | Make Training Material (P) | Resolved! | 2025-11-17 | 2025-12-31 |  |  | 200 | 200 | DANIYAL AHMAD | 192 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-502 | [5 empty] | 2025-10-28T11:33:46.597+0500 | 2026-02-18T13:13:27.178+0500
O2 | O2-505 | O2-505 | Story | Story |  | Research/URS (P) | Resolved! |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-456 | O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-505 | [5 empty] | 2025-10-28T11:34:42.291+0500 | 2025-10-29T15:37:13.827+0500
O2 | O2-506 | O2-506 | Story | Story |  | Research/DDS | To Do | 2026-05-04 | 2026-05-08 |  |  | 40 | 40 | Zain Munir | 0 |  | O2-456 | O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-506 | [5 empty] | 2025-10-28T11:34:47.501+0500 | 2026-04-14T15:36:47.824+0500
O2 | O2-507 | O2-507 | Story | Story |  | Development | To Do | 2026-05-11 | 2026-05-29 |  |  | 152 | 152 | Zain Munir | 0 |  | O2-456 | O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-507 | [5 empty] | 2025-10-28T11:34:52.467+0500 | 2026-04-14T15:37:28.677+0500
O2 | O2-509 | O2-509 | Story | Story |  | SQA | To Do | 2026-06-01 | 2026-06-05 |  |  | 40 | 40 | Muhammad Abbas | 0 |  | O2-456 | O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-509 | [5 empty] | 2025-10-28T11:35:01.117+0500 | 2026-04-14T15:36:06.081+0500
O2 | O2-51 | O2-51 | Story | Story |  | SQA | Resolved! | 2025-09-29 | 2025-10-02 |  |  | 32 | 32 | Muhammad Abbas | 32 |  | O2-34 | O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-51 | [5 empty] | 2025-10-02T14:19:30.501+0500 | 2025-10-17T16:45:03.701+0500
O2 | O2-510 | O2-510 | Story | Story |  | Make Training Material | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-456 | O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-510 | [5 empty] | 2025-10-28T11:35:06.249+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-513 | O2-513 | Story | Story |  | Research/URS (P) | Resolved! | 2025-10-06 | 2025-10-17 |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-513 | [5 empty] | 2025-10-28T11:36:03.037+0500 | 2026-02-12T09:31:41.340+0500
O2 | O2-514 | O2-514 | Story | Story |  | Research/DDS | Resolved! | 2026-01-26 | 2026-01-30 |  |  | 120 | 120 | Zain Munir | 98 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-514 | [5 empty] | 2025-10-28T11:36:08.372+0500 | 2026-02-13T16:27:40.274+0500
O2 | O2-515 | O2-515 | Story | Story |  | Development | Resolved! | 2026-02-02 | 2026-02-23 |  |  | 120 | 120 | Zain Munir | 61.5 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | [5 empty] | 2025-10-28T11:36:18.500+0500 | 2026-02-19T14:11:27.995+0500
O2 | O2-517 | O2-517 | Story | Story |  | SQA | Resolved! | 2026-02-18 | 2026-02-27 |  |  | 40 | 40 | Muhammad Abbas | 50.5 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-517 | [5 empty] | 2025-10-28T11:36:26.445+0500 | 2026-02-27T10:31:05.187+0500
O2 | O2-518 | O2-518 | Story | Story |  | Make Training Material (P) | To Do |  | 2026-02-27 |  |  | 40 | 40 | Mariam Zulfiqar | 0 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-518 | [5 empty] | 2025-10-28T11:36:29.964+0500 | 2026-03-03T12:45:00.425+0500
O2 | O2-519 | O2-519 | Story | Story |  | User Manual | To Do | 2026-02-18 | 2026-02-27 |  |  | 24 | 24 | Hassan Malik | 0 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-519 | [5 empty] | 2025-10-28T11:36:34.196+0500 | 2026-02-19T09:52:01.242+0500
O2 | O2-52 | O2-52 | Story | Story |  | User Manual | Resolved! | 2025-10-01 | 2025-10-02 |  |  | 8 | 8 | Hassan Malik | 8 |  | O2-34 | O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-52 | [5 empty] | 2025-10-02T14:19:49.346+0500 | 2025-11-13T09:46:23.289+0500
O2 | O2-520 | O2-520 | Story | Story |  | Production Release | Resolved! | 2026-03-17 | 2026-03-19 |  |  | 80 | 80 | Ameer Hamza Khan | 34.5 |  | O2-457 | O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-457 | https://octopusdtlsupport.atlassian.net/browse/O2-520 | [5 empty] | 2025-10-28T11:36:38.168+0500 | 2026-03-31T13:05:17.481+0500
O2 | O2-521 | O2-521 | Story | Story |  | Research/URS (P) | Resolved! | 2025-09-01 | 2025-09-07 |  |  | 0 | 0 | Mariam Zulfiqar | 20 |  | O2-458 | O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-521 | [5 empty] | 2025-10-28T11:37:28.474+0500 | 2025-11-04T12:39:32.567+0500
O2 | O2-522 | O2-522 | Story | Story |  | Research/DDS | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-458 | O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-522 | [5 empty] | 2025-10-28T11:37:35.371+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-523 | O2-523 | Story | Story |  | Development | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-458 | O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-523 | [5 empty] | 2025-10-28T11:37:39.514+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-524 | O2-524 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | O2-458 | O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-524 | [5 empty] | 2025-10-28T11:37:43.642+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-526 | O2-526 | Story | Story |  | Make Training Material (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-458 | O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-526 | [5 empty] | 2025-10-28T11:37:53.048+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-527 | O2-527 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-458 | O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-527 | [5 empty] | 2025-10-28T11:37:57.322+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-528 | O2-528 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-458 | O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-458 | https://octopusdtlsupport.atlassian.net/browse/O2-528 | [5 empty] | 2025-10-28T11:38:01.737+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-529 | O2-529 | Story | Story |  | Tags, Groups, FMEA, Alerts Update | Resolved! | 2025-12-26 | 2026-01-07 |  |  | 64 | 64 | Danish Rashid | 64 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-529 | [5 empty] | 2025-10-28T11:39:14.138+0500 | 2026-02-18T12:56:21.905+0500
O2 | O2-53 | O2-53 | Story | Story |  | Production Release | Resolved! | 2025-10-03 | 2025-10-03 |  |  | 24 | 24 | Ameer Hamza Khan | 28 |  | O2-34 | O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-34 | https://octopusdtlsupport.atlassian.net/browse/O2-53 | [5 empty] | 2025-10-02T14:19:57.050+0500 | 2025-10-24T16:25:28.518+0500
O2 | O2-530 | O2-530 | Story | Story |  | Template Update | Resolved! | 2026-01-12 | 2026-01-13 |  |  | 16 | 16 | Danish Rashid | 31 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-530 | [5 empty] | 2025-10-28T11:39:24.721+0500 | 2026-02-18T12:57:02.794+0500
O2 | O2-531 | O2-531 | Story | Story |  | OC testing | Resolved! | 2026-01-14 | 2026-01-16 |  |  | 24 | 24 | Danish Rashid | 24 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-531 | [5 empty] | 2025-10-28T11:39:29.956+0500 | 2026-02-18T12:57:42.492+0500
O2 | O2-534 | O2-534 | Story | Story |  | Make Training Material | Resolved! | 2026-01-05 | 2026-01-30 |  |  | 0.17 | 0.17 | Mariam Zulfiqar | 80 |  | O2-459 | O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-459 | https://octopusdtlsupport.atlassian.net/browse/O2-534 | [5 empty] | 2025-10-28T11:39:43.615+0500 | 2026-02-11T09:38:57.299+0500
O2 | O2-537 | O2-537 | Bug Subtask | Bug Subtask |  | APX output calculated tags are not displaying on latest values screen even after hitting publish changes multiple times. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-16 | O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-16 | https://octopusdtlsupport.atlassian.net/browse/O2-537 | [5 empty] | 2025-10-28T12:05:58.875+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-541 | O2-541 | Bug Subtask | Bug Subtask |  | When import data toggle in role management is disabled in edge configuration then it should be restricted from IOT and MQTT establish connection option as well. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-541 | [5 empty] | 2025-10-29T10:50:26.011+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-542 | O2-542 | Bug Subtask | Bug Subtask |  | GPS latest values for both IOT and MQTT devices are not displaying. | Resolved |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-542 | [5 empty] | 2025-10-29T11:35:12.885+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-544 | O2-544 | Sub-task | Sub-task |  | OC Process Testing (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-68 | O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-68 | https://octopusdtlsupport.atlassian.net/browse/O2-544 | [5 empty] | 2025-10-29T12:20:37.590+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-545 | O2-545 | Bug Subtask | Bug Subtask |  | Unable to search real time tag while creating totalizer tag. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 6 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-545 | [5 empty] | 2025-10-29T12:36:36.645+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-546 | O2-546 | Sub-task | Sub-task |  | OC Process Testing (P) | Resolved! | 2026-01-12 | 2026-01-14 | 2026-01-12 | 2026-01-14 | 24 | 24 | Mariam Zulfiqar | 24 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-546 | [5 empty] | 2025-10-29T12:38:02.872+0500 | 2026-01-22T11:54:25.217+0500
O2 | O2-547 | O2-547 | Sub-task | Sub-task |  | Re-do for Existing Asset (P) | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Mariam Zulfiqar | 5 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-547 | [5 empty] | 2025-10-29T12:45:27.250+0500 | 2026-01-30T10:16:11.159+0500
O2 | O2-548 | O2-548 | Story | Story |  | Production Release | To Do | 2026-06-08 | 2026-06-10 |  |  | 24 | 24 | Ameer Hamza Khan | 0 |  | O2-456 | O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-548 | [5 empty] | 2025-10-29T12:51:55.160+0500 | 2026-04-14T15:36:17.195+0500
O2 | O2-549 | O2-549 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-456 | O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | https://octopusdtlsupport.atlassian.net/browse/O2-549 | [5 empty] | 2025-10-29T12:52:14.764+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-550 | O2-550 | Bug Subtask | Bug Subtask |  | Latest values for write back and Bulk write are not getting displayed | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-550 | [5 empty] | 2025-10-29T15:39:19.479+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-551 | O2-551 | Sub-task | Sub-task |  | OC Process Testing (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-515 | O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-515 | https://octopusdtlsupport.atlassian.net/browse/O2-551 | [5 empty] | 2025-10-29T15:45:05.268+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-552 | O2-552 | Sub-task | Sub-task |  | OC Process Testing (P) | To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | O2-523 | O2-523 | https://octopusdtlsupport.atlassian.net/browse/O2-523 | https://octopusdtlsupport.atlassian.net/browse/O2-552 | [5 empty] | 2025-10-29T15:48:52.979+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-553 | O2-553 | Sub-task | Sub-task |  | Bugs Fixing + Tasks + Improvements | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 56 |  | O2-105 | O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-553 | [5 empty] | 2025-10-29T15:49:27.294+0500 | 2025-11-06T10:04:57.729+0500
O2 | O2-554 | O2-554 | Sub-task | Sub-task |  | OC Process Testing (P) | Resolved! | 2026-01-14 | 2026-01-16 | 2026-01-14 | 2026-01-16 | 24 | 24 | Danish Rashid | 24 |  | O2-531 | O2-531 | https://octopusdtlsupport.atlassian.net/browse/O2-531 | https://octopusdtlsupport.atlassian.net/browse/O2-554 | [5 empty] | 2025-10-29T15:52:01.398+0500 | 2026-02-18T12:28:32.449+0500
O2 | O2-555 | O2-555 | Bug Subtask | Bug Subtask |  | Repetition is displaying against selected single tag in results of user-trained anomaly. | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-555 | [5 empty] | 2025-10-30T09:41:30.304+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-556 | O2-556 | Bug Subtask | Bug Subtask |  | Real time tag names are not displaying in results of user trained anomaly. | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-556 | [5 empty] | 2025-10-30T09:44:16.608+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-557 | O2-557 | Bug Subtask | Bug Subtask |  | all types of tags values are not getting landed because there are no values for real time tags, kindly look into it. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 8.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-557 | [5 empty] | 2025-10-30T10:45:27.148+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-558 | O2-558 | Bug Subtask | Bug Subtask |  | GPS listing screen is not loading. | Resolved |  |  |  |  | 0 | 0 | Faiza Nasir | 5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-558 | [5 empty] | 2025-10-30T12:33:34.020+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-559 | O2-559 | Bug Subtask | Bug Subtask |  | All tags are selected in waiting to transfer screen when page record is only set to 50 where as its working fine in import data point screen. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-559 | [5 empty] | 2025-10-30T12:41:05.617+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-56 | O2-56 | Story | Story |  | Development | Resolved! | 2025-10-06 | 2025-10-17 |  |  | 160 | 160 | Ibrahim Ahmed Qureshi | 0 |  | O2-151 | O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-151 | https://octopusdtlsupport.atlassian.net/browse/O2-56 | [5 empty] | 2025-10-02T14:20:27.945+0500 | 2026-02-11T09:38:57.299+0500
O2 | O2-560 | O2-560 | Bug Subtask | Bug Subtask |  | Totalizer Tag creation popup is not closed after tag creation also created tag shows on listing screen after manual refresh | Resolved | 2025-11-04 | 2025-11-05 |  |  | 0 | 0 | Ali Qumail | 8 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-560 | [5 empty] | 2025-10-30T14:50:01.137+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-561 | O2-561 | Task | Task |  | Ingestion_Time - Read API Documentation | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 2 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-561 | [5 empty] | 2025-10-30T15:20:48.452+0500 | 2025-10-30T15:22:00.529+0500
O2 | O2-562 | O2-562 | Sub-task | Sub-task |  | SFTP - Create - Manual IR Configuration Guide | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 8 |  | O2-106 | O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-562 | [5 empty] | 2025-10-30T15:24:39.346+0500 | 2025-11-03T11:15:49.086+0500
O2 | O2-563 | O2-563 | Sub-task | Sub-task |  | How to - Create - Create New SFTP Connector | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 16 |  | O2-106 | O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-563 | [5 empty] | 2025-10-30T15:25:08.381+0500 | 2025-11-04T10:11:29.194+0500
O2 | O2-564 | O2-564 | Sub-task | Sub-task |  | Fields - Update - Create New Connector | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 2 |  | O2-106 | O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-564 | [5 empty] | 2025-10-30T15:27:51.468+0500 | 2025-10-30T15:31:09.511+0500
O2 | O2-565 | O2-565 | Sub-task | Sub-task |  | How to - Update - Add a table of Site-level Validations for Connectors | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 3 |  | O2-106 | O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-106 | https://octopusdtlsupport.atlassian.net/browse/O2-565 | [5 empty] | 2025-10-30T15:29:55.318+0500 | 2025-11-03T16:59:37.693+0500
O2 | O2-566 | O2-566 | Story | Story |  | Fintech Fuel - Go AI Hub Write Up + Product Screenshots | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 8 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-566 | [5 empty] | 2025-10-31T15:41:31.334+0500 | 2025-11-06T10:04:36.991+0500
O2 | O2-567 | O2-567 | Bug Subtask | Bug Subtask |  | User is able to create Batch/BPM workflow and Batch/BPM Trigger with only numeric characters. It should be Alpha-numeric | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 4 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-567 | [5 empty] | 2025-11-03T11:03:45.150+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-568 | O2-568 | Bug Subtask | Bug Subtask |  | Anomaly Error: Failed to save the anomaly Data selection time slot. while we select multiple time slots to verify 720 hours to be available in timeslots. | Resolved |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 3 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-568 | [5 empty] | 2025-11-03T11:59:31.640+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-569 | O2-569 | Bug Subtask | Bug Subtask |  | Create/Edit modal of Real Time and Calculated tag of type Boolean is showing error on Set points field | Resolved | 2025-11-04 | 2025-11-04 |  |  | 0 | 0 | Ali Qumail | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-569 | [5 empty] | 2025-11-03T12:08:22.588+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-57 | O2-57 | Story | Story |  | SQA | Resolved! | 2025-11-19 | 2025-11-20 |  |  | 160 | 160 | Zeeshan Sarwar | 122 |  | O2-35 | O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | [5 empty] | 2025-10-02T14:20:34.218+0500 | 2025-12-01T16:55:22.651+0500
O2 | O2-570 | O2-570 | Bug Subtask | Bug Subtask |  | As mentioned in both info notes "You can select a maximum of 720 hours of data for training." we are not able to select 720 hours of data for training. | Resolved | 2025-11-03 |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 2.5 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-570 | [5 empty] | 2025-11-03T12:37:32.194+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-571 | O2-571 | Bug Subtask | Bug Subtask |  | Float type tag values are not getting updated | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 1 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-571 | [5 empty] | 2025-11-03T12:44:12.028+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-572 | O2-572 | Bug Subtask | Bug Subtask |  | Selected tags from the fields disappeared when user Edit the Time and Counter Tags | Resolved | 2025-11-06 | 2025-11-06 |  |  | 0 | 0 | Ali Qumail | 4 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-572 | [5 empty] | 2025-11-03T12:52:42.736+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-573 | O2-573 | Sub-task | Sub-task |  | Generate ERD Diagram using AI Plant UML | Resolved! |  |  | 2026-01-30 | 2026-01-30 | 0 | 0 | Faiza Nasir | 13 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-573 | [5 empty] | 2025-11-03T14:00:43.078+0500 | 2026-02-09T13:07:42.217+0500
O2 | O2-574 | O2-574 | Sub-task | Sub-task |  | Generate Flow Diagrams | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-574 | [5 empty] | 2025-11-03T14:02:36.366+0500 | 2025-12-10T10:09:07.223+0500
O2 | O2-575 | O2-575 | Sub-task | Sub-task |  | Finalize Content of DDS | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-575 | [5 empty] | 2025-11-03T14:03:00.605+0500 | 2026-02-03T14:37:32.755+0500
O2 | O2-576 | O2-576 | Bug Subtask | Bug Subtask |  | BPM Activity Deletion system alarm is not triggering | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-576 | [5 empty] | 2025-11-03T16:43:16.629+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-577 | O2-577 | Story | Story |  | Asset Description Retrieval | Resolved! | 2025-11-03 | 2025-11-14 |  |  | 80 | 80 | Taimur Zahid | 40 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-577 | [5 empty] | 2025-11-04T10:22:42.209+0500 | 2026-02-20T09:58:02.688+0500
O2 | O2-578 | O2-578 | Bug Subtask | Bug Subtask |  | When the user clicks Save and Publish after executing all and saving the output, an error appears saying "Table is required." However, when the user clicks on End Activity to add a table, the Save button does not appear. | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-578 | [5 empty] | 2025-11-04T10:49:36.111+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-579 | O2-579 | Bug Subtask | Bug Subtask |  | Again Live Values are not getting updated. | Resolved | 2025-11-04 |  |  |  | 0 | 0 | Mohsin Junaid | 0.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-579 | [5 empty] | 2025-11-04T10:54:43.892+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-58 | O2-58 | Story | Story |  | User Manual | Resolved! | 2025-11-19 | 2025-11-20 |  |  | 160 | 160 | Hassan Malik | 24 |  | O2-35 | O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-58 | [5 empty] | 2025-10-02T14:20:47.167+0500 | 2025-12-01T15:40:05.816+0500
O2 | O2-580 | O2-580 | Bug Subtask | Bug Subtask |  | Correlation Matrix should not be disabled when model is running or stopped. | Resolved | 2025-11-12 | 2025-11-12 |  |  | 0 | 0 | Ali Qumail | 8 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-580 | [5 empty] | 2025-11-04T11:03:54.168+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-581 | O2-581 | Bug Subtask | Bug Subtask |  | There is duplication in anomaly group results on OmniConnect and in export file of anomaly also. | Resolved | 2025-11-04 |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-581 | [5 empty] | 2025-11-04T11:11:40.371+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-582 | O2-582 | Bug Subtask | Bug Subtask |  | The user changed the subtype of one APX asset, and after importing the file, errors are appearing for all APX assets in the fault file. | Resolved |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-582 | [5 empty] | 2025-11-04T14:24:38.615+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-583 | O2-583 | Bug Subtask | Bug Subtask |  | Scheduled Raw: Table is created but all log records are fail and no data is available in tables. | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-583 | [5 empty] | 2025-11-04T14:36:07.320+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-584 | O2-584 | Bug Subtask | Bug Subtask |  | Export To SQL : Displaying an Invalid error "User is not Authorized" with all failure log results No Data Availability in sql. | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-584 | [5 empty] | 2025-11-04T14:44:41.067+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-585 | O2-585 | Bug Subtask | Bug Subtask |  | Schedule Site Hierarchy is displaying success with 0 Effected Rows in Log details but no data or table is created in sql db. | Resolved | 2025-11-04 |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-585 | [5 empty] | 2025-11-04T15:05:33.200+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-586 | O2-586 | Task | Task |  | IOT Edge Installatation Guide | Resolved! |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 16 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-586 | [5 empty] | 2025-11-04T15:26:00.839+0500 | 2026-02-11T09:39:08.033+0500
O2 | O2-587 | O2-587 | Bug Subtask | Bug Subtask |  | Batch Monitoring is displaying error instead of results | Resolved |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-587 | [5 empty] | 2025-11-04T15:35:04.313+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-588 | O2-588 | Bug Subtask | Bug Subtask |  | Error is displaying instead of data for anomaly Analysis, for the time when there was data available. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 34 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-588 | [5 empty] | 2025-11-05T10:22:55.861+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-589 | O2-589 | Task | Task |  | Enable APx assets in APx. Block Modification through ISL | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 11 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-589 | [5 empty] | 2025-11-05T11:23:44.433+0500 | 2025-11-06T10:02:51.739+0500
O2 | O2-59 | O2-59 | Story | Story |  | Production Release | Resolved! | 2025-11-21 | 2025-11-21 |  |  | 16 | 16 | Ameer Hamza Khan | 8 |  | O2-35 | O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-35 | https://octopusdtlsupport.atlassian.net/browse/O2-59 | [5 empty] | 2025-10-02T14:20:54.354+0500 | 2025-12-01T15:40:56.437+0500
O2 | O2-590 | O2-590 | Bug Subtask | Bug Subtask |  | Now its showing error on "Create Model" screen with success message, right after clicking the next button of data selection screen. and "Generated Models Summary" is also Missing. | Resolved |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 5 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-590 | [5 empty] | 2025-11-05T12:20:37.952+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-591 | O2-591 | Sub-task | Sub-task |  | Production Release | Resolved! | 2025-11-05 | 2025-11-10 |  |  | 120 | 120 | Muhammad Abbas | 103 |  | O2-105 | O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-591 | [5 empty] | 2025-11-05T12:28:09.864+0500 | 2026-02-13T13:01:49.699+0500
O2 | O2-592 | O2-592 | Sub-task | Sub-task |  | User Manual Enhancement | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 16 |  | O2-586 | O2-586 | https://octopusdtlsupport.atlassian.net/browse/O2-586 | https://octopusdtlsupport.atlassian.net/browse/O2-592 | [5 empty] | 2025-11-06T10:01:29.801+0500 | 2025-12-08T11:27:06.314+0500
O2 | O2-593 | O2-593 | Bug Subtask | Bug Subtask |  | Statistical Alarms Are not getting triggered, these were configured 3 hours ago | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-593 | [5 empty] | 2025-11-06T13:05:04.282+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-594 | O2-594 | Bug Subtask | Bug Subtask |  | The system alarm name for live values should only be "Live Values Accessed" on Production, just like it is on staging. | Resolved |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-105 | O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-594 | [5 empty] | 2025-11-06T14:17:11.406+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-595 | O2-595 | Bug Subtask | Bug Subtask |  | Error is getting displayed right after when user clicks on the next button Goes to the "Create Model" screen, and here is another issue now, this time Correlation Matrix is missing when we click on its button, Kindly look into it ⁠ | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 1 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-595 | [5 empty] | 2025-11-06T15:56:47.714+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-596 | O2-596 | Bug Subtask | Bug Subtask |  | Schedule for Stats: Giving FAILURE in logs with 4 effected rows and the message "No data available for this execution". Hence Data is shown in the SQL DB's Table | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-596 | [5 empty] | 2025-11-06T16:20:47.095+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-597 | O2-597 | Bug Subtask | Bug Subtask |  | Anomaly Results Are not getting displayed | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-597 | [5 empty] | 2025-11-06T16:49:37.992+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-598 | O2-598 | Bug Subtask | Bug Subtask |  | Correlation Matrix Values are overlapping while user clicks on its button, in LCD mood | Resolved | 2025-11-07 | 2025-11-07 |  |  | 0 | 0 | Ali Qumail | 8.5 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-598 | [5 empty] | 2025-11-07T09:58:23.520+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-599 | O2-599 | Bug Subtask | Bug Subtask |  | Duplication in Data Alarms for for all tags Timer, Totalizer and real | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-105 | O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-599 | [5 empty] | 2025-11-07T10:34:41.847+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-6 | O2-6 | Story | Story |  | SQA | Resolved! | 2025-11-18 | 2025-11-20 |  |  | 80 | 80 | Muhammad Abbas | 264.37 |  | O2-2 | O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | [5 empty] | 2025-10-02T13:56:17.879+0500 | 2025-12-01T16:50:03.007+0500
O2 | O2-60 | O2-60 | Story | Story |  | Research/URS | To Do | 2026-04-13 | 2026-04-14 |  |  | 16 | 16 | Ameer Hamza Khan | 8 |  | O2-36 | O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-60 | [5 empty] | 2025-10-02T14:21:08.037+0500 | 2026-04-09T11:13:55.330+0500
O2 | O2-600 | O2-600 | Epic | Epic |  | MPCL - APX | To Do |  | 2025-11-30 |  |  | 0 | 0 | awais akhter | 1232 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-600 | [5 empty] | 2025-11-07T12:25:34.925+0500 | 2026-01-27T16:27:51.433+0500
O2 | O2-601 | O2-601 | Story | Story |  | APX Reliability | Resolved! | 2025-04-01 | 2025-11-30 |  |  | 0 | 0 | Abdulrehman | 704 |  | O2-600 | O2-600 | https://octopusdtlsupport.atlassian.net/browse/O2-600 | https://octopusdtlsupport.atlassian.net/browse/O2-601 | [5 empty] | 2025-11-07T12:26:03.838+0500 | 2025-12-31T10:33:42.500+0500
O2 | O2-602 | O2-602 | Story | Story |  | APX - Strainer | Resolved! | 2025-06-02 | 2025-07-31 |  |  | 0 | 0 | Abdulrehman | 352 |  | O2-600 | O2-600 | https://octopusdtlsupport.atlassian.net/browse/O2-600 | https://octopusdtlsupport.atlassian.net/browse/O2-602 | [5 empty] | 2025-11-07T12:26:13.673+0500 | 2025-11-10T10:15:14.284+0500
O2 | O2-603 | O2-603 | Story | Story |  | APX - Foaming | Resolved! | 2025-09-01 | 2025-09-30 |  |  | 0 | 0 | Abdulrehman | 176 |  | O2-600 | O2-600 | https://octopusdtlsupport.atlassian.net/browse/O2-600 | https://octopusdtlsupport.atlassian.net/browse/O2-603 | [5 empty] | 2025-11-07T12:26:24.039+0500 | 2025-11-10T12:11:52.334+0500
O2 | O2-604 | O2-604 | Bug Subtask | Bug Subtask |  | Real Tag is not getting deleted in first attempt. | Resolved | 2025-11-10 | 2025-11-10 |  |  | 0 | 0 | Ali Qumail | 6 |  | O2-105 | O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-604 | [5 empty] | 2025-11-10T12:09:50.565+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-605 | O2-605 | Bug Subtask | Bug Subtask |  | Error is Reoccurring on Blue Prod for anomaly User train group | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0.5 |  | O2-105 | O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-605 | [5 empty] | 2025-11-10T15:51:17.785+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-606 | O2-606 | Bug Subtask | Bug Subtask |  | After creation of model again "Correlation Matrix" data is missing | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0.5 |  | O2-105 | O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-105 | https://octopusdtlsupport.atlassian.net/browse/O2-606 | [5 empty] | 2025-11-10T15:59:18.221+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-607 | O2-607 | Task | Task |  | Alarm Configuration Enhancement Development | Resolved! | 2025-11-10 | 2026-01-01 |  |  | 12 | 12 | Ali Qumail | 12 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-607 | [5 empty] | 2025-11-10T17:02:37.849+0500 | 2026-03-02T14:11:47.002+0500
O2 | O2-608 | O2-608 | Sub-task | Sub-task |  | Add a column named "Tag Type" in the Data Not Landing Alert emails. | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 8 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-608 | [5 empty] | 2025-11-11T09:54:08.791+0500 | 2025-11-13T18:51:43.992+0500
O2 | O2-609 | O2-609 | Sub-task | Sub-task |  | UI Development | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 24 |  | O2-5 | O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-609 | [5 empty] | 2025-11-11T11:08:49.298+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-61 | O2-61 | Story | Story |  | Research/DDS | To Do | 2026-04-15 | 2026-04-16 |  |  | 40 | 40 | Ameer Hamza Khan | 0 |  | O2-36 | O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-61 | [5 empty] | 2025-10-02T14:21:14.021+0500 | 2026-04-09T11:13:51.721+0500
O2 | O2-610 | O2-610 | Sub-task | Sub-task |  | Frontend End Development | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 40 |  | O2-5 | O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-610 | [5 empty] | 2025-11-11T11:09:12.222+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-611 | O2-611 | Sub-task | Sub-task |  | Backend Development | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 72 |  | O2-5 | O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-611 | [5 empty] | 2025-11-11T11:09:30.973+0500 | 2025-12-09T17:34:33.203+0500
O2 | O2-612 | O2-612 | Sub-task | Sub-task |  | End-to-end application testing | Resolved! |  |  |  |  | 0 | 0 | ahad omer | 16 |  | O2-5 | O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-5 | https://octopusdtlsupport.atlassian.net/browse/O2-612 | [5 empty] | 2025-11-11T11:10:34.505+0500 | 2025-12-09T17:34:36.620+0500
O2 | O2-613 | O2-613 | Story | Story |  | OmniChat Review | Resolved! |  |  | 2026-01-08 | 2026-01-09 | 0 | 0 | Hassan Malik | 24 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-613 | [5 empty] | 2025-11-11T14:30:44.666+0500 | 2026-01-28T10:54:18.730+0500
O2 | O2-614 | O2-614 | Bug Subtask | Bug Subtask |  | Formula Validation API is getting failed , Unable to create Call tag | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 1 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-614 | [5 empty] | 2025-11-11T14:41:29.235+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-615 | O2-615 | Bug Subtask | Bug Subtask |  | IOT Values are not getting updated again. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0.5 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-615 | [5 empty] | 2025-11-11T14:56:34.367+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-616 | O2-616 | Sub-task | Sub-task |  | Storage Accounts Deletion - 2025 | Resolved! | 2025-11-01 | 2025-11-25 |  |  | 32 | 32 | Taimur Zahid | 32 |  | O2-135 | O2-135 | https://octopusdtlsupport.atlassian.net/browse/O2-135 | https://octopusdtlsupport.atlassian.net/browse/O2-616 | [5 empty] | 2025-11-11T15:49:34.552+0500 | 2026-03-10T10:57:06.965+0500
O2 | O2-617 | O2-617 | Bug Subtask | Bug Subtask |  | Duplication in Calculated tag | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-617 | [5 empty] | 2025-11-11T16:31:36.520+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-618 | O2-618 | Sub-task | Sub-task |  | Product Related Security Documentation | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 24 |  | O2-356 | O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-618 | [5 empty] | 2025-11-11T16:33:01.827+0500 | 2026-01-14T10:04:52.745+0500
O2 | O2-619 | O2-619 | Sub-task | Sub-task |  | Organization Related Security Documentation | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-356 | O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-619 | [5 empty] | 2025-11-11T16:33:18.402+0500 | 2026-01-14T10:04:49.373+0500
O2 | O2-62 | O2-62 | Story | Story |  | Development | To Do | 2026-04-17 | 2026-04-30 |  |  | 56 | 56 | Ameer Hamza Khan | 0 |  | O2-36 | O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-62 | [5 empty] | 2025-10-02T14:21:22.918+0500 | 2026-04-09T11:16:05.822+0500
O2 | O2-620 | O2-620 | Bug Subtask | Bug Subtask |  | In Enterprise Connectors, the trigger should automatically start upon first-time creation; when the user stops and restarts it, the system should prompt for a new start time in UTC. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 8 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-620 | [5 empty] | 2025-11-12T10:09:26.167+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-621 | O2-621 | Bug Subtask | Bug Subtask |  | Duplicate calculated tags are creating through import site layout. | Request received |  |  |  |  | 0 | 0 | Ali Qumail | 2 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-621 | [5 empty] | 2025-11-12T10:35:48.698+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-622 | O2-622 | Bug Subtask | Bug Subtask |  | Unknown error occurs during CAL tag creation via Import Site Layout when importing 400–500 tags; resources fail to load (not related to internet connection). | Resolved |  |  |  |  | 0 | 0 | Faiza Nasir | 3 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-622 | [5 empty] | 2025-11-12T10:50:10.236+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-623 | O2-623 | Bug Subtask | Bug Subtask |  | Rmapped name is displaying instead of user selected tag names against parameters. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 24 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-623 | [5 empty] | 2025-11-12T11:31:21.552+0500 | 2026-02-26T10:38:40.497+0500
O2 | O2-624 | O2-624 | Bug Subtask | Bug Subtask |  | Response is not correct for APX asset in omni agent. Whether it should display data or it should tell that only output cal tag data for performance asset can be seen. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 16 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-624 | [5 empty] | 2025-11-12T11:37:12.503+0500 | 2026-02-26T10:40:35.800+0500
O2 | O2-625 | O2-625 | Bug Subtask | Bug Subtask |  | Wrong response is given as I have asked about health parameters and it has given me performance output parameters, omni agent is restricted for health APX asset so it should response accordingly. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 16 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-625 | [5 empty] | 2025-11-12T11:44:33.036+0500 | 2026-02-26T10:41:11.481+0500
O2 | O2-626 | O2-626 | Bug Subtask | Bug Subtask |  | While using Cal tag in Anomaly group creation, NO data is getting displayed in "Correlation Matrix". | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-626 | [5 empty] | 2025-11-12T11:54:25.176+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-627 | O2-627 | Bug Subtask | Bug Subtask |  | Totalizer Calculated tag Live values are not landing where as Calculated tag used in Totalizer condition live values are populating | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-627 | [5 empty] | 2025-11-12T14:31:54.099+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-629 | O2-629 | Bug Subtask | Bug Subtask |  | Table view is not created in omni agent APX. | Request received |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 0 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-629 | [5 empty] | 2025-11-12T16:00:53.773+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-63 | O2-63 | Story | Story |  | SQA | To Do | 2026-05-04 | 2026-05-06 |  |  | 24 | 24 | Muhammad Abbas | 0 |  | O2-36 | O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-63 | [5 empty] | 2025-10-02T14:21:30.134+0500 | 2026-04-09T11:19:10.061+0500
O2 | O2-630 | O2-630 | Story | Story |  | Security Implementation Project Report | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 8 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-630 | [5 empty] | 2025-11-12T16:51:36.143+0500 | 2025-11-12T16:56:36.834+0500
O2 | O2-632 | O2-632 | Sub-task | Sub-task |  | Costing | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-630 | O2-630 | https://octopusdtlsupport.atlassian.net/browse/O2-630 | https://octopusdtlsupport.atlassian.net/browse/O2-632 | [5 empty] | 2025-11-12T16:55:49.346+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-633 | O2-633 | Bug Subtask | Bug Subtask |  | Anomaly Groups are getting created while all permissions are off and Only read permission is allowed When Create permission is off and all other are allowed | Resolved | 2025-11-13 | 2025-11-13 |  |  | 0 | 0 | Ali Qumail | 7 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-633 | [5 empty] | 2025-11-12T16:57:06.098+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-634 | O2-634 | Sub-task | Sub-task |  | FE and BE Development - OmniAgent APX | To Do |  |  |  |  | 0 | 0 | awais akhter | 88 |  | O2-377 | O2-377 | https://octopusdtlsupport.atlassian.net/browse/O2-377 | https://octopusdtlsupport.atlassian.net/browse/O2-634 | [5 empty] | 2025-11-13T09:18:27.479+0500 | 2025-12-30T13:15:00.087+0500
O2 | O2-635 | O2-635 | Sub-task | Sub-task |  | Production Sanity | Resolved! | 2025-11-13 | 2025-11-14 |  |  | 160 | 160 | Muhammad Abbas | 136.57 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-635 | [5 empty] | 2025-11-13T09:51:49.493+0500 | 2026-02-13T13:01:18.794+0500
O2 | O2-637 | O2-637 | Bug Subtask | Bug Subtask |  | While stopping the model its giving an error " There is no model created for this group " while model is in running state. its on the group which is having call tag in it. | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-637 | [5 empty] | 2025-11-13T11:06:59.990+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-638 | O2-638 | Sub-task | Sub-task |  | Key Vault Integration in OC | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 29 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-638 | [5 empty] | 2025-11-13T11:58:03.185+0500 | 2025-11-19T17:16:01.869+0500
O2 | O2-639 | O2-639 | Sub-task | Sub-task |  | Finalizing and changes after review from lead | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 22 |  | O2-39 | O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-39 | https://octopusdtlsupport.atlassian.net/browse/O2-639 | [5 empty] | 2025-11-13T11:59:07.985+0500 | 2026-02-03T14:42:41.463+0500
O2 | O2-64 | O2-64 | Story | Story |  | Production Release | To Do | 2026-05-07 | 2026-05-08 |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-36 | O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-64 | [5 empty] | 2025-10-02T14:21:35.880+0500 | 2026-04-09T11:20:15.284+0500
O2 | O2-640 | O2-640 | Bug Subtask | Bug Subtask |  | Downloaded CSV file and sheet name should be user friendly against APX data details in omni agent. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-640 | [5 empty] | 2025-11-13T12:16:48.424+0500 | 2026-02-26T10:41:34.598+0500
O2 | O2-641 | O2-641 | Sub-task | Sub-task |  | How To - APX <> OmniAgent | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 8 |  | O2-58 | O2-58 | https://octopusdtlsupport.atlassian.net/browse/O2-58 | https://octopusdtlsupport.atlassian.net/browse/O2-641 | [5 empty] | 2025-11-13T12:26:22.129+0500 | 2025-11-24T09:48:00.769+0500
O2 | O2-642 | O2-642 | Sub-task | Sub-task |  | Fields - APX <> OmniAgent | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 16 |  | O2-58 | O2-58 | https://octopusdtlsupport.atlassian.net/browse/O2-58 | https://octopusdtlsupport.atlassian.net/browse/O2-642 | [5 empty] | 2025-11-13T12:26:35.018+0500 | 2025-12-01T10:10:25.108+0500
O2 | O2-643 | O2-643 | Bug Subtask | Bug Subtask |  | User friendly error message should display on frontend when CSV file link is expired and it is clicked again rather than displaying backend error in a new tab. | Not a Bug |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-643 | [5 empty] | 2025-11-13T12:29:20.301+0500 | 2026-02-26T10:24:12.581+0500
O2 | O2-645 | O2-645 | Bug Subtask | Bug Subtask |  | Write back FAIL, NO Vales are getting fetched on front End, But Simulator is working properly. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-645 | [5 empty] | 2025-11-14T10:59:19.993+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-646 | O2-646 | Bug Subtask | Bug Subtask |  | Anomaly Analysis are Failed | Resolved |  |  | 2026-01-02 | 2026-01-02 | 0 | 0 | Ibrahim Ahmed Qureshi | 34 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-646 | [5 empty] | 2025-11-14T12:37:07.188+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-647 | O2-647 | Bug Subtask | Bug Subtask |  | OMNI Agent is returning non-existing tags. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-647 | [5 empty] | 2025-11-14T15:12:08.173+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-648 | O2-648 | Sub-task | Sub-task |  | ODL-PD-110 - Identity and Access Management Procedures | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 64 |  | O2-356 | O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-356 | https://octopusdtlsupport.atlassian.net/browse/O2-648 | [5 empty] | 2025-11-17T10:52:04.532+0500 | 2025-12-01T16:24:41.235+0500
O2 | O2-649 | O2-649 | Bug Subtask | Bug Subtask |  | Anomaly Failed Again | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 1 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-649 | [5 empty] | 2025-11-18T12:30:59.339+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-65 | O2-65 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-36 | O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-36 | https://octopusdtlsupport.atlassian.net/browse/O2-65 | [5 empty] | 2025-10-02T14:21:50.409+0500 | 2025-12-30T13:14:52.331+0500
O2 | O2-650 | O2-650 | Bug Subtask | Bug Subtask |  | Stats Alarms are getting displayed for the time when site wasn't even created | Resolved |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-69 | O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | https://octopusdtlsupport.atlassian.net/browse/O2-650 | [5 empty] | 2025-11-18T15:08:04.651+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-651 | O2-651 | Bug Subtask | Bug Subtask |  | Circular dependency in formula is present due to which selected formula calculation is not ending where it is applied. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 2 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-651 | [5 empty] | 2025-11-18T16:50:54.197+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-652 | O2-652 | Bug Subtask | Bug Subtask |  | UI Disturbed for all dropdowns of Settings | Request received |  |  |  |  | 0 | 0 | Muhammad Abdullah | 0 |  | O2-112 | O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-112 | https://octopusdtlsupport.atlassian.net/browse/O2-652 | [5 empty] | 2025-11-19T09:42:39.966+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-653 | O2-653 | Sub-task | Sub-task |  | Sanity_Staging | Resolved! | 2025-11-19 | 2025-11-20 |  |  | 80 | 80 | Muhammad Abbas | 75.8 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-653 | [5 empty] | 2025-11-19T10:16:18.860+0500 | 2026-02-13T13:03:19.217+0500
O2 | O2-654 | O2-654 | Bug Subtask | Bug Subtask |  | Response is not given against asked query in APX omni agent. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-654 | [5 empty] | 2025-11-19T10:35:25.918+0500 | 2026-02-26T10:41:50.059+0500
O2 | O2-657 | O2-657 | Bug Subtask | Bug Subtask |  | Bulk Fetch Connection String is not working as expected | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-657 | [5 empty] | 2025-11-19T10:55:46.348+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-658 | O2-658 | Bug Subtask | Bug Subtask |  | Omni agent for APX is giving response for health asset as well where as it is restricted for now. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-658 | [5 empty] | 2025-11-19T11:01:36.903+0500 | 2026-02-26T10:42:08.060+0500
O2 | O2-659 | O2-659 | Bug Subtask | Bug Subtask |  | In Batch BPM, the output table column description limit is not applied, causing the API to crash while saving. | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-659 | [5 empty] | 2025-11-19T20:44:33.591+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-660 | O2-660 | Bug Subtask | Bug Subtask |  | When using a user-defined table as an existing table for a new Batch BPM job, the API does not return or display the column descriptions after importing the schema. | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-660 | [5 empty] | 2025-11-19T21:03:56.287+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-661 | O2-661 | Bug Subtask | Bug Subtask |  | In Batch BPM module, when a user clones a job, the system allows creating another job with the same name. | Resolved |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-661 | [5 empty] | 2025-11-19T21:17:17.132+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-662 | O2-662 | Bug Subtask | Bug Subtask |  | Area dependency is displaying on assets even after cancelling the pop up display while deleting respective area. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 3 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-662 | [5 empty] | 2025-11-20T10:13:13.467+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-663 | O2-663 | Bug Subtask | Bug Subtask |  | Calculated and Totalizer tag values are not updating, whereas the Real-time tag live values are populating. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-663 | [5 empty] | 2025-11-20T10:28:46.581+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-664 | O2-664 | Bug Subtask | Bug Subtask |  | Incorrect Spelling of "Calculated" in Alarm Name Description on System Alarms Viewer Screen | Resolved |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-664 | [5 empty] | 2025-11-20T12:31:15.831+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-665 | O2-665 | Bug Subtask | Bug Subtask |  | Error is displaying while configuring AHU APX performance asset. Dash should be automatically changed into underscore same as it is changing spaces. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 3 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-665 | [5 empty] | 2025-11-20T12:32:31.775+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-667 | O2-667 | Bug Subtask | Bug Subtask |  | Totalizer tags values are not getting updated. | Resolved |  |  |  |  | 0 | 0 | Mohsin Junaid | 1 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-667 | [5 empty] | 2025-11-20T12:51:22.298+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-668 | O2-668 | Bug Subtask | Bug Subtask |  | When a user-defined function is used in BPM, the process validates successfully and the output is saved. However, when selecting “Execute All & Save Output,” the RUN STATUS shows ERROR. | Resolved |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-668 | [5 empty] | 2025-11-20T13:09:39.022+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-669 | O2-669 | Bug Subtask | Bug Subtask |  | Huge gap is displaying between two real time tag Mapped names created through ISL. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-669 | [5 empty] | 2025-11-20T14:40:42.892+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-67 | O2-67 | Story | Story |  | Research/DDS | Resolved! | 2025-09-29 | 2025-10-01 |  |  | 24 | 24 | Muhammad Zeeshan Aslam | 24 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-67 | [5 empty] | 2025-10-02T14:22:11.743+0500 | 2025-10-29T12:21:27.169+0500
O2 | O2-670 | O2-670 | Story | Story |  | OmniAgent - Value Proposition PPT | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 24 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-670 | [5 empty] | 2025-11-20T15:11:32.046+0500 | 2025-12-08T09:34:25.251+0500
O2 | O2-671 | O2-671 | Story | Story |  | [Research] - OmniConnect Dashboarding Competitors | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 64 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-671 | [5 empty] | 2025-11-20T15:19:57.577+0500 | 2025-12-12T09:42:05.688+0500
O2 | O2-672 | O2-672 | Bug Subtask | Bug Subtask |  | Unexcepted error is occurring after login, unless we refresh the application | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-672 | [5 empty] | 2025-11-20T15:32:29.240+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-673 | O2-673 | Sub-task | Sub-task |  | Sanity_Production | Resolved! | 2025-11-21 | 2025-11-17 |  |  | 160 | 160 | Muhammad Abbas | 121.57 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-673 | [5 empty] | 2025-11-21T09:44:36.108+0500 | 2026-02-13T13:03:41.259+0500
O2 | O2-678 | O2-678 | Bug Subtask | Bug Subtask |  | After recent deployment of OC fast Publish Changes is not working for all sites | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-678 | [5 empty] | 2025-11-21T11:27:01.366+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-679 | O2-679 | Sub-task | Sub-task |  | Fields - Update Write KQL Query Dialog Fields | Resolved! |  |  |  |  | 0 | 0 | Maria Sharafat | 8 |  | O2-7 | O2-7 | https://octopusdtlsupport.atlassian.net/browse/O2-7 | https://octopusdtlsupport.atlassian.net/browse/O2-679 | [5 empty] | 2025-11-21T16:29:48.019+0500 | 2026-02-11T09:39:05.017+0500
O2 | O2-68 | O2-68 | Story | Story |  | Development | Resolved! | 2025-10-01 | 2025-10-13 |  |  | 264 | 264 | Muhammad Zeeshan Aslam | 132 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-68 | [5 empty] | 2025-10-02T14:22:18.540+0500 | 2025-10-29T11:52:25.833+0500
O2 | O2-680 | O2-680 | Bug Subtask | Bug Subtask |  | Anomaly Results are not getting displayed, model was created successfully | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 3 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-680 | [5 empty] | 2025-11-21T17:49:16.914+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-681 | O2-681 | Bug Subtask | Bug Subtask |  | Omni agent is not giving correct answer for APX health asset. | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-57 | O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-57 | https://octopusdtlsupport.atlassian.net/browse/O2-681 | [5 empty] | 2025-11-24T10:57:17.918+0500 | 2026-02-26T10:42:18.101+0500
O2 | O2-682 | O2-682 | Bug Subtask | Bug Subtask |  | Critical Issue: Trending is showing an Error (400 bad request), while user selects real type tag directly on trending screen. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 1 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-682 | [5 empty] | 2025-11-24T11:03:19.966+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-686 | O2-686 | Sub-task | Sub-task |  | Prep Prod Planning /Tasks | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 5 |  | O2-8 | O2-8 | https://octopusdtlsupport.atlassian.net/browse/O2-8 | https://octopusdtlsupport.atlassian.net/browse/O2-686 | [5 empty] | 2025-11-24T16:32:51.235+0500 | 2026-01-20T14:58:28.697+0500
O2 | O2-687 | O2-687 | Sub-task | Sub-task |  | Production Green Release | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 8 |  | O2-8 | O2-8 | https://octopusdtlsupport.atlassian.net/browse/O2-8 | https://octopusdtlsupport.atlassian.net/browse/O2-687 | [5 empty] | 2025-11-24T16:33:07.704+0500 | 2026-01-20T14:57:48.503+0500
O2 | O2-688 | O2-688 | Sub-task | Sub-task |  | Production Blue Release | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 4 |  | O2-8 | O2-8 | https://octopusdtlsupport.atlassian.net/browse/O2-8 | https://octopusdtlsupport.atlassian.net/browse/O2-688 | [5 empty] | 2025-11-24T16:33:17.594+0500 | 2026-01-20T14:58:23.111+0500
O2 | O2-689 | O2-689 | Sub-task | Sub-task |  | Moving all Web Appsettings and Function Apps secrets in Production Green to Key Vault | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 9 |  | O2-134 | O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-134 | https://octopusdtlsupport.atlassian.net/browse/O2-689 | [5 empty] | 2025-11-24T16:44:14.270+0500 | 2025-12-10T14:21:36.142+0500
O2 | O2-69 | O2-69 | Story | Story |  | SQA | Resolved! | 2025-10-20 | 2025-11-13 |  |  | 120 | 120 | Namra Zahid | 278.07 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-69 | [5 empty] | 2025-10-02T14:22:24.160+0500 | 2025-11-19T10:13:23.636+0500
O2 | O2-690 | O2-690 | Sub-task | Sub-task |  | Schema changes for Additional Property with Scaffolding | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 3 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-690 | [5 empty] | 2025-11-24T16:58:02.833+0500 | 2026-01-06T16:22:20.058+0500
O2 | O2-691 | O2-691 | Sub-task | Sub-task |  | API Developments CRUD for Additional Property | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 36 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-691 | [5 empty] | 2025-11-24T16:58:50.355+0500 | 2026-01-06T16:21:14.493+0500
O2 | O2-692 | O2-692 | Sub-task | Sub-task |  | Development + API Integrations + Unit Testing | Resolved! |  |  | 2026-01-01 | 2026-01-01 | 0 | 0 | Zain Munir | 140 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-692 | [5 empty] | 2025-11-25T09:42:45.350+0500 | 2026-01-06T16:21:28.737+0500
O2 | O2-693 | O2-693 | Sub-task | Sub-task |  | Dynamic Headers Table UI Development | Resolved! | 2025-11-21 | 2026-01-02 |  |  | 112 | 112 | Ali Qumail | 112 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-693 | [5 empty] | 2025-11-25T10:17:12.780+0500 | 2026-03-02T14:11:52.984+0500
O2 | O2-694 | O2-694 | Bug Subtask | Bug Subtask |  | Anomaly Fail: Error with success message is getting displayed and after that create model screen is not appearing its just keep on Processing | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-694 | [5 empty] | 2025-11-25T13:08:35.338+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-695 | O2-695 | Bug Subtask | Bug Subtask |  | Bulk Connection strings are not getting Fetched, | Request received |  |  |  |  | 0 | 0 | Muhammad Yousha Agha | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-695 | [5 empty] | 2025-11-25T14:27:33.699+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-696 | O2-696 | Task | Task |  | MPN Migration | Resolved! | 2025-11-24 | 2025-11-28 |  |  | 64 | 64 | Taimur Zahid | 0 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-696 | [5 empty] | 2025-11-25T15:36:31.706+0500 | 2026-01-23T17:14:22.916+0500
O2 | O2-697 | O2-697 | Epic | Epic |  | Calculated Tags Enhancements (With No Code) | On Hold | 2026-05-04 | 2026-05-29 |  |  | 325.6 | 325.6 | Mohsin Junaid | 48 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-697 | [5 empty] | 2025-11-25T15:42:52.886+0500 | 2026-04-08T15:52:49.376+0500
O2 | O2-698 | O2-698 | Story | Story |  | SQA | To Do | 2026-05-22 | 2026-05-29 |  |  | 96 | 96 | Muhammad Abbas | 0 |  | O2-697 | O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-698 | [5 empty] | 2025-11-25T15:43:06.084+0500 | 2026-04-08T15:27:41.992+0500
O2 | O2-7 | O2-7 | Story | Story |  | User Manual | Resolved! | 2025-11-18 | 2025-11-20 |  |  | 32 | 32 | Hassan Malik | 8 |  | O2-2 | O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-7 | [5 empty] | 2025-10-02T13:56:48.617+0500 | 2025-11-21T16:29:10.405+0500
O2 | O2-70 | O2-70 | Story | Story |  | User Manual | Resolved! | 2025-10-20 | 2025-11-13 |  |  | 120 | 120 | Hassan Malik | 24 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-70 | [5 empty] | 2025-10-02T14:22:39.430+0500 | 2025-12-02T22:17:05.054+0500
O2 | O2-700 | O2-700 | Story | Story |  | Development | In-Progress | 2026-02-16 | 2026-02-20 |  |  | 120 | 120 | Mohsin Junaid | 88 |  | O2-697 | O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | [5 empty] | 2025-11-25T15:44:00.463+0500 | 2026-02-17T18:34:31.873+0500
O2 | O2-701 | O2-701 | Story | Story |  | Production Release | To Do | 2026-03-10 | 2026-03-13 |  |  | 56 | 56 | Taimur Zahid | 0 |  | O2-697 | O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-701 | [5 empty] | 2025-11-25T15:44:22.667+0500 | 2026-03-26T14:46:38.296+0500
O2 | O2-702 | O2-702 | Bug Subtask | Bug Subtask |  | Anomaly Analysis Failed Again | Resolved |  |  |  |  | 0 | 0 | Ibrahim Ahmed Qureshi | 0 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-702 | [5 empty] | 2025-11-25T16:15:16.502+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-703 | O2-703 | Story | Story |  | User Manual | To Do | 2025-12-22 | 2025-12-25 |  |  | 32 | 32 | Hassan Malik | 0 |  | O2-697 | O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-703 | [5 empty] | 2025-11-26T10:42:45.855+0500 | 2026-02-13T10:49:23.903+0500
O2 | O2-704 | O2-704 | Task | Task |  | QA Testing | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 110.27 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-704 | [5 empty] | 2025-11-26T14:53:42.661+0500 | 2026-02-11T09:39:07.072+0500
O2 | O2-705 | O2-705 | Task | Task |  | OmniConnect Demonstration | Resolved! |  |  |  |  | 0 | 0 | Sarmad Sabir | 111.5 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-705 | [5 empty] | 2025-11-26T14:54:02.776+0500 | 2026-03-04T13:12:51.104+0500
O2 | O2-706 | O2-706 | Sub-task | Sub-task |  | Test Case Updating | Resolved! | 2025-11-26 | 2025-12-23 |  |  | 120 | 120 | Muhammad Abbas | 110.27 |  | O2-704 | O2-704 | https://octopusdtlsupport.atlassian.net/browse/O2-704 | https://octopusdtlsupport.atlassian.net/browse/O2-706 | [5 empty] | 2025-11-26T14:59:16.379+0500 | 2026-02-13T13:09:29.746+0500
O2 | O2-707 | O2-707 | Task | Task |  | OC-Regression 12/15/2025 | Resolved! | 2025-12-02 | 2025-12-14 | 2026-01-01 | 2026-01-08 | 0 | 0 | Muhammad Abbas | 290.67 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-707 | [5 empty] | 2025-11-26T18:43:53.926+0500 | 2026-01-30T14:46:51.612+0500
O2 | O2-708 | O2-708 | Task | Task |  | Automation of OMNI Connect Manual Test Cases. | Resolved! | 2025-12-02 | 2026-12-31 |  |  | 0 | 0 | Muhammad Abbas | 9 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-708 | [5 empty] | 2025-11-26T18:43:59.192+0500 | 2026-02-11T09:39:07.072+0500
O2 | O2-71 | O2-71 | Story | Story |  | Production Release | Resolved! | 2025-11-14 | 2025-11-14 |  |  | 8 | 8 | Muhammad Zeeshan Aslam | 16 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-71 | [5 empty] | 2025-10-02T14:22:45.614+0500 | 2026-01-22T14:21:39.392+0500
O2 | O2-711 | O2-711 | Sub-task | Sub-task |  | Bug Fixing, Improvements and Tasks | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 56 |  | O2-6 | O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-6 | https://octopusdtlsupport.atlassian.net/browse/O2-711 | [5 empty] | 2025-12-01T16:07:48.188+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-712 | O2-712 | Story | Story |  | User Manual | Resolved! | 2026-01-05 | 2026-01-15 | 2026-01-09 | 2026-01-12 | 16 | 16 | Hassan Malik | 16 |  | O2-33 | O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-33 | https://octopusdtlsupport.atlassian.net/browse/O2-712 | [5 empty] | 2025-12-01T16:48:08.188+0500 | 2026-03-02T13:50:55.990+0500
O2 | O2-713 | O2-713 | Epic | Epic |  | IT Table to OT Tag Conversion - Phase 1 | To Do |  |  |  |  | 0 | 0 | awais akhter | 56 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-713 | [5 empty] | 2025-12-02T11:33:56.652+0500 | 2026-01-27T16:28:11.531+0500
O2 | O2-714 | O2-714 | Epic | Epic |  | BPM Editable & Reusability Enhancement | Resolved! | 2025-12-01 | 2025-12-19 | 2026-01-07 | 2026-01-09 | 0 | 0 | awais akhter | 64 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-714 | [5 empty] | 2025-12-02T11:34:40.004+0500 | 2026-02-19T11:32:18.651+0500
O2 | O2-715 | O2-715 | Story | Story |  | Development | Resolved! | 2025-12-01 | 2025-12-22 |  |  | 160 | 160 | ahad omer | 146.5 |  | O2-714 | O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-715 | [5 empty] | 2025-12-02T11:35:08.066+0500 | 2026-02-11T09:38:56.892+0500
O2 | O2-716 | O2-716 | Story | Story |  | SQA | Resolved! | 2025-12-22 | 2026-01-01 |  |  | 128 | 128 | Muhammad Abbas | 24 |  | O2-714 | O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-716 | [5 empty] | 2025-12-02T11:35:11.450+0500 | 2026-01-21T10:23:17.649+0500
O2 | O2-717 | O2-717 | Story | Story |  | Production Release | Resolved! | 2026-01-02 | 2026-01-02 | 2026-01-05 | 2026-01-08 | 16 | 16 | ahad omer | 136.5 |  | O2-714 | O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | [5 empty] | 2025-12-02T11:35:30.051+0500 | 2026-02-11T09:38:56.892+0500
O2 | O2-718 | O2-718 | Story | Story |  | User Manual | Resolved! | 2025-12-22 | 2026-01-01 |  |  | 32 | 32 | Hassan Malik | 16 |  | O2-714 | O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-718 | [5 empty] | 2025-12-02T11:35:41.625+0500 | 2026-01-08T16:21:57.450+0500
O2 | O2-719 | O2-719 | Story | Story |  | Development | To Do | 2025-12-15 | 2026-01-09 |  |  | 240 | 240 | ahad omer | 80 |  | O2-713 | O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-719 | [5 empty] | 2025-12-02T11:41:11.416+0500 | 2026-02-19T14:06:58.088+0500
O2 | O2-720 | O2-720 | Story | Story |  | SQA | To Do | 2026-01-12 | 2026-01-16 |  |  | 200 | 200 | Muhammad Abbas | 0 |  | O2-713 | O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-720 | [5 empty] | 2025-12-02T11:41:12.156+0500 | 2026-02-19T14:06:56.347+0500
O2 | O2-721 | O2-721 | Story | Story |  | User Manual | To Do | 2026-01-12 | 2026-01-16 |  |  | 40 | 40 | Hassan Malik | 0 |  | O2-713 | O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-721 | [5 empty] | 2025-12-02T11:41:15.977+0500 | 2026-02-19T14:02:55.279+0500
O2 | O2-722 | O2-722 | Story | Story |  | Production Release | To Do | 2026-01-19 | 2026-01-19 |  |  | 56 | 56 | ahad omer | 0 |  | O2-713 | O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-722 | [5 empty] | 2025-12-02T11:41:19.611+0500 | 2026-02-19T14:06:53.797+0500
O2 | O2-723 | O2-723 | Bug Subtask | Bug Subtask |  | UI Issue on Login Page After Updating a User With Multiple Site Assignments (Logged-in User Auto Logout) | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-723 | [5 empty] | 2025-12-02T14:19:32.525+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-724 | O2-724 | Sub-task | Sub-task |  | Login Module | Resolved! | 2025-12-02 | 2025-12-03 |  |  | 16 | 16 | Muhammad Abbas | 9 |  | O2-708 | O2-708 | https://octopusdtlsupport.atlassian.net/browse/O2-708 | https://octopusdtlsupport.atlassian.net/browse/O2-724 | [5 empty] | 2025-12-02T14:23:43.388+0500 | 2026-02-13T13:04:58.613+0500
O2 | O2-725 | O2-725 | Sub-task | Sub-task |  | APx Step Template API Development Modification | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 32 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-725 | [5 empty] | 2025-12-02T17:02:38.738+0500 | 2026-01-06T15:12:36.154+0500
O2 | O2-726 | O2-726 | Sub-task | Sub-task |  | APx Asset API Modification to incorporate Additional Properties | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 16 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-726 | [5 empty] | 2025-12-02T17:05:02.414+0500 | 2026-01-06T15:12:42.110+0500
O2 | O2-727 | O2-727 | Story | Story |  | Asset Hierarchy Metadata | Resolved! | 2025-12-01 | 2025-12-08 |  |  | 0 | 0 | Aiza Hamid | 128 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-727 | [5 empty] | 2025-12-04T12:27:34.554+0500 | 2025-12-30T10:40:43.720+0500
O2 | O2-728 | O2-728 | Task | Task |  | OC competitive research. | Resolved! | 2025-12-04 |  |  |  | 0 | 0 | Muhammad Abbas | 70.6 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-728 | [5 empty] | 2025-12-04T16:48:59.000+0500 | 2026-01-30T11:30:44.875+0500
O2 | O2-729 | O2-729 | Story | Story |  | [Research] - Fintech vs SM365 and others - Competitors | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 24 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-729 | [5 empty] | 2025-12-08T09:40:31.011+0500 | 2025-12-10T10:30:32.308+0500
O2 | O2-730 | O2-730 | Sub-task | Sub-task |  | User Manual - API Guide | Resolved! | 2025-12-04 | 2025-12-08 |  |  | 0 | 0 | Maria Sharafat | 40 |  | O2-727 | O2-727 | https://octopusdtlsupport.atlassian.net/browse/O2-727 | https://octopusdtlsupport.atlassian.net/browse/O2-730 | [5 empty] | 2025-12-08T09:47:56.760+0500 | 2025-12-11T11:47:06.451+0500
O2 | O2-731 | O2-731 | Sub-task | Sub-task |  | OmniAgent PPT for Tom and Some enrichments | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 32 |  | O2-377 | O2-377 | https://octopusdtlsupport.atlassian.net/browse/O2-377 | https://octopusdtlsupport.atlassian.net/browse/O2-731 | [5 empty] | 2025-12-08T12:09:18.723+0500 | 2026-02-11T09:39:06.257+0500
O2 | O2-74 | O2-74 | Sub-task | Sub-task |  | DB Design and Pipeline Design | Resolved! |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-74 | [5 empty] | 2025-10-03T12:36:07.384+0500 | 2025-10-06T10:50:58.568+0500
O2 | O2-75 | O2-75 | Sub-task | Sub-task |  | Implementation | Resolved! |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 48 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-75 | [5 empty] | 2025-10-03T12:47:58.772+0500 | 2025-10-08T10:20:49.992+0500
O2 | O2-755 | O2-755 | Task | Task |  | OmniAgent Enhancement User guidance | Resolved! |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 64 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-755 | [5 empty] | 2025-12-11T10:00:10.960+0500 | 2026-02-13T14:51:31.070+0500
O2 | O2-756 | O2-756 | Sub-task | Sub-task |  | OCM Development | Resolved! |  |  |  |  | 0 | 0 | Ali Qumail | 32 |  | O2-700 | O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-700 | https://octopusdtlsupport.atlassian.net/browse/O2-756 | [5 empty] | 2025-12-11T10:16:20.866+0500 | 2026-01-06T09:55:13.912+0500
O2 | O2-757 | O2-757 | Sub-task | Sub-task |  | Update Password Validation Error Message Displayed on Setup new password screen | Resolved! | 2026-01-21 | 2026-01-21 |  |  | 0.08 | 0.08 | Zain Munir | 0 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-757 | [5 empty] | 2025-12-11T12:14:13.825+0500 | 2026-02-23T11:48:38.152+0500
O2 | O2-758 | O2-758 | Sub-task | Sub-task |  | UI Development | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 31 |  | O2-715 | O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-758 | [5 empty] | 2025-12-11T14:14:58.072+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-759 | O2-759 | Sub-task | Sub-task |  | Frontend End Development | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 38 |  | O2-715 | O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-759 | [5 empty] | 2025-12-11T14:15:15.292+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-76 | O2-76 | Sub-task | Sub-task |  | Dev Unit Testing | Resolved! |  |  |  |  | 0 | 0 | Hamza Ali | 0 |  | O2-50 | O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-50 | https://octopusdtlsupport.atlassian.net/browse/O2-76 | [5 empty] | 2025-10-03T12:49:31.687+0500 | 2025-10-03T19:30:36.609+0500
O2 | O2-760 | O2-760 | Sub-task | Sub-task |  | Backend Development | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 49.5 |  | O2-715 | O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-760 | [5 empty] | 2025-12-11T14:15:31.389+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-761 | O2-761 | Sub-task | Sub-task |  | End-to-end application testing | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 28 |  | O2-715 | O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-715 | https://octopusdtlsupport.atlassian.net/browse/O2-761 | [5 empty] | 2025-12-11T14:15:44.944+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-762 | O2-762 | Task | Task |  | [Presentation] - Octopus Digital Agentic IPs | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 10 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-762 | [5 empty] | 2025-12-11T15:23:34.175+0500 | 2025-12-12T09:42:42.164+0500
O2 | O2-763 | O2-763 | Task | Task |  | [Presentation] - [Diagram] - Fintech Fuel Concept | Resolved! |  |  |  |  | 0 | 0 | Hassan Malik | 2 |  | O2-221 | O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-221 | https://octopusdtlsupport.atlassian.net/browse/O2-763 | [5 empty] | 2025-12-11T15:26:52.867+0500 | 2025-12-11T15:28:20.864+0500
O2 | O2-764 | O2-764 | Task | Task |  | POC - IT to OT tags | To Do |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-764 | [5 empty] | 2025-12-12T09:50:13.142+0500 | 2025-12-30T13:15:01.587+0500
O2 | O2-766 | O2-766 | Sub-task | Sub-task |  | Schema Changes to add APx Curve Section | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 4 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-766 | [5 empty] | 2025-12-12T15:15:29.120+0500 | 2026-01-06T15:12:47.356+0500
O2 | O2-767 | O2-767 | Sub-task | Sub-task |  | APx Curve Template API modification , Include Sections as well | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 20 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-767 | [5 empty] | 2025-12-12T15:16:54.543+0500 | 2026-01-06T15:12:52.480+0500
O2 | O2-771 | O2-771 | Bug Subtask | Bug Subtask |  | No tag of string type is being created—neither conditional cal, nor timer, nor counter. | Resolved |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-771 | [5 empty] | 2025-12-15T16:24:28.050+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-772 | O2-772 | Bug Subtask | Bug Subtask |  | Anomaly Analysis are failed to load again. | Resolved |  |  |  |  | 0 | 0 | Aiza Hamid | 0.5 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-772 | [5 empty] | 2025-12-16T14:36:08.125+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-773 | O2-773 | Bug Subtask | Bug Subtask |  | Error is displaying in all condition based tags, when a condition is defined between two tags but one tag is in first line and second is entered in second line of condition expression field. | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 4 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-773 | [5 empty] | 2025-12-17T10:19:52.903+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-774 | O2-774 | Sub-task | Sub-task |  | Unit mandatory check should be removed from all calculated, conditional calculated and totalizer tags. | Resolved! |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 4 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-774 | [5 empty] | 2025-12-17T10:25:24.422+0500 | 2025-12-29T12:38:52.294+0500
O2 | O2-775 | O2-775 | Bug Subtask | Bug Subtask |  | SMS OPT IN Showing this Error while verifying the number. | Resolved |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 1 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-775 | [5 empty] | 2025-12-17T11:38:18.086+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-776 | O2-776 | Bug Subtask | Bug Subtask |  | It has been more than 40 minutes of checking the notify me button but still no Alarm SMS are getting received till now. | Resolved |  |  | 2026-01-07 | 2026-01-07 | 0 | 0 | Ameer Hamza Khan | 1 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-776 | [5 empty] | 2025-12-17T12:30:41.734+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-777 | O2-777 | Sub-task | Sub-task |  | While creating/editing a site, spaces should also be allowed on Staging, just like they are allowed on Production | Resolved! |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-777 | [5 empty] | 2025-12-17T16:36:02.854+0500 | 2026-02-11T09:39:06.901+0500
O2 | O2-778 | O2-778 | Bug Subtask | Bug Subtask |  | Output Table Name popup is not closed after success message | Request received |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-778 | [5 empty] | 2025-12-18T14:15:34.771+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-779 | O2-779 | Sub-task | Sub-task |  | Bug Fixing, Improvements and Tasks | Resolved! |  |  |  |  | 0 | 0 | Arslan sohail | 24 |  | O2-716 | O2-716 | https://octopusdtlsupport.atlassian.net/browse/O2-716 | https://octopusdtlsupport.atlassian.net/browse/O2-779 | [5 empty] | 2025-12-19T15:27:29.094+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-780 | O2-780 | Sub-task | Sub-task |  | UI/UX Design and Implementation | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 16 |  | O2-719 | O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-780 | [5 empty] | 2025-12-19T16:16:41.163+0500 | 2026-02-19T14:06:58.583+0500
O2 | O2-781 | O2-781 | Sub-task | Sub-task |  | Unit Testing (Frontend and Backend) | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-719 | O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-781 | [5 empty] | 2025-12-19T16:16:46.624+0500 | 2026-02-19T14:06:59.054+0500
O2 | O2-782 | O2-782 | Sub-task | Sub-task |  | Frontend Development | To Do |  |  |  |  | 0 | 0 | Arslan sohail | 0 |  | O2-719 | O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-782 | [5 empty] | 2025-12-19T16:16:46.625+0500 | 2026-02-19T14:06:59.651+0500
O2 | O2-783 | O2-783 | Sub-task | Sub-task |  | End-to-End Application Testing | To Do |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-719 | O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-783 | [5 empty] | 2025-12-19T16:16:46.640+0500 | 2026-02-19T14:07:00.312+0500
O2 | O2-784 | O2-784 | Sub-task | Sub-task |  | Backend/API Development | To Do |  |  |  |  | 0 | 0 | ahad omer | 16 |  | O2-719 | O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-784 | [5 empty] | 2025-12-19T16:16:46.724+0500 | 2026-02-19T14:07:00.708+0500
O2 | O2-785 | O2-785 | Story | Story |  | Research/URS | To Do |  |  |  |  | 0 | 0 | ahad omer | 56 |  | O2-713 | O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-713 | https://octopusdtlsupport.atlassian.net/browse/O2-785 | [5 empty] | 2025-12-21T22:42:17.741+0500 | 2026-02-26T11:04:29.008+0500
O2 | O2-786 | O2-786 | Sub-task | Sub-task |  | APx Curve Modal APIs modification , Include Sections as well | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 24 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-786 | [5 empty] | 2025-12-23T19:40:38.636+0500 | 2026-01-06T15:12:57.151+0500
O2 | O2-787 | O2-787 | Sub-task | Sub-task |  | Performance Dashboard for VFD Development | Resolved! | 2025-12-23 | 2026-01-21 | 2026-01-02 | 2026-01-21 | 56 | 56 | Zain Munir | 52 |  | O2-1095 | O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-1095 | https://octopusdtlsupport.atlassian.net/browse/O2-787 | [5 empty] | 2025-12-24T10:18:07.529+0500 | 2026-02-13T15:55:17.545+0500
O2 | O2-788 | O2-788 | Story | Story |  | Research/URS | Resolved! | 2026-01-01 | 2026-01-16 |  |  | 128 | 128 | Ayyan Babar | 96 |  | O2-793 | O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-788 | [5 empty] | 2025-12-26T10:03:06.604+0500 | 2026-03-26T10:20:58.758+0500
O2 | O2-789 | O2-789 | Story | Story |  | Development | Resolved! | 2026-01-16 | 2026-02-11 |  |  | 160 | 160 | Ayyan Babar | 274.5 |  | O2-793 | O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-789 | [5 empty] | 2025-12-26T10:03:16.805+0500 | 2026-03-11T14:51:19.011+0500
O2 | O2-790 | O2-790 | Story | Story |  | SQA | Resolved! | 2026-01-05 | 2026-01-09 |  |  | 48 | 48 | Muhammad Abbas | 253 |  | O2-793 | O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | [5 empty] | 2025-12-26T10:03:18.433+0500 | 2026-03-26T10:20:49.932+0500
O2 | O2-791 | O2-791 | Story | Story |  | User manual | Resolved! | 2026-01-05 | 2026-01-09 | 2026-04-09 | 2026-04-09 | 4 | 4 | Hassan Malik | 1 |  | O2-793 | O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-791 | [5 empty] | 2025-12-26T10:03:21.615+0500 | 2026-04-09T10:56:00.598+0500
O2 | O2-792 | O2-792 | Story | Story |  | Production Release | Resolved! | 2026-01-12 | 2026-01-15 |  |  | 80 | 80 | Ayyan Babar | 257.5 |  | O2-793 | O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-793 | https://octopusdtlsupport.atlassian.net/browse/O2-792 | [5 empty] | 2025-12-26T10:03:24.671+0500 | 2026-04-08T11:19:42.192+0500
O2 | O2-793 | O2-793 | Epic | Epic |  | Real-time Tag Streaming | Resolved! | 2025-12-23 | 2026-02-06 | 2026-01-01 | 2026-01-27 | 416 | 416 | Mohsin Junaid | 201 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-793 | [5 empty] | 2025-12-26T10:08:51.545+0500 | 2026-04-09T10:56:03.193+0500
O2 | O2-794 | O2-794 | Story | Story |  | Counter Tag Reset | To Do | 2026-01-15 | 2026-01-26 |  |  | 80 | 80 | Mohsin Junaid | 80 |  | O2-697 | O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-697 | https://octopusdtlsupport.atlassian.net/browse/O2-794 | [5 empty] | 2025-12-26T10:10:39.520+0500 | 2026-02-20T11:10:56.887+0500
O2 | O2-795 | O2-795 | Sub-task | Sub-task |  | APX GetAllAsssets API optimization - Performance bottleneck | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 24 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-795 | [5 empty] | 2025-12-26T15:21:14.723+0500 | 2026-01-06T15:13:05.116+0500
O2 | O2-796 | O2-796 | Sub-task | Sub-task |  | APx Activation API Modification to incorporate Curve Data manipulation for IsAppendable and Sections | Resolved! |  | 2025-12-30 |  |  | 0 | 0 | Faiza Nasir | 13 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-796 | [5 empty] | 2025-12-26T15:22:08.812+0500 | 2026-01-06T15:13:12.313+0500
O2 | O2-798 | O2-798 | Epic | Epic |  | Project Management | In-Progress | 2025-12-01 | 2026-02-27 |  |  | 400 | 400 | Taimur Zahid | 28 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-798 | [5 empty] | 2025-12-29T17:30:58.299+0500 | 2026-02-18T16:37:45.023+0500
O2 | O2-799 | O2-799 | Story | Story |  | EPR: Employee Productivity Report | Resolved! | 2025-12-01 | 2026-01-16 | 2026-01-06 | 2026-01-15 | 120 | 120 | Taimur Zahid | 304 |  | O2-798 | O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-798 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | [5 empty] | 2025-12-29T17:31:09.730+0500 | 2026-02-23T10:12:45.704+0500
O2 | O2-8 | O2-8 | Story | Story |  | Production Release | Resolved! | 2025-11-21 | 2025-11-21 |  |  | 32 | 32 | Faiza Nasir | 25 |  | O2-2 | O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-2 | https://octopusdtlsupport.atlassian.net/browse/O2-8 | [5 empty] | 2025-10-02T13:56:54.864+0500 | 2025-12-01T15:41:09.101+0500
O2 | O2-802 | O2-802 | Task | Task |  | ReadAPI payloads handle milliseconds | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 12 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-802 | [5 empty] | 2025-12-30T10:17:00.342+0500 | 2026-02-11T09:39:07.072+0500
O2 | O2-804 | O2-804 | Story | Story |  | Read API Advancements for OC | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 56 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-804 | [5 empty] | 2025-12-30T10:24:54.579+0500 | 2026-02-20T15:27:02.856+0500
O2 | O2-805 | O2-805 | Story | Story |  | Alarms Configuration Retrieval | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 72 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-805 | [5 empty] | 2025-12-30T10:41:03.674+0500 | 2026-01-22T12:24:06.286+0500
O2 | O2-806 | O2-806 | Story | Story |  | Anomaly Data Configuration | Resolved! |  |  |  |  | 0 | 0 | Aiza Hamid | 4 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-806 | [5 empty] | 2025-12-30T10:47:44.911+0500 | 2026-01-22T12:24:17.603+0500
O2 | O2-809 | O2-809 | Epic | Epic |  | Support for Job Priority in batch/bpm (high/Meduim/low) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-809 | [5 empty] | 2025-12-30T16:15:56.375+0500 | 2026-01-27T16:29:15.545+0500
O2 | O2-810 | O2-810 | Epic | Epic |  | Batch/Bpm modify Existing ADX IT Table | Resolved! | 2025-12-30 | 2026-02-06 |  |  | 480 | 480 | ahad omer | 16 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-810 | [5 empty] | 2025-12-30T16:16:08.300+0500 | 2026-02-25T14:47:45.349+0500
O2 | O2-811 | O2-811 | Epic | Epic |  | Enterprise Connectors External Api Trigger Support (SAP,Azure Sql, ODBC) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-811 | [5 empty] | 2025-12-30T16:16:16.748+0500 | 2026-01-27T16:29:32.922+0500
O2 | O2-812 | O2-812 | Epic | Epic |  | Enterprise connector (MySQL) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-812 | [5 empty] | 2025-12-30T16:16:28.715+0500 | 2026-01-27T16:29:47.471+0500
O2 | O2-813 | O2-813 | Sub-task | Sub-task |  | OCM Development FrontEnd | On Hold |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 80 |  | O2-794 | O2-794 | https://octopusdtlsupport.atlassian.net/browse/O2-794 | https://octopusdtlsupport.atlassian.net/browse/O2-813 | [5 empty] | 2025-12-30T16:16:36.375+0500 | 2026-02-10T11:46:35.497+0500
O2 | O2-814 | O2-814 | Epic | Epic |  | Enterprise connector (Oracle) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-814 | [5 empty] | 2025-12-30T16:16:37.738+0500 | 2026-01-27T16:29:43.357+0500
O2 | O2-815 | O2-815 | Epic | Epic |  | Enterprise Connector Enhancement (Support for upsert/injestion pointer) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-815 | [5 empty] | 2025-12-30T16:16:46.440+0500 | 2026-01-27T16:30:01.589+0500
O2 | O2-816 | O2-816 | Epic | Epic |  | Enterprise connectors Enhancement (use existing IT Table) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-816 | [5 empty] | 2025-12-30T16:16:54.137+0500 | 2026-01-27T16:30:08.126+0500
O2 | O2-817 | O2-817 | Epic | Epic |  | IT/OT Conversion for Enterprise Connectors | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-817 | [5 empty] | 2025-12-30T16:17:01.837+0500 | 2026-01-27T16:30:12.828+0500
O2 | O2-818 | O2-818 | Epic | Epic |  | Recompute for existing Batch/Bpm Jobs | In-Progress | 2026-02-11 | 2026-03-13 |  |  | 480 | 480 | ahad omer | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-818 | [5 empty] | 2025-12-30T16:17:12.609+0500 | 2026-04-09T10:22:37.912+0500
O2 | O2-819 | O2-819 | Epic | Epic |  | Support for SQL Monaco IDE | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-819 | [5 empty] | 2025-12-30T16:17:24.660+0500 | 2026-01-27T16:30:23.064+0500
O2 | O2-820 | O2-820 | Epic | Epic |  | Support for SQL in Batch/Bpm | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-820 | [5 empty] | 2025-12-30T16:17:30.514+0500 | 2026-01-27T10:55:30.938+0500
O2 | O2-821 | O2-821 | Epic | Epic |  | Direct Value Comparison | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-821 | [5 empty] | 2025-12-30T16:17:35.684+0500 | 2026-01-27T15:15:27.825+0500
O2 | O2-822 | O2-822 | Epic | Epic |  | User Activity Logs + Dashboards | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-822 | [5 empty] | 2025-12-30T16:17:41.313+0500 | 2026-01-27T16:25:12.944+0500
O2 | O2-825 | O2-825 | Epic | Epic |  | CSV Bulk Import V2 | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-825 | [5 empty] | 2025-12-30T16:20:03.873+0500 | 2026-01-27T15:16:56.339+0500
O2 | O2-826 | O2-826 | Epic | Epic |  | Data Anomaly V2 | To Do |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-826 | [5 empty] | 2025-12-30T16:20:21.414+0500 | 2026-01-28T11:25:10.077+0500
O2 | O2-827 | O2-827 | Epic | Epic |  | Data Anomaly V3 | To Do |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-827 | [5 empty] | 2025-12-30T16:20:24.439+0500 | 2026-01-28T11:25:39.557+0500
O2 | O2-828 | O2-828 | Task | Task |  | CSV Bulk Import v2 Research | Resolved! |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 32 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-828 | [5 empty] | 2025-12-31T15:11:37.133+0500 | 2026-02-13T14:50:59.048+0500
O2 | O2-834 | O2-834 | Sub-task | Sub-task |  | Unit Testing for APx Performance Modal | Resolved! |  |  | 2026-01-01 | 2026-01-01 | 0 | 0 | Faiza Nasir | 19 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-834 | [5 empty] | 2025-12-31T16:30:30.705+0500 | 2026-01-06T16:21:33.604+0500
O2 | O2-835 | O2-835 | Bug Subtask | Bug Subtask |  | Unable to delete Boolean tag? and clear all is also not working for Boolean tag in export to SQL (schedule) | Resolved | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 4 | 4 | Ali Qumail | 4 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-835 | [5 empty] | 2026-01-01T15:39:10.967+0500 | 2026-03-02T14:11:57.195+0500
O2 | O2-836 | O2-836 | Sub-task | Sub-task |  | Testing by Kamran | Resolved! | 2026-01-02 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 24 | 24 | kamran khalid | 27 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-836 | [5 empty] | 2026-01-02T09:58:30.953+0500 | 2026-02-13T13:33:48.008+0500
O2 | O2-837 | O2-837 | Sub-task | Sub-task |  | Testing by Namra | Resolved! | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8 | 8 | Namra Zahid | 8 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-837 | [5 empty] | 2026-01-02T09:58:42.893+0500 | 2026-02-13T13:13:51.133+0500
O2 | O2-838 | O2-838 | Sub-task | Sub-task |  | Testing by Waqar | Resolved! | 2026-01-02 | 2026-01-05 | 2026-01-02 | 2026-01-06 | 16 | 16 | Waqar Rasheed | 16 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-838 | [5 empty] | 2026-01-02T09:58:52.364+0500 | 2026-02-13T13:25:23.930+0500
O2 | O2-839 | O2-839 | Sub-task | Sub-task |  | Testing by Zeeshan | Resolved! | 2026-01-02 | 2026-01-06 | 2026-01-02 | 2026-01-06 | 24 | 24 | Zeeshan Sarwar | 24 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-839 | [5 empty] | 2026-01-02T09:58:59.957+0500 | 2026-03-10T10:33:51.113+0500
O2 | O2-840 | O2-840 | Bug Subtask | Bug Subtask |  | User is not able to update the site. | Request received |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-707 | O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-707 | https://octopusdtlsupport.atlassian.net/browse/O2-840 | [5 empty] | 2026-01-02T10:30:48.180+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-841 | O2-841 | Bug Subtask | Bug Subtask |  | Export To Excel is Fail to download the data | Resolved |  |  | 2026-01-02 | 2026-01-26 | 0 | 0 | Ali Qumail | 12 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-841 | [5 empty] | 2026-01-02T13:05:04.378+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-842 | O2-842 | Bug Subtask | Bug Subtask |  | Spaces in string conditional cal tag are removing itself after configuring respective tag. | Resolved |  |  | 2026-01-23 | 2026-01-23 | 0 | 0 | Muhammad Ahmad Saleem | 8 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-842 | [5 empty] | 2026-01-02T14:30:34.402+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-843 | O2-843 | Bug Subtask | Bug Subtask |  | Unit is again displaying mandatory while creating calculated tag where as it is fixed on staging. | Resolved |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-843 | [5 empty] | 2026-01-02T14:46:50.615+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-844 | O2-844 | Bug Subtask | Bug Subtask |  | Spaces are not accepted in String type Timer tag condition | Request received |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-844 | [5 empty] | 2026-01-02T15:12:00.843+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-845 | O2-845 | Bug Subtask | Bug Subtask |  | DOWNLOAD csv function is not working incase of "Reusable function" used in query in batch | Request received |  |  |  |  | 0 | 0 | ahad omer | 0 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-845 | [5 empty] | 2026-01-02T16:12:52.772+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-846 | O2-846 | Bug Subtask | Bug Subtask |  | No data is getting exported to sql Schedule for IT Data | Request received |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-846 | [5 empty] | 2026-01-02T16:36:23.141+0500 | 2026-02-11T12:00:49.208+0500
O2 | O2-847 | O2-847 | Sub-task | Sub-task |  | Production Green Deployment | Resolved! |  |  | 2026-01-02 | 2026-01-02 | 0 | 0 | Faiza Nasir | 8 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-847 | [5 empty] | 2026-01-02T16:41:28.837+0500 | 2026-01-06T16:20:34.997+0500
O2 | O2-848 | O2-848 | Task | Task |  | Anomaly Detection Improvements | Resolved! | 2026-01-01 | 2026-01-06 | 2026-01-01 | 2026-01-22 | 0 | 0 | Ali Qumail | 152 |  | O2-37 | O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-37 | https://octopusdtlsupport.atlassian.net/browse/O2-848 | [5 empty] | 2026-01-02T17:24:21.066+0500 | 2026-03-04T10:39:36.743+0500
O2 | O2-849 | O2-849 | Bug Subtask | Bug Subtask |  | Anomaly Results are not getting displayed | Resolved |  |  | 2026-01-02 | 2026-01-05 | 0 | 0 | Muhammad Zeeshan Aslam | 1.5 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-849 | [5 empty] | 2026-01-05T12:29:24.312+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-850 | O2-850 | Task | Task |  | Export To SQL Support Tickets | Resolved! | 2026-01-05 |  | 2026-01-05 | 2026-01-06 | 88 | 88 | Ali Qumail | 88 |  | O2-199 | O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-199 | https://octopusdtlsupport.atlassian.net/browse/O2-850 | [5 empty] | 2026-01-05T17:05:31.244+0500 | 2026-03-02T14:12:02.783+0500
O2 | O2-851 | O2-851 | Bug Subtask | Bug Subtask |  | Pipelines are getting created and data is also available but no tables are getting created in SQL DB and its showing error for Stats Alarms and Hours Data | Bug Fixed |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 0 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-851 | [5 empty] | 2026-01-06T13:01:10.132+0500 | 2026-03-16T12:34:30.910+0500
O2 | O2-852 | O2-852 | Sub-task | Sub-task |  | Production Blue Deployment | Resolved! |  |  | 2026-01-05 | 2026-01-05 | 0 | 0 | Faiza Nasir | 8 |  | O2-717 | O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-717 | https://octopusdtlsupport.atlassian.net/browse/O2-852 | [5 empty] | 2026-01-06T16:20:23.548+0500 | 2026-02-03T14:42:55.314+0500
O2 | O2-853 | O2-853 | Bug Subtask | Bug Subtask |  | Character Limit Missing on Property Name and Property value Field | Resolved |  |  | 2026-01-08 | 2026-01-30 | 0 | 0 | Ali Qumail | 28 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-853 | [5 empty] | 2026-01-08T15:08:53.155+0500 | 2026-02-12T10:06:57.673+0500
O2 | O2-854 | O2-854 | Bug Subtask | Bug Subtask |  | No Validation Message Shown When Adding Duplicate Property | Resolved |  |  | 2026-01-08 | 2026-01-08 | 0 | 0 | Ali Qumail | 4 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-854 | [5 empty] | 2026-01-08T15:19:29.280+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-855 | O2-855 | Bug Subtask | Bug Subtask |  | Asset type and subtype for which template is created, not displaying while creating an APX asset using that asset type and subtype. | Resolved |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-855 | [5 empty] | 2026-01-08T15:34:32.214+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-856 | O2-856 | Story | Story |  | User Manual | Resolved! | 2026-01-07 | 2026-01-09 | 2026-01-07 | 2026-01-08 | 16 | 16 | Hassan Malik | 16 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-856 | [5 empty] | 2026-01-08T16:22:31.114+0500 | 2026-03-02T13:51:22.998+0500
O2 | O2-858 | O2-858 | Sub-task | Sub-task |  | Added Correlation Matrix on Data Selection + Testing | Resolved! | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-848 | O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-858 | [5 empty] | 2026-01-09T10:12:36.245+0500 | 2026-02-13T13:13:43.864+0500
O2 | O2-859 | O2-859 | Sub-task | Sub-task |  | Tested whole Flow, Deployed on Staging and Resolved Bugs | Resolved! | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-848 | O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-848 | https://octopusdtlsupport.atlassian.net/browse/O2-859 | [5 empty] | 2026-01-09T10:15:56.032+0500 | 2026-02-13T13:13:31.944+0500
O2 | O2-861 | O2-861 | Epic | Epic |  | Trending in OmniAgent | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-861 | [5 empty] | 2026-01-09T10:24:55.342+0500 | 2026-01-28T11:26:25.610+0500
O2 | O2-862 | O2-862 | Story | Story |  | Development | Resolved! | 2026-01-07 | 2026-01-08 |  |  | 16 | 16 | Muhammad Ahmad Saleem | 16 |  | O2-861 | O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-862 | [5 empty] | 2026-01-09T10:25:10.867+0500 | 2026-02-13T13:19:09.597+0500
O2 | O2-863 | O2-863 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-861 | O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-863 | [5 empty] | 2026-01-09T10:25:14.196+0500 | 2026-01-09T10:25:14.320+0500
O2 | O2-864 | O2-864 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-861 | O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-864 | [5 empty] | 2026-01-09T10:25:18.282+0500 | 2026-01-09T10:25:18.467+0500
O2 | O2-865 | O2-865 | Story | Story |  | Production Release | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-861 | O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-861 | https://octopusdtlsupport.atlassian.net/browse/O2-865 | [5 empty] | 2026-01-09T10:25:23.880+0500 | 2026-01-09T10:25:23.994+0500
O2 | O2-866 | O2-866 | Sub-task | Sub-task |  | Research work on visualization | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-862 | O2-862 | https://octopusdtlsupport.atlassian.net/browse/O2-862 | https://octopusdtlsupport.atlassian.net/browse/O2-866 | [5 empty] | 2026-01-09T10:26:04.010+0500 | 2026-02-13T13:14:13.089+0500
O2 | O2-870 | O2-870 | Story | Story |  | test | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-870 | [5 empty] | 2026-01-09T15:24:03.330+0500 | 2026-01-09T15:24:03.485+0500
O2 | O2-874 | O2-874 | Bug Subtask | Bug Subtask |  | Input mapping rows added in template are not displaying in configuration of APX asset. | Resolved |  |  | 2026-01-13 | 2026-01-13 | 0 | 0 | Faiza Nasir | 5 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-874 | [5 empty] | 2026-01-12T11:58:52.948+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-875 | O2-875 | Bug Subtask | Bug Subtask |  | Character limit is not implemented same as applied in old APX asset configurations. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 0 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-875 | [5 empty] | 2026-01-12T12:37:45.754+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-876 | O2-876 | Bug Subtask | Bug Subtask |  | Row details are randomly swapping between its own fields in design data, input variable mapping and output variable mapping tabs while creating headers and rows. | Resolved |  |  | 2026-01-26 | 2026-01-26 | 0 | 0 | Ali Qumail | 1 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-876 | [5 empty] | 2026-01-13T10:39:18.841+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-877 | O2-877 | Bug Subtask | Bug Subtask |  | Deactivation or clear configuration against APX asset is not working. | Resolved |  |  | 2026-01-14 | 2026-01-14 | 0 | 0 | Faiza Nasir | 5 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-877 | [5 empty] | 2026-01-13T12:01:36.564+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-878 | O2-878 | Bug Subtask | Bug Subtask |  | Added Steps Disappear After Saving in Template Configuration Tab | Resolved | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 3 | 3 | Faiza Nasir | 3 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-878 | [5 empty] | 2026-01-13T14:31:51.871+0500 | 2026-02-20T13:34:12.733+0500
O2 | O2-879 | O2-879 | Sub-task | Sub-task |  | Add Apx Additional properties in VM API Calls | Resolved! |  |  | 2026-01-12 | 2026-01-14 | 0 | 0 | Faiza Nasir | 9 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-879 | [5 empty] | 2026-01-13T16:37:37.674+0500 | 2026-01-16T20:09:34.235+0500
O2 | O2-880 | O2-880 | Sub-task | Sub-task |  | Bug Fixing | Resolved! |  |  | 2026-01-07 | 2026-01-15 | 0 | 0 | Faiza Nasir | 12 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-880 | [5 empty] | 2026-01-13T16:38:18.712+0500 | 2026-01-16T21:07:33.533+0500
O2 | O2-881 | O2-881 | Bug Subtask | Bug Subtask |  | Property names and options should be restricted in import site layout while creating APX asset using template also the property for which complete template is not defined they should be restricted as well from front end. | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-881 | [5 empty] | 2026-01-14T11:12:21.761+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-882 | O2-882 | Bug Subtask | Bug Subtask |  | The UI becomes misaligned on the Template Configuration tab when a dropdown field is selected. Upon selection, the dropdown field located beneath the selected dropdown unexpectedly shifts its position, causing layout disturbance. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 0 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-882 | [5 empty] | 2026-01-14T14:34:10.876+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-883 | O2-883 | Bug Subtask | Bug Subtask |  | APX asset name is getting changed. | Resolved |  |  |  |  | 0 | 0 | Ali Qumail | 0 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-883 | [5 empty] | 2026-01-14T15:24:18.055+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-884 | O2-884 | Sub-task | Sub-task |  | Research on Code Integration of Backend and FrontEnd | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | O2-862 | O2-862 | https://octopusdtlsupport.atlassian.net/browse/O2-862 | https://octopusdtlsupport.atlassian.net/browse/O2-884 | [5 empty] | 2026-01-15T10:15:28.827+0500 | 2026-02-13T13:14:45.474+0500
O2 | O2-886 | O2-886 | Task | Task |  | Read API Anomaly Data Configuration SQA | Resolved! | 2026-01-14 | 2026-01-16 | 2026-01-14 | 2026-01-15 | 24 | 24 | Muhammad Abbas | 16 |  | O2-130 | O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-130 | https://octopusdtlsupport.atlassian.net/browse/O2-886 | [5 empty] | 2026-01-15T10:24:47.658+0500 | 2026-01-27T16:48:35.564+0500
O2 | O2-887 | O2-887 | Epic | Epic |  | APX Pump – Variable Speed Dashboard | Resolved! | 2025-12-23 | 2026-02-06 |  |  | 240 | 240 | Zain Munir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-887 | [5 empty] | 2026-01-15T10:34:15.818+0500 | 2026-02-26T09:45:46.439+0500
O2 | O2-892 | O2-892 | Epic | Epic |  | OC Intuitive UI/UX | To Do | 2026-01-15 | 2026-03-31 |  |  | 368 | 368 | Hassan Wali | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-892 | [5 empty] | 2026-01-15T11:10:33.871+0500 | 2026-02-23T15:18:20.636+0500
O2 | O2-893 | O2-893 | Story | Story |  | Information Architecure | To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | O2-892 | O2-892 | https://octopusdtlsupport.atlassian.net/browse/O2-892 | https://octopusdtlsupport.atlassian.net/browse/O2-893 | [5 empty] | 2026-01-15T11:11:13.891+0500 | 2026-01-15T11:11:52.931+0500
O2 | O2-894 | O2-894 | Story | Story |  | Revamping UI/UX | To Do |  |  |  |  | 336 | 336 | Hassan Wali | 563.5 |  | O2-892 | O2-892 | https://octopusdtlsupport.atlassian.net/browse/O2-892 | https://octopusdtlsupport.atlassian.net/browse/O2-894 | [5 empty] | 2026-01-15T11:11:39.332+0500 | 2026-02-23T15:19:35.716+0500
O2 | O2-895 | O2-895 | Bug Subtask | Bug Subtask |  | Export Site Layout file is not downloading. | Resolved | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 4 | 4 | Muhammad Usman Javed | 1 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-895 | [5 empty] | 2026-01-15T11:16:08.576+0500 | 2026-02-23T12:44:15.255+0500
O2 | O2-896 | O2-896 | Task | Task |  | OC-Sanity Green env 1/16/26 | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 40 |  | O2-714 | O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | [5 empty] | 2026-01-16T10:30:44.789+0500 | 2026-01-27T16:43:52.625+0500
O2 | O2-897 | O2-897 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | kamran khalid | 8 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-897 | [5 empty] | 2026-01-16T10:55:37.251+0500 | 2026-01-16T16:55:38.557+0500
O2 | O2-898 | O2-898 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Namra Zahid | 8 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-898 | [5 empty] | 2026-01-16T10:55:49.522+0500 | 2026-02-13T13:14:26.547+0500
O2 | O2-899 | O2-899 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Muhammad Abbas | 8 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-899 | [5 empty] | 2026-01-16T10:55:58.763+0500 | 2026-03-10T10:28:55.543+0500
O2 | O2-9 | O2-9 | Epic | Epic |  | Batch/BPM V3 (Box re-usable, Mix and Match) | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 25.5 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-9 | [5 empty] | 2025-10-02T14:00:32.522+0500 | 2026-02-11T10:58:55.955+0500
O2 | O2-900 | O2-900 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Zeeshan Sarwar | 8 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-900 | [5 empty] | 2026-01-16T10:56:09.871+0500 | 2026-02-13T13:21:24.129+0500
O2 | O2-901 | O2-901 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Waqar Rasheed | 8 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-901 | [5 empty] | 2026-01-16T10:56:19.271+0500 | 2026-02-13T13:25:46.937+0500
O2 | O2-902 | O2-902 | Bug Subtask | Bug Subtask |  | Correlation Matrix is getting vanished right after clicking on "Apply" button. | On Hold |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 0 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-902 | [5 empty] | 2026-01-16T12:52:35.805+0500 | 2026-02-09T14:06:44.004+0500
O2 | O2-904 | O2-904 | Bug Subtask | Bug Subtask |  | Forgot Password Email Not Received | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-904 | [5 empty] | 2026-01-16T15:23:33.502+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-905 | O2-905 | Sub-task | Sub-task |  | APX Engine - Steam table integration in APX Performance via Ebsilon engine | Resolved! | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8 | 8 | Arsalan Zafar Khan | 8 |  | O2-40 | O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-40 | https://octopusdtlsupport.atlassian.net/browse/O2-905 | [5 empty] | 2026-01-16T15:28:24.334+0500 | 2026-02-10T11:30:59.246+0500
O2 | O2-906 | O2-906 | Bug Subtask | Bug Subtask |  | Emails Not Received for User Activation, OTP, and Forgot Password | Resolved |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 0 |  | O2-896 | O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-896 | https://octopusdtlsupport.atlassian.net/browse/O2-906 | [5 empty] | 2026-01-16T15:35:15.050+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-907 | O2-907 | Sub-task | Sub-task |  | Research and Poc | To Do |  |  | 2026-01-01 | 2026-01-02 | 0 | 0 | Syed Yousaf Qadri | 48 |  | O2-719 | O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-719 | https://octopusdtlsupport.atlassian.net/browse/O2-907 | [5 empty] | 2026-01-16T16:10:45.343+0500 | 2026-02-19T14:07:01.155+0500
O2 | O2-911 | O2-911 | Story | Story |  | DEV | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-911 | [5 empty] | 2026-01-16T16:26:50.908+0500 | 2026-01-16T16:26:51.047+0500
O2 | O2-918 | O2-918 | Sub-task | Sub-task |  | Coordination with Process Team over APx Template | Resolved! |  |  | 2026-01-08 | 2026-01-08 | 0 | 0 | Faiza Nasir | 5 |  | O2-41 | O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-41 | https://octopusdtlsupport.atlassian.net/browse/O2-918 | [5 empty] | 2026-01-16T20:11:01.359+0500 | 2026-01-16T21:07:19.659+0500
O2 | O2-919 | O2-919 | Task | Task |  | OC-Sanity Blue env 1/19/26 | Resolved! |  |  | 2026-01-20 | 2026-01-20 | 0 | 0 | Muhammad Abbas | 74 |  | O2-714 | O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-714 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | [5 empty] | 2026-01-19T10:59:30.123+0500 | 2026-01-27T16:45:08.609+0500
O2 | O2-920 | O2-920 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 8 | 8 | kamran khalid | 17 |  | O2-919 | O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-920 | [5 empty] | 2026-01-19T11:00:39.720+0500 | 2026-02-13T13:34:38.858+0500
O2 | O2-921 | O2-921 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 8 | 8 | Muhammad Abbas | 16 |  | O2-919 | O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-921 | [5 empty] | 2026-01-19T11:00:47.380+0500 | 2026-02-13T13:06:08.454+0500
O2 | O2-922 | O2-922 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | 16 | 16 | Waqar Rasheed | 16 |  | O2-919 | O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-922 | [5 empty] | 2026-01-19T11:00:54.022+0500 | 2026-02-13T13:26:22.254+0500
O2 | O2-923 | O2-923 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 8 | 8 | Zeeshan Sarwar | 16 |  | O2-919 | O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-923 | [5 empty] | 2026-01-19T11:01:05.855+0500 | 2026-03-10T10:33:27.828+0500
O2 | O2-924 | O2-924 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-01-19 | 2026-01-19 |  |  | 8 | 8 | Namra Zahid | 0 |  | O2-919 | O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-924 | [5 empty] | 2026-01-19T14:12:30.155+0500 | 2026-02-13T13:15:15.789+0500
O2 | O2-925 | O2-925 | Sub-task | Sub-task |  | EPR - January 19, 2026 | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-21 | 2026-01-21 | 8 | 8 | Taimur Zahid | 4 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-925 | [5 empty] | 2026-01-19T15:46:51.659+0500 | 2026-01-26T10:53:39.077+0500
O2 | O2-926 | O2-926 | Sub-task | Sub-task |  | EPR - January 20, 2026 | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-22 | 2026-01-22 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-926 | [5 empty] | 2026-01-19T15:46:59.688+0500 | 2026-01-26T10:50:06.962+0500
O2 | O2-927 | O2-927 | Sub-task | Sub-task |  | EPR - January 21, 2026 | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-28 | 2026-01-28 | 8 | 8 | Taimur Zahid | 4 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-927 | [5 empty] | 2026-01-19T15:47:08.058+0500 | 2026-01-28T12:28:38.291+0500
O2 | O2-928 | O2-928 | Sub-task | Sub-task |  | EPR - January 1, 2026 | Resolved! | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-928 | [5 empty] | 2026-01-19T15:48:29.217+0500 | 2026-02-13T17:10:38.424+0500
O2 | O2-929 | O2-929 | Sub-task | Sub-task |  | EPR - January 2, 2026 | Resolved! | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-929 | [5 empty] | 2026-01-19T15:48:37.848+0500 | 2026-02-13T17:11:46.750+0500
O2 | O2-930 | O2-930 | Sub-task | Sub-task |  | EPR - January 5, 2026 | Resolved! | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-930 | [5 empty] | 2026-01-19T15:49:15.992+0500 | 2026-02-13T17:17:39.573+0500
O2 | O2-931 | O2-931 | Sub-task | Sub-task |  | EPR - January 6, 2026 | Resolved! | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-931 | [5 empty] | 2026-01-19T15:49:21.889+0500 | 2026-02-13T17:18:50.125+0500
O2 | O2-932 | O2-932 | Sub-task | Sub-task |  | EPR - January 7, 2026 | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-932 | [5 empty] | 2026-01-19T15:49:24.934+0500 | 2026-02-13T17:19:40.536+0500
O2 | O2-933 | O2-933 | Sub-task | Sub-task |  | EPR - January 8, 2026 | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-933 | [5 empty] | 2026-01-19T15:49:30.977+0500 | 2026-02-13T17:20:38.507+0500
O2 | O2-934 | O2-934 | Sub-task | Sub-task |  | EPR - January 9, 2026 | Resolved! | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-934 | [5 empty] | 2026-01-19T15:49:37.792+0500 | 2026-02-13T17:31:34.372+0500
O2 | O2-935 | O2-935 | Sub-task | Sub-task |  | EPR - January 12, 2026 | Resolved! | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-935 | [5 empty] | 2026-01-19T15:49:57.682+0500 | 2026-02-13T17:22:56.678+0500
O2 | O2-936 | O2-936 | Sub-task | Sub-task |  | EPR - January 13, 2026 | Resolved! | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-936 | [5 empty] | 2026-01-19T15:50:03.203+0500 | 2026-02-13T17:24:27.240+0500
O2 | O2-937 | O2-937 | Sub-task | Sub-task |  | EPR - January 14, 2026 | Resolved! | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-937 | [5 empty] | 2026-01-19T15:50:09.713+0500 | 2026-02-13T17:25:29.948+0500
O2 | O2-938 | O2-938 | Sub-task | Sub-task |  | EPR - January 15, 2026 | Resolved! | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-938 | [5 empty] | 2026-01-19T15:50:14.744+0500 | 2026-02-13T17:26:44.449+0500
O2 | O2-939 | O2-939 | Sub-task | Sub-task |  | EPR - January 16, 2026 | Resolved! | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Taimur Zahid | 8 |  | O2-799 | O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-799 | https://octopusdtlsupport.atlassian.net/browse/O2-939 | [5 empty] | 2026-01-19T15:50:20.305+0500 | 2026-02-13T17:27:49.588+0500
O2 | O2-94 | O2-94 | Epic | Epic |  | Scheduled Pulls from Data Source (REST API) | Resolved! |  |  |  |  | 0 | 0 | Hamza Ali | 24 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-94 | [5 empty] | 2025-10-03T19:54:07.115+0500 | 2026-02-18T16:18:59.331+0500
O2 | O2-940 | O2-940 | Bug Subtask | Bug Subtask |  | Anomaly Results are not getting displayed, Kindly Look into it. | Resolved |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-919 | O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-940 | [5 empty] | 2026-01-20T12:16:52.575+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-941 | O2-941 | Epic | Epic |  | Ashghal Release | Resolved! | 2026-01-19 | 2026-01-27 | 2026-02-02 | 2026-02-11 | 368 | 368 | Unassigned | 482 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-941 | [5 empty] | 2026-01-20T13:58:45.330+0500 | 2026-02-11T16:51:42.500+0500
O2 | O2-942 | O2-942 | Story | Story |  | Key Vault Setup and Integration | Resolved! | 2026-01-15 | 2026-01-16 |  |  | 88 | 88 | Taimur Zahid | 72 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | [5 empty] | 2026-01-20T14:55:24.840+0500 | 2026-01-23T15:11:09.599+0500
O2 | O2-943 | O2-943 | Task | Task |  | ADX Schema Changes and Verification | Resolved! |  |  | 2026-01-21 | 2026-01-28 | 0 | 0 | Mohsin Junaid | 24 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-943 | [5 empty] | 2026-01-20T14:56:20.906+0500 | 2026-02-11T09:39:07.411+0500
O2 | O2-944 | O2-944 | Task | Task |  | OmniConnect DE Logs SQL Database Schema Changes and Verification | Resolved! |  |  | 2026-01-20 | 2026-01-23 | 8 | 8 | Ibrahim Ahmed Qureshi | 32 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-944 | [5 empty] | 2026-01-20T14:57:01.364+0500 | 2026-02-11T09:39:07.072+0500
O2 | O2-945 | O2-945 | Task | Task |  | BPM Batch Compute Deployments | Resolved! |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 8 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-945 | [5 empty] | 2026-01-20T15:03:29.650+0500 | 2026-02-11T09:39:07.411+0500
O2 | O2-946 | O2-946 | Task | Task |  | Log analytics | Resolved! |  |  | 2026-01-20 | 2026-01-26 | 0 | 0 | Mohsin Junaid | 16 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-946 | [5 empty] | 2026-01-20T15:03:46.350+0500 | 2026-01-28T11:11:04.981+0500
O2 | O2-947 | O2-947 | Task | Task |  | OC Faster Deployments | Resolved! |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-947 | [5 empty] | 2026-01-20T15:04:04.146+0500 | 2026-02-11T09:39:07.411+0500
O2 | O2-948 | O2-948 | Task | Task |  | Diagnostics Deployments | Resolved! |  |  | 2026-01-19 | 2026-01-27 | 0 | 0 | Mohsin Junaid | 16 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-948 | [5 empty] | 2026-01-20T15:04:18.007+0500 | 2026-01-28T11:11:25.645+0500
O2 | O2-949 | O2-949 | Task | Task |  | Stats Alarms Deployments | Resolved! |  |  | 2026-01-22 | 2026-01-22 | 0 | 0 | Hamza Ali | 4 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-949 | [5 empty] | 2026-01-20T15:04:28.097+0500 | 2026-02-11T09:39:07.411+0500
O2 | O2-95 | O2-95 | Epic | Epic |  | Scheduled Pulls from Data Source (SFTP) | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 57 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-95 | [5 empty] | 2025-10-03T19:54:21.834+0500 | 2026-02-11T10:55:09.352+0500
O2 | O2-950 | O2-950 | Task | Task |  | Scheduled Pulls and Exports Deployments | Resolved! |  |  | 2026-01-20 | 2026-01-27 | 0 | 0 | Hamza Ali | 24 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-950 | [5 empty] | 2026-01-20T15:04:56.286+0500 | 2026-02-11T09:39:07.411+0500
O2 | O2-951 | O2-951 | Task | Task |  | Read API Deployments | Resolved! | 2026-01-21 | 2026-01-22 |  |  | 16 | 16 | Aiza Hamid | 16 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-951 | [5 empty] | 2026-01-20T15:05:08.220+0500 | 2026-02-11T09:39:07.411+0500
O2 | O2-952 | O2-952 | Task | Task |  | Anamoly Detection Deployments | Resolved! |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 0 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-952 | [5 empty] | 2026-01-20T15:05:27.161+0500 | 2026-02-11T09:39:07.411+0500
O2 | O2-953 | O2-953 | Sub-task | Sub-task |  | Key Vault Configuration and Secrets Creation | Resolved! | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Taimur Zahid | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-953 | [5 empty] | 2026-01-20T15:12:33.468+0500 | 2026-01-20T15:13:57.499+0500
O2 | O2-954 | O2-954 | Sub-task | Sub-task |  | Managed Identities RBAC to Key Vault | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Taimur Zahid | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-954 | [5 empty] | 2026-01-20T15:12:52.681+0500 | 2026-01-20T15:15:19.993+0500
O2 | O2-955 | O2-955 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Aiza Hamid | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-955 | [5 empty] | 2026-01-20T15:15:49.139+0500 | 2026-01-22T10:43:57.167+0500
O2 | O2-956 | O2-956 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | To Do |  |  | 2026-01-23 | 2026-01-23 | 0 | 0 | Hamza Ali | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-956 | [5 empty] | 2026-01-20T15:16:11.596+0500 | 2026-01-28T11:39:38.871+0500
O2 | O2-957 | O2-957 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-957 | [5 empty] | 2026-01-20T15:16:24.685+0500 | 2026-03-04T10:58:07.995+0500
O2 | O2-958 | O2-958 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | Resolved! |  |  | 2026-01-23 | 2026-01-23 | 0 | 0 | Mohsin Junaid | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-958 | [5 empty] | 2026-01-20T15:16:28.833+0500 | 2026-02-11T09:39:06.257+0500
O2 | O2-959 | O2-959 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | Resolved! |  |  | 2026-01-19 | 2026-01-19 | 0 | 0 | Ibrahim Ahmed Qureshi | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-959 | [5 empty] | 2026-01-20T15:16:33.407+0500 | 2026-02-26T10:26:25.543+0500
O2 | O2-960 | O2-960 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | To Do |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 0 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-960 | [5 empty] | 2026-01-20T15:16:37.992+0500 | 2026-01-20T15:17:14.479+0500
O2 | O2-961 | O2-961 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 8 | 8 | Hassan Saeed Wattoo | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-961 | [5 empty] | 2026-01-20T15:16:42.708+0500 | 2026-02-13T12:48:30.988+0500
O2 | O2-962 | O2-962 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | Resolved! | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Muhammad Yousha Agha | 8 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-962 | [5 empty] | 2026-01-20T15:17:24.698+0500 | 2026-01-20T15:45:52.214+0500
O2 | O2-963 | O2-963 | Sub-task | Sub-task |  | Key Vault Secret Retrieval Testing and Changes | Resolved! |  |  |  |  | 0 | 0 | Ayyan Babar | 0 |  | O2-942 | O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-942 | https://octopusdtlsupport.atlassian.net/browse/O2-963 | [5 empty] | 2026-01-20T15:17:52.330+0500 | 2026-03-25T10:59:29.527+0500
O2 | O2-964 | O2-964 | Bug Subtask | Bug Subtask |  | SQL: Displaying Invalid Error for Hours , Not on Staging, Only On Production | Resolved |  |  | 2026-01-01 | 2026-01-01 | 0 | 0 | Ali Qumail | 1 |  | O2-919 | O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-919 | https://octopusdtlsupport.atlassian.net/browse/O2-964 | [5 empty] | 2026-01-20T15:30:42.346+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-965 | O2-965 | Task | Task |  | Key Vaults, Secrets Generation for Web App service | Resolved! |  |  | 2026-01-19 | 2026-01-20 | 0 | 0 | Faiza Nasir | 8 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-965 | [5 empty] | 2026-01-20T16:30:51.436+0500 | 2026-01-26T10:57:01.452+0500
O2 | O2-966 | O2-966 | Task | Task |  | Database Comparer Overview | Resolved! |  |  | 2026-01-20 | 2026-01-20 | 0 | 0 | Faiza Nasir | 4 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-966 | [5 empty] | 2026-01-20T16:55:03.847+0500 | 2026-01-26T10:57:07.061+0500
O2 | O2-967 | O2-967 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8 | 8 | Zeeshan Sarwar | 8 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-967 | [5 empty] | 2026-01-21T10:28:29.929+0500 | 2026-03-10T10:37:16.084+0500
O2 | O2-968 | O2-968 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-01-21 | 2026-01-26 | 2026-01-21 | 2026-02-17 | 40 | 40 | Waqar Rasheed | 38.5 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-968 | [5 empty] | 2026-01-21T10:28:35.959+0500 | 2026-02-17T16:49:48.722+0500
O2 | O2-969 | O2-969 | Story | Story |  | SQA | Resolved! | 2026-01-20 | 2026-01-26 |  |  | 144 | 144 | Muhammad Abbas | 162 |  | O2-810 | O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-810 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | [5 empty] | 2026-01-21T10:33:37.260+0500 | 2026-03-04T16:43:57.205+0500
O2 | O2-970 | O2-970 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-01-21 | 2026-01-23 | 2026-01-21 | 2026-01-30 | 24 | 24 | kamran khalid | 26 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-970 | [5 empty] | 2026-01-21T10:34:11.663+0500 | 2026-02-13T13:35:23.161+0500
O2 | O2-971 | O2-971 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! |  |  | 2026-01-21 | 2026-01-30 | 24 | 24 | Muhammad Abbas | 32 |  | O2-969 | O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-969 | https://octopusdtlsupport.atlassian.net/browse/O2-971 | [5 empty] | 2026-01-21T10:34:42.144+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-972 | O2-972 | Bug Subtask | Bug Subtask |  | Real-Time Tag Latest Values Are Not Displayed | Resolved |  |  |  |  | 8 | 8 | Mohsin Junaid | 0 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-972 | [5 empty] | 2026-01-21T10:42:09.333+0500 | 2026-02-13T16:18:38.768+0500
O2 | O2-973 | O2-973 | Bug Subtask | Bug Subtask |  | Docker containers are not loading. | Resolved |  |  | 2026-01-01 | 2026-01-21 | 80 | 80 | Muhammad Yousha Agha | 96 |  | O2-790 | O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-790 | https://octopusdtlsupport.atlassian.net/browse/O2-973 | [5 empty] | 2026-01-21T12:08:02.881+0500 | 2026-02-11T12:00:36.991+0500
O2 | O2-98 | O2-98 | Story | Story |  | Development | Resolved! | 2025-09-22 | 2025-10-03 |  |  | 960 | 960 | Faiza Nasir | 307 |  | O2-94 | O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-98 | [5 empty] | 2025-10-03T19:54:29.374+0500 | 2025-10-24T16:26:58.100+0500
O2 | O2-980 | O2-980 | Task | Task |  | All Code deployment with Merge Conflict Resolved | Resolved! |  |  | 2026-01-21 | 2026-01-21 | 0 | 0 | Faiza Nasir | 6 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-980 | [5 empty] | 2026-01-21T17:30:48.578+0500 | 2026-01-26T10:57:13.110+0500
O2 | O2-981 | O2-981 | Task | Task |  | Keyvault integration in App service | Resolved! |  |  | 2026-01-21 | 2026-01-21 | 0 | 0 | Faiza Nasir | 4 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-981 | [5 empty] | 2026-01-21T17:31:18.510+0500 | 2026-01-26T10:57:21.855+0500
O2 | O2-982 | O2-982 | Story | Story |  | DE Production Release to Ashghal | Resolved! | 2026-01-15 | 2026-01-15 |  |  | 8 | 8 | Taimur Zahid | 8 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-982 | [5 empty] | 2026-01-22T10:31:10.339+0500 | 2026-02-20T11:06:33.644+0500
O2 | O2-983 | O2-983 | Sub-task | Sub-task |  | Schema Changes in DE Logs Database | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 8 | 8 | Aiza Hamid | 8 |  | O2-951 | O2-951 | https://octopusdtlsupport.atlassian.net/browse/O2-951 | https://octopusdtlsupport.atlassian.net/browse/O2-983 | [5 empty] | 2026-01-22T10:47:06.799+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-984 | O2-984 | Sub-task | Sub-task |  | Code changes for Ashghal | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | Aiza Hamid | 8 |  | O2-951 | O2-951 | https://octopusdtlsupport.atlassian.net/browse/O2-951 | https://octopusdtlsupport.atlassian.net/browse/O2-984 | [5 empty] | 2026-01-22T10:47:10.496+0500 | 2026-02-11T09:39:03.693+0500
O2 | O2-986 | O2-986 | Task | Task |  | OC-VPC-Regression 01/22/2025 | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 258 |  | O2-941 | O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-941 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | [5 empty] | 2026-01-22T11:08:09.034+0500 | 2026-01-27T16:57:09.085+0500
O2 | O2-987 | O2-987 | Sub-task | Sub-task |  | Testing By Kamran | Resolved! | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 32 | 32 | kamran khalid | 33 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-987 | [5 empty] | 2026-01-22T11:09:22.447+0500 | 2026-02-13T13:36:06.728+0500
O2 | O2-988 | O2-988 | Sub-task | Sub-task |  | Testing By M.Abbas | Resolved! | 2026-01-22 | 2026-01-26 | 2026-01-22 | 2026-01-27 | 32 | 32 | Muhammad Abbas | 32 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-988 | [5 empty] | 2026-01-22T11:09:29.631+0500 | 2026-03-10T10:25:02.648+0500
O2 | O2-989 | O2-989 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 32 | 32 | Waqar Rasheed | 32 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-989 | [5 empty] | 2026-01-22T11:09:50.801+0500 | 2026-02-13T13:28:06.890+0500
O2 | O2-99 | O2-99 | Story | Story |  | SQA | Resolved! | 2025-10-06 | 2025-10-14 |  |  | 640 | 640 | Muhammad Abbas | 423.38 |  | O2-94 | O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-94 | https://octopusdtlsupport.atlassian.net/browse/O2-99 | [5 empty] | 2025-10-03T19:54:30.747+0500 | 2025-10-24T16:28:08.495+0500
O2 | O2-990 | O2-990 | Sub-task | Sub-task |  | Testing By Zeeshan | Resolved! | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 32 | 32 | Zeeshan Sarwar | 32 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-990 | [5 empty] | 2026-01-22T11:09:59.487+0500 | 2026-02-13T13:22:41.605+0500
O2 | O2-991 | O2-991 | Sub-task | Sub-task |  | Testing By Namra | Resolved! | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-01-27 | 32 | 32 | Namra Zahid | 32 |  | O2-986 | O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-986 | https://octopusdtlsupport.atlassian.net/browse/O2-991 | [5 empty] | 2026-01-22T11:10:10.228+0500 | 2026-02-13T13:15:54.859+0500
O2 | O2-992 | O2-992 | Epic | Epic |  | Boiler What-If | To Do |  |  |  |  | 0 | 0 | awais akhter | 40 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/O2-992 | [5 empty] | 2026-01-22T11:24:46.716+0500 | 2026-01-26T18:22:09.282+0500
O2 | O2-993 | O2-993 | Story | Story |  | Design What-If Model (P) | Resolved! | 2025-12-23 | 2026-01-02 |  |  | 40 | 40 | Faiq Butt | 40 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-993 | [5 empty] | 2026-01-22T11:25:41.548+0500 | 2026-02-10T11:10:50.918+0500
O2 | O2-994 | O2-994 | Story | Story |  | Development (if required) | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-994 | [5 empty] | 2026-01-22T11:26:10.100+0500 | 2026-01-22T11:26:10.270+0500
O2 | O2-995 | O2-995 | Story | Story |  | Template, wizards and dashboard design (P) | Resolved! |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-995 | [5 empty] | 2026-01-22T11:29:09.396+0500 | 2026-02-10T11:11:03.306+0500
O2 | O2-996 | O2-996 | Story | Story |  | Dashboard development and Asset type addition | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-996 | [5 empty] | 2026-01-22T11:29:17.041+0500 | 2026-01-22T11:29:17.175+0500
O2 | O2-997 | O2-997 | Story | Story |  | OC Process testing (P) | Resolved! |  |  |  |  | 0 | 0 | Faiq Butt | 24 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-997 | [5 empty] | 2026-01-22T11:29:43.912+0500 | 2026-02-18T12:16:24.130+0500
O2 | O2-998 | O2-998 | Story | Story |  | SQA | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-998 | [5 empty] | 2026-01-22T11:29:51.978+0500 | 2026-01-22T11:29:52.127+0500
O2 | O2-999 | O2-999 | Story | Story |  | User Manual | To Do |  |  |  |  | 0 | 0 | awais akhter | 0 |  | O2-992 | O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-992 | https://octopusdtlsupport.atlassian.net/browse/O2-999 | [5 empty] | 2026-01-22T11:29:58.845+0500 | 2026-01-22T11:29:58.968+0500
OAM | OAM-4 | OAM-4 | Task | Task |  | Cost Calculation | In-Process |  |  | 2026-01-12 | 2026-03-06 | 0 | 0 | Usama Tariq | 480 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/OAM-4 | [5 empty] | 2023-10-10T15:23:23.133+0500 | 2026-03-30T14:20:51.346+0500
OAM | OAM-44 | OAM-44 | Story | Story |  | Testing status code with QA | Resolved! |  |  |  |  | 0 | 0 | Usama Tariq | 192 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/OAM-44 | [5 empty] | 2025-03-04T11:56:58.650+0500 | 2026-02-20T16:00:42.987+0500
OAM | OAM-45 | OAM-45 | Sub-task | Sub-task |  | Testing status code with QA | Considered in Roadmap & Queued | 2025-01-02 | 2025-03-31 |  |  | 0 | 0 | awais akhter | 16 |  | OAM-44 | OAM-44 | https://octopusdtlsupport.atlassian.net/browse/OAM-44 | https://octopusdtlsupport.atlassian.net/browse/OAM-45 | [5 empty] | 2025-03-04T11:58:06.023+0500 | 2025-03-04T11:59:24.493+0500
OAM | OAM-46 | OAM-46 | Story | Story |  | Weekly Cost meeting | In-Process |  |  | 2026-01-01 | 2026-03-13 | 0 | 0 | Usama Tariq | 388 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/OAM-46 | [5 empty] | 2025-03-04T12:02:09.900+0500 | 2026-03-30T14:20:13.754+0500
OAM | OAM-50 | OAM-50 | Sub-task | Sub-task |  | Power BI Dashboard | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | awais akhter | 84 |  | OAM-4 | OAM-4 | https://octopusdtlsupport.atlassian.net/browse/OAM-4 | https://octopusdtlsupport.atlassian.net/browse/OAM-50 | [5 empty] | 2025-07-01T11:59:13.585+0500 | 2025-07-01T12:35:46.124+0500
OAM | OAM-51 | OAM-51 | Story | Story |  | Support Tickets (RND) | In-Process |  |  | 2026-01-19 | 2026-03-30 | 0 | 0 | Usama Tariq | 160 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/OAM-51 | [5 empty] | 2025-10-08T10:10:35.863+0500 | 2026-03-30T15:29:16.393+0500
OAM | OAM-52 | OAM-52 | Story | Story |  | Cost File for CFO | Selected for Development |  |  | 2026-02-09 | 2026-03-18 | 0 | 0 | Usama Tariq | 32 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/OAM-52 | [5 empty] | 2026-02-09T10:43:45.146+0500 | 2026-03-30T14:21:58.086+0500
OAM | OAM-53 | OAM-53 | Story | Story |  | Subscription Error's RND | Selected for Development |  |  | 2026-02-11 | 2026-02-26 | 0 | 0 | Usama Tariq | 56 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/OAM-53 | [5 empty] | 2026-02-11T17:21:44.016+0500 | 2026-03-04T11:56:30.026+0500
ODL | ODL-10 | ODL-10 | Sub-task | Sub-task |  | Live Values+Tag Dependencies+Bulk Tag Deletion Handover Session | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1.5 | 1.5 | Zain Munir | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-10 | [5 empty] | 2026-01-30T15:57:24.301+0500 | 2026-02-20T17:03:30.744+0500
ODL | ODL-100 | ODL-100 | Sub-task | Sub-task |  | Unified Jira projects manager | Resolved! | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | 26 | 26 | Hassan Malik | 26 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-100 | [5 empty] | 2026-03-16T15:11:40.940+0500 | 2026-03-17T14:23:29.239+0500
ODL | ODL-101 | ODL-101 | Sub-task | Sub-task |  | Epics Planner for Leadership Budgeting | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1 | 1 | Hassan Malik | 1 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-101 | [5 empty] | 2026-03-16T15:12:39.644+0500 | 2026-03-17T15:20:37.844+0500
ODL | ODL-102 | ODL-102 | Sub-task | Sub-task |  | Employee Performance Dashboard (Simple/Advanced scoring) | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1 | 1 | Hassan Malik | 1 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-102 | [5 empty] | 2026-03-16T15:13:46.105+0500 | 2026-03-17T15:20:30.989+0500
ODL | ODL-103 | ODL-103 | Epic | Epic |  | Support Tickets: Avanceon Retail Team | Backlog / To Do |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/ODL-103 | [5 empty] | 2026-03-17T13:05:02.985+0500 | 2026-03-17T13:05:45.840+0500
ODL | ODL-104 | ODL-104 | Story | Story |  | Support Tickets | In-Process |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 12 |  | ODL-103 | ODL-103 | https://octopusdtlsupport.atlassian.net/browse/ODL-103 | https://octopusdtlsupport.atlassian.net/browse/ODL-104 | [5 empty] | 2026-03-17T13:06:58.526+0500 | 2026-03-17T13:14:49.629+0500
ODL | ODL-105 | ODL-105 | Sub-task | Sub-task |  | Datetime is getting disturbed while creating work orders in M365 from CBRE posted file | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 8 | 8 | Ameer Hamza Khan | 8 |  | ODL-104 | ODL-104 | https://octopusdtlsupport.atlassian.net/browse/ODL-104 | https://octopusdtlsupport.atlassian.net/browse/ODL-105 | [5 empty] | 2026-03-17T13:10:13.270+0500 | 2026-03-17T13:12:45.468+0500
ODL | ODL-106 | ODL-106 | Sub-task | Sub-task |  | Work Order type is not saving as mentioned in CBRE posted sheet | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2 | 2 | Ameer Hamza Khan | 2 |  | ODL-104 | ODL-104 | https://octopusdtlsupport.atlassian.net/browse/ODL-104 | https://octopusdtlsupport.atlassian.net/browse/ODL-106 | [5 empty] | 2026-03-17T13:10:56.653+0500 | 2026-03-17T13:15:10.963+0500
ODL | ODL-107 | ODL-107 | Sub-task | Sub-task |  | Null target start and finish datetime exception handled | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2 | 2 | Ameer Hamza Khan | 2 |  | ODL-104 | ODL-104 | https://octopusdtlsupport.atlassian.net/browse/ODL-104 | https://octopusdtlsupport.atlassian.net/browse/ODL-107 | [5 empty] | 2026-03-17T13:11:25.622+0500 | 2026-03-17T13:15:25.667+0500
ODL | ODL-108 | ODL-108 | Story | Story |  | Handover | Backlog / To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | ODL-80 | ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-108 | [5 empty] | 2026-03-17T15:23:40.986+0500 | 2026-03-17T15:24:23.964+0500
ODL | ODL-109 | ODL-109 | Story | Story |  | Bug Fixing | Backlog / To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | ODL-80 | ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-109 | [5 empty] | 2026-03-17T15:24:49.798+0500 | 2026-03-17T15:24:50.018+0500
ODL | ODL-11 | ODL-11 | Sub-task | Sub-task |  | Data Alarms+Statistical Alarms+ Tag Diagnostics Handover Session | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8 | 8 | Zain Munir | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-11 | [5 empty] | 2026-01-30T15:58:03.770+0500 | 2026-03-02T14:18:04.136+0500
ODL | ODL-110 | ODL-110 | Story | Story |  | TK approved Employee Performance Dashboard & Metrics | Backlog / To Do |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | ODL-80 | ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-110 | [5 empty] | 2026-03-17T15:25:37.046+0500 | 2026-03-17T15:25:37.267+0500
ODL | ODL-111 | ODL-111 | Sub-task | Sub-task |  | 1. Proposal & PO | Resolved! | 2025-09-25 | 2025-10-09 |  |  | 24 | 24 | Mariam Zulfiqar | 24 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-111 | [5 empty] | 2026-03-26T09:38:45.878+0500 | 2026-03-26T09:50:12.325+0500
ODL | ODL-112 | ODL-112 | Sub-task | Sub-task |  | 2. ODL in-house tasks (engineering) | Resolved! | 2025-10-01 |  |  |  | 112 | 112 | Mariam Zulfiqar | 104 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-112 | [5 empty] | 2026-03-26T09:38:58.031+0500 | 2026-03-26T10:09:36.453+0500
ODL | ODL-113 | ODL-113 | Sub-task | Sub-task |  | 3. DEWA approval | Resolved! | 2025-11-03 | 2025-11-07 |  |  | 32 | 32 | Mariam Zulfiqar | 20 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-113 | [5 empty] | 2026-03-26T09:39:12.532+0500 | 2026-03-26T10:11:15.636+0500
ODL | ODL-114 | ODL-114 | Sub-task | Sub-task |  | 4. Hand-over to Avanceon | Resolved! | 2025-11-03 | 2025-11-28 |  |  | 24 | 24 | Mariam Zulfiqar | 24 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-114 | [5 empty] | 2026-03-26T09:39:30.561+0500 | 2026-03-26T10:12:03.790+0500
ODL | ODL-115 | ODL-115 | Sub-task | Sub-task |  | 5. PQ Documentation for DEWA approval | Resolved! | 2025-12-08 |  |  |  | 16 | 16 | Mariam Zulfiqar | 16 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-115 | [5 empty] | 2026-03-26T09:39:37.230+0500 | 2026-03-26T10:12:32.613+0500
ODL | ODL-116 | ODL-116 | Sub-task | Sub-task |  | 7. OCP document scope | Resolved! | 2026-03-04 | 2026-03-27 | 2026-03-09 | 2026-03-25 | 5 | 5 | Mariam Zulfiqar | 5 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-116 | [5 empty] | 2026-03-26T09:39:56.670+0500 | 2026-03-26T10:13:41.545+0500
ODL | ODL-117 | ODL-117 | Sub-task | Sub-task |  | Commissioning support | Backlog / To Do |  |  |  |  | 0 | 0 | Mariam Zulfiqar | 0 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-117 | [5 empty] | 2026-03-26T09:40:03.662+0500 | 2026-03-26T09:43:29.548+0500
ODL | ODL-118 | ODL-118 | Sub-task | Sub-task |  | Sprint Planning Activity March 31, 26. | Resolved! |  |  | 2026-03-31 | 2026-03-31 | 2 | 2 | Arsalan Zafar Khan | 2 |  | ODL-54 | ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-118 | [5 empty] | 2026-04-01T09:37:12.530+0500 | 2026-04-01T09:38:12.240+0500
ODL | ODL-119 | ODL-119 | Epic | Epic |  | Organizational Trainings/Workshops/Drills | Backlog / To Do | 2026-01-01 | 2026-12-31 |  |  | 0 | 0 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/ODL-119 | [5 empty] | 2026-04-02T14:23:13.582+0500 | 2026-04-02T14:23:25.363+0500
ODL | ODL-12 | ODL-12 | Sub-task | Sub-task |  | Real and GPS Handover Session | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2 | 2 | Muhammad Ahmad Saleem | 2 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-12 | [5 empty] | 2026-01-30T17:12:38.192+0500 | 2026-02-23T13:29:28.113+0500
ODL | ODL-120 | ODL-120 | Story | Story |  | Mindset Training | Resolved! | 2026-03-31 | 2026-03-31 |  |  | 0 | 0 | Hassan Malik | 12 |  | ODL-119 | ODL-119 | https://octopusdtlsupport.atlassian.net/browse/ODL-119 | https://octopusdtlsupport.atlassian.net/browse/ODL-120 | [5 empty] | 2026-04-02T14:24:13.721+0500 | 2026-04-02T14:35:30.489+0500
ODL | ODL-121 | ODL-121 | Sub-task | Sub-task |  | Mindset training - AHK | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4 | 4 | Ameer Hamza Khan | 4 |  | ODL-120 | ODL-120 | https://octopusdtlsupport.atlassian.net/browse/ODL-120 | https://octopusdtlsupport.atlassian.net/browse/ODL-121 | [5 empty] | 2026-04-02T15:14:05.002+0500 | 2026-04-02T15:14:55.451+0500
ODL | ODL-122 | ODL-122 | Sub-task | Sub-task |  | Mindset training - MZ | Resolved! | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-02 | 4 | 4 | Mariam Zulfiqar | 4 |  | ODL-120 | ODL-120 | https://octopusdtlsupport.atlassian.net/browse/ODL-120 | https://octopusdtlsupport.atlassian.net/browse/ODL-122 | [5 empty] | 2026-04-02T17:06:20.655+0500 | 2026-04-08T09:51:08.356+0500
ODL | ODL-123 | ODL-123 | Sub-task | Sub-task |  | Mindset Training - Taimur Zahid | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4 | 4 | Taimur Zahid | 4 |  | ODL-120 | ODL-120 | https://octopusdtlsupport.atlassian.net/browse/ODL-120 | https://octopusdtlsupport.atlassian.net/browse/ODL-123 | [5 empty] | 2026-04-03T10:45:51.280+0500 | 2026-04-03T10:46:31.945+0500
ODL | ODL-124 | ODL-124 | Sub-task | Sub-task |  | Jira Time Log Activity 8 April 2026 | Resolved! | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2 | 2 | Arsalan Zafar Khan | 2 |  | ODL-54 | ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-124 | [5 empty] | 2026-04-09T09:11:48.504+0500 | 2026-04-09T09:12:27.613+0500
ODL | ODL-125 | ODL-125 | Task | Task |  | Chillowatt product review and understanding | Resolved! | 2026-04-07 | 2026-04-09 |  |  | 0 | 0 | ahad omer | 16 |  | ODL-64 | ODL-64 | https://octopusdtlsupport.atlassian.net/browse/ODL-64 | https://octopusdtlsupport.atlassian.net/browse/ODL-125 | [5 empty] | 2026-04-20T16:11:06.509+0500 | 2026-04-20T16:26:19.149+0500
ODL | ODL-126 | ODL-126 | Sub-task | Sub-task |  | Chillowatt Process Understanding | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 0 | 0 | ahad omer | 8 |  | ODL-125 | ODL-125 | https://octopusdtlsupport.atlassian.net/browse/ODL-125 | https://octopusdtlsupport.atlassian.net/browse/ODL-126 | [5 empty] | 2026-04-20T16:11:52.704+0500 | 2026-04-20T16:13:54.620+0500
ODL | ODL-127 | ODL-127 | Sub-task | Sub-task |  | Chillowatt Handover Code Understanding | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0 | 0 | ahad omer | 8 |  | ODL-125 | ODL-125 | https://octopusdtlsupport.atlassian.net/browse/ODL-125 | https://octopusdtlsupport.atlassian.net/browse/ODL-127 | [5 empty] | 2026-04-20T16:12:15.770+0500 | 2026-04-20T16:26:49.537+0500
ODL | ODL-128 | ODL-128 | Task | Task |  | OEE URS Understanding and review leading to DDS | Resolved! | 2026-04-02 | 2026-04-03 |  |  | 0 | 0 | ahad omer | 16 |  | ODL-64 | ODL-64 | https://octopusdtlsupport.atlassian.net/browse/ODL-64 | https://octopusdtlsupport.atlassian.net/browse/ODL-128 | [5 empty] | 2026-04-20T16:30:40.907+0500 | 2026-04-20T16:32:54.682+0500
ODL | ODL-129 | ODL-129 | Sub-task | Sub-task |  | URS review OEE | Resolved! | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 0 | 0 | ahad omer | 16 |  | ODL-128 | ODL-128 | https://octopusdtlsupport.atlassian.net/browse/ODL-128 | https://octopusdtlsupport.atlassian.net/browse/ODL-129 | [5 empty] | 2026-04-20T16:31:46.893+0500 | 2026-04-20T16:32:46.846+0500
ODL | ODL-13 | ODL-13 | Sub-task | Sub-task |  | Calculated, Counter and Timer Tags Handover | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-13 | [5 empty] | 2026-01-30T17:25:32.236+0500 | 2026-02-23T13:51:35.351+0500
ODL | ODL-130 | ODL-130 | Story | Story |  | Knowledge Transfer | Resolved! |  |  |  |  | 0 | 0 | Unassigned | 4 |  | ODL-63 | ODL-63 | https://octopusdtlsupport.atlassian.net/browse/ODL-63 | https://octopusdtlsupport.atlassian.net/browse/ODL-130 | [5 empty] | 2026-04-22T16:15:16.699+0500 | 2026-04-22T16:18:43.871+0500
ODL | ODL-131 | ODL-131 | Sub-task | Sub-task |  | KT Session for Fuel-Chat and Omni-Chat | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 4 | 4 | Muhammad Zeeshan Aslam | 4 |  | ODL-130 | ODL-130 | https://octopusdtlsupport.atlassian.net/browse/ODL-130 | https://octopusdtlsupport.atlassian.net/browse/ODL-131 | [5 empty] | 2026-04-22T16:17:22.604+0500 | 2026-04-22T16:18:29.328+0500
ODL | ODL-132 | ODL-132 | Sub-task | Sub-task |  | Support, Bug fixing, meeting with clients/new customer and internal meeting with team | Backlog / To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  | ODL-76 | ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-132 | [5 empty] | 2026-05-05T16:51:26.173+0500 | 2026-05-05T16:51:26.388+0500
ODL | ODL-14 | ODL-14 | Sub-task | Sub-task |  | Anomaly Detection Handover Session | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1.5 | 1.5 | Zain Munir | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-14 | [5 empty] | 2026-02-03T15:56:29.244+0500 | 2026-02-20T17:11:30.529+0500
ODL | ODL-15 | ODL-15 | Sub-task | Sub-task |  | Export Handover Session | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1.5 | 1.5 | Zain Munir | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-15 | [5 empty] | 2026-02-03T15:56:38.897+0500 | 2026-02-20T17:14:16.970+0500
ODL | ODL-16 | ODL-16 | Sub-task | Sub-task |  | Apx Template/Insights/Performance Handover Session | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3 | 3 | Zain Munir | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-16 | [5 empty] | 2026-02-04T16:14:24.639+0500 | 2026-02-20T17:15:22.920+0500
ODL | ODL-17 | ODL-17 | Sub-task | Sub-task |  | Handover - Site status screen , Read API notification , Data point management | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1 | 1 | Faiza Nasir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-17 | [5 empty] | 2026-02-09T12:55:13.442+0500 | 2026-02-23T13:09:25.794+0500
ODL | ODL-18 | ODL-18 | Sub-task | Sub-task |  | Handover - Real API Dashboard | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2.5 | 2.5 | Faiza Nasir | 2.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-18 | [5 empty] | 2026-02-09T12:55:34.257+0500 | 2026-03-06T10:42:15.922+0500
ODL | ODL-19 | ODL-19 | Sub-task | Sub-task |  | HANDOVER - Import Site Layout | Resolved! | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2 | 2 | Faiza Nasir | 2 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-19 | [5 empty] | 2026-02-09T12:58:58.246+0500 | 2026-02-23T13:14:32.646+0500
ODL | ODL-20 | ODL-20 | Sub-task | Sub-task |  | Handover Session 11 - APX insights | Resolved! |  |  | 2026-02-04 | 2026-02-04 | 1 | 1 | Faiza Nasir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-20 | [5 empty] | 2026-02-09T13:02:55.359+0500 | 2026-02-23T13:13:34.064+0500
ODL | ODL-21 | ODL-21 | Sub-task | Sub-task |  | Handover Session 7 - Create formula , Variable , Asset subtype , Asset type | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 4.5 | 4.5 | Faiza Nasir | 4.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-21 | [5 empty] | 2026-02-09T13:03:59.402+0500 | 2026-03-06T10:42:48.796+0500
ODL | ODL-22 | ODL-22 | Sub-task | Sub-task |  | Handover Session 6 - Bulk Device Replication , Connection strings (EDGE) | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2.5 | 2.5 | Faiza Nasir | 2.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-22 | [5 empty] | 2026-02-09T13:04:16.228+0500 | 2026-03-06T10:42:34.867+0500
ODL | ODL-23 | ODL-23 | Sub-task | Sub-task |  | Handover - Setting | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 3 | 3 | Muhammad Ahmad Saleem | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-23 | [5 empty] | 2026-02-10T11:08:34.482+0500 | 2026-03-06T10:18:15.231+0500
ODL | ODL-25 | ODL-25 | Sub-task | Sub-task |  | Handover -User Management + Authorization | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-25 | [5 empty] | 2026-02-12T09:20:10.764+0500 | 2026-02-23T13:33:35.923+0500
ODL | ODL-26 | ODL-26 | Sub-task | Sub-task |  | Handover - Nested Cal Tag + Code Review | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 7.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-26 | [5 empty] | 2026-02-12T09:21:16.130+0500 | 2026-02-20T17:03:13.547+0500
ODL | ODL-27 | ODL-27 | Sub-task | Sub-task |  | Handover - On Hold Modules | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 3 | 3 | Muhammad Ahmad Saleem | 4.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-27 | [5 empty] | 2026-02-12T09:26:40.836+0500 | 2026-02-23T13:35:53.629+0500
ODL | ODL-28 | ODL-28 | Sub-task | Sub-task |  | Handover - Final Queries + Resolved Concerns | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 6 | 6 | Muhammad Ahmad Saleem | 6 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-28 | [5 empty] | 2026-02-12T09:27:22.104+0500 | 2026-03-06T10:19:11.002+0500
ODL | ODL-29 | ODL-29 | Sub-task | Sub-task |  | Handover -User Management + Authorization | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2 | 2 | Faiza Nasir | 2 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-29 | [5 empty] | 2026-02-12T11:22:06.220+0500 | 2026-03-13T16:23:26.531+0500
ODL | ODL-30 | ODL-30 | Sub-task | Sub-task |  | Handover - Device Diagnostics & Nested Cal Tag + Code Review | Resolved! | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 1.5 | 1.5 | Faiza Nasir | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-30 | [5 empty] | 2026-02-12T11:22:18.296+0500 | 2026-03-13T16:23:59.813+0500
ODL | ODL-31 | ODL-31 | Sub-task | Sub-task |  | Handover - On Hold Modules | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 1 | 1 | Faiza Nasir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-31 | [5 empty] | 2026-02-12T11:23:06.815+0500 | 2026-03-13T16:25:38.184+0500
ODL | ODL-32 | ODL-32 | Sub-task | Sub-task |  | Handover - Final Queries + Resolved Concerns | Resolved! | 2026-03-11 | 2026-03-11 | 2026-02-11 | 2026-02-11 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-32 | [5 empty] | 2026-02-12T11:23:52.635+0500 | 2026-03-13T16:27:23.518+0500
ODL | ODL-33 | ODL-33 | Sub-task | Sub-task |  | Handover - Final Quiz and Queries | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1 | 1 | Zain Munir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-33 | [5 empty] | 2026-02-12T12:36:40.082+0500 | 2026-02-19T14:04:54.681+0500
ODL | ODL-34 | ODL-34 | Sub-task | Sub-task |  | Real Time / GPS Tag Handover Session | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-34 | [5 empty] | 2026-02-12T16:30:23.586+0500 | 2026-03-04T13:26:31.352+0500
ODL | ODL-35 | ODL-35 | Sub-task | Sub-task |  | Calculated+Timer+Counter Tags Handover Session | Backlog / To Do | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-35 | [5 empty] | 2026-02-12T16:30:40.934+0500 | 2026-03-04T13:28:01.902+0500
ODL | ODL-36 | ODL-36 | Sub-task | Sub-task |  | Calculated+Timer+Counter Tags Handover Session | Backlog / To Do | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-36 | [5 empty] | 2026-02-12T16:30:54.681+0500 | 2026-03-04T13:28:38.159+0500
ODL | ODL-37 | ODL-37 | Sub-task | Sub-task |  | Live Values+Tag Dependencies+Bulk Tag Deletion Handover Session | Backlog / To Do | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-37 | [5 empty] | 2026-02-12T16:31:02.259+0500 | 2026-03-04T12:24:47.813+0500
ODL | ODL-38 | ODL-38 | Sub-task | Sub-task |  | Anomaly Detection Handover Session | Backlog / To Do | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-38 | [5 empty] | 2026-02-12T16:31:11.821+0500 | 2026-03-04T12:29:10.911+0500
ODL | ODL-39 | ODL-39 | Sub-task | Sub-task |  | Export Handover Session | Backlog / To Do | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-39 | [5 empty] | 2026-02-12T16:31:20.161+0500 | 2026-03-04T12:28:56.042+0500
ODL | ODL-4 | ODL-4 | Epic | Epic |  | DEWA Pumps Operating Philosophy | Backlog / To Do |  |  | 2026-01-28 | 2026-01-28 | 0 | 0 | Mariam Zulfiqar | 1 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/ODL-4 | [5 empty] | 2026-01-23T16:38:22.837+0500 | 2026-01-30T11:38:41.228+0500
ODL | ODL-40 | ODL-40 | Sub-task | Sub-task |  | Apx Template/Insights/Performance Handover Session | Backlog / To Do | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-40 | [5 empty] | 2026-02-12T16:31:29.499+0500 | 2026-03-04T12:31:43.455+0500
ODL | ODL-41 | ODL-41 | Sub-task | Sub-task |  | Handover -User Management + Authorization | Backlog / To Do | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-41 | [5 empty] | 2026-02-12T16:32:09.082+0500 | 2026-03-04T12:39:53.275+0500
ODL | ODL-42 | ODL-42 | Sub-task | Sub-task |  | Handover - Nested Cal Tag + Code Review | Backlog / To Do | 2026-03-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-42 | [5 empty] | 2026-02-12T16:32:17.410+0500 | 2026-03-04T12:40:48.949+0500
ODL | ODL-43 | ODL-43 | Sub-task | Sub-task |  | Handover - On Hold Modules | Backlog / To Do | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-43 | [5 empty] | 2026-02-12T16:32:24.973+0500 | 2026-03-04T12:41:57.342+0500
ODL | ODL-44 | ODL-44 | Sub-task | Sub-task |  | Handover - Final Queries + Resolved Concerns | Backlog / To Do | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1 | 1 | Sarmad Sabir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-44 | [5 empty] | 2026-02-12T16:32:34.917+0500 | 2026-03-04T12:43:50.766+0500
ODL | ODL-45 | ODL-45 | Sub-task | Sub-task |  | Handover Quiz | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1.5 | 1.5 | Faiza Nasir | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-45 | [5 empty] | 2026-02-12T16:55:03.425+0500 | 2026-03-13T16:29:33.653+0500
ODL | ODL-46 | ODL-46 | Epic | Epic |  | EPR Reporting | Backlog / To Do |  |  |  |  | 0 | 0 | NOOR UL AAIEN | 2 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | [5 empty] | 2026-02-13T11:09:51.628+0500 | 2026-04-15T09:21:05.205+0500
ODL | ODL-47 | ODL-47 | Story | Story |  | Taimur Zahid | In-Process | 2026-02-13 | 2026-02-20 |  |  | 8 | 8 | Taimur Zahid | 8 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-47 | [5 empty] | 2026-02-13T11:10:06.081+0500 | 2026-03-05T15:38:52.000+0500
ODL | ODL-48 | ODL-48 | Sub-task | Sub-task |  | Handover : Queries related to Anomaly and Tags | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 5 | 5 | Muhammad Ahmad Saleem | 5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-48 | [5 empty] | 2026-02-13T12:10:29.342+0500 | 2026-02-23T13:32:00.031+0500
ODL | ODL-49 | ODL-49 | Sub-task | Sub-task |  | Handover Quiz | Resolved! | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-49 | [5 empty] | 2026-02-13T14:28:52.180+0500 | 2026-02-13T14:31:49.797+0500
ODL | ODL-5 | ODL-5 | Story | Story |  | Ali Qumail - Handover sessions | Resolved! |  |  |  |  | 0 | 0 | Ali Qumail | 103 |  | ODL-63 | ODL-63 | https://octopusdtlsupport.atlassian.net/browse/ODL-63 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | [5 empty] | 2026-01-29T10:30:31.428+0500 | 2026-02-23T13:52:50.010+0500
ODL | ODL-50 | ODL-50 | Story | Story |  | Zain Munir | Backlog / To Do |  |  |  |  | 0 | 0 | Zain Munir | 2.5 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-50 | [5 empty] | 2026-02-13T16:06:11.703+0500 | 2026-02-13T16:07:18.461+0500
ODL | ODL-51 | ODL-51 | Sub-task | Sub-task |  | 13 Feb 2026 | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Taimur Zahid | 8 |  | ODL-47 | ODL-47 | https://octopusdtlsupport.atlassian.net/browse/ODL-47 | https://octopusdtlsupport.atlassian.net/browse/ODL-51 | [5 empty] | 2026-02-13T16:06:53.151+0500 | 2026-02-13T16:13:37.108+0500
ODL | ODL-52 | ODL-52 | Sub-task | Sub-task |  | Scrum + Jira Activity 13 Feb 2026 | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2.5 | 2.5 | Zain Munir | 2.5 |  | ODL-50 | ODL-50 | https://octopusdtlsupport.atlassian.net/browse/ODL-50 | https://octopusdtlsupport.atlassian.net/browse/ODL-52 | [5 empty] | 2026-02-13T16:07:30.034+0500 | 2026-02-20T09:33:18.386+0500
ODL | ODL-54 | ODL-54 | Story | Story |  | Arsalan Zafar Khan | Backlog / To Do |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 8 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | [5 empty] | 2026-02-13T16:24:21.401+0500 | 2026-02-13T16:25:04.704+0500
ODL | ODL-55 | ODL-55 | Sub-task | Sub-task |  | Jira Time Log Activity 13 Feb 2026 | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2 | 2 | Arsalan Zafar Khan | 2 |  | ODL-54 | ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-55 | [5 empty] | 2026-02-13T16:38:26.872+0500 | 2026-02-20T12:26:27.854+0500
ODL | ODL-57 | ODL-57 | Story | Story |  | Mohsin Junaid | In-Process |  |  |  |  | 0 | 0 | Mohsin Junaid | 8 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-57 | [5 empty] | 2026-02-13T16:59:10.313+0500 | 2026-02-13T17:01:19.781+0500
ODL | ODL-58 | ODL-58 | Sub-task | Sub-task |  | 13 Feb 2026 | In-Process |  |  | 2026-02-13 | 2026-02-13 | 0 | 0 | Mohsin Junaid | 8 |  | ODL-57 | ODL-57 | https://octopusdtlsupport.atlassian.net/browse/ODL-57 | https://octopusdtlsupport.atlassian.net/browse/ODL-58 | [5 empty] | 2026-02-13T17:00:20.241+0500 | 2026-03-02T17:23:39.826+0500
ODL | ODL-59 | ODL-59 | Story | Story |  | Faiza Nasir | In-Process |  |  |  |  | 0 | 0 | Faiza Nasir | 6 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-59 | [5 empty] | 2026-02-16T12:18:54.604+0500 | 2026-03-02T17:23:39.346+0500
ODL | ODL-6 | ODL-6 | Sub-task | Sub-task |  | Real Time / GPS Tag Handover Session | Resolved! | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2 | 2 | Zain Munir | 2 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-6 | [5 empty] | 2026-01-29T10:31:57.662+0500 | 2026-02-19T14:03:08.761+0500
ODL | ODL-60 | ODL-60 | Sub-task | Sub-task |  | Add planned dates and estimates for all assigned tasks / stories | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2 | 2 | Faiza Nasir | 2 |  | ODL-59 | ODL-59 | https://octopusdtlsupport.atlassian.net/browse/ODL-59 | https://octopusdtlsupport.atlassian.net/browse/ODL-60 | [5 empty] | 2026-02-16T12:19:46.013+0500 | 2026-03-13T16:31:02.533+0500
ODL | ODL-61 | ODL-61 | Story | Story |  | Muhammad Ahmad Saleem | Backlog / To Do |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 3 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-61 | [5 empty] | 2026-02-16T16:03:08.294+0500 | 2026-02-16T16:03:53.614+0500
ODL | ODL-62 | ODL-62 | Sub-task | Sub-task |  | 13 February 2026 | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 3 | 3 | Muhammad Ahmad Saleem | 3 |  | ODL-61 | ODL-61 | https://octopusdtlsupport.atlassian.net/browse/ODL-61 | https://octopusdtlsupport.atlassian.net/browse/ODL-62 | [5 empty] | 2026-02-16T16:04:43.948+0500 | 2026-02-16T16:09:39.824+0500
ODL | ODL-63 | ODL-63 | Epic | Epic |  | Handover Sessions | In-Process |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/ODL-63 | [5 empty] | 2026-02-19T10:58:47.434+0500 | 2026-02-19T13:35:25.742+0500
ODL | ODL-64 | ODL-64 | Epic | Epic |  | General Research work | Backlog / To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/ODL-64 | [5 empty] | 2026-02-19T14:36:39.216+0500 | 2026-02-19T14:36:45.891+0500
ODL | ODL-65 | ODL-65 | Sub-task | Sub-task |  | Next Sprint Planning Activity 19 Feb. | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2 | 2 | Arsalan Zafar Khan | 2 |  | ODL-54 | ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-54 | https://octopusdtlsupport.atlassian.net/browse/ODL-65 | [5 empty] | 2026-02-20T12:26:17.553+0500 | 2026-03-13T11:03:59.069+0500
ODL | ODL-66 | ODL-66 | Task | Task |  | Muhammad Abdullah | Backlog / To Do |  |  |  |  | 0 | 0 | Muhammad Abdullah | 2 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-66 | [5 empty] | 2026-02-20T15:25:27.368+0500 | 2026-02-20T15:25:34.124+0500
ODL | ODL-67 | ODL-67 | Sub-task | Sub-task |  | Next Sprint Planning Activity 19 Feb. | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2 | 2 | Muhammad Abdullah | 2 |  | ODL-66 | ODL-66 | https://octopusdtlsupport.atlassian.net/browse/ODL-66 | https://octopusdtlsupport.atlassian.net/browse/ODL-67 | [5 empty] | 2026-02-20T15:26:27.254+0500 | 2026-03-13T11:04:50.748+0500
ODL | ODL-68 | ODL-68 | Sub-task | Sub-task |  | Live Values,Tag Dependencies,Bulk Tag Deletion Handover Session | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-68 | [5 empty] | 2026-02-20T17:01:15.292+0500 | 2026-02-20T17:02:52.896+0500
ODL | ODL-69 | ODL-69 | Sub-task | Sub-task |  | Manual,Totalizer Tags Handover Session | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-69 | [5 empty] | 2026-02-20T17:05:55.644+0500 | 2026-02-20T17:07:52.991+0500
ODL | ODL-7 | ODL-7 | Sub-task | Sub-task |  | Real Time and GPS Tags handover Session | Resolved! |  |  | 2026-01-28 | 2026-01-28 | 1 | 1 | Faiza Nasir | 1 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-7 | [5 empty] | 2026-01-29T10:32:00.540+0500 | 2026-02-23T13:15:13.117+0500
ODL | ODL-70 | ODL-70 | Sub-task | Sub-task |  | Data Alarms,Statistical Alarms, Tag Diagnostics Handover Session | Resolved! | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-70 | [5 empty] | 2026-02-20T17:09:16.801+0500 | 2026-02-20T17:10:48.837+0500
ODL | ODL-71 | ODL-71 | Sub-task | Sub-task |  | Anomaly Detection Handover | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-71 | [5 empty] | 2026-02-20T17:11:44.581+0500 | 2026-02-20T17:12:55.011+0500
ODL | ODL-72 | ODL-72 | Sub-task | Sub-task |  | Export Handover | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-72 | [5 empty] | 2026-02-20T17:13:33.928+0500 | 2026-02-20T17:17:48.571+0500
ODL | ODL-73 | ODL-73 | Sub-task | Sub-task |  | Apx Template,Insights,Performance Handover Session | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3 | 3 | Muhammad Ahmad Saleem | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-73 | [5 empty] | 2026-02-20T17:15:37.042+0500 | 2026-02-20T17:17:12.757+0500
ODL | ODL-74 | ODL-74 | Sub-task | Sub-task |  | Real API Dashboard - Handover | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-74 | [5 empty] | 2026-02-20T17:18:57.121+0500 | 2026-02-20T17:20:16.012+0500
ODL | ODL-75 | ODL-75 | Sub-task | Sub-task |  | Handover Session- Bulk Device Replication , Connection strings (EDGE) | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 1.5 | 1.5 | Muhammad Ahmad Saleem | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-75 | [5 empty] | 2026-02-20T17:23:51.947+0500 | 2026-02-20T17:25:16.537+0500
ODL | ODL-76 | ODL-76 | Story | Story |  | Nadeem Ahmed | Backlog / To Do | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2 | 2 | nadeem ahmed | 8.5 |  | ODL-46 | ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-46 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | [5 empty] | 2026-02-23T14:47:23.674+0500 | 2026-03-03T10:00:27.146+0500
ODL | ODL-77 | ODL-77 | Sub-task | Sub-task |  | Next sprint planning 2026 | Resolved! |  |  |  |  | 0 | 0 | Unassigned | 0 |  | ODL-76 | ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-77 | [5 empty] | 2026-02-23T14:48:10.984+0500 | 2026-05-05T16:45:25.159+0500
ODL | ODL-78 | ODL-78 | Sub-task | Sub-task |  | Meeting with team to improve capability of LogChat | Resolved! |  |  |  |  | 0 | 0 | nadeem ahmed | 0 |  | ODL-76 | ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-78 | [5 empty] | 2026-02-23T15:03:40.452+0500 | 2026-03-03T09:55:56.659+0500
ODL | ODL-79 | ODL-79 | Sub-task | Sub-task |  | Project Planning and Jira Management for team | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 4 | 4 | Faiza Nasir | 4 |  | ODL-59 | ODL-59 | https://octopusdtlsupport.atlassian.net/browse/ODL-59 | https://octopusdtlsupport.atlassian.net/browse/ODL-79 | [5 empty] | 2026-02-25T10:53:04.109+0500 | 2026-03-06T10:43:45.329+0500
ODL | ODL-8 | ODL-8 | Sub-task | Sub-task |  | Calculated+Timer+Counter Tags Handover Session | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1.5 | 1.5 | Zain Munir | 1.5 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-8 | [5 empty] | 2026-01-29T14:54:05.613+0500 | 2026-02-19T14:03:19.195+0500
ODL | ODL-80 | ODL-80 | Epic | Epic |  | Project Management - EPR Reports Building | Backlog / To Do | 2026-02-03 | 2026-03-13 |  |  | 240 | 240 | Hassan Malik | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/ODL-80 | [5 empty] | 2026-03-02T11:33:22.621+0500 | 2026-03-02T11:44:30.583+0500
ODL | ODL-81 | ODL-81 | Story | Story |  | Custom Reports (non power bi) | Resolved! | 2026-02-03 | 2026-03-13 |  |  | 199 | 199 | Hassan Malik | 191 |  | ODL-80 | ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | [5 empty] | 2026-03-02T11:35:11.826+0500 | 2026-03-17T15:22:46.051+0500
ODL | ODL-82 | ODL-82 | Sub-task | Sub-task |  | Audit of Power BI and Requirements analysis | Resolved! | 2026-02-03 | 2026-02-09 | 2026-02-04 | 2026-02-09 | 40 | 40 | Hassan Malik | 24 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-82 | [5 empty] | 2026-03-02T11:38:21.243+0500 | 2026-03-18T09:43:53.588+0500
ODL | ODL-83 | ODL-83 | Story | Story |  | SQA | Backlog / To Do |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | ODL-80 | ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-80 | https://octopusdtlsupport.atlassian.net/browse/ODL-83 | [5 empty] | 2026-03-02T11:41:48.323+0500 | 2026-03-02T11:50:49.647+0500
ODL | ODL-84 | ODL-84 | Task | Task |  | DEWA Pumps Operating Philosophy | Backlog / To Do |  |  |  |  | 0 | 0 | Unassigned | 199 |  | ODL-4 | ODL-4 | https://octopusdtlsupport.atlassian.net/browse/ODL-4 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | [5 empty] | 2026-03-02T13:02:33.169+0500 | 2026-03-02T13:02:33.311+0500
ODL | ODL-85 | ODL-85 | Sub-task | Sub-task |  | 6. Support Avanceon for development | In-Process | 2025-12-01 |  | 2026-01-28 | 2026-02-27 | 0 | 0 | Mariam Zulfiqar | 6 |  | ODL-84 | ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-84 | https://octopusdtlsupport.atlassian.net/browse/ODL-85 | [5 empty] | 2026-03-02T13:04:03.692+0500 | 2026-03-26T10:13:03.495+0500
ODL | ODL-86 | ODL-86 | Sub-task | Sub-task |  | Basic Report Structuring | Resolved! | 2026-02-10 | 2026-02-16 | 2026-02-10 | 2026-02-16 | 40 | 40 | Hassan Malik | 40 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-86 | [5 empty] | 2026-03-02T17:21:28.087+0500 | 2026-03-17T14:12:48.615+0500
ODL | ODL-87 | ODL-87 | Sub-task | Sub-task |  | Advanced Report Structuring | Resolved! | 2026-02-17 | 2026-02-23 | 2026-02-17 | 2026-02-23 | 34 | 34 | Hassan Malik | 34 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-87 | [5 empty] | 2026-03-02T17:21:37.346+0500 | 2026-03-17T14:15:12.526+0500
ODL | ODL-88 | ODL-88 | Sub-task | Sub-task |  | Adding Data Story Reports | Resolved! | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-27 | 26 | 26 | Hassan Malik | 26 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-88 | [5 empty] | 2026-03-02T17:21:48.052+0500 | 2026-03-17T14:19:42.447+0500
ODL | ODL-9 | ODL-9 | Sub-task | Sub-task |  | Manual+Totalizer Tags Handover Session | Resolved! | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 1.5 | 1.5 | Zain Munir | 3 |  | ODL-5 | ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-5 | https://octopusdtlsupport.atlassian.net/browse/ODL-9 | [5 empty] | 2026-01-29T14:54:36.009+0500 | 2026-02-20T17:05:37.817+0500
ODL | ODL-90 | ODL-90 | Sub-task | Sub-task |  | CDC review at CP-1 meeting with Colgate team | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2 | 2 | nadeem ahmed | 2 |  | ODL-76 | ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-90 | [5 empty] | 2026-03-03T09:57:17.323+0500 | 2026-03-03T09:59:10.242+0500
ODL | ODL-91 | ODL-91 | Sub-task | Sub-task |  | Improving Employee Performance Report | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 6.5 | 6.5 | Hassan Malik | 6.5 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-91 | [5 empty] | 2026-03-05T11:00:47.007+0500 | 2026-03-17T15:10:56.116+0500
ODL | ODL-92 | ODL-92 | Sub-task | Sub-task |  | Improving Score Card Report - Nested Report | Resolved! | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-03-09 | 13 | 13 | Hassan Malik | 13 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-92 | [5 empty] | 2026-03-05T11:01:03.957+0500 | 2026-03-17T14:25:34.852+0500
ODL | ODL-93 | ODL-93 | Sub-task | Sub-task |  | Digital Log road map meeting | Resolved! | 2026-03-04 | 2026-03-04 |  |  | 1 | 1 | Unassigned | 0 |  | ODL-76 | ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-93 | [5 empty] | 2026-03-05T15:04:54.621+0500 | 2026-03-30T16:57:57.393+0500
ODL | ODL-94 | ODL-94 | Sub-task | Sub-task |  | Custom Report development for Zomco demo | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 4 | 4 | nadeem ahmed | 3 |  | ODL-76 | ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-94 | [5 empty] | 2026-03-10T15:06:13.048+0500 | 2026-03-10T15:08:40.206+0500
ODL | ODL-95 | ODL-95 | Sub-task | Sub-task |  | Meeting with Zomco regarding Digital Log Demo - along with PreSale team | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1.5 | 1.5 | nadeem ahmed | 1.5 |  | ODL-76 | ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-76 | https://octopusdtlsupport.atlassian.net/browse/ODL-95 | [5 empty] | 2026-03-10T15:07:10.164+0500 | 2026-05-05T16:45:07.984+0500
ODL | ODL-96 | ODL-96 | Sub-task | Sub-task |  | Building Colossal Refresh | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6.5 | 6.5 | Hassan Malik | 6.5 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-96 | [5 empty] | 2026-03-16T15:08:56.963+0500 | 2026-03-17T15:11:32.818+0500
ODL | ODL-97 | ODL-97 | Sub-task | Sub-task |  | Unified Data Refresh for All Reports | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5 | 6.5 | Hassan Malik | 6.5 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-97 | [5 empty] | 2026-03-16T15:09:34.524+0500 | 2026-03-17T15:14:50.488+0500
ODL | ODL-98 | ODL-98 | Sub-task | Sub-task |  | Fixing data sync issues across reports | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 4 | 4 | Hassan Malik | 4 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-98 | [5 empty] | 2026-03-16T15:09:58.205+0500 | 2026-03-17T15:13:00.860+0500
ODL | ODL-99 | ODL-99 | Sub-task | Sub-task |  | Building IPP Planner and IPP Dashboard | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2.5 | 2.5 | Hassan Malik | 2.5 |  | ODL-81 | ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-81 | https://octopusdtlsupport.atlassian.net/browse/ODL-99 | [5 empty] | 2026-03-16T15:11:01.662+0500 | 2026-03-17T15:13:36.729+0500
RLT | RLT-10 | RLT-10 | Task | Task |  | Leaves Arslan Sohail | Considered in Roadmap & Queued |  |  | 2026-01-26 | 2026-04-16 | 0 | 0 | Arslan sohail | 200 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-10 | [5 empty] | 2024-05-08T18:49:46.158+0500 | 2026-04-20T16:48:28.974+0500
RLT | RLT-100 | RLT-100 | Sub-task | Sub-task |  | Leave for one day 19-12-25 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-100 | [5 empty] | 2025-12-29T12:28:27.426+0500 | 2025-12-29T12:30:18.123+0500
RLT | RLT-101 | RLT-101 | Sub-task | Sub-task |  | Leave for one day 26-12-25 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-101 | [5 empty] | 2025-12-29T12:28:57.752+0500 | 2025-12-29T12:30:43.459+0500
RLT | RLT-102 | RLT-102 | Sub-task | Sub-task |  | Annual leave 23 December | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-102 | [5 empty] | 2025-12-29T12:29:49.859+0500 | 2026-02-11T17:52:15.666+0500
RLT | RLT-103 | RLT-103 | Sub-task | Sub-task |  | Annual leave 24 December | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-103 | [5 empty] | 2025-12-29T12:30:16.716+0500 | 2026-02-11T17:52:17.256+0500
RLT | RLT-104 | RLT-104 | Sub-task | Sub-task |  | Annual leave 26 December | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-104 | [5 empty] | 2025-12-29T12:30:37.273+0500 | 2026-02-11T17:52:18.781+0500
RLT | RLT-105 | RLT-105 | Sub-task | Sub-task |  | Annual leave 29 December | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-105 | [5 empty] | 2025-12-29T12:30:54.027+0500 | 2026-02-11T17:52:20.768+0500
RLT | RLT-106 | RLT-106 | Sub-task | Sub-task |  | Annual leave 30 December | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-106 | [5 empty] | 2025-12-29T12:31:05.319+0500 | 2026-02-11T17:52:22.333+0500
RLT | RLT-107 | RLT-107 | Sub-task | Sub-task |  | Annual leave 31 December | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-107 | [5 empty] | 2025-12-29T12:31:13.609+0500 | 2026-02-11T17:52:23.920+0500
RLT | RLT-108 | RLT-108 | Sub-task | Sub-task |  | Annual leave 01 Jan 2026 | Annual Leave |  |  | 2026-01-01 | 2026-01-01 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-108 | [5 empty] | 2025-12-29T12:31:46.708+0500 | 2026-02-11T17:51:58.963+0500
RLT | RLT-109 | RLT-109 | Sub-task | Sub-task |  | Annual leave 02 Jan 2026 | Annual Leave |  |  | 2026-01-02 | 2026-01-02 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-109 | [5 empty] | 2025-12-29T12:31:59.987+0500 | 2026-02-11T17:52:00.705+0500
RLT | RLT-11 | RLT-11 | Task | Task |  | Leaves Arslan Zafar | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Arsalan Zafar Khan | 126.5 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-11 | [5 empty] | 2024-05-08T18:49:59.625+0500 | 2026-03-18T09:24:17.928+0500
RLT | RLT-110 | RLT-110 | Sub-task | Sub-task |  | Annual leave 05 Jan 2026 | Annual Leave |  |  | 2026-01-05 | 2026-01-05 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-110 | [5 empty] | 2025-12-29T12:32:13.159+0500 | 2026-02-11T17:52:02.414+0500
RLT | RLT-111 | RLT-111 | Sub-task | Sub-task |  | Annual leave 06 Jan 2026 | Annual Leave |  |  | 2026-01-06 | 2026-01-06 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-111 | [5 empty] | 2025-12-29T12:32:23.305+0500 | 2026-02-11T17:52:04.138+0500
RLT | RLT-112 | RLT-112 | Sub-task | Sub-task |  | Annual leave 07 Jan 2026 | Annual Leave |  |  | 2026-01-07 | 2026-01-07 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-112 | [5 empty] | 2025-12-29T12:32:38.579+0500 | 2026-02-11T17:52:05.988+0500
RLT | RLT-113 | RLT-113 | Sub-task | Sub-task |  | Annual leave 08 Jan 2026 | Annual Leave |  |  | 2026-01-08 | 2026-01-08 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-113 | [5 empty] | 2025-12-29T12:32:48.458+0500 | 2026-02-11T17:52:07.867+0500
RLT | RLT-114 | RLT-114 | Sub-task | Sub-task |  | Annual leave 09 Jan 2026 | Annual Leave |  |  | 2026-01-09 | 2026-01-09 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-114 | [5 empty] | 2025-12-29T12:32:58.182+0500 | 2026-02-11T17:52:09.489+0500
RLT | RLT-115 | RLT-115 | Sub-task | Sub-task |  | Annual leave 12 Jan 2026 | Annual Leave |  |  | 2026-01-12 | 2026-01-12 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-115 | [5 empty] | 2025-12-29T12:33:15.889+0500 | 2026-02-11T17:52:11.314+0500
RLT | RLT-116 | RLT-116 | Sub-task | Sub-task |  | Annual Leaves | Annual Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 48 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-116 | [5 empty] | 2025-12-29T12:40:30.796+0500 | 2026-04-20T11:26:25.006+0500
RLT | RLT-118 | RLT-118 | Story | Story |  | Leaves Taimur Zahid | Selected for Development | 2025-01-01 | 2028-12-31 |  |  | 480 | 480 | Taimur Zahid | 53 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | [5 empty] | 2025-12-30T10:30:38.756+0500 | 2026-03-03T10:58:04.690+0500
RLT | RLT-119 | RLT-119 | Task | Task |  | Leaves of Mohsin Junaid | Planned Leave |  |  | 2026-03-02 | 2026-03-02 | 0 | 0 | Mohsin Junaid | 80 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-119 | [5 empty] | 2026-01-01T12:17:07.557+0500 | 2026-03-03T09:49:24.782+0500
RLT | RLT-121 | RLT-121 | Sub-task | Sub-task |  | Planned Leave 30th January 2026 | Sick Leave | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8 | 8 | Muhammad Imran Aslam | 8 |  | RLT-26 | RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-121 | [5 empty] | 2026-01-29T11:55:40.854+0500 | 2026-03-02T14:17:45.818+0500
RLT | RLT-122 | RLT-122 | Sub-task | Sub-task |  | Planned Leave on 5 Jan 26 | Planned Leave | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-122 | [5 empty] | 2026-01-29T16:12:38.580+0500 | 2026-03-02T12:44:58.393+0500
RLT | RLT-123 | RLT-123 | Sub-task | Sub-task |  | Planned Leave on 6 Jan 26 | Planned Leave | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-123 | [5 empty] | 2026-01-29T16:14:04.146+0500 | 2026-03-02T12:45:03.019+0500
RLT | RLT-124 | RLT-124 | Sub-task | Sub-task |  | Planned Leave on 7 Jan 26 | Planned Leave | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-124 | [5 empty] | 2026-01-29T16:14:12.725+0500 | 2026-03-02T12:45:09.193+0500
RLT | RLT-125 | RLT-125 | Sub-task | Sub-task |  | Planned Leave on 8 Jan 26 | Planned Leave | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-125 | [5 empty] | 2026-01-29T16:14:22.813+0500 | 2026-03-02T12:45:13.551+0500
RLT | RLT-126 | RLT-126 | Sub-task | Sub-task |  | Planned Leave on 9 Jan 26 | Planned Leave | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-126 | [5 empty] | 2026-01-29T16:14:32.314+0500 | 2026-03-02T12:45:28.982+0500
RLT | RLT-127 | RLT-127 | Sub-task | Sub-task |  | Planned Leave on 12 Jan 26 | Planned Leave | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-127 | [5 empty] | 2026-01-29T16:14:44.784+0500 | 2026-03-02T12:45:31.965+0500
RLT | RLT-128 | RLT-128 | Sub-task | Sub-task |  | Planned Leave on 13 Jan 26 | Planned Leave | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-128 | [5 empty] | 2026-01-29T16:14:52.540+0500 | 2026-03-02T12:45:34.794+0500
RLT | RLT-129 | RLT-129 | Sub-task | Sub-task |  | Planned Leave on 14 Jan 26 | Planned Leave | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-129 | [5 empty] | 2026-01-29T16:14:59.917+0500 | 2026-03-02T12:45:39.947+0500
RLT | RLT-13 | RLT-13 | Task | Task |  | Leaves Faiza | Internal QA/QC | 2024-05-06 | 2024-05-06 |  |  | 0 | 0 | Faiza Nasir | 219 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | [5 empty] | 2024-05-08T18:50:24.310+0500 | 2025-10-30T09:50:36.123+0500
RLT | RLT-130 | RLT-130 | Sub-task | Sub-task |  | Planned Leave on 15 Jan 26 | Planned Leave | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-130 | [5 empty] | 2026-01-29T16:15:07.577+0500 | 2026-03-02T12:45:43.917+0500
RLT | RLT-131 | RLT-131 | Sub-task | Sub-task |  | Planned Leave on 16 Jan 26 | Planned Leave | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-131 | [5 empty] | 2026-01-29T16:15:19.775+0500 | 2026-03-02T12:45:47.698+0500
RLT | RLT-132 | RLT-132 | Sub-task | Sub-task |  | Planned Leave on 19 Jan 26 | Planned Leave | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Zain Munir | 8 |  | RLT-61 | RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | https://octopusdtlsupport.atlassian.net/browse/RLT-132 | [5 empty] | 2026-01-29T16:15:35.431+0500 | 2026-03-02T12:45:51.097+0500
RLT | RLT-133 | RLT-133 | Sub-task | Sub-task |  | 23 January 2026 | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-133 | [5 empty] | 2026-01-30T16:26:41.753+0500 | 2026-03-02T14:48:16.498+0500
RLT | RLT-134 | RLT-134 | Task | Task |  | Leaves Muhammad Ahmad saleem | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Ahmad Saleem | 61 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | [5 empty] | 2026-01-30T16:44:24.352+0500 | 2026-01-30T16:44:24.438+0500
RLT | RLT-135 | RLT-135 | Sub-task | Sub-task |  | Leave - December 26, 2025 | Planned Leave | 2025-12-26 | 2025-12-26 |  |  | 8 | 8 | Taimur Zahid | 0 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-135 | [5 empty] | 2026-01-30T16:50:21.761+0500 | 2026-03-03T10:58:33.251+0500
RLT | RLT-136 | RLT-136 | Sub-task | Sub-task |  | Leave - January 15, 2026 | Emergency Leave | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Taimur Zahid | 8 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-136 | [5 empty] | 2026-01-30T16:52:12.481+0500 | 2026-03-03T10:59:01.745+0500
RLT | RLT-137 | RLT-137 | Sub-task | Sub-task |  | 16 January 2026 | Considered in Roadmap & Queued | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-137 | [5 empty] | 2026-01-30T16:55:38.238+0500 | 2026-02-23T13:27:56.569+0500
RLT | RLT-138 | RLT-138 | Sub-task | Sub-task |  | 19 January 2026 | Considered in Roadmap & Queued | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-138 | [5 empty] | 2026-01-30T16:58:26.334+0500 | 2026-02-23T13:28:28.851+0500
RLT | RLT-139 | RLT-139 | Sub-task | Sub-task |  | 20 January 2026 | Considered in Roadmap & Queued | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-139 | [5 empty] | 2026-01-30T17:00:11.242+0500 | 2026-02-23T13:28:50.647+0500
RLT | RLT-140 | RLT-140 | Sub-task | Sub-task |  | 22 January 2026 | Considered in Roadmap & Queued | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-140 | [5 empty] | 2026-02-02T09:32:58.433+0500 | 2026-03-02T13:51:49.750+0500
RLT | RLT-141 | RLT-141 | Sub-task | Sub-task |  | Casual Leave 30 Jan 2026 | Sick Leave | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 8 | 8 | Muhammad Abdullah | 8 |  | RLT-32 | RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-141 | [5 empty] | 2026-02-02T09:35:15.456+0500 | 2026-03-02T13:42:10.695+0500
RLT | RLT-142 | RLT-142 | Sub-task | Sub-task |  | 20 January 2026 | Sick Leave | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-142 | [5 empty] | 2026-02-02T09:35:20.753+0500 | 2026-03-02T13:51:58.269+0500
RLT | RLT-143 | RLT-143 | Sub-task | Sub-task |  | 16 January 2026 | Annual Leave | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-143 | [5 empty] | 2026-02-02T09:42:22.742+0500 | 2026-03-02T13:52:05.234+0500
RLT | RLT-144 | RLT-144 | Sub-task | Sub-task |  | 2 January 2026 | Annual Leave | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-144 | [5 empty] | 2026-02-02T09:44:54.755+0500 | 2026-03-02T13:52:11.634+0500
RLT | RLT-145 | RLT-145 | Sub-task | Sub-task |  | 1 January 2026 | Annual Leave | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-145 | [5 empty] | 2026-02-02T09:46:26.737+0500 | 2026-02-22T22:25:09.624+0500
RLT | RLT-146 | RLT-146 | Sub-task | Sub-task |  | 1st January medical emergency leave | Emergency Leave | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-146 | [5 empty] | 2026-02-02T09:58:28.694+0500 | 2026-03-12T14:27:01.794+0500
RLT | RLT-147 | RLT-147 | Sub-task | Sub-task |  | 12th January medical emergency leave | Emergency Leave | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-147 | [5 empty] | 2026-02-02T09:58:51.878+0500 | 2026-03-12T14:26:59.112+0500
RLT | RLT-148 | RLT-148 | Sub-task | Sub-task |  | 13th January medical emergency leave | Emergency Leave | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-148 | [5 empty] | 2026-02-02T09:59:03.349+0500 | 2026-03-12T14:26:55.938+0500
RLT | RLT-149 | RLT-149 | Sub-task | Sub-task |  | 14th January medical emergency leave | Emergency Leave | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-149 | [5 empty] | 2026-02-02T09:59:15.697+0500 | 2026-03-12T14:26:50.476+0500
RLT | RLT-15 | RLT-15 | Task | Task |  | Leaves Namra | Considered in Roadmap & Queued |  |  | 2026-01-19 | 2026-01-19 | 0 | 0 | Namra Zahid | 240 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | [5 empty] | 2024-05-08T18:50:39.685+0500 | 2026-05-12T14:24:15.122+0500
RLT | RLT-150 | RLT-150 | Sub-task | Sub-task |  | 15th January medical emergency leave | Emergency Leave | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-150 | [5 empty] | 2026-02-02T09:59:24.016+0500 | 2026-03-12T14:26:47.316+0500
RLT | RLT-151 | RLT-151 | Sub-task | Sub-task |  | 16th January medical emergency leave | Emergency Leave | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-151 | [5 empty] | 2026-02-02T09:59:31.838+0500 | 2026-03-12T14:26:43.911+0500
RLT | RLT-152 | RLT-152 | Sub-task | Sub-task |  | 9 February 2026 | Annual Leave | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-152 | [5 empty] | 2026-02-02T15:40:47.714+0500 | 2026-03-02T13:40:02.680+0500
RLT | RLT-153 | RLT-153 | Sub-task | Sub-task |  | 10 February 2026 | Annual Leave | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-153 | [5 empty] | 2026-02-02T15:44:47.744+0500 | 2026-03-02T13:40:17.949+0500
RLT | RLT-154 | RLT-154 | Sub-task | Sub-task |  | 11 February 2026 | Annual Leave | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-154 | [5 empty] | 2026-02-02T15:45:02.836+0500 | 2026-03-02T13:40:31.852+0500
RLT | RLT-155 | RLT-155 | Sub-task | Sub-task |  | 12 February 2026 | Annual Leave | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-155 | [5 empty] | 2026-02-02T15:45:14.619+0500 | 2026-03-02T13:40:48.160+0500
RLT | RLT-156 | RLT-156 | Sub-task | Sub-task |  | 13 February 2026 | Annual Leave | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-156 | [5 empty] | 2026-02-02T15:45:29.536+0500 | 2026-03-02T13:41:07.864+0500
RLT | RLT-158 | RLT-158 | Sub-task | Sub-task |  | 11 Dec 2025 | Considered in Roadmap & Queued | 2025-12-11 | 2025-12-11 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-158 | [5 empty] | 2026-02-09T11:46:56.973+0500 | 2026-02-22T19:46:10.958+0500
RLT | RLT-159 | RLT-159 | Sub-task | Sub-task |  | 12 Dec 2025 | Considered in Roadmap & Queued | 2025-12-12 | 2025-12-12 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-159 | [5 empty] | 2026-02-09T11:47:06.053+0500 | 2026-02-22T19:46:13.041+0500
RLT | RLT-160 | RLT-160 | Sub-task | Sub-task |  | 15 Dec 2025 | Considered in Roadmap & Queued | 2025-12-15 | 2025-12-15 |  |  | 8 | 8 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-160 | [5 empty] | 2026-02-09T11:51:20.359+0500 | 2026-03-04T09:36:28.954+0500
RLT | RLT-161 | RLT-161 | Sub-task | Sub-task |  | 16 Dec 2025 | Considered in Roadmap & Queued | 2025-12-16 | 2025-12-16 |  |  | 0 | 0 | Maria Sharafat | 0 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-161 | [5 empty] | 2026-02-09T11:51:54.896+0500 | 2026-02-22T19:46:26.392+0500
RLT | RLT-162 | RLT-162 | Sub-task | Sub-task |  | 17 Dec 2025 | Considered in Roadmap & Queued | 2025-12-17 | 2025-12-17 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-162 | [5 empty] | 2026-02-09T11:52:00.422+0500 | 2026-02-22T19:46:28.318+0500
RLT | RLT-163 | RLT-163 | Sub-task | Sub-task |  | 18 Dec 2025 | Considered in Roadmap & Queued | 2025-12-18 | 2025-12-18 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-163 | [5 empty] | 2026-02-09T11:53:10.375+0500 | 2026-02-22T19:46:31.389+0500
RLT | RLT-164 | RLT-164 | Sub-task | Sub-task |  | 19 Dec 2025 | Considered in Roadmap & Queued | 2025-12-19 | 2025-12-19 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-164 | [5 empty] | 2026-02-09T11:53:14.080+0500 | 2026-02-22T19:46:33.428+0500
RLT | RLT-165 | RLT-165 | Sub-task | Sub-task |  | 22 Dec 2025 | Considered in Roadmap & Queued | 2025-12-22 | 2025-12-22 |  |  | 8 | 8 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-165 | [5 empty] | 2026-02-09T11:53:33.572+0500 | 2026-03-04T09:37:29.676+0500
RLT | RLT-166 | RLT-166 | Sub-task | Sub-task |  | 23 Dec 2025 | Considered in Roadmap & Queued | 2025-12-23 | 2025-12-23 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-166 | [5 empty] | 2026-02-09T11:53:39.098+0500 | 2026-02-22T19:46:38.123+0500
RLT | RLT-167 | RLT-167 | Sub-task | Sub-task |  | 24 Dec 2025 | Considered in Roadmap & Queued | 2025-12-24 | 2025-12-24 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-167 | [5 empty] | 2026-02-09T11:53:44.213+0500 | 2026-02-22T19:46:58.513+0500
RLT | RLT-169 | RLT-169 | Sub-task | Sub-task |  | 26 Dec 2025 | Considered in Roadmap & Queued | 2025-12-26 | 2025-12-26 |  |  | 8 | 8 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-169 | [5 empty] | 2026-02-09T11:54:02.241+0500 | 2026-03-04T09:37:19.034+0500
RLT | RLT-17 | RLT-17 | Task | Task |  | Leaves Muhammad Abbas | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abbas | 152 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | [5 empty] | 2024-05-08T18:50:57.707+0500 | 2026-02-20T16:54:44.429+0500
RLT | RLT-170 | RLT-170 | Sub-task | Sub-task |  | 30 Dec 2025 | Considered in Roadmap & Queued | 2025-12-30 | 2025-12-30 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-170 | [5 empty] | 2026-02-09T11:54:10.424+0500 | 2026-02-22T19:47:04.741+0500
RLT | RLT-171 | RLT-171 | Sub-task | Sub-task |  | 31 Dec 2025 | Considered in Roadmap & Queued | 2025-12-31 | 2025-12-31 |  |  | 0 | 0 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-171 | [5 empty] | 2026-02-09T11:54:15.720+0500 | 2026-02-22T19:46:46.110+0500
RLT | RLT-172 | RLT-172 | Sub-task | Sub-task |  | Maternity Leaves 1 Jan - 31 March 2026 | Considered in Roadmap & Queued | 2026-01-01 | 2026-03-31 | 2026-01-01 | 2026-03-01 | 528 | 528 | Maria Sharafat | 528 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-172 | [5 empty] | 2026-02-09T11:55:01.825+0500 | 2026-02-22T19:46:43.796+0500
RLT | RLT-173 | RLT-173 | Sub-task | Sub-task |  | Annual Leaves 1 April - 30 April 2026 | Considered in Roadmap & Queued | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-01 | 176 | 176 | Maria Sharafat | 176 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-173 | [5 empty] | 2026-02-09T11:55:23.395+0500 | 2026-03-04T09:37:51.939+0500
RLT | RLT-174 | RLT-174 | Sub-task | Sub-task |  | 29 Dec 2025 | Considered in Roadmap & Queued | 2025-12-29 | 2025-12-29 |  |  | 8 | 8 | Maria Sharafat | 8 |  | RLT-8 | RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | https://octopusdtlsupport.atlassian.net/browse/RLT-174 | [5 empty] | 2026-02-09T12:21:00.155+0500 | 2026-03-04T09:37:13.970+0500
RLT | RLT-175 | RLT-175 | Sub-task | Sub-task |  | Planned Leave 2nd March 2026 | Planned Leave | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | RLT-26 | RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-175 | [5 empty] | 2026-02-09T12:35:20.693+0500 | 2026-03-03T12:50:38.421+0500
RLT | RLT-176 | RLT-176 | Sub-task | Sub-task |  | Planned Leave 7th May 2026 | Planned Leave | 2026-05-07 | 2026-05-07 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | RLT-26 | RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-176 | [5 empty] | 2026-02-09T12:37:43.185+0500 | 2026-05-05T14:16:59.354+0500
RLT | RLT-177 | RLT-177 | Sub-task | Sub-task |  | 6 February 2026 | Annual Leave | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-177 | [5 empty] | 2026-02-09T19:00:42.160+0500 | 2026-03-02T13:41:27.375+0500
RLT | RLT-178 | RLT-178 | Sub-task | Sub-task |  | planned leave | Considered in Roadmap & Queued |  |  | 2026-01-31 | 2026-01-31 | 8 | 8 | awais akhter | 8 |  | RLT-6 | RLT-6 | https://octopusdtlsupport.atlassian.net/browse/RLT-6 | https://octopusdtlsupport.atlassian.net/browse/RLT-178 | [5 empty] | 2026-02-10T11:06:49.183+0500 | 2026-02-10T11:08:07.100+0500
RLT | RLT-179 | RLT-179 | Sub-task | Sub-task |  | Leave - Febuary 9, 2026 | Considered in Roadmap & Queued | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Taimur Zahid | 8 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-179 | [5 empty] | 2026-02-10T11:39:49.036+0500 | 2026-03-03T10:59:48.962+0500
RLT | RLT-180 | RLT-180 | Sub-task | Sub-task |  | Unplanned Leave (29 January 2026) | Considered in Roadmap & Queued | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 0 | 0 | awais akhter | 8 |  | RLT-37 | RLT-37 | https://octopusdtlsupport.atlassian.net/browse/RLT-37 | https://octopusdtlsupport.atlassian.net/browse/RLT-180 | [5 empty] | 2026-02-10T12:40:15.418+0500 | 2026-02-10T12:41:36.559+0500
RLT | RLT-181 | RLT-181 | Sub-task | Sub-task |  | 9 February 2026 | Sick Leave | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-181 | [5 empty] | 2026-02-11T10:36:03.415+0500 | 2026-02-23T13:41:38.922+0500
RLT | RLT-182 | RLT-182 | Sub-task | Sub-task |  | Leave for one day 07-01-26 | Resolved! |  |  | 2026-01-07 | 2026-01-07 | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-182 | [5 empty] | 2026-02-11T17:17:28.509+0500 | 2026-04-08T14:28:51.583+0500
RLT | RLT-183 | RLT-183 | Task | Task |  | Leaves Hamza Ali | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Hamza Ali | 48 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | [5 empty] | 2026-02-11T17:46:49.894+0500 | 2026-02-11T17:49:53.512+0500
RLT | RLT-184 | RLT-184 | Sub-task | Sub-task |  | Planned Leave 12-01-2026 | Considered in Roadmap & Queued |  |  | 2026-01-12 | 2026-01-12 | 0 | 0 | awais akhter | 8 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-184 | [5 empty] | 2026-02-11T17:51:13.598+0500 | 2026-02-11T17:52:18.566+0500
RLT | RLT-185 | RLT-185 | Sub-task | Sub-task |  | Planned Leave 13-01-2026 | Considered in Roadmap & Queued |  |  | 2026-01-13 | 2026-01-13 | 0 | 0 | awais akhter | 8 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-185 | [5 empty] | 2026-02-11T17:51:25.960+0500 | 2026-02-11T17:52:49.143+0500
RLT | RLT-186 | RLT-186 | Sub-task | Sub-task |  | Unplanned Leave 26-01-2026 | Considered in Roadmap & Queued |  |  | 2026-01-26 | 2026-01-26 | 0 | 0 | awais akhter | 8 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-186 | [5 empty] | 2026-02-11T17:52:01.866+0500 | 2026-02-11T17:53:12.428+0500
RLT | RLT-187 | RLT-187 | Sub-task | Sub-task |  | Annual leave 13 Jan 2026 | Annual Leave |  |  | 2026-01-13 | 2026-01-13 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-187 | [5 empty] | 2026-02-11T17:52:49.800+0500 | 2026-02-11T17:53:31.947+0500
RLT | RLT-188 | RLT-188 | Sub-task | Sub-task |  | Annual Leaves | Considered in Roadmap & Queued |  |  | 2026-01-01 | 2026-01-09 | 0 | 0 | Muhammad Usman Javed | 56 |  | RLT-22 | RLT-22 | https://octopusdtlsupport.atlassian.net/browse/RLT-22 | https://octopusdtlsupport.atlassian.net/browse/RLT-188 | [5 empty] | 2026-02-12T11:42:39.205+0500 | 2026-02-20T16:33:09.305+0500
RLT | RLT-189 | RLT-189 | Sub-task | Sub-task |  | Casual & Sick Leaves | Considered in Roadmap & Queued |  |  | 2026-03-03 | 2026-03-03 | 0 | 0 | Muhammad Usman Javed | 8 |  | RLT-22 | RLT-22 | https://octopusdtlsupport.atlassian.net/browse/RLT-22 | https://octopusdtlsupport.atlassian.net/browse/RLT-189 | [5 empty] | 2026-02-12T11:42:51.061+0500 | 2026-03-05T11:18:36.551+0500
RLT | RLT-190 | RLT-190 | Sub-task | Sub-task |  | Leave for one day 13-02-26 | Resolved! |  |  | 2026-02-13 | 2026-02-13 | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-190 | [5 empty] | 2026-02-16T09:46:44.663+0500 | 2026-04-08T14:30:05.863+0500
RLT | RLT-191 | RLT-191 | Sub-task | Sub-task |  | Sick Leave | Sick Leave | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | Faiza Nasir | 8 |  | RLT-13 | RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-191 | [5 empty] | 2026-02-18T11:05:20.730+0500 | 2026-03-02T13:49:52.860+0500
RLT | RLT-192 | RLT-192 | Sub-task | Sub-task |  | Casual Leave 16 Feb 2026 | Resolved! |  |  | 2026-02-16 | 2026-02-16 | 8 | 8 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-192 | [5 empty] | 2026-02-20T16:56:22.031+0500 | 2026-03-09T13:34:46.951+0500
RLT | RLT-193 | RLT-193 | Sub-task | Sub-task |  | 23 February 2026 | Sick Leave | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-193 | [5 empty] | 2026-02-24T23:32:38.182+0500 | 2026-02-26T16:19:42.006+0500
RLT | RLT-194 | RLT-194 | Sub-task | Sub-task |  | Unplanned Leave 19-02-2026 | Sick Leave | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 8 | 8 | Hamza Ali | 8 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-194 | [5 empty] | 2026-02-25T16:00:55.915+0500 | 2026-03-12T13:09:15.420+0500
RLT | RLT-195 | RLT-195 | Sub-task | Sub-task |  | Sick Leave 23 Feb 2026 | Sick Leave | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 8 | 8 | Muhammad Abdullah | 6.5 |  | RLT-32 | RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-195 | [5 empty] | 2026-02-26T09:20:17.518+0500 | 2026-03-02T13:42:46.034+0500
RLT | RLT-196 | RLT-196 | Sub-task | Sub-task |  | 25 February 2026 | Sick Leave | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-196 | [5 empty] | 2026-02-26T16:16:29.891+0500 | 2026-02-26T16:18:34.222+0500
RLT | RLT-197 | RLT-197 | Sub-task | Sub-task |  | Leave - March 2, 2026 | Sick Leave | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5 | 6.5 | Taimur Zahid | 6.5 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-197 | [5 empty] | 2026-03-03T10:33:33.251+0500 | 2026-03-12T12:32:46.909+0500
RLT | RLT-198 | RLT-198 | Sub-task | Sub-task |  | Leave 23rd Feb | Sick Leave | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 6.5 | 6.5 | Sarmad Sabir | 6.5 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-198 | [5 empty] | 2026-03-04T12:34:22.063+0500 | 2026-03-04T13:06:26.598+0500
RLT | RLT-199 | RLT-199 | Sub-task | Sub-task |  | Kashmir Day 5th Feb | Resolved! | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 8 | 8 | Sarmad Sabir | 8 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-199 | [5 empty] | 2026-03-04T12:36:10.764+0500 | 2026-03-10T10:08:02.041+0500
RLT | RLT-200 | RLT-200 | Sub-task | Sub-task |  | Leave Jan 5th | Sick Leave | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 8 | 8 | Sarmad Sabir | 8 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-200 | [5 empty] | 2026-03-04T13:06:00.903+0500 | 2026-03-04T13:13:14.287+0500
RLT | RLT-201 | RLT-201 | Sub-task | Sub-task |  | Leave Jan 26th | Sick Leave | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 8 | 8 | Sarmad Sabir | 8 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-201 | [5 empty] | 2026-03-04T13:06:07.832+0500 | 2026-03-04T13:23:55.452+0500
RLT | RLT-202 | RLT-202 | Sub-task | Sub-task |  | Sick Leave- 4th March 2026 | Sick Leave | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8 | 8 | Hassan Malik | 8 |  | RLT-40 | RLT-40 | https://octopusdtlsupport.atlassian.net/browse/RLT-40 | https://octopusdtlsupport.atlassian.net/browse/RLT-202 | [5 empty] | 2026-03-05T12:40:13.046+0500 | 2026-03-05T12:42:07.496+0500
RLT | RLT-203 | RLT-203 | Sub-task | Sub-task |  | Casual Leave 6 march 2026 | Resolved! |  |  | 2026-03-06 | 2026-03-06 | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-203 | [5 empty] | 2026-03-07T13:23:02.827+0500 | 2026-05-12T14:28:43.119+0500
RLT | RLT-204 | RLT-204 | Sub-task | Sub-task |  | Sick leave for one day 06-03-26 | Resolved! |  |  | 2026-03-06 | 2026-03-06 | 0 | 0 | Zeeshan Sarwar | 6.5 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-204 | [5 empty] | 2026-03-09T09:46:03.515+0500 | 2026-04-08T14:30:09.242+0500
RLT | RLT-205 | RLT-205 | Sub-task | Sub-task |  | Leave 9th March | Sick Leave | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5 | 6.5 | Sarmad Sabir | 6.5 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-205 | [5 empty] | 2026-03-10T13:38:27.645+0500 | 2026-03-10T13:39:41.130+0500
RLT | RLT-206 | RLT-206 | Task | Task |  | Leaves Muhammad Zeeshan Aslam | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Zeeshan Aslam | 248 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | [5 empty] | 2026-03-12T12:29:31.532+0500 | 2026-04-08T12:10:16.014+0500
RLT | RLT-207 | RLT-207 | Sub-task | Sub-task |  | 16-02-2026 | Sick Leave | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | RLT-206 | RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-207 | [5 empty] | 2026-03-12T12:30:10.770+0500 | 2026-03-12T13:26:44.034+0500
RLT | RLT-208 | RLT-208 | Sub-task | Sub-task |  | 4th March compassionate leave | Emergency Leave | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-208 | [5 empty] | 2026-03-12T14:24:19.854+0500 | 2026-03-12T14:29:23.083+0500
RLT | RLT-209 | RLT-209 | Sub-task | Sub-task |  | 5th March compassionate leave | Emergency Leave | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-209 | [5 empty] | 2026-03-12T14:24:37.074+0500 | 2026-03-12T14:29:13.987+0500
RLT | RLT-210 | RLT-210 | Sub-task | Sub-task |  | 6th March compassionate leave | Emergency Leave | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-210 | [5 empty] | 2026-03-12T14:24:43.659+0500 | 2026-03-12T14:29:56.966+0500
RLT | RLT-211 | RLT-211 | Sub-task | Sub-task |  | 10th March compassionate leave | Emergency Leave | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 8 | 8 | Ameer Hamza Khan | 8 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-211 | [5 empty] | 2026-03-12T14:24:50.835+0500 | 2026-03-12T14:30:21.379+0500
RLT | RLT-212 | RLT-212 | Sub-task | Sub-task |  | Leave for one day 13-03-26 | Resolved! |  |  | 2026-03-13 | 2026-03-13 | 0 | 0 | Zeeshan Sarwar | 6.5 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-212 | [5 empty] | 2026-03-16T10:13:38.671+0500 | 2026-03-16T10:14:56.283+0500
RLT | RLT-213 | RLT-213 | Sub-task | Sub-task |  | Sick Leaves | Considered in Roadmap & Queued |  |  | 2026-02-16 | 2026-05-06 | 0 | 0 | Faiq Butt | 24 |  | RLT-92 | RLT-92 | https://octopusdtlsupport.atlassian.net/browse/RLT-92 | https://octopusdtlsupport.atlassian.net/browse/RLT-213 | [5 empty] | 2026-03-16T10:25:09.006+0500 | 2026-05-11T09:49:24.135+0500
RLT | RLT-214 | RLT-214 | Sub-task | Sub-task |  | Annual Leaves | Considered in Roadmap & Queued |  |  | 2026-03-09 | 2026-03-09 | 0 | 0 | Faiq Butt | 32 |  | RLT-92 | RLT-92 | https://octopusdtlsupport.atlassian.net/browse/RLT-92 | https://octopusdtlsupport.atlassian.net/browse/RLT-214 | [5 empty] | 2026-03-16T10:25:46.061+0500 | 2026-04-10T09:48:13.273+0500
RLT | RLT-215 | RLT-215 | Sub-task | Sub-task |  | Compassionate Leaves | Considered in Roadmap & Queued |  |  | 2026-02-17 | 2026-03-03 | 0 | 0 | Faiq Butt | 32 |  | RLT-92 | RLT-92 | https://octopusdtlsupport.atlassian.net/browse/RLT-92 | https://octopusdtlsupport.atlassian.net/browse/RLT-215 | [5 empty] | 2026-03-16T10:26:02.317+0500 | 2026-04-10T09:48:16.109+0500
RLT | RLT-216 | RLT-216 | Sub-task | Sub-task |  | Leave - March 16, 2026 | Sick Leave |  |  | 2026-03-16 | 2026-03-16 | 6.5 | 6.5 | Taimur Zahid | 6.5 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-216 | [5 empty] | 2026-03-17T14:30:47.138+0500 | 2026-03-17T14:31:21.119+0500
RLT | RLT-217 | RLT-217 | Sub-task | Sub-task |  | Casual Leave 17 March 2026 | Sick Leave | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 4 | 4 | Muhammad Abdullah | 6.5 |  | RLT-32 | RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-217 | [5 empty] | 2026-03-18T09:18:48.663+0500 | 2026-04-15T15:10:06.149+0500
RLT | RLT-218 | RLT-218 | Sub-task | Sub-task |  | Sick Leave March 16, 2026 | Sick Leave | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5 | 6.5 | Arsalan Zafar Khan | 6.5 |  | RLT-11 | RLT-11 | https://octopusdtlsupport.atlassian.net/browse/RLT-11 | https://octopusdtlsupport.atlassian.net/browse/RLT-218 | [5 empty] | 2026-03-18T09:24:00.476+0500 | 2026-03-18T09:28:18.821+0500
RLT | RLT-219 | RLT-219 | Sub-task | Sub-task |  | Leave - March 24, 2026 | Sick Leave | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Taimur Zahid | 8 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-219 | [5 empty] | 2026-03-25T15:18:55.401+0500 | 2026-03-25T15:19:42.879+0500
RLT | RLT-22 | RLT-22 | Task | Task |  | Leaves Muhammad Usman Javed | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Usman Javed | 88 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-22 | [5 empty] | 2024-05-08T18:51:44.092+0500 | 2025-10-10T10:33:09.243+0500
RLT | RLT-220 | RLT-220 | Sub-task | Sub-task |  | Planned Leave 15th Apr 2026 | Sick Leave | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8 | 8 | Muhammad Imran Aslam | 8 |  | RLT-26 | RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-220 | [5 empty] | 2026-03-26T12:12:31.418+0500 | 2026-04-16T12:05:17.242+0500
RLT | RLT-221 | RLT-221 | Sub-task | Sub-task |  | Hajj Leaves - 4 May to 26 May | Annual Leave | 2026-05-04 | 2026-05-26 |  |  | 136 | 136 | Faiza Nasir | 0 |  | RLT-13 | RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-221 | [5 empty] | 2026-03-26T14:33:48.333+0500 | 2026-04-14T17:15:08.983+0500
RLT | RLT-222 | RLT-222 | Sub-task | Sub-task |  | Hajj Leaves - 1 June to 19 June | Annual Leave | 2026-06-01 | 2026-06-19 |  |  | 120 | 120 | Faiza Nasir | 0 |  | RLT-13 | RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-222 | [5 empty] | 2026-03-26T15:39:14.675+0500 | 2026-04-15T10:56:01.611+0500
RLT | RLT-223 | RLT-223 | Sub-task | Sub-task |  | Unplanned Leaves 25th,26th march 2026 | Emergency Leave |  |  | 2026-03-25 | 2026-03-26 | 0 | 0 | Hassan Saeed Wattoo | 16 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-223 | [5 empty] | 2026-03-26T19:29:29.673+0500 | 2026-03-26T19:30:10.326+0500
RLT | RLT-224 | RLT-224 | Sub-task | Sub-task |  | Leave for one day 27-03-26 | Resolved! |  |  | 2026-03-27 | 2026-03-27 | 0 | 0 | Hassan Malik | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-224 | [5 empty] | 2026-03-30T09:52:29.268+0500 | 2026-03-30T09:53:02.525+0500
RLT | RLT-225 | RLT-225 | Sub-task | Sub-task |  | Annual Leave 31-03-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-225 | [5 empty] | 2026-03-30T13:58:12.699+0500 | 2026-03-30T14:02:58.092+0500
RLT | RLT-226 | RLT-226 | Sub-task | Sub-task |  | Annual Leave 01-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-226 | [5 empty] | 2026-03-30T13:58:38.186+0500 | 2026-03-30T14:03:43.217+0500
RLT | RLT-227 | RLT-227 | Sub-task | Sub-task |  | Annual Leave 02-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-227 | [5 empty] | 2026-03-30T13:58:53.955+0500 | 2026-03-30T14:03:46.902+0500
RLT | RLT-228 | RLT-228 | Sub-task | Sub-task |  | Annual Leave 03-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-228 | [5 empty] | 2026-03-30T13:59:18.689+0500 | 2026-03-30T14:03:50.076+0500
RLT | RLT-229 | RLT-229 | Sub-task | Sub-task |  | Annual Leave 06-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-229 | [5 empty] | 2026-03-30T13:59:49.840+0500 | 2026-03-30T14:03:54.734+0500
RLT | RLT-23 | RLT-23 | Task | Task |  | Leaves Ameer Hamza Khan | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Ameer Hamza Khan | 104 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | [5 empty] | 2024-05-08T18:51:54.040+0500 | 2024-05-08T18:57:00.366+0500
RLT | RLT-230 | RLT-230 | Sub-task | Sub-task |  | Annual Leave 07-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-230 | [5 empty] | 2026-03-30T14:00:00.812+0500 | 2026-03-30T14:03:58.226+0500
RLT | RLT-231 | RLT-231 | Sub-task | Sub-task |  | Annual Leave 08-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-231 | [5 empty] | 2026-03-30T14:00:10.270+0500 | 2026-03-30T14:04:01.192+0500
RLT | RLT-232 | RLT-232 | Sub-task | Sub-task |  | Annual Leave 09-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-232 | [5 empty] | 2026-03-30T14:00:19.416+0500 | 2026-03-30T14:04:04.269+0500
RLT | RLT-233 | RLT-233 | Sub-task | Sub-task |  | Annual Leave 10-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-233 | [5 empty] | 2026-03-30T14:00:32.846+0500 | 2026-03-30T14:04:06.632+0500
RLT | RLT-234 | RLT-234 | Sub-task | Sub-task |  | Annual Leave 13-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-234 | [5 empty] | 2026-03-30T14:00:51.764+0500 | 2026-03-30T14:04:09.962+0500
RLT | RLT-235 | RLT-235 | Sub-task | Sub-task |  | Annual Leave 14-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-235 | [5 empty] | 2026-03-30T14:01:00.500+0500 | 2026-03-30T14:04:13.019+0500
RLT | RLT-236 | RLT-236 | Sub-task | Sub-task |  | Annual Leave 15-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-236 | [5 empty] | 2026-03-30T14:01:12.839+0500 | 2026-03-30T14:04:17.947+0500
RLT | RLT-237 | RLT-237 | Sub-task | Sub-task |  | Annual Leave 16-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-237 | [5 empty] | 2026-03-30T14:01:36.891+0500 | 2026-03-30T14:04:20.627+0500
RLT | RLT-238 | RLT-238 | Sub-task | Sub-task |  | Annual Leave 17-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-238 | [5 empty] | 2026-03-30T14:01:46.313+0500 | 2026-03-30T14:04:23.699+0500
RLT | RLT-239 | RLT-239 | Sub-task | Sub-task |  | Annual Leave 20-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-239 | [5 empty] | 2026-03-30T14:02:10.666+0500 | 2026-03-30T14:04:26.556+0500
RLT | RLT-240 | RLT-240 | Sub-task | Sub-task |  | Annual Leave 21-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-240 | [5 empty] | 2026-03-30T14:02:22.109+0500 | 2026-03-30T14:04:29.337+0500
RLT | RLT-241 | RLT-241 | Sub-task | Sub-task |  | Annual Leave 22-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-241 | [5 empty] | 2026-03-30T14:02:30.892+0500 | 2026-03-30T14:04:32.290+0500
RLT | RLT-242 | RLT-242 | Sub-task | Sub-task |  | Annual Leave 23-04-26 | Annual Leave |  |  |  |  | 0 | 0 | Hassan Malik | 0 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-242 | [5 empty] | 2026-03-30T14:02:38.994+0500 | 2026-03-30T14:04:34.724+0500
RLT | RLT-243 | RLT-243 | Sub-task | Sub-task |  | Leave - March 26, 2026 | Annual Leave | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8 | 8 | Taimur Zahid | 8 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-243 | [5 empty] | 2026-03-30T16:37:30.587+0500 | 2026-03-30T16:38:25.565+0500
RLT | RLT-244 | RLT-244 | Sub-task | Sub-task |  | Leave - March 27, 2026 | Annual Leave | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | Taimur Zahid | 8 |  | RLT-118 | RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-118 | https://octopusdtlsupport.atlassian.net/browse/RLT-244 | [5 empty] | 2026-03-30T16:37:34.271+0500 | 2026-03-30T16:38:53.931+0500
RLT | RLT-245 | RLT-245 | Sub-task | Sub-task |  | Unplanned Leave 24-03-2026 | Annual Leave |  |  | 2026-03-24 | 2026-03-24 | 8 | 8 | Hamza Ali | 8 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-245 | [5 empty] | 2026-03-31T15:35:44.636+0500 | 2026-04-09T10:32:10.011+0500
RLT | RLT-246 | RLT-246 | Sub-task | Sub-task |  | Casual/Sick Leaves (March) | Considered in Roadmap & Queued |  |  | 2026-03-31 | 2026-03-31 | 0 | 0 | Hassan Malik | 8 |  | RLT-91 | RLT-91 | https://octopusdtlsupport.atlassian.net/browse/RLT-91 | https://octopusdtlsupport.atlassian.net/browse/RLT-246 | [5 empty] | 2026-04-01T09:35:48.073+0500 | 2026-04-01T09:36:09.224+0500
RLT | RLT-247 | RLT-247 | Sub-task | Sub-task |  | Sick Leave 30th March | Sick Leave | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 8 | 8 | Sarmad Sabir | 8 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-247 | [5 empty] | 2026-04-01T09:59:23.701+0500 | 2026-04-01T10:00:53.041+0500
RLT | RLT-248 | RLT-248 | Sub-task | Sub-task |  | Sick Leave 31st March | Sick Leave | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8 | 8 | Sarmad Sabir | 8 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-248 | [5 empty] | 2026-04-01T09:59:35.330+0500 | 2026-04-01T10:01:06.003+0500
RLT | RLT-249 | RLT-249 | Sub-task | Sub-task |  | 24-March-2026 | Considered in Roadmap & Queued | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Namra Zahid | 8 |  | RLT-15 | RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-249 | [5 empty] | 2026-04-01T11:04:10.369+0500 | 2026-04-02T12:55:08.834+0500
RLT | RLT-250 | RLT-250 | Sub-task | Sub-task |  | 25-March-2026 | Considered in Roadmap & Queued | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8 | 8 | Namra Zahid | 8 |  | RLT-15 | RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-250 | [5 empty] | 2026-04-01T11:04:28.726+0500 | 2026-04-02T12:55:05.634+0500
RLT | RLT-251 | RLT-251 | Sub-task | Sub-task |  | 26-March-2026 | Considered in Roadmap & Queued | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 8 | 8 | Namra Zahid | 8 |  | RLT-15 | RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-251 | [5 empty] | 2026-04-01T11:04:49.248+0500 | 2026-04-02T16:12:11.603+0500
RLT | RLT-252 | RLT-252 | Sub-task | Sub-task |  | 27-March-2026 | Considered in Roadmap & Queued | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | Namra Zahid | 8 |  | RLT-15 | RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-252 | [5 empty] | 2026-04-01T11:05:02.410+0500 | 2026-04-02T12:54:58.392+0500
RLT | RLT-253 | RLT-253 | Sub-task | Sub-task |  | 30-March-2026 | Considered in Roadmap & Queued | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8 | 8 | Namra Zahid | 8 |  | RLT-15 | RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-15 | https://octopusdtlsupport.atlassian.net/browse/RLT-253 | [5 empty] | 2026-04-01T11:05:53.099+0500 | 2026-04-02T12:55:01.858+0500
RLT | RLT-254 | RLT-254 | Sub-task | Sub-task |  | 30 March 2026 | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-254 | [5 empty] | 2026-04-02T09:50:44.669+0500 | 2026-04-06T13:46:48.048+0500
RLT | RLT-255 | RLT-255 | Sub-task | Sub-task |  | 31 March 2026 | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-255 | [5 empty] | 2026-04-02T09:50:54.090+0500 | 2026-04-06T13:46:56.783+0500
RLT | RLT-256 | RLT-256 | Sub-task | Sub-task |  | 3 April 2026 | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8 | 8 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-256 | [5 empty] | 2026-04-02T09:51:57.729+0500 | 2026-04-06T13:47:06.055+0500
RLT | RLT-257 | RLT-257 | Sub-task | Sub-task |  | Sick Leave April | Sick Leave | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Mariam Zulfiqar | 8 |  | RLT-34 | RLT-34 | https://octopusdtlsupport.atlassian.net/browse/RLT-34 | https://octopusdtlsupport.atlassian.net/browse/RLT-257 | [5 empty] | 2026-04-02T14:24:10.979+0500 | 2026-05-06T13:01:51.344+0500
RLT | RLT-258 | RLT-258 | Sub-task | Sub-task |  | Annual Leaves April | Annual Leave | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-13 | 16 | 16 | Mariam Zulfiqar | 16 |  | RLT-34 | RLT-34 | https://octopusdtlsupport.atlassian.net/browse/RLT-34 | https://octopusdtlsupport.atlassian.net/browse/RLT-258 | [5 empty] | 2026-04-02T14:28:05.620+0500 | 2026-05-06T13:01:42.202+0500
RLT | RLT-259 | RLT-259 | Sub-task | Sub-task |  | Annual Leaves (April) | Considered in Roadmap & Queued | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-15 | 8 | 8 | Danish Rashid | 8 |  | RLT-91 | RLT-91 | https://octopusdtlsupport.atlassian.net/browse/RLT-91 | https://octopusdtlsupport.atlassian.net/browse/RLT-259 | [5 empty] | 2026-04-02T14:33:24.818+0500 | 2026-04-21T09:51:12.960+0500
RLT | RLT-26 | RLT-26 | Task | Task |  | Leaves Muhammad Imran Aslam | Considered in Roadmap & Queued | 2024-06-21 | 2024-06-24 | 2026-01-14 | 2026-01-14 | 0 | 0 | Muhammad Imran Aslam | 398.5 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | [5 empty] | 2024-05-08T18:53:03.678+0500 | 2026-01-16T11:27:25.101+0500
RLT | RLT-260 | RLT-260 | Sub-task | Sub-task |  | Annual Leaves (March) | Considered in Roadmap & Queued | 2026-04-10 | 2026-04-10 |  |  | 8 | 8 | DANIYAL AHMAD | 0 |  | RLT-93 | RLT-93 | https://octopusdtlsupport.atlassian.net/browse/RLT-93 | https://octopusdtlsupport.atlassian.net/browse/RLT-260 | [5 empty] | 2026-04-02T14:35:15.198+0500 | 2026-04-02T14:36:45.224+0500
RLT | RLT-261 | RLT-261 | Sub-task | Sub-task |  | 11 May 2026 - 30 May 2026 | Planned Leave | 2026-05-11 | 2026-05-26 | 2026-05-11 | 2026-05-26 | 120 | 120 | Muhammad Zeeshan Aslam | 96 |  | RLT-206 | RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-261 | [5 empty] | 2026-04-08T12:11:34.091+0500 | 2026-04-09T11:27:24.401+0500
RLT | RLT-262 | RLT-262 | Sub-task | Sub-task |  | 1 Jun 2026 - 26 Jun 2026 | Planned Leave | 2026-06-01 | 2026-06-26 | 2026-06-01 | 2026-06-23 | 160 | 160 | Muhammad Zeeshan Aslam | 136 |  | RLT-206 | RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-262 | [5 empty] | 2026-04-08T12:15:23.682+0500 | 2026-05-07T11:37:56.388+0500
RLT | RLT-263 | RLT-263 | Sub-task | Sub-task |  | 10 April 2026 | Planned Leave | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8 | 8 | Muhammad Zeeshan Aslam | 8 |  | RLT-206 | RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-206 | https://octopusdtlsupport.atlassian.net/browse/RLT-263 | [5 empty] | 2026-04-08T12:22:55.974+0500 | 2026-04-08T22:32:42.309+0500
RLT | RLT-264 | RLT-264 | Sub-task | Sub-task |  | Unplanned Leave 08-04-2026 | Annual Leave | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 0 | 0 | Hamza Ali | 8 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-264 | [5 empty] | 2026-04-09T10:32:03.404+0500 | 2026-04-09T10:32:51.738+0500
RLT | RLT-265 | RLT-265 | Sub-task | Sub-task |  | 15 April 2026 | Planned Leave | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-265 | [5 empty] | 2026-04-13T10:26:05.111+0500 | 2026-04-13T10:31:10.655+0500
RLT | RLT-266 | RLT-266 | Sub-task | Sub-task |  | 16 April 2026 | Planned Leave | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-266 | [5 empty] | 2026-04-13T10:28:21.751+0500 | 2026-04-13T10:31:12.735+0500
RLT | RLT-267 | RLT-267 | Sub-task | Sub-task |  | 17 April 2026 | Planned Leave | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-267 | [5 empty] | 2026-04-13T10:28:41.068+0500 | 2026-04-13T10:31:14.337+0500
RLT | RLT-268 | RLT-268 | Sub-task | Sub-task |  | 20 April 2026 | Planned Leave | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-268 | [5 empty] | 2026-04-13T10:33:38.088+0500 | 2026-04-13T10:34:40.994+0500
RLT | RLT-269 | RLT-269 | Sub-task | Sub-task |  | 21 April 2026 | Planned Leave | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8 | 8 | Waqar Rasheed | 8 |  | RLT-66 | RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | https://octopusdtlsupport.atlassian.net/browse/RLT-269 | [5 empty] | 2026-04-13T10:33:47.402+0500 | 2026-04-13T10:35:14.974+0500
RLT | RLT-270 | RLT-270 | Sub-task | Sub-task |  | Sick Leave | Sick Leave | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 0 | 0 | Faiza Nasir | 8 |  | RLT-13 | RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-270 | [5 empty] | 2026-04-14T17:13:59.578+0500 | 2026-04-14T17:14:36.683+0500
RLT | RLT-271 | RLT-271 | Sub-task | Sub-task |  | Casual Leave 13 April 2026 | Resolved! | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8 | 8 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-271 | [5 empty] | 2026-04-15T10:06:15.017+0500 | 2026-05-12T15:15:11.651+0500
RLT | RLT-272 | RLT-272 | Sub-task | Sub-task |  | Casual Leave 9 April 2026 | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 3 | 3 | Muhammad Abdullah | 3 |  | RLT-32 | RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | https://octopusdtlsupport.atlassian.net/browse/RLT-272 | [5 empty] | 2026-04-15T15:13:08.689+0500 | 2026-04-15T15:16:35.632+0500
RLT | RLT-273 | RLT-273 | Sub-task | Sub-task |  | 10th April 2026 | Sick Leave | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-273 | [5 empty] | 2026-04-16T11:52:50.782+0500 | 2026-04-17T11:12:59.589+0500
RLT | RLT-274 | RLT-274 | Sub-task | Sub-task |  | 13th April 2026 | Sick Leave | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | RLT-134 | RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-134 | https://octopusdtlsupport.atlassian.net/browse/RLT-274 | [5 empty] | 2026-04-17T11:13:29.616+0500 | 2026-04-17T11:14:50.360+0500
RLT | RLT-275 | RLT-275 | Sub-task | Sub-task |  | Annual Leaves 23rd April till 30th march | Annual Leave | 2026-04-23 | 2026-04-30 | 2026-04-23 | 2026-04-30 | 48 | 48 | Hassan Saeed Wattoo | 48 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-275 | [5 empty] | 2026-04-20T11:26:10.792+0500 | 2026-04-22T16:10:15.924+0500
RLT | RLT-276 | RLT-276 | Sub-task | Sub-task |  | Casual Leaves (April) | Considered in Roadmap & Queued |  |  | 2026-04-10 | 2026-04-16 | 0 | 0 | DANIYAL AHMAD | 16 |  | RLT-93 | RLT-93 | https://octopusdtlsupport.atlassian.net/browse/RLT-93 | https://octopusdtlsupport.atlassian.net/browse/RLT-276 | [5 empty] | 2026-04-21T09:44:28.016+0500 | 2026-04-21T09:45:03.513+0500
RLT | RLT-277 | RLT-277 | Sub-task | Sub-task |  | Casual Leave 21 April 2026 | Resolved! | 2026-05-21 | 2026-05-21 | 2026-04-21 | 2026-04-21 | 8 | 8 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-277 | [5 empty] | 2026-04-23T10:05:29.769+0500 | 2026-05-12T15:19:05.189+0500
RLT | RLT-278 | RLT-278 | Sub-task | Sub-task |  | Casual Leave 22 April 2026 | Resolved! | 2026-05-22 | 2026-05-22 | 2026-04-22 | 2026-04-22 | 8 | 8 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-278 | [5 empty] | 2026-04-23T10:06:37.482+0500 | 2026-05-12T15:20:00.388+0500
RLT | RLT-279 | RLT-279 | Sub-task | Sub-task |  | Planned Leave 20th May 2026 | Considered in Roadmap & Queued | 2026-05-20 | 2026-05-20 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | RLT-26 | RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-26 | https://octopusdtlsupport.atlassian.net/browse/RLT-279 | [5 empty] | 2026-04-23T11:41:31.825+0500 | 2026-04-23T11:42:27.323+0500
RLT | RLT-280 | RLT-280 | Sub-task | Sub-task |  | Leave 20th April | Planned Leave | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8 | 8 | Sarmad Sabir | 8 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-280 | [5 empty] | 2026-04-23T14:52:50.741+0500 | 2026-04-23T14:53:43.674+0500
RLT | RLT-281 | RLT-281 | Sub-task | Sub-task |  | Leave 21st April | Planned Leave | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8 | 8 | Sarmad Sabir | 8 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-281 | [5 empty] | 2026-04-23T14:52:59.840+0500 | 2026-04-23T14:54:02.519+0500
RLT | RLT-282 | RLT-282 | Sub-task | Sub-task |  | 4 April 2026 - 8 April 2026 | Resolved! | 2026-05-04 | 2026-05-08 | 2026-04-24 | 2026-05-08 | 40 | 40 | Hassan Malik | 40 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-282 | [5 empty] | 2026-04-24T09:29:02.479+0500 | 2026-04-24T09:32:27.712+0500
RLT | RLT-283 | RLT-283 | Sub-task | Sub-task |  | Traveling out of town to attend a marriage ceremony | Planned Leave | 2026-04-22 | 2026-04-24 | 2026-04-22 | 2026-04-24 | 24 | 24 | Ameer Hamza Khan | 24 |  | RLT-23 | RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-23 | https://octopusdtlsupport.atlassian.net/browse/RLT-283 | [5 empty] | 2026-04-27T08:54:09.670+0500 | 2026-04-27T08:55:46.313+0500
RLT | RLT-284 | RLT-284 | Sub-task | Sub-task |  | Planned Leave 11-05-2026 | Annual Leave | 2026-05-11 | 2026-05-11 |  |  | 8 | 8 | Hamza Ali | 0 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-284 | [5 empty] | 2026-04-29T13:09:20.304+0500 | 2026-04-29T13:15:03.412+0500
RLT | RLT-285 | RLT-285 | Sub-task | Sub-task |  | Planned Leave 12-05-2026 | Annual Leave | 2026-05-12 | 2026-05-12 |  |  | 8 | 8 | Hamza Ali | 0 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-285 | [5 empty] | 2026-04-29T13:09:45.016+0500 | 2026-04-29T13:14:51.839+0500
RLT | RLT-286 | RLT-286 | Sub-task | Sub-task |  | Planned Leave 13-05-2026 | Annual Leave | 2026-05-13 | 2026-05-13 |  |  | 8 | 8 | Hamza Ali | 0 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-286 | [5 empty] | 2026-04-29T13:09:51.812+0500 | 2026-04-29T13:14:36.633+0500
RLT | RLT-287 | RLT-287 | Sub-task | Sub-task |  | Planned Leave 14-05-2026 | Annual Leave | 2026-05-14 | 2026-05-14 |  |  | 8 | 8 | Hamza Ali | 0 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-287 | [5 empty] | 2026-04-29T13:10:00.374+0500 | 2026-04-29T13:13:48.354+0500
RLT | RLT-288 | RLT-288 | Sub-task | Sub-task |  | Planned Leave 15-05-2026 | Annual Leave | 2026-05-15 | 2026-05-15 |  |  | 8 | 8 | Hamza Ali | 0 |  | RLT-183 | RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-183 | https://octopusdtlsupport.atlassian.net/browse/RLT-288 | [5 empty] | 2026-04-29T13:10:09.937+0500 | 2026-04-29T13:14:07.919+0500
RLT | RLT-289 | RLT-289 | Sub-task | Sub-task |  | Labour Day | Resolved! |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | RLT-73 | RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | https://octopusdtlsupport.atlassian.net/browse/RLT-289 | [5 empty] | 2026-05-04T10:48:35.207+0500 | 2026-05-04T10:48:57.637+0500
RLT | RLT-290 | RLT-290 | Sub-task | Sub-task |  | Casual Leaves (April) | Considered in Roadmap & Queued | 2026-04-01 | 2026-04-30 | 2026-04-24 | 2026-04-24 | 0 | 0 | Muhammad Abdul Wasi | 4 |  | RLT-94 | RLT-94 | https://octopusdtlsupport.atlassian.net/browse/RLT-94 | https://octopusdtlsupport.atlassian.net/browse/RLT-290 | [5 empty] | 2026-05-04T12:07:25.358+0500 | 2026-05-04T14:04:02.609+0500
RLT | RLT-291 | RLT-291 | Sub-task | Sub-task |  | Annual Leaves May | Considered in Roadmap & Queued | 2026-05-18 | 2026-05-20 |  |  | 24 | 24 | Mariam Zulfiqar | 0 |  | RLT-34 | RLT-34 | https://octopusdtlsupport.atlassian.net/browse/RLT-34 | https://octopusdtlsupport.atlassian.net/browse/RLT-291 | [5 empty] | 2026-05-06T13:02:54.544+0500 | 2026-05-06T13:04:22.803+0500
RLT | RLT-32 | RLT-32 | Task | Task |  | Leaves Muhammad Abdullah | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Abdullah | 140 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-32 | [5 empty] | 2024-05-08T18:55:02.907+0500 | 2025-12-26T09:08:15.565+0500
RLT | RLT-34 | RLT-34 | Task | Task |  | Leaves Mariam Zulfiqar | Considered in Roadmap & Queued |  |  | 2026-02-06 | 2026-02-09 | 0 | 0 | Mariam Zulfiqar | 116 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-34 | [5 empty] | 2024-05-08T18:55:30.940+0500 | 2026-02-10T11:08:15.192+0500
RLT | RLT-35 | RLT-35 | Task | Task |  | Leaves Zeeshan | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 191 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | [5 empty] | 2024-05-08T19:00:43.187+0500 | 2025-06-05T09:39:55.532+0500
RLT | RLT-37 | RLT-37 | Task | Task |  | Leaves Usama Tariq | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Usama Tariq | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-37 | [5 empty] | 2024-05-08T19:01:18.965+0500 | 2026-02-11T17:27:43.188+0500
RLT | RLT-39 | RLT-39 | Task | Task |  | Leaves Hassan Saeed Wattoo | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 328 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | [5 empty] | 2024-05-08T19:01:39.139+0500 | 2024-05-15T13:17:27.089+0500
RLT | RLT-4 | RLT-4 | Task | Task |  | Leaves Usama Tahir | Planned Leave | 2024-04-29 | 2024-04-30 |  |  | 0 | 0 | Danish Rashid | 16 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-4 | [5 empty] | 2024-04-25T12:08:21.289+0500 | 2026-01-22T14:54:11.730+0500
RLT | RLT-40 | RLT-40 | Task | Task |  | Leaves Yousaf Qadri | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Syed Yousaf Qadri | 80 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-40 | [5 empty] | 2024-05-08T19:01:47.689+0500 | 2026-03-05T12:39:36.053+0500
RLT | RLT-41 | RLT-41 | Task | Task |  | Leaves Nadeem Ahmad Khan | Considered in Roadmap & Queued |  |  | 2026-01-08 | 2026-03-25 | 0 | 0 | nadeem ahmed | 176.13 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-41 | [5 empty] | 2024-05-08T19:02:12.383+0500 | 2026-03-27T17:29:07.623+0500
RLT | RLT-42 | RLT-42 | Task | Task |  | Leaves Ahad Omer | Considered in Roadmap & Queued |  |  | 2026-01-09 | 2026-04-14 | 0 | 0 | ahad omer | 296 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-42 | [5 empty] | 2024-05-08T19:02:29.669+0500 | 2026-04-20T16:28:29.085+0500
RLT | RLT-43 | RLT-43 | Sub-task | Sub-task |  | Planned Leave 15th May 2024 | Planned Leave | 2024-05-15 | 2024-05-15 |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-43 | [5 empty] | 2024-05-15T13:17:36.997+0500 | 2024-08-16T16:28:48.485+0500
RLT | RLT-44 | RLT-44 | Sub-task | Sub-task |  | Leaves Faiza | Sick Leave | 2024-05-29 | 2024-05-31 |  |  | 0 | 0 | Faiza Nasir | 136 |  | RLT-13 | RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-44 | [5 empty] | 2024-05-27T17:19:47.991+0500 | 2025-12-30T10:15:12.915+0500
RLT | RLT-45 | RLT-45 | Sub-task | Sub-task |  | Leave for one day 05-06-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-45 | [5 empty] | 2024-06-06T09:10:07.974+0500 | 2024-06-06T09:11:39.142+0500
RLT | RLT-46 | RLT-46 | Sub-task | Sub-task |  | Planned Leave 20th June 2024 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-46 | [5 empty] | 2024-06-21T09:20:21.600+0500 | 2024-08-16T16:28:56.168+0500
RLT | RLT-47 | RLT-47 | Sub-task | Sub-task |  | Leave for two days 20 and 21-06-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 16 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-47 | [5 empty] | 2024-06-24T09:18:18.735+0500 | 2024-06-24T09:19:43.343+0500
RLT | RLT-49 | RLT-49 | Sub-task | Sub-task |  | Emergency leave | Considered in Roadmap & Queued | 2024-07-11 |  |  |  | 0 | 0 | Faiza Nasir | 29 |  | RLT-13 | RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-13 | https://octopusdtlsupport.atlassian.net/browse/RLT-49 | [5 empty] | 2024-07-18T11:05:11.868+0500 | 2026-01-29T16:48:09.549+0500
RLT | RLT-5 | RLT-5 | Story | Story |  | Leaves Hassan Malik | Planned Leave |  |  |  |  | 0 | 0 | Hassan Malik | 239 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | [5 empty] | 2024-04-26T09:03:27.177+0500 | 2026-04-24T09:32:26.358+0500
RLT | RLT-50 | RLT-50 | Sub-task | Sub-task |  | Sick leave for one day 22-07-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-50 | [5 empty] | 2024-07-23T09:08:09.289+0500 | 2024-07-23T09:09:17.479+0500
RLT | RLT-52 | RLT-52 | Sub-task | Sub-task |  | Urgent work leave 05-08-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-52 | [5 empty] | 2024-08-06T09:08:48.315+0500 | 2024-08-06T09:11:15.823+0500
RLT | RLT-53 | RLT-53 | Sub-task | Sub-task |  | Planned Leave 15th Aug 2024 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-53 | [5 empty] | 2024-08-16T16:28:43.991+0500 | 2024-08-16T16:29:17.981+0500
RLT | RLT-54 | RLT-54 | Sub-task | Sub-task |  | Leave for one day 30-08-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-54 | [5 empty] | 2024-08-28T16:51:09.454+0500 | 2024-09-03T09:15:53.284+0500
RLT | RLT-55 | RLT-55 | Sub-task | Sub-task |  | Leave for one day 02-09-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-55 | [5 empty] | 2024-08-28T16:51:29.824+0500 | 2024-09-03T09:16:12.471+0500
RLT | RLT-56 | RLT-56 | Sub-task | Sub-task |  | Sick leave 28th Aug 2024 | Sick Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-56 | [5 empty] | 2024-09-03T10:03:57.925+0500 | 2024-09-03T10:04:14.562+0500
RLT | RLT-57 | RLT-57 | Sub-task | Sub-task |  | Sick Leave 13th Sept 2024 | Sick Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-57 | [5 empty] | 2024-09-23T11:07:49.200+0500 | 2024-09-23T11:08:09.638+0500
RLT | RLT-58 | RLT-58 | Sub-task | Sub-task |  | Leave for one day 14-11-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-58 | [5 empty] | 2024-11-15T09:25:05.670+0500 | 2024-11-15T09:38:06.205+0500
RLT | RLT-59 | RLT-59 | Sub-task | Sub-task |  | Planned Leave 8th Nov 2024 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 0 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-59 | [5 empty] | 2024-11-21T12:24:36.990+0500 | 2024-12-31T11:38:57.134+0500
RLT | RLT-6 | RLT-6 | Task | Task |  | Leaves Awais Akhter | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | awais akhter | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-6 | [5 empty] | 2024-05-08T16:23:38.977+0500 | 2024-05-08T18:31:23.320+0500
RLT | RLT-60 | RLT-60 | Sub-task | Sub-task |  | Planned Leave 19th Nov 2024 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-60 | [5 empty] | 2024-11-21T12:25:03.206+0500 | 2024-12-31T11:39:07.591+0500
RLT | RLT-61 | RLT-61 | Task | Task |  | Leaves Zain Munir | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Zain Munir | 248 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-61 | [5 empty] | 2024-12-03T16:44:37.982+0500 | 2026-01-29T16:25:03.752+0500
RLT | RLT-62 | RLT-62 | Sub-task | Sub-task |  | Sick leave for one day 30-12-24 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-62 | [5 empty] | 2024-12-31T09:30:13.907+0500 | 2024-12-31T09:30:33.151+0500
RLT | RLT-63 | RLT-63 | Sub-task | Sub-task |  | Planned Leave 29th Nov 2024 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-63 | [5 empty] | 2024-12-31T11:38:18.228+0500 | 2024-12-31T11:39:11.165+0500
RLT | RLT-64 | RLT-64 | Sub-task | Sub-task |  | Planned Leave 16th Dec 2024 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-64 | [5 empty] | 2024-12-31T11:39:25.533+0500 | 2025-03-25T09:09:27.662+0500
RLT | RLT-65 | RLT-65 | Sub-task | Sub-task |  | Annual Leave 23rd Dec, 24th Dec, 26th Dec, 27th Dec | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 32 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-65 | [5 empty] | 2024-12-31T11:40:34.525+0500 | 2025-03-25T09:09:36.616+0500
RLT | RLT-66 | RLT-66 | Task | Task |  | Leaves Waqar Rasheed | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Waqar Rasheed | 184 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-66 | [5 empty] | 2025-01-01T11:29:01.897+0500 | 2026-02-02T15:45:34.646+0500
RLT | RLT-67 | RLT-67 | Sub-task | Sub-task |  | Casual Leave for half day 02-01-25 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 4 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-67 | [5 empty] | 2025-01-06T09:19:42.013+0500 | 2025-01-06T09:21:11.598+0500
RLT | RLT-68 | RLT-68 | Sub-task | Sub-task |  | Leave for one day 03-01-25 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-68 | [5 empty] | 2025-01-06T09:20:06.483+0500 | 2025-01-06T09:21:08.280+0500
RLT | RLT-71 | RLT-71 | Sub-task | Sub-task |  | Leave for one day 27-02-25 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-71 | [5 empty] | 2025-02-28T09:31:26.122+0500 | 2025-02-28T09:31:46.578+0500
RLT | RLT-72 | RLT-72 | Sub-task | Sub-task |  | Annual leave 31 Jan | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-72 | [5 empty] | 2025-03-04T11:51:16.894+0500 | 2025-03-04T11:51:47.087+0500
RLT | RLT-73 | RLT-73 | Task | Task |  | Sarmad Sabir | Considered in Roadmap & Queued |  |  |  |  | 240 | 240 | Unassigned | 181 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-73 | [5 empty] | 2025-03-05T13:22:26.942+0500 | 2026-04-23T14:52:39.477+0500
RLT | RLT-74 | RLT-74 | Sub-task | Sub-task |  | Planned Leave 21st Feb 2025 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-74 | [5 empty] | 2025-03-25T09:09:51.777+0500 | 2025-04-29T14:36:06.523+0500
RLT | RLT-77 | RLT-77 | Sub-task | Sub-task |  | Planned Leave 3rd April 2025 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-77 | [5 empty] | 2025-04-29T14:35:54.729+0500 | 2025-04-29T14:36:21.782+0500
RLT | RLT-78 | RLT-78 | Sub-task | Sub-task |  | Planned Leave 4th April 2025 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-78 | [5 empty] | 2025-04-29T14:36:42.933+0500 | 2025-04-29T14:37:01.596+0500
RLT | RLT-79 | RLT-79 | Sub-task | Sub-task |  | Sick leave | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-79 | [5 empty] | 2025-05-15T10:52:44.037+0500 | 2025-09-11T09:15:11.410+0500
RLT | RLT-8 | RLT-8 | Task | Task |  | Leaves Maria Sharafat | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Maria Sharafat | 808 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-8 | [5 empty] | 2024-05-08T18:48:51.250+0500 | 2026-02-09T11:45:33.360+0500
RLT | RLT-80 | RLT-80 | Sub-task | Sub-task |  | 16 may 2025 | Sick Leave | 2025-05-16 | 2025-05-16 |  |  | 0 | 0 | Hassan Malik | 8 |  | RLT-5 | RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-5 | https://octopusdtlsupport.atlassian.net/browse/RLT-80 | [5 empty] | 2025-05-20T15:48:34.680+0500 | 2025-05-20T15:48:58.959+0500
RLT | RLT-81 | RLT-81 | Sub-task | Sub-task |  | Annual leave 22 May | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-81 | [5 empty] | 2025-05-21T17:45:49.062+0500 | 2025-09-11T09:15:14.892+0500
RLT | RLT-82 | RLT-82 | Sub-task | Sub-task |  | Planned Leave 5th June 2025 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-82 | [5 empty] | 2025-06-10T11:05:56.983+0500 | 2025-09-26T09:55:20.879+0500
RLT | RLT-83 | RLT-83 | Sub-task | Sub-task |  | Annual leave 07 July | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-83 | [5 empty] | 2025-07-07T12:00:55.557+0500 | 2025-09-11T09:15:19.601+0500
RLT | RLT-84 | RLT-84 | Sub-task | Sub-task |  | Casual leave | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 0 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-84 | [5 empty] | 2025-09-11T09:14:17.734+0500 | 2025-09-11T09:15:22.445+0500
RLT | RLT-85 | RLT-85 | Sub-task | Sub-task |  | Casual leave 10 sept 25 | Resolved! |  |  |  |  | 0 | 0 | Muhammad Abbas | 8 |  | RLT-17 | RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-17 | https://octopusdtlsupport.atlassian.net/browse/RLT-85 | [5 empty] | 2025-09-11T09:16:09.033+0500 | 2025-09-11T09:16:45.168+0500
RLT | RLT-86 | RLT-86 | Sub-task | Sub-task |  | Planned Leave 15th July 2025 | Sick Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-86 | [5 empty] | 2025-09-26T09:55:06.810+0500 | 2025-09-26T09:55:30.527+0500
RLT | RLT-87 | RLT-87 | Sub-task | Sub-task |  | Planned 1st Sept 2025 | Sick Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-87 | [5 empty] | 2025-09-26T09:56:28.622+0500 | 2025-09-26T10:05:11.707+0500
RLT | RLT-88 | RLT-88 | Sub-task | Sub-task |  | Planned Leave 15th Aug 2025 | Sick Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-88 | [5 empty] | 2025-09-26T10:05:27.334+0500 | 2025-09-26T10:05:46.408+0500
RLT | RLT-89 | RLT-89 | Sub-task | Sub-task |  | Compassionate Leave 29th Sept, 30th Sept, 1st Oct | Emergency Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 24 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-89 | [5 empty] | 2025-10-08T10:16:40.435+0500 | 2025-11-06T09:37:59.818+0500
RLT | RLT-90 | RLT-90 | Sub-task | Sub-task |  | Planned Leave 5th Nov 2025 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-90 | [5 empty] | 2025-11-06T09:38:11.154+0500 | 2025-12-08T11:30:11.084+0500
RLT | RLT-91 | RLT-91 | Task | Task |  | Leaves Danish Rashid | Considered in Roadmap & Queued |  |  | 2026-01-02 | 2026-01-06 | 0 | 0 | Danish Rashid | 40 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-91 | [5 empty] | 2025-11-07T12:39:43.451+0500 | 2026-01-22T14:56:09.939+0500
RLT | RLT-92 | RLT-92 | Task | Task |  | Leaves Faiq Butt | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Faiq Butt | 88 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-92 | [5 empty] | 2025-11-07T12:40:30.029+0500 | 2026-03-16T10:29:48.653+0500
RLT | RLT-93 | RLT-93 | Task | Task |  | Leaves Daniyal Ahmed | Considered in Roadmap & Queued |  |  | 2026-01-01 | 2026-02-03 | 0 | 0 | DANIYAL AHMAD | 88 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-93 | [5 empty] | 2025-11-07T12:40:44.626+0500 | 2026-04-02T14:36:14.481+0500
RLT | RLT-94 | RLT-94 | Task | Task |  | Leaves Abdul Wasi | Considered in Roadmap & Queued |  |  | 2026-01-01 | 2026-02-17 | 0 | 0 | Muhammad Abdul Wasi | 44 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/RLT-94 | [5 empty] | 2025-11-07T12:41:28.164+0500 | 2026-02-18T11:21:28.198+0500
RLT | RLT-95 | RLT-95 | Sub-task | Sub-task |  | Sick Leave 18th Nov 2025 | Sick Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-95 | [5 empty] | 2025-12-08T11:30:01.035+0500 | 2025-12-08T11:30:30.413+0500
RLT | RLT-96 | RLT-96 | Sub-task | Sub-task |  | Compassionate Leaves 24th Nov, 25th Nov 2025 | Emergency Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 16 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-96 | [5 empty] | 2025-12-08T11:30:53.468+0500 | 2025-12-08T11:31:21.845+0500
RLT | RLT-97 | RLT-97 | Sub-task | Sub-task |  | 3rd Dec 2025 | Planned Leave |  |  |  |  | 0 | 0 | Hassan Saeed Wattoo | 8 |  | RLT-39 | RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-39 | https://octopusdtlsupport.atlassian.net/browse/RLT-97 | [5 empty] | 2025-12-08T11:31:59.693+0500 | 2025-12-08T11:32:24.681+0500
RLT | RLT-99 | RLT-99 | Sub-task | Sub-task |  | Leave for one day 05-12-25 | Resolved! |  |  |  |  | 0 | 0 | Zeeshan Sarwar | 8 |  | RLT-35 | RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-35 | https://octopusdtlsupport.atlassian.net/browse/RLT-99 | [5 empty] | 2025-12-29T12:28:16.268+0500 | 2025-12-29T12:29:46.783+0500
SUBS | SUBS-10 | SUBS-10 | Story | Story |  | Handover | To Do | 2026-02-27 | 2026-02-27 |  |  | 11 | 11 | Ameer Hamza Khan | 13.37 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | [5 empty] | 2026-02-27T10:32:44.487+0500 | 2026-03-25T11:28:19.406+0500
SUBS | SUBS-100 | SUBS-100 | Sub-task | Sub-task |  | Products + Features Frontend, API Modification & Integration | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5 | 6.5 | Zain Munir | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-100 | [5 empty] | 2026-02-20T09:44:16.508+0500 | 2026-03-25T11:29:03.426+0500
SUBS | SUBS-101 | SUBS-101 | Sub-task | Sub-task |  | Account Activation Page UI | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 4 | 4 | Sarmad Sabir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-101 | [5 empty] | 2026-02-20T10:40:42.970+0500 | 2026-03-25T11:29:03.829+0500
SUBS | SUBS-102 | SUBS-102 | Sub-task | Sub-task |  | Account Activation API Integration | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-102 | [5 empty] | 2026-02-20T10:42:59.687+0500 | 2026-03-25T11:29:04.351+0500
SUBS | SUBS-103 | SUBS-103 | Sub-task | Sub-task |  | Super Admin - Plans API Integration | Resolved! | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-02-20 | 6.5 | 6.5 | Sarmad Sabir | 6 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-103 | [5 empty] | 2026-02-20T10:43:39.749+0500 | 2026-03-25T11:29:04.835+0500
SUBS | SUBS-104 | SUBS-104 | Sub-task | Sub-task |  | Super Admin - Tiers API Integration | Resolved! |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-104 | [5 empty] | 2026-02-20T10:44:09.381+0500 | 2026-03-25T11:29:05.567+0500
SUBS | SUBS-105 | SUBS-105 | Sub-task | Sub-task |  | SM Meetings | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 4 | 4 | Sarmad Sabir | 4 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-105 | [5 empty] | 2026-02-20T15:19:02.581+0500 | 2026-03-25T11:29:06.072+0500
SUBS | SUBS-106 | SUBS-106 | Sub-task | Sub-task |  | Config Version Screen + Version Compatibility & APIs Integration | Resolved! | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-02-23 | 16 | 16 | Zain Munir | 14 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-106 | [5 empty] | 2026-02-20T15:32:42.144+0500 | 2026-03-25T11:29:06.515+0500
SUBS | SUBS-107 | SUBS-107 | Sub-task | Sub-task |  | User Managemnet APIs integration | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 2 | 2 | Faiza Nasir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-107 | [5 empty] | 2026-02-20T16:41:45.981+0500 | 2026-03-25T11:29:07.074+0500
SUBS | SUBS-108 | SUBS-108 | Sub-task | Sub-task |  | Plans Tiers API Integration | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-25 | 6 | 6 | Faiza Nasir | 6 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-108 | [5 empty] | 2026-02-20T16:46:01.584+0500 | 2026-03-25T11:29:07.505+0500
SUBS | SUBS-109 | SUBS-109 | Sub-task | Sub-task |  | Overall development team discussions / Coordinations | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-109 | [5 empty] | 2026-02-23T13:56:33.194+0500 | 2026-03-25T11:29:07.960+0500
SUBS | SUBS-11 | SUBS-11 | Story | Story |  | SQA | Resolved! | 2026-03-02 | 2026-03-11 |  |  | 160 | 160 | Muhammad Abbas | 177.5 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | [5 empty] | 2026-02-04T16:24:29.887+0500 | 2026-03-25T11:28:19.875+0500
SUBS | SUBS-110 | SUBS-110 | Sub-task | Sub-task |  | Quotation Understanding + Meetings | Resolved! | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-110 | [5 empty] | 2026-02-23T13:57:53.727+0500 | 2026-03-25T11:29:08.405+0500
SUBS | SUBS-111 | SUBS-111 | Sub-task | Sub-task |  | Qoutations API Logic revision | Resolved! | 2026-02-23 | 2026-02-26 | 2026-02-23 | 2026-02-26 | 13 | 13 | Faiza Nasir | 13 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-111 | [5 empty] | 2026-02-24T09:42:21.298+0500 | 2026-03-25T11:29:08.848+0500
SUBS | SUBS-112 | SUBS-112 | Sub-task | Sub-task |  | Product Information Screen | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 6.5 | 6.5 | Zain Munir | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-112 | [5 empty] | 2026-02-24T15:26:50.909+0500 | 2026-03-25T11:29:09.361+0500
SUBS | SUBS-113 | SUBS-113 | Sub-task | Sub-task |  | Integrated Quotation API + Calculations | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 7.5 | 7.5 | Muhammad Ahmad Saleem | 7.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-113 | [5 empty] | 2026-02-24T23:36:55.061+0500 | 2026-03-25T11:29:09.854+0500
SUBS | SUBS-114 | SUBS-114 | Sub-task | Sub-task |  | Changes with Plans and Tiers APIs | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 5 | 5 | Sarmad Sabir | 4.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-114 | [5 empty] | 2026-02-25T11:21:26.129+0500 | 2026-03-25T11:29:10.314+0500
SUBS | SUBS-115 | SUBS-115 | Sub-task | Sub-task |  | Preview page diagram for Admin | Resolved! | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 4 | 4 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-115 | [5 empty] | 2026-02-25T11:21:45.956+0500 | 2026-03-25T11:29:10.745+0500
SUBS | SUBS-116 | SUBS-116 | Sub-task | Sub-task |  | Integrated Save Quote Api + Modified Calculator | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 6.5 | 6.5 | Zain Munir | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-116 | [5 empty] | 2026-02-26T09:51:12.799+0500 | 2026-03-25T11:29:11.267+0500
SUBS | SUBS-117 | SUBS-117 | Sub-task | Sub-task |  | Audit Logs integration in all modules CRUD operation | Resolved! | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26 | 5 | 5 | Faiza Nasir | 5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-117 | [5 empty] | 2026-02-26T10:07:50.029+0500 | 2026-03-25T11:29:11.730+0500
SUBS | SUBS-118 | SUBS-118 | Sub-task | Sub-task |  | Get Quotes for Sales Person API Integration | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 3 | 3 | Sarmad Sabir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-118 | [5 empty] | 2026-02-26T11:51:54.295+0500 | 2026-03-25T11:29:12.172+0500
SUBS | SUBS-119 | SUBS-119 | Sub-task | Sub-task |  | Redesigned the Login Page | Resolved! | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 1.5 | 1.5 | Sarmad Sabir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-119 | [5 empty] | 2026-02-26T11:53:09.012+0500 | 2026-03-25T11:29:12.680+0500
SUBS | SUBS-12 | SUBS-12 | Story | Story |  | Bug-Fixing | In-Progress | 2026-03-02 | 2026-03-11 |  |  | 0 | 0 | Faiza Nasir | 208.5 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | [5 empty] | 2026-02-27T14:57:02.692+0500 | 2026-03-25T11:28:20.399+0500
SUBS | SUBS-120 | SUBS-120 | Sub-task | Sub-task |  | Flow testing | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-120 | [5 empty] | 2026-02-26T13:14:51.165+0500 | 2026-03-25T11:29:13.116+0500
SUBS | SUBS-121 | SUBS-121 | Sub-task | Sub-task |  | Bug Fix for Tiers Tab (Admin) | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 1 | 1 | Sarmad Sabir | 1 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-121 | [5 empty] | 2026-02-26T15:07:47.465+0500 | 2026-03-25T11:29:13.561+0500
SUBS | SUBS-122 | SUBS-122 | Sub-task | Sub-task |  | Production Deployment | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 1.5 | 1.5 | Sarmad Sabir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-122 | [5 empty] | 2026-02-26T15:08:02.821+0500 | 2026-03-25T11:29:14.040+0500
SUBS | SUBS-123 | SUBS-123 | Sub-task | Sub-task |  | Code Merging, Final Run Down Changes + Handover Session | Resolved! | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-27 | 16 | 16 | Zain Munir | 13 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-123 | [5 empty] | 2026-02-26T15:18:54.966+0500 | 2026-03-25T11:29:14.436+0500
SUBS | SUBS-124 | SUBS-124 | Sub-task | Sub-task |  | Flow Testing + Issue Fixing | Resolved! | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 7.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-124 | [5 empty] | 2026-02-26T16:21:44.811+0500 | 2026-03-25T11:29:14.872+0500
SUBS | SUBS-125 | SUBS-125 | Sub-task | Sub-task |  | Staging Release plus bug fixing on staging | Resolved! | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | 5 | 5 | Sarmad Sabir | 5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-125 | [5 empty] | 2026-03-02T10:07:52.850+0500 | 2026-03-25T11:29:15.304+0500
SUBS | SUBS-126 | SUBS-126 | Sub-task | Sub-task |  | Update Layout for Plans | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2.5 | 2.5 | Sarmad Sabir | 2.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-126 | [5 empty] | 2026-03-03T10:25:37.939+0500 | 2026-03-25T11:29:15.790+0500
SUBS | SUBS-127 | SUBS-127 | Sub-task | Sub-task |  | Pagination across the admin side | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-127 | [5 empty] | 2026-03-03T10:26:14.628+0500 | 2026-03-25T11:29:16.197+0500
SUBS | SUBS-128 | SUBS-128 | Sub-task | Sub-task |  | Bug Fixing before QA | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 1 | 1 | Sarmad Sabir | 1 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-128 | [5 empty] | 2026-03-03T10:26:51.507+0500 | 2026-03-25T11:29:16.598+0500
SUBS | SUBS-129 | SUBS-129 | Sub-task | Sub-task |  | Added View and Export Quotation Functionality | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-129 | [5 empty] | 2026-03-04T10:17:41.357+0500 | 2026-03-25T11:29:17.053+0500
SUBS | SUBS-13 | SUBS-13 | Story | Story |  | Development | Resolved! | 2026-01-09 | 2026-02-23 |  |  | 288 | 288 | Faiza Nasir | 437.28 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | [5 empty] | 2026-01-15T10:52:03.786+0500 | 2026-03-25T11:28:21.186+0500
SUBS | SUBS-130 | SUBS-130 | Sub-task | Sub-task |  | Plans UI + Preview Page UI Fix | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 3 | 3 | Sarmad Sabir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-130 | [5 empty] | 2026-03-04T15:20:28.975+0500 | 2026-03-25T11:29:17.472+0500
SUBS | SUBS-131 | SUBS-131 | Sub-task | Sub-task |  | Activate Account API Fix + Account Activation Screen fallback for staging | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 3.5 | 3.5 | Sarmad Sabir | 3.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-131 | [5 empty] | 2026-03-04T15:21:01.616+0500 | 2026-03-25T11:29:17.901+0500
SUBS | SUBS-132 | SUBS-132 | Sub-task | Sub-task |  | Post Handover feedback Integration Discussions | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2 | 2 | Faiza Nasir | 1.28 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-132 | [5 empty] | 2026-03-04T15:34:38.570+0500 | 2026-03-25T11:29:18.322+0500
SUBS | SUBS-133 | SUBS-133 | Sub-task | Sub-task |  | Account Activation Email | Resolved! | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-133 | [5 empty] | 2026-03-04T15:36:21.848+0500 | 2026-03-25T11:29:18.760+0500
SUBS | SUBS-134 | SUBS-134 | Sub-task | Sub-task |  | Validation for Plans screen | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-134 | [5 empty] | 2026-03-05T14:51:55.838+0500 | 2026-03-25T11:29:19.211+0500
SUBS | SUBS-135 | SUBS-135 | Sub-task | Sub-task |  | Edit tier functionality changed | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 3 | 3 | Sarmad Sabir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-135 | [5 empty] | 2026-03-05T14:52:21.282+0500 | 2026-03-25T11:29:19.617+0500
SUBS | SUBS-136 | SUBS-136 | Sub-task | Sub-task |  | Preparing DL and Fintech Data for Demo | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 1.5 | 1.5 | Sarmad Sabir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-136 | [5 empty] | 2026-03-05T14:53:56.397+0500 | 2026-03-25T11:29:20.035+0500
SUBS | SUBS-137 | SUBS-137 | Sub-task | Sub-task |  | Added Edit Quotation Funtionality +Enhance Template | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-137 | [5 empty] | 2026-03-05T15:48:14.824+0500 | 2026-03-25T11:29:20.487+0500
SUBS | SUBS-138 | SUBS-138 | Sub-task | Sub-task |  | Added Pagination and Fix Issues in User and Sales Screen | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 5.5 | 5.5 | Muhammad Ahmad Saleem | 5.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-138 | [5 empty] | 2026-03-06T14:33:43.251+0500 | 2026-03-25T11:29:20.921+0500
SUBS | SUBS-139 | SUBS-139 | Sub-task | Sub-task |  | Make quotation sharable for User | Resolved! | 2026-03-09 | 2026-03-10 | 2026-03-06 | 2026-03-10 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-139 | [5 empty] | 2026-03-06T16:00:38.162+0500 | 2026-03-25T11:29:21.384+0500
SUBS | SUBS-14 | SUBS-14 | Sub-task | Sub-task |  | Resource Management | Resolved! | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-17 | 2 | 2 | Faiza Nasir | 1.5 |  | SUBS-9 | SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-14 | [5 empty] | 2026-03-17T15:22:42.505+0500 | 2026-03-25T11:28:21.976+0500
SUBS | SUBS-140 | SUBS-140 | Sub-task | Sub-task |  | Demo with TK & Asmar + Post Demo Discussions | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 6.5 | 6.5 | Zain Munir | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-140 | [5 empty] | 2026-03-09T14:55:04.673+0500 | 2026-03-25T11:29:21.784+0500
SUBS | SUBS-141 | SUBS-141 | Sub-task | Sub-task |  | POST API changes for versions | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 3.5 | 3.5 | Sarmad Sabir | 3.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-141 | [5 empty] | 2026-03-10T10:02:52.435+0500 | 2026-03-25T11:29:22.174+0500
SUBS | SUBS-142 | SUBS-142 | Sub-task | Sub-task |  | UI adjustments for Plan and Tiers | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 3 | 3 | Sarmad Sabir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-142 | [5 empty] | 2026-03-10T10:03:32.595+0500 | 2026-03-25T11:29:22.594+0500
SUBS | SUBS-143 | SUBS-143 | Sub-task | Sub-task |  | On submit Set all plans, products, plan teirs , pricing version, etc Status = APPROVED | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-143 | [5 empty] | 2026-03-10T10:56:05.722+0500 | 2026-03-25T11:29:23.039+0500
SUBS | SUBS-144 | SUBS-144 | Sub-task | Sub-task |  | Make Quotation Invalid in case of pricing change of plan or plan tiers | Resolved! | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-144 | [5 empty] | 2026-03-10T10:56:38.978+0500 | 2026-03-25T11:29:23.527+0500
SUBS | SUBS-145 | SUBS-145 | Sub-task | Sub-task |  | Do not allow Plan, Plan tiers, Meters to be deleted if used in Quotations | Resolved! | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 1.5 | 1.5 | Faiza Nasir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-145 | [5 empty] | 2026-03-10T12:17:01.017+0500 | 2026-03-25T11:29:23.950+0500
SUBS | SUBS-146 | SUBS-146 | Sub-task | Sub-task |  | Feature should not delete that is used in Plan | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-146 | [5 empty] | 2026-03-10T15:07:16.381+0500 | 2026-03-25T11:29:24.453+0500
SUBS | SUBS-147 | SUBS-147 | Sub-task | Sub-task |  | Post Demo Discussion to Incorporate Feedback | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 1.5 | 1.5 | Faiza Nasir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-147 | [5 empty] | 2026-03-10T15:25:11.827+0500 | 2026-03-25T11:29:24.916+0500
SUBS | SUBS-148 | SUBS-148 | Sub-task | Sub-task |  | Added Export API+ Fixed User Update Issue+ Discussion | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 4.5 | 4.5 | Muhammad Ahmad Saleem | 4.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-148 | [5 empty] | 2026-03-11T09:17:00.964+0500 | 2026-03-25T11:29:25.344+0500
SUBS | SUBS-149 | SUBS-149 | Sub-task | Sub-task |  | Added Share Functionality + Fix Issues | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 4.5 | 4.5 | Muhammad Ahmad Saleem | 4.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-149 | [5 empty] | 2026-03-11T09:21:19.087+0500 | 2026-03-25T11:29:25.785+0500
SUBS | SUBS-15 | SUBS-15 | Sub-task | Sub-task |  | Azure Resource management | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 4 | 4 | Ameer Hamza Khan | 4 |  | SUBS-9 | SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-15 | [5 empty] | 2026-03-17T15:26:03.915+0500 | 2026-03-25T11:28:22.415+0500
SUBS | SUBS-150 | SUBS-150 | Sub-task | Sub-task |  | Make all newly created qoutes marked as approved | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-150 | [5 empty] | 2026-03-11T15:14:30.548+0500 | 2026-03-25T11:29:26.259+0500
SUBS | SUBS-151 | SUBS-151 | Sub-task | Sub-task |  | Set quote status as Void on any change in plan and plan tier pricings | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-151 | [5 empty] | 2026-03-11T15:15:13.876+0500 | 2026-03-25T11:29:26.774+0500
SUBS | SUBS-152 | SUBS-152 | Sub-task | Sub-task |  | Remove all checks in quotes that checks statuses in CRUD Operations | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-152 | [5 empty] | 2026-03-11T15:16:11.954+0500 | 2026-03-25T11:29:27.220+0500
SUBS | SUBS-153 | SUBS-153 | Sub-task | Sub-task |  | Add base price of chosen plan in Quotations | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-153 | [5 empty] | 2026-03-11T15:16:52.802+0500 | 2026-03-25T11:29:27.679+0500
SUBS | SUBS-154 | SUBS-154 | Sub-task | Sub-task |  | Fixed Currency in Calculator and View Quotation + User issue | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-154 | [5 empty] | 2026-03-12T12:21:57.614+0500 | 2026-03-25T11:29:28.148+0500
SUBS | SUBS-155 | SUBS-155 | Sub-task | Sub-task |  | Complete flow test + Handover to QA + Post Handover Meeting | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-155 | [5 empty] | 2026-03-12T13:51:52.626+0500 | 2026-03-25T11:29:28.536+0500
SUBS | SUBS-156 | SUBS-156 | Sub-task | Sub-task |  | Requirement gathering and team management | Resolved! | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-02-27 | 40 | 40 | Ameer Hamza Khan | 40 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-156 | [5 empty] | 2026-03-12T14:07:10.862+0500 | 2026-03-25T11:29:28.999+0500
SUBS | SUBS-157 | SUBS-157 | Sub-task | Sub-task |  | Added Revise,Invalid Quotation Functionality | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-157 | [5 empty] | 2026-03-13T10:40:17.335+0500 | 2026-03-25T11:29:29.460+0500
SUBS | SUBS-158 | SUBS-158 | Sub-task | Sub-task |  | Set ONE Default plan feature | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-158 | [5 empty] | 2026-03-13T13:55:04.482+0500 | 2026-03-25T11:29:29.893+0500
SUBS | SUBS-159 | SUBS-159 | Sub-task | Sub-task |  | Email confirmation status in User Table | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-159 | [5 empty] | 2026-03-13T13:55:35.592+0500 | 2026-03-25T11:29:30.351+0500
SUBS | SUBS-16 | SUBS-16 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Waqar Rasheed | 8 |  | SUBS-9 | SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-16 | [5 empty] | 2026-03-18T10:52:51.289+0500 | 2026-03-26T10:51:59.495+0500
SUBS | SUBS-160 | SUBS-160 | Sub-task | Sub-task |  | Implement Resend Email in User Table | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1.5 | 1.5 | Sarmad Sabir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-160 | [5 empty] | 2026-03-13T13:56:04.487+0500 | 2026-03-25T11:29:30.759+0500
SUBS | SUBS-161 | SUBS-161 | Sub-task | Sub-task |  | UI Fix for Users Page | To Do |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-161 | [5 empty] | 2026-03-13T13:56:24.710+0500 | 2026-03-25T11:29:31.212+0500
SUBS | SUBS-162 | SUBS-162 | Sub-task | Sub-task |  | Preparing data for Demo + Sanity Check with Excel Sheet | To Do |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-162 | [5 empty] | 2026-03-13T14:00:28.516+0500 | 2026-03-25T11:29:31.637+0500
SUBS | SUBS-163 | SUBS-163 | Sub-task | Sub-task |  | Testing for demo + Fixed Some issue | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 3.5 | 3.5 | Muhammad Ahmad Saleem | 3.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-163 | [5 empty] | 2026-03-13T15:23:12.309+0500 | 2026-03-25T11:29:32.085+0500
SUBS | SUBS-164 | SUBS-164 | Sub-task | Sub-task |  | Modified Share Functionality +Revise UI + Fixed Invalid Quotation | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 5.5 | 5.5 | Muhammad Ahmad Saleem | 5.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-164 | [5 empty] | 2026-03-13T15:24:10.881+0500 | 2026-03-25T11:29:32.558+0500
SUBS | SUBS-165 | SUBS-165 | Sub-task | Sub-task |  | Handover By Kamran | To Do | 2026-02-27 | 2026-02-27 |  |  | 1 | 1 | kamran khalid | 0 |  | SUBS-10 | SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-165 | [5 empty] | 2026-02-27T10:35:48.941+0500 | 2026-03-25T11:29:33.039+0500
SUBS | SUBS-166 | SUBS-166 | Sub-task | Sub-task |  | Handover By Namra | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 1 | 1 | Namra Zahid | 2.22 |  | SUBS-10 | SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-166 | [5 empty] | 2026-02-27T10:36:00.461+0500 | 2026-03-25T11:29:33.490+0500
SUBS | SUBS-167 | SUBS-167 | Sub-task | Sub-task |  | Handover By Zeeshan | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 1 | 1 | Zeeshan Sarwar | 2 |  | SUBS-10 | SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-167 | [5 empty] | 2026-02-27T10:36:10.865+0500 | 2026-03-25T11:29:33.924+0500
SUBS | SUBS-168 | SUBS-168 | Sub-task | Sub-task |  | Handover By M.Abbas | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 1 | 1 | Muhammad Abbas | 2.22 |  | SUBS-10 | SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-168 | [5 empty] | 2026-02-27T10:36:34.362+0500 | 2026-03-25T11:29:34.431+0500
SUBS | SUBS-169 | SUBS-169 | Sub-task | Sub-task |  | Handover By Waqar | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 1 | 1 | Waqar Rasheed | 2.22 |  | SUBS-10 | SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-169 | [5 empty] | 2026-02-27T10:36:47.603+0500 | 2026-03-25T11:29:34.851+0500
SUBS | SUBS-17 | SUBS-17 | Sub-task | Sub-task |  | FE Deployment + Unit Testing + DB Cleanup | Resolved! | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-18 | 9.5 | 9.5 | Zain Munir | 9.5 |  | SUBS-9 | SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-17 | [5 empty] | 2026-03-18T13:13:02.031+0500 | 2026-03-25T11:28:23.398+0500
SUBS | SUBS-170 | SUBS-170 | Sub-task | Sub-task |  | Handover To QA - Faiza | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2.22 | 2.22 | Faiza Nasir | 2.22 |  | SUBS-10 | SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-170 | [5 empty] | 2026-02-27T14:26:35.800+0500 | 2026-03-25T11:29:35.348+0500
SUBS | SUBS-171 | SUBS-171 | Sub-task | Sub-task |  | Handover To QA - Sarmad | Resolved! | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2.5 | 2.5 | Sarmad Sabir | 2.5 |  | SUBS-10 | SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-10 | https://octopusdtlsupport.atlassian.net/browse/SUBS-171 | [5 empty] | 2026-03-02T10:05:37.618+0500 | 2026-03-25T11:29:35.822+0500
SUBS | SUBS-172 | SUBS-172 | Sub-task | Sub-task |  | Brainstorming Structure / Tools | Resolved! | 2026-01-29 | 2026-02-03 | 2026-01-29 | 2026-02-03 | 8 | 8 | Faiza Nasir | 8 |  | SUBS-6 | SUBS-6 | https://octopusdtlsupport.atlassian.net/browse/SUBS-6 | https://octopusdtlsupport.atlassian.net/browse/SUBS-172 | [5 empty] | 2026-01-15T10:58:59.844+0500 | 2026-03-25T11:29:36.274+0500
SUBS | SUBS-173 | SUBS-173 | Sub-task | Sub-task |  | Discussion on Requirements | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 8 | 8 | Faiza Nasir | 2 |  | SUBS-6 | SUBS-6 | https://octopusdtlsupport.atlassian.net/browse/SUBS-6 | https://octopusdtlsupport.atlassian.net/browse/SUBS-173 | [5 empty] | 2026-01-15T11:02:44.081+0500 | 2026-03-25T11:29:36.726+0500
SUBS | SUBS-174 | SUBS-174 | Sub-task | Sub-task |  | ERD Diagram Creation | Resolved! | 2026-01-09 | 2026-01-12 | 2026-01-09 | 2026-01-09 | 16 | 16 | Faiza Nasir | 8 |  | SUBS-6 | SUBS-6 | https://octopusdtlsupport.atlassian.net/browse/SUBS-6 | https://octopusdtlsupport.atlassian.net/browse/SUBS-174 | [5 empty] | 2026-01-16T17:19:27.632+0500 | 2026-03-25T11:29:37.214+0500
SUBS | SUBS-175 | SUBS-175 | Bug Subtask | Bug Subtask |  | A Duplicate version name is being generated. | Resolved | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-175 | [5 empty] | 2026-03-02T11:23:13.199+0500 | 2026-03-25T11:29:37.627+0500
SUBS | SUBS-176 | SUBS-176 | Bug Subtask | Bug Subtask |  | Bad Request Error 400, Is being displayed while Entering Decimal Version Number. | Resolved | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 1 | 1 | Faiza Nasir | 0.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-176 | [5 empty] | 2026-03-02T11:38:29.622+0500 | 2026-03-25T11:29:38.059+0500
SUBS | SUBS-177 | SUBS-177 | Bug Subtask | Bug Subtask |  | 400 Bad Request Error occurred, when you clicked the Create button after entering only a space in the name field. | Resolved | 2026-03-02 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-177 | [5 empty] | 2026-03-02T11:43:53.134+0500 | 2026-03-25T11:29:38.502+0500
SUBS | SUBS-178 | SUBS-178 | Bug Subtask | Bug Subtask |  | The created version's table does not have a change summary column to verify the information the user provided during version creation. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-178 | [5 empty] | 2026-03-02T12:01:30.655+0500 | 2026-03-25T11:29:38.952+0500
SUBS | SUBS-179 | SUBS-179 | Bug Subtask | Bug Subtask |  | The name and Change Summary fields are unrestricted. Additionally, it gives 400 Bad Requests for long characters length . | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-179 | [5 empty] | 2026-03-02T12:07:18.158+0500 | 2026-03-25T11:29:39.395+0500
SUBS | SUBS-18 | SUBS-18 | Sub-task | Sub-task |  | Unit Testing | Resolved! | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-9 | SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | https://octopusdtlsupport.atlassian.net/browse/SUBS-18 | [5 empty] | 2026-03-18T15:25:07.336+0500 | 2026-03-25T11:28:23.908+0500
SUBS | SUBS-180 | SUBS-180 | Bug Subtask | Bug Subtask |  | Meter Code Cannot Be Re-Added After Deletion or Used Across Different Versions | Resolved | 2026-03-02 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-180 | [5 empty] | 2026-03-02T12:11:24.266+0500 | 2026-03-25T11:29:39.814+0500
SUBS | SUBS-181 | SUBS-181 | Bug Subtask | Bug Subtask |  | Version is getting created only with a single space in the Change Summary field.with success message. | Resolved | 2026-03-02 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-181 | [5 empty] | 2026-03-02T12:41:51.029+0500 | 2026-03-25T11:29:40.246+0500
SUBS | SUBS-182 | SUBS-182 | Bug Subtask | Bug Subtask |  | Versions are not being approved from the front end or the back end. | Not a Bug |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-182 | [5 empty] | 2026-03-02T15:02:38.310+0500 | 2026-03-25T11:29:40.759+0500
SUBS | SUBS-183 | SUBS-183 | Bug Subtask | Bug Subtask |  | Bug: The system allows entering a long version number, but upon clicking the Create button, the API fails with a 400 Bad Request error. | Resolved | 2026-03-03 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-183 | [5 empty] | 2026-03-03T10:21:42.909+0500 | 2026-03-25T11:29:41.180+0500
SUBS | SUBS-184 | SUBS-184 | Bug Subtask | Bug Subtask |  | Pagination is missing in Versions table | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-184 | [5 empty] | 2026-03-03T10:41:52.551+0500 | 2026-03-25T11:29:41.642+0500
SUBS | SUBS-185 | SUBS-185 | Bug Subtask | Bug Subtask |  | "About" and "Support" links in footer are not redirecting. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-185 | [5 empty] | 2026-03-03T10:46:47.546+0500 | 2026-03-25T11:29:42.083+0500
SUBS | SUBS-186 | SUBS-186 | Bug Subtask | Bug Subtask |  | Search field is missing for Versions. | Resolved | 2026-03-03 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-186 | [5 empty] | 2026-03-03T11:46:36.092+0500 | 2026-03-25T11:29:42.543+0500
SUBS | SUBS-187 | SUBS-187 | Bug Subtask | Bug Subtask |  | Error Message Displayed When Creating Tier, but Tier Is Created Successfully. | Resolved | 2026-03-03 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-187 | [5 empty] | 2026-03-03T11:54:06.780+0500 | 2026-03-25T11:29:42.967+0500
SUBS | SUBS-188 | SUBS-188 | Bug Subtask | Bug Subtask |  | 400 Bad Request Error When Creating Tier with Min Value = 0 and Max Value = Infinity | Resolved | 2026-03-03 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-188 | [5 empty] | 2026-03-03T11:59:11.645+0500 | 2026-03-25T11:29:43.411+0500
SUBS | SUBS-189 | SUBS-189 | Bug Subtask | Bug Subtask |  | Error Shown When Meter Type Is Set to 0 on Calculator Screen During Quotation Save | Not a Bug |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-189 | [5 empty] | 2026-03-03T13:48:06.187+0500 | 2026-03-25T11:29:43.807+0500
SUBS | SUBS-19 | SUBS-19 | Sub-task | Sub-task |  | Same name plans, versions, meter types should not be allowed. | Resolved! | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 4 | 4 | Faiza Nasir | 4 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-19 | [5 empty] | 2026-03-03T10:18:23.606+0500 | 2026-03-25T11:28:24.443+0500
SUBS | SUBS-190 | SUBS-190 | Bug Subtask | Bug Subtask |  | Multiple approval popups and API calls triggered on rapid clicks of “Send for Approval” | Resolved | 2026-03-03 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-190 | [5 empty] | 2026-03-03T15:03:03.850+0500 | 2026-03-25T11:29:44.258+0500
SUBS | SUBS-191 | SUBS-191 | Bug Subtask | Bug Subtask |  | UI layout breaks when entering long characters in Name and Change Summary fields | Resolved | 2026-03-04 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-191 | [5 empty] | 2026-03-04T10:35:58.701+0500 | 2026-03-25T11:29:44.696+0500
SUBS | SUBS-192 | SUBS-192 | Bug Subtask | Bug Subtask |  | Missing Validation When Name or Email Starts/Ends with Space on Calculator Screen | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-192 | [5 empty] | 2026-03-04T11:16:52.534+0500 | 2026-03-25T11:29:45.131+0500
SUBS | SUBS-193 | SUBS-193 | Bug Subtask | Bug Subtask |  | Submit and Cancel buttons disappear in approval popup for versions with long names | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-193 | [5 empty] | 2026-03-04T11:18:07.566+0500 | 2026-03-25T11:29:45.552+0500
SUBS | SUBS-194 | SUBS-194 | Bug Subtask | Bug Subtask |  | Support Icon Not Clickable at Bottom Right | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-194 | [5 empty] | 2026-03-04T12:25:25.634+0500 | 2026-03-25T11:29:45.958+0500
SUBS | SUBS-195 | SUBS-195 | Bug Subtask | Bug Subtask |  | Product duplication allowed in Product Creation | Resolved | 2026-03-04 |  | 2026-03-04 | 2026-03-04 | 2 | 2 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-195 | [5 empty] | 2026-03-04T13:06:04.524+0500 | 2026-03-25T11:29:46.410+0500
SUBS | SUBS-196 | SUBS-196 | Bug Subtask | Bug Subtask |  | Incorrect error message displayed when duplicate Product Code is entered | Resolved | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2 | 2 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-196 | [5 empty] | 2026-03-04T13:09:38.787+0500 | 2026-03-25T11:29:46.832+0500
SUBS | SUBS-197 | SUBS-197 | Bug Subtask | Bug Subtask |  | Product card UI breaks & missing Controls with long Product Name/Code/Description causing toggle and button functionalities to disappear | Resolved | 2026-03-04 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-197 | [5 empty] | 2026-03-04T14:36:04.914+0500 | 2026-03-25T11:29:47.259+0500
SUBS | SUBS-198 | SUBS-198 | Bug Subtask | Bug Subtask |  | Long Product name effects all screens: Feature, Plan,Tier, Product menu etc | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-198 | [5 empty] | 2026-03-04T14:49:44.324+0500 | 2026-03-25T11:29:47.680+0500
SUBS | SUBS-199 | SUBS-199 | Bug Subtask | Bug Subtask |  | Focus moves outside the modal to background page elements, Keyboard focus is not trapped inside Create Product modal | Not a Bug | 2026-03-05 |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-199 | [5 empty] | 2026-03-05T10:36:08.477+0500 | 2026-03-25T11:29:48.137+0500
SUBS | SUBS-20 | SUBS-20 | Sub-task | Sub-task |  | Implement Minimum and Maximum Character Limit on Name Field (Calculator Screen) | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-20 | [5 empty] | 2026-03-03T14:12:29.241+0500 | 2026-03-25T11:28:24.927+0500
SUBS | SUBS-200 | SUBS-200 | Bug Subtask | Bug Subtask |  | Need to display validation messages on all modules where validation is applied but message is missing. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-200 | [5 empty] | 2026-03-05T13:02:14.682+0500 | 2026-03-25T11:29:48.554+0500
SUBS | SUBS-201 | SUBS-201 | Bug Subtask | Bug Subtask |  | No search bar or search functionality is available to search for a product. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-201 | [5 empty] | 2026-03-05T13:51:17.047+0500 | 2026-03-25T11:29:48.986+0500
SUBS | SUBS-202 | SUBS-202 | Bug Subtask | Bug Subtask |  | “More Filters” Button Not Functional on My Quotation Screen | Resolved | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-202 | [5 empty] | 2026-03-09T09:53:04.216+0500 | 2026-03-25T11:29:49.388+0500
SUBS | SUBS-203 | SUBS-203 | Bug Subtask | Bug Subtask |  | The system allows Deletion of a product when its status is Active. Active products should not be deleted directly as they may be linked with other configurations (features, plans, pricing) etc. | Not a Bug |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-203 | [5 empty] | 2026-03-09T10:42:45.557+0500 | 2026-03-25T11:29:49.790+0500
SUBS | SUBS-204 | SUBS-204 | Bug Subtask | Bug Subtask |  | Feature name is getting duplicated. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-204 | [5 empty] | 2026-03-09T15:24:49.145+0500 | 2026-03-25T11:29:50.234+0500
SUBS | SUBS-205 | SUBS-205 | Bug Subtask | Bug Subtask |  | Calculator Screen Data Does Not Clear After Updating a Quotation | Resolved | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-205 | [5 empty] | 2026-03-10T09:49:14.156+0500 | 2026-03-25T11:29:50.663+0500
SUBS | SUBS-206 | SUBS-206 | Bug Subtask | Bug Subtask |  | No Data Displayed When Updating a Quotation | Not a Bug |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-206 | [5 empty] | 2026-03-10T10:28:24.831+0500 | 2026-03-25T11:29:51.107+0500
SUBS | SUBS-207 | SUBS-207 | Bug Subtask | Bug Subtask |  | Incorrect Product Selection After Page Refresh | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-207 | [5 empty] | 2026-03-10T12:12:18.951+0500 | 2026-03-25T11:29:51.544+0500
SUBS | SUBS-208 | SUBS-208 | Bug Subtask | Bug Subtask |  | One Feature Not Deleted When Deleting Multiple Features – “Invalid Network Error” Displayed | Resolved | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-208 | [5 empty] | 2026-03-10T12:36:33.717+0500 | 2026-03-25T11:29:51.989+0500
SUBS | SUBS-209 | SUBS-209 | Bug Subtask | Bug Subtask |  | Meter Type Text Overlaps with Supporting Text When Editing Tier | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-209 | [5 empty] | 2026-03-10T12:46:55.146+0500 | 2026-03-25T11:29:52.417+0500
SUBS | SUBS-21 | SUBS-21 | Sub-task | Sub-task |  | Show Validation Messages Inline (Below Fields) Instead of Top-Right Toast — Apply Across Application | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-21 | [5 empty] | 2026-03-03T14:19:24.354+0500 | 2026-03-25T11:28:25.418+0500
SUBS | SUBS-210 | SUBS-210 | Bug Subtask | Bug Subtask |  | Tier Code Case Inconsistency and Missing Validation on Tiers Screen | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-210 | [5 empty] | 2026-03-10T12:56:51.336+0500 | 2026-03-25T11:29:52.921+0500
SUBS | SUBS-211 | SUBS-211 | Bug Subtask | Bug Subtask |  | Export Document UI Is Disturbed | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-211 | [5 empty] | 2026-03-10T14:15:06.825+0500 | 2026-03-25T11:29:53.520+0500
SUBS | SUBS-212 | SUBS-212 | Bug Subtask | Bug Subtask |  | Logged-In User Is Also Displayed in Share Quotation List | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-212 | [5 empty] | 2026-03-10T14:18:16.916+0500 | 2026-03-25T11:29:53.976+0500
SUBS | SUBS-213 | SUBS-213 | Bug Subtask | Bug Subtask |  | Token is not received on email | Not a Bug |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-213 | [5 empty] | 2026-03-11T10:58:00.247+0500 | 2026-03-25T11:29:54.370+0500
SUBS | SUBS-214 | SUBS-214 | Bug Subtask | Bug Subtask |  | Incorrect Button/Text Label Displayed as “Send Reset Instruction” Instead of “Send Reset Token” | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-214 | [5 empty] | 2026-03-11T11:03:11.887+0500 | 2026-03-25T11:29:54.816+0500
SUBS | SUBS-215 | SUBS-215 | Bug Subtask | Bug Subtask |  | Unable to Login with Newly Created User | Resolved | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-215 | [5 empty] | 2026-03-11T11:04:38.748+0500 | 2026-03-25T11:29:55.241+0500
SUBS | SUBS-216 | SUBS-216 | Bug Subtask | Bug Subtask |  | HTTP 401 Unauthorized Error Displayed When Logging Out from Plans and Tiers Screens | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-216 | [5 empty] | 2026-03-11T11:10:34.663+0500 | 2026-03-25T11:29:55.651+0500
SUBS | SUBS-217 | SUBS-217 | Bug Subtask | Bug Subtask |  | Status Column Displayed Without Actions Column on Versions Screen | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-217 | [5 empty] | 2026-03-11T11:52:30.734+0500 | 2026-03-25T11:29:56.137+0500
SUBS | SUBS-218 | SUBS-218 | Bug Subtask | Bug Subtask |  | Plan is getting created with 0 Base Price. | Not a Bug |  |  | 2026-03-11 | 2026-03-11 | 0.08 | 0.08 | Faiza Nasir | 0.08 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-218 | [5 empty] | 2026-03-11T12:31:37.322+0500 | 2026-03-25T11:29:56.575+0500
SUBS | SUBS-219 | SUBS-219 | Bug Subtask | Bug Subtask |  | Incorrect Currency Symbol Displayed on Plan Card for EUR and GBP | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-219 | [5 empty] | 2026-03-11T12:53:22.867+0500 | 2026-03-25T11:29:57.007+0500
SUBS | SUBS-22 | SUBS-22 | Sub-task | Sub-task |  | Bugs Fixing + Improvement in the Admin Screens | Resolved! | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 19.5 | 19.5 | Zain Munir | 19.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-22 | [5 empty] | 2026-03-03T15:02:05.446+0500 | 2026-03-25T11:28:25.857+0500
SUBS | SUBS-220 | SUBS-220 | Bug Subtask | Bug Subtask |  | If super admin block any user the message login page should User blocked please contact admin | Resolved | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-220 | [5 empty] | 2026-03-12T14:18:16.763+0500 | 2026-03-25T11:29:57.435+0500
SUBS | SUBS-221 | SUBS-221 | Bug Subtask | Bug Subtask |  | Long Plan Description Breaks Plan Card Layout and Causes Misalignment | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-221 | [5 empty] | 2026-03-13T12:03:36.081+0500 | 2026-03-25T11:29:57.862+0500
SUBS | SUBS-222 | SUBS-222 | Bug Subtask | Bug Subtask |  | Base Price Field Accepts Extremely Large Values and Shows Inconsistent Behavior (Scientific Notation / Infinity / 0) | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-222 | [5 empty] | 2026-03-13T12:26:43.240+0500 | 2026-03-25T11:29:58.367+0500
SUBS | SUBS-223 | SUBS-223 | Bug Subtask | Bug Subtask |  | Generic Network Error Displayed When Using Same Plan Code Across Different Products | Resolved | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-223 | [5 empty] | 2026-03-13T12:45:13.321+0500 | 2026-03-25T11:29:58.889+0500
SUBS | SUBS-224 | SUBS-224 | Bug Subtask | Bug Subtask |  | Success Message Shown When Re-Sharing Quotation Back to Original User, but Quotation Is Not Actually Shared | Resolved | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-224 | [5 empty] | 2026-03-13T12:47:28.848+0500 | 2026-03-25T11:29:59.351+0500
SUBS | SUBS-225 | SUBS-225 | Bug Subtask | Bug Subtask |  | Calculator Screen Not Reset When Changing Plan | Resolved | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-225 | [5 empty] | 2026-03-13T12:53:17.877+0500 | 2026-03-25T11:29:59.914+0500
SUBS | SUBS-226 | SUBS-226 | Bug Subtask | Bug Subtask |  | Total Amount on Quotation Screen Is Incorrect After Editing Quotation | Resolved | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-226 | [5 empty] | 2026-03-13T13:00:59.595+0500 | 2026-03-25T11:30:00.501+0500
SUBS | SUBS-227 | SUBS-227 | Bug Subtask | Bug Subtask |  | Inactive Product Becomes Active Automatically After Update | Resolved | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-227 | [5 empty] | 2026-03-13T14:29:20.533+0500 | 2026-03-25T11:30:01.125+0500
SUBS | SUBS-228 | SUBS-228 | Bug Subtask | Bug Subtask |  | User Can Re-Share Quotation Even When Edit Permission Is Disabled | Resolved | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 3 | 3 | Muhammad Ahmad Saleem | 3 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-228 | [5 empty] | 2026-03-16T10:08:49.326+0500 | 2026-03-25T11:30:01.711+0500
SUBS | SUBS-229 | SUBS-229 | Bug Subtask | Bug Subtask |  | The Plan Code field accepts lowercase characters (aa).However, based on the validation rules used for Product Code, Feature Code, only uppercase letters, numbers and underscores should be allowed.secondly Plan Code Field Accepts Invalid Special Characters | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-229 | [5 empty] | 2026-03-16T10:13:02.378+0500 | 2026-03-25T11:30:02.270+0500
SUBS | SUBS-23 | SUBS-23 | Sub-task | Sub-task |  | Add Scrollbar to Price Summary and Subscription Configuration Sections on Calculator Screen | Resolved! | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-23 | [5 empty] | 2026-03-04T11:52:00.325+0500 | 2026-03-25T11:28:26.364+0500
SUBS | SUBS-230 | SUBS-230 | Bug Subtask | Bug Subtask |  | Base Price Field Does Not Accept Decimal Values | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-230 | [5 empty] | 2026-03-16T10:32:30.769+0500 | 2026-03-25T11:30:02.851+0500
SUBS | SUBS-231 | SUBS-231 | Bug Subtask | Bug Subtask |  | Plan Code Not Displayed on Plan Card After Plan Creation | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-231 | [5 empty] | 2026-03-16T10:41:11.638+0500 | 2026-03-25T11:30:03.339+0500
SUBS | SUBS-232 | SUBS-232 | Bug Subtask | Bug Subtask |  | Edit Status Message Persists Unnecessarily on Plans Screen | Not a Bug |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-232 | [5 empty] | 2026-03-16T10:49:01.516+0500 | 2026-03-25T11:30:03.866+0500
SUBS | SUBS-233 | SUBS-233 | Bug Subtask | Bug Subtask |  | Preview Screen Displays Only One Feature While Multiple Active Features Exist | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-233 | [5 empty] | 2026-03-16T14:19:45.393+0500 | 2026-03-25T11:30:04.340+0500
SUBS | SUBS-234 | SUBS-234 | Bug Subtask | Bug Subtask |  | Plan is not getting Inactive | Resolved | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-234 | [5 empty] | 2026-03-16T15:05:32.030+0500 | 2026-03-25T11:30:04.873+0500
SUBS | SUBS-235 | SUBS-235 | Bug Subtask | Bug Subtask |  | Invalid Pricing Format Displayed for Non-USD Currencies in Preview | Resolved |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-235 | [5 empty] | 2026-03-17T12:20:54.842+0500 | 2026-03-25T11:30:05.383+0500
SUBS | SUBS-236 | SUBS-236 | Epic | Epic |  | Subscription Management V2 | In-Progress |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/SUBS-236 | [5 empty] | 2026-03-25T15:14:51.023+0500 | 2026-04-09T10:53:11.061+0500
SUBS | SUBS-237 | SUBS-237 | Epic | Epic |  | Technical Support | To Do |  |  |  |  | 0 | 0 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/SUBS-237 | [5 empty] | 2026-03-26T10:43:34.998+0500 | 2026-03-26T10:43:35.092+0500
SUBS | SUBS-238 | SUBS-238 | Story | Story |  | Demo / Handover / Discussions | In-Progress |  |  |  |  | 0 | 0 | Faiza Nasir | 46.42 |  | SUBS-236 | SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | [5 empty] | 2026-03-26T10:55:57.109+0500 | 2026-03-26T16:57:41.477+0500
SUBS | SUBS-239 | SUBS-239 | Story | Story |  | Development | In-Progress |  |  |  |  | 0 | 0 | Faiza Nasir | 80 |  | SUBS-236 | SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | [5 empty] | 2026-03-26T10:56:19.871+0500 | 2026-03-26T11:03:47.051+0500
SUBS | SUBS-24 | SUBS-24 | Sub-task | Sub-task |  | Duplicate Product , Pricing Config fixed | Resolved! |  |  | 2026-03-03 | 2026-03-03 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-24 | [5 empty] | 2026-03-04T14:52:50.949+0500 | 2026-03-25T11:28:26.849+0500
SUBS | SUBS-240 | SUBS-240 | Story | Story |  | SQA | Resolved! | 2026-03-25 | 2026-03-27 |  |  | 24 | 24 | Waqar Rasheed | 64.5 |  | SUBS-236 | SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | [5 empty] | 2026-03-26T10:56:51.368+0500 | 2026-04-10T11:59:10.575+0500
SUBS | SUBS-241 | SUBS-241 | Story | Story |  | Bug Fixing | Resolved! |  |  |  |  | 0 | 0 | Faiza Nasir | 19.5 |  | SUBS-236 | SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | [5 empty] | 2026-03-26T10:57:17.121+0500 | 2026-04-16T11:19:54.068+0500
SUBS | SUBS-242 | SUBS-242 | Story | Story |  | Production Release | In-Progress |  |  |  |  | 0 | 0 | Faiza Nasir | 34 |  | SUBS-236 | SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-236 | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | [5 empty] | 2026-03-26T10:58:34.855+0500 | 2026-04-09T14:18:39.518+0500
SUBS | SUBS-243 | SUBS-243 | Sub-task | Sub-task |  | Demo with Management + Internal Team Discussion | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Zain Munir | 8 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-243 | [5 empty] | 2026-03-26T10:58:54.468+0500 | 2026-03-26T11:00:44.263+0500
SUBS | SUBS-244 | SUBS-244 | Sub-task | Sub-task |  | Updated Product Configs + Info Update | Resolved! | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8 | 8 | Zain Munir | 8 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-244 | [5 empty] | 2026-03-26T11:02:19.190+0500 | 2026-03-26T11:07:16.830+0500
SUBS | SUBS-245 | SUBS-245 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-27 | 24 | 24 | Waqar Rasheed | 24 |  | SUBS-240 | SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-245 | [5 empty] | 2026-03-26T11:04:10.612+0500 | 2026-03-27T16:29:52.582+0500
SUBS | SUBS-246 | SUBS-246 | Bug Subtask | Bug Subtask |  | Old Forgot Password Link Remains Valid After New Reset Email and Even After Use | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-246 | [5 empty] | 2026-03-26T11:20:42.228+0500 | 2026-03-26T16:08:42.600+0500
SUBS | SUBS-247 | SUBS-247 | Bug Subtask | Bug Subtask |  | User is able to set current password as new password. | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-247 | [5 empty] | 2026-03-26T11:26:10.614+0500 | 2026-03-26T16:09:57.557+0500
SUBS | SUBS-248 | SUBS-248 | Bug Subtask | Bug Subtask |  | Eye Icon on New Password Field Also Affects Confirm Password Field | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-248 | [5 empty] | 2026-03-26T11:32:26.416+0500 | 2026-03-26T16:11:43.718+0500
SUBS | SUBS-249 | SUBS-249 | Sub-task | Sub-task |  | Added Discount Field + Integrated New Tier price logic | Resolved! | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-249 | [5 empty] | 2026-03-26T11:42:56.048+0500 | 2026-03-26T11:44:37.332+0500
SUBS | SUBS-25 | SUBS-25 | Sub-task | Sub-task |  | Add “Created At” Column on My Quotation Screen and Correct "Last Modified" column Behavior | Resolved! |  |  | 2026-03-05 | 2026-03-05 | 2 | 2 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-25 | [5 empty] | 2026-03-04T15:03:02.879+0500 | 2026-03-25T11:28:27.308+0500
SUBS | SUBS-250 | SUBS-250 | Bug Subtask | Bug Subtask |  | Feature Code Validation Incorrectly Applied Across Products | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-250 | [5 empty] | 2026-03-26T11:56:36.923+0500 | 2026-03-26T16:14:54.028+0500
SUBS | SUBS-251 | SUBS-251 | Sub-task | Sub-task |  | “Back to Login” Link Missing on Set New Password Screen | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-251 | [5 empty] | 2026-03-26T12:07:02.895+0500 | 2026-03-26T15:37:19.525+0500
SUBS | SUBS-252 | SUBS-252 | Sub-task | Sub-task |  | Implement Reset Password Option Within the Application | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-252 | [5 empty] | 2026-03-26T12:14:43.949+0500 | 2026-03-26T15:37:22.511+0500
SUBS | SUBS-253 | SUBS-253 | Bug Subtask | Bug Subtask |  | Final Bundle Rate Not Applied Correctly Across All Sites at Maximum Threshold | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-253 | [5 empty] | 2026-03-26T12:50:36.403+0500 | 2026-03-27T16:27:23.920+0500
SUBS | SUBS-254 | SUBS-254 | Bug Subtask | Bug Subtask |  | Added Discount Not Reflected in Subscription Summary on Viewing Quotation | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-254 | [5 empty] | 2026-03-26T12:54:17.345+0500 | 2026-03-27T16:28:00.065+0500
SUBS | SUBS-255 | SUBS-255 | Bug Subtask | Bug Subtask |  | Discount Not Retained and Price Changes When Opening Quotation in Edit Mode | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-255 | [5 empty] | 2026-03-26T12:58:12.855+0500 | 2026-03-27T16:28:24.537+0500
SUBS | SUBS-256 | SUBS-256 | Bug Subtask | Bug Subtask |  | Meter Type Label Not Displayed on Calculator Screen (OmniChat) | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-256 | [5 empty] | 2026-03-26T14:43:30.268+0500 | 2026-03-27T16:28:48.024+0500
SUBS | SUBS-257 | SUBS-257 | Sub-task | Sub-task |  | QA reported Bugs for Auth and Admin Flow | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 4 | 4 | Zain Munir | 4 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-257 | [5 empty] | 2026-03-26T15:44:55.264+0500 | 2026-03-26T15:48:51.074+0500
SUBS | SUBS-258 | SUBS-258 | Sub-task | Sub-task |  | Added In-app Reset Password Module | Resolved! | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 4 | 4 | Zain Munir | 4 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-258 | [5 empty] | 2026-03-26T15:50:04.539+0500 | 2026-03-26T15:50:45.556+0500
SUBS | SUBS-259 | SUBS-259 | Sub-task | Sub-task |  | Add discount in Qoutes | Resolved! | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 5 | 5 | Faiza Nasir | 5 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-259 | [5 empty] | 2026-03-26T16:18:06.061+0500 | 2026-03-26T16:59:48.821+0500
SUBS | SUBS-26 | SUBS-26 | Sub-task | Sub-task |  | Implement validation to restrict numeric-only values in Product Name | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-26 | [5 empty] | 2026-03-04T15:23:04.701+0500 | 2026-03-25T11:28:27.743+0500
SUBS | SUBS-260 | SUBS-260 | Sub-task | Sub-task |  | Demo with Management / Feedback | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 5 | 5 | Faiza Nasir | 5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-260 | [5 empty] | 2026-03-26T16:53:41.053+0500 | 2026-03-26T17:01:14.757+0500
SUBS | SUBS-261 | SUBS-261 | Sub-task | Sub-task |  | QA Reported Bugs for Calculator and Quotations | Resolved! | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 8 | 8 | Zain Munir | 8 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-261 | [5 empty] | 2026-03-27T12:57:00.430+0500 | 2026-03-27T13:59:17.362+0500
SUBS | SUBS-262 | SUBS-262 | Sub-task | Sub-task |  | Testing By Waqar | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8 | 8 | Waqar Rasheed | 8 |  | SUBS-242 | SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-262 | [5 empty] | 2026-03-30T10:32:46.351+0500 | 2026-03-30T16:47:12.144+0500
SUBS | SUBS-263 | SUBS-263 | Bug Subtask | Bug Subtask |  | User Unable to Save Quotation on Production | Resolved | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-263 | [5 empty] | 2026-03-30T10:58:03.523+0500 | 2026-03-30T11:06:37.548+0500
SUBS | SUBS-264 | SUBS-264 | Sub-task | Sub-task |  | FE & BE Deployments + DB Migrations and Cleanup | Resolved! | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8 | 8 | Zain Munir | 8 |  | SUBS-242 | SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-264 | [5 empty] | 2026-03-31T12:00:05.253+0500 | 2026-03-31T12:00:49.323+0500
SUBS | SUBS-265 | SUBS-265 | Sub-task | Sub-task |  | Omni Connect Configuration | Resolved! | 2026-03-31 | 2026-04-02 | 2026-03-31 | 2026-04-02 | 24 | 24 | Waqar Rasheed | 24 |  | SUBS-240 | SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-265 | [5 empty] | 2026-03-31T12:13:46.059+0500 | 2026-04-03T10:42:13.547+0500
SUBS | SUBS-266 | SUBS-266 | Sub-task | Sub-task |  | Configuring OmniConnect + Moving Data to Production | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8 | 8 | Zain Munir | 8 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-266 | [5 empty] | 2026-03-31T16:33:17.636+0500 | 2026-03-31T16:33:51.516+0500
SUBS | SUBS-267 | SUBS-267 | Sub-task | Sub-task |  | Demo with TOM | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2 | 2 | Zain Munir | 2 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-267 | [5 empty] | 2026-04-01T16:45:38.944+0500 | 2026-04-01T16:46:27.255+0500
SUBS | SUBS-268 | SUBS-268 | Sub-task | Sub-task |  | Incorporating Changes by TOM | Resolved! | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 8 | 8 | Zain Munir | 8 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-268 | [5 empty] | 2026-04-01T16:47:09.999+0500 | 2026-04-01T16:47:38.265+0500
SUBS | SUBS-269 | SUBS-269 | Sub-task | Sub-task |  | Demo with TOM | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2 | 2 | Waqar Rasheed | 2 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-269 | [5 empty] | 2026-04-01T16:53:44.468+0500 | 2026-04-01T16:54:39.748+0500
SUBS | SUBS-27 | SUBS-27 | Sub-task | Sub-task |  | Bug fixing | Resolved! | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-04 | 24 | 24 | Faiza Nasir | 9 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-27 | [5 empty] | 2026-03-04T15:32:35.596+0500 | 2026-03-25T11:28:28.211+0500
SUBS | SUBS-270 | SUBS-270 | Bug Subtask | Bug Subtask |  | Price is not showing for Report Builder and Offline Mode features in DL | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-270 | [5 empty] | 2026-04-02T10:57:12.711+0500 | 2026-04-02T11:26:20.201+0500
SUBS | SUBS-271 | SUBS-271 | Sub-task | Sub-task |  | Final reviewing after bugs fixing and before IA/Tom's review | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 8 | 8 | Ameer Hamza Khan | 4 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-271 | [5 empty] | 2026-04-02T13:07:29.027+0500 | 2026-04-02T15:13:35.572+0500
SUBS | SUBS-272 | SUBS-272 | Sub-task | Sub-task |  | Added MeterType Update Feature + Unit Testing + Deployments on Staging | Resolved! | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 8 | 8 | Zain Munir | 8 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-272 | [5 empty] | 2026-04-02T13:47:34.698+0500 | 2026-04-02T16:27:08.069+0500
SUBS | SUBS-273 | SUBS-273 | Sub-task | Sub-task |  | Bug Fixing and Discussions | Resolved! | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 2.5 | 2.5 | Faiza Nasir | 2.5 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-273 | [5 empty] | 2026-04-02T14:30:54.503+0500 | 2026-04-06T10:54:39.676+0500
SUBS | SUBS-274 | SUBS-274 | Sub-task | Sub-task |  | Deployments + Data Migration + Product Info Updates | Resolved! | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 8 | 8 | Zain Munir | 8 |  | SUBS-242 | SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-274 | [5 empty] | 2026-04-03T16:38:50.507+0500 | 2026-04-03T16:39:45.655+0500
SUBS | SUBS-275 | SUBS-275 | Sub-task | Sub-task |  | Pricing Demo to TOM | Resolved! | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-275 | [5 empty] | 2026-04-06T10:57:44.427+0500 | 2026-04-06T10:59:23.475+0500
SUBS | SUBS-276 | SUBS-276 | Sub-task | Sub-task |  | Internal review after incorporating all feedbacks | In-Progress | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 12 | 12 | Ameer Hamza Khan | 12 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-276 | [5 empty] | 2026-04-06T14:05:43.331+0500 | 2026-04-06T14:07:57.203+0500
SUBS | SUBS-277 | SUBS-277 | Sub-task | Sub-task |  | OmniConnect's Pricing Review with Asmar | Resolved! |  |  | 2026-04-07 | 2026-04-07 | 1 | 1 | Zain Munir | 1 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-277 | [5 empty] | 2026-04-07T15:59:27.912+0500 | 2026-04-07T16:00:06.122+0500
SUBS | SUBS-278 | SUBS-278 | Sub-task | Sub-task |  | 2nd Pricing review with TOM | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 1.5 | 1.5 | Waqar Rasheed | 1.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-278 | [5 empty] | 2026-04-08T10:49:40.177+0500 | 2026-04-10T10:43:47.064+0500
SUBS | SUBS-279 | SUBS-279 | Sub-task | Sub-task |  | Changes Overview with Asmar | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 0.67 | 0.67 | Faiza Nasir | 0.67 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-279 | [5 empty] | 2026-04-08T12:18:37.398+0500 | 2026-04-08T12:21:30.710+0500
SUBS | SUBS-28 | SUBS-28 | Sub-task | Sub-task |  | DO not delete any plan or product if it is being used in Qoutations | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 4 | 4 | Faiza Nasir | 4 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-28 | [5 empty] | 2026-03-05T12:22:05.607+0500 | 2026-03-25T11:28:29.071+0500
SUBS | SUBS-280 | SUBS-280 | Sub-task | Sub-task |  | Second Demo to Tom | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 1.5 | 1.5 | Faiza Nasir | 1.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-280 | [5 empty] | 2026-04-08T12:21:55.339+0500 | 2026-04-08T12:52:32.420+0500
SUBS | SUBS-281 | SUBS-281 | Sub-task | Sub-task |  | Add sorting mechanism for products and features | Resolved! | 2026-04-08 | 2026-04-10 | 2026-04-08 | 2026-04-08 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-281 | [5 empty] | 2026-04-08T12:53:11.271+0500 | 2026-04-09T12:48:44.418+0500
SUBS | SUBS-282 | SUBS-282 | Sub-task | Sub-task |  | Pricing overview with Asmar | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 1 | 1 | Waqar Rasheed | 1 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-282 | [5 empty] | 2026-04-08T15:21:50.009+0500 | 2026-04-08T15:22:36.249+0500
SUBS | SUBS-283 | SUBS-283 | Sub-task | Sub-task |  | Testing by Waqar After Changes incorporated as per TOM’s feedback. | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 8 | 8 | Waqar Rasheed | 8 |  | SUBS-242 | SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-283 | [5 empty] | 2026-04-08T15:29:37.955+0500 | 2026-04-09T17:28:09.970+0500
SUBS | SUBS-284 | SUBS-284 | Sub-task | Sub-task |  | 2nd Pricing review with Tom | Resolved! |  |  | 2026-04-07 | 2026-04-07 | 1.5 | 1.5 | Zain Munir | 1.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-284 | [5 empty] | 2026-04-09T10:02:43.488+0500 | 2026-04-09T15:52:02.580+0500
SUBS | SUBS-285 | SUBS-285 | Sub-task | Sub-task |  | Incorporate Sorting, Info Icons and UI adjustments in review from Tom | Resolved! |  |  | 2026-04-08 | 2026-04-09 | 15.5 | 15.5 | Zain Munir | 15.5 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-285 | [5 empty] | 2026-04-09T10:04:17.557+0500 | 2026-04-09T15:51:20.477+0500
SUBS | SUBS-286 | SUBS-286 | Bug Subtask | Bug Subtask |  | Calculator Screen Not Reset When Changing Product While Editing Quotation | Resolved |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-286 | [5 empty] | 2026-04-09T12:16:17.047+0500 | 2026-04-09T12:55:00.107+0500
SUBS | SUBS-287 | SUBS-287 | Sub-task | Sub-task |  | Manage Onetime total in quotations | Resolved! | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-287 | [5 empty] | 2026-04-09T12:26:27.601+0500 | 2026-04-09T12:27:04.106+0500
SUBS | SUBS-288 | SUBS-288 | Bug Subtask | Bug Subtask |  | Products Not Loading on Production | Resolved |  |  | 2026-04-09 | 2026-04-09 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | SUBS-241 | SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-241 | https://octopusdtlsupport.atlassian.net/browse/SUBS-288 | [5 empty] | 2026-04-09T14:14:12.942+0500 | 2026-04-09T14:28:04.848+0500
SUBS | SUBS-289 | SUBS-289 | Sub-task | Sub-task |  | Production Deployment - Tom's Feedback | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-242 | SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-242 | https://octopusdtlsupport.atlassian.net/browse/SUBS-289 | [5 empty] | 2026-04-09T14:19:47.388+0500 | 2026-04-09T14:20:20.196+0500
SUBS | SUBS-29 | SUBS-29 | Sub-task | Sub-task |  | Setup 1 active pricing configuration per Product | Resolved! | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-06 | 6 | 6 | Faiza Nasir | 6 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-29 | [5 empty] | 2026-03-05T13:21:10.014+0500 | 2026-03-25T11:28:29.529+0500
SUBS | SUBS-290 | SUBS-290 | Sub-task | Sub-task |  | 3rd Pricing Review with Tom | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5 | 0.5 | Zain Munir | 0.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-290 | [5 empty] | 2026-04-09T15:51:53.460+0500 | 2026-04-09T17:06:04.932+0500
SUBS | SUBS-291 | SUBS-291 | Sub-task | Sub-task |  | 3rd Pricing Review with Tom | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5 | 0.5 | Waqar Rasheed | 0.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-291 | [5 empty] | 2026-04-10T10:44:22.614+0500 | 2026-04-10T10:45:16.346+0500
SUBS | SUBS-292 | SUBS-292 | Sub-task | Sub-task |  | 3rd Pricing Review with Tom | Resolved! | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-292 | [5 empty] | 2026-04-15T12:47:45.228+0500 | 2026-04-15T12:49:38.987+0500
SUBS | SUBS-293 | SUBS-293 | Sub-task | Sub-task |  | IP meeting Demo | Resolved! | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-293 | [5 empty] | 2026-04-15T12:47:55.160+0500 | 2026-04-15T12:48:59.034+0500
SUBS | SUBS-294 | SUBS-294 | Sub-task | Sub-task |  | Pre Launch Demo with Sales Team | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2 | 2 | Zain Munir | 2 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-294 | [5 empty] | 2026-04-21T15:10:12.196+0500 | 2026-04-21T15:11:28.859+0500
SUBS | SUBS-295 | SUBS-295 | Sub-task | Sub-task |  | Pre-Launch Demo Sales Team | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 1.5 | 1.5 | Faiza Nasir | 1.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-295 | [5 empty] | 2026-04-22T16:16:06.695+0500 | 2026-04-22T16:16:39.712+0500
SUBS | SUBS-296 | SUBS-296 | Sub-task | Sub-task |  | CRM ID Verification | Resolved! | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 1 | Waqar Rasheed | 1 |  | SUBS-240 | SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-296 | [5 empty] | 2026-04-23T09:55:34.132+0500 | 2026-04-23T14:51:05.387+0500
SUBS | SUBS-297 | SUBS-297 | Sub-task | Sub-task |  | CRM Id Addition & Pre Launch Review Modifications | Resolved! | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 10.5 | 10.5 | Zain Munir | 10.5 |  | SUBS-239 | SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-239 | https://octopusdtlsupport.atlassian.net/browse/SUBS-297 | [5 empty] | 2026-04-23T10:52:52.869+0500 | 2026-04-23T16:24:55.466+0500
SUBS | SUBS-298 | SUBS-298 | Sub-task | Sub-task |  | Verification of Sales Team Configuration Requirements | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 3.5 | 3.5 | Waqar Rasheed | 3.5 |  | SUBS-240 | SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-298 | [5 empty] | 2026-04-23T14:53:25.992+0500 | 2026-04-24T11:45:47.842+0500
SUBS | SUBS-299 | SUBS-299 | Sub-task | Sub-task |  | Meeting with KM for OmniDocs Pricing | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5 | 0.5 | Zain Munir | 0.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-299 | [5 empty] | 2026-04-23T16:25:22.464+0500 | 2026-04-23T16:26:07.607+0500
SUBS | SUBS-30 | SUBS-30 | Sub-task | Sub-task |  | Admin Improvements + One Time Payment Implementation | Resolved! | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 13 | 13 | Zain Munir | 13 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-30 | [5 empty] | 2026-03-05T14:54:27.409+0500 | 2026-03-25T11:28:30.475+0500
SUBS | SUBS-300 | SUBS-300 | Sub-task | Sub-task |  | Meeting with Khurram Mir over Pricing | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5 | 0.5 | Faiza Nasir | 0.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-300 | [5 empty] | 2026-04-23T16:37:40.474+0500 | 2026-04-23T16:43:18.736+0500
SUBS | SUBS-301 | SUBS-301 | Sub-task | Sub-task |  | Meeting with Khurram Mir for OmniDocs Pricing | Resolved! | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 0.5 | 0.5 | Waqar Rasheed | 0.5 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-301 | [5 empty] | 2026-04-23T16:51:21.607+0500 | 2026-04-23T16:52:03.501+0500
SUBS | SUBS-302 | SUBS-302 | Sub-task | Sub-task |  | Omni Docs Configuration | Resolved! | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 8 | 8 | Waqar Rasheed | 8 |  | SUBS-240 | SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-302 | [5 empty] | 2026-04-27T11:45:56.582+0500 | 2026-04-27T16:38:31.617+0500
SUBS | SUBS-303 | SUBS-303 | Sub-task | Sub-task |  | Meeting with Asmar for Omni Connect Pricing and Sales feedback | Resolved! | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.75 | 0.75 | Waqar Rasheed | 0.75 |  | SUBS-238 | SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-238 | https://octopusdtlsupport.atlassian.net/browse/SUBS-303 | [5 empty] | 2026-04-28T16:26:41.411+0500 | 2026-04-28T16:27:41.239+0500
SUBS | SUBS-304 | SUBS-304 | Sub-task | Sub-task |  | Incorporate Omni Connect Enhancements | Resolved! | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 4 | 4 | Waqar Rasheed | 4 |  | SUBS-240 | SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-240 | https://octopusdtlsupport.atlassian.net/browse/SUBS-304 | [5 empty] | 2026-04-29T15:08:50.009+0500 | 2026-04-29T15:09:41.423+0500
SUBS | SUBS-31 | SUBS-31 | Sub-task | Sub-task |  | Special Characters Not Handled Correctly in Feature Name Field | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-31 | [5 empty] | 2026-03-10T13:15:04.010+0500 | 2026-03-25T11:28:30.945+0500
SUBS | SUBS-32 | SUBS-32 | Sub-task | Sub-task |  | Meter Type UI Fix + Tiers validations | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1.5 | 1.5 | Sarmad Sabir | 1.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-32 | [5 empty] | 2026-03-10T13:24:21.159+0500 | 2026-03-25T11:28:31.501+0500
SUBS | SUBS-33 | SUBS-33 | Sub-task | Sub-task |  | On Save and Update Quotation, redirect the user to My Quotation page | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-33 | [5 empty] | 2026-03-10T13:24:37.026+0500 | 2026-03-25T11:28:32.024+0500
SUBS | SUBS-34 | SUBS-34 | Sub-task | Sub-task |  | Created by, Updated By, Created On, Column Should be implemented in the Application. | To Do |  |  |  |  | 0 | 0 | Faiza Nasir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-34 | [5 empty] | 2026-03-10T13:27:11.836+0500 | 2026-03-25T11:28:32.526+0500
SUBS | SUBS-35 | SUBS-35 | Sub-task | Sub-task |  | UI improvement for Plans screen | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-35 | [5 empty] | 2026-03-10T13:27:38.886+0500 | 2026-03-25T11:28:33.004+0500
SUBS | SUBS-36 | SUBS-36 | Sub-task | Sub-task |  | UI improvement for tiers screen | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-36 | [5 empty] | 2026-03-10T13:28:02.137+0500 | 2026-03-25T11:28:33.500+0500
SUBS | SUBS-37 | SUBS-37 | Sub-task | Sub-task |  | UI improvement for Preview screen | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.33 | 0.33 | Sarmad Sabir | 0.33 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-37 | [5 empty] | 2026-03-10T13:28:31.151+0500 | 2026-03-25T11:28:33.985+0500
SUBS | SUBS-38 | SUBS-38 | Sub-task | Sub-task |  | UI improvement for Parameters Screen | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.67 | 0.67 | Sarmad Sabir | 0.67 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-38 | [5 empty] | 2026-03-10T13:28:58.342+0500 | 2026-03-25T11:28:34.665+0500
SUBS | SUBS-39 | SUBS-39 | Sub-task | Sub-task |  | UI improvement for Versions screen | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1 | 1 | Sarmad Sabir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-39 | [5 empty] | 2026-03-10T13:29:12.905+0500 | 2026-03-25T11:28:35.136+0500
SUBS | SUBS-40 | SUBS-40 | Sub-task | Sub-task |  | UI improvement for Products and Features screen | Resolved! | 2026-03-10 |  | 2026-03-10 | 2026-03-10 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-40 | [5 empty] | 2026-03-10T13:29:31.654+0500 | 2026-03-25T11:28:35.619+0500
SUBS | SUBS-41 | SUBS-41 | Sub-task | Sub-task |  | Change “Platform Fees” Text to “Subscription Fee” on Viewing Quotation Screen | Resolved! |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-41 | [5 empty] | 2026-03-10T14:10:00.471+0500 | 2026-03-25T11:28:36.074+0500
SUBS | SUBS-42 | SUBS-42 | Sub-task | Sub-task |  | Implement Search Functionality on Share Quotation Popup | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 1 | 1 | Muhammad Ahmad Saleem | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-42 | [5 empty] | 2026-03-10T14:21:20.764+0500 | 2026-03-25T11:28:36.575+0500
SUBS | SUBS-43 | SUBS-43 | Sub-task | Sub-task |  | QA Reported Bugs related to Admin screens | Resolved! | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-11 | 13 | 13 | Zain Munir | 13 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-43 | [5 empty] | 2026-03-10T15:11:30.816+0500 | 2026-03-25T11:28:37.024+0500
SUBS | SUBS-44 | SUBS-44 | Sub-task | Sub-task |  | Project Demo | Resolved! | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-44 | [5 empty] | 2026-03-10T15:13:42.464+0500 | 2026-03-25T11:28:37.471+0500
SUBS | SUBS-45 | SUBS-45 | Sub-task | Sub-task |  | Export Document UI Fix + Subscription fee text | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 1 | 1 | Sarmad Sabir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-45 | [5 empty] | 2026-03-10T15:14:56.104+0500 | 2026-03-25T11:28:37.903+0500
SUBS | SUBS-46 | SUBS-46 | Sub-task | Sub-task |  | Share functionality fixed for quotations | Resolved! | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 0.5 | 0.5 | Sarmad Sabir | 0.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-46 | [5 empty] | 2026-03-10T15:15:11.804+0500 | 2026-03-25T11:28:38.402+0500
SUBS | SUBS-47 | SUBS-47 | Sub-task | Sub-task |  | Bugs, from QA and findings during unit testing, fixing | Resolved! | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-03-13 | 48 | 48 | Ameer Hamza Khan | 48 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-47 | [5 empty] | 2026-03-12T14:19:05.608+0500 | 2026-03-25T11:28:38.860+0500
SUBS | SUBS-48 | SUBS-48 | Sub-task | Sub-task |  | Bugs, from QA and findings during unit testing, fixing | Resolved! | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 6.5 | 6.5 | Zain Munir | 6.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-48 | [5 empty] | 2026-03-12T15:09:49.974+0500 | 2026-03-25T11:28:39.337+0500
SUBS | SUBS-49 | SUBS-49 | Sub-task | Sub-task |  | Product Demo Discussion + Preparation | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5 | 6.5 | Zain Munir | 6.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-49 | [5 empty] | 2026-03-16T09:56:47.002+0500 | 2026-03-25T11:28:39.775+0500
SUBS | SUBS-5 | SUBS-5 | Epic | Epic |  | Subscription Management | In-Progress | 2026-01-07 | 2026-03-06 |  |  | 520 | 520 | Faiza Nasir | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | [5 empty] | 2026-01-09T10:02:02.653+0500 | 2026-03-25T11:18:57.476+0500
SUBS | SUBS-50 | SUBS-50 | Sub-task | Sub-task |  | Update Brochures of Configured Products with Latest Information | Resolved! |  |  |  |  | 0 | 0 | Zain Munir | 0 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-50 | [5 empty] | 2026-03-16T10:40:31.520+0500 | 2026-03-25T11:28:40.231+0500
SUBS | SUBS-51 | SUBS-51 | Sub-task | Sub-task |  | Demo Preparation | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 8 | 8 | Faiza Nasir | 5.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-51 | [5 empty] | 2026-03-16T12:54:12.132+0500 | 2026-03-25T11:28:40.681+0500
SUBS | SUBS-52 | SUBS-52 | Sub-task | Sub-task |  | Bug Fixing | Resolved! | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-16 | 16 | 16 | Faiza Nasir | 11 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-52 | [5 empty] | 2026-03-16T12:54:58.309+0500 | 2026-03-25T11:28:41.127+0500
SUBS | SUBS-53 | SUBS-53 | Sub-task | Sub-task |  | QA Reported Bugs Fix for Plans Screen | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2.5 | 2.5 | Sarmad Sabir | 2.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-53 | [5 empty] | 2026-03-16T12:55:40.017+0500 | 2026-03-25T11:28:41.624+0500
SUBS | SUBS-54 | SUBS-54 | Sub-task | Sub-task |  | QA Reported Bugs Fix for Tiers Screen | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-54 | [5 empty] | 2026-03-16T12:56:01.319+0500 | 2026-03-25T11:28:42.131+0500
SUBS | SUBS-55 | SUBS-55 | Sub-task | Sub-task |  | Demo Prep / Data Prep / Bugs Fixing for Demo | Resolved! | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 6.5 | 6.5 | Sarmad Sabir | 6.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-55 | [5 empty] | 2026-03-16T13:39:26.685+0500 | 2026-03-25T11:28:42.564+0500
SUBS | SUBS-56 | SUBS-56 | Sub-task | Sub-task |  | Add “Created At” Column on My Quotation Screen and Correct "Last Modified" column Behavior | Resolved! | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-56 | [5 empty] | 2026-03-16T14:44:37.697+0500 | 2026-03-25T11:28:42.991+0500
SUBS | SUBS-57 | SUBS-57 | Sub-task | Sub-task |  | Discussions on KT | Resolved! | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 0.42 | 0.42 | Faiza Nasir | 0.42 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-57 | [5 empty] | 2026-03-16T14:49:27.429+0500 | 2026-03-25T11:28:43.447+0500
SUBS | SUBS-58 | SUBS-58 | Sub-task | Sub-task |  | Task Implementations and Bugs Fixing | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5 | 6.5 | Zain Munir | 6.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-58 | [5 empty] | 2026-03-16T14:55:53.328+0500 | 2026-03-25T11:28:43.883+0500
SUBS | SUBS-59 | SUBS-59 | Sub-task | Sub-task |  | Figuring out issues for preview screen on logout | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-59 | [5 empty] | 2026-03-17T11:22:57.810+0500 | 2026-03-25T11:28:44.314+0500
SUBS | SUBS-6 | SUBS-6 | Story | Story |  | Research/URS | Resolved! | 2026-01-07 | 2026-01-08 |  |  | 32 | 32 | Faiza Nasir | 18 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-6 | [5 empty] | 2026-02-04T15:30:31.436+0500 | 2026-03-25T11:28:16.966+0500
SUBS | SUBS-60 | SUBS-60 | Sub-task | Sub-task |  | Preview stale cache fix for runtime count | Resolved! | 2026-03-17 |  | 2026-03-17 | 2026-03-17 | 3 | 3 | Sarmad Sabir | 3 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-60 | [5 empty] | 2026-03-17T11:25:15.123+0500 | 2026-03-25T11:28:44.908+0500
SUBS | SUBS-61 | SUBS-61 | Sub-task | Sub-task |  | Currency issues on plans and preview page | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1 | 1 | Sarmad Sabir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-61 | [5 empty] | 2026-03-17T12:53:24.101+0500 | 2026-03-25T11:28:45.502+0500
SUBS | SUBS-62 | SUBS-62 | Sub-task | Sub-task |  | Fixed Issues of My Quotation and Calculator screen | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 3.5 | 3.5 | Muhammad Ahmad Saleem | 3.5 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-62 | [5 empty] | 2026-03-17T15:20:18.091+0500 | 2026-03-25T11:28:45.988+0500
SUBS | SUBS-63 | SUBS-63 | Sub-task | Sub-task |  | Bug fixing | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 1 | 1 | Faiza Nasir | 1 |  | SUBS-12 | SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-12 | https://octopusdtlsupport.atlassian.net/browse/SUBS-63 | [5 empty] | 2026-03-17T15:26:40.943+0500 | 2026-03-25T11:28:46.408+0500
SUBS | SUBS-64 | SUBS-64 | Sub-task | Sub-task |  | OMNI- Chat Testing | Resolved! | 2026-03-06 | 2026-03-11 | 2026-03-09 | 2026-03-16 | 32 | 32 | Waqar Rasheed | 30 |  | SUBS-11 | SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-64 | [5 empty] | 2026-02-13T17:37:32.785+0500 | 2026-03-25T11:28:46.885+0500
SUBS | SUBS-65 | SUBS-65 | Sub-task | Sub-task |  | Digital Log Testing | Resolved! | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | 32 | 32 | Namra Zahid | 32 |  | SUBS-11 | SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-65 | [5 empty] | 2026-02-13T17:38:19.331+0500 | 2026-03-25T11:28:47.331+0500
SUBS | SUBS-66 | SUBS-66 | Sub-task | Sub-task |  | Fintech Testing | Resolved! | 2026-03-06 | 2026-03-11 | 2026-03-06 | 2026-03-17 | 40 | 40 | Namra Zahid | 52 |  | SUBS-11 | SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-66 | [5 empty] | 2026-02-13T17:38:35.806+0500 | 2026-03-25T11:28:47.763+0500
SUBS | SUBS-67 | SUBS-67 | Sub-task | Sub-task |  | OMNI Connect Testing | Resolved! | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-17 | 40 | 40 | Waqar Rasheed | 39 |  | SUBS-11 | SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-67 | [5 empty] | 2026-02-13T17:38:50.102+0500 | 2026-03-25T11:28:48.330+0500
SUBS | SUBS-68 | SUBS-68 | Sub-task | Sub-task |  | Product Mapping | Resolved! | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | 16 | 16 | Muhammad Abbas | 14 |  | SUBS-11 | SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-68 | [5 empty] | 2026-02-27T15:06:39.526+0500 | 2026-03-25T11:28:48.790+0500
SUBS | SUBS-69 | SUBS-69 | Sub-task | Sub-task |  | Testing by Zeeshan | Resolved! | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-11 | 16 | 16 | Zeeshan Sarwar | 10.5 |  | SUBS-11 | SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-11 | https://octopusdtlsupport.atlassian.net/browse/SUBS-69 | [5 empty] | 2026-03-09T10:42:05.365+0500 | 2026-03-25T11:28:49.231+0500
SUBS | SUBS-7 | SUBS-7 | Story | Story |  | DDS | To Do | 2026-04-04 | 2026-04-17 |  |  | 0 | 0 | Hassan Malik | 0 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-7 | [5 empty] | 2026-02-04T15:33:09.110+0500 | 2026-03-25T13:48:16.911+0500
SUBS | SUBS-70 | SUBS-70 | Sub-task | Sub-task |  | Frontend Setup & Requirements Discussion | Resolved! | 2026-01-07 | 2026-01-07 | 2026-01-09 | 2026-01-09 | 8 | 8 | Ali Qumail | 8 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-70 | [5 empty] | 2026-01-09T10:20:37.796+0500 | 2026-03-25T11:28:49.703+0500
SUBS | SUBS-71 | SUBS-71 | Sub-task | Sub-task |  | Frontend Setup | Resolved! | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-71 | [5 empty] | 2026-01-12T11:20:57.583+0500 | 2026-03-25T11:28:50.159+0500
SUBS | SUBS-72 | SUBS-72 | Sub-task | Sub-task |  | Pages for Sales Person | Resolved! |  |  |  |  | 0 | 0 | Sarmad Sabir | 0 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-72 | [5 empty] | 2026-01-12T11:23:13.796+0500 | 2026-03-25T11:28:50.589+0500
SUBS | SUBS-73 | SUBS-73 | Sub-task | Sub-task |  | Backend Project Setup | Resolved! | 2026-01-08 | 2026-02-03 | 2026-01-08 | 2026-02-02 | 8.5 | 8.5 | Faiza Nasir | 8.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-73 | [5 empty] | 2026-01-15T10:51:08.176+0500 | 2026-03-25T11:28:51.036+0500
SUBS | SUBS-74 | SUBS-74 | Sub-task | Sub-task |  | Pages for super-admin | Resolved! | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 4 | 4 | Sarmad Sabir | 4 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-74 | [5 empty] | 2026-01-16T14:54:42.749+0500 | 2026-03-25T11:28:51.481+0500
SUBS | SUBS-75 | SUBS-75 | Sub-task | Sub-task |  | Static pages for sales-agent | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-75 | [5 empty] | 2026-01-21T14:24:04.412+0500 | 2026-03-25T11:28:51.900+0500
SUBS | SUBS-76 | SUBS-76 | Sub-task | Sub-task |  | Static pages for approver | Resolved! | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2 | 2 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-76 | [5 empty] | 2026-01-21T14:24:13.594+0500 | 2026-03-25T11:28:52.378+0500
SUBS | SUBS-77 | SUBS-77 | Sub-task | Sub-task |  | Dark mode | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 4 | 4 | Sarmad Sabir | 4 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-77 | [5 empty] | 2026-01-23T16:06:47.792+0500 | 2026-03-25T11:28:52.815+0500
SUBS | SUBS-78 | SUBS-78 | Sub-task | Sub-task |  | Azure setup + Deployment | Resolved! | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 4 | 4 | Sarmad Sabir | 4 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-78 | [5 empty] | 2026-01-23T16:07:34.520+0500 | 2026-03-25T11:28:53.309+0500
SUBS | SUBS-79 | SUBS-79 | Sub-task | Sub-task |  | Designing KT To Sarmad | Resolved! | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-04 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-79 | [5 empty] | 2026-02-04T16:01:43.374+0500 | 2026-03-25T11:28:53.749+0500
SUBS | SUBS-8 | SUBS-8 | Story | Story |  | User Manual | To Do |  |  |  |  | 40 | 40 | Hassan Malik | 0 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-8 | [5 empty] | 2026-02-04T16:24:56.177+0500 | 2026-03-25T11:28:18.418+0500
SUBS | SUBS-80 | SUBS-80 | Sub-task | Sub-task |  | Entity Framework Code first approach setup | Resolved! | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2 | 2 | Faiza Nasir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-80 | [5 empty] | 2026-02-04T16:02:33.059+0500 | 2026-03-25T11:28:54.206+0500
SUBS | SUBS-81 | SUBS-81 | Sub-task | Sub-task |  | Initial Migration Creation | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-81 | [5 empty] | 2026-02-04T16:02:50.657+0500 | 2026-03-25T11:28:54.651+0500
SUBS | SUBS-82 | SUBS-82 | Sub-task | Sub-task |  | Installing required Dependencies | Resolved! | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 3 | 3 | Faiza Nasir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-82 | [5 empty] | 2026-02-09T11:21:45.372+0500 | 2026-03-25T11:28:55.058+0500
SUBS | SUBS-83 | SUBS-83 | Sub-task | Sub-task |  | User Management API Development | Resolved! | 2026-02-06 | 2026-02-18 | 2026-02-06 | 2026-02-18 | 9 | 9 | Faiza Nasir | 9 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-83 | [5 empty] | 2026-02-09T11:22:14.650+0500 | 2026-03-25T11:28:55.463+0500
SUBS | SUBS-84 | SUBS-84 | Sub-task | Sub-task |  | Login / Authentication APIs Development | Resolved! | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-09 | 4 | 4 | Faiza Nasir | 4 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-84 | [5 empty] | 2026-02-09T16:40:48.951+0500 | 2026-03-25T11:28:55.870+0500
SUBS | SUBS-85 | SUBS-85 | Sub-task | Sub-task |  | Pricing Configuration / PRICING_CONFIG_APPROVAL_EVENTS / Products / Features API Development | Resolved! | 2026-02-10 | 2026-02-11 | 2026-02-10 | 2026-02-11 | 10 | 10 | Faiza Nasir | 9.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-85 | [5 empty] | 2026-02-12T11:30:39.456+0500 | 2026-03-25T11:28:56.347+0500
SUBS | SUBS-86 | SUBS-86 | Sub-task | Sub-task |  | Plans / Plan Tiers / PLAN_TIER_SKUS / Allowance / SKU_ALLOWANCES API Development | Resolved! | 2026-02-11 | 2026-02-23 | 2026-02-12 | 2026-02-23 | 9.5 | 9.5 | Faiza Nasir | 9.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-86 | [5 empty] | 2026-02-12T16:02:32.543+0500 | 2026-03-25T11:28:56.775+0500
SUBS | SUBS-87 | SUBS-87 | Sub-task | Sub-task |  | QUOTES / QUOTE_EXPORTS /QUOTE_LINE_ITEMS / QUOTE_NOTES / QOUTE STATUS API Development | Resolved! | 2026-02-17 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5 | 6.5 | Faiza Nasir | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-87 | [5 empty] | 2026-02-12T16:06:30.392+0500 | 2026-03-25T11:28:57.202+0500
SUBS | SUBS-88 | SUBS-88 | Sub-task | Sub-task |  | AUDIT_LOGS APIs Development | Resolved! | 2026-02-13 | 2026-02-16 | 2026-02-13 | 2026-02-16 | 7 | 7 | Faiza Nasir | 7 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-88 | [5 empty] | 2026-02-12T16:07:28.049+0500 | 2026-03-25T11:28:57.633+0500
SUBS | SUBS-89 | SUBS-89 | Sub-task | Sub-task |  | METER_TYPES API Development | Resolved! | 2026-02-16 | 2026-02-19 | 2026-02-16 | 2026-02-18 | 7 | 7 | Faiza Nasir | 7 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-89 | [5 empty] | 2026-02-12T16:11:45.012+0500 | 2026-03-25T11:28:58.037+0500
SUBS | SUBS-9 | SUBS-9 | Story | Story |  | Production Release | To Do |  |  |  |  | 48 | 48 | Ameer Hamza Khan | 24 |  | SUBS-5 | SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-5 | https://octopusdtlsupport.atlassian.net/browse/SUBS-9 | [5 empty] | 2026-02-04T16:25:06.254+0500 | 2026-03-25T11:28:18.937+0500
SUBS | SUBS-90 | SUBS-90 | Sub-task | Sub-task |  | APIs Creation to view products along with plans | Resolved! | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2 | 2 | Faiza Nasir | 1.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-90 | [5 empty] | 2026-02-13T11:42:08.846+0500 | 2026-03-25T11:28:58.464+0500
SUBS | SUBS-91 | SUBS-91 | Sub-task | Sub-task |  | Frontend and Backend setup | Resolved! | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 5 | 5 | Muhammad Ahmad Saleem | 5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-91 | [5 empty] | 2026-02-16T16:13:05.803+0500 | 2026-03-25T11:28:58.884+0500
SUBS | SUBS-92 | SUBS-92 | Sub-task | Sub-task |  | Login Page API Integration | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 4 | 4 | Sarmad Sabir | 2 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-92 | [5 empty] | 2026-02-16T16:32:08.270+0500 | 2026-03-25T11:28:59.447+0500
SUBS | SUBS-93 | SUBS-93 | Sub-task | Sub-task |  | Products API Integration (Super Admin) | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4 | 4 | Sarmad Sabir | 3 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-93 | [5 empty] | 2026-02-17T12:07:47.918+0500 | 2026-03-25T11:28:59.947+0500
SUBS | SUBS-94 | SUBS-94 | Sub-task | Sub-task |  | Reset Pwd Email & JWT Bearer Token | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 4 | 4 | Zain Munir | 4 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-94 | [5 empty] | 2026-02-18T10:12:20.010+0500 | 2026-03-25T11:29:00.530+0500
SUBS | SUBS-95 | SUBS-95 | Sub-task | Sub-task |  | Login API Integration + Authorization | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-95 | [5 empty] | 2026-02-18T15:01:37.667+0500 | 2026-03-25T11:29:01.102+0500
SUBS | SUBS-96 | SUBS-96 | Sub-task | Sub-task |  | User + Product API Integration | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-96 | [5 empty] | 2026-02-18T15:07:14.569+0500 | 2026-03-25T11:29:01.576+0500
SUBS | SUBS-97 | SUBS-97 | Sub-task | Sub-task |  | Meter Types Frontend, API Modification & Integration | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Zain Munir | 8 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-97 | [5 empty] | 2026-02-18T16:11:25.794+0500 | 2026-03-25T11:29:02.007+0500
SUBS | SUBS-98 | SUBS-98 | Sub-task | Sub-task |  | Roles, Forgot, Reset, User API Integration | Resolved! | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 8 | 8 | Muhammad Ahmad Saleem | 8 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-98 | [5 empty] | 2026-02-18T17:57:50.672+0500 | 2026-03-25T11:29:02.551+0500
SUBS | SUBS-99 | SUBS-99 | Sub-task | Sub-task |  | Completed User, Roles Frontend and API Integration | Resolved! | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 6.5 | 6.5 | Muhammad Ahmad Saleem | 6.5 |  | SUBS-13 | SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-13 | https://octopusdtlsupport.atlassian.net/browse/SUBS-99 | [5 empty] | 2026-02-20T09:19:30.885+0500 | 2026-03-25T11:29:02.980+0500
WOM | WOM-125 | WOM-125 | Task | Task |  | Field Service Maintenance | Resolved! | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 0 | 0 | Muhammad Imran Aslam | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-125 | [5 empty] | 2026-01-02T11:40:54.621+0500 | 2026-01-02T11:42:32.062+0500
WOM | WOM-126 | WOM-126 | Task | Task |  | Field Service Configuration | Resolved! | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 0 | 0 | Muhammad Imran Aslam | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-126 | [5 empty] | 2026-01-02T11:42:58.425+0500 | 2026-01-02T11:44:07.548+0500
WOM | WOM-127 | WOM-127 | Task | Task |  | Field Service Configuration | Resolved! | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 0 | 0 | Muhammad Imran Aslam | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-127 | [5 empty] | 2026-01-06T10:01:38.080+0500 | 2026-01-06T10:04:26.189+0500
WOM | WOM-128 | WOM-128 | Task | Task |  | Field Service Configuration | Resolved! | 2026-01-06 | 2026-01-07 | 2026-01-06 | 2026-01-07 | 0 | 0 | Muhammad Imran Aslam | 16 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-128 | [5 empty] | 2026-01-06T10:04:59.037+0500 | 2026-01-06T10:07:15.333+0500
WOM | WOM-129 | WOM-129 | Task | Task |  | Field Service Configuration | Resolved! | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 0 | 0 | Muhammad Imran Aslam | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-129 | [5 empty] | 2026-01-09T16:17:03.402+0500 | 2026-01-09T16:18:42.776+0500
WOM | WOM-130 | WOM-130 | Task | Task |  | Field Service Configuration | Resolved! | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 0 | 0 | Muhammad Imran Aslam | 8 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-130 | [5 empty] | 2026-01-09T16:19:25.443+0500 | 2026-01-09T16:20:43.482+0500
WOM | WOM-131 | WOM-131 | Task | Task |  | Field Service Configuration | Resolved! | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-13 | 0 | 0 | Muhammad Imran Aslam | 16 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-131 | [5 empty] | 2026-01-13T09:20:17.067+0500 | 2026-01-13T09:22:40.254+0500
WOM | WOM-132 | WOM-132 | Task | Task |  | Field Service Configuration | Resolved! | 2026-01-15 | 2026-01-16 | 2026-01-15 | 2026-01-16 | 0 | 0 | Muhammad Imran Aslam | 16 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-132 | [5 empty] | 2026-01-16T11:23:34.478+0500 | 2026-01-16T11:25:27.853+0500
WOM | WOM-133 | WOM-133 | Task | Task |  | Field Service Maintenance | Considered in Roadmap & Queued |  |  |  |  | 0 | 0 | Muhammad Imran Aslam | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-133 | [5 empty] | 2026-02-02T14:40:43.990+0500 | 2026-02-02T14:40:57.255+0500
WOM | WOM-134 | WOM-134 | Epic | Epic |  | Field Service Configuration Maintenance 2026 | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 760 | 760 | Muhammad Imran Aslam | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | [5 empty] | 2026-02-02T14:45:21.314+0500 | 2026-03-05T10:03:38.459+0500
WOM | WOM-135 | WOM-135 | Story | Story |  | Field Service Maintenance | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 96 | 96 | Muhammad Imran Aslam | 22.5 |  | WOM-134 | WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | [5 empty] | 2026-02-02T14:46:57.280+0500 | 2026-03-05T10:09:17.059+0500
WOM | WOM-136 | WOM-136 | Sub-task | Sub-task |  | Field Service Maintenance February 2026 | Resolved! | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-135 | WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-136 | [5 empty] | 2026-02-02T14:50:21.684+0500 | 2026-02-23T13:35:10.498+0500
WOM | WOM-137 | WOM-137 | Story | Story |  | Field Service Configuration | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 96 | 96 | Muhammad Imran Aslam | 22.5 |  | WOM-134 | WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | [5 empty] | 2026-02-02T15:12:48.853+0500 | 2026-03-05T10:19:01.648+0500
WOM | WOM-138 | WOM-138 | Sub-task | Sub-task |  | Field Service Configuration February 2026 | Resolved! | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-137 | WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-138 | [5 empty] | 2026-02-02T15:15:11.087+0500 | 2026-02-23T13:34:54.314+0500
WOM | WOM-139 | WOM-139 | Story | Story |  | Field Service Configuration | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 192 | 192 | Muhammad Imran Aslam | 45 |  | WOM-134 | WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | [5 empty] | 2026-02-03T14:38:19.636+0500 | 2026-03-05T10:21:39.506+0500
WOM | WOM-140 | WOM-140 | Story | Story |  | Field Service Configuration | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 96 | 96 | Muhammad Imran Aslam | 22.5 |  | WOM-134 | WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | [5 empty] | 2026-02-03T14:41:01.219+0500 | 2026-03-05T10:24:47.860+0500
WOM | WOM-141 | WOM-141 | Story | Story |  | Field Service Configuration | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 96 | 96 | Muhammad Imran Aslam | 22.5 |  | WOM-134 | WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | [5 empty] | 2026-02-03T14:43:27.204+0500 | 2026-03-05T10:26:47.852+0500
WOM | WOM-142 | WOM-142 | Story | Story |  | Field Service Configuration | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 192 | 192 | Muhammad Imran Aslam | 45 |  | WOM-134 | WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | [5 empty] | 2026-02-03T14:46:27.973+0500 | 2026-03-05T10:29:07.015+0500
WOM | WOM-143 | WOM-143 | Story | Story |  | Field Service Configuration | Considered in Roadmap & Queued | 2026-01-01 | 2026-12-31 |  |  | 192 | 192 | Muhammad Imran Aslam | 40 |  | WOM-134 | WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-134 | https://octopusdtlsupport.atlassian.net/browse/WOM-143 | [5 empty] | 2026-02-03T14:47:47.770+0500 | 2026-03-30T11:48:38.326+0500
WOM | WOM-144 | WOM-144 | Sub-task | Sub-task |  | Field Service Configuration February 2026 | Resolved! | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | 16 | 16 | Muhammad Imran Aslam | 16 |  | WOM-139 | WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-144 | [5 empty] | 2026-02-03T14:53:23.845+0500 | 2026-02-23T13:34:24.589+0500
WOM | WOM-145 | WOM-145 | Sub-task | Sub-task |  | Field Service Configuration February 2026 | Resolved! | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-140 | WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-145 | [5 empty] | 2026-02-03T14:57:23.155+0500 | 2026-02-23T13:33:59.284+0500
WOM | WOM-146 | WOM-146 | Sub-task | Sub-task |  | Field Service Configuration February 2026 | Resolved! | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-141 | WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-146 | [5 empty] | 2026-02-03T14:59:36.235+0500 | 2026-02-23T13:33:39.841+0500
WOM | WOM-147 | WOM-147 | Sub-task | Sub-task |  | Field Service Configuration February 2026 | Resolved! | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | 13 | 13 | Muhammad Imran Aslam | 13 |  | WOM-142 | WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-147 | [5 empty] | 2026-02-03T15:01:43.886+0500 | 2026-02-24T13:19:57.065+0500
WOM | WOM-148 | WOM-148 | Sub-task | Sub-task |  | Field Service Maintenance March 2026 | Resolved! | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | WOM-135 | WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-148 | [5 empty] | 2026-02-09T11:19:25.084+0500 | 2026-03-09T12:40:05.241+0500
WOM | WOM-149 | WOM-149 | Sub-task | Sub-task |  | Field Service Configuration March 2026 | Resolved! | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | WOM-137 | WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-149 | [5 empty] | 2026-02-09T11:22:22.683+0500 | 2026-03-03T12:52:05.529+0500
WOM | WOM-150 | WOM-150 | Sub-task | Sub-task |  | Field Service Configuration March 2026 | Resolved! | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-10 | 13 | 13 | Muhammad Imran Aslam | 13 |  | WOM-139 | WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-150 | [5 empty] | 2026-02-09T11:26:26.199+0500 | 2026-03-10T11:23:05.382+0500
WOM | WOM-151 | WOM-151 | Sub-task | Sub-task |  | Field Service Configuration March 2026 | Resolved! | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | WOM-140 | WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-151 | [5 empty] | 2026-02-09T11:28:55.519+0500 | 2026-03-16T15:19:34.343+0500
WOM | WOM-152 | WOM-152 | Sub-task | Sub-task |  | Field Service Configuration March 2026 | Resolved! | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 6.5 | 6.5 | Muhammad Imran Aslam | 6.5 |  | WOM-141 | WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-152 | [5 empty] | 2026-02-09T11:31:58.474+0500 | 2026-03-17T15:11:36.077+0500
WOM | WOM-153 | WOM-153 | Sub-task | Sub-task |  | Field Service Configuration March 2026 | Resolved! | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-143 | WOM-143 | https://octopusdtlsupport.atlassian.net/browse/WOM-143 | https://octopusdtlsupport.atlassian.net/browse/WOM-153 | [5 empty] | 2026-02-09T11:34:35.566+0500 | 2026-03-24T15:02:49.069+0500
WOM | WOM-154 | WOM-154 | Sub-task | Sub-task |  | Field Service Configuration March 2026 | Resolved! | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 16 | 16 | Muhammad Imran Aslam | 16 |  | WOM-142 | WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-154 | [5 empty] | 2026-02-09T11:36:21.726+0500 | 2026-03-31T11:59:35.694+0500
WOM | WOM-155 | WOM-155 | Sub-task | Sub-task |  | Field Service Configuration and Testing April 2026 | Resolved! | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-135 | WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-155 | [5 empty] | 2026-03-31T12:16:50.345+0500 | 2026-04-06T16:25:35.162+0500
WOM | WOM-156 | WOM-156 | Sub-task | Sub-task |  | Field Service Configuration and Testing April 2026 | Resolved! | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-137 | WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-156 | [5 empty] | 2026-03-31T12:20:24.527+0500 | 2026-04-07T12:38:49.741+0500
WOM | WOM-157 | WOM-157 | Sub-task | Sub-task |  | Field Service Configuration and Testing April 2026 | Resolved! | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 16 | 16 | Muhammad Imran Aslam | 16 |  | WOM-139 | WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-157 | [5 empty] | 2026-03-31T14:29:22.146+0500 | 2026-04-14T10:37:30.940+0500
WOM | WOM-158 | WOM-158 | Sub-task | Sub-task |  | Field Service Configuration and Testing April 2026 | Resolved! | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-140 | WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-158 | [5 empty] | 2026-03-31T14:38:59.781+0500 | 2026-04-20T11:32:49.842+0500
WOM | WOM-159 | WOM-159 | Sub-task | Sub-task |  | CRM AMS Configuration and Testing April 2026 | Resolved! | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 8 | 8 | Muhammad Imran Aslam | 8 |  | WOM-141 | WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-159 | [5 empty] | 2026-03-31T14:42:03.590+0500 | 2026-04-21T12:38:54.207+0500
WOM | WOM-160 | WOM-160 | Sub-task | Sub-task |  | Field Service Configuration and Testing April 2026 | Resolved! | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-28 | 16 | 16 | Muhammad Imran Aslam | 16 |  | WOM-142 | WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-160 | [5 empty] | 2026-03-31T16:16:21.306+0500 | 2026-04-28T11:49:19.718+0500
WOM | WOM-161 | WOM-161 | Sub-task | Sub-task |  | Field Service Configuration and Testing April 2026 | Resolved! | 2026-04-02 | 2026-04-03 | 2026-04-02 | 2026-04-03 | 16 | 16 | Muhammad Imran Aslam | 16 |  | WOM-143 | WOM-143 | https://octopusdtlsupport.atlassian.net/browse/WOM-143 | https://octopusdtlsupport.atlassian.net/browse/WOM-161 | [5 empty] | 2026-04-06T10:53:52.543+0500 | 2026-04-06T10:55:40.602+0500
WOM | WOM-162 | WOM-162 | Sub-task | Sub-task |  | Field Service Configuration and Testing May 2026 | Resolved! | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | 16 | 16 | Muhammad Imran Aslam | 16 |  | WOM-143 | WOM-143 | https://octopusdtlsupport.atlassian.net/browse/WOM-143 | https://octopusdtlsupport.atlassian.net/browse/WOM-162 | [5 empty] | 2026-04-20T14:42:33.770+0500 | 2026-05-05T14:15:32.595+0500
WOM | WOM-163 | WOM-163 | Sub-task | Sub-task |  | Field Service Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-11 | 2026-05-11 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | WOM-135 | WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-135 | https://octopusdtlsupport.atlassian.net/browse/WOM-163 | [5 empty] | 2026-04-23T11:26:57.234+0500 | 2026-04-23T11:28:13.023+0500
WOM | WOM-164 | WOM-164 | Sub-task | Sub-task |  | Field Service Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-12 | 2026-05-12 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | WOM-137 | WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-137 | https://octopusdtlsupport.atlassian.net/browse/WOM-164 | [5 empty] | 2026-04-23T11:29:43.390+0500 | 2026-04-23T11:30:24.655+0500
WOM | WOM-165 | WOM-165 | Sub-task | Sub-task |  | Field Service Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-14 | 2026-05-15 |  |  | 16 | 16 | Muhammad Imran Aslam | 0 |  | WOM-139 | WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-139 | https://octopusdtlsupport.atlassian.net/browse/WOM-165 | [5 empty] | 2026-04-23T11:34:03.855+0500 | 2026-04-23T11:34:58.553+0500
WOM | WOM-166 | WOM-166 | Sub-task | Sub-task |  | Field Service Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-18 | 2026-05-18 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | WOM-140 | WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-140 | https://octopusdtlsupport.atlassian.net/browse/WOM-166 | [5 empty] | 2026-04-23T11:43:52.734+0500 | 2026-04-23T11:45:01.544+0500
WOM | WOM-167 | WOM-167 | Sub-task | Sub-task |  | Field Service Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-19 | 2026-05-19 |  |  | 8 | 8 | Muhammad Imran Aslam | 0 |  | WOM-141 | WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-141 | https://octopusdtlsupport.atlassian.net/browse/WOM-167 | [5 empty] | 2026-04-23T11:46:00.859+0500 | 2026-04-23T11:46:34.140+0500
WOM | WOM-168 | WOM-168 | Sub-task | Sub-task |  | Field Service Configuration and Testing May 2026 | Considered in Roadmap & Queued | 2026-05-21 | 2026-05-22 |  |  | 16 | 16 | Muhammad Imran Aslam | 0 |  | WOM-142 | WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-142 | https://octopusdtlsupport.atlassian.net/browse/WOM-168 | [5 empty] | 2026-04-23T11:50:44.534+0500 | 2026-04-23T11:51:34.007+0500
WOM | WOM-169 | WOM-169 | Epic | Epic |  | Test, created from EPR Tool | Considered in Roadmap & Queued | 2026-03-29 | 2026-05-15 |  |  | 744 | 744 | Unassigned | 0 |  |  |  |  | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | [5 empty] | 2026-04-30T16:44:29.583+0500 | 2026-04-30T16:44:29.741+0500
WOM | WOM-170 | WOM-170 | Story | Story |  | Process Design | Considered in Roadmap & Queued | 2026-03-29 | 2026-03-31 |  |  | 16 | 16 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-170 | [5 empty] | 2026-04-30T16:44:32.575+0500 | 2026-04-30T16:44:32.693+0500
WOM | WOM-171 | WOM-171 | Story | Story |  | URS | Considered in Roadmap & Queued | 2026-03-31 | 2026-04-04 |  |  | 40 | 40 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-171 | [5 empty] | 2026-04-30T16:44:34.611+0500 | 2026-04-30T16:44:34.748+0500
WOM | WOM-172 | WOM-172 | Sub-task | Sub-task |  | Mar effort | Considered in Roadmap & Queued | 2026-03-31 | 2026-03-31 |  |  | 8 | 8 | Unassigned | 0 |  | WOM-171 | WOM-171 | https://octopusdtlsupport.atlassian.net/browse/WOM-171 | https://octopusdtlsupport.atlassian.net/browse/WOM-172 | [5 empty] | 2026-04-30T16:44:37.698+0500 | 2026-04-30T16:44:37.864+0500
WOM | WOM-173 | WOM-173 | Sub-task | Sub-task |  | Apr effort | Considered in Roadmap & Queued | 2026-04-01 | 2026-04-04 |  |  | 32 | 32 | Unassigned | 0 |  | WOM-171 | WOM-171 | https://octopusdtlsupport.atlassian.net/browse/WOM-171 | https://octopusdtlsupport.atlassian.net/browse/WOM-173 | [5 empty] | 2026-04-30T16:44:40.986+0500 | 2026-04-30T16:44:41.184+0500
WOM | WOM-174 | WOM-174 | Story | Story |  | DDS | Considered in Roadmap & Queued | 2026-04-01 | 2026-04-18 |  |  | 64 | 64 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-174 | [5 empty] | 2026-04-30T16:44:42.756+0500 | 2026-04-30T16:44:42.888+0500
WOM | WOM-175 | WOM-175 | Story | Story |  | Development | Considered in Roadmap & Queued | 2026-04-15 | 2026-04-25 |  |  | 360 | 360 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-175 | [5 empty] | 2026-04-30T16:44:44.356+0500 | 2026-04-30T16:44:44.462+0500
WOM | WOM-176 | WOM-176 | Story | Story |  | Handover | Considered in Roadmap & Queued | 2026-04-30 | 2026-04-30 |  |  | 4 | 4 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-176 | [5 empty] | 2026-04-30T16:44:46.542+0500 | 2026-04-30T16:44:46.722+0500
WOM | WOM-177 | WOM-177 | Story | Story |  | SQA | Considered in Roadmap & Queued | 2026-04-30 | 2026-05-07 |  |  | 40 | 40 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-177 | [5 empty] | 2026-04-30T16:44:48.344+0500 | 2026-04-30T16:44:48.449+0500
WOM | WOM-178 | WOM-178 | Sub-task | Sub-task |  | Apr effort | Considered in Roadmap & Queued | 2026-04-30 | 2026-04-30 |  |  | 4.97 | 4.97 | Unassigned | 0 |  | WOM-177 | WOM-177 | https://octopusdtlsupport.atlassian.net/browse/WOM-177 | https://octopusdtlsupport.atlassian.net/browse/WOM-178 | [5 empty] | 2026-04-30T16:44:50.823+0500 | 2026-04-30T16:44:50.961+0500
WOM | WOM-179 | WOM-179 | Sub-task | Sub-task |  | May effort | Considered in Roadmap & Queued | 2026-05-01 | 2026-05-07 |  |  | 35.03 | 35.03 | Unassigned | 0 |  | WOM-177 | WOM-177 | https://octopusdtlsupport.atlassian.net/browse/WOM-177 | https://octopusdtlsupport.atlassian.net/browse/WOM-179 | [5 empty] | 2026-04-30T16:44:52.997+0500 | 2026-04-30T16:44:53.144+0500
WOM | WOM-180 | WOM-180 | Story | Story |  | Bug Fixing | Considered in Roadmap & Queued | 2026-04-30 | 2026-05-07 |  |  | 52.08 | 52.08 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-180 | [5 empty] | 2026-04-30T16:44:54.698+0500 | 2026-04-30T16:44:54.856+0500
WOM | WOM-181 | WOM-181 | Sub-task | Sub-task |  | Apr effort | Considered in Roadmap & Queued | 2026-04-30 | 2026-04-30 |  |  | 6.48 | 6.48 | Unassigned | 0 |  | WOM-180 | WOM-180 | https://octopusdtlsupport.atlassian.net/browse/WOM-180 | https://octopusdtlsupport.atlassian.net/browse/WOM-181 | [5 empty] | 2026-04-30T16:44:56.892+0500 | 2026-04-30T16:44:57.010+0500
WOM | WOM-182 | WOM-182 | Sub-task | Sub-task |  | May effort | Considered in Roadmap & Queued | 2026-05-01 | 2026-05-07 |  |  | 45.6 | 45.6 | Unassigned | 0 |  | WOM-180 | WOM-180 | https://octopusdtlsupport.atlassian.net/browse/WOM-180 | https://octopusdtlsupport.atlassian.net/browse/WOM-182 | [5 empty] | 2026-04-30T16:44:59.039+0500 | 2026-04-30T16:44:59.161+0500
WOM | WOM-183 | WOM-183 | Story | Story |  | Process QA Testing | Considered in Roadmap & Queued | 2026-05-01 | 2026-05-07 |  |  | 48 | 48 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-183 | [5 empty] | 2026-04-30T16:45:00.694+0500 | 2026-04-30T16:45:00.874+0500
WOM | WOM-184 | WOM-184 | Story | Story |  | Doc / User Manual | Considered in Roadmap & Queued | 2026-05-05 | 2026-05-07 |  |  | 88 | 88 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-184 | [5 empty] | 2026-04-30T16:45:02.469+0500 | 2026-04-30T16:45:02.575+0500
WOM | WOM-185 | WOM-185 | Story | Story |  | Regression SQA Testing | Considered in Roadmap & Queued | 2026-05-07 | 2026-05-08 |  |  | 88 | 88 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-185 | [5 empty] | 2026-04-30T16:45:04.022+0500 | 2026-04-30T16:45:04.135+0500
WOM | WOM-186 | WOM-186 | Story | Story |  | Production Release | Considered in Roadmap & Queued | 2026-05-08 | 2026-05-15 |  |  | 16 | 16 | Unassigned | 0 |  | WOM-169 | WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-169 | https://octopusdtlsupport.atlassian.net/browse/WOM-186 | [5 empty] | 2026-04-30T16:45:05.832+0500 | 2026-04-30T16:45:06.053+0500