## Summary
|  |  |  | Most-likely | Face value
|  |  |  | Optimistic | Might take lesser effort
|  |  |  | Pessimistic | Might take more effort
|  |  |  | Calculated Man-Days | Calibrated estimate
MAN-DAYS
|  |  | 50% | 10%
# of Epics | Product | Most-likely Man-days | Optimistic Man-days (50%) | Pessimistic (10%) | Calculated Man-Days | TK Approved
51 | OmniConnect | 810 | 405 | 1012.5 | 776.25 | 388.125
54 | Fintech Fuel | 1210 | 605 | 1331 | 1129.3333 | 564.6667
14 | OmniChat | 413 | 206.5 | 454.3 | 400.4667 | 200.2333
31 | Digital Log | 972 | 486 | 1215 | 931.5 | 465.75
| Support (3 person) | 176 | 88 | 193.6 | 164.2667 | 164.2667
| Total | 3581 | 1790.5 | 4206.4 | 3401.8167 | 1783.0417

## OmniConnect RMI
OmniConnect Roadmap Items | [6 empty] | BHW | TK | AA | TS |  | RnD Most likely | [9 empty] | TK Budgeted | [17 empty] | `=($Y3-($M3+$T3+$Q3)) * (SUBSTITUTE(MID(AH$2, SEARCH("(", AH$2) + 1, 5), "%)", "") / 100)
Sr # | Category | Components | Road Map Items | Jira ID | Originator | Value | Priority | Priority | Priority | Priority | Plan Status | Prc Design | R/URS | R/DDS | Dev | SQA | Prc Test | Doc | Reg SQA | Release | Man Days | Optimistic (50%) | Pessimistic (10%) | Est Formula | TK's TARGET | Start Date | Dev End | SQA HO | Prod Date | Prc Design | R/URS (5%) | R/DDS (10%) | Dev (50%) | SQA (15%) | Prc Test | Doc (10%) | Reg SQA (10%) | Release
1 | Input | Streaming | OC Streaming (80% done) | https://octopusdtlsupport.atlassian.net/browse/O2-793 | RnD |  | 1 |  |  | 1 | Plan |  | 2 | 20 | 40 | 20 |  | 0 | 2 |  | 84 | 42 | 105 | 80.5 | 40.25 |  |  |  | 1900-01-04 | 0 | 2.0125 | 4.025 | 20.125 | 6.0375 | 0 | 4.025 | 4.025 | 0 | 40.25
2 |  |  | OC streaming on Pub Sub |  | Imp Team |  | 1 |  |  | 1 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Bulk Device creation | BULK DEVICE CREATION FOR NON SMART DEVICES (on hold, no further thought process undertaken) Current feature is to bulk create MQTT/IOT devices which has ability to directly connect to Azure IOT hub as an independent devices. It does not cover the schenario where multiple non smart devices are connected to one gateway from where the data is send to cloud. Now need is to replicate such non smart devices (connected to gateway) on OC as logical devices. |  | Management |  | 2 |  |  | 2 | [5 empty] | 5 |  |  |  | 1 | 6 | 3 | 7.5 | 5.75 | 2.875 |  |  |  |  | 0 | 0 | 0 | 0 | 1.875 | 0 | 0 | 0 | 1 | 2.875
4 |  | Import Site Layout | Import Site Layout catchup till date |  | RnD |  | 2 |  |  | 3 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Scheduled Pull | Support for Wide tables from SQL Source | https://octopusdtlsupport.atlassian.net/browse/O2-2188 | RnD |  |  |  |  | 2 |  |  |  |  | 12 | 2 |  | 2 | 5 | 4 | 25 | 12.5 | 31.25 | 23.9583 | 11.9792 | 2026-05-08 | 2026-05-14 | 2026-05-15 | 2026-05-19 | 0 | 0 | 0 | 4.2949 | 1.2885 | 0 | 1.1979 | 1.1979 | 4 | 11.9792 | Need to understand this
6 |  |  | Support for Wide tables from API Source | https://octopusdtlsupport.atlassian.net/browse/O2-2189 | RnD |  |  |  |  | 2 |  |  |  |  | 12 | 2 |  | 2 | 5 | 4 | 25 | 12.5 | 31.25 | 23.9583 | 11.9792 | 2026-05-22 | 2026-05-28 | 2026-05-29 | 2026-06-02 | 0 | 0 | 0 | 4.2949 | 1.2885 | 0 | 1.1979 | 1.1979 | 4 | 11.9792 | Need to understand this
7 |  |  | Support for Wide tables from SFTP Source | https://octopusdtlsupport.atlassian.net/browse/O2-2190 | RnD |  |  |  |  | 2 |  | 0 |  |  | 12 | 2 | 0 | 2 | 5 | 4 | 25 | 12.5 | 31.25 | 23.9583 | 11.9792 | 2026-06-03 | 2026-06-09 | 2026-06-10 | 2026-06-12 | 0 | 0 | 0 | 4.2949 | 1.2885 | 0 | 1.1979 | 1.1979 | 4 | 11.9792 | Need to understand this
|  |  | OmniEdge diagnostics metrics collection | https://octopusdtlsupport.atlassian.net/browse/O2-2269 | RnD | [6 empty] | 2 | 2 | 3 | 2 | 1 | 0 | 0 | 0 | 3 | 17 | 8.5 | 21.25 | 16.2917 | 8.1458 | 2026-04-08 | 2026-04-17 | 2026-04-24 | 2026-04-30 | 2 | 0.40729 | 0.81458 | 0.22676 | 0.068029 | 0 | 0.81458 | 0.81458 | 3 | 8.1458
8 | Enrichment | APX | APX - WhatIf Pump |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 8 |  | 1 | 1 | 11 | 5.5 | 13.75 | 10.5417 | 5.2708 |  |  |  |  | 0 | 0 | 0 | 0 | -4.2563 | 8 | 0 | 0.52708 | 1 | 5.2708
9 |  |  | APX - WhatIf Compressor |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 3 |  | 1 | 1 | 6 | 3 | 7.5 | 5.75 | 2.875 |  |  |  |  | 0 | 0 | 0 | 0 | -1.4125 | 3 | 0 | 0.2875 | 1 | 2.875
10 |  |  | APX - WhatIf Condenser |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 5 |  | 1 | 1 | 8 | 4 | 10 | 7.6667 | 3.8333 |  |  |  |  | 0 | 0 | 0 | 0 | -2.55 | 5 | 0 | 0.38333 | 1 | 3.8333
11 |  |  | APX - WhatIf Heat Exchanger |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 3 |  | 1 | 1 | 6 | 3 | 7.5 | 5.75 | 2.875 |  |  |  |  | 0 | 0 | 0 | 0 | -1.4125 | 3 | 0 | 0.2875 | 1 | 2.875
12 |  |  | APX - WhatIf Boiler |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 0 |  | 1 | 1 | 3 | 1.5 | 3.75 | 2.875 | 1.4375 |  |  |  |  | 0 | 0 | 0 | 0 | 0.29375 | 0 | 0 | 0.14375 | 1 | 1.4375
13 |  |  | APX - Health Pump |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 4 |  | 1 | 1 | 7 | 3.5 | 8.75 | 6.7083 | 3.3542 |  |  |  |  | 0 | 0 | 0 | 0 | -1.9813 | 4 | 0 | 0.33542 | 1 | 3.3542
14 |  |  | APX - Health Compressor |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 3 |  | 1 | 1 | 6 | 3 | 7.5 | 5.75 | 2.875 |  |  |  |  | 0 | 0 | 0 | 0 | -1.4125 | 3 | 0 | 0.2875 | 1 | 2.875
15 |  |  | APX - Health Motor |  | Process Team |  | 1 |  |  | 1 | Plan | 0 |  |  |  | 1 | 4 |  | 1 | 1 | 7 | 3.5 | 8.75 | 6.7083 | 3.3542 |  |  |  |  | 0 | 0 | 0 | 0 | -1.9813 | 4 | 0 | 0.33542 | 1 | 3.3542
16 |  |  | DEV - WhatIf Visual Screens (Pump, Comp,Cond,Hex, Boiler) II | https://octopusdtlsupport.atlassian.net/browse/O2-1991 | Process Team |  | 1 |  |  | 1 | UnPlan | 1 |  | 5 | 30 | 5 | 3 |  |  | 3 | 47 | 23.5 | 58.75 | 45.0417 | 22.5208 | 2026-04-06 | 2026-04-23 | 2026-04-24 | 2026-04-29 | 1 | 0 | 2.2521 | 10.2067 | 3.062 | 3 | 0 | 0 | 3 | 22.5208
17 |  |  | DEV - Tempate Tool Enhancement for WhatIf and Health | https://octopusdtlsupport.atlassian.net/browse/O2-2186 | Process Team |  | 1 |  |  | 1 |  | 4 |  |  | 20 | 10 | 5 | 5 |  | 3 | 47 | 23.5 | 58.75 | 45.0417 | 22.5208 | 2026-04-06 | 2026-04-16 | 2026-04-17 | 2026-04-27 | 4 | 0 | 0 | 6.3606 | 1.9082 | 5 | 2.2521 | 0 | 3 | 22.5208
18 |  |  | DEV - Performance Module Enhancements (Results in OC ) |  | Process Team |  | 1 |  |  | 1 | UnPlan | 5 |  |  |  |  | 0 |  |  |  | 5 | 2.5 | 6.25 | 4.7917 | 2.3958 |  |  |  |  | 5 | 0 | 0 | -2.6042 | 0 | 0 | 0 | 0 | 0 | 2.3958
19 |  |  | APX - Demos |  | Process Team |  | 1 |  |  | 1+ | Plan | 8 |  |  |  |  | 0 |  |  |  | 8 | 4 | 10 | 7.6667 | 3.8333 |  |  |  |  | 8 | 0 | 0 | -4.1667 | 0 | 0 | 0 | 0 | 0 | 3.8333
20 |  | Batch / BPM | IT/OT Conversion Batch/BPM (on hold) |  | RnD | [5 empty] | UnPlan | - |  |  |  |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | 0 | 0 |  | 0 | - | 0 | 0 | 0 | 0
21 |  |  | Support for SQL Language in Batch/BPM(Features Supported by adx) (Discussion Required) |  | RnD |  |  |  |  | 2 | UnPlan | - |  |  |  |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | 0 | 0 |  | 0 | - | 0 | 0 | 0 | 0
25 |  |  | "Create Asset from Template" Add BPM support (Discussion Required) |  | RnD | Faster Impl |  |  |  | 2 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 |  | Enterprise connectors | Enterprise Connectors Pipeline OnDemand Trigger |  | Imp Team | Faster Impl | 3 |  |  | 3 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In the meantime we should document the process of achieving that as project implementation
27 |  |  | IT/OT Conversion for Enterprise Connectors (on hold) |  | RnD |  | 3 |  |  | 1 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 |  | Calculated Tags Enhancement | Nesting of Counter, Timer, Totalizer | https://octopusdtlsupport.atlassian.net/browse/O2-697 | RnD |  | 1 |  |  | 2 | Plan |  |  | 2 | 20 | 15 |  | 4 | 25 | 19 | 85 | 42.5 | 106.25 | 81.4583 | 40.7292 | 2026-05-04 | 2026-05-21 | 2026-05-22 | 2026-05-29 | 0 | 0 | 4.0729 | 7.3157 | 2.1947 | 0 | 4.0729 | 4.0729 | 19 | 40.7292 | Thought it was already done
29 |  | Anomaly Detection Engine (ADE) | ADE for Batch/BPM IT Data (Discussion Requried) |  | RnD |  | 2 |  |  | 1+ | UnPlan | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 |  |  | ADE for Enterprise Connectors IT Data (Discussion Required) |  | RnD | [5 empty] | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  | Alarm | Alarms for Batch IT Data | https://octopusdtlsupport.atlassian.net/browse/O2-2277 | RnD |  | 1 |  |  | 3 | UnPlan |  |  | 3 | 24 | 5 |  | 1 | 5 |  | 38 | 19 | 47.5 | 36.4167 | 18.2083 | 2026-04-09 | 2026-04-22 | 2026-04-23 | 2026-04-30 | 0 | 0 | 1.8208 | 9.8045 | 2.9413 | 0 | 1.8208 | 1.8208 | 0 | 18.2083
|  |  | Alarms for BPM IT Data | https://octopusdtlsupport.atlassian.net/browse/O2-2278 | RnD |  | 1 |  |  | 3 | UnPlan |  |  | 6 | 27 | 5 |  | 1 | 5 |  | 44 | 22 | 55 | 42.1667 | 21.0833 | 2026-05-04 | 2026-05-25 | 2026-05-26 | 2026-06-02 | 0 | 0 | 2.1083 | 11.3526 | 3.4058 | 0 | 2.1083 | 2.1083 | 0 | 21.0833
32 |  |  | Alarms for Enterprise Connectors IT Data SQL | https://octopusdtlsupport.atlassian.net/browse/O2-2279 | RnD | [5 empty] | UnPlan |  |  | 3 | 15 | 5 |  |  | 5 |  | 28 | 14 | 35 | 26.8333 | 13.4167 | 2026-05-27 | 2026-06-05 | 2026-06-08 | 2026-06-15 | 0 | 0 | 1.3417 | 8.2564 | 2.4769 | 0 | 0 | 1.3417 | 0 | 13.4167
33 |  |  | Alarms for Enterprise Connectors IT Data Rest API | https://octopusdtlsupport.atlassian.net/browse/O2-2280 | RnD | [8 empty] | 3 | 15 | 5 |  |  | 5 |  | 28 | 14 | 35 | 26.8333 | 13.4167 | 2026-06-09 | 2026-06-18 | 2026-06-19 | 2026-06-26 | 0 | 0 | 1.3417 | 8.2564 | 2.4769 | 0 | 0 | 1.3417 | 0 | 13.4167
34 |  |  | Alarms for Enterprise Connectors IT Data SFTP | https://octopusdtlsupport.atlassian.net/browse/O2-2296 | RnD | [8 empty] | 3 | 15 | 5 |  |  | 5 |  | 28 | 14 | 35 | 26.8333 | 13.4167 | 2026-06-22 | 2026-07-01 | 2026-07-02 | 2026-07-09 | 0 | 0 | 1.3417 | 8.2564 | 2.4769 | 0 | 0 | 1.3417 | 0 | 13.4167
35 |  |  | Alarms for Enterprise Connectors IT Data SAP | https://octopusdtlsupport.atlassian.net/browse/O2-2321 | RnD | [8 empty] | 3 | 15 | 5 |  |  | 5 |  | 28 | 14 | 35 | 26.8333 | 13.4167 | 2026-07-03 | 2026-07-14 | 2026-07-15 | 2026-07-22 | 0 | 0 | 1.3417 | 8.2564 | 2.4769 | 0 | 0 | 1.3417 | 0 | 13.4167
36 |  | Diagnostics | ML based Tier 4 Diagnostics (Landing Pattern based alerts) |  | RnD |  | 1 |  |  |  | UnPlan |  |  |  | 4 | 3 |  | 1 |  |  | 8 | 4 | 10 | 7.6667 | 3.8333 |  |  |  |  | 0 | 0 | 0 | 2.6538 | 0.79615 | 0 | 0.38333 | 0 | 0 | 3.8333
37 |  | OmniOEE | OmniOEE Phase 1 - Batch/BPM Std Compute Module (Curated, Library-stored) |  | Management |  | 3 |  |  | 1 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Need to understand it. Also we should be able to document this and do it as project
38 |  |  | OmniOEE Phase 2 – Full OEE System (Production Planning, Configuration, Data, Visualizations) |  | Management |  | 3 |  |  | 2 | UnPlan | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  | OmniALA | Aux Load Advisor |  | Management |  | 3 |  |  | 1 | UnPlan |  |  | 10 | [6 empty] | 10 | 5 | 12.5 | 9.5833 | 4.7917 |  |  |  |  | 0 | 0 | 0.47917 | 4.3125 | 0 | 0 | 0 | 0 | 0 | 4.7917 | Document and make it sound as a product till we get an order
40 |  | ML | Pattern Recognition |  | RnD |  | 2 |  |  | 1 | UnPlan |  |  | 2 | 8 | 5 |  | 5 |  |  | 20 | 10 | 25 | 19.1667 | 9.5833 |  |  |  |  | 0 | 0 | 0.95833 | 5.8974 | 1.7692 | 0 | 0.95833 | 0 | 0 | 9.5833 | This should be very easy to implement using AI coding assistance
41 |  |  | Forcasting |  | RnD |  | 2 |  |  | 1 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This should be very easy to implement using AI coding assistance
42 | Output | OmniAgent | Multi Agent Support |  | RnD |  |  |  |  | 1 | UnPlan |  |  | 1 | 2 | 2 |  | 1 |  |  | 6 | 3 | 7.5 | 5.75 | 2.875 |  |  |  |  | 0 | 0 | 0.2875 | 1.7692 | 0.53077 | 0 | 0.2875 | 0 | 0 | 2.875 | What is this?
43 |  |  | ADE to AutoPrompt to OmniAgent to RCA/Advice |  | Management |  | 1 |  |  | 1+ | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  | Trending | OC Trending V2 | https://octopusdtlsupport.atlassian.net/browse/O2-456 | Imp Team, Process Team |  | 3 |  |  | 1 | UnPlan |  |  | 10 | 30 | 10 |  |  | 5 | 12 | 67 | 33.5 | 83.75 | 64.2083 | 32.1042 | 2026-05-04 | 2026-05-29 | 2026-06-01 | 2026-06-10 | 0 | 0 | 3.2104 | 10.5256 | 3.1577 | 0 | 0 | 3.2104 | 12 | 32.1042
45 |  | Audit Trail | Audit Trail |  | Competitive |  | 2 |  |  | 1 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 |  | UI UX | Revamped UI |  | Management |  | 1 |  |  | 1+ | [10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 |  | Unified Notification Engine | Unified Notification Engine | https://octopusdtlsupport.atlassian.net/browse/O2-36 | RnD |  | 2 |  |  | 1 | UnPlan |  | 5 | 5 | 12 | 5 |  |  |  | 12 | 39 | 19.5 | 48.75 | 37.375 | 18.6875 | 2026-04-13 | 2026-04-30 | 2026-05-04 | 2026-05-07 | 0 | 0.93438 | 1.8688 | 2.988 | 0.89639 | 0 | 0 | 0 | 12 | 18.6875
|  | Export to SQL | Export to SQL Enhancement | https://octopusdtlsupport.atlassian.net/browse/O2-1976 | Imp Team | [7 empty] | 0 | 5 | 10 | 5 |  | 3 | 5 | 10 | 38 | 19 | 47.5 | 36.4167 | 18.2083 | 2026-03-17 | 2026-04-03 | 2026-04-09 | 2026-04-16 | 0 | 0.91042 | 1.8208 | 1.4119 | 0.42356 | 0 | 1.8208 | 1.8208 | 10 | 18.2083
48 | Administration | Subscription Management | Pricing Module |  | Management |  | 1 |  |  | 1 | Plan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 |  |  | Subscription Management |  | Management |  | 1 |  |  | 2 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 |  | DRP | Redundancy in Blob Storage |  | RnD |  | 3 |  |  | 3 | UnPlan | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Why is this needed?
[21 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 4.2646 | 29.0854 | 134.0897 | 28.1269 | 38 | 22.1375 | 29.4208 | 83

## Sheet6 (hidden)
Man days
Most likely | 20 | 60
30% | 26 | 26
| 13.3333 | 13.3333
99.3333
16.5556

## Fintech Fuel RMI
Fintech Fuel Roadmap Items | [6 empty] | BHW | TK | AA | TS |  | RnD Most likely | [9 empty] | TK Budgeted
Sr # | Category | Components | Road Map Items | JIRA ID | Originator | Value | Priority | Priority | Priority | Priority | Plan Status | Prc Design | R/URS | R/DDS | Dev | SQA | Prc Test | Doc | Reg SQA | Release | Man Days | Optimistic (50%) | Pessimistic (10%) | Est Formula | TK's TARGET | Start Date | Dev End | SQA HO | Prod Date | Prc Design | R/URS (5%) | R/DDS (10%) | Dev (50%) | SQA (15%) | Prc Test | Doc (10%) | Reg SQA (10%) | Release
1 | Input | Alsons | Alsons Connectivity for Reading (done) (6h) |  | PGL | [7 empty] | 2 | 1 | 5 | 0 |  | 0 |  | 2 | 10 | 5 | 11 | 9.3333 | 4.6667 |  |  |  |  | 0 | 0.23333 | 0.46667 | 1.1538 | 0.34615 | 0 | 0.46667 | 0 | 2
2 |  |  | Alsons Data Compatibility POC with FintechFuel - (41h) |  | PGL | [8 empty] | 5 | 48 | 15 |  |  |  | 2 | 70 | 35 | 77 | 65.3333 | 32.6667 |  |  |  |  | 0 | 0 | 3.2667 | 21.0769 | 6.3231 | 0 | 0 | 0 | 2
|  |  | Alsons Integration with FintechFuel |  | RnD | [7 empty] | 0 | 0 | 23 | 15 |  | 5 | 15 | 2 | 60 | 30 | 66 | 56 | 28 | 2026-03-30 | 2026-04-14 | 2026-04-15 | 2026-05-06 | 0 | 1.4 | 2.8 | 12.4615 | 3.7385 | 0 | 2.8 | 2.8 | 2
3 | Enrichment | Business Alarms | Configurable alert thresholds and Recipients (done) |  | PGL | [8 empty] | 15 | 32 | 7 |  | 4 | 6 | 2 | 66 | 33 | 72.6 | 61.6 | 30.8 |  |  |  |  | 0 | 0 | 3.08 | 15.0462 | 4.5138 | 0 | 3.08 | 3.08 | 2
4 |  |  | Leak and theft alerts |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
5 |  |  | Theft detection (internal/external) |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
6 |  |  | Nozzle bypass detection |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
7 |  |  | Calibration drift alerts |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
8 |  |  | Sensor malfunction alerts |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
9 |  |  | Unauthorized dispensing alerts |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
10 |  |  | Power outage detection |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
11 |  |  | Alert escalation workflows |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
12 |  |  | Alert acknowledgment and resolution tracking |  | PGL | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
13 |  |  | Nozzle flow rate |  | Competitive | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
14 |  |  | Under-Dispensing |  | Competitive | [8 empty] | 3 | 5 | 3 |  | 1 | 5 | 2 | 19 | 9.5 | 20.9 | 17.7333 | 8.8667 |  |  |  |  | 0 | 0 | 0.88667 | 3.2359 | 0.97077 | 0 | 0.88667 | 0.88667 | 2
15 |  | System Alarms | Connectivity loss alerts (done) |  | PGL | [8 empty] | 2 | 5 | 2 |  | 1 | 2 | 2 | 14 | 7 | 15.4 | 13.0667 | 6.5333 |  |  |  |  | 0 | 0 | 0.65333 | 1.9795 | 0.59385 | 0 | 0.65333 | 0.65333 | 2
16 |  | ML | Pricing/profit optimization |  | Competitive | [14 empty] | 2 | 2 | 1 | 2.2 | 1.8667 | 0.93333 |  |  |  |  | 0 | 0 | 0 | -1.0667 | 0 | 0 | 0 | 0 | 2
17 |  |  | Predictive Maintenance |  | Competitive | [14 empty] | 2 | 2 | 1 | 2.2 | 1.8667 | 0.93333 |  |  |  |  | 0 | 0 | 0 | -1.0667 | 0 | 0 | 0 | 0 | 2
18 |  |  | Sudden Loss indicator |  | Competitive | [14 empty] | 2 | 2 | 1 | 2.2 | 1.8667 | 0.93333 |  |  |  |  | 0 | 0 | 0 | -1.0667 | 0 | 0 | 0 | 0 | 2
19 | Administration | URM | User & role management | https://octopusdtlsupport.atlassian.net/browse/FF-541 | PGL | [8 empty] | 5 | 6 | 3 |  | 3 | 5 | 2 | 24 | 12 | 26.4 | 22.4 | 11.2 | 2026-07-24 |  |  |  | 0 | 0 | 1.12 | 4.4923 | 1.3477 | 0 | 1.12 | 1.12 | 2
20 |  | Configuration | Station and tank configuration |  | PGL | [8 empty] | 3 | 5 | 4 |  | 1 | 3 | 2 | 18 | 9 | 19.8 | 16.8 | 8.4 |  |  |  |  | 0 | 0 | 0.84 | 2.9846 | 0.89538 | 0 | 0.84 | 0.84 | 2
21 |  |  | Product mapping |  | PGL | [8 empty] | 3 | 3 | 2 |  | 1 | 3 | 2 | 14 | 7 | 15.4 | 13.0667 | 6.5333 |  |  |  |  | 0 | 0 | 0.65333 | 1.9795 | 0.59385 | 0 | 0.65333 | 0.65333 | 2
22 |  |  | Unit and currency settings |  | PGL | [8 empty] | 4 | 10 | 5 |  | 3 | 6 | 2 | 30 | 15 | 33 | 28 | 14 |  |  |  |  | 0 | 0 | 1.4 | 6 | 1.8 | 0 | 1.4 | 1.4 | 2 | *Would require a session with IA as well for showing data on dashboard of sites with different currencies *Understanding session is required with PGL
23 |  | Audit | Audit trails (phase 1) - User-management | https://octopusdtlsupport.atlassian.net/browse/FF-446 | PGL | [8 empty] | 5 | 15 | 5 |  |  |  | 2 | 27 | 13.5 | 29.7 | 25.2 | 12.6 | 2026-05-18 | 2026-05-29 | 2026-06-01 | 2026-06-03 | 0 | 0 | 1.26 | 7.1846 | 2.1554 | 0 | 0 | 0 | 2
24 |  |  | Audit trails (phase 2) - Module Interaction | https://octopusdtlsupport.atlassian.net/browse/FF-512 | PGL | [8 empty] | 5 | 15 | 5 |  | 2 | 5 | 2 | 34 | 17 | 37.4 | 31.7333 | 15.8667 | 2026-06-04 | 2026-06-17 | 2026-06-18 | 2026-06-22 | 0 | 0 | 1.5867 | 7.0051 | 2.1015 | 0 | 1.5867 | 1.5867 | 2
25 |  |  | Audit trails (phase 3) - Activity Log | https://octopusdtlsupport.atlassian.net/browse/FF-517 | PGL | [8 empty] | 5 | 10 | 5 |  | 2 | 5 | 2 | 29 | 14.5 | 31.9 | 27.0667 | 13.5333 | 2026-06-22 | 2026-06-30 | 2026-07-01 | 2026-07-03 | 0 | 0 | 1.3533 | 5.7487 | 1.7246 | 0 | 1.3533 | 1.3533 | 2
26 | OutPut | Mobile | Mobile View without Manual submit Data |  | Competitive | [7 empty] | 5 | 3 | 15 | 10 |  | 3 | 5 | 2 | 43 | 21.5 | 47.3 | 40.1333 | 20.0667 |  |  |  |  | 0 | 1.0033 | 2.0067 | 8.4949 | 2.5485 | 0 | 2.0067 | 2.0067 | 2
27 |  | ReadAPI | ReadAPI to pull data from FintechFuel - (21h) |  | Competitive | [9 empty] | 20 | 10 |  | 5 | 6 | 2 | 43 | 21.5 | 47.3 | 40.1333 | 20.0667 | 2026-07-06 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 0 | 0 | 0 | 10.8103 | 3.2431 | 0 | 2.0067 | 2.0067 | 2
28 |  | Write-Back | Write-Back Price to stations - (10h) | https://octopusdtlsupport.atlassian.net/browse/FF-302 | PGL | [8 empty] | 6 | 26 | 10 |  |  | 3 | 2 | 47 | 23.5 | 51.7 | 43.8667 | 21.9333 | 2026-04-20 | 2026-04-30 | 2026-05-01 | 2026-05-11 | 0 | 0 | 2.1933 | 11.959 | 3.5877 | 0 | 0 | 2.1933 | 2
29 |  | Notification | Notification via Email /SMS |  | PGL | [8 empty] | 1 | 2 | 2 |  | 1 | 2 |  | 8 | 4 | 8.8 | 7.4667 | 3.7333 |  |  |  |  | 0 | 0 | 0.37333 | 2.0103 | 0.60308 | 0 | 0.37333 | 0.37333 | 0
30 |  | Gen AI | FuelChat - Summarized version | https://octopusdtlsupport.atlassian.net/browse/FF-312 | RnD | [8 empty] | 3 | 10 | 10 |  |  | 2 | 1 | 26 | 13 | 28.6 | 24.2667 | 12.1333 | 2026-05-04 | 2026-05-11 | 2026-05-12 | 2026-05-18 | 0 | 0 | 1.2133 | 6.6974 | 2.0092 | 0 | 0 | 1.2133 | 1
31 |  | Multi-language | Support for multi language | https://octopusdtlsupport.atlassian.net/browse/FF-498 | Competitive | [8 empty] | 7 | 15 | 5 |  | 3 | 3 |  | 33 | 16.5 | 36.3 | 30.8 | 15.4 | 2026-04-08 | 2026-04-22 | 2026-05-04 | 2026-05-06 | 0 | 0 | 1.54 | 8.2923 | 2.4877 | 0 | 1.54 | 1.54 | 0
32 | Support Tickets | Support Tickets | None | [17 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | TO CATEGORIZE YET | TO CATEGORIZE YET | System health monitoring(Site Diagnostic) - (12h) | https://octopusdtlsupport.atlassian.net/browse/FF-274 | PGL | [8 empty] | 5 | 35 | 5 |  | 5 |  | 2 | 52 | 26 | 57.2 | 48.5333 | 24.2667 | 2026-04-08 | 2026-04-17 | 2026-05-04 | 2026-05-06 | 0 | 0 | 2.4267 | 13.3949 | 4.0185 | 0 | 2.4267 | 0 | 2
34 | TO CATEGORIZE YET | TO CATEGORIZE YET | Calculate Tank delivery (Alsons device) | https://octopusdtlsupport.atlassian.net/browse/FF-542 | PGL | [8 empty] | 3 | 3 | 2 |  | 5 |  | 2 | 15 | 7.5 | 16.5 | 14 | 7 |  |  |  |  | 0 | 0 | 0.7 | 2.7692 | 0.83077 | 0 | 0.7 | 0 | 2
35 | TO CATEGORIZE YET | TO CATEGORIZE YET | Unified Platform & Multi-Site Visibility (Consolidated view for all sites) - The client wants a unified platform that provides information from all plant sites in one place. - Key data points requested in the unified view include storage tank volume and timestamped deliveries. - The solution must support network-scale visibility for hundreds of sites, not just a small pilot set. - Different user levels, including management, leadership, supervisors, and operations teams, need different views of the same data. - Visibility of sites, targets, and data should follow the assigned user hierarchy. |  | PGL | [8 empty] | 4 | 10 | 5 |  | 5 |  | 2 | 26 | 13 | 28.6 | 24.2667 | 12.1333 |  |  |  |  | 0 | 0 | 1.2133 | 5.9282 | 1.7785 | 0 | 1.2133 | 0 | 2
36 | TO CATEGORIZE YET | TO CATEGORIZE YET | Deliveries & Delivery Identification - Deliveries are already available with timestamps in Fintech Fuel. - The client wants to distinguish PGL deliveries from non-PGL deliveries, with a clear classification such as PGL and Not PGL. - At COCO sites, current deliveries are considered PGL deliveries. - At DODO sites, the client needs a way to identify who decanted product into storage because multiple providers may use the same storage. - The current level of control at DODO sites is weaker than at COCO sites, and the client wants better controls in Fintech Fuel. - The Deliveries page should use the industry term Delivery Note instead of Bill of Lading. - For imported products, a delivery note or lading reference should be captured on the UI. - A lading reference is currently seen as a reference point only and not as a full control mechanism. - The client wants this requirement captured as a KPI or future control area even if it is initially implemented as a wish-list item. - The system should highlight cases where actual decanted quantity exceeds expected quantity. - Manual delivery references alone are not sufficient to establish end-to-end control. |  | PGL | [8 empty] | 4 | 4 | 3 |  | 5 |  | 2 | 18 | 9 | 19.8 | 16.8 | 8.4 |  |  |  |  | 0 | 0 | 0.84 | 3.6308 | 1.0892 | 0 | 0.84 | 0 | 2
37 | TO CATEGORIZE YET | TO CATEGORIZE YET | Dashboard Enhancements - Visual representations - Sales vs target trend must be dynamic not just last 7 days - Stock level must be dynamic not just last 7 days - Remove minute-level filters - Show time of fetched data on stock-level - positive/negative variance with color coding |  | PGL | [8 empty] | 0 | 2 | 2 |  | 5 |  | 2 | 11 | 5.5 | 12.1 | 10.2667 | 5.1333 |  |  |  |  | 0 | 0 | 0.51333 | 1.6205 | 0.48615 | 0 | 0.51333 | 0 | 2
38 | TO CATEGORIZE YET | TO CATEGORIZE YET | Historical Comparison & Trend Analysis - Comparison of different metrices like sales vs deliveries etc. |  | PGL | [8 empty] | 2 | 6 | 3 |  | 5 |  | 2 | 18 | 9 | 19.8 | 16.8 | 8.4 |  |  |  |  | 0 | 0 | 0.84 | 3.6308 | 1.0892 | 0 | 0.84 | 0 | 2
39 | TO CATEGORIZE YET | TO CATEGORIZE YET | Reconciliation & Variance Analysis - Reconciliation is a key area for the client, especially to monitor external uplifting. - The reconciliation report should help users see how frequently variation occurs over time. - The client wants anomaly highlighting for variances above selected thresholds. - The current tabulated Excel-like representation is difficult to consume and needs a better UI/UX treatment. - The user wants a product-tile style interaction where clicking a product reveals its reconciliation details. - There is currently no way to define a threshold value in the system; the client asked for configurable selected thresholds. - The system should highlight anomalies at the time of reconciliation. - The reconciliation workflow should support investigation into why a difference exists. - Initial anomaly reasons should at least include data disconnectivity, whether due to internet issues or equipment malfunction. - The reconciliation report must show consistent data and clearly reflect when a site is not transmitting data. - If data is missing, the report should show an exclusion note so the variance can be interpreted correctly. - The client suggested a rule such as flagging any site where no data transmission happens for 60 or more minutes. - Capturing the anomaly event is considered the first priority; the detailed report presentation can be refined with users afterward. - The report should include a summary table on top for the selected period with one row per product, instead of only date-by-date product entries. - The user emphasized that reconciliation UI/UX quality is a possible road blocker. |  | PGL | [8 empty] | 5 | 17 | 5 |  | 5 |  | 2 | 34 | 17 | 37.4 | 31.7333 | 15.8667 |  |  |  |  | 0 | 0 | 1.5867 | 8.2256 | 2.4677 | 0 | 1.5867 | 0 | 2
40 | TO CATEGORIZE YET | TO CATEGORIZE YET | Data Accuracy, Connectivity & Equipment Failure - Data accuracy is a major concern for the client. - Two primary failure scenarios were identified: -- Internet disconnectivity between the site and the cloud. -- Site hardware or controller malfunction. - In internet disconnectivity scenarios, the controller device must accumulate data and transmit it once connectivity is restored. - No data loss is acceptable when internet connectivity is interrupted. - If the controller or site equipment is not working, the system must raise an alert. - The client wants the system to inform users whether a site cannot reconcile because of internet disconnectivity or equipment malfunction. - If equipment fails and data is not captured, the system must provide manual entry for lost site data. - Manual entry is considered necessary to maintain 100% data accuracy and complete reconciliation. - The client requested an admin-level tool for manual data entry when ATG or related equipment is down. - The discussion referenced a practical case where if ATG is down for two hours, the system should allow offline or manual input. - Offline input data is therefore a required feature. |  | PGL | [8 empty] | 3 | 23 | 5 |  | 5 |  | 2 | 38 | 19 | 41.8 | 35.4667 | 17.7333 |  |  |  |  | 0 | 0 | 1.7733 | 9.3744 | 2.8123 | 0 | 1.7733 | 0 | 2
41 | TO CATEGORIZE YET | TO CATEGORIZE YET | Alerts, Diagnostics & Notifications - Alerts should not remain isolated in one report; they should connect with diagnostics and related operational reports. - Email notifications should be available for alerts. - A diagnostics or connectivity view should show which sites are disconnected. - Connectivity and equipment-down conditions should raise alerts. - If a device fails to ping within a configured time period, the system should raise an alert if the controller supports that information. - The client suggested using controller ping behavior as a simple basis for equipment-down alerting. - Thresholds for alarms should be configurable. - A 0.5% threshold was specifically mentioned in the discussion. |  | PGL | [8 empty] | 1 | 5 | 3 |  | 5 |  | 2 | 16 | 8 | 17.6 | 14.9333 | 7.4667 |  |  |  |  | 0 | 0 | 0.74667 | 3.0564 | 0.91692 | 0 | 0.74667 | 0 | 2
42 | TO CATEGORIZE YET | TO CATEGORIZE YET | Reporting, Terminology & Units - Nozzle-level sales are not clear to the client, partly because of the nomenclature used in the nozzle report. - The transaction report does not clearly mention the unit of measure. - The client wants units such as liters or currency to be visible consistently across the application. - Report terminology and naming should be reviewed so reports are easier for the business to understand. - The client asked the team to review nomenclature used in summarized and detailed reports. |  | PGL | [8 empty] | 0 | 2 | 1 |  | 5 |  | 2 | 10 | 5 | 11 | 9.3333 | 4.6667 |  |  |  |  | 0 | 0 | 0.46667 | 1.3333 | 0.4 | 0 | 0.46667 | 0 | 2
43 | TO CATEGORIZE YET | TO CATEGORIZE YET | Loss/Gain Analytics & Tank Illustration - The client asked for tank-wise visibility in addition to product-wise views. - The discussion clarified that this requirement is already fulfilled through the Stock Levels report. - The gap identified was client awareness and product discoverability, not missing functionality. - Tank illustration is also required. |  | PGL | [8 empty] | 0 | 1 | 2 |  | 5 |  | 2 | 10 | 5 | 11 | 9.3333 | 4.6667 |  |  |  |  | 0 | 0 | 0.46667 | 1.3333 | 0.4 | 0 | 0.46667 | 0 | 2
44 | TO CATEGORIZE YET | TO CATEGORIZE YET | Sales Targets & Organizational Hierarchy - Sales targets are maintained at multiple levels, including yearly, quarterly, monthly, and weekly. - The client does not use daily targets as a primary planning level. - Weekly contribution to yearly targets is important. - Targets are established globally for fuel and are often maintained in Excel at area and station level. - The client wants an Excel upload feature so sales targets can be populated in bulk. - A sample Excel file is to be shared by the client after checking with the sales team. - The client also wants targets and sites linked to territory managers and other organizational roles. - The current page can partially support target assignment but does not fully reflect the organizational hierarchy such as region-wise or territory-manager-wise structures. - Further alignment with the sales team is needed to define how targets should be modeled in Fintech Fuel and to set expectations. |  | PGL | [8 empty] | 3 | 15 | 5 |  | 5 |  | 2 | 30 | 15 | 33 | 28 | 14 |  |  |  |  | 0 | 0 | 1.4 | 7.0769 | 2.1231 | 0 | 1.4 | 0 | 2
45 | TO CATEGORIZE YET | TO CATEGORIZE YET | Date Range & Time Handling - The client objected to 8 AM to 8 PM reconciliation windows from a UX perspective. - Date filtering should behave as full-day selection: - Single day selection should mean 00:00 to 23:59. - Multi-day selection should mean from the start of the first day to the end of the last day. - Site-level time window configuration exists, but implementation would require client approval. - A possible tolerance buffer of 5% to 10% was discussed to account for timing-related variances such as transactions crossing midnight. - The team agreed that the transaction end time is the correct timestamp to use for calculations. |  | PGL | [8 empty] | 0 | 3 | 3 |  | 5 |  | 2 | 13 | 6.5 | 14.3 | 12.1333 | 6.0667 |  |  |  |  | 0 | 0 | 0.60667 | 2.1949 | 0.65846 | 0 | 0.60667 | 0 | 2
46 | TO CATEGORIZE YET | TO CATEGORIZE YET | Price Monitoring & Control - The client wants head-office price communication to each dispenser. - This feature has been built for ALSONs and is in progress for the DOVER Fusion Controller. - If a site changes the selling price from the approved head-office price, Fintech Fuel should raise an alert. - The client gave an example where a site selling at a higher price than the approved price must be flagged. - The client expects exact price matching and does not want a tolerance-based comparison here. - If no transaction has occurred, the current logic may not receive PPU data; this limitation needs a workaround. - Price comparison and price history should be visible in the application. - Price change alerting should not depend only on transactions because the damage may already be done by then. - The team needs to confirm whether the FC controller communicates price changes directly. |  | PGL | [8 empty] | 5 | 15 | 8 |  | 5 |  | 2 | 35 | 17.5 | 38.5 | 32.6667 | 16.3333 |  |  |  |  | 0 | 0 | 1.6333 | 8.5128 | 2.5538 | 0 | 1.6333 | 0 | 2
47 | TO CATEGORIZE YET | TO CATEGORIZE YET | Role-Based Access - Ground staff should have read-only access. - Head-office staff should have edit and configuration control. - Manual entry and sensitive corrections should follow user-role restrictions. - The client requested user management roles and an approval system through hierarchy for manual data entry and related control workflows. |  | PGL | [8 empty] | 0 | 6 | 4 |  | 5 |  | 2 | 17 | 8.5 | 18.7 | 15.8667 | 7.9333 |  |  |  |  | 0 | 0 | 0.79333 | 3.3436 | 1.0031 | 0 | 0.79333 | 0 | 2
48 | TO CATEGORIZE YET | TO CATEGORIZE YET | Leak & Theft Alerts |  | PGL | [12 empty] | 5 |  | 2 | 7 | 3.5 | 7.7 | 6.5333 | 3.2667 |  |  |  |  | 0 | 0 | 0.32667 | 0.47179 | 0.14154 | 0 | 0.32667 | 0 | 2
49 | TO CATEGORIZE YET | TO CATEGORIZE YET | Sample test for litre quantity from dispenser and then pouring back to tank or detained (discarded) |  | To compliance with OGRA | [8 empty] | 0 | 3 | 1 |  | 5 |  | 2 | 11 | 5.5 | 12.1 | 10.2667 | 5.1333 |  |  |  |  | 0 | 0 | 0.51333 | 1.6205 | 0.48615 | 0 | 0.51333 | 0 | 2
50 | TO CATEGORIZE YET | TO CATEGORIZE YET | Get delivery data from OMC companies from their ERP via API and match with how much exact delivery is delivered to Tank at Site to make sure if the Dealer has decanted some delivery to else where or not. |  | To compliance with OGRA | [8 empty] | 1 | 3 | 1 |  | 5 |  | 2 | 12 | 6 | 13.2 | 11.2 | 5.6 |  |  |  |  | 0 | 0 | 0.56 | 1.9077 | 0.57231 | 0 | 0.56 | 0 | 2
51 | TO CATEGORIZE YET | TO CATEGORIZE YET | Take manual dip reading with DateTime stamp for opening and closing stocks. And make separate reconciliation report wchih will take manual dip readings entered by user. |  | To compliance with OGRA | [8 empty] | 1 | 5 | 1 |  | 5 |  | 2 | 14 | 7 | 15.4 | 13.0667 | 6.5333 |  |  |  |  | 0 | 0 | 0.65333 | 2.4821 | 0.74462 | 0 | 0.65333 | 0 | 2
52 | TO CATEGORIZE YET | TO CATEGORIZE YET | Configurable Site Reconn. Time (done) |  | PGL | [8 empty] | 0 | 10 | 2 |  |  |  |  | 12 | 6 | 13.2 | 11.2 | 5.6 |  |  |  |  | 0 | 0 | 0.56 | 3.8769 | 1.1631 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0

## OmniChat RMI
OmniChat Roadmap Items | [6 empty] | BHW | TK | AA | TS |  | RnD Most likely | [9 empty] | TK Budgeted
Sr # | Category | Components | Road Map Items | Jira ID | Originator | Value | Priority | Priority | Priority | Priority | Plan Status | Prc Design | R/URS | R/DDS | Dev | SQA | Prc Test | Doc | Reg SQA | Release | Man Days | Optimistic (50%) | Pessimistic (10%) | Est Formula | TK's TARGET | Start Date | Dev End | SQA HO | Prod Date | Prc Design | R/URS (5%) | R/DDS (10%) | Dev (50%) | SQA (15%) | Prc Test | Doc (10%) | Reg SQA (10%) | Release
1 | Input | [19 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Enrichment | Omni Agent Connector | Connects to OmniAgent via API for OC related queries | https://octopusdtlsupport.atlassian.net/browse/O2-1461 | RnD | [7 empty] | 0 | 4 | 28 | 5 | 5 | 3 | 5 | 4 | 54 | 27 | 59.4 | 50.4 | 25.2 | 2026-02-23 | 2026-04-17 | 2026-04-20 | 2026-05-01 | 0 | 1.26 | 2.52 | 5.6769 | 1.7031 | 5 | 2.52 | 2.52 | 4
3 |  | Dashboard | Dashboard level Filtering | https://octopusdtlsupport.atlassian.net/browse/MN-30 | Impl Team | [7 empty] | 0 | 0 | 10 | 5 | 5 | 3 | 5 | 2 | 30 | 15 | 33 | 28 | 14 | 2026-04-20 | 2026-04-23 | 2026-04-24 | 2026-05-08 | 0 | 0.7 | 1.4 | 1.6154 | 0.48462 | 5 | 1.4 | 1.4 | 2
4 |  |  | Panel level Filtering | https://octopusdtlsupport.atlassian.net/browse/MN-75 | Impl Team | [7 empty] | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 2 | 32 | 16 | 35.2 | 29.8667 | 14.9333 | 2026-04-21 | 2026-05-01 | 2026-05-04 | 2026-05-12 | 0 | 0.74667 | 1.4933 | 2.0821 | 0.62462 | 5 | 1.4933 | 1.4933 | 2
5 |  |  | Panel Resizing | https://octopusdtlsupport.atlassian.net/browse/MN-76 | Impl Team | [7 empty] | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 2 | 27 | 13.5 | 29.7 | 25.2 | 12.6 | 2026-04-29 | 2026-05-06 | 2026-05-07 | 2026-05-22 | 0 | 0.63 | 1.26 | 0.91538 | 0.27462 | 5 | 1.26 | 1.26 | 2
6 |  |  | Auto Dashboard sharing | https://octopusdtlsupport.atlassian.net/browse/MN-77 | Impl Team | [7 empty] | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 2 | 32 | 16 | 35.2 | 29.8667 | 14.9333 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-22 | 0 | 0.74667 | 1.4933 | 2.0821 | 0.62462 | 5 | 1.4933 | 1.4933 | 2
|  |  | Text Overlap in Graphs (x-axis) | https://octopusdtlsupport.atlassian.net/browse/MN-153 | [16 empty] | 0 | 0 | 0 | 15 | 7 | 2026-04-16 | 2026-04-17 | 2026-04-20 | 2026-04-22 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0
7 |  | DataSet | Auto Dataset Selection | https://octopusdtlsupport.atlassian.net/browse/MN-29 | Impl Team | [9 empty] | 13 | 5 | 3 | 3 | 3 | 2 | 29 | 14.5 | 31.9 | 27.0667 | 13.5333 | 2026-05-01 | 2026-05-14 | 2026-05-15 | 2026-05-22 | 0 | 0 | 0 | 4.4821 | 1.3446 | 3 | 1.3533 | 1.3533 | 2
8 |  |  | Advanced Multiple Dataset | https://octopusdtlsupport.atlassian.net/browse/MN-32 | Impl Team | [9 empty] | 51 | 10 | 5 | 5 | 2 | 3 | 76 | 38 | 83.6 | 70.9333 | 35.4667 | 2026-05-19 | 2026-06-29 | 2026-06-30 | 2026-07-07 | 0 | 0 | 0 | 15.6718 | 4.7015 | 5 | 3.5467 | 3.5467 | 3
9 |  | Sharing | Group Chat | https://octopusdtlsupport.atlassian.net/browse/MN-31 | Impl Team | [6 empty] | 0 | 0 | 3 | 50 | 10 | 5 | 5 | 10 | 3 | 86 | 43 | 94.6 | 80.2667 | 40.1333 | 2026-07-01 | 2026-08-13 | 2026-08-17 | 2026-08-26 | 0 | 2.0067 | 4.0133 | 13.9128 | 4.1738 | 5 | 4.0133 | 4.0133 | 3
10 |  | Communication Channels | Extend quering to enterprise communication channels |  | Impl Team | [15 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Output | [19 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Administration | URM | Password Reset | https://octopusdtlsupport.atlassian.net/browse/MN-53 | RnD | [6 empty] | 0 | 0 | 0 | 2 | 3 | 1 | 2 | 2 | 1 | 11 | 5.5 | 12.1 | 10.2667 | 5.1333 |  |  |  | 2026-04-20 | 0 | 0.25667 | 0.51333 | 1.0282 | 0.30846 | 1 | 0.51333 | 0.51333 | 1
13 | Documentation | Documentation | User Manual |  | RnD | [15 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Support Tickets | Issue Fixing | Known Issues fixing (reported during handover) | https://octopusdtlsupport.atlassian.net/browse/MN-78 | Impl Team | [6 empty] | 0 | 0 | 0 | 30 | 4 | 0 | 0 | 0 | 2 | 36 | 18 | 39.6 | 33.6 | 16.8 | 2026-04-20 | 2026-04-30 | 2026-05-01 | 2026-05-08 | 0 | 0.84 | 1.68 | 6.8615 | 2.0585 | 0 | 1.68 | 1.68 | 2 | First regression on OmniChat
[21 empty] | 0 | 0 | 0 | 0 | 0

## Sheet4 (hidden)
Estimations
EPR | Planned vs Actual
Efficiency
Schedule variance in days
Later | Technical Debt

## Sheet1 (hidden)
Digital Log - Absolute range | DEV | 30 |  |  | 3 | Enrichment
Digital Log - Absolute range | MAN | 5 |  |  |  | Enrichment | Digital Log - Absolute range | 35 | Enrichment
Digital Log - Attachment pic with each Checklist (, audio, video, pdf, etc) | DEV | 15 |  |  | 3 | Input | Digital Log - Attachment pic with each Checklist (, audio, video, pdf, etc) | 20 | Input
Digital Log - Attachment pic with each Checklist (, audio, video, pdf, etc) | MAN | 5 |  |  |  | Input | Digital Log - Attachments at remarks from approver1, approver2 | 23 | Input
Digital Log - Attachments at remarks from approver1, approver2 | DEV | 18 |  |  | 3 | Input | Digital Log - Bulk creation of parameters through importing CSV file(s) (User can develop a template of parameters and then can use for multiple areas/assets) | 29 | Input
Digital Log - Attachments at remarks from approver1, approver2 | MAN | 5 |  |  |  | Input | Digital Log - Calculated tags | 50 | Enrichment
Digital Log - Bulk creation of parameters through importing CSV file(s) (User can develop a template of parameters and then can use for multiple areas/assets) | DEV | 24 |  |  | 3 | Input | Digital Log - Delete option to admin (to delete unclaimed checklists) Data Collector → Inbox |  | Administration
Digital Log - Bulk creation of parameters through importing CSV file(s) (User can develop a template of parameters and then can use for multiple areas/assets) | MAN | 5 |  |  |  | Input | Digital Log - DL Analytics (Dependent upon client need & Data) |  | Enrichment
Digital Log - Calculated tags | DEV | 45 |  |  | 3 | Enrichment | Digital Log - DL Default Reports |  | Enrichment
Digital Log - Calculated tags | MAN | 5 |  |  |  | Enrichment | Digital Log - DL Trial on WebSite |  | Input
Digital Log - Delete option to admin (to delete unclaimed checklists) Data Collector → Inbox | DEV | 6 |  |  | 3 | Enrichment | Digital Log - Domain Migration to Brand Octopus Digital |  | Administration
Digital Log - Delete option to admin (to delete unclaimed checklists) Data Collector → Inbox | MAN | 5 |  |  |  | Enrichment
Digital Log - DL Analytics (Dependent upon client need & Data) | DEV | 60 |  |  | 3 | Administration
Digital Log - DL Analytics (Dependent upon client need & Data) | MAN | 5 |  |  |  | Administration
Digital Log - DL Default Reports | DEV | 45 |  |  | 3 | Enrichment
Digital Log - DL Default Reports | SQA |  |  |  |  | Enrichment
Digital Log - DL Default Reports | MAN | 5 |  |  |  | Enrichment
Digital Log - DL Default Reports - Research |  | 3 | 2026-01-09 | 2026-01-13 | 1 | Enrichment
Digital Log - DL Trial on WebSite | DEV | 75 |  |  | 3 | Enrichment
Digital Log - DL Trial on WebSite | MAN | 5 |  |  |  | Enrichment
Digital Log - Domain Migration to Brand Octopus Digital | DEV | 12 | 2026-02-09 | 2026-02-12 | 3 | Enrichment
Digital Log - Domain Migration to Brand Octopus Digital | SQA | 4 | 2026-02-13 | 2026-02-19 | 1 | Enrichment
Digital Log - Domain Migration to Brand Octopus Digital | MAN | 5 | 2026-02-13 | 2026-02-19 |  | Enrichment
Digital Log - Email text formatting | DEV | 15 |  |  | 3 | Enrichment
Digital Log - Email text formatting | MAN | 5 |  |  |  | Enrichment

## Digital Log RMI
Digital Log Roadmap Items | [6 empty] | BHW | TK | AA | TS |  | RnD Most likely | [9 empty] | TK Budgeted
Sr # | Category | Components | Road Map Items | JIRA ID | Originator | Value | Priority | Priority | Priority | Priority | Plan Status | Prc Design | R/URS | R/DDS | Dev | SQA | Prc Test | Doc | Reg SQA | Release | Man Days | Optimistic (50%) | Pessimistic (10%) | Est Formula | TK's TARGET | Start Date | Dev End | SQA HO | Prod Date | Prc Design | R/URS (5%) | R/DDS (10%) | Dev (50%) | SQA (15%) | Prc Test | Doc (10%) | Reg SQA (10%) | Release
1 | Input | Data Collector | Journals for Web |  | Competitive | [7 empty] | 1 | 2 | 23 | 2 |  | 3 | 3 | 1 | 35 | 17.5 | 43.75 | 33.5417 | 16.7708 |  |  |  |  | 0 | 0.83854 | 1.6771 | 7.6162 | 2.2849 | 0 | 1.6771 | 1.6771 | 1
2 |  |  | Journals for Mobile Android |  | Competitive | [7 empty] | 1 | 2 | 23 | 2 |  | 3 | 3 | 1 | 35 | 17.5 | 43.75 | 33.5417 | 16.7708 |  |  |  |  | 0 | 0.83854 | 1.6771 | 7.6162 | 2.2849 | 0 | 1.6771 | 1.6771 | 1
3 |  |  | Mobile App iOS |  | Competitive | [7 empty] | 1 | 3 | 10 | 10 |  | 5 |  | 5 | 34 | 17 | 42.5 | 32.5833 | 16.2917 |  |  |  |  | 0 | 0.81458 | 1.6292 | 5.5529 | 1.6659 | 0 | 1.6292 | 0 | 5
4 |  |  | Journals for Mobile iOS |  | Competitive | [7 empty] | 1 | 1 | 3 | 2 |  | 1 | 3 | 1 | 12 | 6 | 15 | 11.5 | 5.75 |  |  |  |  | 0 | 0.2875 | 0.575 | 2.1058 | 0.63173 | 0 | 0.575 | 0.575 | 1
5 |  |  | User Remarks Traceability |  | Colgate | [7 empty] | 1 | 2 | 15 | 3 |  | 2 | 3 | 1 | 27 | 13.5 | 33.75 | 25.875 | 12.9375 |  |  |  |  | 0 | 0.64688 | 1.2938 | 5.6995 | 1.7099 | 0 | 1.2938 | 1.2938 | 1
6 |  |  | Calculated tags |  | Client Feedback - Demo | [7 empty] | 2 | 3 | 38 | 5 |  | 3 |  |  | 51 | 25.5 | 63.75 | 48.875 | 24.4375 |  |  |  |  | 0 | 1.2219 | 2.4438 | 14.0986 | 4.2296 | 0 | 2.4438 | 0 | 0
7 |  |  | Attachments at remarks from approver1, approver2 |  | Ashghal | [9 empty] | 15 | 3 |  | 2 |  |  | 20 | 10 | 25 | 19.1667 | 9.5833 |  |  |  |  | 0 | 0 | 0 | 6.6346 | 1.9904 | 0 | 0.95833 | 0 | 0
8 |  |  | Delete option to admin (to delete unclaimed checklists) Data Collector -> Inbox |  | EVTL | [7 empty] | 1 | 1 | 8 | 2 |  | 1 |  |  | 13 | 6.5 | 16.25 | 12.4583 | 6.2292 |  |  |  |  | 0 | 0.31146 | 0.62292 | 3.5938 | 1.0781 | 0 | 0.62292 | 0 | 0
9 |  |  | Attachment pic with each Checklist (, audio, video, pdf, etc) |  | Client Feedback - Demo | [9 empty] | 13 | 3 |  | 1 |  |  | 17 | 8.5 | 21.25 | 16.2917 | 8.1458 |  |  |  |  | 0 | 0 | 0 | 5.6394 | 1.6918 | 0 | 0.81458 | 0 | 0
10 |  |  | Validation of Values to be within defined threshold |  | RnD | [9 empty] | 10 | 3 |  | 2 |  |  | 15 | 7.5 | 18.75 | 14.375 | 7.1875 |  |  |  |  | 0 | 0 | 0 | 4.976 | 1.4928 | 0 | 0.71875 | 0 | 0
11 |  |  | Return & Re-Approval param values and comments traceability | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-221 | Colgate | [7 empty] | 1 | 1 | 15 | 7 |  | 1 |  | 1 | 26 | 13 | 32.5 | 24.9167 | 12.4583 | 2026-04-01 | 2026-04-08 | 2026-04-09 | 2026-04-27 | 0 | 0.62292 | 1.2458 | 6.4183 | 1.9255 | 0 | 1.2458 | 0 | 1
12 |  |  | Digital Signatures (Like DocuSign idea) | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-223 | Competitive | [7 empty] | 1 | 2 | 13 | 3 |  | 2 |  | 1 | 22 | 11 | 27.5 | 21.0833 | 10.5417 | 2026-04-09 | 2026-04-13 | 2026-04-14 | 2026-04-27 | 0 | 0.52708 | 1.0542 | 5.3125 | 1.5937 | 0 | 1.0542 | 0 | 1
13 |  | Hierarchy Builder | Import & export of assets hierarchy |  | Client Feedback - Demo | [7 empty] | 2 | 3 | 25 | 5 |  | 3 |  |  | 38 | 19 | 47.5 | 36.4167 | 18.2083 |  |  |  |  | 0 | 0.91042 | 1.8208 | 10.5048 | 3.1514 | 0 | 1.8208 | 0 | 0
14 |  | Checklist Builder | Import & export of checklists |  | Client Feedback - Demo | [7 empty] | 2 | 3 | 25 | 5 |  | 3 |  |  | 38 | 19 | 47.5 | 36.4167 | 18.2083 |  |  |  |  | 0 | 0.91042 | 1.8208 | 10.5048 | 3.1514 | 0 | 1.8208 | 0 | 0
15 |  | Parameter Builder | Bulk creation of parameters through importing CSV file(s) (User can develop a template of parameters and then can use for multiple areas/assets) |  | Client Feedback - Demo | [7 empty] | 2 | 3 | 20 | 5 |  | 3 |  |  | 33 | 16.5 | 41.25 | 31.625 | 15.8125 |  |  |  |  | 0 | 0.79063 | 1.5813 | 9.1226 | 2.7368 | 0 | 1.5813 | 0 | 0
16 | Enrichment | Audits | Automated Record of actions taken |  | Competitive | [7 empty] | 1 | 2 | 33 | 2 |  | 3 | 3 | 1 | 45 | 22.5 | 56.25 | 43.125 | 21.5625 |  |  |  |  | 0 | 1.0781 | 2.1562 | 10.012 | 3.0036 | 0 | 2.1562 | 2.1562 | 1
17 |  | WorkFlows | Automated Triggered O&M Actions |  | Competitive | [7 empty] | 1 | 2 | 17 | 2 |  | 3 | 3 | 1 | 29 | 14.5 | 36.25 | 27.7917 | 13.8958 |  |  |  |  | 0 | 0.69479 | 1.3896 | 6.1787 | 1.8536 | 0 | 1.3896 | 1.3896 | 1
18 |  | Holiday | Holiday wrt Start and End Time |  | Colgate | [7 empty] | 1 | 1 | 11 | 1 |  | 2 | 3 | 1 | 20 | 10 | 25 | 19.1667 | 9.5833 |  |  |  |  | 0 | 0.47917 | 0.95833 | 4.0224 | 1.2067 | 0 | 0.95833 | 0.95833 | 1
19 |  | Scheduling | Triggering of checklist instance on some event (we have scheduled checklist feature & it is triggered on given frequency) |  | Client Feedback - Demo | [7 empty] | 1 | 2 | 25 | 3 |  | 2 |  |  | 33 | 16.5 | 41.25 | 31.625 | 15.8125 |  |  |  |  | 0 | 0.79063 | 1.5813 | 9.1226 | 2.7368 | 0 | 1.5813 | 0 | 0
20 |  |  | User Specified Time based Checklist Scheduling | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-222 | Colgate | [7 empty] | 1 | 2 | 25 | 3 |  | 2 |  | 1 | 34 | 17 | 42.5 | 32.5833 | 16.2917 | 2026-04-15 | 2026-04-20 | 2026-04-21 | 2026-04-27 | 0 | 0.81458 | 1.6292 | 8.6298 | 2.5889 | 0 | 1.6292 | 0 | 1
21 |  | Trial | DL Trial on WebSite |  | Competitive - Plant Log | [7 empty] | 2 | 3 | 50 | 5 |  | 3 |  |  | 63 | 31.5 | 78.75 | 60.375 | 30.1875 |  |  |  |  | 0 | 1.5094 | 3.0188 | 17.4159 | 5.2248 | 0 | 3.0188 | 0 | 0
22 | Output | LogChat | LogChat - Data Analysis |  | RnD | [7 empty] | 3 | 5 | 17 | 5 |  | 3 |  |  | 33 | 16.5 | 41.25 | 31.625 | 15.8125 |  |  |  |  | 0 | 0.79063 | 1.5813 | 9.1226 | 2.7368 | 0 | 1.5813 | 0 | 0
23 |  |  | LogChat - User Help, Journals | https://octopusdtlsupport.atlassian.net/browse/DIGITALLOG-259 | RnD | [7 empty] | 1 | 2 | 15 | 3 |  | 1 |  | 1 | 23 | 11.5 | 28.75 | 22.0417 | 11.0208 | 2026-04-09 | 2026-04-16 | 2026-04-17 | 2026-04-27 | 0 | 0.55104 | 1.1021 | 5.5889 | 1.6767 | 0 | 1.1021 | 0 | 1
24 |  | Dashboards/Reports | Request for Digital Log Usage Dashboard / Report 1- Total number of active users over time 2- Checklist creation trends (daily/weekly/monthly) 3- Number of completed vs. pending checklists 4- User login frequency |  | RnD | [7 empty] | 1 | 2 | 38 | 5 |  | 5 |  |  | 51 | 25.5 | 63.75 | 48.875 | 24.4375 |  |  |  |  | 0 | 1.2219 | 2.4438 | 14.0986 | 4.2296 | 0 | 2.4438 | 0 | 0
25 |  |  | DL Analytics (Dependent upon client need & Data) |  | Client Feedback - Demo | [7 empty] | 1 | 2 | 25 | 5 |  | 3 |  |  | 36 | 18 | 45 | 34.5 | 17.25 |  |  |  |  | 0 | 0.8625 | 1.725 | 9.9519 | 2.9856 | 0 | 1.725 | 0 | 0
26 |  |  | Reports list is not available/viewable in tablet portrait mode |  | RnD | [9 empty] | 5 | 1 |  |  |  |  | 6 | 3 | 7.5 | 5.75 | 2.875 |  |  |  |  | 0 | 0 | 0 | 2.2115 | 0.66346 | 0 | 0 | 0 | 0
27 |  |  | DL Default Reports |  | Competitive - Plant Log | [7 empty] | 1 | 2 | 25 | 6 |  | 5 |  |  | 39 | 19.5 | 48.75 | 37.375 | 18.6875 |  |  |  |  | 0 | 0.93438 | 1.8688 | 10.7812 | 3.2344 | 0 | 1.8688 | 0 | 0
28 |  | Alerts | Notifications (desktop) at due, overdue checklist(s) |  | RnD | [9 empty] | 50 | 5 |  | 3 |  |  | 58 | 29 | 72.5 | 55.5833 | 27.7917 |  |  |  |  | 0 | 0 | 0 | 19.2404 | 5.7721 | 0 | 2.7792 | 0 | 0
29 |  |  | Email text formatting |  | RnD | [9 empty] | 13 | 2 |  |  |  |  | 15 | 7.5 | 18.75 | 14.375 | 7.1875 |  |  |  |  | 0 | 0 | 0 | 5.5288 | 1.6587 | 0 | 0 | 0 | 0
30 | Administration | User Management | Enhance User Access Rights at granular level of Create, Read, Update, Delete like OmniConnect |  | RnD | [7 empty] | 2 | 3 | 50 | 6 |  | 10 |  |  | 71 | 35.5 | 88.75 | 68.0417 | 34.0208 |  |  |  |  | 0 | 1.701 | 3.4021 | 19.6274 | 5.8882 | 0 | 3.4021 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0

## Support
| Most Likely | Optimistic | Pessimistic | Calculated Estimates | TK Approved
OmniConnect | 5.2083 | 2.6042 | 5.4688 | 4.8177 | 2.4089
Digital Log | 1.25 | 0.625 | 1.3125 | 1.1562 | 0.57812
Fintech Fuel | 4.25 | 2.125 | 4.4625 | 3.9312 | 1.9656
OmniChat | 3.5694 | 1.7847 | 3.7479 | 3.3017 | 1.6509
Subscription Management | 3.5694 | 1.7847 | 3.7479 | 3.3017 | 1.6509
April - June
[6 empty] | 65 | total days | 21.6667 | days per month
[6 empty] | 671.6667 | Capacity | 31 | RnD Team
[6 empty] | 38 | Leaves
|  |  |  | 30 | heads | 633.6667 | Availability
[6 empty] | 35.2037 | per resource availability
[6 empty] | 316.8333 | 3 support days in 3 months |  |  | 316.8333 | 158.4167 | 348.5167 | 295.7111 | 147.8556
[6 empty] | 105.6111 | per month support

## Technical Support Raw Data
ACTUAL HOURS | Jan | Feb | March | Avg
OmniConnect | 48 | 48 | 29 | 41.6667
Digital Log |  | 8 | 12 | 10
Fintech Fuel |  |  | 34 | 34
|  |  |  | 28.5556 | hours
ACTUAL DAYS | Jan | Feb | March | Avg
OmniConnect | 6 | 6 | 3.625 | 5.2083
Digital Log |  | 1 | 1.5 | 1.25
Fintech Fuel |  |  | 4.25 | 4.25
|  |  |  | 3.5694 | days

## Settings
FORMULA EXERCISE
Stage | Optimistics | Most likey | % | Pessimistics | Formula | 0 | Sheet-wise totals
URS | 4 | 8 | 8.889% | 8.8
DDS | 7.5 | 15 | 16.67% | 16.5 |  | 0 = dont show sheet wise total
DEV | 22.5 | 45 | 50% | 49.5 |  | 1 = show sheet wise total (will disturb summary tab)
SQA | 7.5 | 15 | 16.67% | 16.5
Doc | 1 | 2 | 2.222% | 2.2
Buffer | 2.5 | 5 | 5.556% | 5.5
| 45 | 90 |  | 99 | 84
Sheet names
OmniConnect RMI
Fintech Fuel RMI
OmniChat RMI
Digital Log RMI

## Misc (hidden)
Misc Road map Items
Sr # | Category | Components | Road Map Items | Originator | Value | Priority | Plan Status | Man Days
1 | Azure Cost | Azure monthly cost management | Dashboard Cost Distribution |  |  | 1 | Plan | 6
|  | Cost Optimization | Evaluate Cost optimization potential |  |  | 1 | UnPlan | 6
3 |  |  | Cost Optimization |  |  | 1 | UnPlan | 15

## Sheet3 (hidden)
Long Format |  |  | Wide Format
tagName | Timestamp | Value | Timestamp | R1 | R2 | R3 | R4
R1 | 2026-04-08 11:22 | 15 | 2026-04-08 11:24 | 15 | 16 | 17 | 18
R2 | 2026-04-09 11:22 | 16 | 2026-04-09 11:24 | 16 | 17 | 17 | 18
R3 | 2026-04-10 11:22 | 17 | 2026-04-10 11:24 | 17 | 18 | 17 | 18
R4 | 2026-04-11 11:22 | 18 | 2026-04-11 11:24 | 18 | 19 | 17 | 18
R5 | 2026-04-12 11:22 | 19 | 2026-04-12 11:24 | 19 | 20 | 17 | 18
R6 | 2026-04-13 11:22 | 20 | 2026-04-13 11:24 | 20 | 21 | 17 | 18
R7 | 2026-04-14 11:22 | 21 | 2026-04-14 11:24 | 21 | 22 | 17 | 18
R8 | 2026-04-15 11:22 | 22
R9 | 2026-04-16 11:22 | 23
R10 | 2026-04-17 11:22 | 24

## Sheet2
Scenario | Current Solution (200 Only) | Proposed Solution (200 / 206) | Interpretation Improvement
No data available (device off / no value at timestamp) | Returns 200 OK with | Returns 200 OK with | No change — this is a valid absence of data
| null | null
Unexpected device behavior (invalid/null ingestion) | Returns 200 OK with | Returns 200 OK with | No change — still treated as valid but anomalous data
| null | null
Data not yet available (eventual consistency, e.g., ADX delay) | Returns 200 OK with | Returns 206 Partial Content with | Clear distinction: indicates data is incomplete, not absent
| null | null
Client’s ability to distinguish null cause | Not possible — all nulls look identical | Improved — 206 signals incomplete/partial data | Enables better downstream handling and retries.
Risk of silent data quality issues | High — incomplete data may go unnoticed | Reduced — partial responses are explicitly flagged. | Improves observability and data integrity.
Downstream system behavior (data marts, dashboards) | May ingest incomplete data unknowingly | Can implement safeguards (retry, delay ingestion) | Prevents long-term data inconsistencies
RnD | 31
Imp Team
Management
RnD |  | x
Process Team
Process Team
Process Team
Process Team
Process Team
Process Team
Process Team
Process Team
Process Team
Process Team
RnD
RnD
RnD
RnD
RnD
RnD
RnD
Management
Management
Management
RnD
RnD
RnD
Management
Competitive
Management
RnD

## Sheet5
| Product | Total Planned | Unplanned | Onhold
| OC |  | 31 | 2
| FF | [5 empty] | first we didnt do it
| DL | [5 empty] | now we have done
Pricing
OmniChat
Technical Support
|  |  |  | Estimation | Scheduling | Scheduling | Scheduling
RMI | Product | Status | Most likely | TK Approved | Apr | May | June
a |  | Delivered |  |  | 250 | 125 | 124
b
c
d
e
f